## Slide 2: Preparing End Users for Florida PALM
FASM
July 26, 2024

## Slide 3: Preparing End Users for Florida PALM
Agency Readiness Journey
How will agency end users be prepared for Florida PALM go live?
Design
User
Acceptance Testing
Training
Go Live
April – November
2025
July – December
2025
Oct 2023 – Sept
2024
UAT Planning
June 2024 – March
2025
Training Planning
Aug 2024
– June
2025
End User Manual
FIN/PAY
Sandbox
Notes: The End User has been preparing for Florida PALM since the beginning of Design and continues through Training
End User engagement in “Design” started with the Segment Workshops – Started in October 2023
There were tasks for Payroll Business Process Models in November 2023 and Change Impacts for Segments I & II starting in January 2024

## Slide 4: Preparing End Users for Florida PALM Timeline for UAT and Training
Project-Hosted SME Testing
Project-Hosted Expanded SME plus End User Testing
Agency-Led Expanded End User Testing
2025 |  |  |  |  |  |  |  | 
4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Enterprise & Interface Testing
Project-Hosted Training
Agency-Specific Training
Online Transactions
Agency Readiness Stage Gate

## Slide 5: UAT – Online Transactions Project-Hosted SME Testing
When will it be conducted? | Mid-April to Mid-June 2025
Who is expected to participate? | Agency-identified SMEs for each Business Process Grouping
Where will these activities be conducted? | Sites within Tallahassee
What can participants expect? | Materials will be provided by the Project (shared via the Knowledge Center) for how to complete business functions with Florida PALM Project Team members will provide walk throughs of key business functions The functions they can perform are based on their role assignment for Financials / Payroll Wave go live

## Slide 6: UAT – Online Transactions Project-Hosted Expanded SME Plus End User Testing
When will it be conducted? | Mid-June to Mid-August 2025
Who is expected to participate? | Agency-identified SMEs for each Business Process Grouping Expanded group of End Users
Where will these activities be conducted? | A targeted number of in-person sessions will be at sites within Tallahassee and a location(s) in the central part of the State
What can participants expect? | Materials will be provided by the Project (shared via the Knowledge Center) for how to complete business functions with Florida PALM Project Team members will provide walk throughs of key business functions The functions they can perform are based on their role assignment for Financials / Payroll Wave go live SMEs will perform additional cycles of testing of agency business processes Collaboration will begin between Agency SMEs and the first tier End Users

## Slide 7: UAT – Online Transactions State Agency-Led Expanded End User Testing
When will it be conducted? | Mid-August to Mid-November 2025
Who is expected to participate? | All Agency End Users
Where will these activities be conducted? | At Agency-determined sites
What can participants expect? | Agency SMEs will provide support for all End User access and participation in testing Project Team members will provide support for questions and issues reported via UAT ticketing portal

## Slide 8: UAT – Online Transactions Preparing for Online Transactions Testing
Key Agency Activity | RW Tasks | Dates
UAT Planning | 536 – Create Agency-Specific User Acceptance Testing Plan 574 – Prepare Test Scripts and Materials for User Acceptance Testing 579 – Identify, Prepare, and Confirm Understanding of User Acceptance Testing Participants | 6/17 – 12/13/2024 1/6 – 3/14/2025 1/13 – 2/28/2025
Role Assignment | 573 – Complete and Submit End User Role Mapping Worksheet | 1/9 – 2/28/2025
Identity Provider Setup | 578 – Confirm Identity Provider for Florida PALM 591 – Confirm IDP Configuration for Florida PALM 592 – Agency IDP SMEs Added Identified User Acceptance Testing Participants to Agency’s Identity Provider | 3/3 – 3/28/2025 3/3 – 3/21/2025 3/3 – 3/28/2025
Process Changes | 560 – Submit Change Analysis Tool 580 – Update Agency Business Process Documentation 581 – Update Reports Inventory | 10/21 – 12/20/2024 1/13 – 3/28/2025 1/13 – 3/28/2025
Data Cleansing and Conversion | 571 – Complete Data Cleansing Based on Mock conversion 2 583 – Participate in Mock Conversion 3 | 1/6 – 1/17/2025 1/21 – 1/31/2025
User Acceptance Testing is scheduled for April – November 2025

## Slide 9: UAT – Enterprise & Interface Testing Preparing for Interface Testing
Full integration testing is scheduled for July – September 2025
Key Agency Activity | RW Tasks | Dates
Test Planning | 553 – Prepare for Interface Testing 566 – Validate Detailed Cycle 2 Interface Testing Information | 9/3 – 9/27/2024 12/2 – 12/27/2024
System Changes | 575 – Complete Cycle 2 – Technical Interface Testing 576 – Complete Internal Agency Business System Testing 577 – Remediate Agency Business Systems and Update Documentation 609 – Complete ABS Testing and Confirm Ready for Full Integration Testing | 1/6 – 4/25/2025 1/6 – 6/13/2025 1/6 – 6/27/2025 6/16 – 7/3/2025

## Slide 10: Training
When will it be conducted? | July to December 2025
Who is expected to participate? | All Agency End Users
Where will these activities be conducted? | In Person and Online (Recorded and Live)
What can participants expect? | Learning paths identified for user roles Project-Hosted learning for Florida PALM Core: Instructor-Led Online / web-based Support sessions (in-person and virtual) Agency-Led for Agency-Specific Materials provided in Knowledge Center Knowledge Checks and confirmation of learning

## Slide 11: Training Agency Role in Training
Key Agency Activity | RW Tasks | Dates
Training Planning | 549 – Submit Training Survey 568 – Creating Training Plan for Agency Managed End User Training 588 – Confirm and Prepare Participants for Train the Trainer 603 – Participate in Train the Trainer 607 – Update Training Plan | 8/12 – 9/20/2024 12/9 – 3/28/2025 2/24 – 3/2/2025 5/19 – 8/15/2025 6/2 – 6/27/2025
Training Execution | 604 – Create Agency Specific Training 601 – Register for Florida PALM Training 625 – Conduct Agency Specific Training | 5/19 – 9/26/2025 5/5 – 6/13/2025 10/6 – 12/12/2025
Project-Led Training will be held July – November 2025
Agency-Specific Training will be October – December 2025

## Slide 12: Upcoming
Save the dates:
  Design Workshops – Financials:
    Inter/IntraUnit – August 13 & 14
    Asset Accounting & Management – August 15
  Design Workshops – Payroll – August 27, 28, & 29
  Design Workshops – Financials:
    Carry/Certified Forward – September 10
    Cash Checking, Financial Statement & Budget – September 11, & 12
  Testing Town Hall – September 17
  All Segment Recap – October 1, 2, & 3

## Slide 13
Contact us
FloridaPALM@myfloridacfo.com
Project Website
www.myfloridacfo.com/floridapalm/
Knowledge Center
https//:myfloridacfofloridapalm.us.document360.io
Notes: INCLUDE IN EVERY PRESENTATION
Contact information Slide
Additional contact information can be added, however, these two must remain for every presentation