## Task Instructions
The Agency Preparedness Activity Tracker (PAT) includes a list of the implementation tasks agencies need to complete to prepare for FLIPS Go-Live.
Each of the PAT Tracker's columns and what they represent are listed below with a brief description. These tasks can be filtered in numerous ways to account for variables that better align for specific agencies.
Task ID | Represents the number of a given task. There are 12 tasks in total.
Task Name | Summarizes in a few words what a task will entail.
Date Released | Displays when an actual PAT task has been released.
Pilot vs. Nonpilot | Differentiates between Pilot and Nonpilot agencies.
Phase | Represents the number for which phase a certain task exists in.
Task Overview | Describes what will occur within a given task.
Task Status | Gauges the completion level of a task (Not Started, In Progress, or Finished).
Start Date | Displays the official start of a task.
End Date | Displays the offical end of a task.
Comments/Updates | Used for expressing additional information about a specific task.

## PAT Tasks
Task ID | Task Name | Date Released | Pilot vs. Nonpilot | Task Overview | Task Status | Start Date | End Date | Comments/Updates
1 | Identify Change Support Network Members | 2025-09-05 | Pilot | Return a list of agency personnel that will support the CSN. | Completed | 2025-09-08 | 2025-09-24
1 | Identify Change Support Network Members | 2025-09-05 | Nonpilot | Return a list of agency personnel that will support the CSN. | Completed | 2025-09-08 | 2025-09-24
2 | Review and confirm policy changes and determine procedure updates that must be implemented to support the transition to and usages of FLIPS | 2025-10-22 | Pilot | Change Champions within each agency will review draft policies and to assess for potential impacts on their workflows and procedures. Agency procedures should be revised as needed. | Completed | 2025-10-10 | 2025-10-10
2 | Review and confirm policy changes and determine procedure updates that must be implemented to support the transition to and usages of FLIPS | 2025-10-22 | Nonpilot | Change Champions within each agency will review draft policies and to assess for potential impacts on their workflows and procedures. Agency procedures should be revised as needed. | Completed | 2025-10-10 | 2025-10-10
3 | Communication of Changes via Workshop | 2026-04-27 | All Agencies | Attend the workshop to gain knowledge and understanding of FLIPS, (e.g., Functionality, Access, Processes) | Completed | 2026-04-27 | 2026-04-27
4 | Request Access | 2026-04-28 | All Agencies | Complete Access Control form to request end user access to FLIPS. | Completed | 2026-04-27 | 2026-05-01
5 | Confirm Access | 2026-05-01 | All Agencies | Confirm agency has access and is prepared for URL connection with FLIPS. | In Progress | 2026-05-04 | 2026-05-08
6 | Review Training Materials | 2026-05-01 | All Agencies | Share training materials with Contract Managers and Purchasing Agents. | In Progress | 2026-05-04 | 2026-05-08
7 | Review Go-Live Toolkit | 2026-05-01 | All Agencies | Acknowledge receipt of the Go Live Toolkit (e.g., schedule, escalation, path of issues, job aids). | In Progress | 2026-05-04 | 2026-05-08
8 | Provide Agency Contacts for Payee Invitations | 2026-05-01 | All Agencies | Agencies to provide a list of POCs for Payees to contact to start the process to receive an invitation | In Progress | 2026-05-04 | 2026-05-08
9 | Participate in FLIPS Invitation Training Delivery |  | All Agencies | Actively participate in training and report progress. | Not Started | TBD | TBD
10 | Review Go-Live Toolkit |  | All Agencies | Acknowledge receipt of the Go Live Toolkit (e.g., schedule, escalation, path of issues, job aids). | Not Started | TBD | TBD
11 | Monitor/Support FLIPS Go-Live |  | All Agencies | Provide Go-Live Successes and CSN Direction and Feedback | Not Started | TBD | TBD
12 | Share Success and Challenges |  | All Agencies | Provide implementation challenges and success in an Excel format. | Not Started | TBD | TBD
13 | Retire CSN |  | All Agencies | Communicate to agency contacts at the end of implementation and the transition to operational support. | Not Started | TBD | TBD