## High-level Schedule
User Acceptance Testing Schedule by Week
Week | Planned Dates | Business Process | Florida PALM End User Role
Week 1 | 03/22/2021 – 03/26/2021 | 70.1.1 Maintain Bank Accounts 70.1.2 Manage Treasury Correspondence 70.4 Process Bank Cash Transfers 80.2.6 Manage Revolving Funds | Agency CRA Processor Agency Requestor Bank Account Request Processor Cash Transfer Approver Cash Transfer Processor DFS Bank Account Maintainer DFS Correspondence Processor DFS Payment Cancellation Processor DFS Transfer Approver DFS CM Accounting Approver
Week 2 | 03/29/2021 – 04/02/2021 | 10.1.3 Add or Modify Fund Values 10.2.1 Create and Approve Journals 10.2.2 Edit Check (A) 80.1.2 Investing Balance Checking | GL Journal Approver GL Journal Processor GL Reporter DFS COA Maintainer DFS GL Journal Approver DFS Override Processor
Week 3 | 04/05/2021 – 04/09/2021 | Contingency Week
Week 4 | 04/12/2021 – 04/16/2021 | 70.7.2 Distribute Interest 80.2.1 Monitor Trust Fund Cash Balance 60.2.4 Manage Electronic Receipts Data 60.2.5 Process FLAIR Deposits 60.2.6 Treasury Receipts, Adjustments, and Returned Items 70.2 Manage and Reconcile Bank Statements | Agency CM Reporter Agency Deposit Reporter Fund Cash Processor DOR Agency Exception Processor DFS Bank Reconciliation Processor DFS CM Accounting Approver DFS Deposit Approver DFS Deposit Processor DFS GL Journal Processor
Week 5 | 04/19/2021 – 04/23/2021 | 70.6 Create and Maintain Deals Additional UAT testing using DFS/agency-specific examples or executing scenarios that were not covered during previous weeks (includes reporting) | DFS Investment Accounting Processor DFS Investment Reporter DFS CM Accounting Approver End user roles needed to execute DFS/agency-specific additional scenarios
Week 6 | 04/26/2021 – 04/30/2021 | Contingency Week

## Detailed Schedule
User Acceptance Testing Schedule by Day
Week 1
2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26
N/A | DBPR DEO DFS DOH DOR DACS DEP |  | DBPR DEO DFS DOH DOR DACS DEP | DFS
N/A | 10:00 am - 11:00 am '***UAT Kick-Off Meeting*** |  | 9:00 am - 11:30 am Bank Account Request Processor - Submit Electronic Payment Services (EPS) form - Submit Banking Services Form Agency Requestor - Submit the Treasury Correspondence Form Agency CRA Processor - Submit the CRA Payment Cancellation Request Form | 9:00 am - 11:30 am DFS Bank Account Maintainer - Approve Electronic Payment Services (EPS) form - Approve Banking Services Form - Deny the EPS Request Form - Deny Banking Services Request Form - Return the Banking Services Request Form for More Information - Return the EPS Request Form for More Information DFS Correspondence Processor - Review and Approve Treasury Correspondence Form - Review and Deny the Treasury Correspondence Form - Review and Return the Treasury Correspondence Form On Hold 2:00 pm - 4:30 pm DFS Payment Cancellation Processor - Review and Approve CRA Payment Cancellation Request Form - Review and Deny the CRA Payment Cancellation Request Form - Send back the CRA Payment Cancellation Request Form
Week 2
2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02
DBPR DEO DFS DOH DOR DACS DEP | DBPR DEO DFS DOH DOR DACS DEP | DBPR DEO DFS DOH DOR DACS DEP | DBPR DEO DFS DOH DOR DACS DEP | DBPR DEO DFS DOH DOR DACS DEP
9:00 am - 11:30 am Agency CRA Processor - Edit Denied CRA Payment Cancellation Request Form - Re-submit the CRA Payment Cancellation Request Form Bank Account Request Processor - Re-submit the EPS Request Form - Re-submit Banking Services Form with Added Information Agency Requestor - Re-submit the Treasury Correspondence Request Form 10:00 am - 11:00 am Cash Transfer Processor - Request Cash Transfers between Bank Accounts 2:00 pm - 4:30 pm DFS CM Accounting Approver - Update/finalize transactions in provisional status - Update/finalize transactions which are in error status - Review and Modify Accounting Entries - View and Approve Accounting Entries - Review Accounting Events - Review Accounting Summary DFS Transfer Approver - View and Approve Accounting Entries - Manually Approve Settlements - Review Accounting Events - Review Accounting Summary | 9:00 am - 11:30 am Cash Transfer Approver - Select and Approve Cash Transfers between Bank Accounts Agency CM Reporter - Generate Clearing and Revolving Accounts Report Agency CRA Processor - Generate CRA Revolving Fund Replenishment Report 10:00 am - 11:00 am DFS Bank Account Maintainer - Generate Bank Account Listing Report DFS CM Accounting Approver - Generate Finalize Accounting Entries Report - Generate Accounting Errors Report 2:00 pm - 4:30 pm GL Journal Processor/Fund Cash Processor - Create disinvestment journals - Create Redistribution Journals - Review Disinvestment Journals | 9:00 am - 11:30 am DFS COA Maintainer - Add a new Fund values - Inactivate existing Fund values GL Reporter - Generate a Crosswalk Value Report 2:00 pm - 4:30 pm DFS GL Journal Processor - Create GL journals using Spreadsheet Upload (Import Now) - Create GL journals using Spreadsheet Upload (Write File) GL Journal Processor / Fund Cash Processor - Create GL journals using Spreadsheet Upload (Import Now) - Create GL journals using Spreadsheet Upload (Write File) | 9:00 am - 11:30 am GL Journal Processor/Fund Cash Processor - Edit Check Journals - View Journals with Errors - View Journals with Edit Errors - Review and Correct Edit Errors - Modify GL journals online - Delete GL journals online - Review Edit Errors and Delete Journal 2:00 pm - 4:30 pm GL Journal Approver - Approve Disinvestment Journals - Approve Redistribution Journals - Agency (1st Level) DFS GL Journal Approver - Approve Redistribution Journals - DFS (2nd Level) | 9:00 am - 11:30 am GL Journal Processor/Fund Cash Processor - Review and Correct Invested Balance Checking Errors - Review and Delete Invested Balance Checking Errors 2:00 pm - 4:30 pm DFS Override Processor - View Invested Balance (Budget Overview/Detail) - Review and Override Invested Balance Checking Errors - Generate Invested Balance Override Report
Week 3
2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09
Week 4
2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16
DFS | DFS | DFS | DBPR DEO DFS DOH DOR DACS DEP | DBPR DEO DFS DOH DOR DACS DEP
2:00 pm - 4:30 pm DFS Deposit Processor - Create Direct Journal Deposit and add Foreign Item Support (attachments/images) - Create multiple Payments under one Deposit - Create Direct Journal Deposit using Spreadsheet Upload | 9:00 am - 11:30 am DFS Bank Reconciliation Processor - Review reconciliation exceptions 2:00 pm - 4:30 pm DFS Deposit Approver - Review and Approve Direct Journal Deposit - Update and Approve Direct Journal Deposit - Deny action for Online Direct Journal Deposits | 9:00 am - 11:30 am DFS Bank Reconciliation Processor - Force reconcile exceptions - Review and Resolve Exceptions | 9:00 am - 11:30 am DFS CM Accounting Approver - Review and Approve Bank Reconciliation Accounting Entries 2:00 pm - 4:30 pm DOR Agency Exception Processor - Generate Unreconciled Deposits Report Agency Deposit Reporter - Generate and Verify Deposit Report - Generate ACH Notifications of Change Report | 9:00 am - 11:30 am DFS GL Journal Processor - Run Monthly Apportionment Process Agency CM Reporter - Generate Apportionment Report 2:00 pm - 4:30 pm Agency Deposit Reporter - Generate and Verify DOR Agency Deposit Report - Generate Reconciled Deposits Report - Generate Verified Deposit Summary Report - Generate Aging Verified Deposit Summary Report - Generate and Verify Debit Memo Report
Week 5
2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23
DFS/Agency-Specific Roles | DFS/Agency-Specific Roles | DFS/Agency-Specific Roles | DFS/Agency-Specific Roles | DFS/Agency-Specific Roles
9:00 am - 11:30 am DFS Investment Accounting Processor - Set up a new Portfolio - Setup a new Instrument type - Attach portfolio to an Instrument Type | 9:00 am - 11:30 am DFS Investment Accounting Processor - Review Deal Cash Flow - Review Deal Analytics - Review deals In a portfolio manager 2:00 pm - 4:30 pm DFS/Agency Roles - as needed - Opportunity to re-run scripts using additional data scenarios | 9:00 am - 11:30 am DFS Investment Accounting Processor - Override Interest Payment - Update a Transaction Rate 2:00 pm - 4:30 pm DFS/Agency Roles - as needed - Opportunity to re-run scripts using additional data scenarios | 9:00 am - 11:30 am DFS Investment Reporter - Generate Income Summary Report - Generate Investment Balances Comparison Report 2:00 pm - 4:30 pm DFS/Agency Roles - as needed - Opportunity to re-run scripts using additional data scenarios | 2:00 pm - 4:30 pm DFS/Agency Roles - as needed - Opportunity to re-run scripts using additional data scenario
Week 6
2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30
***Contingency Week***
***Contingency Week***

## Detailed Schedule (UPDATED v1) (hidden)
UAT Execution Detailed Schedule
Prep Week 3/1/2021 - 3/5/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| - Run Conversion (except DMC001) - Manually Process CMI003 (JPM,BOA,WF) - Manually Process CMI010 - Manually Process CMI015 - Manually Process GLI037 | - Run Conversion (except DMC001) - Manually Process CMI003 (JPM,BOA,WF) - Manually Process CMI010 - Manually Process CMI015 - Manually Process GLI037 | - Run Conversion (except DMC001) - Manually Process CMI003 (JPM,BOA,WF) - Manually Process CMI010 - Manually Process CMI015 - Manually Process GLI037 | - Run Conversion (except DMC001) - Manually Process CMI003 (JPM,BOA,WF) - Manually Process CMI010 - Manually Process CMI015 - Manually Process GLI037 | - Run Conversion (except DMC001) - Manually Process CMI003 (JPM,BOA,WF) - Manually Process CMI010 - Manually Process CMI015 - Manually Process GLI037
Prep Week 3/8/2021 - 3/12/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| - Manually Process CMI003 (JPM,BOA,WF) - Manually Process CMI010 - Manually Process CMI015 - Manually Process GLI037 | - Manually Process CMI003 (JPM,BOA,WF) - Manually Process CMI010 - Manually Process CMI015 - Manually Process GLI037 | - Manually Process CMI003 (JPM,BOA,WF) - Manually Process CMI010 - Manually Process CMI015 - Manually Process GLI037 | - Manually Process CMI003 (JPM,BOA,WF) - Manually Process CMI010 - Manually Process CMI015 - Manually Process GLI037 | - Manually Process CMI003 (JPM,BOA,WF) - Manually Process CMI010 - Manually Process CMI015 - Manually Process GLI037
Prep Week 3/15/2021 - 3/19/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| - Enable Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT
Week 1 03/22/2021 – 03/26/2021
| Prep Work | Kick-Off | Day 1 | Day 2 | Day 3
| - Batch Processing in UAT | - Batch Processing in UAT - Process CMI009 | - Batch Processing in UAT - Process CMI005 - Process ARI007 - Process ARI014 | - Batch Processing in UAT | - Batch Processing in UAT
| ***Prep Work*** | ***UAT Kick-Off Meeting*** | - Submit Electronic Payment Services (EPS) form - Submit Banking Services Form - Submit the Treasury Correspondence Form - Submit the CRA Payment Cancellation Request Form | ***Morning*** - Approve Electronic Payment Services (EPS) form - Approve Banking Services Form - Deny the EPS Request Form - Deny Banking Services Request Form - Return the Banking Services Request Form for More Information - Return the EPS Request Form for More Information - Review and Approve Treasury Correspondence Form - Review and Deny the Treasury Correspondence Form - Review and Return the Treasury Correspondence Form On Hold - Review and Approve CRA Payment Cancellation Request Form ***Afternoon*** - Edit Denied CRA Payment Cancellation Request Form - Re-submit the EPS Request Form - Re-submit Banking Services Form with Added Information - Re-submit the Treasury Correspondence Request Form - Re-submit the CRA Payment Cancellation Request Form | ***Morning*** - Request Cash Transfers between Bank Accounts - Update/finalize transactions in provisional status - Update/finalize transactions which are in error status - Review and Modify Accounting Entries - View and Approve Accounting Entries - Manually Approve Settlements - Review Accounting Events - Review Accounting Summary ***Afternoon*** - Select and Approve Cash Transfers between Bank Accounts - Generate Bank Account Listing Report - Generate Finalize Accounting Entries Report - Generate Accounting Errors Report - Generate Clearing and Revolving Accounts Report - Generate CRA Revolving Fund Replenishment Report
Week 2 03/29/2021 – 04/02/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT
| ***Morning*** - Add a new Fund values - Inactivate existing Fund values - Create GL journals online ***Afternoon*** - Modify GL journals online - Delete GL journals online - Edit Check Journals | ***Morning*** - Create GL journals using Spreadsheet Upload (Import Now) - Create GL journals using Spreadsheet Upload (Write File) ***Afternoon*** - Review Edit Errors and Delete Journal - Review and Correct Edit Errors - Review, Deny and/or Approve Journals | ***Morning*** - Review and Correct Invested Balance Checking Errors - Review and Override Invested Balance Checking Errors - Review and Delete Invested Balance Checking Errors | ***Morning*** - View Invested Balance (Budget Overview/Detail) - Generate Invested Balance Exceptions Report - Generate Invested Balance Override Report | ***Morning*** - View Deleted Journals Report - Generate a Crosswalk Value Report - View Journals with Errors - View Journals with Edit Errors
Week 3 04/05/2021 – 04/09/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT
Week 4 04/12/2021 – 04/16/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT
| ***Morning*** - Create disinvestment journals - Create Redistribution Journals - Create Direct Journal Deposit and add Foreign Item Support (attachments/images) ***Afternoon*** - Create multiple Payments under one Deposit - Create Direct Journal Deposit using Spreadsheet Upload | ***Morning*** - Review reconciliation exceptions - Approve disinvestment journals - Review disinvestment journals - Approve Redistribution Journals - Agency (1st Level) ***Afternoon*** - Approve Redistribution Journals - State (2nd Level) - Review and Approve Direct Journal Deposit - Update and Approve Direct Journal Deposit - Deny action for Online Direct Journal Deposits | ***Morning*** - Force reconcile exceptions - Review and Resolve Exceptions | ***Morning*** - Review and Approve Bank Reconciliation Accounting Entries - Generate Unreconciled Deposits Report - Generate and Verify Deposit Report - Generate ACH Notifications of Change Report | ***Morning*** - Run Monthly Apportionment Process - Generate Apportionment Report - Generate and Verify DOR Agency Deposit Report - Generate Reconciled Deposits Report ***Afternoon*** - Generate Verified Deposit Summary Report - Generate Aging Verified Deposit Summary Report - Generate and Verify Debit Memo Report
Week 5 04/19/2021 – 04/23/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT
| ***Morning*** - Set up a new Portfolio - Setup a new Instrument type - Attach portfolio to an Instrument Type | ***Morning*** - Review Deal Cash Flow - Review Deal Analytics - Review deals in a portfolio manager | ***Morning*** - Override Interest Payment - Update a Transaction Rate | ***Morning*** - Generate Income Summary Report - Generate Investment Balances Comparison Report
Week 6 04/26/2021 – 04/30/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT | - Batch Processing in UAT
***Contingency Week***
***Contingency Week***

## Detailed Schedule (hidden)
UAT Execution Detailed Schedule
Week 1 03/22/2021 – 03/26/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| - Submit Electronic Payment Services (EPS) form - Submit Banking Services Form - Submit the Treasury Correspondence Form - Submit the CRA Payment Cancellation Request Form | - Approve Electronic Payment Services (EPS) form - Approve Banking Services Form - Deny the EPS Request Form - Deny Banking Services Request Form - Return the Banking Services Request Form for More Information - Return the EPS Request Form for More Information - Review and Approve Treasury Correspondence Form - Review and Deny the Treasury Correspondence Form - Review and Return the Treasury Correspondence Form On Hold - Review and Approve CRA Stop Payment Request Form | - Re-submit the EPS Request Form - Re-submit Banking Services Form with Added Information - Re-submit the Treasury Correspondence Request Form - Request Cash Transfers between Bank Accounts - Edit Denied CRA Payment Cancellation Request Form - Re-submit the CRA Payment Cancellation Request Form | - Select and Approve Cash Transfers between Bank Accounts - Update/finalize transactions in provisional status - Update/finalize transactions which are in error status - Review and Modify Accounting Entries - View and Approve Accounting Entries - Manually Approve Settlements - Review Accounting Events - Review Accounting Summary | - Generate Bank Account Listing Report - Generate Finalize Accounting Entries Report - Generate Accounting Errors Report - Generate Clearing and Revolving Accounts Report - Generate CRA Revolving Fund Replenishment Report
Week 2 03/29/2021 – 04/02/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| - Add a new Fund values - Inactivate existing Fund values - Create GL journals online - Modify GL journals online - Delete GL journals online - Edit Check Journals | - Create GL journals using Spreadsheet Upload (Import Now) - Create GL journals using Spreadsheet Upload (Write File) - Review Edit Errors and Delete Journal - Review and Correct Edit Errors | - Review, Deny and/or Approve Journals - Review and Correct Invested Balance Checking Errors - Review and Override Invested Balance Checking Errors - Review and Delete Invested Balance Checking Errors | - View Invested Balance (Budget Overview/Detail) - Generate Invested Balance Exceptions Report - Generate Invested Balance Override Report | - View Deleted Journals Report - Generate a Crosswalk Value Report - View Journals with Errors - View Journals with Edit Errors
Week 3 04/05/2021 – 04/09/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Week 4 04/12/2021 – 04/16/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| - Create disinvestment journals - Create Redistribution Journals - Create Direct Journal Deposit and add Foreign Item Support (attachments/images) - Create multiple Payments under one Deposit - Create Direct Journal Deposit using Spreadsheet Upload | - Review reconciliation exceptions - Approve disinvestment journals - Review disinvestment journals - Approve Redistribution Journals - Agency (1st Level) - Approve Redistribution Journals - State (2nd Level) - Review and Approve Direct Journal Deposit - Update and Approve Direct Journal Deposit - Deny action for Online Direct Journal Deposits | - Force reconcile exceptions - Generate ACH Notifications of Change Report - Review and Resolve Exceptions | - Review and Approve Bank Reconciliation Accounting Entries - Generate Unreconciled Deposits Report - Generate and Verify Deposit Report | - Generate Apportionment Report - Generate and Verify DOR Agency Deposit Report - Generate Reconciled Deposits Report - Generate Verified Deposit Summary Report - Generate Aging Verified Deposit Summary Report - Generate and Verify Debit Memo Report
Week 5 04/19/2021 – 04/23/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| - Set up a new Portfolio - Setup a new Instrument type - Attach portfolio to an Instrument Type | - Review Deal Cash Flow - Review Deal Analytics - Review deals in a portfolio manager | - Override Interest Payment - Update a Transaction Rate | - Generate Income Summary Report - Generate Investment Balances Comparison Report
Week 6 04/26/2021 – 04/30/2021
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5
***Contingency Week***
***Contingency Week***

## Week 1 (OLD) (hidden)
Planned Start Date | Planned End Date | Business Process | Primary Module | UAT Scenario ID | UAT Scenario Name | UAT Script ID | UAT Script Name | Florida PALM End User Role
2021-03-22 | 2021-03-22 | 70.1.1 Maintain Bank Accounts | CM | UAT.CM.01 | Submitting EPS and Banking Service Requests | UAT.CM.01.01 | Submit Electronic Payment Services (EPS) form | Bank Account Request Processor
2021-03-22 | 2021-03-22 | 70.1.1 Maintain Bank Accounts | CM | UAT.CM.01 | Submitting EPS and Banking Service Requests | UAT.CM.01.03 | Submit Banking Services Form | Bank Account Request Processor
2021-03-22 | 2021-03-22 | 70.1.2 Manage Treasury Correspondence | CM | UAT.CM.02 | Processing Treasury Correspondence Forms | UAT.CM.02.01 | Submit the Treasury Correspondence Form | Agency Requestor
2021-03-22 | 2021-03-22 | 80.2.6 Manage Revolving Funds | CM | UAT.CM.06 | Processing CRA Stop Payment Requests (DFS) | UAT.CM.06.01 | Submit the CRA Payment Cancellation Request Form | Agency CRA Processor
2021-03-23 | 2021-03-23 | 70.1.1 Maintain Bank Accounts | CM | UAT.CM.01 | Submitting EPS and Banking Service Requests | UAT.CM.01.02 | Approve Electronic Payment Services (EPS) form | DFS Bank Account Maintainer
2021-03-23 | 2021-03-23 | 70.1.1 Maintain Bank Accounts | CM | UAT.CM.01 | Submitting EPS and Banking Service Requests | UAT.CM.01.04 | Approve Banking Services Form | DFS Bank Account Maintainer
2021-03-23 | 2021-03-23 | 70.1.1 Maintain Bank Accounts | CM | UAT.CM.01 | Submitting EPS and Banking Service Requests | UAT.CM.01.05 | Deny the EPS Request Form | DFS Bank Account Maintainer
2021-03-23 | 2021-03-23 | 70.1.1 Maintain Bank Accounts | CM | UAT.CM.01 | Submitting EPS and Banking Service Requests | UAT.CM.01.07 | Deny Banking Services Request Form | DFS Bank Account Maintainer
2021-03-23 | 2021-03-23 | 70.1.1 Maintain Bank Accounts | CM | UAT.CM.01 | Submitting EPS and Banking Service Requests | UAT.CM.01.09 | Return the Banking Services Request Form for More Information | DFS Bank Account Maintainer
2021-03-23 | 2021-03-23 | 70.1.1 Maintain Bank Accounts | CM | UAT.CM.01 | Submitting EPS and Banking Service Requests | UAT.CM.01.11 | Return the EPS Request Form for More Information | DFS Bank Account Maintainer
2021-03-23 | 2021-03-23 | 70.1.2 Manage Treasury Correspondence | CM | UAT.CM.02 | Processing Treasury Correspondence Forms | UAT.CM.02.02 | Review and Approve Treasury Correspondence Form | DFS Correspondence Processor
2021-03-23 | 2021-03-23 | 70.1.2 Manage Treasury Correspondence | CM | UAT.CM.02 | Processing Treasury Correspondence Forms | UAT.CM.02.03 | Review and Deny the Treasury Correspondence Form | DFS Correspondence Processor
2021-03-23 | 2021-03-23 | 70.1.2 Manage Treasury Correspondence | CM | UAT.CM.02 | Processing Treasury Correspondence Forms | UAT.CM.02.05 | Review and Return the Treasury Correspondence Form On Hold | DFS Correspondence Processor
2021-03-23 | 2021-03-23 | 80.2.6 Manage Revolving Funds | CM | UAT.CM.06 | Processing CRA Stop Payment Requests (DFS) | UAT.CM.06.02 | Review and Approve CRA Stop Payment Request Form | DFS Payment Cancellation Processor
2021-03-24 | 2021-03-24 | 70.1.1 Maintain Bank Accounts | CM | UAT.CM.01 | Submitting EPS and Banking Service Requests | UAT.CM.01.06 | Re-submit the EPS Request Form | Bank Account Request Processor
2021-03-24 | 2021-03-24 | 70.1.1 Maintain Bank Accounts | CM | UAT.CM.01 | Submitting EPS and Banking Service Requests | UAT.CM.01.10 | Re-submit Banking Services Form with Added Information | Bank Account Request Processor
2021-03-24 | 2021-03-24 | 70.1.2 Manage Treasury Correspondence | CM | UAT.CM.02 | Processing Treasury Correspondence Forms | UAT.CM.02.04 | Re-submit the Treasury Correspondence Request Form | Agency Requestor
2021-03-24 | 2021-03-24 | 70.4 Process Bank Cash Transfers | CM | UAT.CM.04 | Requesting Cash Transfers between Bank Accounts | UAT.CM.04.01 | Request Cash Transfers between Bank Accounts | Cash Transfer Processor
2021-03-24 | 2021-03-24 | 80.2.6 Manage Revolving Funds | CM | UAT.CM.06 | Processing CRA Stop Payment Requests (DFS) | UAT.CM.06.03 | Edit Denied CRA Payment Cancellation Request Form | Agency CRA Processor
2021-03-24 | 2021-03-24 | 80.2.6 Manage Revolving Funds | CM | UAT.CM.06 | Processing CRA Stop Payment Requests (DFS) | UAT.CM.06.04 | Re-submit the CRA Payment Cancellation Request Form | Agency CRA Processor
2021-03-25 | 2021-03-25 | 70.4 Process Bank Cash Transfers | CM | UAT.CM.03 | Approving Cash Transfers between Bank Accounts | UAT.CM.03.01 | Select and Approve Cash Transfers between Bank Accounts | Cash Transfer Approver
2021-03-25 | 2021-03-25 | 70.4 Process Bank Cash Transfers | CM | UAT.CM.05 | Processing Cash Transfers between Bank Accounts | UAT.CM.05.02 | Update/finalize transactions in provisional status | DFS CM Accounting Approver
2021-03-25 | 2021-03-25 | 70.4 Process Bank Cash Transfers | CM | UAT.CM.05 | Processing Cash Transfers between Bank Accounts | UAT.CM.05.03 | Update/finalize transactions which are in error status | DFS CM Accounting Approver
2021-03-25 | 2021-03-25 | 70.4 Process Bank Cash Transfers | CM | UAT.CM.05 | Processing Cash Transfers between Bank Accounts | UAT.CM.05.08 | Review and Modify Accounting Entries | DFS CM Accounting Approver
2021-03-25 | 2021-03-25 | 70.4 Process Bank Cash Transfers | CM | UAT.CM.05 | Processing Cash Transfers between Bank Accounts | UAT.CM.05.09 | View and Approve Accounting Entries | DFS Transfer Approver
2021-03-25 | 2021-03-25 | 70.4 Process Bank Cash Transfers | CM | UAT.CM.05 | Processing Cash Transfers between Bank Accounts | UAT.CM.05.10 | Manually Approve Settlements | DFS Transfer Approver
2021-03-25 | 2021-03-25 | 70.4 Process Bank Cash Transfers | CM | UAT.CM.05 | Processing Cash Transfers between Bank Accounts | UAT.CM.05.16 | Review Accounting Events | DFS Transfer Approver
2021-03-25 | 2021-03-25 | 70.4 Process Bank Cash Transfers | CM | UAT.CM.05 | Processing Cash Transfers between Bank Accounts | UAT.CM.05.17 | Review Accounting Summary | DFS Transfer Approver
2021-03-26 | 2021-03-26 | 70.1.1 Maintain Bank Accounts | CM | UAT.CM.01 | Submitting EPS and Banking Service Requests | UAT.CM.01.08 | Generate Bank Account Listing Report | DFS Bank Account Maintainer
2021-03-26 | 2021-03-26 | 70.4 Process Bank Cash Transfers | CM | UAT.CM.05 | Processing Cash Transfers between Bank Accounts | UAT.CM.05.05 | Generate Finalize Accounting Entries Report | DFS CM Accounting Approver
2021-03-26 | 2021-03-26 | 70.4 Process Bank Cash Transfers | CM | UAT.CM.05 | Processing Cash Transfers between Bank Accounts | UAT.CM.05.06 | Generate Accounting Errors Report | DFS CM Accounting Approver
2021-03-26 | 2021-03-26 | 80.2.6 Manage Revolving Funds | CM | UAT.CM.06 | Processing CRA Stop Payment Requests (DFS) | UAT.CM.06.05 | Generate Clearing and Revolving Accounts Report | Agency CM Reporter
2021-03-26 | 2021-03-26 | 80.2.6 Manage Revolving Funds | CM | UAT.CM.06 | Processing CRA Stop Payment Requests (DFS) | UAT.CM.06.06 | Generate CRA Revolving Fund Replenishment Report | Agency CRA Processor

## Week 4 (OLD) (hidden)
Planned Start Date | Planned End Date | Business Process | Primary Module | UAT Scenario ID | UAT Scenario Name | UAT Script ID | UAT Script Name | Florida PALM End User Role
2021-04-12 | 2021-04-12 | 80.2.1 Monitor Trust Fund Cash Balance | GL | UAT.GL.04 | Creating and Approving Disinvestment Journals | UAT.GL.04.01 | Create disinvestment journals | Fund Cash Processor
2021-04-12 | 2021-04-12 | 80.2.1 Monitor Trust Fund Cash Balance | GL | UAT.GL.05 | Creating and Approving Investment Journals | UAT.GL.05.02 | Create Redistribution Journals | Fund Cash Processor
2021-04-12 | 2021-04-12 | 60.2.6 Treasury Receipts, Adjustments, and Returned Items | AR | UAT.AR.03 | Creating and Approving Direct Journal Deposit | UAT.AR.03.01 | Create Direct Journal Deposit and add Foreign Item Support (attachments/images) | DFS Deposit Processor
2021-04-12 | 2021-04-12 | 60.2.6 Treasury Receipts, Adjustments, and Returned Items | AR | UAT.AR.03 | Creating and Approving Direct Journal Deposit | UAT.AR.03.04 | Create multiple Payments under one Deposit | DFS Deposit Processor
2021-04-12 | 2021-04-12 | 60.2.6 Treasury Receipts, Adjustments, and Returned Items | AR | UAT.AR.03 | Creating and Approving Direct Journal Deposit | UAT.AR.03.06 | Create Direct Journal Deposit using Spreadsheet Upload | DFS Deposit Processor
2021-04-13 | 2021-04-13 | 70.2 Manage and Reconcile Bank Statements | CM | UAT.CM.08 | Bank Reconciliation | UAT.CM.08.01 | Review reconciliation exceptions | DFS Bank Reonciliation Processor
2021-04-13 | 2021-04-13 | 80.2.1 Monitor Trust Fund Cash Balance | GL | UAT.GL.04 | Creating and Approving Disinvestment Journals | UAT.GL.04.02 | Approve disinvestment journals | GL Journal Approver
2021-04-13 | 2021-04-13 | 80.2.1 Monitor Trust Fund Cash Balance | GL | UAT.GL.04 | Creating and Approving Disinvestment Journals | UAT.GL.04.03 | Review disinvestment journals | Fund Cash Processor
2021-04-13 | 2021-04-13 | 80.2.1 Monitor Trust Fund Cash Balance | GL | UAT.GL.05 | Creating and Approving Investment Journals | UAT.GL.05.03 | Approve Redistribution Journals - Agency (1st Level) | DFS GL Journal Approver
2021-04-13 | 2021-04-13 | 80.2.1 Monitor Trust Fund Cash Balance | GL | UAT.GL.05 | Creating and Approving Investment Journals | UAT.GL.05.04 | Approve Redistribution Journals - State (2nd Level) | State GL Journal Approver
2021-04-13 | 2021-04-13 | 60.2.6 Treasury Receipts, Adjustments, and Returned Items | AR | UAT.AR.03 | Creating and Approving Direct Journal Deposit | UAT.AR.03.02 | Review and Approve Direct Journal Deposit | DFS Deposit Approver
2021-04-13 | 2021-04-13 | 60.2.6 Treasury Receipts, Adjustments, and Returned Items | AR | UAT.AR.03 | Creating and Approving Direct Journal Deposit | UAT.AR.03.03 | Update and Approve Direct Journal Deposit | DFS Deposit Approver
2021-04-13 | 2021-04-13 | 60.2.6 Treasury Receipts, Adjustments, and Returned Items | AR | UAT.AR.03 | Creating and Approving Direct Journal Deposit | UAT.AR.03.05 | Deny action for Online Direct Journal Deposits | DFS Deposit Approver
2021-04-14 | 2021-04-14 | 60.2.4 Manage Electronic Receipts Data | AR | UAT.AR.01 | Generate ACH NOC Report | UAT.AR.01.01 | Generate ACH Notifications of Change Report | Agency Deposit Reporter
2021-04-14 | 2021-04-14 | 70.2 Manage and Reconcile Bank Statements | CM | UAT.CM.08 | Bank Reconciliation | UAT.CM.08.02 | Force reconcile exceptions | DFS Bank Reconciliation Processor
2021-04-14 | 2021-04-14 | 70.2 Manage and Reconcile Bank Statements | DM | UAT.DM.03 | Managing Reconciliation Exceptions | UAT.DM.03.01 | Review and Resolve Exceptions | DFS Bank Reconciliation Processor
2021-04-15 | 2021-04-15 | 70.2 Manage and Reconcile Bank Statements | CM | UAT.CM.08 | Bank Reconciliation | UAT.CM.08.03 | Review and Approve Bank Reconciliation Accounting Entries | DFS CM Accounting Approver
2021-04-15 | 2021-04-15 | 60.2.5 Process FLAIR Deposits | AR | UAT.AR.02 | Generate FLAIR Deposit Reports | UAT.AR.02.01 | Generate Unreconciled Deposits Report | DOR Agency Exception Processor
2021-04-15 | 2021-04-15 | 60.2.5 Process FLAIR Deposits | AR | UAT.AR.02 | Generate FLAIR Deposit Reports | UAT.AR.02.02 | Generate and Verify Deposit Report | Agency Deposit Reporter
2021-04-16 | 2021-04-16 | 70.7.2 Distribute Interest | CM | UAT.CM.07 | Generate Monthly Reports | UAT.CM.07.01 | Generate Apportionment Report | Agency CM Reporter
2021-04-16 | 2021-04-16 | 60.2.5 Process FLAIR Deposits | AR | UAT.AR.02 | Generate FLAIR Deposit Reports | UAT.AR.02.03 | Generate and Verify DOR Agency Deposit Report | Agency Deposit Reporter
2021-04-16 | 2021-04-16 | 60.2.5 Process FLAIR Deposits | AR | UAT.AR.02 | Generate FLAIR Deposit Reports | UAT.AR.02.04 | Generate Reconciled Deposits Report | Agency Deposit Reporter
2021-04-16 | 2021-04-16 | 60.2.5 Process FLAIR Deposits | AR | UAT.AR.02 | Generate FLAIR Deposit Reports | UAT.AR.02.05 | Generate Verified Deposit Summary Report | Agency Deposit Reporter
2021-04-16 | 2021-04-16 | 60.2.5 Process FLAIR Deposits | AR | UAT.AR.02 | Generate FLAIR Deposit Reports | UAT.AR.02.06 | Generate Aging Verified Deposit Summary Report | Agency Deposit Reporter
2021-04-16 | 2021-04-16 | 60.2.6 Treasury Receipts, Adjustments, and Returned Items | AR | UAT.AR.04 | Generate Debit Memo Report | UAT.AR.04.01 | Generate and Verify Debit Memo Report | Agency Deposit Reporter