## DFS Readiness Workplan Task Tra
DFS Readiness Activity Statuses | [30 empty] | ◄ Unhide column for Task Status values.
Division/Offices
Project Impact | Critical Operational Element | Task ID | Task Name | Task Description | CCN Lead | CCN Due Date | FL PALM Start Date | FL PALM End Date | CCN | A&A | ADM | CS | DIFS | DRM | DUP | DWC | DFC | HR | IAAS | ICA | OIR | OFB | OFR | OGC | OIT | PAF | R&L | SFM | TRS
Archived Task | Data | 324 | Complete FLAIR Data Elements Inventory | Complete and submit the FLAIR Data Elements Inventory documenting which FLAIR data elements your agency currently uses and how they are being used. |  | 2023-03-31 | 2022-12-09 | 2023-03-31 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | Processes | 325 | Complete Data Security and Access Survey | Complete and submit the Data Security and Access Survey to inform the Project about how you currently manage data security and end user access. |  | 2023-02-03 | 2023-01-23 | 2023-02-03 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | Technology | 326 | Update Current State Agency Business System Inventory and Documentation | Review and update the list of current Agency Business Systems. Review and confirm documentation of current state technical design for each system. |  | 2023-10-27 | 2023-03-13 | 2023-10-27 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | Data | 327 | Complete Reports Inventory | Complete and submit the Reports Inventory documenting all agency reports that contain FLAIR data. |  | 2023-07-28 | 2023-04-03 | 2023-07-28 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | Processes | 329 | Update CCN and Project Contacts | Review, update and confirm Change Champion Network (primary and back-up liaisons and Subject Matter Experts) and production support contacts. |  | 2023-06-02 | 2023-05-22 | 2023-06-02 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | People | 330 | Update Authorized Smartsheet Users | Review, update and confirm authorized users' access to all Florida PALM Smartsheet resources. |  | 2023-06-23 | 2023-06-12 | 2023-06-23 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | People | 328 | Document Current Agency Business Processes | Document and submit current agency fiscal and payroll processes, including the people and any agency business systems engaged in the processes. |  | 2023-12-15 | 2023-07-31 | 2023-12-15 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | N/A | 331 | Submit Bimonthly Agency Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. |  | 2023-09-11 | 2023-09-01 | 2023-09-11 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | N/A | 500 | Create Agency Specific Project Charter | Create or update an agency-specific Florida PALM Project Charter identifying your agency's objectives, scope, stakeholders and responsibilities. |  | 2023-12-15 | 2023-10-02 | 2023-12-15 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | N/A | 501 | Create Agency Specific Implementation Schedule | Review the Readiness Workplan and Project timeline; develop an implementation timeline that includes agency specific tasks to successfully implement Florida PALM at your agency. |  | 2023-12-15 | 2023-10-09 | 2023-12-15 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | N/A | 502 | Create Agency Specific Risks and Issues Management Plan | Create or update a plan to identify and manage agency specific risks and issues for Florida PALM implementation. |  | 2023-12-15 | 2023-10-09 | 2023-12-15 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | People | 503 | Create Workforce Readiness Plan | Create a plan to identify and engage impacted stakeholders within your agency workforce including a communication strategy, knowledge transfer needs, and workforce attrition planning. |  | 2023-12-15 | 2023-10-16 | 2023-12-15 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | Technology | 504 | Update Agency Business System Documentation for Segment I | Review Segment I resources; update Agency Business System documentation including functional and technical requirements and test cases. |  | 2024-01-12 | 2023-10-30 | 2024-01-12 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | Technology | 505 | Update Florida PALM Interface Inventory for Segment I | Review Segment I resources; identify and document interface needs for Florida PALM implementation. |  | 2024-01-12 | 2023-10-30 | 2024-01-12 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | N/A | 506 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. |  | 2023-11-13 | 2023-11-01 | 2023-11-13 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | N/A | 507 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. |  | 2023-12-27 | 2023-11-01 | 2023-12-27 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | Processes | 508 | Review Payroll Wave Business Process Models | Share and review standardized business process models for the Payroll Wave. |  | 2024-01-26 | 2023-11-06 | 2024-01-26 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | N/A | 509 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. |  | 2024-01-12 | 2023-12-28 | 2024-01-12 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | N/A | 510 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. |  | 2024-02-29 | 2023-12-28 | 2024-02-29 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Archived Task | People | 511 | Update CCN and Contacts | Review, update and confirm Change Champion Network (primary and back-up liaisons and Subject Matter Experts) and production support contacts. |  | 2024-01-26 | 2024-01-08 | 2024-01-26 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Indirect | People | 512 | Identify Future Florida PALM End Users | Submit list of all agency end users who will need access to Florida PALM at implementation. | Kim Jacobs | 2024-03-01 | 2024-01-16 | 2024-03-01 | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Submitted | Status Values
Direct | Data | 513 | Complete Configuration Workbooks for Segments I and II | Accounts Receiveable - Distribtion Code | Sheila Cole Latora Brockamn | 2024-04-12 | 2024-02-12 | 2024-05-10 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed | NA | NA | NA | NA | NA | NA | NA | Assigned
Direct | Data | 513 | Complete Configuration Workbooks for Segments I and II | Asset Management - Area ID | Sheila Cole Bobby Francis | 2024-04-12 | 2024-02-12 | 2024-05-10 | Submitted | NA | Completed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Started
Direct | Data | 513 | Complete Configuration Workbooks for Segments I and II | Asset Management - Location | Sheila Cole Bobby Francis | 2024-04-12 | 2024-02-12 | 2024-05-10 | Submitted | NA | Completed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed
Direct | Data | 513 | Complete Configuration Workbooks for Segments I and II | Commitment Control - Allotment Control Selection | Alexandra Weimorts Teri Madsen Scott Fennell | 2024-04-12 | 2024-02-12 | 2024-05-10 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed | NA | NA | NA | NA | NA | NA | NA | Needs follow-up
Direct | Data | 513 | Complete Configuration Workbooks for Segments I and II | General Ledger - Budgetary Values Combo Edit | Sheila Cole Budget Office Team | 2024-04-12 | 2024-02-12 | 2024-05-10 | Submitted | Completed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed | NA | NA | NA | NA | NA | NA | NA | NA
Direct | Data | 513 | Complete Configuration Workbooks for Segments I and II | General Ledger - Local Funds | Sheila Cole Mikaela Boatright | 2024-04-12 | 2024-02-12 | 2024-05-10 | Submitted | Completed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed | NA | NA | NA | NA | NA | NA | NA | Submitted
Direct | Data | 513 | Complete Configuration Workbooks for Segments I and II | General Ledger - Other Accumulator (OA1) | Sheila Cole | 2024-03-22 | 2024-01-29 | 2024-05-10 | Submitted | Completed | Completed | NA | Completed | Completed | NA | Completed | Completed | NA | Completed | NA | NA | NA | NA | NA | Completed | Completed | NA | Completed | NA | Pending - Late
Direct | Data | 513 | Complete Configuration Workbooks for Segments I and II | General Ledger - Other Accumulator (OA2) | Sheila Cole | NA | 2024-01-29 | 2024-05-10 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 5 days from late
Direct | Data | 513 | Complete Configuration Workbooks for Segments I and II | General Ledger - Organization | Teri Mann | 2024-03-19 | 2024-01-29 | 2024-05-10 | Submitted | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
N/A | Data | 514 | Complete Data Readiness Analysis and Data Cleansing Activities for Segments I and II | Assest Property (AMC001) | Sheila Cole Carolyn Popple | 2024-04-12 | 2024-01-29 | 2024-04-12 | Submitted | NA | Completed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
N/A | Data | 514 | Complete Data Readiness Analysis and Data Cleansing Activities for Segments I and II | Customer (ARC001) | Sheila Cole | 2024-04-12 | 2024-01-29 | 2024-04-12 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed | NA | NA | NA | NA | NA | NA | NA
N/A | Data | 514 | Complete Data Readiness Analysis and Data Cleansing Activities for Segments I and II | Grants (GMC001) | Sheila Cole | 2024-04-12 | 2024-01-29 | 2024-04-12 | Submitted | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
N/A | Data | 514 | Complete Data Readiness Analysis and Data Cleansing Activities for Segments I and II | Encumbrances (POC001) | Sheila Cole Budget Office Team | 2024-03-29 | 2024-01-29 | 2024-04-12 | Submitted | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
N/A | Processes | 515A | Identify Change Impacts and Update Agency Business Process Documentation for Segments I and II | Review Segment I and II resources; identify changes to people, process, technology, and data and update current state business process documentation. | Alexandra Weimorts | 2024-03-29 | 2024-01-29 | 2024-04-12 | Submitted | NA | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
N/A | Processes | 515B | Identify Change Impacts and Update Agency Business Process Documentation for Segments I and II | Stakeholders are to compare old/new and document what is changing. | Alexandra Weimorts | 2024-05-09 | 2024-01-29 | 2024-04-12 | Submitted | NA | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
N/A | Technology | 516 | Update Agency Business System Documentation for Segment II | Review Segment II resources; update agency business system documentation including functional requirements, technical requirements, and test cases. | Stacey Pollock | 2024-07-01 | 2024-01-29 | 2024-04-12 | Started | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Assigned | NA | NA | NA | NA
Indirect | Technology | 517 | Update Florida PALM Conversion Inventory for Segment II | Review Segment II resources; identify and document conversion needs for Florida PALM implementation. | Shiela Cole | 2024-04-12 | 2024-01-29 | 2024-04-12 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed | NA | NA | NA | NA | NA | NA | NA
Indirect | Technology | 518 | Update Florida PALM Interface Inventory for Segment II | Review Segment II resources; identify and document interface needs for Florida PALM implementation. | Stacey Pollock | 2024-04-12 | 2024-01-29 | 2024-04-12 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Started | NA | NA | NA | NA
N/A | Technology | 519 | Remediate Agency Business Systems based on Segment I | Complete agency business system internal build and unit testing activities based on agency business system documentation updates for Segment I. | Stacey Pollock | 2024-12-01 | 2024-01-29 | 2024-06-28 | Assigned | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
N/A | People | 520 | Update Authorized Smartsheet Users | Review, update and confirm authorized users' access to all Florida PALM Smartsheet resources. | Alexandra Weimorts | 2024-02-16 | 2024-02-05 | 2024-02-16 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
N/A | N/A | 521 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. | Alexandra Weimorts Scott Fennell | 2024-03-11 | 2024-03-01 | 2024-03-11 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
N/A | N/A | 522 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. | Asif Sahaf | 2024-04-30 | 2024-03-01 | 2024-04-30 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
N/A | People | 523 | Share Florida PALM Updates | Share Florida PALM updates and agency progress with key agency stakeholders. | Alexandra Weimorts Richard Fierson | 2024-04-19 | 2024-04-08 | 2024-04-19 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
N/A | People | 524 | Complete and Submit End User Readiness Survey Analysis | Administer end user readiness survey and submit data analysis. | Richard Fierson | 2024-06-14 | 2024-04-15 | 2024-06-14 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
N/A | Data | 526 | Complete Data Readiness Analysis and Data Cleansing Activities for Segment III | Review Segment III resources for change impacts to agency data and evaluate current state data readiness. Update agency data cleansing plan and complete data cleansing activities. | Sheila Cole | 2024-06-28 | 2024-04-29 | 2024-07-12 | Started | Started | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Completed | Assigned | Completed | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned
N/A | Processes | 527 | Identify Change Impacts and Update Agency Business Process Documentation for Segment III | Review Segment III resources; identify changes to people, process, technology, and data and update current state business process documentation. Seg III | Alexandra Weimorts Sheila Cole | 2024-07-05 | 2024-04-15 | 2024-07-12 | Started | NA | Assigned | NA | Assigned | Assigned | Assigned | Assigned | Assigned | NA | NA | NA | NA | Assigned | NA | NA | Assigned | Assigned | NA | Assigned | Assigned
N/A | Technology | 528 | Update Agency Business System Documentation for Segment III | Review Segment III resources; update agency business system documentation including functional requirements, technical requirements, and test cases. | Stacey Pollock | 2024-07-01 | 2024-04-15 | 2024-07-12 | Started | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Indirect | Technology | 529 | Update Florida PALM Conversion Inventory for Segment III | Review Segment III resources; identify and document conversion needs for Florida PALM implementation. Vendors/Supplier | Sheila Cole Teri Mann | 2024-06-28 | 2024-04-29 | 2024-07-12 | Started | NA | NA | NA | NA | Started | NA | Started | NA | NA | NA | NA | NA | Started | NA | NA | NA | NA | NA | NA | NA
Indirect | Technology | 529 | Update Florida PALM Conversion Inventory for Segment III | Accounts Receiveable | Sheila Cole | 2024-06-28 | 2024-04-29 | 2024-07-12 | Started | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Started | NA | NA | NA | NA | NA | NA | NA
Indirect | Technology | 529 | Update Florida PALM Conversion Inventory for Segment III | Contracts | Sheila Cole | 2024-06-28 | 2024-04-29 | 2024-07-12 | Started | Assigned | Assigned | Completed | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Completed | Assigned | Completed | Assigned | Completed | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned
Indirect | Technology | 530 | Update Florida PALM Interface Inventory for Segment III | Review Segment III resources; identify and document interface needs for Florida PALM implementation. | Stacey Pollock |  | 2024-04-15 | 2024-07-12 | Started | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
N/A | Technology | 531 | Remediate Agency Business Systems based on Segment II | Complete agency business system internal build and unit testing activities based on agency business system documentation updates for Segment II. | Stacey Pollock | 2024-12-01 | 2024-04-29 | 2024-09-27 | Started | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
N/A | N/A | 532 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. | Alexandra Weimorts | 2024-05-10 | 2024-05-01 | 2024-05-10 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
N/A | N/A | 533 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. | Asif Sahaf | 2024-06-28 | 2024-05-01 | 2024-06-28 | Started | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
N/A | People | 534 | Update CCN and Contacts | Review, update and confirm Change Champion Network (primary and back-up liaisons and Subject Matter Experts) and production support contacts. | Alexandra Weimorts | 2024-06-14 | 2024-06-03 | 2024-06-14 | Submitted | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
N/A | People | 535 | Update Workforce Readiness Plan | Update Workforce Readiness Plan based on End User Survey results. | Kim Jacobs Latasha Tuck | 2024-08-02 | 2024-06-17 | 2024-08-02 | Started | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Indirect | People | 536-A | Create Agency Specific User Acceptance Testing Plan | Establish Testing objectives, scope, key activities and agy roles/responsibilities Prepare a plan for agency participants to engage in User Acceptance Testing, develop agency testing scripts and materials and test all business processes. | CCN Lead |  | 2024-06-17 | 2024-08-16
Indirect | People | 536-B | Create Agency Specific User Acceptance Testing Plan | Identify key components of test execution including test management Prepare a plan for agency participants to engage in User Acceptance Testing, develop agency testing scripts and materials and test all business processes. | CCN Lead |  | 2024-08-19 | 2024-10-11
Indirect | People | 536-C | Create Agency Specific User Acceptance Testing Plan | Confirm busines sprocesses to be tested and identify UAT success creteria. Prepare a plan for agency participants to engage in User Acceptance Testing, develop agency testing scripts and materials and test all business processes. | CCN Lead |  | 2024-10-14 | 2024-12-13
N/A | People | 537 | Update Authorized Smartsheet Users | Review, update and confirm authorized users' access to all Florida PALM Smartsheet resources. | Alexandra Weimorts | 2024-07-12 | 2024-06-24 | 2024-07-12
N/A | N/A | 538 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. | Alexandra Weimorts Asif Sahaf | 2024-07-10 | 2024-07-01 | 2024-07-10
N/A | N/A | 539 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. |  | 2024-08-29 | 2024-07-01 | 2024-08-29
N/A | People | 540 | Share Florida PALM Updates | Share Florida PALM updates and agency progress with key agency stakeholders. |  |  | 2024-07-15 | 2024-07-26
Direct | Data | 541 | Complete Configuration Workbooks for Segment IV | Confirm agency-specific configurations for Segment IV. |  |  | 2024-07-22 | 2024-08-09
N/A | Data | 542 | Complete Data Readiness Analysis and Data Cleansing Activities for Segment IV | Review Segment IV resources for change impacts to agency data and evaluate current state data readiness. Update agency data cleansing plan and complete data cleansing activities. |  |  | 2024-07-22 | 2024-10-18
N/A | Processes | 543 | Identify Change Impacts and Update Agency Business Process Documentation for Segment IV | Review Segment IV resources; identify changes to people, process, technology, and data and update current state business process documentation. |  |  | 2024-07-22 | 2024-10-18
N/A | Technology | 544 | Update Agency Business System Documentation for Segment IV | Review Segment IV resources; update agency business system documentation including functional requirements, technical requirements, and test cases. |  | 2024-07-01 | 2024-07-22 | 2024-10-18
Direct | Technology | 545 | Update and Finalize Florida PALM Conversion Inventory for Segment IV | Review Segment IV resources; identify and document conversion needs for Florida PALM implementation. |  |  | 2024-07-22 | 2024-10-18
Direct | Technology | 546 | Update Florida PALM Interface Inventory for Segment IV | Review Segment IV resources; identify and document interface needs for Florida PALM implementation. |  |  | 2024-07-22 | 2024-10-18
N/A | Technology | 547 | Remediate Agency Business Systems based on Segment III | Complete agency business system internal build and unit testing activities based on agency business system documentation updates for Segment III. |  | 2024-12-01 | 2024-07-22 | 2024-12-13
Direct | Technology | 548 | Identify and Confirm File Managers | Provide File Manager contact information in preparation of connectivity testing. |  |  | 2024-08-05 | 2024-08-16
Direct | People | 549 | Submit Training Survey | Complete the training survey to identify Train the Trainer participants within your agency, if any. |  |  | 2024-08-12 | 2024-09-20
Direct | Technology | 550 | Confirm Receipt and Distribution of Managed File Transfer Credentials | Confirm receipt and distribution of the provided credentials (i.e., usernames and passwords) for the Florida PALM Managed File Transfer (MFT) solution in advance of connectivity testing. |  |  | 2024-08-26 | 2024-09-13
N/A | N/A | 551 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. |  | 2024-09-10 | 2024-08-30 | 2024-09-10
N/A | N/A | 552 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. |  | 2024-10-31 | 2024-08-30 | 2024-10-31
Indirect | Technology | 553 | Prepare for Interface Testing | Review the interface test approach to prepare for interface testing. Confirm alignment with Florida PALM testing plan and cycle. |  |  | 2024-09-03 | 2024-09-27
Direct | Technology | 554 | Participate in Connectivity Testing for Cycle 1 Interface Testing and Mock Conversion 1 | Complete Connectivity Testing for Cycle 1 Interface Testing and Mock Conversion 1 to confirm the ability to transmit data. Submit results of Connectivity Testing and mitigation plans as needed. |  |  | 2024-09-16 | 2024-09-27
Direct | Data | 555 | Certify Data Readiness in Preparation for Mock Conversion 2 | Complete data readiness activities to be ready for Mock 2 Conversion. |  |  | 2024-09-30 | 2024-11-08
Direct | Technology | 556 | Create Conversion Files in Preparation for Mock Conversion 2 | Create conversion files based on layouts to prepare data for Mock Conversion 2. |  |  | 2024-09-30 | 2024-11-08
Direct | Technology | 557 | Update Florida PALM Interface Inventory for Data Warehouse | Review Data Warehouse functionality and update interface needs for Florida PALM implementation. |  |  | 2024-10-07 | 2024-12-13
N/A | Technology | 558 | Update Agency Business System Documentation | Review Data Warehouse design; update agency business system documentation including functional requirements, technical requirements, and test cases. |  |  | 2024-10-07 | 2024-12-13
N/A | People | 559 | Share Florida PALM Updates | Share Florida PALM updates and agency progress with key agency stakeholders. |  |  | 2024-10-14 | 2024-10-25
N/A | Processes | 560 | Submit Change Analysis Tool | Complete and submit the Change Analysis Tool to document your agency's change impacts to your people, processes, technology and data at implementation. |  |  | 2024-10-21 | 2024-12-20
N/A | Technology | 561 | Remediate Agency Business Systems based on Segment IV | Complete agency business system internal build and unit testing activities based on agency business system documentation updates for Segment IV. |  |  | 2024-10-21 | 2025-03-14
N/A | N/A | 562 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. |  | 2024-11-12 | 2024-11-01 | 2024-11-12
N/A | N/A | 563 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. |  | 2024-12-27 | 2024-11-01 | 2024-12-27
Indirect | People | 564 | Update Future Florida PALM Users | Submit updated list of all agency end users who currently have access to FLAIR. |  |  | 2024-11-04 | 2024-12-06
Direct | Technology | 565 | Participate in Mock Conversion 2 | Extract and validate conversion data from agency business system(s); validate conversion data provided from Florida PALM; and transmit conversion files to Florida PALM for Mock Conversion 2. |  |  | 2024-11-12 | 2024-11-22
Direct | Technology | 566 | Validate Detailed Cycle 2 Interface Testing Information | Review detailed interface testing information to prepare for interface testing activities, validate MFT credentials and agency testing personnel assignments. |  |  | 2024-12-02 | 2024-12-27
Direct | Data | 567 | Share, Review, and Update Configuration Workbooks | Update Configuration Workbooks to prepare for User Acceptance Testing. |  |  | 2024-12-02 | 2025-01-24
N/A | People | 568 | Create Training Plan for Agency Managed End User Training | Share and review Planned Florida PALM end user training curriculum to support identification and planning of agency managed and agency specific end user training topics. Develop and submit a training plan for agency managed end user training. |  |  | 2024-12-09 | 2025-03-28
N/A | N/A | 569 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. |  | 2025-01-10 | 2024-12-30 | 2025-01-10
N/A | N/A | 570 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. |  | 2025-02-27 | 2024-12-30 | 2025-02-27
Direct | Data | 571 | Complete Data Cleansing Based on Mock Conversion 2 | Review Mock Conversion 2 results and perform data cleansing activities to prepare data for Mock Conversion 3. |  |  | 2025-01-06 | 2025-01-17
N/A | People | 572 | Update CCN and Contacts | Review, update and confirm Change Champion Network (primary and back-up liaisons and Subject Matter Experts) and production support contacts. |  |  | 2025-01-06 | 2025-01-17
Direct | People | 573 | Complete and Submit End User Role Mapping Worksheet | Complete and submit the End User Role Mapping Worksheet to assign end users to Florida PALM system roles. |  |  | 2025-01-06 | 2025-02-28
Indirect | Processes | 574 | Prepare Documentation for User Acceptance Testing | Create and prepare User Acceptance Testing test scripts and materials. |  |  | 2025-01-06 | 2025-03-14
Direct | Technology | 575 | Complete Cycle 2 - Technical Interface Testing | Complete Cycle 2 - Technical Interface Testing activities to test interfaces, validating exchanged data in business systems and Florida PALM. Submit results of interface testing and mitigation plans as needed. |  |  | 2025-01-06 | 2025-04-25
N/A | Technology | 576 | Complete Internal Agency Business System Test | Complete internal Agency Business System test to validate system modifications and prepare for full-integration testing. |  |  | 2025-01-06 | 2025-06-13
N/A | Technology | 577 | Remediate Agency Business Systems and Update Documentation | Complete internal build and unit testing activities for agency business systems for Data Warehouse integration. Make updates to agency business systems and related documentation based on interface testing findings. |  |  | 2025-01-06 | 2025-06-27
Direct | Technology | 578 | Confirm Identity Provider for Florida PALM | Confirm intended identity provider(s) planned to store or contain the agency's users for Florida PALM. |  |  | 2025-01-13 | 2025-02-28
Direct | People | 579 | Identify, Prepare, and Confirm Understanding of User Acceptance Testing Participants | Provide list of User Acceptance Testing participants and confirm participants understand updated standardized business process models and are prepared to provide feedback on the outcome of test scenarios. |  |  | 2025-01-13 | 2025-02-28
N/A | Processes | 580 | Update Agency Business Process Documentation | Update agency business process documentation based on Change Analysis Tool and Role Mapping. |  |  | 2025-01-13 | 2025-03-28
N/A | Data | 581 | Update Reports Inventory | Identify how you plan to meet your reporting needs using standard Florida PALM reports or Data Warehouse. |  |  | 2025-01-13 | 2025-03-28
N/A | People | 582 | Share Florida PALM Updates | Share Florida PALM updates and agency progress with key agency stakeholders. |  |  | 2025-01-21 | 2025-01-31
Direct | Technology | 583 | Participate in Mock Conversion 3 | Extract and validate conversion data from agency business system(s); validate conversion data provided from Florida PALM; and transmit conversion files to Florida PALM for Mock Conversion 3. |  |  | 2025-01-21 | 2025-01-31
N/A | People | 584 | Update Authorized Smartsheet Users | Review, update and confirm authorized users' access to all Florida PALM Smartsheet resources. |  |  | 2025-01-27 | 2025-02-07
N/A | People | 585 | Update Workforce Readiness Plan | Update Workforce Readiness Plan based on Role Mapping and Change Analysis. |  |  | 2025-02-03 | 2025-03-14
Indirect | Technology | 586 | Create Agency Deployment Plan to Prepare for Go-Live | Create Agency deployment plan to prepare for internal agency activities needed for go-live. |  |  | 2025-02-10 | 2025-05-02
Direct | Data | 587 | Complete Data Cleansing Based on Mock Conversion 3 | Review Mock Conversion 3 results and perform data cleansing activities to prepare data for Mock Conversion 4. |  |  | 2025-02-24 | 2025-03-21
Direct | People | 588 | Confirm and Prepare Participants for Train the Trainer | Confirm and prepare Train the Trainer participants and register for Train the Trainer sessions. |  |  | 2025-02-24 | 2025-03-28
N/A | N/A | 589 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. |  | 2025-03-10 | 2025-02-28 | 2025-03-10
N/A | N/A | 590 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. |  | 2025-04-30 | 2025-02-28 | 2025-04-30
Direct | Technology | 591 | Confirm IDP Configuration for Florida PALM | Confirm IDP configuration for Florida PALM in preparation of User Acceptance Testing. |  |  | 2025-03-03 | 2025-03-21
Direct | Technology | 592 | Agency IDP SMEs Add Identified User Acceptance Testing Participants to Agency's Identity Provider | Agency IDP SMEs add their agency's identified User Acceptance Testing participants to identity provider in preparation for User Acceptance Testing. |  |  | 2025-03-03 | 2025-03-28
Indirect | N/A | 593 | Update Agency Readiness Certification | Provide update to Agency Readiness Certification in preparation for go-live. |  | 2025-03-28 | 2025-03-03 | 2025-03-28
Direct | Technology | 594 | Participate in Mock Conversion 4 | Extract and validate conversion data from agency business system(s); validate conversion data provided from Florida PALM; and transmit conversion files to Florida PALM for Mock Conversion 4. |  |  | 2025-03-24 | 2025-04-11
N/A | People | 595 | Complete and Submit End User Readiness Survey Analysis | Administer end user readiness survey and submit data analysis. |  |  | 2025-03-31 | 2025-05-30
Direct | People | 596 | Participate in User Acceptance Testing | Participate in User Acceptance Testing to validate outcome of test scenarios. |  |  | 2025-04-07 | 2025-11-14
Direct | Data | 597 | Complete Data Cleansing Based on Mock Conversion 4 | Review Mock Conversion 4 results and perform data cleansing activities to prepare data for go-live. |  |  | 2025-04-14 | 2025-04-25
N/A | People | 598 | Share Florida PALM Updates | Share Florida PALM updates and agency progress with key agency stakeholders. |  |  | 2025-04-14 | 2025-04-25
N/A | N/A | 599 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. |  | 2025-05-12 | 2025-05-01 | 2025-05-12
N/A | N/A | 600 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. |  | 2025-06-30 | 2025-05-01 | 2025-06-30
Direct | People | 601 | Register for Florida PALM Training | Ensure end users are prepared and registered for Florida PALM training. |  |  | 2025-05-05 | 2025-06-13
N/A | Processes | 602 | Update Agency Business Process Documentation | Update agency business process documentation based on User Acceptance Testing. |  |  | 2025-05-05 | 2025-10-03
Direct | People | 603 | Participate in Train the Trainer | Actively participate in Train the Trainer activities. |  |  | 2025-05-19 | 2025-08-15
N/A | People | 604 | Create Agency Specific Training | Develop training materials for agency specific training. |  |  | 2025-05-19 | 2025-09-26
N/A | People | 605 | Update CCN and Contacts | Review, update and confirm Change Champion Network (primary and back-up liaisons and Subject Matter Experts) and production support contacts. |  |  | 2025-06-02 | 2025-06-13
Indirect | N/A | 606 | Update Agency Readiness Certification | Provide update to Agency Readiness Certification in preparation for go-live. |  | 2025-06-27 | 2025-06-02 | 2025-06-27
N/A | People | 607 | Update Training Plan | Update agency specific training plan based on end user survey, User Acceptance Testing findings and Train the Trainer. |  |  | 2025-06-02 | 2025-06-27
N/A | People | 608 | Update Workforce Readiness Plan | Update the Workforce Readiness Plan to include identification of the agency End User Support Team of subject matter experts, development of internal support procedures and communication strategy for go-live campaign. |  |  | 2025-06-02 | 2025-08-29
Direct | Technology | 609 | Confirm Ready for Full Integration Testing | Complete internal Agency Business System test and confirm ready for full-integration testing. |  |  | 2025-06-16 | 2025-07-03
N/A | People | 610 | Update Authorized Smartsheet Users | Review, update and confirm authorized users' access to all Florida PALM Smartsheet resources. |  |  | 2025-06-23 | 2025-07-11
N/A | N/A | 611 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. |  | 2025-07-10 | 2025-07-01 | 2025-07-10
N/A | N/A | 612 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. |  | 2025-08-28 | 2025-07-01 | 2025-08-28
Direct | People | 613 | Participate in Florida PALM Training | End users participate in Florida PALM web-based and instructor-led trainings. |  |  | 2025-07-01 | 2025-11-21
Direct | Technology | 614 | Provide Interface Files to Support User Acceptance Testing and Full Integration Testing | Participate in full integration testing by providing interface files to support User Acceptance Testing. |  |  | 2025-07-07 | 2025-09-26
N/A | Technology | 615 | Remediate Agency Business Systems and Update Documentation | Make updates to agency business systems and related documentation based on UAT full integration findings. |  |  | 2025-07-07 | 2025-09-26
N/A | People | 616 | Share Florida PALM Updates | Share Florida PALM updates and agency progress with key agency stakeholders. |  |  | 2025-07-14 | 2025-07-25
N/A | N/A | 617 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. |  | 2025-09-10 | 2025-08-29 | 2025-09-10
N/A | N/A | 618 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. |  | 2025-10-31 | 2025-08-29 | 2025-10-31
Indirect | N/A | 619 | Update Agency Readiness Certification | Provide update to Agency Readiness Certification in preparation for go-live. |  | 2025-09-26 | 2025-09-02 | 2025-09-26
Indirect | Technology | 620 | Create Agency-Specific Cutover Checklist | Create agency-specific deployment cutover checklist with agency implementation team to prepare for cutover. |  |  | 2025-09-02 | 2025-11-14
N/A | People | 621 | Execute Florida PALM Go-Live Campaign | Ensure agency stakeholders' readiness by executing final communications in preparation for go-live. |  |  | 2025-10-06 | 2025-10-31
Direct | Data | 622 | Review and Confirm Updated Configuration Workbooks | Review and confirm Configuration Workbook to prepare for go-live. |  |  | 2025-10-06 | 2025-10-31
Indirect | Technology | 623 | Create Agency Post-Implementation Support Plan | Create an Agency post-implementation support plan to prepare for internal agency activities needed following go-live. |  |  | 2025-10-06 | 2025-11-14
N/A | Processes | 624 | Finalize and Distribute Agency Business Process Documentation | Provide final Florida PALM Business Process documentation and job aids to end users. |  |  | 2025-10-06 | 2025-12-05
N/A | People | 625 | Conduct Agency Specific Training | Conduct agency specific training to prepare end users for go-live. |  |  | 2025-10-06 | 2025-12-12
Direct | Technology | 626 | Share, Review, and Complete Cutover Checklist | Share and review cutover checklist with agency implementation team to prepare for Cutover. Participate in go-live by completing Cutover Checklist activities. |  |  | 2025-10-20 | 2026-01-09
N/A | N/A | 627 | Submit Bimonthly Agency Readiness Status Report | Agency Sponsor to confirm and submit bimonthly status report, in the format provided by the Project, on the activities and ongoing work within the agency to prepare their systems and impacted employees for the deployment of Florida PALM. |  | 2025-11-10 | 2025-11-03 | 2025-11-10
Direct | N/A | 628 | Submit Agency Readiness Certification | Submit Agency Readiness Certification for Executive Steering Committee go-live decision. |  | 2025-11-14 | 2025-11-03 | 2025-11-14
N/A | People | 629 | Execute Florida PALM Go-Live Campaign | Ensure agency stakeholders' readiness by executing final communications in preparation for go-live. |  |  | 2025-11-03 | 2025-11-26
Direct | People | 630 | Update and Submit End User Role Mapping Worksheet | Update and submit the End User Role Mapping Worksheet to assign end users to Florida PALM system roles in preparation for go-live. |  |  | 2025-11-03 | 2025-12-05
N/A | People | 631 | Require End User Practice | End users practice job functions in the User Acceptance Testing environment to reinforce training. |  |  | 2025-11-03 | 2025-12-12
N/A | N/A | 632 | Manage Agency Specific Implementation Schedule, Risks and Issues | Actively manage your agency's project activities including iterative updates to agency-specific project schedule and manage agency-unique risks and issues. |  | 2026-01-30 | 2025-11-03 | 2026-01-30
N/A | People | 633 | Execute Florida PALM Go-Live Campaign | Ensure agency stakeholders' readiness by executing final communications in preparation for go-live. |  |  | 2025-12-01 | 2026-01-02
Direct | Technology | 634 | Complete Agency-Specific Cutover Checklist | Review Agency-Specific Cutover Checklist with agency implementation team to prepare for Cutover. Participate in go-live by completing checklist activities. |  |  | 2025-12-01 | 2026-01-09
Direct | Technology | 635 | Agency IDP SMEs Add End Users to Agency's Identity Provider | Agency IDP SMEs add agency's identified end users to agency's identity provider in preparation for go-live. |  |  | 2025-12-08 | 2025-12-19
Direct | Data | 636 | Submit Final Conversion Files to Florida PALM for Go-Live | Extract and validate conversion data from agency business system(s); validate conversion data provided from Florida PALM; and transmit final conversion files to Florida PALM for go-live. |  |  | 2025-12-29 | 2026-01-02
N/A | People | 637 | Execute Florida PALM Go-Live Campaign | Share go-live communications with agency end users and other stakeholders. |  |  | 2026-01-05 | 2026-01-09
N/A | People | 638 | Post-Implementation: Attend Florida PALM Hosted Help Sessions | Confirm agency attendance in Help Sessions as needed. |  |  | 2026-01-05 | 2026-01-30
N/A | People | 639 | Post-Implementation: Conduct Agency End User Support Sessions | Conduct agency-specific end user support sessions as needed |  |  | 2026-01-05 | 2026-01-30
N/A | Technology | 640 | Post-Implementation: Remediate Agency Business Systems and Update Documentation | Complete updates to agency business systems and related documentation during hypercare as needed. |  |  | 2026-01-07 | 2026-03-27
N/A | People | 641 | Post-Implementation: Require End User Practice in Florida PALM Sandbox | End users practice job functions and new processes in the Florida PALM Sandbox prior to completing in production. |  |  | 2026-01-12 | 2026-03-27
N/A | N/A | 642 | Post-Implementation: Submit Agency Status Report | Submit Agency post-implementation status report following go-live. |  | 2026-02-10 | 2026-01-30 | 2026-02-10
N/A | People | 643 | Post-Implementation: Attend Florida PALM Hosted Help Sessions | Confirm agency attendance in Help Sessions as needed. |  |  | 2026-02-02 | 2026-02-27
N/A | People | 644 | Post-Implementation: Conduct Agency End User Support Sessions | Conduct agency-specific end user support sessions as needed |  |  | 2026-02-02 | 2026-02-27
N/A | N/A | 645 | Post-Implementation: Submit Agency Status Report | Submit Agency post-implementation status report following go-live. |  | 2026-03-10 | 2026-02-27 | 2026-03-10
N/A | People | 646 | Post-Implementation: Attend Florida PALM Hosted Help Sessions | Confirm agency attendance in Help Sessions as needed. |  |  | 2026-03-02 | 2026-03-27
N/A | People | 647 | Post-Implementation: Conduct Agency End User Support Sessions | Conduct agency-specific end user support sessions as needed |  |  | 2026-03-02 | 2026-03-27
N/A | N/A | 648 | Post-Implementation: Submit Agency Status Report | Submit Agency post-implementation status report following go-live. |  | 2026-04-10 | 2026-04-01 | 2026-04-10
N/A | N/A | 649 | Post-Implementation: Submit Agency Status Report | Submit Agency post-implementation status report following go-live. |  | 2026-05-11 | 2026-05-01 | 2026-05-11
N/A | N/A | 650 | Post-Implementation: Submit Agency Status Report | Submit Agency post-implementation status report following go-live. |  | 2026-06-10 | 2026-06-01 | 2026-06-10
N/A | N/A | 651 | Post-Implementation: Submit Agency Status Report | Submit Agency post-implementation status report following go-live. |  | 2026-07-10 | 2026-07-01 | 2026-07-10
N/A | N/A | 652 | Post-Implementation: Submit Agency Status Report | Submit Agency post-implementation status report following go-live. |  | 2026-08-10 | 2026-07-31 | 2026-08-10
N/A | N/A | 653 | Post-Implementation: Submit Agency Status Report | Submit Agency post-implementation status report following go-live. |  | 2026-09-10 | 2026-09-01 | 2026-09-10
N/A | N/A | 654 | Post-Implementation: Submit Agency Status Report | Submit Agency post-implementation status report following go-live. |  | 2026-10-12 | 2026-10-01 | 2026-10-12
N/A | N/A | 655 | Post-Implementation: Submit Agency Status Report | Submit Agency post-implementation status report following go-live. |  | 2026-11-10 | 2026-10-30 | 2026-11-10
N/A | N/A | 656 | Post-Implementation: Submit Agency Status Report | Submit Agency post-implementation status report following go-live. |  | 2026-12-10 | 2026-12-01 | 2026-12-10
Note on E3: Weimorts, Alexandra: Hyoer-links withing the task description will take user to the workbook or folder for the details