## Instructions
Instructions
1) Review the CMS Wave Cutover Checklist.
2) On the Cutover Checklist worksheet, fill out the information for each checklist item.
a. In Status (Column E), list the current status of the cutover task (e.g., not started, in progress, complete)
b. In Agency Point of Contact (Column F), list the person(s) within your agency responsible for completing the task.
c. In Notes (Column G), provide notes describing the process and timeline to complete the task, as applicable.
3) Confirm completion of checklist with your Readiness Coordinator by July 2, 2021.

## Cutover Checklist
CMS Wave Cutover Checklist
Item Number | Task | Complete by Date | Resources | Status | Agency Point of Contact | Notes
1 | Complete your internal agency business system data cleansing. | 2021-06-18 | - MRW Task: TECH89 - DFS Data Management Approach
2 | Confirm processes are in place to retire your agency business systems (as applicable). | 2021-06-18 | - MRW Task: FUNC30
3 | Confirm your agency understands the Florida PALM Batch schedule. | 2021-06-18 | - MRW Task: FUNC45
4 | Communicate your agency-specific processes regarding system down time for fiscal year end and Florida PALM cutover. | 2021-07-02 | - Year End Memo (https://www.myfloridacfo.com/Division/AA/Memos/documents/aam222021.pdf)
5 | Confirm funding for disbursments between July 1 and July 15. Treasury will not process Trust Fund Disinvestments from June 30 - July 14. Treasury will resume processing Trust Fund disinvestments by July 15, 2021. | 2021-07-02 | - Year End Memo (https://www.myfloridacfo.com/Division/AA/Memos/documents/aam222021.pdf) -Treasury Notification to Trust Fund Administrators
6 | Confirm end user work stations have been updated according to Florida PALM Supported Browsers Job Aid. | 2021-07-02 | - MRW Task: COMM36 - Florida PALM Supported Browsers Job Aid
7 | Confirm your Tier 0 model including escalation paths. | 2021-07-02 | - MRW Task: RDNS237
8 | Share your Security Access Manager contact information with end users. | 2021-07-02 | - MRW Task: RDNS254 - Change Discussion Guides - Florida PALM Website: User Support Webpage (https://myfloridacfo.com/floridapalm/user-support)
9 | Share your Tier 0 Support Team contact information with your end users. | 2021-07-02 | - Florida PALM Website: User Support Webpage (https://myfloridacfo.com/floridapalm/user-support)
10 | Share the Florida PALM User Support Page with your end users. | 2021-07-02 | - Florida PALM Website: User Support Webpage (https://myfloridacfo.com/floridapalm/user-support) - MRW Task: COMM36
11 | Confirm your end users understand the agency-specific processes in place to contact your agency's Tier 0 Support Team and Security Access Managers for support regarding process questions, system access, and password resets. | 2021-07-02 | - MRW Task: RDNS237
12 | Confirm that your Security Access Manager has awareness of what updates have been made to agency's end user role mapping (added, removed, or modified) so that changes can be made after launch. | 2021-07-02 | - MRW Task: RDNS246
13 | Confirm your Identity Provider Subject Matter Expert has added your agency's identified CMS Wave end users to your agency's identity provider as allowed users of Florida PALM. | 2021-07-02 | - MRW Task: TECH104 - MRW Task: TECH110
14 | Confirm your File Transfer Manager is ready to perform interfaces at launch (as applicable). | 2021-07-02 | - MRW Task: TECH93 - MRW Task: TECH103 - Interface Connection Inventory
15 | Confirm users who will use Journal Spreadsheet Uploads have downloaded the spreadsheet templates (as applicable). | 2021-07-02 | - MRW Task: TECH107
16 | Confirm your end users understand the ChartField and Bank Account configurations values for your agency. | 2021-07-02 | - MRW Task: FUNC49 - COA Design Structure Overview (https://myfloridacfo.com/floridapalm/solution)
17 | Identify and internally communicate expectations to end users that will perform business needs on day one versus those who need to access the system to perform future business needs. | 2021-07-02 | -End User Role Mapping Worksheet - Change Champion Network Townhall May 2021 Presentation, slide 6 (https://myfloridacfo.com/floridapalm/agency/meetings-workshops)
18 | Confirm your end users have completed applicable Florida PALM end user Training based on assigned Florida PALM end user roles. | 2021-07-02 | - MRW Task: TRNG37
19 | Confirm your end users have completed your internal agency-specific training. | 2021-07-05 | - MRW Task: TRNG30 - MRW Task: TRNG33
20 | Confirm your end users know where to locate the CMS Wave End User Manual (will be published June 25) | 2021-07-05 | -Florida PALM Website: Solution Webpage (https://myfloridacfo.com/floridapalm/solution)
21 | Communicate to your agency that Florida PALM has launched. | 2021-07-06 | - MRW Task: COMM36 - MRW Task: COMM37 - MRW Task: COMM38 - End User Role Mapping Worksheet
22 | Communicate to your agency end users the link to access Florida PALM. | 2021-07-06 | - MRW Task: COMMM37 - Florida PALM (Production link)