## Sample Schedule Template
ID | RW ID (if applicable) | Activity Coordinator | Task Name | Planned Start Date | Planned Finish Date | Progress (% Complete) | Actual Start Date | Actual Finish Date | Resource Names
`

## As of 6.9.2023 (hidden)
Unique ID | ID | Status | Critical Path Items | RW | DEL, WP, SG # | Task Coordinator | Task Type | Task Name | Work | Duration | Start | Finish | Predecessors | Successors | Notes | Resource Names | Requested Updates | Requested By
0 | 0 | Late | [5 empty] | Project Schedule (Financials, Payroll, Data Warehouse and Business Intelligence) | 38,733.02 hrs | 1177 days | Wed 4/26/23 | Tue 12/28/27
7152 | 1 | Complete |  |  |  | Jimmy Cox | Milestone | Amendment 8 Executed | 0 hrs | 0 days | Wed 4/26/23 | Wed 4/26/23 |  | 11,34FS+3 days,53FS+47 days,91FS+27 days,112FS+27 days,217,348FS+91 days,190,204,602FS+47 days,72FS+27 days,152,171,230,244,258,335,388,444,466,486,506,526,539,643,686,746,787,814,833,852,894,919,938,1011,1030,1055,1069,1149,1163,1188,1202,1262,1298,135... |  | Jimmy Cox
2 | 2 | Late | [5 empty] | Implementation | 30,525.69 hrs | 699 days | Wed 4/26/23 | Wed 2/4/26
3769 | 3 | Late | [5 empty] | Design | 5,219.11 hrs | 475 days | Wed 4/26/23 | Fri 3/14/25
7172 | 4 | Future Task |  |  | SG1 | Jimmy Cox | Create | Stage Gate 1: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 7/3/23 | Mon 7/10/23 |  | 5 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7170 | 5 | Future Task |  |  | SG1 | Jimmy Cox | Create | Stage Gate 1: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Tue 7/11/23 | Mon 7/24/23 | 4 | 6FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7171 | 6 | Future Task |  |  | SG1 | Jimmy Cox | Create | Stage Gate 1: Prepare information package for ESC | 11 hrs | 10 days | Mon 11/13/23 | Tue 11/28/23 | 5FS+77 days | 7 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7169 | 7 | Future Task |  |  | SG1 | Jimmy Cox | Create | Stage Gate 1: Collaborative Review and Update of information package | 11 hrs | 5 days | Wed 11/29/23 | Tue 12/5/23 | 6 | 8 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7168 | 8 | Future Task |  |  | SG1 | Jimmy Cox | Create | Stage Gate 1: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 12/6/23 | Wed 12/6/23 | 7 |  |  | Dusti Kincl
7155 | 9 | Future Task |  |  | SG1 | Jimmy Cox | Milestone | Stage Gate 1: Ready to Start Build | 0 hrs | 0 days | Mon 10/23/23 | Mon 10/23/23 | 51,61 |  | Nov/Dec 2023 | Jimmy Cox,Angie Robertson,Matt Cole
3793 | 10 | On Schedule | Yes |  | D635 | Joy Schneider |  | D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) | 403 hrs | 38 days | Mon 5/8/23 | Thu 6/29/23
7130 | 11 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Develop Outline of Project Schedule | 2 hrs | 1 day | Mon 5/8/23 | Mon 5/8/23 | 1 | 12SS |  | Joy Schneider,Francisca Li
7131 | 12 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Create New Schedule Tasks Workbook | 4 hrs | 1 day | Mon 5/8/23 | Mon 5/8/23 | 11SS | 13,14,15FS+1 day |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner
7132 | 13 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Gather Tasks from State Architects | 60 hrs | 4 days | Tue 5/9/23 | Fri 5/12/23 | 12 | 23 |  | Julian Gotreaux,Gabriela Gibson,Tommy Werner,Angie Robertson,Deana Metcalf,Carolyn Hicks,Jennifer Reeves,Matthew Breeding
7133 | 14 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Load Amendment 8 Deliverables and Work Products to Project Schedule | 4 hrs | 2 days | Tue 5/9/23 | Wed 5/10/23 | 12 | 23 |  | Joy Schneider,Francisca Li
7134 | 15 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Load Resources into Project Schedule | 8 hrs | 1 day | Wed 5/10/23 | Wed 5/10/23 | 12FS+1 day | 16 |  | Joy Schneider,Francisca Li
7135 | 16 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Add and Refine Work Activities for Amendment 8 Deliverables | 17 hrs | 2 days | Thu 5/11/23 | Fri 5/12/23 | 15 | 17SS+1 day |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole
7136 | 17 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Add Tasks from State Architects | 10 hrs | 1 day | Fri 5/12/23 | Fri 5/12/23 | 16SS+1 day | 18,19 |  | Joy Schneider,Francisca Li
7138 | 18 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Add and Refine Work Activities for Amendment 8 Work Products | 60 hrs | 5 days | Mon 5/15/23 | Fri 5/19/23 | 17 | 23 |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole
7139 | 19 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Project Schedule Working Sessions | 85 hrs | 5 days | Mon 5/15/23 | Fri 5/19/23 | 17 | 20 |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Manojkumar Gurjar,Yogesh Deshmukh,Matt Cole,Angie Robertson,Deana Metcalf,Matthew Breeding,Carolyn Hicks,Jimmy Cox,Jennifer Reeves
7140 | 20 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Refine Work Activities for Non-SSI Deliverables and Work Products | 26 hrs | 5 days | Mon 5/22/23 | Fri 5/26/23 | 19 | 21SS+2 days |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Gabriela Gibson
7141 | 21 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Define Tasks to Assign to Critical Path Column | 25 hrs | 11 days | Wed 5/24/23 | Thu 6/8/23 | 20SS+2 days | 22 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Jimmy Cox,Matt Cole
7142 | 22 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Provide Project Schedule Export Reports and Refine Based on Input | 25 hrs | 9 days | Tue 5/30/23 | Fri 6/9/23 | 21 | 23 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Deana Metcalf,Matthew Breeding,Carlos Luis,Jimmy Cox,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Manojkumar Gurjar,Yogesh Deshmukh,Matt Cole,Jennifer Reeves
7143 | 23 | Future Task |  |  | D635 | Joy Schneider | Create | D635 - Conduct Project Schedule Baseline Prep Meeting | 36 hrs | 1 day | Mon 6/12/23 | Mon 6/12/23 | 22,13,14,18 | 24 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Deana Metcalf,Matthew Breeding,Carolyn Hicks,Jimmy Cox,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole,Gabriela Gibson,Jennifer Reeves
4271 | 24 | Future Task |  |  | D635 | Joy Schneider | Submit | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Draft Submission | 0 hrs | 0 days | Mon 6/12/23 | Mon 6/12/23 | 23 | 25 |  | Joy Schneider
4272 | 25 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Pre-Submission Collaborative Review | 14 hrs | 3 days | Tue 6/13/23 | Thu 6/15/23 | 24 | 26 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Gabriela Gibson,Jenifer Hartsfield,Angie Robertson
4273 | 26 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Style Guide Review | 1 hr | 1 day | Fri 6/16/23 | Fri 6/16/23 | 25 | 27 |  | Dusti Kincl
4274 | 27 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Final Collaborative Review | 10 hrs | 3 days | Mon 6/19/23 | Wed 6/21/23 | 26 | 28 |  | Joy Schneider,Francisca Li,Angie Robertson,Jimmy Cox,Jennifer Reeves,Deana Metcalf,Matthew Breeding,Carolyn Hicks
4275 | 28 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Accenture QC | 4 hrs | 2 days | Thu 6/22/23 | Fri 6/23/23 | 27 | 29 |  | Joy Schneider
4276 | 29 | Future Task |  |  | D635 | Joy Schneider | Submit | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Submit | 0 hrs | 0 days | Fri 6/23/23 | Fri 6/23/23 | 28 | 30 |  | Joy Schneider
4277 | 30 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Department QC | 4 hrs | 1 day | Mon 6/26/23 | Mon 6/26/23 | 29 | 31 |  | Tommy Werner,Gabriela Gibson
4278 | 31 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Contract Manager Review | 8 hrs | 3 days | Tue 6/27/23 | Thu 6/29/23 | 30 | 32 |  | Sean Buchanan
4279 | 32 | Future Task |  |  | D635 | Joy Schneider | Accept | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Accept | 0 hrs | 0 days | Thu 6/29/23 | Thu 6/29/23 | 31 | 2360 | 2023-06-01 | Sean Buchanan
4280 | 33 | Late | Yes |  | D636 | Stacey Terry |  | D636 - Completion of Solution Design (Requirements) Segment I | 309 hrs | 82 days | Mon 5/1/23 | Thu 8/24/23
4308 | 34 | Late |  |  | D636 | Stacey Terry | Create | D636 - Identify Functional Designs (Segment I) | 50 hrs | 10 days | Mon 5/1/23 | Fri 5/12/23 | 1FS+3 days | 35 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4281 | 35 | Late |  |  | D636 | Stacey Terry | Create | DED D636 - Completion of Solution Design (Requirements) Segment I - Create | 8 hrs | 10 days | Mon 5/15/23 | Fri 5/26/23 | 34 | 36 |  | Stacey Terry,Mary Punty
4282 | 36 | Late |  |  | D636 | Stacey Terry | Submit | DED D636 - Completion of Solution Design (Requirements) Segment I - Submit | 0 hrs | 0 days | Fri 5/26/23 | Fri 5/26/23 | 35 | 37 |  | Stacey Terry,Joy Schneider
4283 | 37 | Late |  |  | D636 | Stacey Terry | Review | DED D636 - Completion of Solution Design (Requirements) Segment I - Collaborative Review | 24 hrs | 4 days | Tue 5/30/23 | Fri 6/2/23 | 36 | 38 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4284 | 38 | Late |  |  | D636 | Stacey Terry | Approve | DED D636 - Completion of Solution Design (Requirements) Segment I - Approve | 0 hrs | 0 days | Fri 6/2/23 | Fri 6/2/23 | 37 | 39 |  | Jimmy Cox
4309 | 39 | Future Task |  |  | D636 | Stacey Terry | Create | D636 - Update Deliverable Work Unit Tracker for Functional Designs (Segment I) | 50 hrs | 5 days | Mon 6/5/23 | Fri 6/9/23 | 38 | 40 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4310 | 40 | Future Task |  |  | D636 | Stacey Terry | Create | D636 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment I) | 50 hrs | 4 days | Mon 6/12/23 | Thu 6/15/23 | 39 | 41 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4311 | 41 | Future Task |  | RW-Communication - Segment 1 Workshop? (suggest move to IWP101) | D636 | Stacey Terry | Create | D636 - Create, Review and Approve Functional Design Documents (Segment I) | 50 hrs | 32 days | Fri 6/16/23 | Tue 8/1/23 | 40 | 42FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4312 | 42 | Future Task |  |  | D636 | Stacey Terry | Create | D636 - Create Summary Document | 20 hrs | 11 days | Tue 7/18/23 | Tue 8/1/23 | 41FS-11 days | 43,1587SS,1631SS,1674SS,1499,1544 |  | Deana Metcalf,Stacey Terry,Mary Punty
4285 | 43 | Future Task |  |  | D636 | Stacey Terry | Submit | DEL D636 - Completion of Solution Design (Requirements) Segment I - Draft Submission | 0 hrs | 0 days | Tue 8/1/23 | Tue 8/1/23 | 42 | 44 |  | Stacey Terry,Joy Schneider
4286 | 44 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Wed 8/2/23 | Tue 8/8/23 | 43 | 45 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4287 | 45 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Style Guide Review | 1 hr | 1 day | Wed 8/9/23 | Wed 8/9/23 | 44 | 46 |  | Dusti Kincl
4288 | 46 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Final Collaborative Review | 20 hrs | 5 days | Thu 8/10/23 | Wed 8/16/23 | 45 | 47 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4289 | 47 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Accenture QC | 4 hrs | 2 days | Thu 8/17/23 | Fri 8/18/23 | 46 | 48 |  | Joy Schneider
4290 | 48 | Future Task |  |  | D636 | Stacey Terry | Submit | DEL D636 - Completion of Solution Design (Requirements) Segment I - Submit | 0 hrs | 0 days | Fri 8/18/23 | Fri 8/18/23 | 47 | 491709 |  | Joy Schneider
4291 | 49 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Department QC | 4 hrs | 1 day | Mon 8/21/23 | Mon 8/21/23 | 48 | 50 |  | Tommy Werner,Gabriela Gibson
4292 | 50 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Contract Manager Review | 8 hrs | 3 days | Tue 8/22/23 | Thu 8/24/23 | 49 | 51 |  | Sean Buchanan
4293 | 51 | Future Task |  |  | D636 | Stacey Terry | Accept | DEL D636 - Completion of Solution Design (Requirements) Segment I - Accept | 0 hrs | 0 days | Thu 8/24/23 | Thu 8/24/23 | 50 | 221,580,594,600,9,571 | July 2023 (Aug 2023) | Sean Buchanan
4294 | 52 | Future Task | Yes |  | D637 | Stacey Terry |  | D637 - Completion of Solution Design (Requirements) Segment II | 342 hrs | 96 days | Mon 7/3/23 | Thu 11/16/23
4313 | 53 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Identify Functional Designs (Segment II) | 50 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 1FS+47 days | 54 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4295 | 54 | Future Task |  |  | D637 | Stacey Terry | Create | DED D637 - Completion of Solution Design (Requirements) Segment II - Create | 16 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 53 | 55 |  | Stacey Terry,Mary Punty
4296 | 55 | Future Task |  |  | D637 | Stacey Terry | Submit | DED D637 - Completion of Solution Design (Requirements) Segment II - Submit | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 54 | 56 |  | Stacey Terry,Joy Schneider
4297 | 56 | Future Task |  |  | D637 | Stacey Terry | Review | DED D637 - Completion of Solution Design (Requirements) Segment II - Collaborative Review | 24 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 55 | 57 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4298 | 57 | Future Task |  |  | D637 | Stacey Terry | Approve | DED D637 - Completion of Solution Design (Requirements) Segment II - Approve | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 56 | 58 |  | Jimmy Cox
4314 | 58 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Update Deliverable Work Unit Tracker for Functional Designs (Segment II) | 50 hrs | 4 days | Tue 8/15/23 | Fri 8/18/23 | 57 | 59 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4315 | 59 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment II) | 50 hrs | 5 days | Mon 8/21/23 | Fri 8/25/23 | 58 | 60 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4316 | 60 | Future Task |  | RW-Communication - Segment 2 Workshop? (suggest move to IWP101) | D637 | Stacey Terry | Create | D637 - Create, Review and Approve Functional Design Documents (Segment II) | 50 hrs | 40 days | Mon 8/28/23 | Mon 10/23/23 | 59 | 61FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4317 | 61 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Create Summary Document | 50 hrs | 11 days | Mon 10/9/23 | Mon 10/23/23 | 60FS-11 days | 62,1590SS,1456SS,1634SS+2 days,1677SS+5 days,1502,1547,9 |  | Deana Metcalf,Stacey Terry,Mary Punty
4299 | 62 | Future Task |  |  | D637 | Stacey Terry | Submit | DEL D637 - Completion of Solution Design (Requirements) Segment II - Draft Submission | 0 hrs | 0 days | Mon 10/23/23 | Mon 10/23/23 | 61 | 63 |  | Stacey Terry,Joy Schneider
4300 | 63 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 10/24/23 | Mon 10/30/23 | 62 | 64 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4301 | 64 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Style Guide Review | 1 hr | 1 day | Tue 10/31/23 | Tue 10/31/23 | 63 | 65 |  | Dusti Kincl
4302 | 65 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Final Collaborative Review | 20 hrs | 5 days | Wed 11/1/23 | Tue 11/7/23 | 64 | 66 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4303 | 66 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Accenture QC | 1 hr | 2 days | Wed 11/8/23 | Thu 11/9/23 | 65 | 67 |  | Francisca Li
4304 | 67 | Future Task |  |  | D637 | Stacey Terry | Submit | DEL D637 - Completion of Solution Design (Requirements) Segment II - Submit | 0 hrs | 0 days | Thu 11/9/23 | Thu 11/9/23 | 66 | 68 |  | Joy Schneider
4305 | 68 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Department QC | 2 hrs | 1 day | Mon 11/13/23 | Mon 11/13/23 | 67 | 69 |  | Tommy Werner,Gabriela Gibson
4306 | 69 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Contract Manager Review | 8 hrs | 3 days | Tue 11/14/23 | Thu 11/16/23 | 68 | 70 |  | Sean Buchanan
4307 | 70 | Future Task |  |  | D637 | Stacey Terry | Accept | DEL D637 - Completion of Solution Design (Requirements) Segment II - Accept | 0 hrs | 0 days | Thu 11/16/23 | Thu 11/16/23 | 69 | 580594600571 | October 2023 (Nov 2023) | Sean Buchanan
5585 | 71 | Future Task | Yes |  | D638 | Manojkumar Gurjar |  | D638 - Updated Data Conversion and Migration Strategy | 209 hrs | 80 days | Mon 6/5/23 | Tue 9/26/23
5586 | 72 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | DED D638 - Updated Data Conversion and Migration Strategy - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 73 |  | Manojkumar Gurjar,Kurt Meisner
5587 | 73 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DED D638 - Updated Data Conversion and Migration Strategy - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 72 | 74 |  | Manojkumar Gurjar,Joy Schneider
5588 | 74 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DED D638 - Updated Data Conversion and Migration Strategy - Collaborative Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 73 | 75 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5589 | 75 | Future Task |  |  | D638 | Manojkumar Gurjar | Approve | DED D638 - Updated Data Conversion and Migration Strategy - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 74 | 76 |  | Jimmy Cox
5590 | 76 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | D638 - Define the approach for Data Cleansing | 4 hrs | 14 days | Mon 7/3/23 | Fri 7/21/23 | 75 | 77SS+4 days |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5591 | 77 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | D638 - Define Communication/Collaboration for Data Conversion approach | 4 hrs | 10 days | Mon 7/10/23 | Fri 7/21/23 | 76SS+4 days | 79,78SS |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
7245 | 78 | Future Task |  | RW | D638 | Manojkumar Gurjar | Create | D638 - Create Conversion Approach document | 4 hrs | 10 days | Mon 7/10/23 | Fri 7/21/23 | 77SS | 79 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5592 | 79 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | D638 - Identify Data Conversion Resources | 50 hrs | 10 days | Mon 7/24/23 | Fri 8/4/23 | 77,78 | 80 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer,Jeevan Mahajan,Janmejay Khare
5593 | 80 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | D638 - Updated Data Conversion and Migration Strategy Document | 50 hrs | 19 days | Mon 8/7/23 | Thu 8/31/23 | 79 | 81 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5594 | 81 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DEL D638 - Updated Data Conversion and Migration Strategy - Draft Submission | 0 hrs | 0 days | Thu 8/31/23 | Thu 8/31/23 | 80 | 82 |  | Manojkumar Gurjar,Joy Schneider
5595 | 82 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 81 | 83 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5596 | 83 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Style Guide Review | 1 hr | 1 day | Mon 9/11/23 | Mon 9/11/23 | 82 | 84 |  | Dusti Kincl
5597 | 84 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Final Collaborative Review | 20 hrs | 5 days | Tue 9/12/23 | Mon 9/18/23 | 83 | 85 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5598 | 85 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Accenture QC | 4 hrs | 2 days | Tue 9/19/23 | Wed 9/20/23 | 84 | 86 |  | Joy Schneider
5599 | 86 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DEL D638 - Updated Data Conversion and Migration Strategy - Submit | 0 hrs | 0 days | Wed 9/20/23 | Wed 9/20/23 | 85 | 87 |  | Joy Schneider
5600 | 87 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Department QC | 4 hrs | 1 day | Thu 9/21/23 | Thu 9/21/23 | 86 | 88 |  | Tommy Werner,Gabriela Gibson
5601 | 88 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Contract Manager Review | 8 hrs | 3 days | Fri 9/22/23 | Tue 9/26/23 | 87 | 89 |  | Sean Buchanan
5602 | 89 | Future Task |  |  | D638 | Manojkumar Gurjar | Accept | DEL D638 - Updated Data Conversion and Migration Strategy - Accept | 0 hrs | 0 days | Tue 9/26/23 | Tue 9/26/23 | 88 |  | 2023-10-01 | Sean Buchanan
4375 | 90 | Future Task | Yes |  | D639 | Stacey Terry |  | D639 - Development of Standardized Business Process Models – Payroll | 241 hrs | 94 days | Mon 6/5/23 | Mon 10/16/23
4376 | 91 | Future Task |  |  | D639 | Stacey Terry | Create | DED D639 - Development of Standardized Business Process Models – Payroll - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 92 |  | Stacey Terry,Mary Punty
4377 | 92 | Future Task |  |  | D639 | Stacey Terry | Submit | DED D639 - Development of Standardized Business Process Models – Payroll - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 91 | 93 |  | Stacey Terry,Joy Schneider
4378 | 93 | Future Task |  |  | D639 | Stacey Terry | Review | DED D639 - Development of Standardized Business Process Models – Payroll - Collaborative Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 92 | 94 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4379 | 94 | Future Task |  |  | D639 | Stacey Terry | Approve | DED D639 - Development of Standardized Business Process Models – Payroll - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 93 | 95 |  | Jimmy Cox
4417 | 95 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Identify Payroll Wave Business Processes and Subprocesses | 25 hrs | 5 days | Mon 7/3/23 | Mon 7/10/23 | 94 | 96SS+2 days |  | Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari
4418 | 96 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Update Deliverable Work Unit Tracker for Payroll Wave Business Processes and Subprocesses | 4 hrs | 5 days | Thu 7/6/23 | Wed 7/12/23 | 95SS+2 days | 97 |  | Stacey Terry,Yogesh Deshmukh
4419 | 97 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Review and Confirm Deliverable Work Unit Tracker for Payroll Wave Business Processes and Subprocesses | 20 hrs | 5 days | Thu 7/13/23 | Wed 7/19/23 | 96 | 98SS |  | Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4420 | 98 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Create Payroll Wave Business Process Models | 30 hrs | 30 days | Thu 7/13/23 | Wed 8/23/23 | 97SS | 99 |  | Jimmy Cox,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari,Heather Cleary,Joanne Lane,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Donnie Doctor,Ryan R...
4421 | 99 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Prepare Materials / Conduct Office Hours | 25 hrs | 10 days | Thu 8/24/23 | Thu 9/7/23 | 98 | 100 |  | Jimmy Cox,Angie Robertson,Carolyn Hicks,Dusti Kincl,Kimberly Kemp,Deana Metcalf,Stacey Terry,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Janice Jackson,LaVondria Norton,Robert Hic...
4422 | 100 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Refine Payroll Wave Business Process Models | 20 hrs | 5 days | Fri 9/8/23 | Thu 9/14/23 | 99 | 101 |  | Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari
4423 | 101 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Create Summary Document | 20 hrs | 5 days | Fri 9/15/23 | Thu 9/21/23 | 100 | 102 |  | Deana Metcalf,Stacey Terry,Mary Punty
4380 | 102 | Future Task |  |  | D639 | Stacey Terry | Submit | DEL D639 - Development of Standardized Business Process Models – Payroll - Draft Submission | 0 hrs | 0 days | Thu 9/21/23 | Thu 9/21/23 | 101 | 103 |  | Stacey Terry,Joy Schneider
4381 | 103 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 9/22/23 | Thu 9/28/23 | 102 | 104 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4382 | 104 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Style Guide Review | 1 hr | 1 day | Fri 9/29/23 | Fri 9/29/23 | 103 | 105 |  | Dusti Kincl
4383 | 105 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Final Collaborative Review | 20 hrs | 5 days | Mon 10/2/23 | Fri 10/6/23 | 104 | 106 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4384 | 106 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Accenture QC | 4 hrs | 2 days | Mon 10/9/23 | Tue 10/10/23 | 105 | 107 |  | Joy Schneider
4385 | 107 | Future Task |  |  | D639 | Stacey Terry | Submit | DEL D639 - Development of Standardized Business Process Models – Payroll - Submit | 0 hrs | 0 days | Tue 10/10/23 | Tue 10/10/23 | 106 | 108 |  | Joy Schneider
4386 | 108 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Department QC | 4 hrs | 1 day | Wed 10/11/23 | Wed 10/11/23 | 107 | 109 |  | Tommy Werner,Gabriela Gibson
4387 | 109 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Contract Manager Review | 8 hrs | 3 days | Thu 10/12/23 | Mon 10/16/23 | 108 | 110 |  | Sean Buchanan
4388 | 110 | Future Task |  | RW-Communication | D639 | Stacey Terry | Accept | DEL D639 - Development of Standardized Business Process Models – Payroll - Accept | 0 hrs | 0 days | Mon 10/16/23 | Mon 10/16/23 | 109 | 1853580 | 2023-10-01 | Sean Buchanan
4389 | 111 | Future Task | Yes |  | D640 | Stacey Terry |  | D640 - Development of the Master Data Configuration Workbooks | 311 hrs | 142 days | Mon 6/5/23 | Wed 12/27/23
4390 | 112 | Future Task |  |  | D640 | Stacey Terry | Create | DED D640 - Development of the Master Data Configuration Workbooks - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 113,116SS+9 days |  | Stacey Terry,Mary Punty
4391 | 113 | Future Task |  |  | D640 | Stacey Terry | Submit | DED D640 - Development of the Master Data Configuration Workbooks - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 112 | 114 |  | Stacey Terry,Joy Schneider
4392 | 114 | Future Task |  |  | D640 | Stacey Terry | Review | DED D640 - Development of the Master Data Configuration Workbooks - Collaborative Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 113 | 115 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4393 | 115 | Future Task |  |  | D640 | Stacey Terry | Approve | DED D640 - Development of the Master Data Configuration Workbooks - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 114 |  |  | Jimmy Cox
4424 | 116 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Identify Configuration Inventory | 20 hrs | 10 days | Fri 6/16/23 | Thu 6/29/23 | 112SS+9 days | 117 |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Donnie Doctor,Ryan Raagas,Pooj...
4425 | 117 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Update Design Work Unit Tracker for Configuration | 4 hrs | 5 days | Fri 6/30/23 | Fri 7/7/23 | 116 | 118 |  | Stacey Terry,Yogesh Deshmukh
4426 | 118 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Review and Confirm Design Work Unit Tracker for Configuration | 50 hrs | 4 days | Mon 7/10/23 | Thu 7/13/23 | 117 | 119 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4427 | 119 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Create, Review, and Confirm Configuration Workbooks and Agency Configuration Workbook Templates | 40 hrs | 80 days | Fri 7/14/23 | Fri 11/3/23 | 118 | 120SS+20 days |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Donnie Doctor,Ryan Raagas,Pooj...
4428 | 120 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Configure Application | 40 hrs | 70 days | Fri 8/11/23 | Mon 11/20/23 | 119SS+20 days | 121 |  | Apoorva Panchanadikar,Divya Gupta,Supriya Vaddi,Suyesh Shingare,Purushottam Karambelkar,Ankita Sarang,Yash Jamkhedkar,Sajal Saurabh,Timtim Goel
4429 | 121 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Finalize Configuration Workbooks | 30 hrs | 10 days | Tue 11/21/23 | Wed 12/6/23 | 120 | 122FS-10 days |  | Apoorva Panchanadikar,Divya Gupta,Supriya Vasudevan,Suyesh Shingare,Purushottam Karambelkar,Ankita Sarang,Yash Jamkhedkar,Sajal Saurabh,Timtim Goel,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Jack Je...
4430 | 122 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Create Summary Document | 30 hrs | 7 days | Tue 11/21/23 | Fri 12/1/23 | 121FS-10 days | 123 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Mary Punty
4394 | 123 | Future Task |  |  | D640 | Stacey Terry | Submit | DEL D640 - Development of the Master Data Configuration Workbooks - Draft Submission | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 122 | 124 |  | Stacey Terry,Joy Schneider
4395 | 124 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 12/4/23 | Fri 12/8/23 | 123 | 125 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4396 | 125 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Style Guide Review | 1 hr | 1 day | Mon 12/11/23 | Mon 12/11/23 | 124 | 126 |  | Dusti Kincl
4397 | 126 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Final Collaborative Review | 20 hrs | 5 days | Tue 12/12/23 | Mon 12/18/23 | 125 | 127 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4398 | 127 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Accenture QC | 4 hrs | 2 days | Tue 12/19/23 | Wed 12/20/23 | 126 | 128 |  | Joy Schneider
4399 | 128 | Future Task |  |  | D640 | Stacey Terry | Submit | DEL D640 - Development of the Master Data Configuration Workbooks - Submit | 0 hrs | 0 days | Wed 12/20/23 | Wed 12/20/23 | 127 | 129 |  | Joy Schneider
4400 | 129 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Department QC | 4 hrs | 1 day | Thu 12/21/23 | Thu 12/21/23 | 128 | 130 |  | Tommy Werner,Gabriela Gibson
4401 | 130 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Contract Manager Review | 8 hrs | 3 days | Fri 12/22/23 | Wed 12/27/23 | 129 | 131 |  | Sean Buchanan
4402 | 131 | Future Task |  | RW-Communication | D640 | Stacey Terry | Accept | DEL D640 - Development of the Master Data Configuration Workbooks - Accept | 0 hrs | 0 days | Wed 12/27/23 | Wed 12/27/23 | 130 | 576FS+6 days | 2023-12-01 | Sean Buchanan
4318 | 132 | Future Task |  |  | D641 | Stacey Terry |  | D641 - Completion of Solution Design (Requirements) Segment III | 327 hrs | 96 days | Mon 10/2/23 | Tue 2/20/24
4332 | 133 | Future Task |  |  | D641 | Stacey Terry | Create | Identify Functional Designs (Segment III) | 50 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 1 | 134 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4319 | 134 | Future Task |  |  | D641 | Stacey Terry | Create | DED D641 - Completion of Solution Design (Requirements) Segment III - Create | 16 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 133 | 135 |  | Stacey Terry,Mary Punty
4320 | 135 | Future Task |  |  | D641 | Stacey Terry | Submit | DED D641 - Completion of Solution Design (Requirements) Segment III - Submit | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 134 | 136 |  | Stacey Terry,Joy Schneider
4321 | 136 | Future Task |  |  | D641 | Stacey Terry | Review | DED D641 - Completion of Solution Design (Requirements) Segment III - Collaborative Review | 24 hrs | 10 days | Mon 10/30/23 | Mon 11/13/23 | 135 | 137 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4322 | 137 | Future Task |  |  | D641 | Stacey Terry | Approve | DED D641 - Completion of Solution Design (Requirements) Segment III - Approve | 0 hrs | 0 days | Mon 11/13/23 | Mon 11/13/23 | 136 | 138 |  | Jimmy Cox
4333 | 138 | Future Task |  |  | D641 | Stacey Terry | Create | D641 - Update Deliverable Work Unit Tracker for Functional Designs (Segment III) | 40 hrs | 4 days | Tue 11/14/23 | Fri 11/17/23 | 137 | 139 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4334 | 139 | Future Task |  |  | D641 | Stacey Terry | Create | D641 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment III) | 40 hrs | 5 days | Mon 11/20/23 | Tue 11/28/23 | 138 | 140 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4335 | 140 | Future Task |  | RW-Communication (suggest move to IWP101) | D641 | Stacey Terry | Create | D641 - Create, Review and Approve Functional Design Documents (Segment III) | 50 hrs | 40 days | Wed 11/29/23 | Fri 1/26/24 | 139 | 141FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4336 | 141 | Future Task |  |  | D641 | Stacey Terry | Create | D641 - Create Summary Document | 50 hrs | 11 days | Thu 1/11/24 | Fri 1/26/24 | 140FS-11 days | 142,1593SS,1637SS,1680SS+5 days,1505SS,1550,1459SS |  | Deana Metcalf,Stacey Terry,Mary Punty
4323 | 142 | Future Task |  |  | D641 | Stacey Terry | Submit | DEL D641 - Completion of Solution Design (Requirements) Segment III - Draft Submission | 0 hrs | 0 days | Fri 1/26/24 | Fri 1/26/24 | 141 | 143 |  | Stacey Terry,Joy Schneider
4324 | 143 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 1/29/24 | Fri 2/2/24 | 142 | 144 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4325 | 144 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Style Guide Review | 1 hr | 1 day | Mon 2/5/24 | Mon 2/5/24 | 143 | 145 |  | Dusti Kincl
4326 | 145 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Final Collaborative Review | 20 hrs | 5 days | Tue 2/6/24 | Mon 2/12/24 | 144 | 146 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4327 | 146 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Accenture QC | 4 hrs | 2 days | Tue 2/13/24 | Wed 2/14/24 | 145 | 147 |  | Joy Schneider
4328 | 147 | Future Task |  |  | D641 | Stacey Terry | Submit | DEL D641 - Completion of Solution Design (Requirements) Segment III - Submit | 0 hrs | 0 days | Wed 2/14/24 | Wed 2/14/24 | 146 | 148 |  | Joy Schneider
4329 | 148 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Department QC | 4 hrs | 1 day | Thu 2/15/24 | Thu 2/15/24 | 147 | 149 |  | Tommy Werner,Gabriela Gibson
4330 | 149 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Contract Manager Review | 8 hrs | 3 days | Fri 2/16/24 | Tue 2/20/24 | 148 | 150 |  | Sean Buchanan
4331 | 150 | Future Task |  |  | D641 | Stacey Terry | Accept | DEL D641 - Completion of Solution Design (Requirements) Segment III - Accept | 0 hrs | 0 days | Tue 2/20/24 | Tue 2/20/24 | 149 | 580594600571 | January 2024 (Feb 2024) | Sean Buchanan
4337 | 151 | Future Task | Yes |  | D644 | Stacey Terry |  | D644 - Completion of Solution Design (Requirements) Segment IV | 337 hrs | 85 days | Mon 1/29/24 | Fri 5/24/24
4351 | 152 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Identify Functional Designs (Segment IV) | 50 hrs | 10 days | Mon 1/29/24 | Fri 2/9/24 | 1 | 153 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4338 | 153 | Future Task |  |  | D644 | Stacey Terry | Create | DED D644 - Completion of Solution Design (Requirements) Segment IV - Create | 16 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 152 | 154 |  | Stacey Terry,Mary Punty
4339 | 154 | Future Task |  |  | D644 | Stacey Terry | Submit | DED D644 - Completion of Solution Design (Requirements) Segment IV - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 153 | 155 |  | Stacey Terry,Joy Schneider
4340 | 155 | Future Task |  |  | D644 | Stacey Terry | Review | DED D644 - Completion of Solution Design (Requirements) Segment IV - Collaborative Review | 24 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 154 | 156 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4341 | 156 | Future Task |  |  | D644 | Stacey Terry | Approve | DED D644 - Completion of Solution Design (Requirements) Segment IV - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 155 | 157 |  | Jimmy Cox
4352 | 157 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Update Deliverable Work Unit Tracker for Functional Designs (Segment IV) | 50 hrs | 4 days | Mon 3/11/24 | Thu 3/14/24 | 156 | 158 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4353 | 158 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment IV) | 50 hrs | 4 days | Fri 3/15/24 | Wed 3/20/24 | 157 | 159 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4354 | 159 | Future Task |  | RW-Communication (suggest move to IWP101) | D644 | Stacey Terry | Create | D644 - Create, Review and Approve Functional Design Documents (Segment IV) | 50 hrs | 30 days | Thu 3/21/24 | Wed 5/1/24 | 158 | 160FS-8 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4355 | 160 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Create Summary Document | 40 hrs | 8 days | Mon 4/22/24 | Wed 5/1/24 | 159FS-8 days | 161,1606SS,1650SS,1693SS+5 days,1518SS,1563SS |  | Deana Metcalf,Stacey Terry,Mary Punty
4342 | 161 | Future Task |  |  | D644 | Stacey Terry | Submit | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Draft Submission | 0 hrs | 0 days | Wed 5/1/24 | Wed 5/1/24 | 160 | 162 |  | Stacey Terry,Joy Schneider
4343 | 162 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Pre-Submission Collaborative Review | 20 hrs | 5 days | Thu 5/2/24 | Wed 5/8/24 | 161 | 163594 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4344 | 163 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Style Guide Review | 1 hr | 1 day | Thu 5/9/24 | Thu 5/9/24 | 162 | 164 |  | Dusti Kincl
4345 | 164 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Final Collaborative Review | 20 hrs | 5 days | Fri 5/10/24 | Thu 5/16/24 | 163 | 165 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4346 | 165 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Accenture QC | 4 hrs | 2 days | Fri 5/17/24 | Mon 5/20/24 | 164 | 166 |  | Joy Schneider
4347 | 166 | Future Task |  |  | D644 | Stacey Terry | Submit | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Submit | 0 hrs | 0 days | Mon 5/20/24 | Mon 5/20/24 | 165 | 167 |  | Joy Schneider
4348 | 167 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Department QC | 4 hrs | 1 day | Tue 5/21/24 | Tue 5/21/24 | 166 | 168 |  | Tommy Werner,Gabriela Gibson
4349 | 168 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Contract Manager Review | 8 hrs | 3 days | Wed 5/22/24 | Fri 5/24/24 | 167 | 169 |  | Sean Buchanan
4350 | 169 | Future Task |  |  | D644 | Stacey Terry | Accept | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Accept | 0 hrs | 0 days | Fri 5/24/24 | Fri 5/24/24 | 168 | 580FS+24 days,600,571FS+83 days | April 2024 (May 2024) | Sean Buchanan
4356 | 170 | Future Task | Yes |  | D650 | Stacey Terry |  | D650 - Completion of Solution Design (Requirements) DW/BI | 347 hrs | 160 days | Fri 3/1/24 | Tue 10/15/24
4357 | 171 | Future Task |  |  | D650 | Stacey Terry | Create | DED D650 - Completion of Solution Design (Requirements) DW/BI - Create | 16 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 1 | 172 |  | Stacey Terry,Mary Punty
4358 | 172 | Future Task |  |  | D650 | Stacey Terry | Submit | DED D650 - Completion of Solution Design (Requirements) DW/BI - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 171 | 173 |  | Stacey Terry,Joy Schneider
4359 | 173 | Future Task |  |  | D650 | Stacey Terry | Review | DED D650 - Completion of Solution Design (Requirements) DW/BI - Collaborative Review | 24 hrs | 10 days | Fri 3/15/24 | Thu 3/28/24 | 172 | 174 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4360 | 174 | Future Task |  |  | D650 | Stacey Terry | Approve | DED D650 - Completion of Solution Design (Requirements) DW/BI - Approve | 0 hrs | 0 days | Thu 3/28/24 | Thu 3/28/24 | 173 | 175 |  | Jimmy Cox
4370 | 175 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Identify Functional Designs DW/BI | 50 hrs | 10 days | Fri 3/29/24 | Thu 4/11/24 | 174 | 176 |  | Stacey Terry,Yogesh Deshmukh
4371 | 176 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Update Deliverable Work Unit Tracker for Functional Designs DW/BI | 50 hrs | 10 days | Fri 4/12/24 | Thu 4/25/24 | 175 | 177 |  | Stacey Terry,Yogesh Deshmukh
4372 | 177 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs DW/BI | 50 hrs | 10 days | Fri 4/26/24 | Thu 5/9/24 | 176 | 178 |  | Stacey Terry,Yogesh Deshmukh
4373 | 178 | Future Task |  | RW-Communication | D650 | Stacey Terry | Create | D650 - Create, Review and Approve Functional Design Documents DW/BI | 50 hrs | 82 days | Fri 5/10/24 | Thu 9/5/24 | 177 | 179 |  | Stacey Terry,Yogesh Deshmukh
4374 | 179 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Create Summary Document | 50 hrs | 11 days | Fri 9/6/24 | Fri 9/20/24 | 178 | 180 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4361 | 180 | Future Task |  |  | D650 | Stacey Terry | Submit | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Draft Submission | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 179 | 181 |  | Stacey Terry,Joy Schneider
4362 | 181 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 180 | 182 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4363 | 182 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Style Guide Review | 1 hr | 1 day | Mon 9/30/24 | Mon 9/30/24 | 181 | 183 |  | Dusti Kincl
4364 | 183 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Final Collaborative Review | 20 hrs | 5 days | Tue 10/1/24 | Mon 10/7/24 | 182 | 184 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4365 | 184 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Accenture QC | 4 hrs | 2 days | Tue 10/8/24 | Wed 10/9/24 | 183 | 185 |  | Joy Schneider
4366 | 185 | Future Task |  |  | D650 | Stacey Terry | Submit | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Submit | 0 hrs | 0 days | Wed 10/9/24 | Wed 10/9/24 | 184 | 186 |  | Joy Schneider
4367 | 186 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Department QC | 4 hrs | 1 day | Thu 10/10/24 | Thu 10/10/24 | 185 | 187 |  | Tommy Werner,Gabriela Gibson
4368 | 187 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Contract Manager Review | 8 hrs | 3 days | Fri 10/11/24 | Tue 10/15/24 | 186 | 188 |  | Sean Buchanan
4369 | 188 | Future Task |  |  | D650 | Stacey Terry | Accept | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Accept | 0 hrs | 0 days | Tue 10/15/24 | Tue 10/15/24 | 187 |  | 2024-10-01 | Sean Buchanan
4431 | 189 | Future Task |  |  | WP402 | Stacey Terry |  | WP402 - Requirements Traceability Matrix | 248 hrs | 60 days | Mon 6/19/23 | Tue 9/12/23
4432 | 190 | Future Task |  |  | WP402 | Stacey Terry | Create | WPED WP402 - Requirements Traceability Matrix - Create | 8 hrs | 5 days | Mon 6/19/23 | Fri 6/23/23 | 1 | 191 |  | Stacey Terry,Mary Punty
4433 | 191 | Future Task |  |  | WP402 | Stacey Terry | Submit | WPED WP402 - Requirements Traceability Matrix - Submit | 0 hrs | 0 days | Fri 6/23/23 | Fri 6/23/23 | 190 | 192 |  | Joy Schneider,Stacey Terry
4434 | 192 | Future Task |  |  | WP402 | Stacey Terry | Review | WPED WP402 - Requirements Traceability Matrix - Review | 12 hrs | 5 days | Mon 6/26/23 | Fri 6/30/23 | 191 | 193 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4435 | 193 | Future Task |  |  | WP402 | Stacey Terry | Approve | WPED WP402 - Requirements Traceability Matrix - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 192 | 194 |  | Jimmy Cox
4449 | 194 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Create Requirements Traceability Matrix Template | 2 hrs | 3 days | Mon 7/3/23 | Thu 7/6/23 | 193 | 195 |  | Stacey Terry,Yogesh Deshmukh
4450 | 195 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Populate Requirements Traceability Matrix Template | 160 hrs | 10 days | Fri 7/7/23 | Thu 7/20/23 | 194 | 196 |  | Stacey Terry,Yogesh Deshmukh
4451 | 196 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Create Summary Document | 6 hrs | 2 days | Fri 7/21/23 | Mon 7/24/23 | 195 | 197 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4436 | 197 | Future Task |  |  | WP402 | Stacey Terry | Submit | WP WP402 - Requirements Traceability Matrix - Submit | 0 hrs | 0 days | Mon 7/24/23 | Mon 7/24/23 | 196 | 198 |  | Joy Schneider,Stacey Terry
4437 | 198 | Future Task |  |  | WP402 | Stacey Terry | Review | WP WP402 - Requirements Traceability Matrix - Collaborative Review & Update | 20 hrs | 10 days | Tue 7/25/23 | Mon 8/7/23 | 197 | 199 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4438 | 199 | Future Task |  |  | WP402 | Stacey Terry | Review | WP WP402 - Requirements Traceability Matrix - Final Review & Edits | 20 hrs | 5 days | Tue 8/8/23 | Mon 8/14/23 | 198 | 200 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4439 | 200 | Future Task |  |  | WP402 | Stacey Terry | Approve | WP WP402 - Requirements Traceability Matrix - Approve | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 199 | 727,201FS+5 days | 2023-06-01 | Jimmy Cox
7147 | 201 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Load Requirements in Requirements Traceability Tool | 10 hrs | 5 days | Tue 8/22/23 | Mon 8/28/23 | 200FS+5 days | 202 |  | Mary Punty,Joy Schneider
7148 | 202 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Validate Requirements in Requirements Traceability Tool | 10 hrs | 10 days | Tue 8/29/23 | Tue 9/12/23 | 201 |  |  | Deana Metcalf,Stacey Terry
4440 | 203 | Future Task |  |  | WP403 | Stacey Terry |  | WP403 - RICEFW Inventory | 200 hrs | 64 days | Mon 6/19/23 | Mon 9/18/23
4441 | 204 | Future Task |  |  | WP403 | Stacey Terry | Create | WPED WP403 - RICEFW Inventory - Create | 16 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 1 | 205 |  | Stacey Terry,Mary Punty
4442 | 205 | Future Task |  |  | WP403 | Stacey Terry | Submit | WPED WP403 - RICEFW Inventory - Submit | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 204 | 206 |  | Joy Schneider,Stacey Terry
4443 | 206 | Future Task |  |  | WP403 | Stacey Terry | Review | WPED WP403 - RICEFW Inventory - Review | 24 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 205 | 207 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4444 | 207 | Future Task |  |  | WP403 | Stacey Terry | Approve | WPED WP403 - RICEFW Inventory - Approve | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 206 | 208 |  | Jimmy Cox
4454 | 208 | Future Task |  |  | WP403 | Stacey Terry | Create | WP403 - Create RICEFW Inventory Template | 20 hrs | 5 days | Tue 7/18/23 | Mon 7/24/23 | 207 | 209 |  | Deana Metcalf,Stacey Terry
4455 | 209 | Future Task |  |  | WP403 | Stacey Terry | Create | WP403 - Define and document RICEFW Inventory | 50 hrs | 14 days | Tue 7/25/23 | Fri 8/11/23 | 208 | 210 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4456 | 210 | Future Task |  |  | WP403 | Stacey Terry | Create | WP403 - Populate RICEFW Inventory Template | 20 hrs | 5 days | Mon 8/14/23 | Fri 8/18/23 | 209 | 211 |  | Deana Metcalf,Stacey Terry
4457 | 211 | Future Task |  |  | WP403 | Stacey Terry | Create | WP403 - Create Summary Document | 30 hrs | 5 days | Mon 8/21/23 | Fri 8/25/23 | 210 | 212 |  | Deana Metcalf,Stacey Terry,Mary Punty
4445 | 212 | Future Task |  |  | WP403 | Stacey Terry | Submit | WP WP403 - RICEFW Inventory - Submit | 0 hrs | 0 days | Fri 8/25/23 | Fri 8/25/23 | 211 | 213 |  | Joy Schneider,Stacey Terry
4446 | 213 | Future Task |  |  | WP403 | Stacey Terry | Review | WP WP403 - RICEFW Inventory - Collaborative Review & Update | 20 hrs | 10 days | Mon 8/28/23 | Mon 9/11/23 | 212 | 214 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4447 | 214 | Future Task |  |  | WP403 | Stacey Terry | Review | WP WP403 - RICEFW Inventory - Final Review & Edits | 20 hrs | 5 days | Tue 9/12/23 | Mon 9/18/23 | 213 | 215 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4448 | 215 | Future Task |  |  | WP403 | Stacey Terry | Approve | WP WP403 - RICEFW Inventory - Approve | 0 hrs | 0 days | Mon 9/18/23 | Mon 9/18/23 | 214 |  | 2024-04-01 | Jimmy Cox
5667 | 216 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | WP404 - Data Conversion Inventory | 250 hrs | 127 days | Mon 8/7/23 | Thu 2/8/24
5668 | 217 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WPED WP404 - Data Conversion Inventory - Create | 16 hrs | 10 days | Mon 8/7/23 | Fri 8/18/23 | 1 | 218 |  | Manojkumar Gurjar,Kurt Meisner
5669 | 218 | Future Task |  |  | WP404 | Manojkumar Gurjar | Submit | WPED WP404 - Data Conversion Inventory - Submit | 0 hrs | 0 days | Fri 8/18/23 | Fri 8/18/23 | 217 | 219 |  | Manojkumar Gurjar,Joy Schneider
5670 | 219 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WPED WP404 - Data Conversion Inventory - Review | 24 hrs | 10 days | Mon 8/21/23 | Fri 9/1/23 | 218 | 220 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5671 | 220 | Future Task |  |  | WP404 | Manojkumar Gurjar | Approve | WPED WP404 - Data Conversion Inventory - Approve | 0 hrs | 0 days | Fri 9/1/23 | Fri 9/1/23 | 219 | 221FS+19 days |  | Jimmy Cox
5672 | 221 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WP404 - Create Data Conversion Inventory Template | 50 hrs | 32 days | Mon 10/2/23 | Wed 11/15/23 | 220FS+19 days,51 | 222 |  | Manojkumar Gurjar,Kurt Meisner
5673 | 222 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WP404 - Populate Data Conversion Inventory with RICEFW Inventory conversion items | 50 hrs | 16 days | Thu 11/16/23 | Mon 12/11/23 | 221 | 223 |  | Manojkumar Gurjar,Kurt Meisner
5674 | 223 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WP404 - Identify/confirm Anticipated Source Systems and Legacy Tables | 50 hrs | 20 days | Tue 12/12/23 | Wed 1/10/24 | 222 | 224 |  | Kurt Meisner,Manojkumar Gurjar
5675 | 224 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WP404 - Create Data Conversion Inventory Summary Document | 20 hrs | 5 days | Thu 1/11/24 | Thu 1/18/24 | 223 | 225 |  | Manojkumar Gurjar,Kurt Meisner
5676 | 225 | Future Task |  |  | WP404 | Manojkumar Gurjar | Submit | WP WP404 - Data Conversion Inventory - Submit | 0 hrs | 0 days | Thu 1/18/24 | Thu 1/18/24 | 224 | 226 |  | Manojkumar Gurjar,Joy Schneider
5677 | 226 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WP WP404 - Data Conversion Inventory - Collaborative Review & Update | 20 hrs | 10 days | Fri 1/19/24 | Thu 2/1/24 | 225 | 227 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5678 | 227 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WP WP404 - Data Conversion Inventory - Final Review & Edits | 20 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 226 | 228 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5679 | 228 | Future Task |  |  | WP404 | Manojkumar Gurjar | Approve | WP WP404 - Data Conversion Inventory - Approve | 0 hrs | 0 days | Thu 2/8/24 | Thu 2/8/24 | 227 |  | 2024-01-01 | Jimmy Cox
4458 | 229 | Future Task | Yes |  | WP405 | Stacey Terry |  | WP405 - Security Roles Matrix | 280 hrs | 115 days | Mon 2/19/24 | Tue 7/30/24
4459 | 230 | Future Task |  |  | WP405 | Stacey Terry | Create | WPED WP405 - Security Roles Matrix - Create | 16 hrs | 10 days | Mon 2/19/24 | Fri 3/1/24 | 1 | 231 |  | Stacey Terry,Mary Punty
4460 | 231 | Future Task |  |  | WP405 | Stacey Terry | Submit | WPED WP405 - Security Roles Matrix - Submit | 0 hrs | 0 days | Fri 3/1/24 | Fri 3/1/24 | 230 | 232 |  | Joy Schneider,Stacey Terry
4461 | 232 | Future Task |  |  | WP405 | Stacey Terry | Review | WPED WP405 - Security Roles Matrix - Review | 24 hrs | 10 days | Mon 3/4/24 | Fri 3/15/24 | 231 | 233 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4462 | 233 | Future Task |  |  | WP405 | Stacey Terry | Approve | WPED WP405 - Security Roles Matrix - Approve | 0 hrs | 0 days | Fri 3/15/24 | Fri 3/15/24 | 232 | 234FS+30 days |  | Jimmy Cox
4467 | 234 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Create Security Roles Matrix Template | 20 hrs | 5 days | Mon 4/29/24 | Fri 5/3/24 | 233FS+30 days | 235 |  | Stacey Terry,Yogesh Deshmukh
4468 | 235 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Design, Review, and Confirm Security Roles Matrix | 50 hrs | 20 days | Mon 5/6/24 | Mon 6/3/24 | 234 | 236 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4469 | 236 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Finalize Security Roles Matrix Design | 50 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 235 | 237 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4470 | 237 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Configure Security Roles and Permission Lists | 50 hrs | 15 days | Tue 6/11/24 | Mon 7/1/24 | 236 | 238 |  | Manojkumar Gurjar,Paul Jureidini
4471 | 238 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Create Security Roles Matrix Summary Document | 30 hrs | 5 days | Tue 7/2/24 | Tue 7/9/24 | 237 | 239 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4463 | 239 | Future Task |  |  | WP405 | Stacey Terry | Submit | WP WP405 - Security Roles Matrix - Submit | 0 hrs | 0 days | Tue 7/9/24 | Tue 7/9/24 | 238 | 240 |  | Joy Schneider,Stacey Terry
4464 | 240 | Future Task |  |  | WP405 | Stacey Terry | Review | WP WP405 - Security Roles Matrix - Collaborative Review & Update | 20 hrs | 10 days | Wed 7/10/24 | Tue 7/23/24 | 239 | 241 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4465 | 241 | Future Task |  |  | WP405 | Stacey Terry | Review | WP WP405 - Security Roles Matrix - Final Review & Edits | 20 hrs | 5 days | Wed 7/24/24 | Tue 7/30/24 | 240 | 242 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4466 | 242 | Future Task |  |  | WP405 | Stacey Terry | Approve | WP WP405 - Security Roles Matrix - Approve | 0 hrs | 0 days | Tue 7/30/24 | Tue 7/30/24 | 241 | 579 | 2024-07-01 | Jimmy Cox
5680 | 243 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | WP411 - Batch and Interface Procedures | 109 hrs | 114 days | Mon 9/30/24 | Fri 3/14/25
5681 | 244 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WPED WP411 - Batch and Interface Procedures - Create | 16 hrs | 10 days | Mon 9/30/24 | Fri 10/11/24 | 1 | 245 |  | Manojkumar Gurjar,Kurt Meisner
5682 | 245 | Future Task |  |  | WP411 | Manojkumar Gurjar | Submit | WPED WP411 - Batch and Interface Procedures - Submit | 0 hrs | 0 days | Fri 10/11/24 | Fri 10/11/24 | 244 | 246 |  | Manojkumar Gurjar,Joy Schneider
5683 | 246 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WPED WP411 - Batch and Interface Procedures - Review | 24 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 245 | 247 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5684 | 247 | Future Task |  |  | WP411 | Manojkumar Gurjar | Approve | WPED WP411 - Batch and Interface Procedures - Approve | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 246 | 248FS+22 days |  | Jimmy Cox
6701 | 248 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WP411 - Define Interface Procedures | 3 hrs | 28 days | Mon 12/2/24 | Fri 1/10/25 | 247FS+22 days | 249 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
6702 | 249 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WP411 - Create Batch Flow Diagram | 6 hrs | 9 days | Mon 1/13/25 | Fri 1/24/25 | 248 | 250 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
6703 | 250 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WP411 - Create Batch and Interface Procedures Document | 20 hrs | 20 days | Mon 1/27/25 | Fri 2/21/25 | 249 | 251 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
5685 | 251 | Future Task |  |  | WP411 | Manojkumar Gurjar | Submit | WP WP411 - Batch and Interface Procedures - Submit | 0 hrs | 0 days | Fri 2/21/25 | Fri 2/21/25 | 250 | 252 |  | Manojkumar Gurjar,Joy Schneider
5686 | 252 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WP WP411 - Batch and Interface Procedures - Collaborative Review & Update | 20 hrs | 10 days | Mon 2/24/25 | Fri 3/7/25 | 251 | 253 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5687 | 253 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WP WP411 - Batch and Interface Procedures - Final Review & Edits | 20 hrs | 5 days | Mon 3/10/25 | Fri 3/14/25 | 252 | 254 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5688 | 254 | Future Task |  |  | WP411 | Manojkumar Gurjar | Approve | WP WP411 - Batch and Interface Procedures - Approve | 0 hrs | 0 days | Fri 3/14/25 | Fri 3/14/25 | 253 |  |  | Jimmy Cox
6596 | 255 | Late |  |  | I-WP101 | Deana Metcalf |  | I-WP101 - Update Financials BPMs | 1,053.11 hrs | 299 days | Wed 4/26/23 | Mon 7/1/24
6597 | 256 | Complete |  |  | I-WP101 | Deana Metcalf | Create | Identify BPMs by module | 6 hrs | 3 days | Wed 4/26/23 | Fri 4/28/23 | 1 | 263264 |  | Deana Metcalf,Stacey Terry,Tiffany Porter,Janice Jackson,Brendan Jones
6598 | 257 | Late |  |  | I-WP101 | Deana Metcalf |  | WPED I-WP101 - Update Financials BPMs | 1,015.11 hrs | 274 days | Mon 5/1/23 | Thu 5/30/24
6599 | 258 | Complete |  |  | I-WP101 | Deana Metcalf | Create | WPED I-WP101 - Update Financials BPMs - Create | 3 hrs | 6 days | Mon 5/15/23 | Mon 5/22/23 | 1 | 259 |  | Deana Metcalf
6600 | 259 | Complete |  |  | I-WP101 | Deana Metcalf | Submit | WPED I-WP101 - Update Financials BPMs - Submit | 0 hrs | 0 days | Mon 5/22/23 | Mon 5/22/23 | 258 | 260 |  | Deana Metcalf
6601 | 260 | Complete |  |  | I-WP101 | Deana Metcalf | Review | WPED I-WP101 - Update Financials BPMs - Collaborative Review & Update | 1.11 hrs | 1 day | Tue 5/23/23 | Tue 5/23/23 | 259 | 261 |  | Tiffany Porter,Janice Jackson,Brendan Jones,Angie Robertson,Jimmy Cox,Deana Metcalf
6602 | 261 | Complete |  |  | I-WP101 | Deana Metcalf | Approve | WPED I-WP101 - Update Financials BPMs - Approve | 0 hrs | 0 days | Tue 5/23/23 | Tue 5/23/23 | 260 |  |  | Jimmy Cox
6603 | 262 | Late | Yes |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment I - Financials Wave Business Process Models | 170 hrs | 86 days | Mon 5/1/23 | Wed 8/30/23
6604 | 263 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - May | 20 hrs | 22 days | Mon 5/1/23 | Wed 5/31/23 | 256 | 265 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6605 | 264 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - May | 20 hrs | 22 days | Mon 5/1/23 | Wed 5/31/23 | 256 | 266 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6606 | 265 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - June | 20 hrs | 22 days | Thu 6/1/23 | Fri 6/30/23 | 263 | 267 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6607 | 266 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - June | 20 hrs | 22 days | Thu 6/1/23 | Fri 6/30/23 | 264 | 268 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6608 | 267 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - July | 20 hrs | 20 days | Mon 7/3/23 | Mon 7/31/23 | 265 | 269 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6609 | 268 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - July | 20 hrs | 20 days | Mon 7/3/23 | Mon 7/31/23 | 266 | 269 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6610 | 269 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment I - Submit | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 267268 | 270275276277 |  | Deana Metcalf
6611 | 270 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment I - Collaborative Review & Update | 20 hrs | 4 days | Tue 8/1/23 | Fri 8/4/23 | 269 | 271 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6789 | 271 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment I - Advisory Council Review & Updates | 14 hrs | 12 days | Mon 8/7/23 | Tue 8/22/23 | 270 | 272 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson,Dusti Kincl
6612 | 272 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment I - Style Guide Updates | 2 hrs | 1 day | Wed 8/23/23 | Wed 8/23/23 | 271 | 273 |  | Dusti Kincl
6613 | 273 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment I - Final Review & Update | 14 hrs | 5 days | Thu 8/24/23 | Wed 8/30/23 | 272 | 328 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson,Jimmy Cox
6614 | 274 | Future Task | Yes |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment II - Financials Wave Business Process Models | 270 hrs | 85 days | Tue 8/1/23 | Fri 12/1/23
6615 | 275 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - August | 20 hrs | 23 days | Tue 8/1/23 | Thu 8/31/23 | 269 | 278 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6616 | 276 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - August | 20 hrs | 23 days | Tue 8/1/23 | Thu 8/31/23 | 269 | 279 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6617 | 277 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - August | 20 hrs | 23 days | Tue 8/1/23 | Thu 8/31/23 | 269 | 280 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6618 | 278 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - September | 20 hrs | 20 days | Fri 9/1/23 | Fri 9/29/23 | 275 | 281284285 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6619 | 279 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - September | 20 hrs | 20 days | Fri 9/1/23 | Fri 9/29/23 | 276 | 282 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6620 | 280 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - September | 20 hrs | 20 days | Fri 9/1/23 | Fri 9/29/23 | 277 | 283 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6621 | 281 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - October | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 278 | 286 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6622 | 282 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - October | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 279 | 286 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6623 | 283 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - October | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 280 | 286 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6624 | 284 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment LMC models Impacted by Segment II | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 278 | 286 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6625 | 285 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment PPA models Impacted by Segment II | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 278 | 286 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6626 | 286 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment II - Submit | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 281282283284285 | 287,292FS+2 days,293FS+2 days,294FS+2 days |  | Deana Metcalf
6627 | 287 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment II - Collaborative Review & Update | 20 hrs | 5 days | Mon 10/30/23 | Fri 11/3/23 | 286 | 288 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6790 | 288 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment II - Advisory Council Review & Updates | 14 hrs | 11 days | Mon 11/6/23 | Tue 11/21/23 | 287 | 289 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6628 | 289 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment II - Style Guide Updates | 2 hrs | 1 day | Wed 11/22/23 | Wed 11/22/23 | 288 | 290 |  | Dusti Kincl
6629 | 290 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment II - Final Review & Update | 14 hrs | 5 days | Mon 11/27/23 | Fri 12/1/23 | 289 | 328 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson,Jimmy Cox
6630 | 291 | Future Task | Yes |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment III - Financials Wave Business Process Models | 296 hrs | 85 days | Wed 11/1/23 | Wed 3/6/24
6631 | 292 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - November | 20 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23 | 286FS+2 days | 295 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6632 | 293 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - November | 20 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23 | 286FS+2 days | 296 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6633 | 294 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - November | 20 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23 | 286FS+2 days | 297 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6634 | 295 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - December | 20 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23 | 292 | 298301 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6635 | 296 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - December | 20 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23 | 293 | 299302 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6636 | 297 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - December | 20 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23 | 294 | 300303 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6637 | 298 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - January | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 295 | 304 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6638 | 299 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - January | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 296 | 304 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6639 | 300 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - January | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 297 | 304 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6640 | 301 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior LMC segment models Impacted by Segment III | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 295 | 304 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6641 | 302 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior PPA segment models Impacted by Segment III | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 296 | 304 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6642 | 303 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior TRP segment models Impacted by Segment III | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 297 | 304 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6643 | 304 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment III - Submit | 0 hrs | 0 days | Fri 1/26/24 | Fri 1/26/24 | 2.983e+17 | 305,310FS+3 days,311FS+3 days,312FS+3 days |  | Deana Metcalf
6644 | 305 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment III - Collaborative Review & Update | 20 hrs | 5 days | Mon 1/29/24 | Fri 2/2/24 | 304 | 306 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6792 | 306 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment III - Advisory Council Review & Updates | 20 hrs | 17 days | Mon 2/5/24 | Tue 2/27/24 | 305 | 307 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6645 | 307 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment III - Style Guide Updates | 2 hrs | 1 day | Wed 2/28/24 | Wed 2/28/24 | 306 | 308 |  | Dusti Kincl
6646 | 308 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment III - Final Review & Update | 14 hrs | 5 days | Thu 2/29/24 | Wed 3/6/24 | 307 | 328 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson,Jimmy Cox
6647 | 309 | Future Task | Yes |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment IV - Financials Wave Business Process Models | 275 hrs | 85 days | Thu 2/1/24 | Thu 5/30/24
6648 | 310 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - February | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 304FS+3 days | 313 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6649 | 311 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - February | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 304FS+3 days | 314 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6650 | 312 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - February | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 304FS+3 days | 315 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6651 | 313 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - March | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 310 | 316319 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6652 | 314 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - March | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 311 | 317320 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6653 | 315 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - March | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 312 | 318321 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6654 | 316 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - April | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 313 | 322 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6655 | 317 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - April | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 314 | 322 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6656 | 318 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - April | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 315 | 322 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6657 | 319 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior LMC segment models Impacted by Segment IV | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 313 | 322 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6658 | 320 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior PPA segment models Impacted by Segment IV | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 314 | 322 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6659 | 321 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior TRP segment models Impacted by Segment IV | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 315 | 322 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6660 | 322 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment IV - Submit | 0 hrs | 0 days | Fri 4/26/24 | Fri 4/26/24 | 3.1632e+17 | 323 |  | Deana Metcalf
7203 | 323 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment IV - Advisory Council Review & Updates | 8 hrs | 5 days | Mon 4/29/24 | Fri 5/3/24 | 322 | 324 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6661 | 324 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment IV - Collaborative Review & Update | 10 hrs | 12 days | Mon 5/6/24 | Tue 5/21/24 | 323 | 325 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6662 | 325 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment IV - Style Guide Updates | 2 hrs | 1 day | Wed 5/22/24 | Wed 5/22/24 | 324 | 326 |  | Dusti Kincl
6663 | 326 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment IV - Final Review & Update | 15 hrs | 5 days | Thu 5/23/24 | Thu 5/30/24 | 325 | 328 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson,Jimmy Cox
6664 | 327 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 - Update Financials BPMs Review Tasks | 32 hrs | 22 days | Thu 5/30/24 | Mon 7/1/24
6665 | 328 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | WP I-WP101 - Update Financials BPMs - Submit | 0 hrs | 0 days | Thu 5/30/24 | Thu 5/30/24 | 273290308326 | 329 |  | Deana Metcalf
6666 | 329 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WP I-WP101 - Update Financials BPMs - Department QC | 2 hrs | 1 day | Fri 5/31/24 | Fri 5/31/24 | 328 | 330 |  | Gabriela Gibson
6667 | 330 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WP I-WP101 - Update Financials BPMs - Collaborative Review & Update | 20 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 329 | 331 |  | Deana Metcalf,Stacey Terry,Tiffany Porter,Janice Jackson,Brendan Jones
6668 | 331 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WP I-WP101 - Update Financials BPMs - Style Guide Review | 2 hrs | 1 day | Mon 6/17/24 | Mon 6/17/24 | 330 | 332 |  | Dusti Kincl
6669 | 332 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WP I-WP101 - Update Financials BPMs - Final Review & Update | 8 hrs | 10 days | Tue 6/18/24 | Mon 7/1/24 | 331 | 333 |  | Jimmy Cox,Angie Robertson
6670 | 333 | Future Task |  |  | I-WP101 | Deana Metcalf | Approve | WP I-WP101 - Update Financials BPMs - Approve | 0 hrs | 0 days | Mon 7/1/24 | Mon 7/1/24 | 332 |  |  | Jimmy Cox
6671 | 334 | Future Task |  |  | I-WP125 | Deana Metcalf |  | I-WP125 - Updated D66 Chart of Accounts Design | 214 hrs | 63 days | Mon 6/5/23 | Thu 8/31/23
6672 | 335 | Future Task |  |  | I-WP125 | Deana Metcalf | Create | WPED I-WP125 - Update D66 Chart of Accounts Design - Create | 2 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1 | 336 |  | Deana Metcalf
6673 | 336 | Future Task |  |  | I-WP125 | Deana Metcalf | Submit | WPED I-WP125 - Update D66 Chart of Accounts Design - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 335 | 337 |  | Deana Metcalf
6674 | 337 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WPED I-WP125 - Update D66 Chart of Accounts Design - Collaborative Review & Update | 8 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 336 | 338 |  | Janice Jackson,LaWanda Warren,Robert Hicks,Tommy Werner
6675 | 338 | Future Task |  |  | I-WP125 | Deana Metcalf | Approve | WPED I-WP125 - Update D66 Chart of Accounts Design - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 337 | 339 |  | Angie Robertson,Jimmy Cox
6676 | 339 | Future Task |  | RW | I-WP125 | Deana Metcalf | Create | I-WP125 Update D66 Chart of Accounts Design <Activities per WPED> | 100 hrs | 26 days | Mon 7/3/23 | Tue 8/8/23 | 338 | 340 |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp
6677 | 340 | Future Task |  |  | I-WP125 | Deana Metcalf | Submit | WP I-WP125 - Update D66 Chart of Accounts Design - Submit | 0 hrs | 0 days | Tue 8/8/23 | Tue 8/8/23 | 339 | 341 |  | Janice Jackson
6678 | 341 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WP I-WP125 - Update D66 Chart of Accounts Design - Department QC | 1 hr | 1 day | Wed 8/9/23 | Wed 8/9/23 | 340 | 342 |  | Gabriela Gibson
6679 | 342 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WP I-WP125 - Update D66 Chart of Accounts Design - Collaborative Review & Update | 100 hrs | 10 days | Thu 8/10/23 | Wed 8/23/23 | 341 | 343 |  | Deana Metcalf,Janice Jackson,Jennifer Reeves,Angie Robertson
6680 | 343 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WP I-WP125 - Update D66 Chart of Accounts Design - Style Guide Review | 1 hr | 1 day | Thu 8/24/23 | Thu 8/24/23 | 342 | 344 |  | Tatiana Eubanks
6681 | 344 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WP I-WP125 - Update D66 Chart of Accounts Design - Final Review & Update | 2 hrs | 5 days | Fri 8/25/23 | Thu 8/31/23 | 343 | 345 |  | Angie Robertson,Jimmy Cox
6682 | 345 | Future Task |  |  | I-WP125 | Deana Metcalf | Approve | WP I-WP125 - Update D66 Chart of Accounts Design - Approve | 0 hrs | 0 days | Thu 8/31/23 | Thu 8/31/23 | 344 |  |  | Jimmy Cox
3770 | 346 | Future Task | [5 empty] | Build | 3,763 hrs | 618 days | Mon 7/10/23 | Fri 12/19/25
5534 | 347 | Future Task | Yes |  | D642 | Jarad Hermann |  | D642 - Updated Technical Architecture Design | 169 hrs | 98 days | Tue 9/5/23 | Fri 1/26/24
5535 | 348 | Future Task |  |  | D642 | Jarad Hermann | Create | DED D642 - Updated Technical Architecture Design - Create | 8 hrs | 10 days | Tue 9/5/23 | Mon 9/18/23 | 1FS+91 days | 349 |  | Jarad Hermann,Manojkumar Gurjar
5536 | 349 | Future Task |  |  | D642 | Jarad Hermann | Submit | DED D642 - Updated Technical Architecture Design - Submit | 0 hrs | 0 days | Mon 9/18/23 | Mon 9/18/23 | 348 | 350 |  | Jarad Hermann,Joy Schneider
5537 | 350 | Future Task |  |  | D642 | Jarad Hermann | Review | DED D642 - Updated Technical Architecture Design - Collaborative Review | 24 hrs | 10 days | Tue 9/19/23 | Mon 10/2/23 | 349 | 351 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5538 | 351 | Future Task |  |  | D642 | Jarad Hermann | Approve | DED D642 - Updated Technical Architecture Design - Approve | 0 hrs | 0 days | Mon 10/2/23 | Mon 10/2/23 | 350 | 352FS+21 days |  | Jimmy Cox
5539 | 352 | Future Task |  |  | D642 | Jarad Hermann | Create | D642 - Confirm content to be migrated from D80 | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 351FS+21 days | 353SS,354SS,355SS |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5540 | 353 | Future Task |  |  | D642 | Jarad Hermann | Create | D642 - Review, update, & document run time architecture design | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 352SS | 356 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5541 | 354 | Future Task |  |  | D642 | Jarad Hermann | Create | D642 - Review, update, and document development and operational architecture design | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 352SS | 356 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5542 | 355 | Future Task |  |  | D642 | Jarad Hermann | Create | D642 - Review, update, and document architecture blueprint diagrams | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 352SS | 356 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5543 | 356 | Future Task |  |  | D642 | Jarad Hermann | Submit | DEL D642 - Updated Technical Architecture Design - Draft Submission | 0 hrs | 0 days | Tue 1/2/24 | Tue 1/2/24 | 355353354 | 357 |  | Jarad Hermann,Joy Schneider
5544 | 357 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Pre-Submission Collaborative Review | 20 hrs | 5 days | Wed 1/3/24 | Tue 1/9/24 | 356 | 358 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
5545 | 358 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Style Guide Review | 1 hr | 1 day | Wed 1/10/24 | Wed 1/10/24 | 357 | 359 |  | Dusti Kincl
5546 | 359 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Final Collaborative Review | 20 hrs | 5 days | Thu 1/11/24 | Thu 1/18/24 | 358 | 360 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
5547 | 360 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Accenture QC | 4 hrs | 2 days | Fri 1/19/24 | Mon 1/22/24 | 359 | 361 |  | Joy Schneider
5548 | 361 | Future Task |  |  | D642 | Jarad Hermann | Submit | DEL D642 - Updated Technical Architecture Design - Submit | 0 hrs | 0 days | Mon 1/22/24 | Mon 1/22/24 | 360 | 362 |  | Joy Schneider
5549 | 362 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Department QC | 4 hrs | 1 day | Tue 1/23/24 | Tue 1/23/24 | 361 | 363 |  | Tommy Werner,Gabriela Gibson
5550 | 363 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Contract Manager Review | 8 hrs | 3 days | Wed 1/24/24 | Fri 1/26/24 | 362 | 364 |  | Sean Buchanan
5551 | 364 | Future Task |  |  | D642 | Jarad Hermann | Accept | DEL D642 - Updated Technical Architecture Design - Accept | 0 hrs | 0 days | Fri 1/26/24 | Fri 1/26/24 | 363 |  | 2024-03-01 | Sean Buchanan
4486 | 365 | Future Task | Yes |  | D646 | Manojkumar Gurjar |  | D646 - Completion of Build Segment I | 257 hrs | 156 days | Mon 9/18/23 | Tue 4/30/24
4487 | 366 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | DED D646 - Completion of Build Segment I - Create | 16 hrs | 10 days | Mon 9/18/23 | Fri 9/29/23 |  | 367 |  | Manojkumar Gurjar,Kurt Meisner
4488 | 367 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DED D646 - Completion of Build Segment I - Submit | 0 hrs | 0 days | Fri 9/29/23 | Fri 9/29/23 | 366 | 368 |  | Manojkumar Gurjar,Joy Schneider
4489 | 368 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DED D646 - Completion of Build Segment I - Collaborative Review | 24 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 367 | 369 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4490 | 369 | Future Task |  |  | D646 | Manojkumar Gurjar | Approve | DED D646 - Completion of Build Segment I - Approve | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 368 | 370FS+19 days |  | Jimmy Cox
4500 | 370 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Identify RICEFW items for Build Segment I | 20 hrs | 8 days | Mon 11/13/23 | Wed 11/22/23 | 369FS+19 days | 371 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4501 | 371 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Create Work Unit Tracker for Build Segment I | 20 hrs | 5 days | Mon 11/27/23 | Fri 12/1/23 | 370 | 372 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4502 | 372 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Review, Update and Confirm Work Unit Tracker for Build Segment I | 20 hrs | 10 days | Mon 12/4/23 | Fri 12/15/23 | 371 | 373 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4503 | 373 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Conduct Kick-Off meeting for Build Segment I | 20 hrs | 9 days | Mon 12/18/23 | Fri 12/29/23 | 372 | 374 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4504 | 374 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Build and Unit Test RICEFW for Build Segment I - Group 1 | 20 hrs | 21 days | Tue 1/2/24 | Wed 1/31/24 | 373 | 375 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4505 | 375 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Build and Unit Test RICEFW for Build Segment I - Group 2 | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 374 | 376 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4506 | 376 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Build and Unit Test RICEFW for Build Segment I - Group 3 | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 375 | 377FS-5 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4507 | 377 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Create Summary Document for Build Segment I | 20 hrs | 10 days | Mon 3/25/24 | Fri 4/5/24 | 376FS-5 days | 378 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4491 | 378 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DEL D646 - Completion of Build Segment I - Draft Submission | 0 hrs | 0 days | Fri 4/5/24 | Fri 4/5/24 | 377 | 379 |  | Manojkumar Gurjar,Joy Schneider
4492 | 379 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 4/8/24 | Fri 4/12/24 | 378 | 380 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4493 | 380 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Style Guide Review | 1 hr | 1 day | Mon 4/15/24 | Mon 4/15/24 | 379 | 381 |  | Dusti Kincl
4494 | 381 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Final Collaborative Review | 20 hrs | 5 days | Tue 4/16/24 | Mon 4/22/24 | 380 | 382 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4495 | 382 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Accenture QC | 4 hrs | 2 days | Tue 4/23/24 | Wed 4/24/24 | 381 | 383 |  | Joy Schneider
4496 | 383 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DEL D646 - Completion of Build Segment I - Submit | 0 hrs | 0 days | Wed 4/24/24 | Wed 4/24/24 | 382 | 384 |  | Joy Schneider
4497 | 384 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Department QC | 4 hrs | 1 day | Thu 4/25/24 | Thu 4/25/24 | 383 | 385 |  | Tommy Werner,Gabriela Gibson
4498 | 385 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Contract Manager Review | 8 hrs | 3 days | Fri 4/26/24 | Tue 4/30/24 | 384 | 386 |  | Sean Buchanan
4499 | 386 | Future Task |  |  | D646 | Manojkumar Gurjar | Accept | DEL D646 - Completion of Build Segment I - Accept | 0 hrs | 0 days | Tue 4/30/24 | Tue 4/30/24 | 385 | 594600 | 2024-04-01 | Sean Buchanan
4629 | 387 | Future Task | Yes |  | D647 | Manojkumar Gurjar |  | D647 - Establish DW/BI Environments | 149 hrs | 96 days | Tue 1/2/24 | Wed 5/15/24
4630 | 388 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | DED D647 - Establish DW/BI Environments - Create | 8 hrs | 10 days | Tue 1/2/24 | Tue 1/16/24 | 1 | 389 |  | Jarad Hermann,Manojkumar Gurjar
4631 | 389 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DED D647 - Establish DW/BI Environments - Submit | 0 hrs | 0 days | Tue 1/16/24 | Tue 1/16/24 | 388 | 390 |  | Manojkumar Gurjar,Joy Schneider
4632 | 390 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DED D647 - Establish DW/BI Environments - Collaborative Review | 24 hrs | 10 days | Wed 1/17/24 | Tue 1/30/24 | 389 | 391 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4633 | 391 | Future Task |  |  | D647 | Manojkumar Gurjar | Approve | DED D647 - Establish DW/BI Environments - Approve | 0 hrs | 0 days | Tue 1/30/24 | Tue 1/30/24 | 390 | 392 |  | Jimmy Cox
4643 | 392 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | D647 - Establish DW/BI Environment Connections | 20 hrs | 19 days | Wed 1/31/24 | Mon 2/26/24 | 391 | 393 |  | Jarad Hermann,Manojkumar Gurjar
4644 | 393 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | D647 - Environment build and stand up | 20 hrs | 20 days | Tue 2/27/24 | Mon 3/25/24 | 392 | 394 |  | Jarad Hermann,Manojkumar Gurjar
4645 | 394 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | D647 - Verify access to DW/BI Environments | 20 hrs | 20 days | Tue 3/26/24 | Mon 4/22/24 | 393 | 395 |  | Jarad Hermann,Manojkumar Gurjar
4634 | 395 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DEL D647 - Establish DW/BI Environments - Draft Submission | 0 hrs | 0 days | Mon 4/22/24 | Mon 4/22/24 | 394 | 396 |  | Manojkumar Gurjar,Joy Schneider
4635 | 396 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 4/23/24 | Mon 4/29/24 | 395 | 397 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
4636 | 397 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Style Guide Review | 1 hr | 1 day | Tue 4/30/24 | Tue 4/30/24 | 396 | 398 |  | Dusti Kincl
4637 | 398 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Final Collaborative Review | 20 hrs | 5 days | Wed 5/1/24 | Tue 5/7/24 | 397 | 399 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
4638 | 399 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Accenture QC | 4 hrs | 2 days | Wed 5/8/24 | Thu 5/9/24 | 398 | 400 |  | Joy Schneider
4639 | 400 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DEL D647 - Establish DW/BI Environments - Submit | 0 hrs | 0 days | Thu 5/9/24 | Thu 5/9/24 | 399 | 401 |  | Joy Schneider
4640 | 401 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Department QC | 4 hrs | 1 day | Fri 5/10/24 | Fri 5/10/24 | 400 | 402 |  | Tommy Werner,Gabriela Gibson
4641 | 402 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Contract Manager Review | 8 hrs | 3 days | Mon 5/13/24 | Wed 5/15/24 | 401 | 403 |  | Sean Buchanan
4642 | 403 | Future Task |  |  | D647 | Manojkumar Gurjar | Accept | DEL D647 - Establish DW/BI Environments - Accept | 0 hrs | 0 days | Wed 5/15/24 | Wed 5/15/24 | 402 |  | 2024-05-01 | Sean Buchanan
4508 | 404 | Future Task | Yes |  | D648 | Manojkumar Gurjar |  | D648 - Completion of Build Segment II | 197 hrs | 110 days | Mon 2/12/24 | Tue 7/16/24
4509 | 405 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | DED D648 - Completion of Build Segment II - Create | 16 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 |  | 406 |  | Manojkumar Gurjar,Kurt Meisner
4510 | 406 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DED D648 - Completion of Build Segment II - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 405 | 407 |  | Manojkumar Gurjar,Joy Schneider
4511 | 407 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DED D648 - Completion of Build Segment II - Collaborative Review | 24 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 406 | 408 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4512 | 408 | Future Task |  |  | D648 | Manojkumar Gurjar | Approve | DED D648 - Completion of Build Segment II - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 407 | 409FS+20 days |  | Jimmy Cox
4536 | 409 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Create Work Unit Tracker for Build Segment II | 20 hrs | 7 days | Mon 4/8/24 | Tue 4/16/24 | 408FS+20 days | 410 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4537 | 410 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Review, Update and Confirm Work Unit Tracker for Build Segment II | 20 hrs | 8 days | Wed 4/17/24 | Fri 4/26/24 | 409 | 411 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4538 | 411 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Build and Unit Test RICEFW for Build Segment II - Group 1 | 20 hrs | 19 days | Mon 4/29/24 | Thu 5/23/24 | 410 | 412 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4539 | 412 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Build and Unit Test RICEFW for Build Segment II - Group 2 | 20 hrs | 19 days | Fri 5/24/24 | Thu 6/20/24 | 411 | 413FS-9 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4540 | 413 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Create Summary Document for Build Segment II | 20 hrs | 9 days | Mon 6/10/24 | Thu 6/20/24 | 412FS-9 days | 414 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4513 | 414 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DEL D648 - Completion of Build Segment II - Draft Submission | 0 hrs | 0 days | Thu 6/20/24 | Thu 6/20/24 | 413 | 415 |  | Manojkumar Gurjar,Joy Schneider
4514 | 415 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 6/21/24 | Thu 6/27/24 | 414 | 416 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4515 | 416 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Style Guide Review | 1 hr | 1 day | Fri 6/28/24 | Fri 6/28/24 | 415 | 417 |  | Dusti Kincl
4516 | 417 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Final Collaborative Review | 20 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 416 | 418 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4517 | 418 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Accenture QC | 4 hrs | 2 days | Tue 7/9/24 | Wed 7/10/24 | 417 | 419 |  | Joy Schneider
4518 | 419 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DEL D648 - Completion of Build Segment II - Submit | 0 hrs | 0 days | Wed 7/10/24 | Wed 7/10/24 | 418 | 420 |  | Joy Schneider
4519 | 420 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Department QC | 4 hrs | 1 day | Thu 7/11/24 | Thu 7/11/24 | 419 | 421 |  | Tommy Werner,Gabriela Gibson
4520 | 421 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Contract Manager Review | 8 hrs | 3 days | Fri 7/12/24 | Tue 7/16/24 | 420 | 422 |  | Sean Buchanan
4521 | 422 | Future Task |  |  | D648 | Manojkumar Gurjar | Accept | DEL D648 - Completion of Build Segment II - Accept | 0 hrs | 0 days | Tue 7/16/24 | Tue 7/16/24 | 421 | 600 | 2024-07-01 | Sean Buchanan
4522 | 423 | Future Task | Yes |  | D649 | Manojkumar Gurjar |  | D649 - Completion of Build Segment III | 217 hrs | 124 days | Mon 5/6/24 | Tue 10/29/24
4523 | 424 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | DED D649 - Completion of Build Segment III - Create | 16 hrs | 10 days | Mon 5/6/24 | Fri 5/17/24 |  | 425 |  | Manojkumar Gurjar,Kurt Meisner
4524 | 425 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DED D649 - Completion of Build Segment III - Submit | 0 hrs | 0 days | Fri 5/17/24 | Fri 5/17/24 | 424 | 426 |  | Manojkumar Gurjar,Joy Schneider
4525 | 426 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DED D649 - Completion of Build Segment III - Collaborative Review | 24 hrs | 10 days | Mon 5/20/24 | Mon 6/3/24 | 425 | 427 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4526 | 427 | Future Task |  |  | D649 | Manojkumar Gurjar | Approve | DED D649 - Completion of Build Segment III - Approve | 0 hrs | 0 days | Mon 6/3/24 | Mon 6/3/24 | 426 | 428FS+23 days |  | Jimmy Cox
4541 | 428 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Identify RICEFW items for Build Segment III | 20 hrs | 10 days | Mon 7/8/24 | Fri 7/19/24 | 427FS+23 days | 429 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4542 | 429 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Create Work Unit Tracker for Build Segment III | 20 hrs | 5 days | Mon 7/22/24 | Fri 7/26/24 | 428 | 430 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4543 | 430 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Review, Update and Confirm Work Unit Tracker for Build Segment III | 20 hrs | 10 days | Mon 7/29/24 | Fri 8/9/24 | 429 | 431 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4544 | 431 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Build and Unit Test RICEFW for Build Segment III - Group 1 | 20 hrs | 19 days | Mon 8/12/24 | Fri 9/6/24 | 430 | 432 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4545 | 432 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Build and Unit Test RICEFW for Build Segment III - Group 2 | 20 hrs | 20 days | Mon 9/9/24 | Fri 10/4/24 | 431 | 433FS-10 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4546 | 433 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Create Summary Document for Build Segment III | 20 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 432FS-10 days | 434 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4527 | 434 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DEL D649 - Completion of Build Segment III - Draft Submission | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 433 | 435 |  | Manojkumar Gurjar,Joy Schneider
4528 | 435 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 | 434 | 436 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4529 | 436 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Style Guide Review | 1 hr | 1 day | Mon 10/14/24 | Mon 10/14/24 | 435 | 437 |  | Dusti Kincl
4530 | 437 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Final Collaborative Review | 20 hrs | 5 days | Tue 10/15/24 | Mon 10/21/24 | 436 | 438 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4531 | 438 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Accenture QC | 4 hrs | 2 days | Tue 10/22/24 | Wed 10/23/24 | 437 | 439 |  | Joy Schneider
4532 | 439 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DEL D649 - Completion of Build Segment III - Submit | 0 hrs | 0 days | Wed 10/23/24 | Wed 10/23/24 | 438 | 440 |  | Joy Schneider
4533 | 440 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Department QC | 4 hrs | 1 day | Thu 10/24/24 | Thu 10/24/24 | 439 | 441 |  | Tommy Werner,Gabriela Gibson
4534 | 441 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Contract Manager Review | 8 hrs | 3 days | Fri 10/25/24 | Tue 10/29/24 | 440 | 442 |  | Sean Buchanan
4535 | 442 | Future Task |  |  | D649 | Manojkumar Gurjar | Accept | DEL D649 - Completion of Build Segment III - Accept | 0 hrs | 0 days | Tue 10/29/24 | Tue 10/29/24 | 441 | 600 | 2024-10-01 | Sean Buchanan
4547 | 443 | Future Task | Yes |  | D653 | Manojkumar Gurjar |  | D653 - Completion of Build Segment I DW/BI | 297 hrs | 147 days | Mon 6/3/24 | Thu 1/2/25
4548 | 444 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | DED D653 - Completion of Build Segment I DW/BI - Create | 16 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 1 | 445 |  | Manojkumar Gurjar,Kurt Meisner
4549 | 445 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DED D653 - Completion of Build Segment I DW/BI - Submit | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 444 | 446 |  | Manojkumar Gurjar,Joy Schneider
4550 | 446 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DED D653 - Completion of Build Segment I DW/BI - Collaborative Review | 24 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 445 | 447 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4551 | 447 | Future Task |  |  | D653 | Manojkumar Gurjar | Approve | DED D653 - Completion of Build Segment I DW/BI - Approve | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 446 | 448 |  | Jimmy Cox
4575 | 448 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Identify RICEFW items for Build Segment I DW/BI | 36 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 447 | 449 |  | Manojkumar Gurjar,Kurt Meisner
4576 | 449 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Create Work Unit Tracker for Build Segment I DW/BI | 20 hrs | 5 days | Mon 7/15/24 | Fri 7/19/24 | 448 | 450 |  | Manojkumar Gurjar,Kurt Meisner
4577 | 450 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Review, Update and Confirm Work Unit Tracker for Build Segment I DW/BI | 40 hrs | 10 days | Mon 7/22/24 | Fri 8/2/24 | 449 | 451 |  | Manojkumar Gurjar,Kurt Meisner
4578 | 451 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Conduct Kick-Off meeting for Build Segment I DW/BI | 40 hrs | 5 days | Mon 8/5/24 | Fri 8/9/24 | 450 | 452 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4579 | 452 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Build and Unit Test RICEFW for Build Segment I DW/BI - Group 1 | 20 hrs | 19 days | Mon 8/12/24 | Fri 9/6/24 | 451 | 453 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4580 | 453 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Build and Unit Test RICEFW for Build Segment I DW/BI - Group 2 | 20 hrs | 20 days | Mon 9/9/24 | Fri 10/4/24 | 452 | 454 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4581 | 454 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Build and Unit Test RICEFW for Build Segment I DW/BI - Group 3 | 20 hrs | 20 days | Mon 10/7/24 | Fri 11/1/24 | 453 | 455 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4582 | 455 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Create Summary Document for Build Segment I DW/BI | 4 hrs | 22 days | Mon 11/4/24 | Fri 12/6/24 | 454 | 456 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4552 | 456 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DEL D653 - Completion of Build Segment I DW/BI - Draft Submission | 0 hrs | 0 days | Fri 12/6/24 | Fri 12/6/24 | 455 | 457 |  | Manojkumar Gurjar,Joy Schneider
4553 | 457 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 12/9/24 | Fri 12/13/24 | 456 | 458 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4554 | 458 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Style Guide Review | 1 hr | 1 day | Mon 12/16/24 | Mon 12/16/24 | 457 | 459 |  | Dusti Kincl
4555 | 459 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Final Collaborative Review | 20 hrs | 5 days | Tue 12/17/24 | Mon 12/23/24 | 458 | 460 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4556 | 460 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Accenture QC | 4 hrs | 2 days | Tue 12/24/24 | Thu 12/26/24 | 459 | 461 | Holiday | Joy Schneider
4557 | 461 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DEL D653 - Completion of Build Segment I DW/BI - Submit | 0 hrs | 0 days | Thu 12/26/24 | Thu 12/26/24 | 460 | 462 |  | Joy Schneider
4558 | 462 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Department QC | 4 hrs | 1 day | Fri 12/27/24 | Fri 12/27/24 | 461 | 463 |  | Tommy Werner,Gabriela Gibson
4559 | 463 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Contract Manager Review | 8 hrs | 3 days | Mon 12/30/24 | Thu 1/2/25 | 462 | 464 |  | Sean Buchanan
4560 | 464 | Future Task |  |  | D653 | Manojkumar Gurjar | Accept | DEL D653 - Completion of Build Segment I DW/BI - Accept | 0 hrs | 0 days | Thu 1/2/25 | Thu 1/2/25 | 463 | 600 | 2025-01-01 | Sean Buchanan
4561 | 465 | Future Task | Yes |  | D654 | Manojkumar Gurjar |  | D654 - Completion of Build Segment IV | 217 hrs | 122 days | Mon 8/5/24 | Thu 1/30/25
4562 | 466 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | DED D654 - Completion of Build Segment IV - Create | 16 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 1 | 467 |  | Manojkumar Gurjar,Kurt Meisner
4563 | 467 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DED D654 - Completion of Build Segment IV - Submit | 0 hrs | 0 days | Fri 8/16/24 | Fri 8/16/24 | 466 | 468 |  | Manojkumar Gurjar,Joy Schneider
4564 | 468 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DED D654 - Completion of Build Segment IV - Collaborative Review | 24 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 467 | 469 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4565 | 469 | Future Task |  |  | D654 | Manojkumar Gurjar | Approve | DED D654 - Completion of Build Segment IV - Approve | 0 hrs | 0 days | Fri 8/30/24 | Fri 8/30/24 | 468 | 470FS+24 days |  | Jimmy Cox
4583 | 470 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Identify RICEFW items for Build Segment IV | 20 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 469FS+24 days | 471 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4584 | 471 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Create Work Unit Tracker for Build Segment IV | 20 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 470 | 472 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4585 | 472 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Review, Update and Confirm Work Unit Tracker for Build Segment IV | 20 hrs | 10 days | Mon 10/28/24 | Fri 11/8/24 | 471 | 473 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4586 | 473 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Build and Unit Test RICEFW for Build Segment IV - Group 1 | 20 hrs | 17 days | Tue 11/12/24 | Fri 12/6/24 | 472 | 474 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4587 | 474 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Build and Unit Test RICEFW for Build Segment IV - Group 2 | 20 hrs | 19 days | Mon 12/9/24 | Mon 1/6/25 | 473 | 475FS-14 days,476 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4588 | 475 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Create Summary Document for Build Segment IV | 20 hrs | 13 days | Mon 12/16/24 | Fri 1/3/25 | 474FS-14 days | 476 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4566 | 476 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DEL D654 - Completion of Build Segment IV - Draft Submission | 0 hrs | 0 days | Mon 1/6/25 | Mon 1/6/25 | 474475 | 477 |  | Manojkumar Gurjar,Joy Schneider
4567 | 477 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 1/7/25 | Mon 1/13/25 | 476 | 478 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4568 | 478 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Style Guide Review | 1 hr | 1 day | Tue 1/14/25 | Tue 1/14/25 | 477 | 479 |  | Dusti Kincl
4569 | 479 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Final Collaborative Review | 20 hrs | 5 days | Wed 1/15/25 | Wed 1/22/25 | 478 | 480 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4570 | 480 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Accenture QC | 4 hrs | 2 days | Thu 1/23/25 | Fri 1/24/25 | 479 | 481 |  | Joy Schneider
4571 | 481 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DEL D654 - Completion of Build Segment IV - Submit | 0 hrs | 0 days | Fri 1/24/25 | Fri 1/24/25 | 480 | 482 |  | Joy Schneider
4572 | 482 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Department QC | 4 hrs | 1 day | Mon 1/27/25 | Mon 1/27/25 | 481 | 483 |  | Tommy Werner,Gabriela Gibson
4573 | 483 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Contract Manager Review | 8 hrs | 3 days | Tue 1/28/25 | Thu 1/30/25 | 482 | 484 |  | Sean Buchanan
4574 | 484 | Future Task |  |  | D654 | Manojkumar Gurjar | Accept | DEL D654 - Completion of Build Segment IV - Accept | 0 hrs | 0 days | Thu 1/30/25 | Thu 1/30/25 | 483 | 600 | 2025-01-01 | Sean Buchanan
4589 | 485 | Future Task | Yes |  | D659 | Manojkumar Gurjar |  | D659 - Completion of Build Segment II DW/BI | 219 hrs | 116 days | Mon 9/9/24 | Tue 2/25/25
4590 | 486 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | DED D659 - Completion of Build Segment II DW/BI - Create | 16 hrs | 10 days | Mon 9/9/24 | Fri 9/20/24 | 1 | 487 |  | Manojkumar Gurjar,Kurt Meisner
4591 | 487 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DED D659 - Completion of Build Segment II DW/BI - Submit | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 486 | 488 |  | Manojkumar Gurjar,Joy Schneider
4592 | 488 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DED D659 - Completion of Build Segment II DW/BI - Collaborative Review | 24 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 487 | 489 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4593 | 489 | Future Task |  |  | D659 | Manojkumar Gurjar | Approve | DED D659 - Completion of Build Segment II DW/BI - Approve | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 488 | 490 |  | Jimmy Cox
4603 | 490 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Identify RICEFW items for Build Segment II DW/BI | 40 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 489 | 491 |  | Manojkumar Gurjar,Kurt Meisner
4604 | 491 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Create Work Unit Tracker for Build Segment II DW/BI | 20 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 490 | 492 |  | Manojkumar Gurjar,Kurt Meisner
4605 | 492 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Review, Update and Confirm Work Unit Tracker for Build Segment II DW/BI | 20 hrs | 5 days | Mon 10/28/24 | Fri 11/1/24 | 491 | 493 |  | Manojkumar Gurjar,Kurt Meisner
4606 | 493 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Build and Unit Test RICEFW for Build Segment II DW/BI - Group 1 | 20 hrs | 17 days | Mon 11/4/24 | Wed 11/27/24 | 492 | 494 |  | Manojkumar Gurjar,Kurt Meisner
4607 | 494 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Build and Unit Test RICEFW for Build Segment II DW/BI - Group 2 | 2 hrs | 23 days | Mon 12/2/24 | Fri 1/3/25 | 493 | 495 |  | Manojkumar Gurjar,Kurt Meisner
4608 | 495 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Create Summary Document for Build Segment II DW/BI | 20 hrs | 19 days | Mon 1/6/25 | Fri 1/31/25 | 494 | 496 |  | Manojkumar Gurjar,Kurt Meisner
4594 | 496 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DEL D659 - Completion of Build Segment II DW/BI - Draft Submission | 0 hrs | 0 days | Fri 1/31/25 | Fri 1/31/25 | 495 | 497 |  | Manojkumar Gurjar,Joy Schneider
4595 | 497 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 2/3/25 | Fri 2/7/25 | 496 | 498 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4596 | 498 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Style Guide Review | 1 hr | 1 day | Mon 2/10/25 | Mon 2/10/25 | 497 | 499 |  | Dusti Kincl
4597 | 499 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Final Collaborative Review | 20 hrs | 5 days | Tue 2/11/25 | Mon 2/17/25 | 498 | 500 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4598 | 500 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Accenture QC | 4 hrs | 2 days | Tue 2/18/25 | Wed 2/19/25 | 499 | 501 |  | Joy Schneider
4599 | 501 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DEL D659 - Completion of Build Segment II DW/BI - Submit | 0 hrs | 0 days | Wed 2/19/25 | Wed 2/19/25 | 500 | 502 |  | Joy Schneider
4600 | 502 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Department QC | 4 hrs | 1 day | Thu 2/20/25 | Thu 2/20/25 | 501 | 503 |  | Tommy Werner,Gabriela Gibson
4601 | 503 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Contract Manager Review | 8 hrs | 3 days | Fri 2/21/25 | Tue 2/25/25 | 502 | 504 |  | Sean Buchanan
4602 | 504 | Future Task |  |  | D659 | Manojkumar Gurjar | Accept | DEL D659 - Completion of Build Segment II DW/BI - Accept | 0 hrs | 0 days | Tue 2/25/25 | Tue 2/25/25 | 503 | 600 | 2025-04-01 | Sean Buchanan
4609 | 505 | Future Task | Yes |  | D668 | Manojkumar Gurjar |  | D668 - Completion of Build Segment III DW/BI | 281 hrs | 93 days | Wed 10/30/24 | Mon 3/17/25
4610 | 506 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | DED D668 - Completion of Build Segment III DW/BI - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1 | 507 |  | Manojkumar Gurjar,Kurt Meisner
4611 | 507 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DED D668 - Completion of Build Segment III DW/BI - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 506 | 508 |  | Manojkumar Gurjar,Joy Schneider
4612 | 508 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DED D668 - Completion of Build Segment III DW/BI - Collaborative Review | 24 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 507 | 509 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4613 | 509 | Future Task |  |  | D668 | Manojkumar Gurjar | Approve | DED D668 - Completion of Build Segment III DW/BI - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 508 | 510 |  | Jimmy Cox
4623 | 510 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Identify RICEFW items for Build Segment III DW/BI | 40 hrs | 5 days | Mon 12/2/24 | Fri 12/6/24 | 509 | 511SS+2 days |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4624 | 511 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Create Work Unit Tracker for Build Segment III DW/BI | 40 hrs | 5 days | Wed 12/4/24 | Tue 12/10/24 | 510SS+2 days | 512 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4625 | 512 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Review, Update and Confirm Work Unit Tracker for Build Segment III DW/BI | 24 hrs | 3 days | Wed 12/11/24 | Fri 12/13/24 | 511 | 513 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4626 | 513 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Build and Unit Test RICEFW for Build Segment III DW/BI - Group 1 | 20 hrs | 18 days | Mon 12/16/24 | Fri 1/10/25 | 512 | 514 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4627 | 514 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Build and Unit Test RICEFW for Build Segment III DW/BI - Group 2 | 20 hrs | 18 days | Mon 1/13/25 | Thu 2/6/25 | 513 | 515 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4628 | 515 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Create Summary Document for Build Segment III DW/BI | 40 hrs | 10 days | Fri 2/7/25 | Thu 2/20/25 | 514 | 516 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4614 | 516 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DEL D668 - Completion of Build Segment III DW/BI - Draft Submission | 0 hrs | 0 days | Thu 2/20/25 | Thu 2/20/25 | 515 | 517 |  | Manojkumar Gurjar,Joy Schneider
4615 | 517 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 2/21/25 | Thu 2/27/25 | 516 | 518 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4616 | 518 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Style Guide Review | 1 hr | 1 day | Fri 2/28/25 | Fri 2/28/25 | 517 | 519 |  | Dusti Kincl
4617 | 519 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Final Collaborative Review | 20 hrs | 5 days | Mon 3/3/25 | Fri 3/7/25 | 518 | 520 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4618 | 520 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Accenture QC | 4 hrs | 2 days | Mon 3/10/25 | Tue 3/11/25 | 519 | 521 |  | Joy Schneider
4619 | 521 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DEL D668 - Completion of Build Segment III DW/BI - Submit | 0 hrs | 0 days | Tue 3/11/25 | Tue 3/11/25 | 520 | 522 |  | Joy Schneider
4620 | 522 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Department QC | 4 hrs | 1 day | Wed 3/12/25 | Wed 3/12/25 | 521 | 523 |  | Tommy Werner,Gabriela Gibson
4621 | 523 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Contract Manager Review | 8 hrs | 3 days | Thu 3/13/25 | Mon 3/17/25 | 522 | 524 |  | Sean Buchanan
4622 | 524 | Future Task |  |  | D668 | Manojkumar Gurjar | Accept | DEL D668 - Completion of Build Segment III DW/BI - Accept | 0 hrs | 0 days | Mon 3/17/25 | Mon 3/17/25 | 523 | 600 | 2025-08-01 | Sean Buchanan
4646 | 525 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | WP410 - Integration and Interface Strategy | 160 hrs | 115 days | Mon 7/10/23 | Thu 12/21/23
4647 | 526 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WPED WP410 - Integration and Interface Strategy - Create | 16 hrs | 10 days | Mon 7/10/23 | Fri 7/21/23 | 1 | 527 |  | Manojkumar Gurjar,Kurt Meisner
4648 | 527 | Future Task |  |  | WP410 | Manojkumar Gurjar | Submit | WPED WP410 - Integration and Interface Strategy - Submit | 0 hrs | 0 days | Fri 7/21/23 | Fri 7/21/23 | 526 | 528 |  | Manojkumar Gurjar,Joy Schneider
4649 | 528 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WPED WP410 - Integration and Interface Strategy - Review | 24 hrs | 10 days | Mon 7/24/23 | Fri 8/4/23 | 527 | 529 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4650 | 529 | Future Task |  |  | WP410 | Manojkumar Gurjar | Approve | WPED WP410 - Integration and Interface Strategy - Approve | 0 hrs | 0 days | Fri 8/4/23 | Fri 8/4/23 | 528 | 530FS+20 days |  | Jimmy Cox
4655 | 530 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WP410 - Define Interface and Integration Approach | 20 hrs | 19 days | Tue 9/5/23 | Fri 9/29/23 | 529FS+20 days | 531 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4656 | 531 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WP410 - Create Interface and Integration Architecture Diagram | 20 hrs | 15 days | Mon 10/2/23 | Fri 10/20/23 | 530 | 532533 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4657 | 532 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WP410 - Review and update Interface and Integration Operations | 20 hrs | 19 days | Mon 10/23/23 | Fri 11/17/23 | 531 | 533 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4658 | 533 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WP410 - Finalize the Interface and Integration Strategy Document | 20 hrs | 7 days | Mon 11/20/23 | Thu 11/30/23 | 531532 | 534 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4651 | 534 | Future Task |  |  | WP410 | Manojkumar Gurjar | Submit | WP WP410 - Integration and Interface Strategy - Submit | 0 hrs | 0 days | Thu 11/30/23 | Thu 11/30/23 | 533 | 535 |  | Manojkumar Gurjar,Joy Schneider
4652 | 535 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WP WP410 - Integration and Interface Strategy - Collaborative Review & Update | 20 hrs | 10 days | Fri 12/1/23 | Thu 12/14/23 | 534 | 536 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4653 | 536 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WP WP410 - Integration and Interface Strategy - Final Review & Edits | 20 hrs | 5 days | Fri 12/15/23 | Thu 12/21/23 | 535 | 537 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4654 | 537 | Future Task |  | RW-Communication | WP410 | Manojkumar Gurjar | Approve | WP WP410 - Integration and Interface Strategy - Approve | 0 hrs | 0 days | Thu 12/21/23 | Thu 12/21/23 | 536 | 1081FS+68 days | 2023-11-01 | Jimmy Cox
5603 | 538 | Future Task |  |  | WP426 | Jarad Hermann |  | WP426 - System Infrastructure Capacity Plan | 148 hrs | 72 days | Mon 9/8/25 | Fri 12/19/25
5604 | 539 | Future Task |  |  | WP426 | Jarad Hermann | Create | WPED WP426 - System Infrastructure Capacity Plan - Create | 8 hrs | 10 days | Mon 9/8/25 | Fri 9/19/25 | 1 | 540 |  | Jarad Hermann
5605 | 540 | Future Task |  |  | WP426 | Jarad Hermann | Submit | WPED WP426 - System Infrastructure Capacity Plan - Submit | 0 hrs | 0 days | Fri 9/19/25 | Fri 9/19/25 | 539 | 541 |  | Joy Schneider,Jarad Hermann
5606 | 541 | Future Task |  |  | WP426 | Jarad Hermann | Review | WPED WP426 - System Infrastructure Capacity Plan - Review | 16 hrs | 10 days | Mon 9/22/25 | Fri 10/3/25 | 540 | 542 |  | Jarad Hermann,Jimmy Cox,Angie Robertson,Sean Buchanan
5607 | 542 | Future Task |  |  | WP426 | Jarad Hermann | Approve | WPED WP426 - System Infrastructure Capacity Plan - Approve | 0 hrs | 0 days | Fri 10/3/25 | Fri 10/3/25 | 541 | 543FS+20 days |  | Jimmy Cox
5608 | 543 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Review and refine the FL PALM Capacity Plan (excel doc) | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 542FS+20 days | 544SS,545SS,546SS,547SS |  | Jarad Hermann,Bryan Sohayda
5609 | 544 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Review and refine the FL PALM Capacity Plan (word doc) | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 543SS | 548 |  | Jarad Hermann,Bryan Sohayda
5610 | 545 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Define and document current infrastructure demand | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 543SS | 548 |  | Jarad Hermann,Bryan Sohayda
5611 | 546 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Define and document current infrastructure capacity | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 543SS | 548 |  | Jarad Hermann,Bryan Sohayda
5612 | 547 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Define and document projected infrastructure demand | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 543SS | 548 |  | Jarad Hermann,Bryan Sohayda
5613 | 548 | Future Task |  |  | WP426 | Jarad Hermann | Submit | WP WP426 - System Infrastructure Capacity Plan - Submit | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 547544545546 | 549 |  | Joy Schneider,Jarad Hermann
5614 | 549 | Future Task |  |  | WP426 | Jarad Hermann | Review | WP WP426 - System Infrastructure Capacity Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 12/1/25 | Fri 12/12/25 | 548 | 550 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5615 | 550 | Future Task |  |  | WP426 | Jarad Hermann | Review | WP WP426 - System Infrastructure Capacity Plan - Final Review & Edits | 12 hrs | 5 days | Mon 12/15/25 | Fri 12/19/25 | 549 | 551 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5616 | 551 | Future Task |  |  | WP426 | Jarad Hermann | Approve | WP WP426 - System Infrastructure Capacity Plan - Approve | 0 hrs | 0 days | Fri 12/19/25 | Fri 12/19/25 | 550 |  |  | Jimmy Cox
3868 | 552 | Future Task | [5 empty] | Environment Builds | 137 hrs | 207 days | Mon 8/5/24 | Fri 5/30/25
4203 | 553 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure System Test Environment | 10 hrs | 15 days | Mon 8/5/24 | Fri 8/23/24 | 620 | 554 |  | Manojkumar Gurjar,Jarad Hermann
4204 | 554 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate System Test Environment | 8 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 553 | 651 |  | Manojkumar Gurjar,Jarad Hermann
4195 | 555 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Interface Test Environment | 10 hrs | 14 days | Tue 9/3/24 | Fri 9/20/24 | 1094FS-10 days | 556 |  | Manojkumar Gurjar,Jarad Hermann
4196 | 556 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate Interface Test Environment | 8 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 555 | 796 |  | Manojkumar Gurjar,Jarad Hermann
4197 | 557 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Mock Conversion Test Environment | 10 hrs | 15 days | Mon 8/5/24 | Fri 8/23/24 | 1041 | 558 |  | Manojkumar Gurjar,Jarad Hermann
4198 | 558 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate Mock Conversion Test Environment | 8 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 557 | 630 |  | Manojkumar Gurjar,Jarad Hermann
4199 | 559 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure UAT Test Environment | 10 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1272FS+215 days | 560 |  | Manojkumar Gurjar,Jarad Hermann
4200 | 560 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate UAT Test Environment | 10 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 559 | 562 |  | Manojkumar Gurjar,Jarad Hermann
7246 | 561 | Future Task |  |  |  | Manojkumar Gurjar | Milestone | Confirm Receipt of Agency Role Mapping Worksheet | 0 hrs | 0 days | Mon 3/3/25 | Mon 3/3/25 | 1871 |  |  | Manojkumar Gurjar,Jarad Hermann
4201 | 562 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Load Security Roles to ForgeRock for UAT | 4 hrs | 4 days | Mon 3/3/25 | Thu 3/6/25 | 5601871 | 563 |  | Jarad Hermann
4202 | 563 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Validate Security Roles in ForgeRock for UAT | 5 hrs | 5 days | Fri 3/7/25 | Thu 3/13/25 | 562 | 1274600 |  | Jarad Hermann
4191 | 564 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Dry Run Test Environment | 10 hrs | 14 days | Mon 5/5/25 | Thu 5/22/25 |  | 565 |  | Manojkumar Gurjar,Jarad Hermann
4192 | 565 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate Dry Run Test Environment | 8 hrs | 5 days | Fri 5/23/25 | Fri 5/30/25 | 564 | 837 |  | Manojkumar Gurjar,Jarad Hermann
4193 | 566 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Performance Test Environment | 10 hrs | 15 days | Mon 5/5/25 | Fri 5/23/25 | 1197 | 567 |  | Manojkumar Gurjar,Jarad Hermann
4194 | 567 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate Performance Test Environment | 8 hrs | 4 days | Tue 5/27/25 | Fri 5/30/25 | 566 | 979 |  | Manojkumar Gurjar,Jarad Hermann
4189 | 568 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Disaster Recovery Test Environment | 10 hrs | 15 days | Mon 3/3/25 | Fri 3/21/25 | 1183 | 569 |  | Manojkumar Gurjar,Jarad Hermann
4190 | 569 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate Disaster Recovery Test Environment | 8 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 568 | 997FS+1 day |  | Manojkumar Gurjar,Jarad Hermann
6809 | 570 | Future Task | [5 empty] | Other | 1,315 hrs | 290 days | Mon 1/8/24 | Fri 2/28/25
7219 | 571 | Future Task |  |  |  | Stacey Terry | Create | Draft Workflow Configuration Updates | 2 hrs | 3 days | Tue 9/24/24 | Thu 9/26/24 | 51,70,150,169FS+83 days | 572 |  | Stacey Terry,Yogesh Deshmukh
7220 | 572 | Future Task |  |  |  | Stacey Terry | Create | Draft Workflow Management Updates | 2 hrs | 3 days | Fri 9/27/24 | Tue 10/1/24 | 571 | 573 |  | Stacey Terry,Yogesh Deshmukh
7218 | 573 | Future Task |  |  |  | Stacey Terry | Create | Draft Workflow Monitoring Updates | 2 hrs | 3 days | Wed 10/2/24 | Fri 10/4/24 | 572 | 574 |  | Stacey Terry,Yogesh Deshmukh
7221 | 574 | Future Task |  |  |  | Stacey Terry | Create | Review and Confirmation Workflow Administration Guide Updates | 5 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 | 573 | 575 |  | Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Angie Robertson,Jimmy Cox
7217 | 575 | Future Task |  |  |  | Stacey Terry | Create | Approve Updates to Workflow Administration Guide | 0 hrs | 0 days | Fri 10/11/24 | Fri 10/11/24 | 574 | 1387 |  | Jimmy Cox
7144 | 576 | Future Task |  | RW |  | Stacey Terry | Create | Support Agency Configuration Workbook | 20 hrs | 103 days | Mon 1/8/24 | Fri 5/31/24 | 131FS+6 days | 578,577SS+84 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
7222 | 577 | Future Task |  | RW |  | Stacey Terry | Create | Confirm Completeness of Agency Configuration Workbooks | 20 hrs | 39 days | Mon 5/6/24 | Fri 6/28/24 | 576SS+84 days |  |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
7145 | 578 | Future Task |  |  |  | Stacey Terry | Create | Update Configuration Workbooks and Load Agency Configurations | 20 hrs | 64 days | Mon 6/3/24 | Fri 8/30/24 | 576 |  |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
6808 | 579 | Future Task |  |  |  | Stacey Terry | Create | Define User Preferences | 2 hrs | 10 days | Wed 7/31/24 | Tue 8/13/24 | 242 | 1865 |  | Stacey Terry
6810 | 580 | Future Task |  |  |  | Stacey Terry | Create | Create Batch Design/Online | 2 hrs | 22 days | Mon 7/1/24 | Wed 7/31/24 | 51,70,110,150,169FS+24 days | 581 |  | Stacey Terry,Manojkumar Gurjar
6807 | 581 | Future Task |  |  |  | Stacey Terry | Create | Create Batch Design/Interface | 2 hrs | 22 days | Thu 8/1/24 | Fri 8/30/24 | 580 | 582 |  | Stacey Terry,Manojkumar Gurjar
6811 | 582 | Future Task |  |  |  | Stacey Terry | Create | Review and Confirm Batch Design | 2 hrs | 20 days | Tue 9/3/24 | Mon 9/30/24 | 581 | 583 |  | Stacey Terry,Manojkumar Gurjar
7243 | 583 | Future Task |  |  |  | Manojkumar Gurjar | Create | Setup/configure Tidal Batch/ FIN online | 240 hrs | 40 days | Tue 10/1/24 | Tue 11/26/24 | 582 | 584,585SS |  | Rahul Yadav,Carlos Luis
7242 | 584 | Future Task |  |  |  | Manojkumar Gurjar | Create | Setup/Configure Tidal Batch / FIN interfaces | 240 hrs | 40 days | Wed 11/27/24 | Tue 1/28/25 | 583 | 587 |  | Rahul Yadav,Carlos Luis
7241 | 585 | Future Task |  |  |  | Manojkumar Gurjar | Create | Setup/configure Tidal Batch/ Payroll online | 240 hrs | 40 days | Tue 10/1/24 | Tue 11/26/24 | 583SS | 586 |  | Rahul Yadav,Carlos Luis
7240 | 586 | Future Task |  |  |  | Manojkumar Gurjar | Create | Setup/Configure Tidal Batch / Payroll interfaces | 240 hrs | 40 days | Wed 11/27/24 | Tue 1/28/25 | 585 | 587 |  | Rahul Yadav,Carlos Luis
7239 | 587 | Future Task |  |  |  | Manojkumar Gurjar | Create | Review/Finalize Tidal Batch configuration | 276 hrs | 23 days | Wed 1/29/25 | Fri 2/28/25 | 586584 | 1274 |  | Rahul Yadav,Carlos Luis
3771 | 588 | Future Task | [5 empty] | Test | 19,605.58 hrs | 621 days | Mon 7/3/23 | Thu 12/18/25
7173 | 589 | Future Task |  |  | SG2 | Jimmy Cox | Create | Stage Gate 2: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 3/4/24 | Fri 3/8/24 |  | 590 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7174 | 590 | Future Task |  |  | SG2 | Jimmy Cox | Create | Stage Gate 2: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 589 | 591FS+80 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7175 | 591 | Future Task |  |  | SG2 | Jimmy Cox | Create | Stage Gate 2: Prepare information package for ESC | 11 hrs | 10 days | Wed 7/17/24 | Tue 7/30/24 | 590FS+80 days | 592 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7176 | 592 | Future Task |  |  | SG2 | Jimmy Cox | Create | Stage Gate 2: Collaborative Review and Update of information package | 11 hrs | 5 days | Wed 7/31/24 | Tue 8/6/24 | 591 | 593 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7177 | 593 | Future Task |  |  | SG2 | Jimmy Cox | Create | Stage Gate 2: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 8/7/24 | Wed 8/7/24 | 592 |  |  | Dusti Kincl
7153 | 594 | Future Task |  |  | SG2 | Jimmy Cox | Milestone | Stage Gate 2: Ready to Begin System Testing | 0 hrs | 0 days | Wed 5/8/24 | Wed 5/8/24 | 51,70,150,162,386 |  | July/August 2024 | Jimmy Cox,Angie Robertson,Matt Cole
7178 | 595 | Future Task |  |  | SG3 | Jimmy Cox | Create | Stage Gate 3: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 |  | 596 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7179 | 596 | Future Task |  |  | SG3 | Jimmy Cox | Create | Stage Gate 3: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 595 | 597FS+76 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7180 | 597 | Future Task |  |  | SG3 | Jimmy Cox | Create | Stage Gate 3: Prepare information package for ESC | 11 hrs | 10 days | Wed 2/19/25 | Tue 3/4/25 | 596FS+76 days | 598 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7181 | 598 | Future Task |  |  | SG3 | Jimmy Cox | Create | Stage Gate 3: Collaborative Review and Update of information package | 11 hrs | 5 days | Wed 3/5/25 | Tue 3/11/25 | 597 | 599 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7182 | 599 | Future Task |  |  | SG3 | Jimmy Cox | Create | Stage Gate 3: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 3/12/25 | Wed 3/12/25 | 598 |  |  | Dusti Kincl
7154 | 600 | Future Task |  |  | SG3 | Jimmy Cox | Milestone | Stage Gate 3: Ready to Begin UAT | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 51,70,150,169,386,422,442,464,484,504,524,1272,752,692,651,563 |  | March 2025 - ESC | Executive Steering Committee
4662 | 601 | Future Task |  |  | D643 | Stacey Terry |  | D643 - Updated System Testing Plan | 217 hrs | 179 days | Mon 7/3/23 | Tue 3/19/24
4663 | 602 | Future Task |  |  | D643 | Stacey Terry | Create | DED D643 - Updated System Testing Plan - Create | 16 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 1FS+47 days | 603 |  | Stacey Terry,Mary Punty
4664 | 603 | Future Task |  |  | D643 | Stacey Terry | Submit | DED D643 - Updated System Testing Plan - Submit | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 602 | 604 |  | Stacey Terry,Joy Schneider
4665 | 604 | Future Task |  |  | D643 | Stacey Terry | Review | DED D643 - Updated System Testing Plan - Collaborative Review | 24 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 603 | 605 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4666 | 605 | Future Task |  |  | D643 | Stacey Terry | Approve | DED D643 - Updated System Testing Plan - Approve | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 604 | 606FS+80 days |  | Jimmy Cox
4685 | 606 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define System Test approach for Financials and Payroll | 20 hrs | 15 days | Mon 11/27/23 | Fri 12/15/23 | 605FS+80 days | 607 |  | Yogesh Deshmukh,Stacey Terry,Mary Punty,Manojkumar Gurjar,Kurt Meisner,Matt Cole
4686 | 607 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define System Test Cycles for Financials and Payroll | 20 hrs | 9 days | Mon 12/18/23 | Fri 12/29/23 | 606 | 608FS-4 days |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Mary Punty
4687 | 608 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Identify System Test Resources for Financials and Payroll | 20 hrs | 11 days | Tue 12/26/23 | Wed 1/10/24 | 607FS-4 days | 609SS+4 days |  | Stacey Terry,Manojkumar Gurjar,Janice Jackson,Tiffany Porter,Brendan Jones,Jennifer Reeves,Deana Metcalf,Matthew Breeding,Carolyn Hicks
4688 | 609 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define System Test Tools and Test Management processes | 20 hrs | 11 days | Tue 1/2/24 | Wed 1/17/24 | 608SS+4 days | 610FS-2 days |  | Yogesh Deshmukh,Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jennifer Reeves
4689 | 610 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Create Initial List of System Test Scenarios for Financials and Payroll | 20 hrs | 24 days | Tue 1/16/24 | Fri 2/16/24 | 609FS-2 days | 611FS-5 days |  | Yogesh Deshmukh,Stacey Terry,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4690 | 611 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define requirements traceability approach for system testing | 20 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 610FS-5 days | 612 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Mary Punty,Jennifer Reeves
4667 | 612 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 - Updated System Testing Plan - Draft Submission | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 611 | 613 |  | Stacey Terry,Joy Schneider
4668 | 613 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 2/26/24 | Fri 3/1/24 | 612 | 614 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4669 | 614 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Style Guide Review | 1 hr | 1 day | Mon 3/4/24 | Mon 3/4/24 | 613 | 615 |  | Dusti Kincl
4670 | 615 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Final Collaborative Review | 20 hrs | 5 days | Tue 3/5/24 | Mon 3/11/24 | 614 | 616 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4671 | 616 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Accenture QC | 4 hrs | 2 days | Tue 3/12/24 | Wed 3/13/24 | 615 | 617 |  | Joy Schneider
4672 | 617 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 - Updated System Testing Plan - Submit | 0 hrs | 0 days | Wed 3/13/24 | Wed 3/13/24 | 616 | 618 |  | Joy Schneider
4673 | 618 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Department QC | 4 hrs | 1 day | Thu 3/14/24 | Thu 3/14/24 | 617 | 619 |  | Tommy Werner,Gabriela Gibson
4674 | 619 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Contract Manager Review | 8 hrs | 3 days | Fri 3/15/24 | Tue 3/19/24 | 618 | 620 |  | Sean Buchanan
4675 | 620 | Future Task |  |  | D643 | Stacey Terry | Accept | DEL D643 - Updated System Testing Plan - Accept | 0 hrs | 0 days | Tue 3/19/24 | Tue 3/19/24 | 619 | 553,1249FS+101 days | 2024-03-01 | Sean Buchanan
5004 | 621 | Future Task | Yes |  | D651 | Manojkumar Gurjar |  | D651 - Completion of Mock Conversion I | 305 hrs | 90 days | Mon 6/17/24 | Tue 10/22/24
5005 | 622 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | DED D651 - Completion of Mock Conversion I - Create | 16 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 1053FS-47 days | 623 |  | Manojkumar Gurjar,Kurt Meisner
5006 | 623 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DED D651 - Completion of Mock Conversion I - Submit | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 622 | 624 |  | Manojkumar Gurjar,Joy Schneider
5007 | 624 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DED D651 - Completion of Mock Conversion I - Collaborative Review | 24 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 623 | 625 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5008 | 625 | Future Task |  |  | D651 | Manojkumar Gurjar | Approve | DED D651 - Completion of Mock Conversion I - Approve | 0 hrs | 0 days | Mon 7/15/24 | Mon 7/15/24 | 624 | 628FS+19 days,627FS+19 days,626FS+14 days |  | Jimmy Cox
7224 | 626 | Future Task |  | RW | D651 | Manojkumar Gurjar | Create | D651 - Confirm Agency Conversion Build and Unit Test Activities | 20 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 625FS+14 days | 629 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
7207 | 627 | Future Task |  | RW | D651 | Manojkumar Gurjar | Milestone | D651 - Confirm Conversion Files Received | 0 hrs | 0 days | Fri 8/9/24 | Fri 8/9/24 | 625FS+19 days | 629 |  | Matthew Breeding
5018 | 628 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | D651 - Confirm Mock 1 Conversion Test Environment Readiness | 20 hrs | 5 days | Mon 8/12/24 | Fri 8/16/24 | 625FS+19 days | 629 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5019 | 629 | Future Task |  | RW | D651 | Manojkumar Gurjar | Create | D651 - Create Mock 1 Conversion Checklist | 20 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 628627626 | 630 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5020 | 630 | Future Task |  | RW | D651 | Manojkumar Gurjar | Create | D651 - Execute Mock 1 – Conversion | 108 hrs | 9 days | Tue 9/3/24 | Fri 9/13/24 | 62955816991703 | 631 |  | Jeevan Mahajan,Janmejay Khare
5021 | 631 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | D651 - Validate Mock 1 – Conversion | 20 hrs | 5 days | Mon 9/16/24 | Fri 9/20/24 | 630 | 632 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5022 | 632 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | D651 - Conduct Mock 1 - Conversion Test Exit Criteria Review Meeting | 20 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 631 | 633 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5009 | 633 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DEL D651 - Completion of Mock Conversion I - Draft Submission | 0 hrs | 0 days | Fri 9/27/24 | Fri 9/27/24 | 632 | 634 |  | Manojkumar Gurjar,Joy Schneider
5010 | 634 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 9/30/24 | Fri 10/4/24 | 633 | 635 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5011 | 635 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Style Guide Review | 1 hr | 1 day | Mon 10/7/24 | Mon 10/7/24 | 634 | 636 |  | Dusti Kincl
5012 | 636 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Final Collaborative Review | 20 hrs | 5 days | Tue 10/8/24 | Mon 10/14/24 | 635 | 637 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5013 | 637 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Accenture QC | 4 hrs | 2 days | Tue 10/15/24 | Wed 10/16/24 | 636 | 638 |  | Joy Schneider
5014 | 638 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DEL D651 - Completion of Mock Conversion I - Submit | 0 hrs | 0 days | Wed 10/16/24 | Wed 10/16/24 | 637 | 639 |  | Joy Schneider
5015 | 639 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Department QC | 4 hrs | 1 day | Thu 10/17/24 | Thu 10/17/24 | 638 | 640 |  | Tommy Werner,Gabriela Gibson
5016 | 640 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Contract Manager Review | 8 hrs | 3 days | Fri 10/18/24 | Tue 10/22/24 | 639 | 641 |  | Sean Buchanan
5017 | 641 | Future Task |  |  | D651 | Manojkumar Gurjar | Accept | DEL D651 - Completion of Mock Conversion I - Accept | 0 hrs | 0 days | Tue 10/22/24 | Tue 10/22/24 | 640 | 666FS-32 days | 2024-11-01 | Sean Buchanan
4696 | 642 | Future Task | Yes |  | D652 | Stacey Terry |  | D652 - Completion of System Test Segment I | 4,480 hrs | 123 days | Mon 7/8/24 | Thu 1/2/25
4697 | 643 | Future Task |  |  | D652 | Stacey Terry | Create | DED D652 - Completion of System Test Segment I - Create | 16 hrs | 10 days | Mon 7/8/24 | Fri 7/19/24 | 1 | 644 |  | Stacey Terry,Mary Punty
4698 | 644 | Future Task |  |  | D652 | Stacey Terry | Submit | DED D652 - Completion of System Test Segment I - Submit | 0 hrs | 0 days | Fri 7/19/24 | Fri 7/19/24 | 643 | 645 |  | Stacey Terry,Joy Schneider
4699 | 645 | Future Task |  |  | D652 | Stacey Terry | Review | DED D652 - Completion of System Test Segment I - Collaborative Review | 24 hrs | 10 days | Mon 7/22/24 | Fri 8/2/24 | 644 | 646 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4700 | 646 | Future Task |  |  | D652 | Stacey Terry | Approve | DED D652 - Completion of System Test Segment I - Approve | 0 hrs | 0 days | Fri 8/2/24 | Fri 8/2/24 | 645 | 647 |  | Jimmy Cox
4752 | 647 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Create Work Unit Tracker for System Test Segment 1 Execution | 20 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 646 | 648 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4753 | 648 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Review, Update and confirm Work Unit Tracker for System Test Segment 1 Execution | 20 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 647 | 649SS+5 days |  | Mary Punty,Stacey Terry,Deana Metcalf,Janice Jackson,Tiffany Porter,Brendan Jones
4754 | 649 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Confirm System Test Environment Readiness | 20 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 648SS+5 days | 650SS |  | Manojkumar Gurjar,Jarad Hermann
4755 | 650 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Conduct System Test Kick Off Meeting | 30 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 649SS | 651 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4756 | 651 | Future Task | Maybe |  | D652 | Stacey Terry | Create | D652 - Execute System Test Segment 1 | 4,284 hrs | 51 days | Tue 9/17/24 | Wed 11/27/24 | 6501067554 | 652,653FS-3 days,600 |  | Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4757 | 652 | Future Task |  |  | D652 | Stacey Terry | Milestone | D652 - Milestone: System Test Segment 1 Execution Complete | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 651 | 1758 |  | Stacey Terry
4758 | 653 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Create Completion of System Testing Segment 1 Summary Document | 3 hrs | 8 days | Mon 11/25/24 | Fri 12/6/24 | 651FS-3 days | 654SS+3 days,655SS+3 days,656 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4759 | 654 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Conduct System Test Segment 1 Exit Criteria Review Meeting | 3 hrs | 5 days | Mon 12/2/24 | Fri 12/6/24 | 653SS+3 days | 656 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4760 | 655 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Confirm requirements traceability for System Test Segment 1 | 3 hrs | 5 days | Mon 12/2/24 | Fri 12/6/24 | 653SS+3 days | 656 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4701 | 656 | Future Task |  |  | D652 | Stacey Terry | Submit | DEL D652 - Completion of System Test Segment I - Draft Submission | 0 hrs | 0 days | Fri 12/6/24 | Fri 12/6/24 | 653654655 | 657 |  | Stacey Terry,Joy Schneider
4702 | 657 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 12/9/24 | Fri 12/13/24 | 656 | 658 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4703 | 658 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Style Guide Review | 1 hr | 1 day | Mon 12/16/24 | Mon 12/16/24 | 657 | 659 |  | Dusti Kincl
4704 | 659 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Final Collaborative Review | 20 hrs | 5 days | Tue 12/17/24 | Mon 12/23/24 | 658 | 660 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4705 | 660 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Accenture QC | 4 hrs | 2 days | Tue 12/24/24 | Thu 12/26/24 | 659 | 661 |  | Joy Schneider
4706 | 661 | Future Task |  |  | D652 | Stacey Terry | Submit | DEL D652 - Completion of System Test Segment I - Submit | 0 hrs | 0 days | Thu 12/26/24 | Thu 12/26/24 | 660 | 662 |  | Joy Schneider
4707 | 662 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Department QC | 4 hrs | 1 day | Fri 12/27/24 | Fri 12/27/24 | 661 | 663 |  | Tommy Werner,Gabriela Gibson
4708 | 663 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Contract Manager Review | 8 hrs | 3 days | Mon 12/30/24 | Thu 1/2/25 | 662 | 664 |  | Sean Buchanan
4709 | 664 | Future Task |  |  | D652 | Stacey Terry | Accept | DEL D652 - Completion of System Test Segment I - Accept | 0 hrs | 0 days | Thu 1/2/25 | Thu 1/2/25 | 663 |  | 2024-12-01 | Sean Buchanan
4710 | 665 | Future Task | Yes |  | D655 | Manojkumar Gurjar |  | D655 - Completion of Mock Conversion II (System Test Environment) | 237 hrs | 94 days | Mon 9/9/24 | Fri 1/24/25
4711 | 666 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | DED D655 - Completion of Mock Conversion II (System Test Environment) - Create | 16 hrs | 10 days | Mon 9/9/24 | Fri 9/20/24 | 641FS-32 days | 667 |  | Manojkumar Gurjar,Kurt Meisner
4712 | 667 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DED D655 - Completion of Mock Conversion II (System Test Environment) - Submit | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 666 | 668 |  | Manojkumar Gurjar,Joy Schneider
4713 | 668 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DED D655 - Completion of Mock Conversion II (System Test Environment) - Collaborative Review | 24 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 667 | 669 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4714 | 669 | Future Task |  |  | D655 | Manojkumar Gurjar | Approve | DED D655 - Completion of Mock Conversion II (System Test Environment) - Approve | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 668 | 671FS+29 days,670FS+29 days |  | Jimmy Cox
7208 | 670 | Future Task |  | RW | D655 | Manojkumar Gurjar | Milestone | D655 - Confirm Conversion Files Received | 0 hrs | 0 days | Fri 11/15/24 | Fri 11/15/24 | 669FS+29 days | 672 |  | Matthew Breeding
4761 | 671 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | D655 - Confirm Mock 2 Conversion - System Test Environment Readiness | 20 hrs | 4 days | Mon 11/18/24 | Thu 11/21/24 | 669FS+29 days | 672 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4762 | 672 | Future Task |  | RW | D655 | Manojkumar Gurjar | Create | D655 - Create Mock 2 Conversion Checklist (System Test Environment) | 20 hrs | 5 days | Fri 11/22/24 | Mon 12/2/24 | 671670 | 673 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4763 | 673 | Future Task |  | RW | D655 | Manojkumar Gurjar | Create | D655 - Execute Mock 2 – Conversion (System Test Environment) | 60 hrs | 10 days | Tue 12/3/24 | Mon 12/16/24 | 672 | 674 |  | Jeevan Mahajan,Janmejay Khare
4764 | 674 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | D655 - Validate Mock 2 – Conversion (System Test Environment) | 20 hrs | 4 days | Tue 12/17/24 | Fri 12/20/24 | 673 | 675 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4765 | 675 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | D655 - Conduct Mock 2 - Conversion (System Test Environment) Test Exit Criteria Review Meeting | 20 hrs | 5 days | Mon 12/23/24 | Mon 12/30/24 | 674 | 676 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4715 | 676 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Draft Submission | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 675 | 677 |  | Manojkumar Gurjar,Joy Schneider
4716 | 677 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 12/31/24 | Tue 1/7/25 | 676 | 678 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4717 | 678 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Style Guide Review | 1 hr | 1 day | Wed 1/8/25 | Wed 1/8/25 | 677 | 679 |  | Dusti Kincl
4718 | 679 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Final Collaborative Review | 20 hrs | 5 days | Thu 1/9/25 | Wed 1/15/25 | 678 | 680 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4719 | 680 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Accenture QC | 4 hrs | 2 days | Thu 1/16/25 | Fri 1/17/25 | 679 | 681 |  | Joy Schneider
4720 | 681 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Submit | 0 hrs | 0 days | Fri 1/17/25 | Fri 1/17/25 | 680 | 682 |  | Joy Schneider
4721 | 682 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Department QC | 4 hrs | 1 day | Tue 1/21/25 | Tue 1/21/25 | 681 | 683 |  | Tommy Werner,Gabriela Gibson
4722 | 683 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Contract Manager Review | 8 hrs | 3 days | Wed 1/22/25 | Fri 1/24/25 | 682 | 684 |  | Sean Buchanan
4723 | 684 | Future Task |  |  | D655 | Manojkumar Gurjar | Accept | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Accept | 0 hrs | 0 days | Fri 1/24/25 | Fri 1/24/25 | 683 | 707FS-64 days | 2025-01-01 | Sean Buchanan
4724 | 685 | Future Task | Yes |  | D656 | Stacey Terry |  | D656 - Completion of System Test Segment II | 1,814 hrs | 99 days | Mon 10/7/24 | Fri 2/28/25
4725 | 686 | Future Task |  |  | D656 | Stacey Terry | Create | DED D656 - Completion of System Test Segment II - Create | 16 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1 | 687 |  | Stacey Terry,Mary Punty
4726 | 687 | Future Task |  |  | D656 | Stacey Terry | Submit | DED D656 - Completion of System Test Segment II - Submit | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 686 | 688 |  | Stacey Terry,Joy Schneider
4727 | 688 | Future Task |  |  | D656 | Stacey Terry | Review | DED D656 - Completion of System Test Segment II - Collaborative Review | 20 hrs | 10 days | Mon 10/21/24 | Fri 11/1/24 | 687 | 689 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4728 | 689 | Future Task |  |  | D656 | Stacey Terry | Approve | DED D656 - Completion of System Test Segment II - Approve | 0 hrs | 0 days | Fri 11/1/24 | Fri 11/1/24 | 688 | 690 |  | Jimmy Cox
4766 | 690 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Create Work Unit Tracker for System Test Segment 2 Execution | 6 hrs | 9 days | Mon 11/4/24 | Fri 11/15/24 | 689 | 691 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4767 | 691 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Review, Update and confirm Work Unit Tracker for System Test Segment 2 Execution | 20 hrs | 8 days | Mon 11/18/24 | Wed 11/27/24 | 690 | 692 |  | Mary Punty,Stacey Terry,Deana Metcalf,Janice Jackson,Tiffany Porter,Brendan Jones
4768 | 692 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Execute System Test Segment 2 | 1,680 hrs | 40 days | Mon 12/2/24 | Wed 1/29/25 | 691 | 693,694FS-5 days,600 |  | Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4769 | 693 | Future Task |  |  | D656 | Stacey Terry | Milestone | D656 - Milestone: System Test Segment 2 Execution Complete | 0 hrs | 0 days | Wed 1/29/25 | Wed 1/29/25 | 692 |  |  | Stacey Terry
4770 | 694 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Create Completion of System Testing Segment 2 Summary Document | 6 hrs | 10 days | Thu 1/23/25 | Wed 2/5/25 | 692FS-5 days | 695SS+5 days,696SS+5 days,697 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4771 | 695 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Conduct System Test Segment 2 Exit Criteria Review Meeting | 3 hrs | 5 days | Thu 1/30/25 | Wed 2/5/25 | 694SS+5 days | 697 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4772 | 696 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Confirm requirements traceability for System Test Segment 2 | 6 hrs | 5 days | Thu 1/30/25 | Wed 2/5/25 | 694SS+5 days | 697 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4729 | 697 | Future Task |  |  | D656 | Stacey Terry | Submit | DEL D656 - Completion of System Test Segment II - Draft Submission | 0 hrs | 0 days | Wed 2/5/25 | Wed 2/5/25 | 694695696 | 698 |  | Stacey Terry,Joy Schneider
4730 | 698 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Thu 2/6/25 | Wed 2/12/25 | 697 | 699 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4731 | 699 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Style Guide Review | 1 hr | 1 day | Thu 2/13/25 | Thu 2/13/25 | 698 | 700 |  | Dusti Kincl
4732 | 700 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Final Collaborative Review | 20 hrs | 5 days | Fri 2/14/25 | Thu 2/20/25 | 699 | 701 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4733 | 701 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Accenture QC | 4 hrs | 2 days | Fri 2/21/25 | Mon 2/24/25 | 700 | 702 |  | Joy Schneider
4734 | 702 | Future Task |  |  | D656 | Stacey Terry | Submit | DEL D656 - Completion of System Test Segment II - Submit | 0 hrs | 0 days | Mon 2/24/25 | Mon 2/24/25 | 701 | 703 |  | Joy Schneider
4735 | 703 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Department QC | 4 hrs | 1 day | Tue 2/25/25 | Tue 2/25/25 | 702 | 704 |  | Tommy Werner,Gabriela Gibson
4736 | 704 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Contract Manager Review | 8 hrs | 3 days | Wed 2/26/25 | Fri 2/28/25 | 703 | 705 |  | Sean Buchanan
4737 | 705 | Future Task |  |  | D656 | Stacey Terry | Accept | DEL D656 - Completion of System Test Segment II - Accept | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 704 |  | 2025-02-01 | Sean Buchanan
4738 | 706 | Future Task | Yes |  | D657 | Manojkumar Gurjar |  | D657 - Completion of Mock Conversion III (UAT) | 393 hrs | 101 days | Mon 10/21/24 | Tue 3/18/25
4739 | 707 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | DED D657 - Completion of Mock Conversion III (UAT) - Create | 16 hrs | 10 days | Mon 10/21/24 | Fri 11/1/24 | 684FS-64 days | 708 |  | Manojkumar Gurjar,Kurt Meisner
4740 | 708 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DED D657 - Completion of Mock Conversion III (UAT) - Submit | 0 hrs | 0 days | Fri 11/1/24 | Fri 11/1/24 | 707 | 709 |  | Manojkumar Gurjar,Joy Schneider
4741 | 709 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DED D657 - Completion of Mock Conversion III (UAT) - Collaborative Review | 24 hrs | 10 days | Mon 11/4/24 | Mon 11/18/24 | 708 | 710 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4742 | 710 | Future Task |  |  | D657 | Manojkumar Gurjar | Approve | DED D657 - Completion of Mock Conversion III (UAT) - Approve | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 709 | 712FS+24 days,711FS+24 days |  | Jimmy Cox
7209 | 711 | Future Task |  | RW | D657 | Manojkumar Gurjar | Milestone | D657 - Confirm Conversion Files Received | 0 hrs | 0 days | Tue 12/24/24 | Tue 12/24/24 | 710FS+24 days | 713
4773 | 712 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | D657 - Confirm Mock 3 Conversion - UAT Environment Readiness | 2 hrs | 5 days | Thu 12/26/24 | Thu 1/2/25 | 710FS+24 days | 713 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4774 | 713 | Future Task |  | RW | D657 | Manojkumar Gurjar | Create | D657 - Create Mock 3 Conversion Checklist (UAT) | 2 hrs | 6 days | Fri 1/3/25 | Fri 1/10/25 | 712711 | 714 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4775 | 714 | Future Task |  | RW | D657 | Manojkumar Gurjar | Create | D657 - Execute Mock 3 – Conversion (UAT) | 252 hrs | 21 days | Mon 1/13/25 | Tue 2/11/25 | 713 | 715 |  | Jeevan Mahajan,Janmejay Khare
4776 | 715 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | D657 - Validate Mock 3 – Conversion (UAT) | 20 hrs | 4 days | Wed 2/12/25 | Mon 2/17/25 | 714 | 716 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4777 | 716 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | D657 - Conduct Mock 3 - Conversion UAT Exit Criteria Review Meeting | 20 hrs | 4 days | Tue 2/18/25 | Fri 2/21/25 | 715 | 717 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4743 | 717 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DEL D657 - Completion of Mock Conversion III (UAT) - Draft Submission | 0 hrs | 0 days | Fri 2/21/25 | Fri 2/21/25 | 716 | 718 |  | Manojkumar Gurjar,Joy Schneider
4744 | 718 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 717 | 719 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4745 | 719 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Style Guide Review | 1 hr | 1 day | Mon 3/3/25 | Mon 3/3/25 | 718 | 720 |  | Dusti Kincl
4746 | 720 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Final Collaborative Review | 20 hrs | 5 days | Tue 3/4/25 | Mon 3/10/25 | 719 | 721 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4747 | 721 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Accenture QC | 4 hrs | 2 days | Tue 3/11/25 | Wed 3/12/25 | 720 | 722 |  | Joy Schneider
4748 | 722 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DEL D657 - Completion of Mock Conversion III (UAT) - Submit | 0 hrs | 0 days | Wed 3/12/25 | Wed 3/12/25 | 721 | 723 |  | Joy Schneider
4749 | 723 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Department QC | 4 hrs | 1 day | Thu 3/13/25 | Thu 3/13/25 | 722 | 724 |  | Tommy Werner,Gabriela Gibson
4750 | 724 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Contract Manager Review | 8 hrs | 3 days | Fri 3/14/25 | Tue 3/18/25 | 723 | 725 |  | Sean Buchanan
4751 | 725 | Future Task |  |  | D657 | Manojkumar Gurjar | Accept | DEL D657 - Completion of Mock Conversion III (UAT) - Accept | 0 hrs | 0 days | Tue 3/18/25 | Tue 3/18/25 | 724 | 767FS-46 days,1284 | 2025-02-01 | Sean Buchanan
5023 | 726 | Future Task |  |  | D660 | Stacey Terry |  | D660 - Payroll Parallel Testing Plan | 182 hrs | 94 days | Mon 12/2/24 | Tue 4/15/25
5024 | 727 | Future Task |  |  | D660 | Stacey Terry | Create | DED D660 - Payroll Parallel Testing Plan - Create | 16 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 200 | 728 |  | Stacey Terry,Mary Punty
5025 | 728 | Future Task |  |  | D660 | Stacey Terry | Submit | DED D660 - Payroll Parallel Testing Plan - Submit | 0 hrs | 0 days | Fri 12/13/24 | Fri 12/13/24 | 727 | 729,1110SS-4 days |  | Stacey Terry,Joy Schneider
5026 | 729 | Future Task |  |  | D660 | Stacey Terry | Review | DED D660 - Payroll Parallel Testing Plan - Collaborative Review | 24 hrs | 10 days | Mon 12/16/24 | Mon 12/30/24 | 728 | 730 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5027 | 730 | Future Task |  |  | D660 | Stacey Terry | Approve | DED D660 - Payroll Parallel Testing Plan - Approve | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 729 | 731FS+22 days |  | Jimmy Cox
5037 | 731 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Define Payroll Parallel Test approach | 20 hrs | 20 days | Mon 2/3/25 | Fri 2/28/25 | 730FS+22 days | 732FS-5 days |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5038 | 732 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Define Payroll Parallel Test Cycles | 15 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 731FS-5 days | 733 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5039 | 733 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Identify Test Resources for Payroll Parallel Test | 20 hrs | 5 days | Mon 3/3/25 | Fri 3/7/25 | 732 | 734 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5040 | 734 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Define Payroll Parallel Test Tools and Test Management processes | 20 hrs | 5 days | Mon 3/10/25 | Fri 3/14/25 | 733 | 735FS-5 days |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5041 | 735 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Create Initial List of Payroll Parallel Test Scenarios | 20 hrs | 10 days | Mon 3/10/25 | Fri 3/21/25 | 734FS-5 days | 736 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5028 | 736 | Future Task |  |  | D660 | Stacey Terry | Submit | DEL D660 - Payroll Parallel Testing Plan - Draft Submission | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 735 | 737 |  | Stacey Terry,Joy Schneider
5029 | 737 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 736 | 738 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5030 | 738 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Style Guide Review | 1 hr | 1 day | Mon 3/31/25 | Mon 3/31/25 | 737 | 739 |  | Dusti Kincl
5031 | 739 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Final Collaborative Review | 10 hrs | 5 days | Tue 4/1/25 | Mon 4/7/25 | 738 | 740 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5032 | 740 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Accenture QC | 4 hrs | 2 days | Tue 4/8/25 | Wed 4/9/25 | 739 | 741 |  | Joy Schneider
5033 | 741 | Future Task |  |  | D660 | Stacey Terry | Submit | DEL D660 - Payroll Parallel Testing Plan - Submit | 0 hrs | 0 days | Wed 4/9/25 | Wed 4/9/25 | 740 | 742 |  | Joy Schneider
5034 | 742 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Department QC | 4 hrs | 1 day | Thu 4/10/25 | Thu 4/10/25 | 741 | 743 |  | Tommy Werner,Gabriela Gibson
5035 | 743 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Contract Manager Review | 8 hrs | 3 days | Fri 4/11/25 | Tue 4/15/25 | 742 | 744 |  | Sean Buchanan
5036 | 744 | Future Task |  |  | D660 | Stacey Terry | Accept | DEL D660 - Payroll Parallel Testing Plan - Accept | 0 hrs | 0 days | Tue 4/15/25 | Tue 4/15/25 | 743 | 871FS-37 days | 2025-04-01 | Sean Buchanan
4778 | 745 | Future Task | Yes |  | D661 | Stacey Terry |  | D661 - Completion of System Test DW/BI | 547 hrs | 130 days | Mon 10/21/24 | Mon 4/28/25
4779 | 746 | Future Task |  |  | D661 | Stacey Terry | Create | DED D661 - Completion of System Test DW/BI - Create | 16 hrs | 10 days | Mon 10/21/24 | Fri 11/1/24 | 1 | 747 |  | Stacey Terry,Mary Punty
4780 | 747 | Future Task |  |  | D661 | Stacey Terry | Submit | DED D661 - Completion of System Test DW/BI - Submit | 0 hrs | 0 days | Fri 11/1/24 | Fri 11/1/24 | 746 | 748 |  | Stacey Terry,Joy Schneider
4781 | 748 | Future Task |  |  | D661 | Stacey Terry | Review | DED D661 - Completion of System Test DW/BI - Collaborative Review | 24 hrs | 10 days | Mon 11/4/24 | Mon 11/18/24 | 747 | 749 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4782 | 749 | Future Task |  |  | D661 | Stacey Terry | Approve | DED D661 - Completion of System Test DW/BI - Approve | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 748 | 750FS+10 days |  | Jimmy Cox
4820 | 750 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Create Work Unit Tracker for System Test DW/BI Execution | 36 hrs | 9 days | Thu 12/5/24 | Tue 12/17/24 | 749FS+10 days | 751 |  | Manojkumar Gurjar,Mary Punty
4821 | 751 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Review, Update and confirm Work Unit Tracker for System Test DW/BI Execution | 20 hrs | 10 days | Wed 12/18/24 | Thu 1/2/25 | 750 | 752 |  | Manojkumar Gurjar,Mary Punty
4822 | 752 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Execute System Test DW/BI | 360 hrs | 60 days | Fri 1/3/25 | Fri 3/28/25 | 751 | 753,754FS-6 days,600 |  | Jack Jenkins,Anthony Bastidas
4823 | 753 | Future Task |  |  | D661 | Stacey Terry | Milestone | D661 - Milestone: System Test DW/BI Execution Complete | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 752 |  |  | Stacey Terry
4824 | 754 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Create Completion of System Testing DW/BI Summary Document | 4 hrs | 10 days | Fri 3/21/25 | Thu 4/3/25 | 752FS-6 days | 755SS+5 days,757 |  | Manojkumar Gurjar,Mary Punty
4825 | 755 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Conduct System Test DW/BI Exit Criteria Review Meeting | 10 hrs | 5 days | Fri 3/28/25 | Thu 4/3/25 | 754SS+5 days | 756SS,757 |  | Manojkumar Gurjar,Mary Punty
4826 | 756 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Confirm requirements traceability for System Test DW/BI | 20 hrs | 5 days | Fri 3/28/25 | Thu 4/3/25 | 755SS | 757 |  | Manojkumar Gurjar,Mary Punty
4783 | 757 | Future Task |  |  | D661 | Stacey Terry | Submit | DEL D661 - Completion of System Test DW/BI - Draft Submission | 0 hrs | 0 days | Thu 4/3/25 | Thu 4/3/25 | 754755756 | 758 |  | Stacey Terry,Joy Schneider
4784 | 758 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 4/4/25 | Thu 4/10/25 | 757 | 759 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4785 | 759 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Style Guide Review | 1 hr | 1 day | Fri 4/11/25 | Fri 4/11/25 | 758 | 760 |  | Dusti Kincl
4786 | 760 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Final Collaborative Review | 20 hrs | 5 days | Mon 4/14/25 | Fri 4/18/25 | 759 | 761 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4787 | 761 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Accenture QC | 4 hrs | 2 days | Mon 4/21/25 | Tue 4/22/25 | 760 | 762 |  | Joy Schneider
4788 | 762 | Future Task |  |  | D661 | Stacey Terry | Submit | DEL D661 - Completion of System Test DW/BI - Submit | 0 hrs | 0 days | Tue 4/22/25 | Tue 4/22/25 | 761 | 763 |  | Joy Schneider
4789 | 763 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Department QC | 4 hrs | 1 day | Wed 4/23/25 | Wed 4/23/25 | 762 | 764 |  | Tommy Werner,Gabriela Gibson
4790 | 764 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Contract Manager Review | 8 hrs | 3 days | Thu 4/24/25 | Mon 4/28/25 | 763 | 765 |  | Sean Buchanan
4791 | 765 | Future Task |  |  | D661 | Stacey Terry | Accept | DEL D661 - Completion of System Test DW/BI - Accept | 0 hrs | 0 days | Mon 4/28/25 | Mon 4/28/25 | 764 | 1276FS+4 days | 2025-05-01 | Sean Buchanan
4792 | 766 | Future Task | Yes |  | D662 | Manojkumar Gurjar |  | D662 - Completion of Dress Rehearsal (Mock Conversion IV) | 297 hrs | 96 days | Mon 1/13/25 | Wed 5/28/25
4793 | 767 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Create | 16 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 725FS-46 days | 768 |  | Manojkumar Gurjar,Kurt Meisner
4794 | 768 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Submit | 0 hrs | 0 days | Mon 1/27/25 | Mon 1/27/25 | 767 | 769 |  | Manojkumar Gurjar,Joy Schneider
4795 | 769 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Collaborative Review | 24 hrs | 10 days | Tue 1/28/25 | Mon 2/10/25 | 768 | 770 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4796 | 770 | Future Task |  |  | D662 | Manojkumar Gurjar | Approve | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Approve | 0 hrs | 0 days | Mon 2/10/25 | Mon 2/10/25 | 769 | 772FS+24 days,771FS+24 days |  | Jimmy Cox
7210 | 771 | Future Task |  | RW | D662 | Manojkumar Gurjar | Milestone | D662 - Confirm Conversion Files Received | 0 hrs | 0 days | Fri 3/14/25 | Fri 3/14/25 | 770FS+24 days | 773 |  | Matthew Breeding
4827 | 772 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | D662 - Confirm Mock 4 Conversion - (Dress Rehearsal) Environment Readiness | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 770FS+24 days | 773 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4828 | 773 | Future Task |  | RW | D662 | Manojkumar Gurjar | Create | D662 - Create Mock 4 Conversion Checklist (Dress Rehearsal) | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 772771 | 774 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4829 | 774 | Future Task |  | RW | D662 | Manojkumar Gurjar | Create | D662 - Execute Mock 4 – Conversion (Dress Rehearsal) | 120 hrs | 10 days | Mon 3/31/25 | Fri 4/11/25 | 773 | 775 |  | Jeevan Mahajan,Janmejay Khare
4830 | 775 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | D662 - Validate Mock 4 – Conversion (Dress Rehearsal) | 20 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 774 | 776 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4831 | 776 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | D662 - Conduct Mock 4 - Conversion (Dress Rehearsal) Exit Criteria Review Meeting | 20 hrs | 5 days | Mon 4/28/25 | Fri 5/2/25 | 775 | 777 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4797 | 777 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Draft Submission | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 776 | 778 |  | Manojkumar Gurjar,Joy Schneider
4798 | 778 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 5/5/25 | Fri 5/9/25 | 777 | 779 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4799 | 779 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Style Guide Review | 1 hr | 1 day | Mon 5/12/25 | Mon 5/12/25 | 778 | 780 |  | Dusti Kincl
4800 | 780 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Final Collaborative Review | 20 hrs | 5 days | Tue 5/13/25 | Mon 5/19/25 | 779 | 781 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4801 | 781 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Accenture QC | 4 hrs | 2 days | Tue 5/20/25 | Wed 5/21/25 | 780 | 782 |  | Joy Schneider
4802 | 782 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Submit | 0 hrs | 0 days | Wed 5/21/25 | Wed 5/21/25 | 781 | 783 |  | Joy Schneider
4803 | 783 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Department QC | 4 hrs | 1 day | Thu 5/22/25 | Thu 5/22/25 | 782 | 784 |  | Tommy Werner,Gabriela Gibson
4804 | 784 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Contract Manager Review | 8 hrs | 3 days | Fri 5/23/25 | Wed 5/28/25 | 783 | 785 |  | Sean Buchanan
4805 | 785 | Future Task |  |  | D662 | Manojkumar Gurjar | Accept | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Accept | 0 hrs | 0 days | Wed 5/28/25 | Wed 5/28/25 | 784 | 1284 | 2025-05-01 | Sean Buchanan
4806 | 786 | Future Task | Yes |  | D663 | Manojkumar Gurjar |  | D663 - Completion of Interface Testing Segment I | 541.58 hrs | 223 days | Mon 8/12/24 | Mon 6/30/25
4807 | 787 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | DED D663 - Completion of Interface Testing Segment I - Create | 24 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 1 | 788 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4808 | 788 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DED D663 - Completion of Interface Testing Segment I - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 787 | 789 |  | Manojkumar Gurjar,Joy Schneider
4809 | 789 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DED D663 - Completion of Interface Testing Segment I - Collaborative Review | 28 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 788 | 790 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4810 | 790 | Future Task |  |  | D663 | Manojkumar Gurjar | Approve | DED D663 - Completion of Interface Testing Segment I - Approve | 0 hrs | 0 days | Mon 9/9/24 | Mon 9/9/24 | 789 | 792FS+19 days,791FS+15 days |  | Jimmy Cox
7244 | 791 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Confirm Agency Interface Connections Information received | 10 hrs | 9 days | Tue 10/1/24 | Fri 10/11/24 | 790FS+15 days | 793 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4832 | 792 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Create Interface Testing Segment 1 Execution Work Unit Tracker | 30 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 790FS+19 days | 793,797SS,798SS |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4833 | 793 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Review/Confirm Interface Testing Segment 1 Execution Work Unit Tracker | 15 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 792791 | 794 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4834 | 794 | Future Task |  | RW | D663 | Manojkumar Gurjar | Create | D663 - Conduct Interface Testing Segment 1 Readiness Review Meeting | 15 hrs | 5 days | Mon 10/28/24 | Fri 11/1/24 | 793 | 795 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4835 | 795 | Future Task |  | RW | D663 | Manojkumar Gurjar | Create | D663 - Conduct Interface Test Kickoff Meeting with Integration Partners | 3 hrs | 9 days | Mon 11/4/24 | Fri 11/15/24 | 794 | 796 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4836 | 796 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Confirm Interface Test Environment Readiness | 15 hrs | 5 days | Mon 11/18/24 | Fri 11/22/24 | 795556 | 799 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4837 | 797 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Establish Interface Connectivity Segment 1 | 20 hrs | 20 days | Mon 10/7/24 | Fri 11/1/24 | 792SS | 799FS+17 days |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
7223 | 798 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Completed Interface Connection Inventory Files Received | 0 hrs | 0 days | Mon 10/7/24 | Mon 10/7/24 | 792SS | 799FS+17 days |  | Matthew Breeding
4838 | 799 | Future Task |  | RW | D663 | Manojkumar Gurjar | Create | D663 - Execute Interface Testing Segment 1 | 315 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 797FS+17 days,796,798FS+17 days,1660 | 800801 |  | Rahul Yadav,Carlos Luis
4839 | 800 | Future Task |  |  | D663 | Manojkumar Gurjar | Milestone | D663 - Milestone: Interface Testing Segment 1 Complete | 0 hrs | 0 days | Wed 4/30/25 | Wed 4/30/25 | 799 | 803 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4840 | 801 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Conduct Test Exit Criteria Review Meeting | 15 hrs | 5 days | Thu 5/1/25 | Wed 5/7/25 | 799 | 802 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4841 | 802 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Confirm requirements traceability for Interface Testing Segment 1 | 15 hrs | 10 days | Thu 5/8/25 | Wed 5/21/25 | 801 | 803 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4842 | 803 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Create Completion of Interface Testing Segment 1 Summary Document | 1.58 hrs | 10 days | Thu 5/22/25 | Thu 6/5/25 | 802800 | 804 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4811 | 804 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DEL D663 - Completion of Interface Testing Segment I - Draft Submission | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 803 | 805 |  | Manojkumar Gurjar,Joy Schneider
4812 | 805 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Pre-Submission Collaborative Review | 6 hrs | 5 days | Fri 6/6/25 | Thu 6/12/25 | 804 | 806 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4813 | 806 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Style Guide Review | 1 hr | 1 day | Fri 6/13/25 | Fri 6/13/25 | 805 | 807 |  | Dusti Kincl
4814 | 807 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Final Collaborative Review | 12 hrs | 5 days | Mon 6/16/25 | Fri 6/20/25 | 806 | 808 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4815 | 808 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Accenture QC | 4 hrs | 2 days | Mon 6/23/25 | Tue 6/24/25 | 807 | 809 |  | Joy Schneider
4816 | 809 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DEL D663 - Completion of Interface Testing Segment I - Submit | 0 hrs | 0 days | Tue 6/24/25 | Tue 6/24/25 | 808 | 810 |  | Joy Schneider
4817 | 810 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Department QC | 4 hrs | 1 day | Wed 6/25/25 | Wed 6/25/25 | 809 | 811 |  | Tommy Werner,Gabriela Gibson
4818 | 811 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Contract Manager Review | 8 hrs | 3 days | Thu 6/26/25 | Mon 6/30/25 | 810 | 812 |  | Sean Buchanan
4819 | 812 | Future Task |  |  | D663 | Manojkumar Gurjar | Accept | DEL D663 - Completion of Interface Testing Segment I - Accept | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 811 |  | 2025-06-01 | Sean Buchanan
5042 | 813 | Future Task |  |  | D666 | Stacey Terry |  | D666 - Support of UAT Segment I | 111 hrs | 119 days | Mon 1/13/25 | Mon 6/30/25
5043 | 814 | Future Task |  |  | D666 | Stacey Terry | Create | DED D666 - Support of UAT Segment I - Create | 16 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 1 | 815 |  | Stacey Terry,Mary Punty
5044 | 815 | Future Task |  |  | D666 | Stacey Terry | Submit | DED D666 - Support of UAT Segment I - Submit | 0 hrs | 0 days | Mon 1/27/25 | Mon 1/27/25 | 814 | 816 |  | Stacey Terry,Joy Schneider
5045 | 816 | Future Task |  |  | D666 | Stacey Terry | Review | DED D666 - Support of UAT Segment I - Collaborative Review | 24 hrs | 10 days | Tue 1/28/25 | Mon 2/10/25 | 815 | 817 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5046 | 817 | Future Task |  |  | D666 | Stacey Terry | Approve | DED D666 - Support of UAT Segment I - Approve | 0 hrs | 0 days | Mon 2/10/25 | Mon 2/10/25 | 816 | 818FS+24 days |  | Jimmy Cox
5056 | 818 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Identify UAT support resources for UAT Segment 1 | 20 hrs | 11 days | Mon 3/17/25 | Mon 3/31/25 | 817FS+24 days | 819 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5057 | 819 | Future Task |  | RW | D666 | Stacey Terry | Create | D666 - Participate in UAT sessions for UAT Segment 1 | 6 hrs | 43 days | Tue 4/1/25 | Fri 5/30/25 | 818 | 820SS,857 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp
5058 | 820 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Support resolution of UAT issues for UAT Segment 1 | 7 hrs | 42 days | Tue 4/1/25 | Thu 5/29/25 | 819SS | 821FS-4 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
5059 | 821 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Confirm requirements traceability for UAT Segment 1 | 3 hrs | 4 days | Fri 5/23/25 | Thu 5/29/25 | 820FS-4 days | 822SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5060 | 822 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Create UAT Segment 1 Summary Document | 3 hrs | 9 days | Fri 5/23/25 | Thu 6/5/25 | 821SS | 823 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5047 | 823 | Future Task |  |  | D666 | Stacey Terry | Submit | DEL D666 - Support of UAT Segment I - Draft Submission | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 822 | 824 |  | Stacey Terry,Joy Schneider
5048 | 824 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Pre-Submission Collaborative Review | 5 hrs | 5 days | Fri 6/6/25 | Thu 6/12/25 | 823 | 825 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5049 | 825 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Style Guide Review | 1 hr | 1 day | Fri 6/13/25 | Fri 6/13/25 | 824 | 826 |  | Dusti Kincl
5050 | 826 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Final Collaborative Review | 10 hrs | 5 days | Mon 6/16/25 | Fri 6/20/25 | 825 | 827 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5051 | 827 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Accenture QC | 4 hrs | 2 days | Mon 6/23/25 | Tue 6/24/25 | 826 | 828 |  | Joy Schneider
5052 | 828 | Future Task |  |  | D666 | Stacey Terry | Submit | DEL D666 - Support of UAT Segment I - Submit | 0 hrs | 0 days | Tue 6/24/25 | Tue 6/24/25 | 827 | 829 |  | Joy Schneider
5053 | 829 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Department QC | 4 hrs | 1 day | Wed 6/25/25 | Wed 6/25/25 | 828 | 830 |  | Tommy Werner,Gabriela Gibson
5054 | 830 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Contract Manager Review | 8 hrs | 3 days | Thu 6/26/25 | Mon 6/30/25 | 829 | 831 |  | Sean Buchanan
5055 | 831 | Future Task |  |  | D666 | Stacey Terry | Accept | DEL D666 - Support of UAT Segment I - Accept | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 830 |  | 2025-06-01 | Sean Buchanan
5520 | 832 | Future Task | Yes |  | D667 | Stacey Terry |  | D667 - Completion of Mock Go-Lives (Dry Run #1) | 285 hrs | 81 days | Mon 4/7/25 | Wed 7/30/25
5521 | 833 | Future Task |  |  | D667 | Stacey Terry | Create | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Create | 6 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 1 | 834 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5522 | 834 | Future Task |  |  | D667 | Stacey Terry | Submit | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Submit | 0 hrs | 0 days | Fri 4/18/25 | Fri 4/18/25 | 833 | 835 |  | Stacey Terry,Joy Schneider
5523 | 835 | Future Task |  |  | D667 | Stacey Terry | Review | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Collaborative Review | 8 hrs | 10 days | Mon 4/21/25 | Fri 5/2/25 | 834 | 836 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5524 | 836 | Future Task |  |  | D667 | Stacey Terry | Approve | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Approve | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 835 | 837 |  | Jimmy Cox
6697 | 837 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Confirm Mock Go-Live Dry Run #1 Execution Readiness | 3 hrs | 5 days | Mon 6/2/25 | Fri 6/6/25 | 836565 | 838 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6698 | 838 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Execute Mock Go-Live Dry Run #1 | 180 hrs | 10 days | Mon 6/9/25 | Fri 6/20/25 | 837 | 839 |  | Kurt Meisner,Glaiza Barnes,Roxanne Camba
6699 | 839 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Document Mock Go-Live Dry Run Results #1 | 6 hrs | 5 days | Mon 6/23/25 | Fri 6/27/25 | 838 | 840 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6700 | 840 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Create Mock Go-Live Dry Run #1 Summary Document | 6 hrs | 5 days | Mon 6/30/25 | Mon 7/7/25 | 839 | 842,841SS+2 days |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
7204 | 841 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Update Deployment & Contingency Plan based on Mock Go-Live Dry Run #1 results | 3 hrs | 2 days | Wed 7/2/25 | Thu 7/3/25 | 840SS+2 days | 842 |  | Stacey Terry,Mary Punty,Manojkumar Gurjar
5525 | 842 | Future Task |  |  | D667 | Stacey Terry | Submit | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Draft Submission | 0 hrs | 0 days | Mon 7/7/25 | Mon 7/7/25 | 840841 | 843 |  | Stacey Terry,Joy Schneider
5526 | 843 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Pre-Submission Collaborative Review | 28 hrs | 5 days | Tue 7/8/25 | Mon 7/14/25 | 842 | 844 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5527 | 844 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Style Guide Review | 1 hr | 1 day | Tue 7/15/25 | Tue 7/15/25 | 843 | 845 |  | Dusti Kincl
5528 | 845 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Final Collaborative Review | 28 hrs | 5 days | Wed 7/16/25 | Tue 7/22/25 | 844 | 846 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5529 | 846 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Accenture QC | 4 hrs | 2 days | Wed 7/23/25 | Thu 7/24/25 | 845 | 847 |  | Joy Schneider
5530 | 847 | Future Task |  |  | D667 | Stacey Terry | Submit | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Submit | 0 hrs | 0 days | Thu 7/24/25 | Thu 7/24/25 | 846 | 848 |  | Joy Schneider
5531 | 848 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Department QC | 4 hrs | 1 day | Fri 7/25/25 | Fri 7/25/25 | 847 | 849 |  | Tommy Werner,Gabriela Gibson
5532 | 849 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Contract Manager Review | 8 hrs | 3 days | Mon 7/28/25 | Wed 7/30/25 | 848 | 850 |  | Sean Buchanan
5533 | 850 | Future Task |  |  | D667 | Stacey Terry | Accept | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Accept | 0 hrs | 0 days | Wed 7/30/25 | Wed 7/30/25 | 849 | 1284 | 2025-07-01 | Sean Buchanan
5061 | 851 | Future Task |  |  | D669 | Stacey Terry |  | D669 - Support of UAT Segment II | 114 hrs | 97 days | Mon 4/14/25 | Thu 8/28/25
5062 | 852 | Future Task |  |  | D669 | Stacey Terry | Create | DED D669 - Support of UAT Segment II - Create | 2 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 1 | 853 |  | Stacey Terry,Mary Punty
5063 | 853 | Future Task |  |  | D669 | Stacey Terry | Submit | DED D669 - Support of UAT Segment II - Submit | 0 hrs | 0 days | Fri 4/25/25 | Fri 4/25/25 | 852 | 854 |  | Stacey Terry,Joy Schneider
5064 | 854 | Future Task |  |  | D669 | Stacey Terry | Review | DED D669 - Support of UAT Segment II - Collaborative Review | 12 hrs | 10 days | Mon 4/28/25 | Fri 5/9/25 | 853 | 855 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5065 | 855 | Future Task |  |  | D669 | Stacey Terry | Approve | DED D669 - Support of UAT Segment II - Approve | 0 hrs | 0 days | Fri 5/9/25 | Fri 5/9/25 | 854 | 856FS+8 days |  | Jimmy Cox
5075 | 856 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Identify UAT support resources for UAT Segment 2 | 6 hrs | 5 days | Thu 5/22/25 | Thu 5/29/25 | 855FS+8 days | 857 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5076 | 857 | Future Task |  | RW | D669 | Stacey Terry | Create | D669 - Participate in UAT sessions for UAT Segment 2 | 6 hrs | 43 days | Mon 6/2/25 | Thu 7/31/25 | 856819 | 858SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp
5077 | 858 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Support resolution of UAT issues for UAT Segment 2 | 7 hrs | 43 days | Mon 6/2/25 | Thu 7/31/25 | 857SS | 859FS-4 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
5078 | 859 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Confirm requirements traceability for UAT Segment 2 | 3 hrs | 4 days | Mon 7/28/25 | Thu 7/31/25 | 858FS-4 days | 860SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5079 | 860 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Create UAT Segment 2 Summary Document | 21 hrs | 7 days | Mon 7/28/25 | Tue 8/5/25 | 859SS | 861 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5066 | 861 | Future Task |  |  | D669 | Stacey Terry | Submit | DEL D669 - Support of UAT Segment II - Draft Submission | 0 hrs | 0 days | Tue 8/5/25 | Tue 8/5/25 | 860 | 862 |  | Stacey Terry,Joy Schneider
5067 | 862 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Wed 8/6/25 | Tue 8/12/25 | 861 | 863 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5068 | 863 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Style Guide Review | 1 hr | 1 day | Wed 8/13/25 | Wed 8/13/25 | 862 | 864 |  | Dusti Kincl
5069 | 864 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Final Collaborative Review | 20 hrs | 5 days | Thu 8/14/25 | Wed 8/20/25 | 863 | 865 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5070 | 865 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Accenture QC | 4 hrs | 2 days | Thu 8/21/25 | Fri 8/22/25 | 864 | 866 |  | Joy Schneider
5071 | 866 | Future Task |  |  | D669 | Stacey Terry | Submit | DEL D669 - Support of UAT Segment II - Submit | 0 hrs | 0 days | Fri 8/22/25 | Fri 8/22/25 | 865 | 867 |  | Joy Schneider
5072 | 867 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Department QC | 4 hrs | 1 day | Mon 8/25/25 | Mon 8/25/25 | 866 | 868 |  | Tommy Werner,Gabriela Gibson
5073 | 868 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Contract Manager Review | 8 hrs | 3 days | Tue 8/26/25 | Thu 8/28/25 | 867 | 869 |  | Sean Buchanan
5074 | 869 | Future Task |  |  | D669 | Stacey Terry | Accept | DEL D669 - Support of UAT Segment II - Accept | 0 hrs | 0 days | Thu 8/28/25 | Thu 8/28/25 | 868 |  | 2025-08-01 | Sean Buchanan
4843 | 870 | Future Task | Yes |  | D670 | Stacey Terry |  | D670 - Completion of Payroll Parallel Testing | 1,689 hrs | 133 days | Mon 2/24/25 | Fri 8/29/25
4844 | 871 | Future Task |  |  | D670 | Stacey Terry | Create | DED D670 - Completion of Payroll Parallel Testing - Create | 16 hrs | 10 days | Mon 2/24/25 | Fri 3/7/25 | 744FS-37 days | 872 |  | Stacey Terry,Mary Punty
4845 | 872 | Future Task |  |  | D670 | Stacey Terry | Submit | DED D670 - Completion of Payroll Parallel Testing - Submit | 0 hrs | 0 days | Fri 3/7/25 | Fri 3/7/25 | 871 | 873 |  | Stacey Terry,Joy Schneider
4846 | 873 | Future Task |  |  | D670 | Stacey Terry | Review | DED D670 - Completion of Payroll Parallel Testing - Collaborative Review | 24 hrs | 10 days | Mon 3/10/25 | Fri 3/21/25 | 872 | 874 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4847 | 874 | Future Task |  |  | D670 | Stacey Terry | Approve | DED D670 - Completion of Payroll Parallel Testing - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 873 | 875 |  | Jimmy Cox
4955 | 875 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Create Work Unit Tracker for Payroll Parallel Test Execution | 40 hrs | 10 days | Mon 3/24/25 | Fri 4/4/25 | 874 | 876 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty
4956 | 876 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Review, Update and confirm Work Unit Tracker for Payroll Parallel Test Execution | 20 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 875 | 877 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Jennifer Peddicord
4957 | 877 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Confirm Payroll Parallel Test Environment Readiness | 20 hrs | 5 days | Mon 4/21/25 | Fri 4/25/25 | 876 | 878 |  | Manojkumar Gurjar,Jarad Hermann
4958 | 878 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Conduct Parallel Payroll Test Kick Off Meeting | 12 hrs | 5 days | Mon 4/28/25 | Fri 5/2/25 | 877 | 879 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Jennifer Peddicord
4959 | 879 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Execute Parallel Payroll Testing | 1,440 hrs | 60 days | Mon 5/5/25 | Tue 7/29/25 | 878 | 880,881FS-4 days |  | Tim Elmer,Deana Metcalf,Jennifer Peddicord,Rochelle Martin
4960 | 880 | Future Task |  |  | D670 | Stacey Terry | Milestone | D670 - Milestone: Payroll Parallel Test Execution Complete | 0 hrs | 0 days | Tue 7/29/25 | Tue 7/29/25 | 879 | 884 |  | Stacey Terry
4961 | 881 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Conduct Payroll Parallel Test Exit Criteria Review Meeting | 10 hrs | 10 days | Thu 7/24/25 | Wed 8/6/25 | 879FS-4 days | 882SS,883SS,884 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
4962 | 882 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Confirm requirements traceability for Payroll Parallel test | 20 hrs | 10 days | Thu 7/24/25 | Wed 8/6/25 | 881SS | 884 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty
4963 | 883 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Create Completion of Payroll Parallel Test Summary Document | 30 hrs | 10 days | Thu 7/24/25 | Wed 8/6/25 | 881SS | 884 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4848 | 884 | Future Task |  |  | D670 | Stacey Terry | Submit | DEL D670 - Completion of Payroll Parallel Testing - Draft Submission | 0 hrs | 0 days | Wed 8/6/25 | Wed 8/6/25 | 880881883882 | 885 |  | Stacey Terry,Joy Schneider
4849 | 885 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Pre-Submission Collaborative Review | 20 hrs | 5 days | Thu 8/7/25 | Wed 8/13/25 | 884 | 886 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4850 | 886 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Style Guide Review | 1 hr | 1 day | Thu 8/14/25 | Thu 8/14/25 | 885 | 887 |  | Dusti Kincl
4851 | 887 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Final Collaborative Review | 20 hrs | 5 days | Fri 8/15/25 | Thu 8/21/25 | 886 | 888 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4852 | 888 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Accenture QC | 4 hrs | 2 days | Fri 8/22/25 | Mon 8/25/25 | 887 | 889 |  | Joy Schneider
4853 | 889 | Future Task |  |  | D670 | Stacey Terry | Submit | DEL D670 - Completion of Payroll Parallel Testing - Submit | 0 hrs | 0 days | Mon 8/25/25 | Mon 8/25/25 | 888 | 890 |  | Joy Schneider
4854 | 890 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Department QC | 4 hrs | 1 day | Tue 8/26/25 | Tue 8/26/25 | 889 | 891 |  | Tommy Werner,Gabriela Gibson
4855 | 891 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Contract Manager Review | 8 hrs | 3 days | Wed 8/27/25 | Fri 8/29/25 | 890 | 892 |  | Sean Buchanan
4856 | 892 | Future Task |  |  | D670 | Stacey Terry | Accept | DEL D670 - Completion of Payroll Parallel Testing - Accept | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 891 |  | 2025-08-01 | Sean Buchanan
4857 | 893 | Future Task | Yes |  | D671 | Manojkumar Gurjar |  | D671 - Completion of Interface Testing Segment II | 1,217 hrs | 180 days | Mon 2/3/25 | Wed 10/15/25
4858 | 894 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | DED D671 - Completion of Interface Testing Segment II - Create | 6 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1 | 895 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4859 | 895 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DED D671 - Completion of Interface Testing Segment II - Submit | 0 hrs | 0 days | Fri 2/14/25 | Fri 2/14/25 | 894 | 896 |  | Manojkumar Gurjar,Joy Schneider
4860 | 896 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DED D671 - Completion of Interface Testing Segment II - Collaborative Review | 8 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 895 | 897 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4861 | 897 | Future Task |  |  | D671 | Manojkumar Gurjar | Approve | DED D671 - Completion of Interface Testing Segment II - Approve | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 896 | 898FS+20 days |  | Jimmy Cox
4964 | 898 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Create Interface Testing Segment 2 Execution Work Unit Tracker | 6 hrs | 4 days | Mon 3/31/25 | Thu 4/3/25 | 897FS+20 days | 899 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4965 | 899 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Review/Confirm Interface Testing Segment 2 Execution Work Unit Tracker | 6 hrs | 4 days | Fri 4/4/25 | Wed 4/9/25 | 898 | 900 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4966 | 900 | Future Task |  | RW | D671 | Manojkumar Gurjar | Create | D671 - Conduct Interface Testing Segment 2 Readiness Review Meeting | 15 hrs | 5 days | Thu 4/10/25 | Wed 4/16/25 | 899 | 901 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4967 | 901 | Future Task |  | RW | D671 | Manojkumar Gurjar | Create | D671 - Conduct Interface Test Kickoff Meeting with Integration Partners | 30 hrs | 5 days | Thu 4/17/25 | Wed 4/23/25 | 900 | 902 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4968 | 902 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Confirm Interface Test Environment Readiness | 15 hrs | 5 days | Thu 4/24/25 | Wed 4/30/25 | 901 | 903 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4969 | 903 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Establish Interface Connectivity Segment 2 | 20 hrs | 7 days | Thu 5/1/25 | Fri 5/9/25 | 902 | 904 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4970 | 904 | Future Task |  | RW | D671 | Manojkumar Gurjar | Create | D671 - Execute Interface Testing Segment 2 | 936 hrs | 78 days | Mon 5/12/25 | Fri 8/29/25 | 903 | 905 |  | Rahul Yadav,Carlos Luis
4971 | 905 | Future Task |  |  | D671 | Manojkumar Gurjar | Milestone | D671 - Milestone: Interface Testing Segment 2 Complete | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 904 | 906 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4972 | 906 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Conduct Test Exit Criteria Review Meeting | 30 hrs | 5 days | Tue 9/2/25 | Mon 9/8/25 | 905 | 907 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4973 | 907 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Confirm requirements traceability for Interface Testing Segment 2 | 40 hrs | 5 days | Tue 9/9/25 | Mon 9/15/25 | 906 | 908 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4974 | 908 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Create Completion of Interface Testing Segment 2 deliverable (D671) | 40 hrs | 5 days | Tue 9/16/25 | Mon 9/22/25 | 907 | 909 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4862 | 909 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DEL D671 - Completion of Interface Testing Segment II - Draft Submission | 0 hrs | 0 days | Mon 9/22/25 | Mon 9/22/25 | 908 | 910 |  | Manojkumar Gurjar,Joy Schneider
4863 | 910 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Pre-Submission Collaborative Review | 24 hrs | 5 days | Tue 9/23/25 | Mon 9/29/25 | 909 | 911 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4864 | 911 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Style Guide Review | 1 hr | 1 day | Tue 9/30/25 | Tue 9/30/25 | 910 | 912 |  | Dusti Kincl
4865 | 912 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Final Collaborative Review | 24 hrs | 5 days | Wed 10/1/25 | Tue 10/7/25 | 911 | 913 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4866 | 913 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Accenture QC | 4 hrs | 2 days | Wed 10/8/25 | Thu 10/9/25 | 912 | 914 |  | Joy Schneider
4867 | 914 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DEL D671 - Completion of Interface Testing Segment II - Submit | 0 hrs | 0 days | Thu 10/9/25 | Thu 10/9/25 | 913 | 915 |  | Joy Schneider
4868 | 915 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Department QC | 4 hrs | 1 day | Fri 10/10/25 | Fri 10/10/25 | 914 | 916 |  | Tommy Werner,Gabriela Gibson
4869 | 916 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Contract Manager Review | 8 hrs | 3 days | Mon 10/13/25 | Wed 10/15/25 | 915 | 917 |  | Sean Buchanan
4870 | 917 | Future Task |  |  | D671 | Manojkumar Gurjar | Accept | DEL D671 - Completion of Interface Testing Segment II - Accept | 0 hrs | 0 days | Wed 10/15/25 | Wed 10/15/25 | 916 |  | 2025-10-01 | Sean Buchanan
4871 | 918 | Future Task |  |  | D672 | Stacey Terry |  | D672 - Support of UAT Segment III | 116 hrs | 123 days | Tue 6/24/25 | Thu 12/18/25
4872 | 919 | Future Task |  |  | D672 | Stacey Terry | Create | DED D672 - Support of UAT Segment III - Create | 16 hrs | 10 days | Tue 6/24/25 | Tue 7/8/25 | 1 | 920 |  | Stacey Terry,Mary Punty
4873 | 920 | Future Task |  |  | D672 | Stacey Terry | Submit | DED D672 - Support of UAT Segment III - Submit | 0 hrs | 0 days | Tue 7/8/25 | Tue 7/8/25 | 919 | 921 |  | Stacey Terry,Joy Schneider
4874 | 921 | Future Task |  |  | D672 | Stacey Terry | Review | DED D672 - Support of UAT Segment III - Collaborative Review | 24 hrs | 10 days | Wed 7/9/25 | Tue 7/22/25 | 920 | 922 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4875 | 922 | Future Task |  |  | D672 | Stacey Terry | Approve | DED D672 - Support of UAT Segment III - Approve | 0 hrs | 0 days | Tue 7/22/25 | Tue 7/22/25 | 921 | 923 |  | Jimmy Cox
4975 | 923 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Identify UAT support resources for UAT Segment 3 | 6 hrs | 7 days | Wed 7/23/25 | Thu 7/31/25 | 922 | 924 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4976 | 924 | Future Task |  | RW | D672 | Stacey Terry | Create | D672 - Participate in UAT sessions for UAT Segment 3 | 6 hrs | 77 days | Fri 8/1/25 | Wed 11/19/25 | 923 | 925SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp
4977 | 925 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Support resolution of UAT issues for UAT Segment 3 | 7 hrs | 77 days | Fri 8/1/25 | Wed 11/19/25 | 924SS | 926FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
4978 | 926 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Confirm requirements traceability for UAT Segment 3 | 3 hrs | 5 days | Thu 11/13/25 | Wed 11/19/25 | 925FS-5 days | 927SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4979 | 927 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Create UAT Segment 3 Summary Document | 3 hrs | 7 days | Thu 11/13/25 | Fri 11/21/25 | 926SS | 928 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4876 | 928 | Future Task |  |  | D672 | Stacey Terry | Submit | DEL D672 - Support of UAT Segment III - Draft Submission | 0 hrs | 0 days | Fri 11/21/25 | Fri 11/21/25 | 927 | 929 |  | Stacey Terry,Joy Schneider
4877 | 929 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 11/24/25 | Tue 12/2/25 | 928 | 930 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4878 | 930 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Style Guide Review | 1 hr | 1 day | Wed 12/3/25 | Wed 12/3/25 | 929 | 931 |  | Dusti Kincl
4879 | 931 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Final Collaborative Review | 20 hrs | 5 days | Thu 12/4/25 | Wed 12/10/25 | 930 | 932 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4880 | 932 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Accenture QC | 4 hrs | 2 days | Thu 12/11/25 | Fri 12/12/25 | 931 | 933 |  | Francisca Li
4881 | 933 | Future Task |  |  | D672 | Stacey Terry | Submit | DEL D672 - Support of UAT Segment III - Submit | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 932 | 934 |  | Joy Schneider
4882 | 934 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Department QC | 4 hrs | 1 day | Mon 12/15/25 | Mon 12/15/25 | 933 | 935 |  | Tommy Werner,Gabriela Gibson
4883 | 935 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Contract Manager Review | 2 hrs | 3 days | Tue 12/16/25 | Thu 12/18/25 | 934 | 936 |  | Sean Buchanan
4884 | 936 | Future Task |  |  | D672 | Stacey Terry | Accept | DEL D672 - Support of UAT Segment III - Accept | 0 hrs | 0 days | Thu 12/18/25 | Thu 12/18/25 | 935 |  | 2025-11-01 | Sean Buchanan
4885 | 937 | Future Task | Yes |  | D673 | Stacey Terry |  | D673 - Completion of Mock Go-Lives (Dry Run #2) | 366 hrs | 86 days | Mon 7/7/25 | Tue 11/4/25
4886 | 938 | Future Task |  |  | D673 | Stacey Terry | Create | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Create | 24 hrs | 10 days | Mon 7/7/25 | Fri 7/18/25 | 1 | 939 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4887 | 939 | Future Task |  |  | D673 | Stacey Terry | Submit | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Submit | 0 hrs | 0 days | Fri 7/18/25 | Fri 7/18/25 | 938 | 940 |  | Stacey Terry,Joy Schneider
4888 | 940 | Future Task |  |  | D673 | Stacey Terry | Review | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Collaborative Review | 32 hrs | 10 days | Mon 7/21/25 | Fri 8/1/25 | 939 | 941 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4889 | 941 | Future Task |  |  | D673 | Stacey Terry | Approve | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Approve | 0 hrs | 0 days | Fri 8/1/25 | Fri 8/1/25 | 940 | 942FS+20 days |  | Jimmy Cox
4980 | 942 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Confirm Mock Go-Live Dry Run #2 Execution Readiness | 24 hrs | 4 days | Tue 9/2/25 | Fri 9/5/25 | 941FS+20 days | 943 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4981 | 943 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Execute Mock Go-Live Dry Run #2 | 160 hrs | 10 days | Mon 9/8/25 | Fri 9/19/25 | 942 | 944 |  | Kurt Meisner,Glaiza Barnes,Roxanne Camba
4982 | 944 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Document Mock Go-Live Dry Run Results #2 | 30 hrs | 5 days | Mon 9/22/25 | Fri 9/26/25 | 943 | 945 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4983 | 945 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Create Mock Go-Live Dry Run #2 Summary Document | 20 hrs | 10 days | Mon 9/29/25 | Fri 10/10/25 | 944 | 947,946SS+2 days |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
7205 | 946 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Update Deployment & Contingency Plan based on Mock Go-Live Dry Run #2 results | 3 hrs | 2 days | Wed 10/1/25 | Thu 10/2/25 | 945SS+2 days | 947 |  | Stacey Terry,Mary Punty,Manojkumar Gurjar
4890 | 947 | Future Task |  |  | D673 | Stacey Terry | Submit | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Draft Submission | 0 hrs | 0 days | Fri 10/10/25 | Fri 10/10/25 | 945946 | 948 |  | Stacey Terry,Joy Schneider
4891 | 948 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Pre-Submission Collaborative Review | 28 hrs | 5 days | Mon 10/13/25 | Fri 10/17/25 | 947 | 949 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4892 | 949 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Style Guide Review | 1 hr | 1 day | Mon 10/20/25 | Mon 10/20/25 | 948 | 950 |  | Dusti Kincl
4893 | 950 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Final Collaborative Review | 28 hrs | 5 days | Tue 10/21/25 | Mon 10/27/25 | 949 | 951 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4894 | 951 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Accenture QC | 4 hrs | 2 days | Tue 10/28/25 | Wed 10/29/25 | 950 | 952 |  | Joy Schneider
4895 | 952 | Future Task |  |  | D673 | Stacey Terry | Submit | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Submit | 0 hrs | 0 days | Wed 10/29/25 | Wed 10/29/25 | 951 | 953 |  | Joy Schneider
4896 | 953 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Department QC | 4 hrs | 1 day | Thu 10/30/25 | Thu 10/30/25 | 952 | 954 |  | Tommy Werner,Gabriela Gibson
4897 | 954 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Contract Manager Review | 8 hrs | 3 days | Fri 10/31/25 | Tue 11/4/25 | 953 | 955 |  | Sean Buchanan
4898 | 955 | Future Task |  |  | D673 | Stacey Terry | Accept | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Accept | 0 hrs | 0 days | Tue 11/4/25 | Tue 11/4/25 | 954 | 1284 | 2025-11-01 | Sean Buchanan
4899 | 956 | Future Task | Yes |  | D674 | Jarad Hermann |  | D674 - Completion of Penetration Testing | 346 hrs | 164 days | Mon 4/7/25 | Wed 11/26/25
4900 | 957 | Future Task |  |  | D674 | Jarad Hermann | Create | DED D674 - Completion of Penetration Testing - Create | 2 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 1212FS+10 days,1247FS+10 days | 958 | Note: should be in version we go live with | Jarad Hermann,Mary Punty
4901 | 958 | Future Task |  |  | D674 | Jarad Hermann | Submit | DED D674 - Completion of Penetration Testing - Submit | 0 hrs | 0 days | Fri 4/18/25 | Fri 4/18/25 | 957 | 959 |  | Jarad Hermann,Joy Schneider
4902 | 959 | Future Task |  |  | D674 | Jarad Hermann | Review | DED D674 - Completion of Penetration Testing - Collaborative Review | 5 hrs | 10 days | Mon 4/21/25 | Fri 5/2/25 | 958 | 960 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4903 | 960 | Future Task |  |  | D674 | Jarad Hermann | Approve | DED D674 - Completion of Penetration Testing - Approve | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 959 | 961FS+19 days |  | Jimmy Cox
4984 | 961 | Future Task |  |  | D674 | Jarad Hermann | Create | D674 - Execute/Complete Penetration Test | 256 hrs | 64 days | Mon 6/2/25 | Fri 8/29/25 | 960FS+19 days | 962 |  | Vivek Sharma,Matthew Warren
4985 | 962 | Future Task |  |  | D674 | Jarad Hermann | Create | D674 - Review Penetration Test Outcome | 10 hrs | 20 days | Tue 9/2/25 | Mon 9/29/25 | 961 | 963SS |  | Jarad Hermann,Bryan Sohayda
4986 | 963 | Future Task |  |  | D674 | Jarad Hermann | Create | D674 - Remediate Penetration Test | 10 hrs | 44 days | Tue 9/2/25 | Fri 10/31/25 | 962SS | 964SS |  | Jarad Hermann,Bryan Sohayda
4987 | 964 | Future Task |  |  | D674 | Jarad Hermann | Create | D674 - Create Final Pen Testing Results/Remediation Summary Report | 20 hrs | 44 days | Tue 9/2/25 | Fri 10/31/25 | 963SS | 965 |  | Jarad Hermann,Bryan Sohayda
4904 | 965 | Future Task |  |  | D674 | Jarad Hermann | Submit | DEL D674 - Completion of Penetration Testing - Draft Submission | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 964 | 966 |  | Jarad Hermann,Joy Schneider
4905 | 966 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 11/3/25 | Fri 11/7/25 | 965 | 967 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4906 | 967 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Style Guide Review | 1 hr | 1 day | Mon 11/10/25 | Mon 11/10/25 | 966 | 968 |  | Dusti Kincl
4907 | 968 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Final Collaborative Review | 16 hrs | 5 days | Wed 11/12/25 | Tue 11/18/25 | 967 | 969 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4908 | 969 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Accenture QC | 4 hrs | 2 days | Wed 11/19/25 | Thu 11/20/25 | 968 | 970 |  | Joy Schneider
4909 | 970 | Future Task |  |  | D674 | Jarad Hermann | Submit | DEL D674 - Completion of Penetration Testing - Submit | 0 hrs | 0 days | Thu 11/20/25 | Thu 11/20/25 | 969 | 971 |  | Joy Schneider
4910 | 971 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Department QC | 4 hrs | 1 day | Fri 11/21/25 | Fri 11/21/25 | 970 | 972 |  | Tommy Werner,Gabriela Gibson
4911 | 972 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Contract Manager Review | 2 hrs | 3 days | Mon 11/24/25 | Wed 11/26/25 | 971 | 973 |  | Sean Buchanan
4912 | 973 | Future Task |  |  | D674 | Jarad Hermann | Accept | DEL D674 - Completion of Penetration Testing - Accept | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 972 | 1284 | 2025-11-01 | Sean Buchanan
4913 | 974 | Future Task | Yes |  | D675 | Jarad Hermann |  | D675 - Completion of Performance Testing | 824 hrs | 159 days | Mon 4/14/25 | Wed 11/26/25
4914 | 975 | Future Task |  |  | D675 | Jarad Hermann | Create | DED D675 - Completion of Performance Testing - Create | 2 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 1200FS-28 days,1236FS-28 days | 976 |  | Jarad Hermann,Mary Punty
4915 | 976 | Future Task |  |  | D675 | Jarad Hermann | Submit | DED D675 - Completion of Performance Testing - Submit | 0 hrs | 0 days | Fri 4/25/25 | Fri 4/25/25 | 975 | 977 |  | Jarad Hermann,Joy Schneider
4916 | 977 | Future Task |  |  | D675 | Jarad Hermann | Review | DED D675 - Completion of Performance Testing - Collaborative Review | 5 hrs | 10 days | Mon 4/28/25 | Fri 5/9/25 | 976 | 978 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4917 | 978 | Future Task |  |  | D675 | Jarad Hermann | Approve | DED D675 - Completion of Performance Testing - Approve | 0 hrs | 0 days | Fri 5/9/25 | Fri 5/9/25 | 977 | 979 |  | Jimmy Cox
4988 | 979 | Future Task |  |  | D675 | Jarad Hermann | Create | D675 - Execute Performance Testing | 648 hrs | 108 days | Mon 6/2/25 | Fri 10/31/25 | 978567 | 980FS-10 days,983 |  | Vivek Sharma,Matthew Warren,Rob Lazar
4989 | 980 | Future Task |  |  | D675 | Jarad Hermann | Create | D675 - Create Completion of Performance Testing Summary Document | 40 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 979FS-10 days | 981SS,982SS,983 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4990 | 981 | Future Task |  |  | D675 | Jarad Hermann | Create | D675 - Conduct Performance Testing Exit Criteria Review Meeting | 40 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 980SS | 983 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4991 | 982 | Future Task |  |  | D675 | Jarad Hermann | Create | D675 - Confirm requirements traceability for Performance Testing | 40 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 980SS | 983 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4918 | 983 | Future Task |  |  | D675 | Jarad Hermann | Submit | DEL D675 - Completion of Performance Testing - Draft Submission | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 982979980981 | 984 |  | Jarad Hermann,Joy Schneider
4919 | 984 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 11/3/25 | Fri 11/7/25 | 983 | 985 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4920 | 985 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Style Guide Review | 1 hr | 1 day | Mon 11/10/25 | Mon 11/10/25 | 984 | 986 |  | Dusti Kincl
4921 | 986 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Final Collaborative Review | 16 hrs | 5 days | Wed 11/12/25 | Tue 11/18/25 | 985 | 987 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4922 | 987 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Accenture QC | 4 hrs | 2 days | Wed 11/19/25 | Thu 11/20/25 | 986 | 988 |  | Joy Schneider
4923 | 988 | Future Task |  |  | D675 | Jarad Hermann | Submit | DEL D675 - Completion of Performance Testing - Submit | 0 hrs | 0 days | Thu 11/20/25 | Thu 11/20/25 | 987 | 989 |  | Joy Schneider
4924 | 989 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Department QC | 4 hrs | 1 day | Fri 11/21/25 | Fri 11/21/25 | 988 | 990 |  | Tommy Werner,Gabriela Gibson
4925 | 990 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Contract Manager Review | 8 hrs | 3 days | Mon 11/24/25 | Wed 11/26/25 | 989 | 991 |  | Sean Buchanan
4926 | 991 | Future Task |  |  | D675 | Jarad Hermann | Accept | DEL D675 - Completion of Performance Testing - Accept | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 990 | 1284 | 2025-11-01 | Sean Buchanan
4927 | 992 | Future Task | Yes |  | D676 | Jarad Hermann |  | D676 - Completion of Disaster Recovery Testing | 411 hrs | 135 days | Mon 2/3/25 | Tue 8/12/25
4928 | 993 | Future Task |  |  | D676 | Jarad Hermann | Create | DED D676 - Completion of Disaster Recovery Testing - Create | 8 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1224FS-35 days,1186FS-35 days,1173 | 994 |  | Jarad Hermann,Mary Punty
4929 | 994 | Future Task |  |  | D676 | Jarad Hermann | Submit | DED D676 - Completion of Disaster Recovery Testing - Submit | 0 hrs | 0 days | Fri 2/14/25 | Fri 2/14/25 | 993 | 995 |  | Jarad Hermann,Joy Schneider
4930 | 995 | Future Task |  |  | D676 | Jarad Hermann | Review | DED D676 - Completion of Disaster Recovery Testing - Collaborative Review | 20 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 994 | 996 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4931 | 996 | Future Task |  |  | D676 | Jarad Hermann | Approve | DED D676 - Completion of Disaster Recovery Testing - Approve | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 995 | 997 |  | Jimmy Cox
4992 | 997 | Future Task |  |  | D676 | Jarad Hermann | Create | D676 - Execute Disaster Recovery Testing | 256 hrs | 64 days | Tue 4/1/25 | Mon 6/30/25 | 996,569FS+1 day | 998 |  | Vivek Sharma,Matthew Warren
4993 | 998 | Future Task |  |  | D676 | Jarad Hermann | Create | D676 - Create Completion of Disaster Recovery Testing Summary Document | 26 hrs | 13 days | Tue 7/1/25 | Fri 7/18/25 | 997 | 999SS,1000SS,1001 |  | Jarad Hermann,Vivek Sharma
4994 | 999 | Future Task |  |  | D676 | Jarad Hermann | Create | D676 - Conduct Disaster Recovery Testing Exit Criteria Review Meeting | 26 hrs | 13 days | Tue 7/1/25 | Fri 7/18/25 | 998SS | 1001 |  | Jarad Hermann,Vivek Sharma
4995 | 1000 | Future Task |  |  | D676 | Jarad Hermann | Create | D676 - Confirm requirements traceability for Disaster Recovery Testing | 26 hrs | 13 days | Tue 7/1/25 | Fri 7/18/25 | 998SS | 1001 |  | Jarad Hermann,Vivek Sharma
4932 | 1001 | Future Task |  |  | D676 | Jarad Hermann | Submit | DEL D676 - Completion of Disaster Recovery Testing - Draft Submission | 0 hrs | 0 days | Fri 7/18/25 | Fri 7/18/25 | 1000998999 | 1002 |  | Jarad Hermann,Joy Schneider
4933 | 1002 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 7/21/25 | Fri 7/25/25 | 1001 | 1003 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4934 | 1003 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Style Guide Review | 1 hr | 1 day | Mon 7/28/25 | Mon 7/28/25 | 1002 | 1004 |  | Dusti Kincl
4935 | 1004 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Final Collaborative Review | 16 hrs | 5 days | Tue 7/29/25 | Mon 8/4/25 | 1003 | 1005 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4936 | 1005 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Accenture QC | 4 hrs | 2 days | Tue 8/5/25 | Wed 8/6/25 | 1004 | 1006 |  | Joy Schneider
4937 | 1006 | Future Task |  |  | D676 | Jarad Hermann | Submit | DEL D676 - Completion of Disaster Recovery Testing - Submit | 0 hrs | 0 days | Wed 8/6/25 | Wed 8/6/25 | 1005 | 1007 |  | Joy Schneider
4938 | 1007 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Department QC | 4 hrs | 1 day | Thu 8/7/25 | Thu 8/7/25 | 1006 | 1008 |  | Tommy Werner,Jenifer Hartsfield
4939 | 1008 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Contract Manager Review | 8 hrs | 3 days | Fri 8/8/25 | Tue 8/12/25 | 1007 | 1009 |  | Sean Buchanan
4940 | 1009 | Future Task |  |  | D676 | Jarad Hermann | Accept | DEL D676 - Completion of Disaster Recovery Testing - Accept | 0 hrs | 0 days | Tue 8/12/25 | Tue 8/12/25 | 1008 | 1284 | 2025-11-01 | Sean Buchanan
4941 | 1010 | Future Task | Yes |  | D677 | Stacey Terry |  | D677 - Completion of Mock Go-Lives (Dry Run #3) | 402 hrs | 76 days | Mon 8/25/25 | Fri 12/12/25
4942 | 1011 | Future Task |  |  | D677 | Stacey Terry | Create | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Create | 24 hrs | 10 days | Mon 8/25/25 | Mon 9/8/25 | 1 | 1012 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4943 | 1012 | Future Task |  |  | D677 | Stacey Terry | Submit | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Submit | 0 hrs | 0 days | Mon 9/8/25 | Mon 9/8/25 | 1011 | 1013 |  | Stacey Terry,Joy Schneider
4944 | 1013 | Future Task |  |  | D677 | Stacey Terry | Review | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Collaborative Review | 32 hrs | 10 days | Tue 9/9/25 | Mon 9/22/25 | 1012 | 1014 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4945 | 1014 | Future Task |  |  | D677 | Stacey Terry | Approve | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Approve | 0 hrs | 0 days | Mon 9/22/25 | Mon 9/22/25 | 1013 | 1015FS+24 days |  | Jimmy Cox
5000 | 1015 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Confirm Mock Go-Live Dry Run #3 Readiness | 40 hrs | 4 days | Mon 10/27/25 | Thu 10/30/25 | 1014FS+24 days | 1016FS+1 day |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5001 | 1016 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Execute Mock Go-Live Dry Run #3 | 180 hrs | 10 days | Mon 11/3/25 | Mon 11/17/25 | 1015FS+1 day | 1017 |  | Kurt Meisner,Glaiza Barnes,Roxanne Camba
5002 | 1017 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Document Mock Go-Live Dry Run Results #3 | 30 hrs | 3 days | Tue 11/18/25 | Thu 11/20/25 | 1016 | 1018 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5003 | 1018 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Create Mock Go-Live Dry Run #3 Summary Document | 20 hrs | 2 days | Fri 11/21/25 | Mon 11/24/25 | 1017 | 1020,1019SS |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
7206 | 1019 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Update Deployment & Contingency Plan based on Mock Go-Live Dry Run #3 results | 3 hrs | 2 days | Fri 11/21/25 | Mon 11/24/25 | 1018SS | 1020 |  | Stacey Terry,Mary Punty,Manojkumar Gurjar
4946 | 1020 | Future Task |  |  | D677 | Stacey Terry | Submit | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Draft Submission | 0 hrs | 0 days | Mon 11/24/25 | Mon 11/24/25 | 10181019 | 1021 |  | Stacey Terry,Joy Schneider
4947 | 1021 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Pre-Submission Collaborative Review | 28 hrs | 3 days | Tue 11/25/25 | Mon 12/1/25 | 1020 | 1022 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4948 | 1022 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Style Guide Review | 1 hr | 1 day | Tue 12/2/25 | Tue 12/2/25 | 1021 | 1023 |  | Dusti Kincl
4949 | 1023 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Final Collaborative Review | 28 hrs | 3 days | Wed 12/3/25 | Fri 12/5/25 | 1022 | 1024 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4950 | 1024 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Accenture QC | 4 hrs | 1 day | Mon 12/8/25 | Mon 12/8/25 | 1023 | 1025 |  | Joy Schneider
4951 | 1025 | Future Task |  |  | D677 | Stacey Terry | Submit | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Submit | 0 hrs | 0 days | Mon 12/8/25 | Mon 12/8/25 | 1024 | 1026 |  | Joy Schneider
4952 | 1026 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Department QC | 4 hrs | 1 day | Tue 12/9/25 | Tue 12/9/25 | 1025 | 1027 |  | Tommy Werner,Gabriela Gibson
4953 | 1027 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Contract Manager Review | 8 hrs | 3 days | Wed 12/10/25 | Fri 12/12/25 | 1026 | 1028 |  | Sean Buchanan
4954 | 1028 | Future Task |  |  | D677 | Stacey Terry | Accept | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Accept | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 1027 | 1284 | 2025-12-01 | Sean Buchanan
5080 | 1029 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | WP406 - Mock Conversion Testing Plan | 180 hrs | 114 days | Mon 2/12/24 | Mon 7/22/24
5081 | 1030 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WPED WP406 - Mock Conversion Testing Plan - Create | 24 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 1 | 1031 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5082 | 1031 | Future Task |  |  | WP406 | Manojkumar Gurjar | Submit | WPED WP406 - Mock Conversion Testing Plan - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 1030 | 1032 |  | Joy Schneider,Manojkumar Gurjar
5083 | 1032 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WPED WP406 - Mock Conversion Testing Plan - Review | 28 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 1031 | 1033 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5084 | 1033 | Future Task |  |  | WP406 | Manojkumar Gurjar | Approve | WPED WP406 - Mock Conversion Testing Plan - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 1032 | 1034FS+20 days |  | Jimmy Cox
5116 | 1034 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WP406 - Define Mock Conversion Testing Approach | 20 hrs | 10 days | Mon 4/8/24 | Fri 4/19/24 | 1033FS+20 days | 1035 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5117 | 1035 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WP406 - Identify Resources for Mock Conversion Testing | 20 hrs | 10 days | Mon 4/22/24 | Fri 5/3/24 | 1034 | 1036 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5118 | 1036 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WP406 - Define Test Cycles and Scenarios | 20 hrs | 24 days | Mon 5/6/24 | Fri 6/7/24 | 1035 | 1037 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5119 | 1037 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WP406 - Define and review Entry/Exit Criteria for Mock Conversion Testing | 20 hrs | 15 days | Mon 6/10/24 | Fri 6/28/24 | 1036 | 1038 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5085 | 1038 | Future Task |  |  | WP406 | Manojkumar Gurjar | Submit | WP WP406 - Mock Conversion Testing Plan - Submit | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 1037 | 1039 |  | Joy Schneider,Manojkumar Gurjar
5086 | 1039 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WP WP406 - Mock Conversion Testing Plan - Collaborative Review & Update | 24 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 1038 | 1040 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5087 | 1040 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WP WP406 - Mock Conversion Testing Plan - Final Review & Edits | 24 hrs | 5 days | Tue 7/16/24 | Mon 7/22/24 | 1039 | 1041 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5088 | 1041 | Future Task |  | RW-Communication | WP406 | Manojkumar Gurjar | Approve | WP WP406 - Mock Conversion Testing Plan - Approve | 0 hrs | 0 days | Mon 7/22/24 | Mon 7/22/24 | 1040 | 1043FS-45 days,557 | 2024-05-01 | Jimmy Cox
5089 | 1042 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | WP407 - Mock Conversion Scripts | 160 hrs | 67 days | Fri 5/17/24 | Wed 8/21/24
5090 | 1043 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WPED WP407 - Mock Conversion Scripts - Create | 24 hrs | 10 days | Fri 5/17/24 | Fri 5/31/24 | 1041FS-45 days | 1044 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5091 | 1044 | Future Task |  |  | WP407 | Manojkumar Gurjar | Submit | WPED WP407 - Mock Conversion Scripts - Submit | 0 hrs | 0 days | Fri 5/31/24 | Fri 5/31/24 | 1043 | 1045 |  | Joy Schneider,Manojkumar Gurjar
5092 | 1045 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WPED WP407 - Mock Conversion Scripts - Review | 28 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 1044 | 1046 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5093 | 1046 | Future Task |  |  | WP407 | Manojkumar Gurjar | Approve | WPED WP407 - Mock Conversion Scripts - Approve | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 1045 | 1047 |  | Jimmy Cox
5120 | 1047 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WP407 - Create Test Scripts | 20 hrs | 19 days | Mon 6/17/24 | Fri 7/12/24 | 1046 | 1048 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5121 | 1048 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WP407 - Identify System Test Scripts for Mock Conversion Testing | 20 hrs | 8 days | Mon 7/15/24 | Wed 7/24/24 | 1047 | 1049 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5122 | 1049 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WP407 - Review System Test Scripts for Mock Conversion Testing | 20 hrs | 5 days | Thu 7/25/24 | Wed 7/31/24 | 1048 | 1050 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5094 | 1050 | Future Task |  |  | WP407 | Manojkumar Gurjar | Submit | WP WP407 - Mock Conversion Scripts - Submit | 0 hrs | 0 days | Wed 7/31/24 | Wed 7/31/24 | 1049 | 1051 |  | Joy Schneider,Manojkumar Gurjar
5095 | 1051 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WP WP407 - Mock Conversion Scripts - Collaborative Review & Update | 24 hrs | 10 days | Thu 8/1/24 | Wed 8/14/24 | 1050 | 1052 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5096 | 1052 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WP WP407 - Mock Conversion Scripts - Final Review & Edits | 24 hrs | 5 days | Thu 8/15/24 | Wed 8/21/24 | 1051 | 1053 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5097 | 1053 | Future Task |  |  | WP407 | Manojkumar Gurjar | Approve | WP WP407 - Mock Conversion Scripts - Approve | 0 hrs | 0 days | Wed 8/21/24 | Wed 8/21/24 | 1052 | 622FS-47 days | 2024-07-01 | Jimmy Cox
5098 | 1054 | Future Task |  |  | WP408 | Stacey Terry |  | WP408 - System Test Scripts | 188 hrs | 153 days | Mon 2/12/24 | Mon 9/16/24
5099 | 1055 | Future Task |  |  | WP408 | Stacey Terry | Create | WPED WP408 - System Test Scripts - Create | 16 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 1 | 1056 |  | Stacey Terry,Mary Punty
5100 | 1056 | Future Task |  |  | WP408 | Stacey Terry | Submit | WPED WP408 - System Test Scripts - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 1055 | 1057 |  | Joy Schneider,Stacey Terry
5101 | 1057 | Future Task |  |  | WP408 | Stacey Terry | Review | WPED WP408 - System Test Scripts - Review | 12 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 1056 | 1058 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5102 | 1058 | Future Task |  |  | WP408 | Stacey Terry | Approve | WPED WP408 - System Test Scripts - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 1057 | 1059 |  | Jimmy Cox
5123 | 1059 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Create Work Unit Tracker for System Test Preparation | 20 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 1058 | 1060 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5124 | 1060 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Review, update, & confirm Work Unit Tracker for System Test Preparation | 20 hrs | 10 days | Mon 3/25/24 | Fri 4/5/24 | 1059 | 1061FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter
5125 | 1061 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Create System Test Script Template | 30 hrs | 5 days | Mon 4/1/24 | Fri 4/5/24 | 1060FS-5 days | 1062 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5126 | 1062 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Create, Review and Confirm System Test Scripts and Data | 20 hrs | 93 days | Mon 4/8/24 | Fri 8/16/24 | 1061 | 1063 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
5127 | 1063 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Create System Test Script Summary Document | 30 hrs | 5 days | Mon 8/19/24 | Fri 8/23/24 | 1062 | 1064 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5103 | 1064 | Future Task |  |  | WP408 | Stacey Terry | Submit | WP WP408 - System Test Scripts - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 1063 | 1065 |  | Joy Schneider,Stacey Terry
5104 | 1065 | Future Task |  |  | WP408 | Stacey Terry | Review | WP WP408 - System Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1064 | 1066 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5105 | 1066 | Future Task |  |  | WP408 | Stacey Terry | Review | WP WP408 - System Test Scripts - Final Review & Edits | 20 hrs | 5 days | Tue 9/10/24 | Mon 9/16/24 | 1065 | 1067 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5106 | 1067 | Future Task |  |  | WP408 | Stacey Terry | Approve | WP WP408 - System Test Scripts - Approve | 0 hrs | 0 days | Mon 9/16/24 | Mon 9/16/24 | 1066 | 651 | 2024-09-01 | Jimmy Cox
5107 | 1068 | Future Task |  |  | WP409 | Stacey Terry |  | WP409 - Regression Testing Plan | 116 hrs | 78 days | Mon 8/5/24 | Fri 11/22/24
5108 | 1069 | Future Task |  |  | WP409 | Stacey Terry | Create | WPED WP409 - Regression Testing Plan - Create | 2 hrs | 9 days | Mon 8/5/24 | Thu 8/15/24 | 1 | 1070 |  | Stacey Terry,Mary Punty
5109 | 1070 | Future Task |  |  | WP409 | Stacey Terry | Submit | WPED WP409 - Regression Testing Plan - Submit | 0 hrs | 0 days | Thu 8/15/24 | Thu 8/15/24 | 1069 | 1071 |  | Joy Schneider,Stacey Terry
5110 | 1071 | Future Task |  |  | WP409 | Stacey Terry | Review | WPED WP409 - Regression Testing Plan - Review | 24 hrs | 10 days | Fri 8/16/24 | Thu 8/29/24 | 1070 | 1072 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5111 | 1072 | Future Task |  |  | WP409 | Stacey Terry | Approve | WPED WP409 - Regression Testing Plan - Approve | 0 hrs | 0 days | Thu 8/29/24 | Thu 8/29/24 | 1071 | 1073FS+20 days |  | Jimmy Cox
5128 | 1073 | Future Task |  |  | WP409 | Stacey Terry | Create | WP409 - Create Regression Testing Approach/Plan | 20 hrs | 24 days | Mon 9/30/24 | Thu 10/31/24 | 1072FS+20 days | 1074SS+10 days,1076 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5129 | 1074 | Future Task |  |  | WP409 | Stacey Terry | Create | WP409 - Define the scope of the Regression Test suite | 20 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 1073SS+10 days | 1075SS+5 days,1076 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5130 | 1075 | Future Task |  |  | WP409 | Stacey Terry | Create | WP409 - Identify testing resources for Regression Testing | 20 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 1074SS+5 days | 1076 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5112 | 1076 | Future Task |  |  | WP409 | Stacey Terry | Submit | WP WP409 - Regression Testing Plan - Submit | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 107310741075 | 1077 |  | Joy Schneider,Stacey Terry
5113 | 1077 | Future Task |  |  | WP409 | Stacey Terry | Review | WP WP409 - Regression Testing Plan - Collaborative Review & Update | 10 hrs | 10 days | Fri 11/1/24 | Fri 11/15/24 | 1076 | 1078 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5114 | 1078 | Future Task |  |  | WP409 | Stacey Terry | Review | WP WP409 - Regression Testing Plan - Final Review & Edits | 20 hrs | 5 days | Mon 11/18/24 | Fri 11/22/24 | 1077 | 1079 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5115 | 1079 | Future Task |  |  | WP409 | Stacey Terry | Approve | WP WP409 - Regression Testing Plan - Approve | 0 hrs | 0 days | Fri 11/22/24 | Fri 11/22/24 | 1078 | 1123FS-17 days,1135FS+5 days | 2024-12-01 | Jimmy Cox
5257 | 1080 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | WP412 - Interface Testing Plan | 220 hrs | 118 days | Mon 4/1/24 | Mon 9/16/24
5258 | 1081 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WPED WP412 - Interface Testing Plan - Create | 24 hrs | 10 days | Mon 4/1/24 | Fri 4/12/24 | 537FS+68 days | 1082,1096SS+29 days |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5259 | 1082 | Future Task |  |  | WP412 | Manojkumar Gurjar | Submit | WPED WP412 - Interface Testing Plan - Submit | 0 hrs | 0 days | Fri 4/12/24 | Fri 4/12/24 | 1081 | 1083 |  | Joy Schneider,Manojkumar Gurjar
5260 | 1083 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WPED WP412 - Interface Testing Plan - Review | 28 hrs | 10 days | Mon 4/15/24 | Fri 4/26/24 | 1082 | 1084 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5261 | 1084 | Future Task |  |  | WP412 | Manojkumar Gurjar | Approve | WPED WP412 - Interface Testing Plan - Approve | 0 hrs | 0 days | Fri 4/26/24 | Fri 4/26/24 | 1083 | 1085FS+24 days |  | Jimmy Cox
5284 | 1085 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Define Interface Test approach | 20 hrs | 15 days | Mon 6/3/24 | Fri 6/21/24 | 1084FS+24 days | 1086 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5285 | 1086 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Define Interface Test Cycles | 20 hrs | 14 days | Mon 6/24/24 | Fri 7/12/24 | 1085 | 1087 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5286 | 1087 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Identify Test Resources for Interface Testing | 20 hrs | 5 days | Mon 7/15/24 | Fri 7/19/24 | 1086 | 1088 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5287 | 1088 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Define Test Tools and Test Management processes for Interface Testing | 20 hrs | 5 days | Mon 7/22/24 | Fri 7/26/24 | 1087 | 1089 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5288 | 1089 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Create Initial List of Interface Test Scenarios | 20 hrs | 10 days | Mon 7/29/24 | Fri 8/9/24 | 1088 | 1090 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5289 | 1090 | Future Task |  | RW | WP412 | Manojkumar Gurjar | Create | WP412 - Prepare High-level Interface Test Approach for Integration Partners | 20 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 1089 | 1091 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5262 | 1091 | Future Task |  |  | WP412 | Manojkumar Gurjar | Submit | WP WP412 - Interface Testing Plan - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 1090 | 1092 |  | Joy Schneider,Manojkumar Gurjar
5263 | 1092 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WP WP412 - Interface Testing Plan - Collaborative Review & Update | 24 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1091 | 1093 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5264 | 1093 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WP WP412 - Interface Testing Plan - Final Review & Edits | 24 hrs | 5 days | Tue 9/10/24 | Mon 9/16/24 | 1092 | 1094 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5265 | 1094 | Future Task |  |  | WP412 | Manojkumar Gurjar | Approve | WP WP412 - Interface Testing Plan - Approve | 0 hrs | 0 days | Mon 9/16/24 | Mon 9/16/24 | 1093 | 555FS-10 days | 2024-08-01 | Jimmy Cox
5266 | 1095 | Future Task |  |  | WP413 | Stacey Terry |  | WP413 - Interface Test Scripts | 180 hrs | 89 days | Fri 5/10/24 | Mon 9/16/24
5267 | 1096 | Future Task |  |  | WP413 | Stacey Terry | Create | WPED WP413 - Interface Test Scripts - Create | 16 hrs | 10 days | Fri 5/10/24 | Thu 5/23/24 | 1081SS+29 days | 1097 |  | Stacey Terry,Mary Punty
5268 | 1097 | Future Task |  |  | WP413 | Stacey Terry | Submit | WPED WP413 - Interface Test Scripts - Submit | 0 hrs | 0 days | Thu 5/23/24 | Thu 5/23/24 | 1096 | 1098 |  | Joy Schneider,Stacey Terry
5269 | 1098 | Future Task |  |  | WP413 | Stacey Terry | Review | WPED WP413 - Interface Test Scripts - Review | 24 hrs | 10 days | Fri 5/24/24 | Fri 6/7/24 | 1097 | 1099 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5270 | 1099 | Future Task |  |  | WP413 | Stacey Terry | Approve | WPED WP413 - Interface Test Scripts - Approve | 0 hrs | 0 days | Fri 6/7/24 | Fri 6/7/24 | 1098 | 1100 |  | Jimmy Cox
5290 | 1100 | Future Task |  |  | WP413 | Stacey Terry | Create | WP413 - Create Work Unit Tracker for Interface Test Preparation | 20 hrs | 10 days | Mon 6/10/24 | Fri 6/21/24 | 1099 | 1101 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5291 | 1101 | Future Task |  |  | WP413 | Stacey Terry | Create | WP413 - Review, update, & confirm Work Unit Tracker for Interface Test Preparation | 20 hrs | 5 days | Mon 6/24/24 | Fri 6/28/24 | 1100 | 1102 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5292 | 1102 | Future Task |  |  | WP413 | Stacey Terry | Create | WP413 - Create, Review and Confirm Interface Test Scenarios/Scripts and Data | 20 hrs | 24 days | Mon 7/1/24 | Fri 8/2/24 | 1101 | 1103 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5293 | 1103 | Future Task |  |  | WP413 | Stacey Terry | Create | WP413 - Create Interface Test Scripts Summary Document | 20 hrs | 5 days | Mon 8/5/24 | Fri 8/9/24 | 1102 | 1104 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5271 | 1104 | Future Task |  |  | WP413 | Stacey Terry | Submit | WP WP413 - Interface Test Scripts - Submit | 0 hrs | 0 days | Fri 8/9/24 | Fri 8/9/24 | 1103 | 1105 |  | Joy Schneider,Stacey Terry
5272 | 1105 | Future Task |  |  | WP413 | Stacey Terry | Review | WP WP413 - Interface Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 1104 | 1106 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5273 | 1106 | Future Task |  |  | WP413 | Stacey Terry | Review | WP WP413 - Interface Test Scripts - Final Review & Edits | 20 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 1105 | 1107 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5274 | 1107 | Future Task |  |  | WP413 | Stacey Terry | Approve | WP WP413 - Interface Test Scripts - Approve | 0 hrs | 0 days | Fri 8/30/24 | Fri 8/30/24 | 1106 | 1108 | 2024-08-01 | Jimmy Cox
7149 | 1108 | Future Task |  | RW | WP413 | Stacey Terry | Create | Prepare and share Test Scenarios and Scripts with Integration partners | 20 hrs | 10 days | Tue 9/3/24 | Mon 9/16/24 | 1107 |  |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5275 | 1109 | Future Task |  |  | WP414 | Stacey Terry |  | WP414 - Payroll Parallel Test Scripts | 160 hrs | 80 days | Tue 12/10/24 | Thu 4/3/25
5276 | 1110 | Future Task |  |  | WP414 | Stacey Terry | Create | WPED WP414 - Payroll Parallel Test Scripts - Create | 16 hrs | 10 days | Tue 12/10/24 | Mon 12/23/24 | 728SS-4 days | 1111 |  | Stacey Terry,Mary Punty
5277 | 1111 | Future Task |  |  | WP414 | Stacey Terry | Submit | WPED WP414 - Payroll Parallel Test Scripts - Submit | 0 hrs | 0 days | Mon 12/23/24 | Mon 12/23/24 | 1110 | 1112 |  | Joy Schneider,Stacey Terry
5278 | 1112 | Future Task |  |  | WP414 | Stacey Terry | Review | WPED WP414 - Payroll Parallel Test Scripts - Review | 24 hrs | 10 days | Tue 12/24/24 | Wed 1/8/25 | 1111 | 1113 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5279 | 1113 | Future Task |  |  | WP414 | Stacey Terry | Approve | WPED WP414 - Payroll Parallel Test Scripts - Approve | 0 hrs | 0 days | Wed 1/8/25 | Wed 1/8/25 | 1112 | 1114 |  | Jimmy Cox
5295 | 1114 | Future Task |  |  | WP414 | Stacey Terry | Create | WP414 - Create Work Unit Tracker for Payroll Parallel Test Preparation | 20 hrs | 5 days | Thu 1/9/25 | Wed 1/15/25 | 1113 | 1115 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh
5296 | 1115 | Future Task |  |  | WP414 | Stacey Terry | Create | WP414 - Review, update, & confirm Work Unit Tracker for Payroll Parallel Test Preparation | 20 hrs | 10 days | Thu 1/16/25 | Thu 1/30/25 | 1114 | 1116FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
5297 | 1116 | Future Task |  |  | WP414 | Stacey Terry | Create | WP414 - Create, Review and Confirm Payroll Parallel Test Scenarios/Scripts and Data | 20 hrs | 30 days | Fri 1/24/25 | Thu 3/6/25 | 1115FS-5 days | 1117FS-5 days |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Jennifer Peddicord
5298 | 1117 | Future Task |  |  | WP414 | Stacey Terry | Create | WP414 - Create Payroll Parallel Test Script Summary Document | 20 hrs | 10 days | Fri 2/28/25 | Thu 3/13/25 | 1116FS-5 days | 1118 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5280 | 1118 | Future Task |  |  | WP414 | Stacey Terry | Submit | WP WP414 - Payroll Parallel Test Scripts - Submit | 0 hrs | 0 days | Thu 3/13/25 | Thu 3/13/25 | 1117 | 1119 |  | Joy Schneider,Stacey Terry
5281 | 1119 | Future Task |  |  | WP414 | Stacey Terry | Review | WP WP414 - Payroll Parallel Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Fri 3/14/25 | Thu 3/27/25 | 1118 | 1120 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5282 | 1120 | Future Task |  |  | WP414 | Stacey Terry | Review | WP WP414 - Payroll Parallel Test Scripts - Final Review & Edits | 20 hrs | 5 days | Fri 3/28/25 | Thu 4/3/25 | 1119 | 1121 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5283 | 1121 | Future Task |  |  | WP414 | Stacey Terry | Approve | WP WP414 - Payroll Parallel Test Scripts - Approve | 0 hrs | 0 days | Thu 4/3/25 | Thu 4/3/25 | 1120 |  | 2025-03-01 | Jimmy Cox
5131 | 1122 | Future Task |  |  | WP415 | Stacey Terry |  | WP415 - Regression Test Scripts | 140 hrs | 63 days | Wed 10/30/24 | Mon 2/3/25
5132 | 1123 | Future Task |  |  | WP415 | Stacey Terry | Create | WPED WP415 - Regression Test Scripts - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1079FS-17 days | 1124 |  | Stacey Terry,Mary Punty
5133 | 1124 | Future Task |  |  | WP415 | Stacey Terry | Submit | WPED WP415 - Regression Test Scripts - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 1123 | 1125 |  | Joy Schneider,Stacey Terry
5134 | 1125 | Future Task |  |  | WP415 | Stacey Terry | Review | WPED WP415 - Regression Test Scripts - Review | 24 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 1124 | 1126 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5135 | 1126 | Future Task |  |  | WP415 | Stacey Terry | Approve | WPED WP415 - Regression Test Scripts - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1125 | 1127 |  | Jimmy Cox
5221 | 1127 | Future Task |  |  | WP415 | Stacey Terry | Create | WP415 - Create Regression Test Suite | 20 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 1126 | 1128 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5222 | 1128 | Future Task |  |  | WP415 | Stacey Terry | Create | WP415 - Review, update & confirm Regression Test Suite | 20 hrs | 9 days | Mon 12/16/24 | Fri 12/27/24 | 1127 | 1129 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter
5223 | 1129 | Future Task |  |  | WP415 | Stacey Terry | Create | WP415 - Create Regression Test Scripts Summary Document | 20 hrs | 9 days | Mon 12/30/24 | Fri 1/10/25 | 1128 | 1130 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5136 | 1130 | Future Task |  |  | WP415 | Stacey Terry | Submit | WP WP415 - Regression Test Scripts - Submit | 0 hrs | 0 days | Fri 1/10/25 | Fri 1/10/25 | 1129 | 1131 |  | Joy Schneider,Stacey Terry
5137 | 1131 | Future Task |  |  | WP415 | Stacey Terry | Review | WP WP415 - Regression Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 1130 | 1132 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5138 | 1132 | Future Task |  |  | WP415 | Stacey Terry | Review | WP WP415 - Regression Test Scripts - Final Review & Edits | 20 hrs | 5 days | Tue 1/28/25 | Mon 2/3/25 | 1131 | 1133 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5139 | 1133 | Future Task |  |  | WP415 | Stacey Terry | Approve | WP WP415 - Regression Test Scripts - Approve | 0 hrs | 0 days | Mon 2/3/25 | Mon 2/3/25 | 1132 |  | 2024-12-01 | Jimmy Cox
5140 | 1134 | Future Task | Yes |  | WP416 | Stacey Terry |  | WP416 - Completion of Regression Testing | 1,733 hrs | 160 days | Wed 12/4/24 | Tue 7/22/25
5141 | 1135 | Future Task |  |  | WP416 | Stacey Terry | Create | WPED WP416 - Completion of Regression Testing - Create | 16 hrs | 10 days | Wed 12/4/24 | Tue 12/17/24 | 1079FS+5 days | 1136 |  | Stacey Terry,Mary Punty
5142 | 1136 | Future Task |  |  | WP416 | Stacey Terry | Submit | WPED WP416 - Completion of Regression Testing - Submit | 0 hrs | 0 days | Tue 12/17/24 | Tue 12/17/24 | 1135 | 1137 |  | Joy Schneider,Stacey Terry
5143 | 1137 | Future Task |  |  | WP416 | Stacey Terry | Review | WPED WP416 - Completion of Regression Testing - Review | 24 hrs | 10 days | Wed 12/18/24 | Thu 1/2/25 | 1136 | 1138 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5144 | 1138 | Future Task |  |  | WP416 | Stacey Terry | Approve | WPED WP416 - Completion of Regression Testing - Approve | 0 hrs | 0 days | Thu 1/2/25 | Thu 1/2/25 | 1137 | 1139 |  | Jimmy Cox
5224 | 1139 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Create Work Unit Tracker for Regression Test Execution | 20 hrs | 10 days | Fri 1/3/25 | Thu 1/16/25 | 1138 | 1140 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5225 | 1140 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Review, update, and confirm Work Unit Tracker for Regression Test Execution | 20 hrs | 10 days | Fri 1/17/25 | Fri 1/31/25 | 1139 | 1141 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5226 | 1141 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Conduct Regression Test Execution Kickoff Meeting | 20 hrs | 5 days | Mon 2/3/25 | Fri 2/7/25 | 1140 | 1142 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5227 | 1142 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Execute Regression Test | 1,620 hrs | 90 days | Mon 2/10/25 | Mon 6/16/25 | 1141 | 1143 |  | Matthew Culp,Abdel El Bacha,Donnie Doctor
5228 | 1143 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Create Completion of Regression Test Execution Summary Document | 3 hrs | 10 days | Tue 6/17/25 | Mon 6/30/25 | 1142 | 1144 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5145 | 1144 | Future Task |  |  | WP416 | Stacey Terry | Submit | WP WP416 - Completion of Regression Testing - Submit | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 1143 | 1145 |  | Joy Schneider,Stacey Terry
5146 | 1145 | Future Task |  |  | WP416 | Stacey Terry | Review | WP WP416 - Completion of Regression Testing - Collaborative Review & Update | 5 hrs | 10 days | Tue 7/1/25 | Tue 7/15/25 | 1144 | 1146 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5147 | 1146 | Future Task |  |  | WP416 | Stacey Terry | Review | WP WP416 - Completion of Regression Testing - Final Review & Edits | 5 hrs | 5 days | Wed 7/16/25 | Tue 7/22/25 | 1145 | 1147 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5148 | 1147 | Future Task |  |  | WP416 | Stacey Terry | Approve | WP WP416 - Completion of Regression Testing - Approve | 0 hrs | 0 days | Tue 7/22/25 | Tue 7/22/25 | 1146 |  | 2025-06-01 | Jimmy Cox
5149 | 1148 | Future Task |  |  | WP417 | Stacey Terry |  | WP417 - Data Dictionary | 192 hrs | 139 days | Mon 9/23/24 | Fri 4/11/25
5150 | 1149 | Future Task |  |  | WP417 | Stacey Terry | Create | WPED WP417 - Data Dictionary - Create | 16 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 1 | 1150 |  | Stacey Terry,Manojkumar Gurjar
5151 | 1150 | Future Task |  |  | WP417 | Stacey Terry | Submit | WPED WP417 - Data Dictionary - Submit | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 1149 | 1151 |  | Joy Schneider,Stacey Terry
5152 | 1151 | Future Task |  |  | WP417 | Stacey Terry | Review | WPED WP417 - Data Dictionary - Review | 28 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1150 | 1152 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5153 | 1152 | Future Task |  |  | WP417 | Stacey Terry | Approve | WPED WP417 - Data Dictionary - Approve | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 1151 | 1153FS+27 days |  | Jimmy Cox
5229 | 1153 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Update data dictionary with latest tables and data elements as needed - Financials | 20 hrs | 21 days | Mon 12/2/24 | Tue 12/31/24 | 1152FS+27 days | 1154 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5230 | 1154 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Update data dictionary with latest tables and data elements as needed - Payroll | 20 hrs | 21 days | Thu 1/2/25 | Fri 1/31/25 | 1153 | 1155 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5231 | 1155 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Update data dictionary with latest tables and data elements as needed - DW Related | 20 hrs | 20 days | Mon 2/3/25 | Fri 2/28/25 | 1154 | 1156 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5232 | 1156 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Review and confirm data dictionary | 20 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1155 | 1157 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5233 | 1157 | Future Task |  | RW-Communication | WP417 | Stacey Terry | Create | WP417 - Share Data Dictionary | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1156 | 1158 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5154 | 1158 | Future Task |  |  | WP417 | Stacey Terry | Submit | WP WP417 - Data Dictionary - Submit | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1157 | 1159 |  | Joy Schneider,Stacey Terry
5155 | 1159 | Future Task |  |  | WP417 | Stacey Terry | Review | WP WP417 - Data Dictionary - Collaborative Review & Update | 24 hrs | 10 days | Mon 3/24/25 | Fri 4/4/25 | 1158 | 1160 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5156 | 1160 | Future Task |  |  | WP417 | Stacey Terry | Review | WP WP417 - Data Dictionary - Final Review & Edits | 24 hrs | 5 days | Mon 4/7/25 | Fri 4/11/25 | 1159 | 1161 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5157 | 1161 | Future Task |  |  | WP417 | Stacey Terry | Approve | WP WP417 - Data Dictionary - Approve | 0 hrs | 0 days | Fri 4/11/25 | Fri 4/11/25 | 1160 |  | 2025-02-01 | Jimmy Cox
5158 | 1162 | Future Task |  |  | WP418 | Jarad Hermann |  | WP418 - Disaster Recovery Plan | 102 hrs | 106 days | Mon 7/22/24 | Fri 12/20/24
5159 | 1163 | Future Task |  |  | WP418 | Jarad Hermann | Create | WPED WP418 - Disaster Recovery Plan - Create | 2 hrs | 10 days | Mon 7/22/24 | Fri 8/2/24 | 1 | 1164,1175SS+10 days |  | Jarad Hermann
5160 | 1164 | Future Task |  |  | WP418 | Jarad Hermann | Submit | WPED WP418 - Disaster Recovery Plan - Submit | 0 hrs | 0 days | Fri 8/2/24 | Fri 8/2/24 | 1163 | 1165 |  | Joy Schneider,Jarad Hermann
5161 | 1165 | Future Task |  |  | WP418 | Jarad Hermann | Review | WPED WP418 - Disaster Recovery Plan - Review | 16 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 1164 | 1166 |  | Jarad Hermann,Jimmy Cox,Angie Robertson,Sean Buchanan
5162 | 1166 | Future Task |  |  | WP418 | Jarad Hermann | Approve | WPED WP418 - Disaster Recovery Plan - Approve | 0 hrs | 0 days | Fri 8/16/24 | Fri 8/16/24 | 1165 | 1167FS+29 days |  | Jimmy Cox
5234 | 1167 | Future Task |  |  | WP418 | Jarad Hermann | Create | WP418 - Design/Update Disaster Recovery (DR) Plan | 20 hrs | 15 days | Mon 9/30/24 | Fri 10/18/24 | 1166FS+29 days | 1168 |  | Jarad Hermann,Vivek Sharma
5235 | 1168 | Future Task |  |  | WP418 | Jarad Hermann | Create | WP418 - Review Financials Disaster Recovery Plan | 20 hrs | 15 days | Mon 10/21/24 | Fri 11/8/24 | 1167 | 1169 |  | Jarad Hermann,Vivek Sharma
5236 | 1169 | Future Task |  |  | WP418 | Jarad Hermann | Create | WP418 - Create Payroll Disaster Recovery Plan | 20 hrs | 12 days | Tue 11/12/24 | Wed 11/27/24 | 1168 | 1170 |  | Jarad Hermann,Vivek Sharma
5163 | 1170 | Future Task |  |  | WP418 | Jarad Hermann | Submit | WP WP418 - Disaster Recovery Plan - Submit | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1169 | 1171 |  | Joy Schneider,Jarad Hermann
5164 | 1171 | Future Task |  |  | WP418 | Jarad Hermann | Review | WP WP418 - Disaster Recovery Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 1170 | 1172 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5165 | 1172 | Future Task |  |  | WP418 | Jarad Hermann | Review | WP WP418 - Disaster Recovery Plan - Final Review & Edits | 12 hrs | 5 days | Mon 12/16/24 | Fri 12/20/24 | 1171 | 1173 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5166 | 1173 | Future Task |  |  | WP418 | Jarad Hermann | Approve | WP WP418 - Disaster Recovery Plan - Approve | 0 hrs | 0 days | Fri 12/20/24 | Fri 12/20/24 | 1172 | 993 | 2024-11-01 | Jimmy Cox
5167 | 1174 | Future Task |  |  | WP419 | Jarad Hermann |  | WP419 - Disaster Recovery Testing Plan | 116 hrs | 158 days | Mon 8/5/24 | Fri 3/21/25
5168 | 1175 | Future Task |  |  | WP419 | Jarad Hermann | Create | WPED WP419 - Disaster Recovery Testing Plan - Create | 16 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 1163SS+10 days | 1176 |  | Jarad Hermann,Mary Punty
5169 | 1176 | Future Task |  |  | WP419 | Jarad Hermann | Submit | WPED WP419 - Disaster Recovery Testing Plan - Submit | 0 hrs | 0 days | Fri 8/16/24 | Fri 8/16/24 | 1175 | 1177 |  | Joy Schneider,Jarad Hermann
5170 | 1177 | Future Task |  |  | WP419 | Jarad Hermann | Review | WPED WP419 - Disaster Recovery Testing Plan - Review | 20 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 1176 | 1178 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5171 | 1178 | Future Task |  |  | WP419 | Jarad Hermann | Approve | WPED WP419 - Disaster Recovery Testing Plan - Approve | 0 hrs | 0 days | Fri 8/30/24 | Fri 8/30/24 | 1177 | 1179FS+20 days |  | Jimmy Cox
5237 | 1179 | Future Task |  |  | WP419 | Jarad Hermann | Create | WP419 - Define and Document Disaster Recovery Test Tasks including Test Planning, Preparation, Execution, and Closure | 20 hrs | 62 days | Tue 10/1/24 | Tue 12/31/24 | 1178FS+20 days | 1180SS,1214SS+24 days |  | Jarad Hermann,Bryan Sohayda
5238 | 1180 | Future Task |  |  | WP419 | Jarad Hermann | Create | WP419 - Define Disaster Recovery Testing Tools | 20 hrs | 62 days | Tue 10/1/24 | Tue 12/31/24 | 1179SS | 1181 |  | Jarad Hermann,Bryan Sohayda
5239 | 1181 | Future Task |  |  | WP419 | Jarad Hermann | Create | WP419 - Define and Document Disaster Recovery Test Management | 4 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1180 | 1182SS |  | Jarad Hermann,Bryan Sohayda
5240 | 1182 | Future Task |  |  | WP419 | Jarad Hermann | Create | WP419 - Define and Document Disaster Recovery Test Resources and Responsibilities | 4 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1181SS | 1183 |  | Jarad Hermann,Bryan Sohayda
5172 | 1183 | Future Task |  |  | WP419 | Jarad Hermann | Submit | WP WP419 - Disaster Recovery Testing Plan - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 1182 | 1184568 | 2025-02-28 | Joy Schneider,Jarad Hermann
5173 | 1184 | Future Task |  |  | WP419 | Jarad Hermann | Review | WP WP419 - Disaster Recovery Testing Plan - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1183 | 1185 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5174 | 1185 | Future Task |  |  | WP419 | Jarad Hermann | Review | WP WP419 - Disaster Recovery Testing Plan - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1184 | 1186 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5175 | 1186 | Future Task |  |  | WP419 | Jarad Hermann | Approve | WP WP419 - Disaster Recovery Testing Plan - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1185 | 993FS-35 days | 2025-02-01 | Jimmy Cox
5176 | 1187 | Future Task |  |  | WP420 | Jarad Hermann |  | WP420 - Performance Testing Plan | 128 hrs | 172 days | Mon 9/16/24 | Wed 5/21/25
5177 | 1188 | Future Task |  |  | WP420 | Jarad Hermann | Create | WPED WP420 - Performance Testing Plan - Create | 16 hrs | 10 days | Mon 9/16/24 | Fri 9/27/24 | 1 | 1189,1226SS+10 days |  | Jarad Hermann,Mary Punty
5178 | 1189 | Future Task |  |  | WP420 | Jarad Hermann | Submit | WPED WP420 - Performance Testing Plan - Submit | 0 hrs | 0 days | Fri 9/27/24 | Fri 9/27/24 | 1188 | 1190 |  | Joy Schneider,Jarad Hermann
5179 | 1190 | Future Task |  |  | WP420 | Jarad Hermann | Review | WPED WP420 - Performance Testing Plan - Review | 20 hrs | 10 days | Mon 9/30/24 | Fri 10/11/24 | 1189 | 1191 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5180 | 1191 | Future Task |  |  | WP420 | Jarad Hermann | Approve | WPED WP420 - Performance Testing Plan - Approve | 0 hrs | 0 days | Fri 10/11/24 | Fri 10/11/24 | 1190 | 1192FS+32 days,1193SS,1194SS,1195SS,1196SS |  | Jimmy Cox
5241 | 1192 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Identify and establish the projected load of the system | 4 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1191FS+32 days | 1197 |  | Jarad Hermann,Bryan Sohayda
5242 | 1193 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Define test cycles to be included | 20 hrs | 105 days | Mon 10/14/24 | Mon 3/17/25 | 1191SS | 1197 |  | Jarad Hermann,Bryan Sohayda
5243 | 1194 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Define Performance Testing objectives, scope, environments, and metrics | 20 hrs | 105 days | Mon 10/14/24 | Mon 3/17/25 | 1191SS | 1197 |  | Jarad Hermann,Bryan Sohayda
5244 | 1195 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Identify performance testing project team members and responsibilities | 20 hrs | 105 days | Mon 10/14/24 | Mon 3/17/25 | 1191SS | 1197 |  | Jarad Hermann,Bryan Sohayda
5245 | 1196 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Define and document Performance Testing entry and exit criteria | 20 hrs | 105 days | Mon 10/14/24 | Mon 3/17/25 | 1191SS | 1197 |  | Jarad Hermann,Bryan Sohayda
5181 | 1197 | Future Task |  |  | WP420 | Jarad Hermann | Submit | WP WP420 - Performance Testing Plan - Submit | 0 hrs | 0 days | Wed 4/30/25 | Wed 4/30/25 | 1.1961e+19 | 1198566 |  | Joy Schneider,Jarad Hermann
5182 | 1198 | Future Task |  |  | WP420 | Jarad Hermann | Review | WP WP420 - Performance Testing Plan - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 1197 | 1199 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5183 | 1199 | Future Task |  |  | WP420 | Jarad Hermann | Review | WP WP420 - Performance Testing Plan - Final Review & Edits | 4 hrs | 5 days | Thu 5/15/25 | Wed 5/21/25 | 1198 | 1200 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5184 | 1200 | Future Task |  |  | WP420 | Jarad Hermann | Approve | WP WP420 - Performance Testing Plan - Approve | 0 hrs | 0 days | Wed 5/21/25 | Wed 5/21/25 | 1199 | 975FS-28 days | 2025-04-01 | Jimmy Cox
5185 | 1201 | Future Task |  |  | WP421 | Jarad Hermann |  | WP421 - Penetration Testing Plan | 128 hrs | 124 days | Mon 9/23/24 | Fri 3/21/25
5186 | 1202 | Future Task |  |  | WP421 | Jarad Hermann | Create | WPED WP421 - Penetration Testing Plan - Create | 16 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 1 | 1203,1238SS+10 days |  | Jarad Hermann,Mary Punty
5187 | 1203 | Future Task |  |  | WP421 | Jarad Hermann | Submit | WPED WP421 - Penetration Testing Plan - Submit | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 1202 | 1204 |  | Joy Schneider,Jarad Hermann
5188 | 1204 | Future Task |  |  | WP421 | Jarad Hermann | Review | WPED WP421 - Penetration Testing Plan - Review | 20 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1203 | 1205 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5189 | 1205 | Future Task |  |  | WP421 | Jarad Hermann | Approve | WPED WP421 - Penetration Testing Plan - Approve | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 1204 | 1206FS+27 days |  | Jimmy Cox
5246 | 1206 | Future Task |  |  | WP421 | Jarad Hermann | Create | WP421 - Create Penetration Testing Plan/approach | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1205FS+27 days | 1207SS,1208SS,1209 |  | Jarad Hermann,Bryan Sohayda
5247 | 1207 | Future Task |  |  | WP421 | Jarad Hermann | Create | WP421 - Identify resources for Penetration Testing | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1206SS | 1209 |  | Jarad Hermann,Bryan Sohayda
5248 | 1208 | Future Task |  |  | WP421 | Jarad Hermann | Create | WP421 - Define Penetration Testing entry and exit criteria | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1206SS | 1209 |  | Jarad Hermann,Bryan Sohayda
5190 | 1209 | Future Task |  |  | WP421 | Jarad Hermann | Submit | WP WP421 - Penetration Testing Plan - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 120812061207 | 1210 |  | Joy Schneider,Jarad Hermann
5191 | 1210 | Future Task |  |  | WP421 | Jarad Hermann | Review | WP WP421 - Penetration Testing Plan - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1209 | 1211 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5192 | 1211 | Future Task |  |  | WP421 | Jarad Hermann | Review | WP WP421 - Penetration Testing Plan - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1210 | 1212 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5193 | 1212 | Future Task |  |  | WP421 | Jarad Hermann | Approve | WP WP421 - Penetration Testing Plan - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1211 | 957FS+10 days | 2025-02-01 | Jimmy Cox
5194 | 1213 | Future Task |  |  | WP422 | Jarad Hermann |  | WP422 - Disaster Recovery Test Scripts | 128 hrs | 94 days | Mon 11/4/24 | Fri 3/21/25
5195 | 1214 | Future Task |  |  | WP422 | Jarad Hermann | Create | WPED WP422 - Disaster Recovery Test Scripts - Create | 16 hrs | 10 days | Mon 11/4/24 | Mon 11/18/24 | 1179SS+24 days | 1215 |  | Jarad Hermann,Mary Punty
5196 | 1215 | Future Task |  |  | WP422 | Jarad Hermann | Submit | WPED WP422 - Disaster Recovery Test Scripts - Submit | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 1214 | 1216 |  | Joy Schneider,Jarad Hermann
5197 | 1216 | Future Task |  |  | WP422 | Jarad Hermann | Review | WPED WP422 - Disaster Recovery Test Scripts - Review | 20 hrs | 10 days | Tue 11/19/24 | Wed 12/4/24 | 1215 | 1217 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5198 | 1217 | Future Task |  |  | WP422 | Jarad Hermann | Approve | WPED WP422 - Disaster Recovery Test Scripts - Approve | 0 hrs | 0 days | Wed 12/4/24 | Wed 12/4/24 | 1216 | 1218FS+18 days |  | Jimmy Cox
5249 | 1218 | Future Task |  |  | WP422 | Jarad Hermann | Create | WP422 - Finalize Disaster Recovery Test Scripts Inventory | 20 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1217FS+18 days | 1219SS,1220SS,1221 |  | Jarad Hermann,Bryan Sohayda
5250 | 1219 | Future Task |  |  | WP422 | Jarad Hermann | Create | WP422 - Create, review, and confirm DR Test Script Work Unit Tracker | 20 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1218SS | 1221 |  | Jarad Hermann,Bryan Sohayda
5251 | 1220 | Future Task |  |  | WP422 | Jarad Hermann | Create | WP422 - Create, Review and Confirm Disaster Recovery Test Scripts | 20 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1218SS | 1221 |  | Jarad Hermann,Bryan Sohayda
5199 | 1221 | Future Task |  |  | WP422 | Jarad Hermann | Submit | WP WP422 - Disaster Recovery Test Scripts - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 122012181219 | 1222 |  | Joy Schneider,Jarad Hermann
5200 | 1222 | Future Task |  |  | WP422 | Jarad Hermann | Review | WP WP422 - Disaster Recovery Test Scripts - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1221 | 1223 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5201 | 1223 | Future Task |  |  | WP422 | Jarad Hermann | Review | WP WP422 - Disaster Recovery Test Scripts - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1222 | 1224 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5202 | 1224 | Future Task |  |  | WP422 | Jarad Hermann | Approve | WP WP422 - Disaster Recovery Test Scripts - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1223 | 993FS-35 days |  | Jimmy Cox
5203 | 1225 | Future Task |  |  | WP423 | Jarad Hermann |  | WP423 - Performance Test Scripts | 104 hrs | 162 days | Mon 9/30/24 | Wed 5/21/25
5204 | 1226 | Future Task |  |  | WP423 | Jarad Hermann | Create | WPED WP423 - Performance Test Scripts - Create | 16 hrs | 10 days | Mon 9/30/24 | Fri 10/11/24 | 1188SS+10 days | 1227 |  | Jarad Hermann,Mary Punty
5205 | 1227 | Future Task |  |  | WP423 | Jarad Hermann | Submit | WPED WP423 - Performance Test Scripts - Submit | 0 hrs | 0 days | Fri 10/11/24 | Fri 10/11/24 | 1226 | 1228 |  | Joy Schneider,Jarad Hermann
5206 | 1228 | Future Task |  |  | WP423 | Jarad Hermann | Review | WPED WP423 - Performance Test Scripts - Review | 20 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 1227 | 1229 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5207 | 1229 | Future Task |  |  | WP423 | Jarad Hermann | Approve | WPED WP423 - Performance Test Scripts - Approve | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 1228 | 1230FS+22 days |  | Jimmy Cox
5252 | 1230 | Future Task |  |  | WP423 | Jarad Hermann | Create | WP423 - Finalize Performance Test Scripts Inventory | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1229FS+22 days | 1231SS,1232SS,1233 |  | Jarad Hermann,Bryan Sohayda
5253 | 1231 | Future Task |  |  | WP423 | Jarad Hermann | Create | WP423 - Create, review, and confirm Performance Test Script Work Unit Tracker | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1230SS | 1233 |  | Jarad Hermann,Bryan Sohayda
5254 | 1232 | Future Task |  |  | WP423 | Jarad Hermann | Create | WP423 - Create, Review and Confirm Performance Test Scripts | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1230SS | 1233 |  | Jarad Hermann,Bryan Sohayda
5208 | 1233 | Future Task |  |  | WP423 | Jarad Hermann | Submit | WP WP423 - Performance Test Scripts - Submit | 0 hrs | 0 days | Wed 4/30/25 | Wed 4/30/25 | 123212301231 | 1234 |  | Joy Schneider,Jarad Hermann
5209 | 1234 | Future Task |  |  | WP423 | Jarad Hermann | Review | WP WP423 - Performance Test Scripts - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 1233 | 1235 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5210 | 1235 | Future Task |  |  | WP423 | Jarad Hermann | Review | WP WP423 - Performance Test Scripts - Final Review & Edits | 4 hrs | 5 days | Thu 5/15/25 | Wed 5/21/25 | 1234 | 1236 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5211 | 1236 | Future Task |  |  | WP423 | Jarad Hermann | Approve | WP WP423 - Performance Test Scripts - Approve | 0 hrs | 0 days | Wed 5/21/25 | Wed 5/21/25 | 1235 | 975FS-28 days |  | Jimmy Cox
5212 | 1237 | Future Task |  |  | WP424 | Jarad Hermann |  | WP424 - Penetration Test Scripts/Scenarios | 108 hrs | 114 days | Mon 10/7/24 | Fri 3/21/25
5213 | 1238 | Future Task |  |  | WP424 | Jarad Hermann | Create | WPED WP424 - Penetration Test Scripts/Scenarios - Create | 16 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1202SS+10 days | 1239 |  | Jarad Hermann,Mary Punty
5214 | 1239 | Future Task |  |  | WP424 | Jarad Hermann | Submit | WPED WP424 - Penetration Test Scripts/Scenarios - Submit | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 1238 | 1240 |  | Joy Schneider,Jarad Hermann
5215 | 1240 | Future Task |  |  | WP424 | Jarad Hermann | Review | WPED WP424 - Penetration Test Scripts/Scenarios - Review | 20 hrs | 10 days | Mon 10/21/24 | Fri 11/1/24 | 1239 | 1241 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5216 | 1241 | Future Task |  |  | WP424 | Jarad Hermann | Approve | WPED WP424 - Penetration Test Scripts/Scenarios - Approve | 0 hrs | 0 days | Fri 11/1/24 | Fri 11/1/24 | 1240 | 1242FS+17 days |  | Jimmy Cox
5255 | 1242 | Future Task |  |  | WP424 | Jarad Hermann | Create | WP424 - Finalize Penetration Test Scripts Inventory | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1241FS+17 days | 1243SS |  | Jarad Hermann,Bryan Sohayda
5256 | 1243 | Future Task |  |  | WP424 | Jarad Hermann | Create | WP424 - Create, review, and confirm Penetration Test Scripts/Scenarios | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1242SS | 1244 |  | Jarad Hermann,Bryan Sohayda
5217 | 1244 | Future Task |  |  | WP424 | Jarad Hermann | Submit | WP424 - WP WP424 - Penetration Test Scripts/Scenarios - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 1243 | 1245 |  | Joy Schneider,Jarad Hermann
5218 | 1245 | Future Task |  |  | WP424 | Jarad Hermann | Review | WP WP424 - Penetration Test Scripts/Scenarios - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1244 | 1246 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5219 | 1246 | Future Task |  |  | WP424 | Jarad Hermann | Review | WP WP424 - Penetration Test Scripts/Scenarios - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1245 | 1247 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5220 | 1247 | Future Task |  |  | WP424 | Jarad Hermann | Approve | WP WP424 - Penetration Test Scripts/Scenarios - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1246 | 957FS+10 days |  | Jimmy Cox
7247 | 1248 | Future Task |  |  | WP429 | Stacey Terry |  | WP429 - Updated System Testing Plan (BI/DW) | 412 hrs | 80 days | Mon 8/12/24 | Thu 12/5/24
7248 | 1249 | Future Task |  |  | WP429 | Stacey Terry | Create | WPED WP429 - Updated System Testing Plan (BI/DW) - Create | 88 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 620FS+101 days | 1250 |  | Stacey Terry,Mary Punty
7249 | 1250 | Future Task |  |  | WP429 | Stacey Terry | Submit | WPED WP429 - Updated System Testing Plan (BI/DW) - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 1249 | 1251 |  | Joy Schneider,Stacey Terry
7250 | 1251 | Future Task |  |  | WP429 | Stacey Terry | Review | WPED WP429 - Updated System Testing Plan (BI/DW) - Review | 108 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1250 | 1252 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan,Mary Punty
7251 | 1252 | Future Task |  |  | WP429 | Stacey Terry | Approve | WPED WP429 - Updated System Testing Plan (BI/DW) - Approve | 0 hrs | 0 days | Mon 9/9/24 | Mon 9/9/24 | 1251 | 1253 |  | Jimmy Cox
7261 | 1253 | Future Task |  |  | WP429 | Stacey Terry | Create | WP429 - Define System Test approach for DW & BI | 20 hrs | 20 days | Tue 9/10/24 | Mon 10/7/24 | 1252 | 1254SS+10 days |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
7262 | 1254 | Future Task |  |  | WP429 | Stacey Terry | Create | WP429 - Define System Test Cycles for DW & BI | 20 hrs | 15 days | Tue 9/24/24 | Mon 10/14/24 | 1253SS+10 days | 1255SS+5 days |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
7263 | 1255 | Future Task |  |  | WP429 | Stacey Terry | Create | WP429 - Identify System Test Resources for DW & BI | 20 hrs | 10 days | Tue 10/1/24 | Mon 10/14/24 | 1254SS+5 days | 1256 |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
7264 | 1256 | Future Task |  |  | WP429 | Stacey Terry | Create | WP429 - Create Initial List of DW & BI System Test Scenarios | 4 hrs | 20 days | Tue 10/15/24 | Tue 11/12/24 | 1255 | 1257 |  | Jennifer Reeves,Manojkumar Gurjar
7257 | 1257 | Future Task |  |  | WP429 | Stacey Terry | Submit | WP WP429 - Data Dictionary - Submit | 0 hrs | 0 days | Tue 11/12/24 | Tue 11/12/24 | 1256 | 1258 |  | Joy Schneider,Stacey Terry
7258 | 1258 | Future Task |  |  | WP429 | Stacey Terry | Review | WP WP429 - Data Dictionary - Collaborative Review & Update | 96 hrs | 10 days | Wed 11/13/24 | Tue 11/26/24 | 1257 | 1259 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson,Mary Punty
7259 | 1259 | Future Task |  |  | WP429 | Stacey Terry | Review | WP WP429 - Data Dictionary - Final Review & Edits | 56 hrs | 5 days | Wed 11/27/24 | Thu 12/5/24 | 1258 | 1260 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson,Mary Punty
7260 | 1260 | Future Task |  |  | WP429 | Stacey Terry | Approve | WP WP429 - Data Dictionary - Approve | 0 hrs | 0 days | Thu 12/5/24 | Thu 12/5/24 | 1259 |  | 2024-12-01 | Jimmy Cox
5299 | 1261 | Future Task |  |  | I-WP127 | Angie Robertson |  | I-WP127 - User Acceptance Testing Plan | 91 hrs | 159 days | Mon 8/7/23 | Mon 3/25/24
5300 | 1262 | Future Task |  |  | I-WP127 | Angie Robertson | Create | WPED I-WP127 - User Acceptance Testing Plan - Create | 4 hrs | 10 days | Mon 8/7/23 | Fri 8/18/23 | 1 | 1263 |  | Angie Robertson,Jimmy Cox
5301 | 1263 | Future Task |  |  | I-WP127 | Angie Robertson | Submit | WPED I-WP127 - User Acceptance Testing Plan - Submit | 0 hrs | 0 days | Fri 8/18/23 | Fri 8/18/23 | 1262 | 1264 |  | Angie Robertson
5302 | 1264 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WPED I-WP127 - User Acceptance Testing Plan - Collaborative Review & Update | 17 hrs | 10 days | Mon 8/21/23 | Fri 9/1/23 | 1263 | 1265 |  | Carolyn Hicks,Angie Robertson,Matthew Breeding,Jennifer Reeves,Deana Metcalf,Julian Gotreaux,Tommy Werner,Matt Cole,Mary Punty,Stacey Terry
5303 | 1265 | Future Task |  |  | I-WP127 | Angie Robertson | Approve | WPED I-WP127 - User Acceptance Testing Plan - Approve | 0 hrs | 0 days | Fri 9/1/23 | Fri 9/1/23 | 1264 | 1266FS+41 days |  | Jimmy Cox
5310 | 1266 | Future Task |  | RW | I-WP127 | Angie Robertson | Create | Create User Acceptance Plan | 40 hrs | 81 days | Wed 11/1/23 | Thu 2/29/24 | 1265FS+41 days | 1267 |  | Matthew Breeding,Jennifer Reeves,Carolyn Hicks,Deana Metcalf,Angie Robertson
5304 | 1267 | Future Task |  |  | I-WP127 | Angie Robertson | Submit | WP I-WP127 - User Acceptance Testing Plan - Submit | 0 hrs | 0 days | Thu 2/29/24 | Thu 2/29/24 | 1266 | 1268 |  | Angie Robertson
5305 | 1268 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WP I-WP127 - User Acceptance Testing Plan - Department QC | 8 hrs | 1 day | Fri 3/1/24 | Fri 3/1/24 | 1267 | 1269 |  | Gabriela Gibson
5306 | 1269 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WP I-WP127 - User Acceptance Testing Plan - Collaborative Review & Update | 10 hrs | 10 days | Mon 3/4/24 | Fri 3/15/24 | 1268 | 1270 |  | Matthew Breeding,Jennifer Reeves,Carolyn Hicks,Deana Metcalf,Angie Robertson
5307 | 1270 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WP I-WP127 - User Acceptance Testing Plan - Style Guide Review | 2 hrs | 1 day | Mon 3/18/24 | Mon 3/18/24 | 1269 | 1271 |  | Tatiana Eubanks
5308 | 1271 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WP I-WP127 - User Acceptance Testing Plan - Final Review & Update | 10 hrs | 5 days | Tue 3/19/24 | Mon 3/25/24 | 1270 | 1272 |  | Angie Robertson,Jimmy Cox
5309 | 1272 | Future Task |  |  | I-WP127 | Angie Robertson | Approve | WP I-WP127 - User Acceptance Testing Plan - Approve | 0 hrs | 0 days | Mon 3/25/24 | Mon 3/25/24 | 1271 | 1274,559FS+215 days,600 |  | Jimmy Cox
3967 | 1273 | Future Task | [5 empty] | UAT | 1 hr | 163 days | Tue 4/1/25 | Wed 11/19/25
4002 | 1274 | Future Task |  | RW | UAT | Matt Breeding | Create | UAT Testing | 1 hr | 163 days | Tue 4/1/25 | Wed 11/19/25 | 17525631272587 | 1783,1808SS+30 days | Dates to be confirmed in I-WP127 | Jimmy Cox,Angie Robertson
7214 | 1275 | Future Task | [5 empty] | Other | 46 hrs | 15 days | Mon 5/5/25 | Fri 5/23/25
7216 | 1276 | Future Task |  |  |  | Manojkumar Gurjar | Create | Prepare for data migration from FLAIR IW for DW/IW | 6 hrs | 5 days | Mon 5/5/25 | Fri 5/9/25 | 765FS+4 days | 1277 |  | Stacey Terry,Jimmy Cox,Angie Robertson,Matt Cole,Matthew Breeding,Manojkumar Gurjar
7215 | 1277 | Future Task |  |  |  | Manojkumar Gurjar | Create | Validate the IW data migration | 40 hrs | 10 days | Mon 5/12/25 | Fri 5/23/25 | 1276 |  |  | Matthew Breeding,Jennifer Reeves
3772 | 1278 | Future Task | [5 empty] | Deploy | 1,938 hrs | 565 days | Fri 11/3/23 | Wed 2/4/26
7188 | 1279 | Future Task |  |  | SG5 | Jimmy Cox | Create | Stage Gate 5: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 6/30/25 | Mon 7/7/25 |  | 1280 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7189 | 1280 | Future Task |  |  | SG5 | Jimmy Cox | Create | Stage Gate 5: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Tue 7/8/25 | Mon 7/21/25 | 1279 | 1281FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7190 | 1281 | Future Task |  |  | SG5 | Jimmy Cox | Create | Stage Gate 5: Prepare information package for ESC | 11 hrs | 10 days | Fri 11/7/25 | Fri 11/21/25 | 1280FS+77 days | 1282 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7191 | 1282 | Future Task |  |  | SG5 | Jimmy Cox | Create | Stage Gate 5: Collaborative Review and Update of information package | 11 hrs | 5 days | Mon 11/24/25 | Tue 12/2/25 | 1281 | 1283 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7192 | 1283 | Future Task |  |  | SG5 | Jimmy Cox | Create | Stage Gate 5: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 12/3/25 | Wed 12/3/25 | 1282 |  |  | Dusti Kincl
7156 | 1284 | Future Task |  |  | SG5 | Jimmy Cox | Milestone | Stage Gate 5: Deployment Readiness | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 7.2579e+37 |  | December 17, 2025 - ESC | Executive Steering Committee
7193 | 1285 | Future Task |  |  | SG6 | Jimmy Cox | Create | Stage Gate 6: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 7/14/25 | Fri 7/18/25 |  | 1286 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7194 | 1286 | Future Task |  |  | SG6 | Jimmy Cox | Create | Stage Gate 6: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Mon 7/21/25 | Fri 8/1/25 | 1285 | 1287FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7195 | 1287 | Future Task |  |  | SG6 | Jimmy Cox | Create | Stage Gate 6: Prepare information package for ESC | 11 hrs | 10 days | Fri 11/21/25 | Mon 12/8/25 | 1286FS+77 days | 1288 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7196 | 1288 | Future Task |  |  | SG6 | Jimmy Cox | Create | Stage Gate 6: Collaborative Review and Update of information package | 11 hrs | 5 days | Tue 12/9/25 | Mon 12/15/25 | 1287 | 1289 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7197 | 1289 | Future Task |  |  | SG6 | Jimmy Cox | Create | Stage Gate 6: Provide Checklist and information package to the ESC | 1 hr | 1 day | Tue 12/16/25 | Tue 12/16/25 | 1288 |  |  | Dusti Kincl
7157 | 1290 | Future Task |  |  | SG6 | Jimmy Cox | Milestone | Stage Gate 6: Confirm Deployment | 0 hrs | 0 days | Fri 12/19/25 | Fri 12/19/25 | 141814331381 | 1296 | 2025-12-30 | Jimmy Cox,Angie Robertson,Matt Cole
7198 | 1291 | Future Task |  |  | SG7 | Jimmy Cox | Create | Stage Gate 7: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 7/21/25 | Fri 7/25/25 |  | 1292 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7199 | 1292 | Future Task |  |  | SG7 | Jimmy Cox | Create | Stage Gate 7: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Mon 7/28/25 | Fri 8/8/25 | 1291 | 1293FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7200 | 1293 | Future Task |  |  | SG7 | Jimmy Cox | Create | Stage Gate 7: Prepare information package for ESC | 11 hrs | 10 days | Tue 12/2/25 | Mon 12/15/25 | 1292FS+77 days | 1294 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7201 | 1294 | Future Task |  |  | SG7 | Jimmy Cox | Create | Stage Gate 7: Collaborative Review and Update of information package | 11 hrs | 5 days | Tue 12/16/25 | Mon 12/22/25 | 1293 | 1295 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7202 | 1295 | Future Task |  |  | SG7 | Jimmy Cox | Create | Stage Gate 7: Provide Checklist and information package to the ESC | 1 hr | 1 day | Tue 12/23/25 | Tue 12/23/25 | 1294 |  |  | Dusti Kincl
7158 | 1296 | Future Task |  |  | SG7 | Jimmy Cox | Milestone | Stage Gate 7: Go-Live | 0 hrs | 0 days | Fri 12/19/25 | Fri 12/19/25 | 1290 |  | 2026-01-06 | Jimmy Cox,Angie Robertson,Matt Cole
5311 | 1297 | Future Task |  |  | D645 | Mary Punty |  | D645 - Updated Deployment Strategy | 265 hrs | 122 days | Fri 11/3/23 | Tue 4/30/24
5312 | 1298 | Future Task |  |  | D645 | Mary Punty | Create | DED D645 - Updated Deployment Strategy - Create | 16 hrs | 10 days | Fri 11/3/23 | Fri 11/17/23 | 1 | 1299 |  | Mary Punty,Bryan Sohayda
5313 | 1299 | Future Task |  |  | D645 | Mary Punty | Submit | DED D645 - Updated Deployment Strategy - Submit | 0 hrs | 0 days | Fri 11/17/23 | Fri 11/17/23 | 1298 | 1300 |  | Mary Punty,Joy Schneider
5314 | 1300 | Future Task |  |  | D645 | Mary Punty | Review | DED D645 - Updated Deployment Strategy - Collaborative Review | 20 hrs | 10 days | Mon 11/20/23 | Tue 12/5/23 | 1299 | 1301 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5315 | 1301 | Future Task |  |  | D645 | Mary Punty | Approve | DED D645 - Updated Deployment Strategy - Approve | 0 hrs | 0 days | Tue 12/5/23 | Tue 12/5/23 | 1300 | 1302FS+17 days |  | Jimmy Cox
5339 | 1302 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Document assumptions about deployment | 20 hrs | 9 days | Tue 1/2/24 | Fri 1/12/24 | 1301FS+17 days | 1303 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5340 | 1303 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Create Deployment Kickoff Presentation | 20 hrs | 9 days | Tue 1/16/24 | Fri 1/26/24 | 1302 | 1304 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5341 | 1304 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Review Deployment Kickoff Presentation | 20 hrs | 5 days | Mon 1/29/24 | Fri 2/2/24 | 1303 | 1305 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5342 | 1305 | Future Task |  | RW | D645 | Mary Punty | Create | D645 - Describe Deployment Calendar | 20 hrs | 10 days | Mon 2/5/24 | Fri 2/16/24 | 1304 | 1306 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5343 | 1306 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Review Deployment Calendar | 20 hrs | 5 days | Mon 2/19/24 | Fri 2/23/24 | 1305 | 1307 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5344 | 1307 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Describe Cutover Checklist | 20 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 1306 | 1308 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5345 | 1308 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Review Cutover Checklist | 20 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 1307 | 1309 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5346 | 1309 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Finalize Draft - Deployment Strategy | 20 hrs | 5 days | Mon 3/25/24 | Fri 3/29/24 | 1308 | 1310 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5347 | 1310 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Review Draft - Deployment Strategy | 20 hrs | 5 days | Mon 4/1/24 | Fri 4/5/24 | 1309 | 1311 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5316 | 1311 | Future Task |  |  | D645 | Mary Punty | Submit | DEL D645 - Updated Deployment Strategy - Draft Submission | 0 hrs | 0 days | Fri 4/5/24 | Fri 4/5/24 | 1310 | 1312 |  | Mary Punty,Joy Schneider
5317 | 1312 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 4/8/24 | Fri 4/12/24 | 1311 | 1313 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5318 | 1313 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Style Guide Review | 1 hr | 1 day | Mon 4/15/24 | Mon 4/15/24 | 1312 | 1314 |  | Dusti Kincl
5319 | 1314 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Final Collaborative Review | 16 hrs | 5 days | Tue 4/16/24 | Mon 4/22/24 | 1313 | 1315 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5320 | 1315 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Accenture QC | 4 hrs | 2 days | Tue 4/23/24 | Wed 4/24/24 | 1314 | 1316 |  | Joy Schneider
5321 | 1316 | Future Task |  |  | D645 | Mary Punty | Submit | DEL D645 - Updated Deployment Strategy - Submit | 0 hrs | 0 days | Wed 4/24/24 | Wed 4/24/24 | 1315 | 1317 |  | Joy Schneider
5322 | 1317 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Department QC | 4 hrs | 1 day | Thu 4/25/24 | Thu 4/25/24 | 1316 | 1318 |  | Tommy Werner,Gabriela Gibson
5323 | 1318 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Contract Manager Review | 8 hrs | 3 days | Fri 4/26/24 | Tue 4/30/24 | 1317 | 13191321 |  | Sean Buchanan
5324 | 1319 | Future Task |  |  | D645 | Mary Punty | Accept | DEL D645 - Updated Deployment Strategy - Accept | 0 hrs | 0 days | Tue 4/30/24 | Tue 4/30/24 | 1318 |  | 2024-04-01 | Sean Buchanan
5325 | 1320 | Future Task | Yes |  | D658 | Mary Punty |  | D658 - Develop the Deployment and Contingency Plan | 498 hrs | 149 days | Mon 8/26/24 | Mon 3/31/25
5326 | 1321 | Future Task |  |  | D658 | Mary Punty | Create | DED D658 - Develop the Deployment and Contingency Plan - Create | 16 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1318 | 1322 |  | Mary Punty,Bryan Sohayda
5327 | 1322 | Future Task |  |  | D658 | Mary Punty | Submit | DED D658 - Develop the Deployment and Contingency Plan - Submit | 0 hrs | 0 days | Mon 9/9/24 | Mon 9/9/24 | 1321 | 1323 |  | Mary Punty,Joy Schneider
5328 | 1323 | Future Task |  |  | D658 | Mary Punty | Review | DED D658 - Develop the Deployment and Contingency Plan - Collaborative Review | 20 hrs | 10 days | Tue 9/10/24 | Mon 9/23/24 | 1322 | 1324 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5329 | 1324 | Future Task |  |  | D658 | Mary Punty | Approve | DED D658 - Develop the Deployment and Contingency Plan - Approve | 0 hrs | 0 days | Mon 9/23/24 | Mon 9/23/24 | 1323 | 1325FS+24 days |  | Jimmy Cox
5348 | 1325 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Create Deployment and Contingency Plan pitch deck | 18 hrs | 9 days | Mon 10/28/24 | Thu 11/7/24 | 1324FS+24 days | 1326 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5349 | 1326 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review Deployment and Contingency Plan pitch deck | 40 hrs | 4 days | Fri 11/8/24 | Thu 11/14/24 | 1325 | 1327FS+8 days,1331 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5350 | 1327 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Prepare materials for Dec Sponsor Meeting and Review | 25 hrs | 5 days | Wed 11/27/24 | Thu 12/5/24 | 1326FS+8 days | 1328 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5351 | 1328 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Plan for and hold December Sponsor Meeting | 25 hrs | 5 days | Fri 12/6/24 | Thu 12/12/24 | 1327 | 1329FS+11 days |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5352 | 1329 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Gather Deployment and Contingency Plan materials for January ESC Meeting | 35 hrs | 7 days | Tue 12/31/24 | Thu 1/9/25 | 1328FS+11 days | 1330,1335SS |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5353 | 1330 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review Deployment and Contingency Plan materials for January ESC Meeting | 25 hrs | 5 days | Fri 1/10/25 | Thu 1/16/25 | 1329 | 1339 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5354 | 1331 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Identify and document deployment and post-implementation support activities | 20 hrs | 8 days | Fri 11/15/24 | Tue 11/26/24 | 1326 | 1332 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5355 | 1332 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review and document deployment and post-implementation support activities | 25 hrs | 5 days | Wed 11/27/24 | Thu 12/5/24 | 1331 | 1333 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5356 | 1333 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Identify and document timing of cutover activities | 25 hrs | 5 days | Fri 12/6/24 | Thu 12/12/24 | 1332 | 1334 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5357 | 1334 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review and document timing of cutover activities | 25 hrs | 5 days | Fri 12/13/24 | Thu 12/19/24 | 1333 | 1335 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5358 | 1335 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Identify and document contingency scenarios | 20 hrs | 7 days | Tue 12/31/24 | Thu 1/9/25 | 1329SS,1334 | 1336 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5359 | 1336 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review contingency scenarios | 25 hrs | 5 days | Fri 1/10/25 | Thu 1/16/25 | 1335 | 1337 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5360 | 1337 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Define and document the approach to revert changes | 20 hrs | 4 days | Fri 1/17/25 | Thu 1/23/25 | 1336 | 1338 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5361 | 1338 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review the approach to revert changes | 25 hrs | 5 days | Fri 1/24/25 | Thu 1/30/25 | 1337 | 1339 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5362 | 1339 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Gather Deployment and Contingency Plan materials for February ESC Meeting | 25 hrs | 5 days | Fri 1/31/25 | Thu 2/6/25 | 13381330 | 1340 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5363 | 1340 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review Deployment and Contingency Plan materials for February ESC Meeting | 15 hrs | 3 days | Fri 2/7/25 | Tue 2/11/25 | 1339 | 1341FS+12 days |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5364 | 1341 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Confirm approach to Deployment and Contingency | 20 hrs | 5 days | Fri 2/28/25 | Thu 3/6/25 | 1340FS+12 days | 1342 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5330 | 1342 | Future Task |  |  | D658 | Mary Punty | Submit | DEL D658 - Develop the Deployment and Contingency Plan - Draft Submission | 0 hrs | 0 days | Thu 3/6/25 | Thu 3/6/25 | 1341 | 1343 |  | Mary Punty,Joy Schneider
5331 | 1343 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 3/7/25 | Thu 3/13/25 | 1342 | 1344 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5332 | 1344 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Style Guide Review | 1 hr | 1 day | Fri 3/14/25 | Fri 3/14/25 | 1343 | 1345 |  | Dusti Kincl
5333 | 1345 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Final Collaborative Review | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1344 | 1346 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5334 | 1346 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Accenture QC | 4 hrs | 2 days | Mon 3/24/25 | Tue 3/25/25 | 1345 | 1347 |  | Joy Schneider
5335 | 1347 | Future Task |  |  | D658 | Mary Punty | Submit | DEL D658 - Develop the Deployment and Contingency Plan - Submit | 0 hrs | 0 days | Tue 3/25/25 | Tue 3/25/25 | 1346 | 1348 |  | Joy Schneider
5336 | 1348 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Department QC | 4 hrs | 1 day | Wed 3/26/25 | Wed 3/26/25 | 1347 | 1349 |  | Tommy Werner,Gabriela Gibson
5337 | 1349 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Contract Manager Review | 8 hrs | 3 days | Thu 3/27/25 | Mon 3/31/25 | 1348 | 1350 |  | Sean Buchanan
5338 | 1350 | Future Task |  |  | D658 | Mary Punty | Accept | DEL D658 - Develop the Deployment and Contingency Plan - Accept | 0 hrs | 0 days | Mon 3/31/25 | Mon 3/31/25 | 1349 | 1284 | 2025-03-01 | Sean Buchanan
5365 | 1351 | Future Task | Yes |  | D678 | Bryan Sohayda |  | D678 - Final Known Issues & Enhancements Lists | 350 hrs | 86 days | Mon 8/4/25 | Fri 12/5/25
5366 | 1352 | Future Task |  |  | D678 | Bryan Sohayda | Create | DED D678 - Final Known Issues & Enhancements Lists - Create | 16 hrs | 10 days | Mon 8/4/25 | Fri 8/15/25 | 1 | 1353 |  | Mary Punty,Bryan Sohayda
5367 | 1353 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DED D678 - Final Known Issues & Enhancements Lists - Submit | 0 hrs | 0 days | Fri 8/15/25 | Fri 8/15/25 | 1352 | 1354 |  | Bryan Sohayda,Joy Schneider
5368 | 1354 | Future Task |  |  | D678 | Bryan Sohayda | Review | DED D678 - Final Known Issues & Enhancements Lists - Collaborative Review | 20 hrs | 10 days | Mon 8/18/25 | Fri 8/29/25 | 1353 | 1355 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5369 | 1355 | Future Task |  |  | D678 | Bryan Sohayda | Approve | DED D678 - Final Known Issues & Enhancements Lists - Approve | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 1354 | 1356FS+21 days |  | Jimmy Cox
5393 | 1356 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Initial Known Issues & Enhancements Lists | 20 hrs | 22 days | Wed 10/1/25 | Thu 10/30/25 | 1355FS+21 days | 1357SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5394 | 1357 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Review Open SIRs - Candidates for Known Issues List | 25 hrs | 5 days | Wed 10/1/25 | Tue 10/7/25 | 1356SS | 1358,1359SS |  | Bryan Sohayda,Mary Punty,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5395 | 1358 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Finalize Open SIRs - Candidates for Known Issues List | 24 hrs | 4 days | Wed 10/8/25 | Mon 10/13/25 | 1357 | 1360SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5396 | 1359 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Review Open SIRs - Candidates for Known Enhancements List | 30 hrs | 5 days | Wed 10/1/25 | Tue 10/7/25 | 1357SS | 1361 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5397 | 1360 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Finalize Open SIRs - Candidates for Known Enhancements List | 20 hrs | 4 days | Wed 10/8/25 | Mon 10/13/25 | 1358SS | 1361 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5398 | 1361 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Confirm Agreed Upon Known Issues | 30 hrs | 5 days | Tue 10/14/25 | Mon 10/20/25 | 13601359 | 1362SS,1363SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5399 | 1362 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Confirm Agreed Upon Known Enhancements | 30 hrs | 5 days | Tue 10/14/25 | Mon 10/20/25 | 1361SS | 1365 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5400 | 1363 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Create DEL Draft - Wrapper Document and Known Issues/Enhancements Lists | 20 hrs | 5 days | Tue 10/14/25 | Mon 10/20/25 | 1361SS | 1364 |  | Bryan Sohayda,Mary Punty
5401 | 1364 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Review DEL Draft - Wrapper Document and Known Issues/Enhancements Lists | 48 hrs | 8 days | Tue 10/21/25 | Thu 10/30/25 | 1363 | 1365 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5370 | 1365 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DEL D678 - Final Known Issues & Enhancements Lists - Draft Submission | 0 hrs | 0 days | Thu 10/30/25 | Thu 10/30/25 | 13641362 | 1366 |  | Bryan Sohayda,Joy Schneider
5371 | 1366 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 10/31/25 | Thu 11/6/25 | 1365 | 1367 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5372 | 1367 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Style Guide Review | 1 hr | 1 day | Fri 11/7/25 | Fri 11/7/25 | 1366 | 1368 |  | Dusti Kincl
5373 | 1368 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Final Collaborative Review | 16 hrs | 5 days | Mon 11/10/25 | Mon 11/17/25 | 1367 | 1369 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5374 | 1369 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Accenture QC | 4 hrs | 2 days | Tue 11/18/25 | Wed 11/19/25 | 1368 | 1370 |  | Joy Schneider
5375 | 1370 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DEL D678 - Final Known Issues & Enhancements Lists - Submit | 0 hrs | 0 days | Wed 11/19/25 | Wed 11/19/25 | 1369 | 1371 |  | Joy Schneider
5376 | 1371 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Department QC | 4 hrs | 1 day | Thu 11/20/25 | Thu 11/20/25 | 1370 | 1372 |  | Tommy Werner,Gabriela Gibson
5377 | 1372 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Contract Manager Review | 8 hrs | 3 days | Fri 11/21/25 | Tue 11/25/25 | 1371 | 1373 |  | Sean Buchanan
5378 | 1373 | Future Task |  |  | D678 | Bryan Sohayda | Accept | DEL D678 - Final Known Issues & Enhancements Lists - Accept | 0 hrs | 0 days | Tue 11/25/25 | Tue 11/25/25 | 1372 | 1374FS+1 day,1284 | 2025-12-01 | Sean Buchanan
5407 | 1374 | Future Task |  | RW | D678 | Bryan Sohayda | Create | Refresh Known Issues/Enhancements List to Prep for Stage Gate 5 | 18 hrs | 5 days | Mon 12/1/25 | Fri 12/5/25 | 1373FS+1 day |  |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5379 | 1375 | Future Task |  |  | D679 | Stacey Terry |  | D679 - Go-Live of Financials and Payroll Waves | 184 hrs | 82 days | Mon 10/6/25 | Wed 2/4/26
5380 | 1376 | Future Task |  |  | D679 | Stacey Terry | Create | DED D679 - Go-Live of Financials and Payroll Waves - Create | 16 hrs | 10 days | Mon 10/6/25 | Fri 10/17/25 | 1 | 1377 |  | Stacey Terry,Manojkumar Gurjar
5381 | 1377 | Future Task |  |  | D679 | Stacey Terry | Submit | DED D679 - Go-Live of Financials and Payroll Waves - Submit | 0 hrs | 0 days | Fri 10/17/25 | Fri 10/17/25 | 1376 | 1378 |  | Stacey Terry,Joy Schneider
5382 | 1378 | Future Task |  |  | D679 | Stacey Terry | Review | DED D679 - Go-Live of Financials and Payroll Waves - Collaborative Review | 28 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 1377 | 1379 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5383 | 1379 | Future Task |  |  | D679 | Stacey Terry | Approve | DED D679 - Go-Live of Financials and Payroll Waves - Approve | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 1378 | 1380FS+22 days |  | Jimmy Cox
5403 | 1380 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Go-Live of Financials and Payroll Waves | 15 hrs | 5 days | Mon 12/8/25 | Fri 12/12/25 | 1379FS+22 days | 1381 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5404 | 1381 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Document Go-Live Applications Listing | 15 hrs | 5 days | Mon 12/15/25 | Fri 12/19/25 | 1380 | 1385FS+8 days,1290,1382SS |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
7213 | 1382 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Execute Pre-Cutover Activities | 5 hrs | 11 days | Mon 12/15/25 | Tue 12/30/25 | 1381SS | 1383FS-1 day |  | Stacey Terry,Mary Punty,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner
7212 | 1383 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Execute Cutover Activities | 5 hrs | 2 days | Tue 12/30/25 | Wed 12/31/25 | 1382FS-1 day | 1384 |  | Stacey Terry,Mary Punty,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner
7211 | 1384 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Execute Post-Cutover Activities | 5 hrs | 11 days | Fri 1/2/26 | Fri 1/16/26 | 1383 | 1391 |  | Stacey Terry,Mary Punty,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner
5405 | 1385 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Document Go-Live Tasks Completed | 15 hrs | 5 days | Mon 1/5/26 | Fri 1/9/26 | 1381FS+8 days,1765 | 1386SS |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5406 | 1386 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Document Go-List of Agencies Participated | 15 hrs | 5 days | Mon 1/5/26 | Fri 1/9/26 | 1385SS | 1387 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5384 | 1387 | Future Task |  |  | D679 | Stacey Terry | Submit | DEL D679 - Go-Live of Financials and Payroll Waves - Draft Submission | 0 hrs | 0 days | Fri 1/9/26 | Fri 1/9/26 | 1386575 | 1388 |  | Stacey Terry,Joy Schneider
5385 | 1388 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Pre-Submission Collaborative Review | 24 hrs | 5 days | Mon 1/12/26 | Fri 1/16/26 | 1387 | 1389 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5386 | 1389 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Style Guide Review | 1 hr | 1 day | Tue 1/20/26 | Tue 1/20/26 | 1388 | 1390 |  | Dusti Kincl
5387 | 1390 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Final Collaborative Review | 24 hrs | 5 days | Wed 1/21/26 | Tue 1/27/26 | 1389 | 1391 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5388 | 1391 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Accenture QC | 4 hrs | 2 days | Wed 1/28/26 | Thu 1/29/26 | 13901384 | 1392 |  | Joy Schneider
5389 | 1392 | Future Task |  |  | D679 | Stacey Terry | Submit | DEL D679 - Go-Live of Financials and Payroll Waves - Submit | 0 hrs | 0 days | Thu 1/29/26 | Thu 1/29/26 | 1391 | 1393 |  | Joy Schneider
5390 | 1393 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Department QC | 4 hrs | 1 day | Fri 1/30/26 | Fri 1/30/26 | 1392 | 1394 |  | Tommy Werner,Gabriela Gibson
5391 | 1394 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Contract Manager Review | 8 hrs | 3 days | Mon 2/2/26 | Wed 2/4/26 | 1393 | 1395 |  | Sean Buchanan
5392 | 1395 | Future Task |  |  | D679 | Stacey Terry | Accept | DEL D679 - Go-Live of Financials and Payroll Waves - Accept | 0 hrs | 0 days | Wed 2/4/26 | Wed 2/4/26 | 1394 |  | 2026-01-01 | Sean Buchanan
6739 | 1396 | Future Task |  |  | WP425 | Bryan Sohayda |  | WP425 - Production Support Operations Plan | 356 hrs | 129 days | Mon 10/14/24 | Fri 4/18/25
6740 | 1397 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WPED WP425 - Production Support Operations Plan - Create | 8 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 1 | 1398 |  | Bryan Sohayda
6741 | 1398 | Future Task |  |  | WP425 | Bryan Sohayda | Submit | WPED WP425 - Production Support Operations Plan - Submit | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 1397 | 1399 |  | Joy Schneider,Bryan Sohayda
6742 | 1399 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WPED WP425 - Production Support Operations Plan - Review | 16 hrs | 10 days | Mon 10/28/24 | Fri 11/8/24 | 1398 | 1400 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
6743 | 1400 | Future Task |  |  | WP425 | Bryan Sohayda | Approve | WPED WP425 - Production Support Operations Plan - Approve | 0 hrs | 0 days | Fri 11/8/24 | Fri 11/8/24 | 1399 | 1401FS+22 days |  | Jimmy Cox
6744 | 1401 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Update Production Support Operations Plan | 20 hrs | 72 days | Mon 12/16/24 | Fri 3/28/25 | 1400FS+22 days | 1402SS |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6745 | 1402 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Introduction, Overview, Collab taken with partners, team R&R | 20 hrs | 5 days | Mon 12/16/24 | Fri 12/20/24 | 1401SS | 1403FS+8 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6746 | 1403 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document Production Support services provided | 20 hrs | 5 days | Mon 1/6/25 | Fri 1/10/25 | 1402FS+8 days | 1404 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6747 | 1404 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review and provide feedback on Production Support Services Provided draft | 20 hrs | 5 days | Mon 1/13/25 | Fri 1/17/25 | 1403 | 1405 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6748 | 1405 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Create Maintenance Calendar template | 48 hrs | 4 days | Tue 1/21/25 | Fri 1/24/25 | 1404 | 1406 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6749 | 1406 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review Maintenance Calendar template | 20 hrs | 5 days | Mon 1/27/25 | Fri 1/31/25 | 1405 | 1407 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6750 | 1407 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document production support business processes and tools list | 20 hrs | 5 days | Mon 2/3/25 | Fri 2/7/25 | 1406 | 1408 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6751 | 1408 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review and provide feedback on Production Support business processes and tools list draft | 20 hrs | 5 days | Mon 2/10/25 | Fri 2/14/25 | 1407 | 1409 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6752 | 1409 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document production support schedule of activities | 20 hrs | 5 days | Mon 2/17/25 | Fri 2/21/25 | 1408 | 1410 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6753 | 1410 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review and provide feedback on Production Support schedule of activities draft | 20 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 1409 | 1411 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6754 | 1411 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document production support performance expectations | 20 hrs | 5 days | Mon 3/3/25 | Fri 3/7/25 | 1410 | 1412 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6755 | 1412 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review and provide feedback on Production Support performance expectations draft | 20 hrs | 5 days | Mon 3/10/25 | Fri 3/14/25 | 1411 | 1413 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6756 | 1413 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document production support team roles, responsibilities, and staffing | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1412 | 1414 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6757 | 1414 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Full walkthrough of Production Support Operations Plan through facilitated meetings | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 1413 | 1415 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6758 | 1415 | Future Task |  |  | WP425 | Bryan Sohayda | Submit | WP WP425 - Production Support Operations Plan - Submit | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 1414 | 1416 |  | Joy Schneider,Bryan Sohayda
6759 | 1416 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WP WP425 - Production Support Operations Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 3/31/25 | Fri 4/11/25 | 1415 | 1417 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6760 | 1417 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WP WP425 - Production Support Operations Plan - Final Review & Edits | 12 hrs | 5 days | Mon 4/14/25 | Fri 4/18/25 | 1416 | 1418 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6761 | 1418 | Future Task |  |  | WP425 | Bryan Sohayda | Approve | WP WP425 - Production Support Operations Plan - Approve | 0 hrs | 0 days | Fri 4/18/25 | Fri 4/18/25 | 1417 | 1290 | 2025-04-01 | Jimmy Cox
6762 | 1419 | Future Task |  |  | WP427 | Bryan Sohayda |  | WP427 - Production Support Application Configuration Management Plan | 168 hrs | 107 days | Mon 12/2/24 | Fri 5/2/25
6763 | 1420 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WPED WP427 - Production Support Application Configuration Management Plan - Create | 8 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 1 | 1421 |  | Bryan Sohayda
6764 | 1421 | Future Task |  |  | WP427 | Bryan Sohayda | Submit | WPED WP427 - Production Support Application Configuration Management Plan - Submit | 0 hrs | 0 days | Fri 12/13/24 | Fri 12/13/24 | 1420 | 1422 |  | Joy Schneider,Bryan Sohayda
6765 | 1422 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WPED WP427 - Production Support Application Configuration Management Plan - Review | 16 hrs | 10 days | Mon 12/16/24 | Mon 12/30/24 | 1421 | 1423 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
6766 | 1423 | Future Task |  |  | WP427 | Bryan Sohayda | Approve | WPED WP427 - Production Support Application Configuration Management Plan - Approve | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 1422 | 1424FS+22 days |  | Jimmy Cox
6767 | 1424 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Updated Configuration Management Processes for Release and Maintenance | 20 hrs | 50 days | Mon 2/3/25 | Fri 4/11/25 | 1423FS+22 days | 1425SS,1430,1426SS+10 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6768 | 1425 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Define and Document Application Configuration Management Processes for Release and Maintenance | 20 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1424SS | 1426 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6769 | 1426 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Review and confirm Application and Infrastructure Configuration Management Processes for Release and Maintenance | 20 hrs | 5 days | Mon 2/17/25 | Fri 2/21/25 | 1424SS+10 days,1425 | 1427 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6770 | 1427 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Define and document System Configuration Control Process Steps and Diagram | 20 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 1426 | 1428 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6771 | 1428 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Review System Configuration Control Process Steps and Diagram | 20 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1427 | 1429FS+10 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6772 | 1429 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Full draft review pre-submission | 20 hrs | 10 days | Mon 3/31/25 | Fri 4/11/25 | 1428FS+10 days | 1430 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6773 | 1430 | Future Task |  |  | WP427 | Bryan Sohayda | Submit | WP WP427 - Production Support Application Configuration Management Plan - Submit | 0 hrs | 0 days | Fri 4/11/25 | Fri 4/11/25 | 14241429 | 1431 |  | Joy Schneider,Bryan Sohayda
6774 | 1431 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WP WP427 - Production Support Application Configuration Management Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 1430 | 1432 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6775 | 1432 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WP WP427 - Production Support Application Configuration Management Plan - Final Review & Edits | 12 hrs | 5 days | Mon 4/28/25 | Fri 5/2/25 | 1431 | 1433 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6776 | 1433 | Future Task |  |  | WP427 | Bryan Sohayda | Approve | WP WP427 - Production Support Application Configuration Management Plan - Approve | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 1432 | 1290 | 2025-04-01 | Jimmy Cox
2953 | 1434 | Late | [5 empty] | Stakeholder Engagement | 4,324 hrs | 730 days | Mon 5/8/23 | Tue 3/31/26
2972 | 1435 | On Schedule | [5 empty] | Training | 2,890 hrs | 722 days | Thu 5/18/23 | Tue 3/31/26
6906 | 1436 | On Schedule |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 - Data Inventory for Financials and Payroll Wave | 105 hrs | 277 days | Thu 5/18/23 | Fri 6/21/24
6907 | 1437 | On Schedule |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 - Data Inventory for Financials and Payroll Wave | 22 hrs | 277 days | Thu 5/18/23 | Fri 6/21/24
6908 | 1438 | Complete |  |  | I-WP102 | Jennifer Reeves | Create | WPED I-WP102 - Data Inventory for Financials and Payroll Wave - Create | 2 hrs | 10 days | Thu 5/18/23 | Thu 6/1/23 | 1 | 1439 |  | Jennifer Grant,Jennifer Reeves
6909 | 1439 | Complete |  |  | I-WP102 | Jennifer Reeves | Submit | WPED I-WP102 - Data Inventory for Financials and Payroll Wave - Submit | 0 hrs | 0 days | Thu 6/1/23 | Thu 6/1/23 | 1438 | 14401459 |  | Jennifer Grant,Jennifer Reeves
6910 | 1440 | On Schedule |  |  | I-WP102 | Jennifer Reeves | Review | WPED I-WP102 - Data Inventory for Financials and Payroll Wave - Collaborative Review and Update | 8 hrs | 10 days | Fri 6/2/23 | Thu 6/15/23 | 1439 | 1441 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Reeves,Jennifer Grant
6911 | 1441 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | WPED I-WP102 - Data Inventory for Financials and Payroll Wave - Approve | 0 hrs | 0 days | Thu 6/15/23 | Thu 6/15/23 | 1440 | 1450 |  | Jimmy Cox
6912 | 1442 | Future Task |  |  | I-WP102 | Jennifer Reeves | Submit | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Submit | 0 hrs | 0 days | Wed 5/29/24 | Wed 5/29/24 | 1481 | 1443 |  | Jennifer Grant,Jennifer Reeves
6913 | 1443 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Department QC | 2 hrs | 1 day | Thu 5/30/24 | Thu 5/30/24 | 1442 | 1444 |  | Gabriela Gibson
6914 | 1444 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Collaborative Review & Update | 7 hrs | 10 days | Fri 5/31/24 | Thu 6/13/24 | 1443 | 1445 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Nikki Klein,Daylin Reyes,Angie Robertson
6915 | 1445 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Style Guide Review | 1 hr | 1 day | Fri 6/14/24 | Fri 6/14/24 | 1444 | 1446 |  | Tatiana Eubanks
6916 | 1446 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Final Review & Update | 2 hrs | 5 days | Mon 6/17/24 | Fri 6/21/24 | 144514781482 | 1447 |  | Angie Robertson,Jimmy Cox
6917 | 1447 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Approve | 0 hrs | 0 days | Fri 6/21/24 | Fri 6/21/24 | 1446 |  |  | Jimmy Cox
6918 | 1448 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | Data Inventory for Financials and Payroll Wave | 83 hrs | 245 days | Fri 6/16/23 | Wed 6/5/24
6919 | 1449 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment I - Data | 20 hrs | 45 days | Fri 6/16/23 | Fri 8/18/23
6920 | 1450 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create - Data Inventory Format | 7 hrs | 5 days | Fri 6/16/23 | Thu 6/22/23 | 1441 | 1451 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Nikki Klein,Daylin Reyes,Angie Robertson
6921 | 1451 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory Format | 5 hrs | 5 days | Fri 6/23/23 | Thu 6/29/23 | 1450 | 1452 |  | Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Daylin Reyes,Angie Robertson
6922 | 1452 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory Format | 1 hr | 5 days | Fri 6/30/23 | Fri 7/7/23 | 1451 | 1453 |  | Jimmy Cox
6923 | 1453 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | Mon 7/10/23 | Fri 7/28/23 | 1452 | 1454 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6924 | 1454 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 15 days | Mon 7/31/23 | Fri 8/18/23 | 1453 | 1456 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6925 | 1455 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment II - Data | 7 hrs | 20 days | Mon 10/9/23 | Fri 11/3/23
6926 | 1456 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | Mon 10/9/23 | Fri 10/27/23 | 61SS,1454 | 1457 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6927 | 1457 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 5 days | Mon 10/30/23 | Fri 11/3/23 | 1456 | 1459 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6928 | 1458 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment III - Data | 13 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
6929 | 1459 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 1439,1457,141SS | 14601466 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6930 | 1460 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1459 | 14611467 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6931 | 1461 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Functional Teams | 6 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1460 | 1463 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6932 | 1462 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Update & Publish Data Inventory | 18 hrs | 25 days | Fri 2/2/24 | Thu 3/7/24
6933 | 1463 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 5 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1461 | 1464 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6934 | 1464 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1463 | 1465 |  | Jimmy Cox
6935 | 1465 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Coordinate Knowledge Base Update | 2 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1464 | 1478 |  | Jennifer Reeves,Daylin Reyes
6936 | 1466 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create Communication for Data Inventory | 2 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1459 | 1467 |  | Jennifer Grant,Jennifer Reeves
6937 | 1467 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review for Communication for Data Inventory | 2 hrs | 9 days | Fri 2/9/24 | Wed 2/21/24 | 14601466 | 1468 |  | Dusti Kincl,Angie Robertson
6938 | 1468 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Communication | 1 hr | 5 days | Thu 2/22/24 | Wed 2/28/24 | 1467 | 1469 |  | Jimmy Cox
6939 | 1469 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Publish Data Inventory | 4 hrs | 2 days | Thu 2/29/24 | Fri 3/1/24 | 1468 | 1470 |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6940 | 1470 | Future Task |  | RW-Communication | I-WP102 | Jennifer Reeves | Create | I-WP102 Share - Communication for Data Inventory | 1 hr | 2 days | Mon 3/4/24 | Tue 3/5/24 | 1469 | 1472 |  | Dusti Kincl
6941 | 1471 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment IV - Data | 11 hrs | 25 days | Wed 4/10/24 | Tue 5/14/24
6942 | 1472 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 3 hrs | 15 days | Wed 4/10/24 | Tue 4/30/24 | 1470 | 14731479 |  | Jennifer Reeves,Pradeep Koul,Tanya McCarty
6943 | 1473 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 2 hrs | 5 days | Wed 5/1/24 | Tue 5/7/24 | 1472 | 1474 |  | Jennifer Reeves,Matthew Breeding
6944 | 1474 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 6 hrs | 5 days | Wed 5/8/24 | Tue 5/14/24 | 1473 | 1476 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6945 | 1475 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Update & Publish Data Inventory | 14 hrs | 25 days | Wed 5/1/24 | Wed 6/5/24
6946 | 1476 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 3 hrs | 5 days | Wed 5/15/24 | Tue 5/21/24 | 1474 | 1477 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves
6947 | 1477 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory | 2 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1476 | 1478 |  | Angie Robertson,Jimmy Cox
6948 | 1478 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Coordinate Knowledge Base Update | 2 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 14771465 | 1446 |  | Jennifer Reeves,Daylin Reyes
6949 | 1479 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create Communication - Data Inventory | 2 hrs | 5 days | Wed 5/1/24 | Tue 5/7/24 | 1472 | 1480 |  | Jennifer Grant,Jennifer Reeves
6950 | 1480 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Communication for Data Inventory | 2 hrs | 10 days | Wed 5/8/24 | Tue 5/21/24 | 1479 | 1481 |  | Dusti Kincl,Angie Robertson
6951 | 1481 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Communication for Data Inventory | 2 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1480 | 14421482 |  | Jennifer Grant,Jennifer Reeves
6952 | 1482 | Future Task |  | RW-Communication | I-WP102 | Jennifer Reeves | Create | I-WP102 Share Communication for Data Inventory | 1 hr | 2 days | Thu 5/30/24 | Fri 5/31/24 | 1481 | 1446 |  | Dusti Kincl
7039 | 1483 | On Schedule |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 - Accounting Entry Inventory | 271 hrs | 285 days | Thu 5/18/23 | Wed 7/3/24
7040 | 1484 | Complete |  |  | I-WP103 | Jennifer Reeves | Create | WPED I-WP103 - Accounting Entry Inventory - Create | 10 hrs | 10 days | Thu 5/18/23 | Thu 6/1/23 | 1 | 1485 |  | Jennifer Grant,Jennifer Reeves
7041 | 1485 | Complete |  |  | I-WP103 | Jennifer Reeves | Submit | WPED I-WP103 - Accounting Entry Inventory - Submit | 0 hrs | 0 days | Thu 6/1/23 | Thu 6/1/23 | 1484 | 1486 |  | Jennifer Grant,Jennifer Reeves
7042 | 1486 | On Schedule |  |  | I-WP103 | Jennifer Reeves | Review | WPED I-WP103 - Accounting Entry Inventory - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/2/23 | Thu 6/15/23 | 1485 | 1487 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7043 | 1487 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | WPED I-WP103 - Accounting Entry Inventory - Approve | 0 hrs | 0 days | Thu 6/15/23 | Thu 6/15/23 | 1486 | 1496FS+37 days |  | Jimmy Cox
7044 | 1488 | Future Task |  |  | I-WP103 | Jennifer Reeves | Submit | WP I-WP103 - Accounting Entry Inventory - Submit | 0 hrs | 0 days | Mon 6/10/24 | Mon 6/10/24 | 152715001503 | 1489 |  | Jennifer Grant,Jennifer Reeves
7045 | 1489 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP I-WP103 - Accounting Entry Inventory - Department QC | 1 hr | 1 day | Tue 6/11/24 | Tue 6/11/24 | 1488 | 1490 |  | Gabriela Gibson
7046 | 1490 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP I-WP103 - Accounting Entry Inventory - Collaborative Review & Update | 10 hrs | 10 days | Wed 6/12/24 | Tue 6/25/24 | 1489 | 1491 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7047 | 1491 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP I-WP103 - Accounting Entry Inventory - Style Guide Review | 1 hr | 1 day | Wed 6/26/24 | Wed 6/26/24 | 1490 | 1492 |  | Tatiana Eubanks
7048 | 1492 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP I-WP103 - Accounting Entry Inventory - Final Review & Update | 2 hrs | 5 days | Thu 6/27/24 | Wed 7/3/24 | 14911524 | 1493 |  | Angie Robertson,Jimmy Cox
7049 | 1493 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | WP I-WP103 - Accounting Entry Inventory - Approve | 0 hrs | 0 days | Wed 7/3/24 | Wed 7/3/24 | 1492 |  |  | Jimmy Cox
7050 | 1494 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | Accounting Entry Inventory | 237 hrs | 216 days | Wed 8/9/23 | Mon 6/17/24
7051 | 1495 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 1 | 48 hrs | 37 days | Wed 8/9/23 | Fri 9/29/23
7052 | 1496 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Accounting Entry Inventory Format | 10 hrs | 5 days | Wed 8/9/23 | Tue 8/15/23 | 1487FS+37 days | 1497 |  | Jennifer Reeves,Daylin Reyes
7053 | 1497 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory Format | 10 hrs | 6 days | Wed 8/16/23 | Wed 8/23/23 | 1496 | 1498 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7054 | 1498 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory Format | 10 hrs | 5 days | Thu 8/24/23 | Wed 8/30/23 | 1497 | 1499 |  | Jimmy Cox
7055 | 1499 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 16 days | Thu 8/31/23 | Fri 9/22/23 | 1498,42 | 1500 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7056 | 1500 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Mon 9/25/23 | Fri 9/29/23 | 1499 | 1488 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7057 | 1501 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 2 | 18 hrs | 20 days | Tue 10/24/23 | Tue 11/21/23
7058 | 1502 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | Tue 10/24/23 | Tue 11/14/23 | 61 | 1503 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7059 | 1503 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Wed 11/15/23 | Tue 11/21/23 | 1502 | 1488 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7060 | 1504 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 3 | 28 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
7061 | 1505 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 141SS | 15061512 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7062 | 1506 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1505 | 1507 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7063 | 1507 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Functional Teams | 10 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1506 | 1509 |  | Brendan Jones,Janice Jackson,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7064 | 1508 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Update & Publish Accounting Entry Inventory | 54 hrs | 25 days | Fri 2/2/24 | Thu 3/7/24
7065 | 1509 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1507 | 1510 |  | Jennifer Reeves,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson
7066 | 1510 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory | 2 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1509 | 1511 |  | Jimmy Cox
7067 | 1511 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Coordinate Knowledge Base Update | 10 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1510 | 1524 |  | Jennifer Reeves,Daylin Reyes
7068 | 1512 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1505 | 1513 |  | Jennifer Grant,Jennifer Reeves
7069 | 1513 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review for Communication for Accounting Entry Inventory | 10 hrs | 9 days | Fri 2/9/24 | Wed 2/21/24 | 1512 | 1514 |  | Dusti Kincl,Angie Robertson
7070 | 1514 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Thu 2/22/24 | Wed 2/28/24 | 1513 | 1515 |  | Jimmy Cox
7071 | 1515 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Publish - Accounting Entry Inventory | 1 hr | 2 days | Thu 2/29/24 | Fri 3/1/24 | 1514 | 1516 |  | Pradeep Koul,Richard Saltford,Daylin Reyes,Dusti Kincl
7072 | 1516 | Future Task |  | RW-Communication | I-WP103 | Jennifer Reeves | Create | I-WP103 Share - Communication for Accounting Entry Inventory | 1 hr | 2 days | Mon 3/4/24 | Tue 3/5/24 | 1515 | 1518 |  | Dusti Kincl
7073 | 1517 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 4 | 28 hrs | 25 days | Mon 4/22/24 | Fri 5/24/24
7074 | 1518 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | Mon 4/22/24 | Fri 5/10/24 | 160SS,1516 | 15191525 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7075 | 1519 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1518 | 1520 |  | Matthew Breeding,Jennifer Reeves
7076 | 1520 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Functional Teams | 10 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1519 | 1522 |  | Brendan Jones,Janice Jackson,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7077 | 1521 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Update & Publish Accounting Entry Inventory | 61 hrs | 25 days | Mon 5/13/24 | Mon 6/17/24
7078 | 1522 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory | 10 hrs | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1520 | 1523 |  | Jennifer Reeves,Matthew Breeding,Deana Metcalf
7079 | 1523 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory | 10 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1522 | 1524 |  | Jimmy Cox,Angie Robertson
7080 | 1524 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Coordinate Knowledge Base Update | 10 hrs | 5 days | Tue 6/11/24 | Mon 6/17/24 | 15231511 | 1492 |  | Jennifer Reeves,Daylin Reyes
7081 | 1525 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1518 | 1526 |  | Jennifer Grant,Jennifer Reeves
7082 | 1526 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Communication for Accounting Entry Inventory | 10 hrs | 10 days | Mon 5/20/24 | Mon 6/3/24 | 1525 | 1527 |  | Dusti Kincl,Angie Robertson
7083 | 1527 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1526 | 14881528 |  | Jennifer Grant,Jennifer Reeves
7084 | 1528 | Future Task |  | RW-Communication | I-WP103 | Jennifer Reeves | Create | I-WP103 Share Communication for Accounting Entry Inventory | 1 hr | 2 days | Tue 6/11/24 | Wed 6/12/24 | 1527 |  |  | Dusti Kincl
7085 | 1529 | On Schedule |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 - Error Matrix | 113 hrs | 287 days | Thu 5/18/23 | Mon 7/8/24
7086 | 1530 | Complete |  |  | I-WP104 | Jennifer Reeves | Create | WPED I-WP104 - Error Matrix - Create | 9 hrs | 10 days | Thu 5/18/23 | Thu 6/1/23 | 1 | 1531 |  | Jennifer Grant,Jennifer Reeves
7087 | 1531 | Complete |  |  | I-WP104 | Jennifer Reeves | Submit | WPED I-WP104 - Error Matrix - Submit | 0 hrs | 0 days | Thu 6/1/23 | Thu 6/1/23 | 1530 | 1532 |  | Jennifer Grant,Jennifer Reeves
7088 | 1532 | On Schedule |  |  | I-WP104 | Jennifer Reeves | Review | WPED I-WP104 - Error Matrix - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/2/23 | Thu 6/15/23 | 1531 | 15331541 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7089 | 1533 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | WPED I-WP104 - Error Matrix - Approve | 0 hrs | 0 days | Thu 6/15/23 | Thu 6/15/23 | 1532 | 1541 |  | Jimmy Cox
7090 | 1534 | Future Task |  |  | I-WP104 | Jennifer Reeves | Submit | WP I-WP104 - Error Matrix - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 15721573 | 1535 |  | Jennifer Grant,Jennifer Reeves
7091 | 1535 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP I-WP104 - Error Matrix - Department QC | 1 hr | 1 day | Thu 6/13/24 | Thu 6/13/24 | 1534 | 1536 |  | Gabriela Gibson
7092 | 1536 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP I-WP104 - Error Matrix - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1535 | 1537 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7093 | 1537 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP I-WP104 - Error Matrix - Style Guide Review | 1 hr | 1 day | Fri 6/28/24 | Fri 6/28/24 | 1536 | 1538 |  | Tatiana Eubanks
7094 | 1538 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP I-WP104 - Error Matrix - Final Review & Update | 2 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 15371569 | 1539 |  | Angie Robertson,Jimmy Cox
7095 | 1539 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | WP I-WP104 - Error Matrix - Approve | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1538 |  |  | Jimmy Cox
7096 | 1540 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 1 | 15 hrs | 62 days | Fri 6/16/23 | Wed 9/13/23
7097 | 1541 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Error Matrix Format | 2 hrs | 5 days | Fri 6/16/23 | Thu 6/22/23 | 15321533 | 1542 |  | Jennifer Reeves,Daylin Reyes
7098 | 1542 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 5 hrs | 5 days | Fri 6/23/23 | Thu 6/29/23 | 1541 | 1543 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7099 | 1543 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix Format | 1 hr | 5 days | Fri 6/30/23 | Fri 7/7/23 | 1542 | 1544 |  | Jimmy Cox
7100 | 1544 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Wed 8/2/23 | Tue 8/22/23 | 1543,42 | 1545 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7101 | 1545 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 15 days | Wed 8/23/23 | Wed 9/13/23 | 1544 | 1547 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7102 | 1546 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 2 | 7 hrs | 20 days | Tue 10/24/23 | Tue 11/21/23
7103 | 1547 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Tue 10/24/23 | Tue 11/14/23 | 611545 | 1548 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7104 | 1548 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | Wed 11/15/23 | Tue 11/21/23 | 1547 | 1550 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7105 | 1549 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 3 | 13 hrs | 25 days | Mon 1/29/24 | Fri 3/1/24
7106 | 1550 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Mon 1/29/24 | Fri 2/16/24 | 1411548 | 15511557 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7107 | 1551 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | Mon 2/19/24 | Fri 2/23/24 | 1550 | 1552 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7108 | 1552 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Functional Teams | 6 hrs | 5 days | Mon 2/26/24 | Fri 3/1/24 | 1551 | 1554 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7109 | 1553 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Update & Publish Error Matrix | 18 hrs | 25 days | Mon 2/19/24 | Fri 3/22/24
7110 | 1554 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 5 hrs | 5 days | Mon 3/4/24 | Fri 3/8/24 | 1552 | 1555 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7111 | 1555 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix | 1 hr | 5 days | Mon 3/11/24 | Fri 3/15/24 | 1554 | 1556 |  | Jimmy Cox
7112 | 1556 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Coordinate Knowledge Base Update | 2 hrs | 5 days | Mon 3/18/24 | Fri 3/22/24 | 1555 |  |  | Jennifer Reeves,Daylin Reyes
7113 | 1557 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Communication for Error Matrix | 2 hrs | 5 days | Mon 2/19/24 | Fri 2/23/24 | 1550 | 1558 |  | Jennifer Grant,Jennifer Reeves
7114 | 1558 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review for Communication for Error Matrix | 2 hrs | 9 days | Mon 2/26/24 | Thu 3/7/24 | 1557 | 1559 |  | Dusti Kincl,Angie Robertson
7115 | 1559 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Communication for Error Matrix | 1 hr | 5 days | Fri 3/8/24 | Thu 3/14/24 | 1558 | 1560 |  | Jimmy Cox
7116 | 1560 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Publish - Error Matrix | 4 hrs | 2 days | Fri 3/15/24 | Mon 3/18/24 | 1559 | 1561 |  | Pradeep Koul,Richard Saltford,Daylin Reyes,Dusti Kincl
7117 | 1561 | Future Task |  | RW-Communication | I-WP104 | Jennifer Reeves | Create | I-WP104 Share - Communication for Error Matrix | 1 hr | 2 days | Tue 3/19/24 | Wed 3/20/24 | 1560 | 1563 |  | Dusti Kincl
7118 | 1562 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 4 | 13 hrs | 25 days | Mon 4/22/24 | Fri 5/24/24
7119 | 1563 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Mon 4/22/24 | Fri 5/10/24 | 160SS,1561 | 15641570 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7120 | 1564 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1563 | 1565 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7121 | 1565 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Functional Teams | 6 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1564 | 1567 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7122 | 1566 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Update & Publish Error Matrix | 14 hrs | 25 days | Mon 5/13/24 | Mon 6/17/24
7123 | 1567 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 3 hrs | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1565 | 1568 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves
7124 | 1568 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix | 2 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1567 | 1569 |  | Angie Robertson,Jimmy Cox
7125 | 1569 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Coordinate Knowledge Base Update | 2 hrs | 5 days | Tue 6/11/24 | Mon 6/17/24 | 1568 | 1538 |  | Jennifer Reeves,Daylin Reyes
7126 | 1570 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Task Instructions & Communication for Error Matrix | 2 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1563 | 1571 |  | Jennifer Reeves,Nikki Klein
7127 | 1571 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Communication for Error Matrix | 2 hrs | 10 days | Mon 5/20/24 | Mon 6/3/24 | 1570 | 1572 |  | Dusti Kincl,Angie Robertson
7128 | 1572 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Task Instructions & Communication for Error Matrix | 2 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1571 | 15341573 |  | Jennifer Grant,Jennifer Reeves
7129 | 1573 | Future Task |  | RW-Communication | I-WP104 | Jennifer Reeves | Create | I-WP104 Share Communication for Error Matrix | 1 hr | 2 days | Tue 6/11/24 | Wed 6/12/24 | 1572 | 1534 |  | Dusti Kincl
6862 | 1574 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 - Reports Catalogs | 239 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6863 | 1575 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 - Report Catalog | 16 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6864 | 1576 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | WPED I-WP105 - Report Catalog - Create | 2 hrs | 10 days | Fri 6/9/23 | Thu 6/22/23 | 1 | 1577 |  | Jennifer Grant,Jennifer Reeves
6865 | 1577 | Future Task |  |  | I-WP105 | Jennifer Reeves | Submit | WPED I-WP105 - Report Catalog - Submit | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 1576 | 1578 |  | Jennifer Grant,Jennifer Reeves
6866 | 1578 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WPED I-WP105 - Report Catalog - Collaborative Review & Update | 8 hrs | 10 days | Fri 6/23/23 | Fri 7/7/23 | 1577 | 1579 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Reeves,Jennifer Grant
6867 | 1579 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | WPED I-WP105 - Report Catalog - Approve | 0 hrs | 0 days | Fri 7/7/23 | Fri 7/7/23 | 1578 | 1587 |  | Jimmy Cox
6868 | 1580 | Future Task |  |  | I-WP105 | Jennifer Reeves | Submit | WP I-WP105 - Report Catalog - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 16031616 | 1581 |  | Jennifer Grant,Jennifer Reeves
6869 | 1581 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP I-WP105 - Report Catalog - Department QC | 1 hr | 1 day | Thu 6/13/24 | Thu 6/13/24 | 1580 | 1582 |  | Jenifer Hartsfield
6870 | 1582 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP I-WP105 - Report Catalog - Collaborative Review & Update | 2 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1581 | 1583 |  | Jennifer Grant,Jennifer Reeves
6871 | 1583 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP I-WP105 - Report Catalog - Style Guide Review | 1 hr | 1 day | Fri 6/28/24 | Fri 6/28/24 | 1582 | 1584 |  | Tatiana Eubanks
6872 | 1584 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP I-WP105 - Report Catalog - Final Review & Update | 2 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 1583 | 1585 |  | Angie Robertson,Jimmy Cox
6873 | 1585 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | WP I-WP105 - Report Catalog - Approve | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1584 |  |  | Jimmy Cox
6874 | 1586 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 1 - Reports | 35 hrs | 20 days | Tue 7/18/23 | Mon 8/14/23
6875 | 1587 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | Tue 7/18/23 | Mon 8/7/23 | 42SS,1579 | 1588 |  | Pradeep Koul,Tanya McCarty,Stanton Beazley,Jennifer Reeves,Elizabeth Sargent
6876 | 1588 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | Tue 8/8/23 | Mon 8/14/23 | 1587 | 1590 |  | Jennifer Grant,Jennifer Reeves
6877 | 1589 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 2 - Reports | 35 hrs | 20 days | Mon 10/9/23 | Fri 11/3/23
6878 | 1590 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | Mon 10/9/23 | Fri 10/27/23 | 61SS,1588 | 1591 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6879 | 1591 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | Mon 10/30/23 | Fri 11/3/23 | 1590 | 1593 |  | Jennifer Grant,Jennifer Reeves
6880 | 1592 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 3 - Reports | 55 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
6881 | 1593 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 141SS,1591 | 1594 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6882 | 1594 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1593 | 15951601 |  | Jennifer Grant,Jennifer Reeves
6883 | 1595 | Future Task |  |  |  | Jennifer Reeves | Review | I-WP105 Collaborative Review - Functional Teams | 20 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1594 | 1597 |  | Jennifer Grant,Jennifer Reeves,Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
6884 | 1596 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Update & Publish Report Catalog | 41 hrs | 22 days | Fri 2/9/24 | Mon 3/11/24
6885 | 1597 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Report Catalog | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1595 | 1598 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6886 | 1598 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Report Catalog | 2 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1597 | 1599 |  | Jimmy Cox
6887 | 1599 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Coordinate Knowledge Base Update | 18 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1598 | 1600 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6888 | 1600 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Publish - Report Catalog | 4 hrs | 2 days | Fri 3/8/24 | Mon 3/11/24 | 1599 | 1606 |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6889 | 1601 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Create Communication for Report Catalog | 2 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1594 | 1602 |  | Jennifer Grant,Jennifer Reeves
6890 | 1602 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review for Communication | 3 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1601 | 1603 |  | Dusti Kincl,Angie Robertson,Jennifer Reeves
6891 | 1603 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Communication for Report Catalog | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1602 | 15801604 |  | Jimmy Cox
6892 | 1604 | Future Task |  | RW-Communication | I-WP105 | Jennifer Reeves | Create | I-WP105 Share Communication for Report Catalog | 1 hr | 2 days | Fri 3/1/24 | Mon 3/4/24 | 1603 | 1606 |  | Dusti Kincl
6893 | 1605 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 4 - Reports | 32 hrs | 27 days | Mon 4/22/24 | Wed 5/29/24
6894 | 1606 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 10 hrs | 16 days | Mon 4/22/24 | Mon 5/13/24 | 160SS,1604,1600 | 1607 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
6895 | 1607 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 2 hrs | 6 days | Tue 5/14/24 | Tue 5/21/24 | 1606 | 16081614 |  | Jennifer Grant,Jennifer Reeves
6896 | 1608 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Functional Teams | 20 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1607 | 1610 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6897 | 1609 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Update & Publish Report Catalog | 25 hrs | 22 days | Wed 5/22/24 | Fri 6/21/24
6898 | 1610 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Report Catalog | 10 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1608 | 1611 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6899 | 1611 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Report Catalog | 1 hr | 5 days | Thu 6/6/24 | Wed 6/12/24 | 1610 | 1612 |  | Jimmy Cox
6900 | 1612 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Coordinate Knowledge Base Update | 3 hrs | 5 days | Thu 6/13/24 | Wed 6/19/24 | 1611 | 1613 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6901 | 1613 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Publish - Report Catalog | 4 hrs | 2 days | Thu 6/20/24 | Fri 6/21/24 | 1612 |  |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6902 | 1614 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Create Communication for Report Catalog | 2 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1607 | 1615 |  | Jennifer Grant,Jennifer Reeves
6903 | 1615 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review for Communication | 3 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1614 | 1616 |  | Dusti Kincl,Angie Robertson,Jennifer Reeves
6904 | 1616 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Communication for Report Catalog | 1 hr | 5 days | Thu 6/6/24 | Wed 6/12/24 | 1615 | 15801617 |  | Jimmy Cox
6905 | 1617 | Future Task |  | RW-Communication | I-WP105 | Jennifer Reeves | Create | I-WP105 Share Communication for Report Catalog | 1 hr | 2 days | Thu 6/13/24 | Fri 6/14/24 | 1616 |  |  | Dusti Kincl
6953 | 1618 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 - Interface Catalog | 167 hrs | 265 days | Fri 6/9/23 | Wed 6/26/24
6954 | 1619 | Future Task |  |  | I-WP106 | Matt Breeding | Create | WPED I-WP106 - Interface Catalog - Create | 10 hrs | 10 days | Fri 6/9/23 | Thu 6/22/23 | 1 | 1620 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding
6955 | 1620 | Future Task |  |  | I-WP106 | Matt Breeding | Submit | WPED I-WP106 - Interface Catalog - Submit | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 1619 | 1621 |  | Matthew Breeding
6956 | 1621 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WPED I-WP106 - Interface Catalog - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/23/23 | Fri 7/7/23 | 1620 | 1622 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
6957 | 1622 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | WPED I-WP106 - Interface Catalog - Approve | 0 hrs | 0 days | Fri 7/7/23 | Fri 7/7/23 | 1621 | 1631 |  | Jimmy Cox
6958 | 1623 | Future Task |  |  | I-WP106 | Matt Breeding | Submit | WP I-WP106 - Interface Catalog - Submit | 0 hrs | 0 days | Mon 6/3/24 | Mon 6/3/24 | 1659 | 1624 |  | Matthew Breeding
6959 | 1624 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP I-WP106 - Interface Catalog - Department QC | 1 hr | 1 day | Tue 6/4/24 | Tue 6/4/24 | 1623 | 1625 |  | Gabriela Gibson
6960 | 1625 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP I-WP106 - Interface Catalog - Collaborative Review & Update | 10 hrs | 10 days | Wed 6/5/24 | Tue 6/18/24 | 1624 | 1626 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
6961 | 1626 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP I-WP106 - Interface Catalog - Style Guide Review | 2 hrs | 1 day | Wed 6/19/24 | Wed 6/19/24 | 1625 | 1627 |  | Tatiana Eubanks
6962 | 1627 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP I-WP106 - Interface Catalog - Final Review & Update | 10 hrs | 5 days | Thu 6/20/24 | Wed 6/26/24 | 1626 | 1628 |  | Angie Robertson,Jimmy Cox
6963 | 1628 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | WP I-WP106 - Interface Catalog - Approve | 0 hrs | 0 days | Wed 6/26/24 | Wed 6/26/24 | 1627 |  |  | Jimmy Cox
6964 | 1629 | Future Task |  |  | I-WP106 | Matt Breeding |  | Interface Catalog | 124 hrs | 229 days | Tue 7/18/23 | Wed 6/12/24
6965 | 1630 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 1 - Interfaces | 12 hrs | 20 days | Tue 7/18/23 | Mon 8/14/23
6966 | 1631 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Tue 7/18/23 | Mon 8/7/23 | 42SS,1622 | 1632 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6967 | 1632 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Tue 8/8/23 | Mon 8/14/23 | 1631 | 1634 |  | Matthew Breeding
6968 | 1633 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 2 - Interfaces | 12 hrs | 20 days | Wed 10/11/23 | Tue 11/7/23
6969 | 1634 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Wed 10/11/23 | Tue 10/31/23 | 61SS+2 days,1632 | 1635 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6970 | 1635 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Wed 11/1/23 | Tue 11/7/23 | 1634 | 1637 |  | Matthew Breeding
6971 | 1636 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 3 - Interfaces | 22 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
6972 | 1637 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 141SS,1635 | 1638 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6973 | 1638 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1637 | 16391645 |  | Matthew Breeding
6974 | 1639 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Functional Teams | 10 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1638 | 1641 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
6975 | 1640 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Update & Publish Interface Catalog | 45 hrs | 24 days | Fri 2/9/24 | Wed 3/13/24
6976 | 1641 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Interface Catalog | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1639 | 1642 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6977 | 1642 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Interface Catalog | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1641 | 1643 |  | Jimmy Cox
6978 | 1643 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Coordinate Knowledge Base Update | 10 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1642 | 1644 |  | Matthew Breeding,Daylin Reyes
6979 | 1644 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Publish - Interface Catalog | 10 hrs | 2 days | Fri 3/8/24 | Mon 3/11/24 | 1643 | 1648 |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
6980 | 1645 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Create Communication for Interface Catalog | 2 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1638 | 1646 |  | Matthew Breeding,Dusti Kincl
6981 | 1646 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review for Communication for Interface Catalog | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1645 | 1647 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6982 | 1647 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Communication for Interface Catalog | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1646 | 1648 |  | Jimmy Cox
6983 | 1648 | Future Task |  | RW-Communication | I-WP106 | Matt Breeding | Create | I-WP106 Share Communication for Interface Catalog | 1 hr | 2 days | Tue 3/12/24 | Wed 3/13/24 | 16441647 | 1650 |  | Dusti Kincl
6984 | 1649 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 4 - Interfaces | 12 hrs | 20 days | Mon 4/22/24 | Fri 5/17/24
6985 | 1650 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Mon 4/22/24 | Fri 5/10/24 | 160SS,1648 | 16511657 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6986 | 1651 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1650 | 1653 |  | Matthew Breeding
6987 | 1652 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Update & Publish Interface Catalog | 21 hrs | 22 days | Mon 5/13/24 | Wed 6/12/24
6988 | 1653 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Interface Catalog | 10 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1651 | 1654 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6989 | 1654 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Interface Catalog | 1 hr | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1653 | 1655 |  | Jimmy Cox
6990 | 1655 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Coordinate Knowledge Base Update | 2 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1654 | 1656 |  | Matthew Breeding,Daylin Reyes
6991 | 1656 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Publish Interface Catalog | 1 hr | 2 days | Tue 6/11/24 | Wed 6/12/24 | 1655 |  |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
6992 | 1657 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Create Communication for Interface Catalog | 2 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1650 | 1658 |  | Matthew Breeding,Dusti Kincl
6993 | 1658 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review for Communication for Interface Catalog | 3 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1657 | 1659 |  | Dusti Kincl,Angie Robertson,Matthew Breeding
6994 | 1659 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Communication for Interface Catalog | 1 hr | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1658 | 16231660 |  | Jimmy Cox
6995 | 1660 | Future Task |  | RW-Communication | I-WP106 | Matt Breeding | Create | I-WP106 Share Communication for Interface Catalog | 1 hr | 2 days | Tue 6/4/24 | Wed 6/5/24 | 1659 | 799 |  | Dusti Kincl
6996 | 1661 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 - Conversions Inventory | 167 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6997 | 1662 | Future Task |  |  | I-WP107 | Matt Breeding | Create | WPED I-WP107 - Conversions Inventory - Create | 10 hrs | 10 days | Fri 6/9/23 | Thu 6/22/23 | 1 | 1663 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding
6998 | 1663 | Future Task |  |  | I-WP107 | Matt Breeding | Submit | WPED I-WP107 - Conversions Inventory - Submit | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 1662 | 1664 |  | Matthew Breeding
6999 | 1664 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WPED I-WP107 - Conversions Inventory - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/23/23 | Fri 7/7/23 | 1663 | 1665 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7000 | 1665 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | WPED I-WP107 - Conversions Inventory - Approve | 0 hrs | 0 days | Fri 7/7/23 | Fri 7/7/23 | 1664 | 1674 |  | Jimmy Cox
7001 | 1666 | Future Task |  |  | I-WP107 | Matt Breeding | Submit | WP I-WP107 - Conversions Inventory - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 1702 | 1667 |  | Matthew Breeding
7002 | 1667 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP I-WP107 - Conversions Inventory - Department QC | 1 hr | 1 day | Thu 6/13/24 | Thu 6/13/24 | 1666 | 1668 |  | Gabriela Gibson
7003 | 1668 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP I-WP107 - Conversions Inventory - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1667 | 1669 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7004 | 1669 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP I-WP107 - Conversions Inventory - Style Guide Review | 2 hrs | 1 day | Fri 6/28/24 | Fri 6/28/24 | 1668 | 1670 |  | Tatiana Eubanks
7005 | 1670 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP I-WP107 - Conversions Inventory - Final Review & Update | 10 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 1669 | 1671 |  | Angie Robertson,Jimmy Cox
7006 | 1671 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | WP I-WP107 - Conversions Inventory - Approve | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1670 |  |  | Jimmy Cox
7007 | 1672 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Conversions Inventory | 124 hrs | 234 days | Tue 7/18/23 | Wed 6/19/24
7008 | 1673 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment I - Conversions | 11 hrs | 20 days | Tue 7/18/23 | Mon 8/14/23
7009 | 1674 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | Tue 7/18/23 | Mon 8/7/23 | 42SS,1665 | 1675 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7010 | 1675 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 1 hr | 5 days | Tue 8/8/23 | Mon 8/14/23 | 1674 | 1677 |  | Matthew Breeding
7011 | 1676 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment II - Conversions | 15 hrs | 20 days | Mon 10/16/23 | Mon 11/13/23
7012 | 1677 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | Mon 10/16/23 | Fri 11/3/23 | 61SS+5 days,1675 | 1678 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7013 | 1678 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 5 hrs | 5 days | Mon 11/6/23 | Mon 11/13/23 | 1677 | 1680 |  | Matthew Breeding
7014 | 1679 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment III - Conversions | 25 hrs | 25 days | Fri 1/19/24 | Thu 2/22/24
7015 | 1680 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | Fri 1/19/24 | Thu 2/8/24 | 141SS+5 days,1678 | 1681 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7016 | 1681 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 5 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1680 | 16821688 |  | Matthew Breeding
7017 | 1682 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Functional Teams | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1681 | 1684 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
7018 | 1683 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Update & Publish Conversion Catalog | 26 hrs | 27 days | Fri 2/16/24 | Mon 3/25/24
7019 | 1684 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Conversion Catalog | 10 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1682 | 1685 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7020 | 1685 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Conversion Catalog | 1 hr | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1684 | 1686 |  | Jimmy Cox
7021 | 1686 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Coordinate Knowledge Base Update | 2 hrs | 5 days | Fri 3/8/24 | Thu 3/14/24 | 1685 | 1687 |  | Matthew Breeding,Daylin Reyes
7022 | 1687 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Publish - Conversion Catalog | 4 hrs | 5 days | Fri 3/15/24 | Thu 3/21/24 | 1686 | 1691 |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
7023 | 1688 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create Communication for Conversion Catalog | 2 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1681 | 1689 |  | Matthew Breeding,Dusti Kincl
7024 | 1689 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review for Communication for Conversion Catalog | 5 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1688 | 1690 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7025 | 1690 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Communication | 1 hr | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1689 | 1691 |  | Jimmy Cox
7026 | 1691 | Future Task |  | RW-Communication | I-WP107 | Matt Breeding | Create | I-WP107 Share Communication | 1 hr | 2 days | Fri 3/22/24 | Mon 3/25/24 | 16871690 | 1693 |  | Dusti Kincl
7027 | 1692 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment IV - Conversions | 15 hrs | 25 days | Mon 4/29/24 | Mon 6/3/24
7028 | 1693 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create & Maintain - Conversion Catalog | 10 hrs | 15 days | Mon 4/29/24 | Fri 5/17/24 | 160SS+5 days,1691 | 1694 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7029 | 1694 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 1 hr | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1693 | 16951700 |  | Matthew Breeding
7030 | 1695 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Functional Teams | 4 hrs | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1694 | 1697 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
7031 | 1696 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Update & Publish Conversions Catalog | 32 hrs | 17 days | Tue 5/28/24 | Wed 6/19/24
7032 | 1697 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Conversion Catalog | 10 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1695 | 1698 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7033 | 1698 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Conversion Catalog | 1 hr | 5 days | Tue 6/11/24 | Mon 6/17/24 | 1697 | 1699 |  | Jimmy Cox
7034 | 1699 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Publish - Conversion Catalog | 4 hrs | 2 days | Tue 6/18/24 | Wed 6/19/24 | 1698 | 630 |  | Daylin Reyes,Richard Saltford,Pradeep Koul,Dusti Kincl
7035 | 1700 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create Communication for Conversions Catalog | 3 hrs | 2 days | Tue 5/28/24 | Wed 5/29/24 | 1694 | 1701 |  | Dusti Kincl,Pradeep Koul,Richard Barnes
7036 | 1701 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review for Communication for Conversions Catalog | 10 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1700 | 1702 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Nikki Klein,Daylin Reyes,Jennifer Grant
7037 | 1702 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Communication | 3 hrs | 5 days | Thu 6/6/24 | Wed 6/12/24 | 1701 | 16661703 |  | Dusti Kincl,Angie Robertson,Matthew Breeding
7038 | 1703 | Future Task |  | RW-Communication | I-WP107 | Matt Breeding | Create | I-WP107 Share Communication for Conversions Catalog | 1 hr | 5 days | Thu 6/13/24 | Wed 6/19/24 | 1702 | 630 |  | Jimmy Cox
2973 | 1704 | On Schedule |  |  | I-WP108 | Kimberly Kemp |  | I-WP108 - Training Curriculum | 53 hrs | 360 days | Thu 6/1/23 | Thu 10/31/24
2974 | 1705 | On Schedule |  |  | I-WP108 | Carolyn Hicks | Create | WPED I-WP108 - Training Curriculum - Create | 10 hrs | 10 days | Thu 6/1/23 | Wed 6/14/23 | 1 | 1706 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
2975 | 1706 | Future Task |  |  | I-WP108 | Carolyn Hicks | Submit | WPED I-WP108 - Training Curriculum - Submit | 0 hrs | 0 days | Wed 6/14/23 | Wed 6/14/23 | 1705 | 1707 |  | Carolyn Hicks
2976 | 1707 | Future Task |  |  | I-WP108 | Carolyn Hicks | Review | WPED I-WP108 - Training Curriculum - Collaborative Review & Update | 10 hrs | 10 days | Thu 6/15/23 | Wed 6/28/23 | 1706 | 1708 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
2977 | 1708 | Future Task |  |  | I-WP108 | Carolyn Hicks | Approve | WPED I-WP108 - Training Curriculum - Approve | 0 hrs | 0 days | Wed 6/28/23 | Wed 6/28/23 | 1707 | 1709 |  | Angie Robertson,Jimmy Cox
5689 | 1709 | Future Task |  |  | I-WP108 | Kimberly Kemp | Create | I-WP108 Training Curriculum <Activities per WPED> | 10 hrs | 287 days | Mon 8/21/23 | Tue 10/8/24 | 1708,48 | 1710,1721SS+30 days |  | Kimberly Kemp
2978 | 1710 | Future Task |  |  | I-WP108 | Kimberly Kemp | Submit | WP I-WP108 - Training Curriculum - Submit | 0 hrs | 0 days | Tue 10/8/24 | Tue 10/8/24 | 1709 | 1711 |  | Kimberly Kemp
2979 | 1711 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | WP I-WP108 - Training Curriculum - Department QC | 1 hr | 1 day | Wed 10/9/24 | Wed 10/9/24 | 1710 | 1712 |  | Tommy Werner
2980 | 1712 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | WP I-WP108 - Training Curriculum - Collaborative Review & Update | 10 hrs | 10 days | Thu 10/10/24 | Wed 10/23/24 | 1711 | 1713 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
2981 | 1713 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | WP I-WP108 - Training Curriculum - Style Guide Review | 2 hrs | 1 day | Thu 10/24/24 | Thu 10/24/24 | 1712 | 1714 |  | Dusti Kincl
2982 | 1714 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | WP I-WP108 - Training Curriculum - Final Review & Update | 10 hrs | 5 days | Fri 10/25/24 | Thu 10/31/24 | 1713 | 1715 |  | Angie Robertson,Jimmy Cox
2983 | 1715 | Future Task |  | RW | I-WP108 | Kimberly Kemp | Approve | WP I-WP108 - Training Curriculum - Approve | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 1714 | 1721 |  | Jimmy Cox
2984 | 1716 | Future Task |  |  | I-WP109 | Kimberly Kemp |  | I-WP109 - Training Designs | 96 hrs | 567 days | Mon 7/3/23 | Tue 9/30/25
2985 | 1717 | Future Task |  |  | I-WP109 | Carolyn Hicks | Create | WPED I-WP109 - Training Designs - Create | 10 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 1 | 1718 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila | move WPED start to 4/1/2024 | (DONE) Carolyn
2986 | 1718 | Future Task |  |  | I-WP109 | Carolyn Hicks | Submit | WPED I-WP109 - Training Designs - Submit | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 1717 | 1719 |  | Carolyn Hicks
2987 | 1719 | Future Task |  |  | I-WP109 | Carolyn Hicks | Review | WPED I-WP109 - Training Designs - Collaborative Review & Update | 10 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 1718 | 1720 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
2988 | 1720 | Future Task |  |  | I-WP109 | Carolyn Hicks | Approve | WPED I-WP109 - Training Designs - Approve | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 1719 | 1721 |  | Angie Robertson,Jimmy Cox
5690 | 1721 | Future Task |  |  | I-WP109 | Kimberly Kemp | Create | I-WP109 Training Designs <Activities per WPED> | 40 hrs | 212 days | Fri 11/1/24 | Fri 9/5/25 | 1720,1709SS+30 days,1715 | 1722,1733SS |  | Kimberly Kemp | Move start date to 7/1/24 | Carolyn (note from Francisca: IWP108 Approve is a predecessor ending 10/31/2024. Also are we keeping the same duration for this task?) Francisa - yes duration will be the same with new start of 7/1/24. We an begin before 108 is approved.
2989 | 1722 | Future Task |  |  | I-WP109 | Kimberly Kemp | Submit | WP I-WP109 - Training Designs - Submit | 0 hrs | 0 days | Fri 9/5/25 | Fri 9/5/25 | 1721 | 1723 |  | Kimberly Kemp
2990 | 1723 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | WP I-WP109 - Training Designs - Department QC | 8 hrs | 1 day | Mon 9/8/25 | Mon 9/8/25 | 1722 | 1724 |  | Gabriela Gibson
2991 | 1724 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | WP I-WP109 - Training Designs - Collaborative Review & Update | 10 hrs | 10 days | Tue 9/9/25 | Mon 9/22/25 | 1723 | 1725 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
2992 | 1725 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | WP I-WP109 - Training Designs - Style Guide Review | 8 hrs | 1 day | Tue 9/23/25 | Tue 9/23/25 | 1724 | 1726 |  | Tatiana Eubanks
2993 | 1726 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | WP I-WP109 - Training Designs - Final Review & Update | 10 hrs | 5 days | Wed 9/24/25 | Tue 9/30/25 | 1725 | 1727 |  | Angie Robertson,Jimmy Cox
2994 | 1727 | Future Task |  |  | I-WP109 | Kimberly Kemp | Approve | WP I-WP109 - Training Designs - Approve | 0 hrs | 0 days | Tue 9/30/25 | Tue 9/30/25 | 1726 |  |  | Jimmy Cox
2995 | 1728 | Future Task | Yes |  | I-WP110 | Kimberly Kemp |  | I-WP110 - Training Build | 156 hrs | 337 days | Fri 3/1/24 | Mon 6/30/25
2996 | 1729 | Future Task |  |  | I-WP110 | Carolyn Hicks | Create | WPED I-WP110 - Training Build - Create | 10 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 1 | 1730 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell | move WPED to 4/1/2024 | (DONE) Carolyn
2997 | 1730 | Future Task |  |  | I-WP110 | Carolyn Hicks | Submit | WPED I-WP110 - Training Build - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 1729 | 1731 |  | Carolyn Hicks
2998 | 1731 | Future Task |  |  | I-WP110 | Carolyn Hicks | Review | WPED I-WP110 - Training Build - Collaborative Review & Update | 10 hrs | 10 days | Fri 3/15/24 | Thu 3/28/24 | 1730 | 1732 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
2999 | 1732 | Future Task |  |  | I-WP110 | Carolyn Hicks | Approve | WPED I-WP110 - Training Build - Approve | 0 hrs | 0 days | Thu 3/28/24 | Thu 3/28/24 | 1731 | 1733 |  | Angie Robertson,Jimmy Cox
5691 | 1733 | Future Task |  |  | I-WP110 | Kimberly Kemp | Create | I-WP110 Training Build <Activities per WPED> | 100 hrs | 148 days | Fri 11/1/24 | Thu 6/5/25 | 1732,1721SS | 1734 |  | Kimberly Kemp
3000 | 1734 | Future Task |  |  | I-WP110 | Kimberly Kemp | Submit | WP I-WP110 - Training Build - Submit | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 1733 | 1735 |  | Kimberly Kemp
3001 | 1735 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | WP I-WP110 - Training Build - Department QC | 8 hrs | 1 day | Fri 6/6/25 | Fri 6/6/25 | 1734 | 1736 |  | Gabriela Gibson
3002 | 1736 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | WP I-WP110 - Training Build - Collaborative Review & Update | 10 hrs | 10 days | Mon 6/9/25 | Fri 6/20/25 | 1735 | 1737 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3003 | 1737 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | WP I-WP110 - Training Build - Style Guide Review | 8 hrs | 1 day | Mon 6/23/25 | Mon 6/23/25 | 1736 | 1738 |  | Tatiana Eubanks
3004 | 1738 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | WP I-WP110 - Training Build - Final Review & Update | 10 hrs | 5 days | Tue 6/24/25 | Mon 6/30/25 | 1737 | 1739 |  | Angie Robertson,Jimmy Cox
3005 | 1739 | Future Task |  |  | I-WP110 | Kimberly Kemp | Approve | WP I-WP110 - Training Build - Approve | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 1738 | 1779 |  | Jimmy Cox
3006 | 1740 | Future Task |  |  | I-WP111 | Kimberly Kemp |  | I-WP111 - UAT Training Materials | 129 hrs | 154 days | Thu 8/1/24 | Thu 3/13/25
3007 | 1741 | Future Task |  |  | I-WP111 | Carolyn Hicks | Create | WPED I-WP111 - UAT Training Materials - Create | 10 hrs | 10 days | Thu 8/1/24 | Wed 8/14/24 | 1 | 1742 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila | move start date to 6/1/2024 | (DONE) Carolyn (note from Francisca: moved to Monday 6/3/2024)
3008 | 1742 | Future Task |  |  | I-WP111 | Carolyn Hicks | Submit | WPEP I-WP111 - UAT Training Materials - Submit | 0 hrs | 0 days | Wed 8/14/24 | Wed 8/14/24 | 1741 | 1743 |  | Carolyn Hicks
3009 | 1743 | Future Task |  |  | I-WP111 | Carolyn Hicks | Review | WPED I-WP111 - UAT Training Materials - Collaborative Review & Update | 10 hrs | 10 days | Thu 8/15/24 | Wed 8/28/24 | 1742 | 1744 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
3010 | 1744 | Future Task |  |  | I-WP111 | Carolyn Hicks | Approve | WPED I-WP111 - UAT Training Materials - Approve | 0 hrs | 0 days | Wed 8/28/24 | Wed 8/28/24 | 1743 | 1745 |  | Angie Robertson,Jimmy Cox
5692 | 1745 | Future Task |  |  | I-WP111 | Kimberly Kemp | Create | I-WP111 UAT Training Materials <Activities per WPED> | 80 hrs | 117 days | Thu 8/29/24 | Tue 2/18/25 | 1744 | 1746 |  | Kimberly Kemp | Start date on 8/1/24 | (DONE) Carolyn
3011 | 1746 | Future Task |  |  | I-WP111 | Kimberly Kemp | Submit | WP I-WP111 - UAT Training Materials - Submit | 0 hrs | 0 days | Tue 2/18/25 | Tue 2/18/25 | 1745 | 1747 |  | Kimberly Kemp
3012 | 1747 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | WP I-WP111 - UAT Training Materials - Department QC | 1 hr | 1 day | Wed 2/19/25 | Wed 2/19/25 | 1746 | 1748 |  | Tommy Werner
3013 | 1748 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | WP I-WP111 - UAT Training Materials - Collaborative Review & Update | 10 hrs | 10 days | Thu 2/20/25 | Wed 3/5/25 | 1747 | 1749 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3014 | 1749 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | WP I-WP111 - UAT Training Materials - Style Guide Review | 8 hrs | 1 day | Thu 3/6/25 | Thu 3/6/25 | 1748 | 1750 |  | Tatiana Eubanks
3015 | 1750 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | WP I-WP111 - UAT Training Materials - Final Review & Update | 10 hrs | 5 days | Fri 3/7/25 | Thu 3/13/25 | 1749 | 1751 |  | Angie Robertson,Jimmy Cox
3016 | 1751 | Future Task |  |  | I-WP111 | Kimberly Kemp | Approve | WP I-WP111 - UAT Training Materials - Approve | 0 hrs | 0 days | Thu 3/13/25 | Thu 3/13/25 | 1750 | 1752 |  | Jimmy Cox
3017 | 1752 | Future Task |  |  | I-WP111 | Kimberly Kemp | Milestone | WP I-WP111 - UAT Training Materials - Complete | 0 hrs | 0 days | Thu 3/13/25 | Thu 3/13/25 | 1751 | 1274 |  | Kimberly Kemp
3018 | 1753 | Future Task |  | RW | I-WP112 | Kimberly Kemp |  | I-WP112 - End User Manual | 143 hrs | 210 days | Fri 1/31/25 | Wed 11/26/25
3019 | 1754 | Future Task |  |  | I-WP112 | Carolyn Hicks | Create | WPED I-WP112 - End User Manual - Create | 10 hrs | 10 days | Fri 1/31/25 | Thu 2/13/25 | 1 | 1755 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling | move start date to 8/1/2024 | (DONE) Carolyn
3020 | 1755 | Future Task |  |  | I-WP112 | Carolyn Hicks | Submit | WPED I-WP112 - End User Manual - Submit | 0 hrs | 0 days | Thu 2/13/25 | Thu 2/13/25 | 1754 | 1756 |  | Carolyn Hicks
3021 | 1756 | Future Task |  |  | I-WP112 | Carolyn Hicks | Review | WPED I-WP112 - End User Manual - Collaborative Review & Update | 10 hrs | 10 days | Fri 2/14/25 | Thu 2/27/25 | 1755 | 1757 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3022 | 1757 | Future Task |  |  | I-WP112 | Carolyn Hicks | Approve | WPED I-WP112 - End User Manual - Approve | 0 hrs | 0 days | Thu 2/27/25 | Thu 2/27/25 | 1756 | 1758 |  | Angie Robertson,Jimmy Cox
5693 | 1758 | Future Task |  |  | I-WP112 | Kimberly Kemp | Create | I-WP112 End User Manual <Activities per WPED> | 100 hrs | 173 days | Fri 2/28/25 | Fri 10/31/25 | 1757652 | 1759 |  | Kimberly Kemp | Move start date to 11/1/2024 | Carolyn (note from Francisca: "D652 - Milestone: System Test Segment 1 Execution Complete" ends 11/27/2024 and is a predecessor)
3023 | 1759 | Future Task |  |  | I-WP112 | Kimberly Kemp | Submit | WP I-WP112 - End User Manual - Submit | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 1758 | 1760 |  | Kimberly Kemp
3024 | 1760 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | WP I-WP112 - End User Manual - Department QC | 1 hr | 1 day | Mon 11/3/25 | Mon 11/3/25 | 1759 | 1761 |  | Tommy Werner
3025 | 1761 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | WP I-WP112 - End User Manual - Collaborative Review & Update | 10 hrs | 10 days | Tue 11/4/25 | Tue 11/18/25 | 1760 | 1762 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3026 | 1762 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | WP I-WP112 - End User Manual - Style Guide Review | 2 hrs | 1 day | Wed 11/19/25 | Wed 11/19/25 | 1761 | 1763 |  | Tatiana Eubanks
3027 | 1763 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | WP I-WP112 - End User Manual - Final Review & Update | 10 hrs | 5 days | Thu 11/20/25 | Wed 11/26/25 | 1762 | 1764 |  | Angie Robertson,Jimmy Cox
3028 | 1764 | Future Task |  |  | I-WP112 | Kimberly Kemp | Approve | WP I-WP112 - End User Manual - Approve | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 1763 | 1765 |  | Jimmy Cox
3029 | 1765 | Future Task |  |  | I-WP112 | Kimberly Kemp | Milestone | WP I-WP112 - End User Manual - Complete | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 1764 | 1385 |  | Kimberly Kemp
3030 | 1766 | Future Task |  |  | I-WP113 | Kimberly Kemp |  | I-WP113 - ILT Training Delivery Plan | 156 hrs | 85 days | Fri 3/1/24 | Fri 6/28/24
3031 | 1767 | Future Task |  |  | I-WP113 | Carolyn Hicks | Create | WPED I-WP113 - ILT Training Delivery Plan - Create | 10 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 18261838 | 1768 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
3032 | 1768 | Future Task |  |  | I-WP113 | Carolyn Hicks | Submit | WPED I-WP113 - ILT Training Delivery Plan - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 1767 | 1769 |  | Carolyn Hicks
3033 | 1769 | Future Task |  |  | I-WP113 | Carolyn Hicks | Review | WPED I-WP113 - ILT Training Delivery Plan - Collaborative Review & Update | 10 hrs | 10 days | Fri 3/15/24 | Thu 3/28/24 | 1768 | 1770 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
3034 | 1770 | Future Task |  |  | I-WP113 | Carolyn Hicks | Approve | WPED I-WP113- ILT Training Delivery Plan - Approve | 0 hrs | 0 days | Thu 3/28/24 | Thu 3/28/24 | 1769 | 1771 |  | Angie Robertson,Jimmy Cox
5694 | 1771 | Future Task |  |  | I-WP113 | Kimberly Kemp | Create | I-WP113 ILT Training Delivery Plan <Activities per WPED> | 100 hrs | 48 days | Fri 3/29/24 | Wed 6/5/24 | 1770 | 1772 |  | Kimberly Kemp
3035 | 1772 | Future Task |  |  | I-WP113 | Kimberly Kemp | Submit | WP I-WP113 - ILT Training Delivery Plan - Submit | 0 hrs | 0 days | Wed 6/5/24 | Wed 6/5/24 | 1771 | 1773 |  | Kimberly Kemp
3036 | 1773 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | WP I-WP113 - ILT Training Delivery Plan - Department QC | 8 hrs | 1 day | Thu 6/6/24 | Thu 6/6/24 | 1772 | 1774 |  | Gabriela Gibson
3037 | 1774 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | WP I-WP113 - ILT Training Delivery Plan - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/7/24 | Thu 6/20/24 | 1773 | 1775 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3038 | 1775 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | WP I-WP113 - ILT Training Delivery Plan - Style Guide Review | 8 hrs | 1 day | Fri 6/21/24 | Fri 6/21/24 | 1774 | 1776 |  | Tatiana Eubanks
3039 | 1776 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | WP I-WP113 - ILT Training Delivery Plan - Final Review & Update | 10 hrs | 5 days | Mon 6/24/24 | Fri 6/28/24 | 1775 | 1777 |  | Angie Robertson,Jimmy Cox
3040 | 1777 | Future Task |  |  | I-WP113 | Kimberly Kemp | Approve | WP I-WP113 - ILT Training Delivery Plan - Approve | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 1776 | 1779 |  | Jimmy Cox
3041 | 1778 | Future Task |  |  | I-WP114 | Kimberly Kemp |  | I-WP114 - Training Measurement Report | 143 hrs | 104 days | Wed 10/29/25 | Tue 3/31/26
3042 | 1779 | Future Task |  |  | I-WP114 | Carolyn Hicks | Create | WPED I-WP114 - Training Measurement Report - Create | 10 hrs | 10 days | Wed 10/29/25 | Wed 11/12/25 | 177717391838 | 1780 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
3043 | 1780 | Future Task |  |  | I-WP114 | Kimberly Kemp | Submit | WPED I-WP114 - Training Measurement Report - Submit | 0 hrs | 0 days | Wed 11/12/25 | Wed 11/12/25 | 1779 | 1781 |  | Carolyn Hicks
3044 | 1781 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WPED I-WP114 - Training Measurement Report - Collaborative Review & Update | 10 hrs | 10 days | Thu 11/13/25 | Wed 11/26/25 | 1780 | 1782 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
3045 | 1782 | Future Task |  |  | I-WP114 | Kimberly Kemp | Approve | WPED I-WP114 - Training Measurement Report - Approve | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 1781 | 1783 |  | Angie Robertson,Jimmy Cox
5695 | 1783 | Future Task |  |  | I-WP114 | Kimberly Kemp | Create | I-WP114 Training Measurement Report <Activities per WPED> | 100 hrs | 67 days | Mon 12/1/25 | Fri 3/6/26 | 17821274 | 1784 |  | Kimberly Kemp
3046 | 1784 | Future Task |  |  | I-WP114 | Kimberly Kemp | Submit | WP I-WP114 - Training Measurement Report - Submit | 0 hrs | 0 days | Fri 3/6/26 | Fri 3/6/26 | 1783 | 1785 |  | Kimberly Kemp
3047 | 1785 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WP I-WP114 - Training Measurement Report - Department QC | 1 hr | 1 day | Mon 3/9/26 | Mon 3/9/26 | 1784 | 1786 |  | Tommy Werner
3048 | 1786 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WP I-WP114 - Training Measurement Report - Collaborative Review & Update | 10 hrs | 10 days | Tue 3/10/26 | Mon 3/23/26 | 1785 | 1787 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3049 | 1787 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WP I-WP114 - Training Measurement Report - Style Guide Review | 2 hrs | 1 day | Tue 3/24/26 | Tue 3/24/26 | 1786 | 1788 |  | Dusti Kincl
3050 | 1788 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WP I-WP114 - Training Measurement Report - Final Review & Update | 10 hrs | 5 days | Wed 3/25/26 | Tue 3/31/26 | 1787 | 1789 |  | Angie Robertson,Jimmy Cox
3051 | 1789 | Future Task |  |  | I-WP114 | Kimberly Kemp | Approve | WP I-WP114 - Training Measurement Report - Approve | 0 hrs | 0 days | Tue 3/31/26 | Tue 3/31/26 | 1788 |  |  | Jimmy Cox
3052 | 1790 | Future Task |  | RW | I-WP115 | Kimberly Kemp |  | I-WP115 - Train the Trainer | 504 hrs | 167 days | Tue 10/1/24 | Fri 5/30/25
3053 | 1791 | Future Task |  |  | I-WP115 | Carolyn Hicks | Create | WPED I-WP115 - Train the Trainer - Create | 10 hrs | 10 days | Tue 10/1/24 | Mon 10/14/24 | 1 | 1792 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila
3054 | 1792 | Future Task |  |  | I-WP115 | Carolyn Hicks | Submit | WPED I-WP115 - Train the Trainer - Submit | 0 hrs | 0 days | Mon 10/14/24 | Mon 10/14/24 | 1791 | 1793 |  | Carolyn Hicks
3055 | 1793 | Future Task |  |  | I-WP115 | Carolyn Hicks | Review | WPED I-WP115 - Train the Trainer - Collaborative Review & Update | 10 hrs | 10 days | Tue 10/15/24 | Mon 10/28/24 | 1792 | 1794 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
3056 | 1794 | Future Task |  |  | I-WP115 | Carolyn Hicks | Approve | WPED I-WP115 - Train the Trainer - Approve | 0 hrs | 0 days | Mon 10/28/24 | Mon 10/28/24 | 1793 | 1795FS+63 days |  | Angie Robertson,Jimmy Cox
5696 | 1795 | Future Task |  |  | I-WP115 | Kimberly Kemp | Create | I-WP115 Train the Trainer <Activities per WPED> | 448 hrs | 56 days | Mon 2/3/25 | Mon 4/21/25 | 1794FS+63 days | 1796FS+11 days |  | Kimberly Kemp | Move to 4/1/25 to 6/30/25 | (DONE) Carolyn (note from Francisca: WP now completes on 8/8/2025)
3057 | 1796 | Future Task |  |  | I-WP115 | Kimberly Kemp | Submit | WP I-WP115 - Train the Trainer - Submit | 0 hrs | 0 days | Tue 5/6/25 | Tue 5/6/25 | 1795FS+11 days | 1797 |  | Kimberly Kemp
3058 | 1797 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | WP I-WP115 - Train the Trainer - Department QC | 8 hrs | 1 day | Wed 5/7/25 | Wed 5/7/25 | 1796 | 1798 |  | Gabriela Gibson
3059 | 1798 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | WP I-WP115 - Train the Trainer - Collaborative Review & Update | 10 hrs | 10 days | Thu 5/8/25 | Wed 5/21/25 | 1797 | 1799 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3060 | 1799 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | WP I-WP115 - Train the Trainer - Style Guide Review | 8 hrs | 1 day | Thu 5/22/25 | Thu 5/22/25 | 1798 | 1800 |  | Tatiana Eubanks
3061 | 1800 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | WP I-WP115 - Train the Trainer - Final Review & Update | 10 hrs | 5 days | Fri 5/23/25 | Fri 5/30/25 | 1799 | 1801 |  | Angie Robertson,Jimmy Cox
3062 | 1801 | Future Task |  |  | I-WP115 | Kimberly Kemp | Approve | WP I-WP115 - Train the Trainer - Approve | 0 hrs | 0 days | Fri 5/30/25 | Fri 5/30/25 | 1800 | 1802 |  | Jimmy Cox
3063 | 1802 | Future Task |  |  | I-WP115 | Kimberly Kemp | Milestone | WP I-WP115 - Train the Trainer - Complete | 0 hrs | 0 days | Fri 5/30/25 | Fri 5/30/25 | 1801 |  |  | Kimberly Kemp
3087 | 1803 | Future Task |  | RW | I-WP116 | Kimberly Kemp |  | I-WP116 - User Support Sessions | 156 hrs | 209 days | Mon 6/2/25 | Tue 3/31/26
3088 | 1804 | Future Task |  |  | I-WP116 | Carolyn Hicks | Create | WPED I-WP116 - User Support Sessions - Create | 10 hrs | 10 days | Mon 6/2/25 | Fri 6/13/25 | 1 | 1805 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling | move start date to 3/1/2025 | (DONE) Carolyn (note from Francisca: bucket task nowfrom 5/13/2025 through 3/28/2025 and WP approve in 2/12/2026)
3089 | 1805 | Future Task |  |  | I-WP116 | Carolyn Hicks | Submit | WPED I-WP116 - User Support Sessions - Submit | 0 hrs | 0 days | Fri 6/13/25 | Fri 6/13/25 | 1804 | 1806 |  | Carolyn Hicks
3090 | 1806 | Future Task |  |  | I-WP116 | Carolyn Hicks | Review | WPED I-WP116 - User Support Sessions - Collaborative Review & Update | 10 hrs | 10 days | Mon 6/16/25 | Fri 6/27/25 | 1805 | 1807 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3091 | 1807 | Future Task |  |  | I-WP116 | Carolyn Hicks | Approve | WPED I-WP116 - User Support Sessions - Approve | 0 hrs | 0 days | Fri 6/27/25 | Fri 6/27/25 | 1806 | 1808 |  | Angie Robertson,Jimmy Cox
5699 | 1808 | Future Task |  |  | I-WP116 | Kimberly Kemp | Create | I-WP116 User Support Sessions <Activities per WPED> | 100 hrs | 172 days | Mon 6/30/25 | Fri 3/6/26 | 1807,1274SS+30 days | 1809 |  | Kimberly Kemp
3092 | 1809 | Future Task |  |  | I-WP116 | Kimberly Kemp | Submit | WP I-WP116 - User Support Sessions - Submit | 0 hrs | 0 days | Fri 3/6/26 | Fri 3/6/26 | 1808 | 1810 |  | Kimberly Kemp
3093 | 1810 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | WP I-WP116 - User Support Sessions - Department QC | 8 hrs | 1 day | Mon 3/9/26 | Mon 3/9/26 | 1809 | 1811 |  | Gabriela Gibson
3094 | 1811 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | WP I-WP116 - User Support Sessions - Collaborative Review & Update | 10 hrs | 10 days | Tue 3/10/26 | Mon 3/23/26 | 1810 | 1812 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3095 | 1812 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | WP I-WP116 - User Support Sessions - Style Guide Review | 8 hrs | 1 day | Tue 3/24/26 | Tue 3/24/26 | 1811 | 1813 |  | Tatiana Eubanks
3096 | 1813 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | WP I-WP116 - User Support Sessions - Final Review & Update | 10 hrs | 5 days | Wed 3/25/26 | Tue 3/31/26 | 1812 | 1814 |  | Angie Robertson,Jimmy Cox
3097 | 1814 | Future Task |  |  | I-WP116 | Kimberly Kemp | Approve | WP I-WP116 - User Support Sessions - Approve | 0 hrs | 0 days | Tue 3/31/26 | Tue 3/31/26 | 1813 |  |  | Jimmy Cox
3064 | 1815 | Future Task |  |  | I-WP122 | Carolyn Hicks |  | I-WP122 - Update D33 Training Strategy | 143 hrs | 81 days | Wed 11/1/23 | Thu 2/29/24
3065 | 1816 | Future Task |  |  | I-WP122 | Carolyn Hicks | Create | WPED I-WP122 - Update D33 Training Strategy - Create | 10 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23 | 1 | 1817,1828SS |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3066 | 1817 | Future Task |  |  | I-WP122 | Carolyn Hicks | Submit | WPED I-WP122 - Update D33 Training Strategy - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 1816 | 1818 |  | Carolyn Hicks
3067 | 1818 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WPED I-WP122 - Update D33 Training Strategy - Collaborative Review & Update | 10 hrs | 10 days | Thu 11/16/23 | Fri 12/1/23 | 1817 | 1819 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3068 | 1819 | Future Task |  |  | I-WP122 | Carolyn Hicks | Approve | WPED I-WP122 - Update D33 Training Strategy - Approve | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 1818 | 1820 |  | Angie Robertson,Jimmy Cox
5697 | 1820 | Future Task |  | RW | I-WP122 | Carolyn Hicks | Create | I-WP122 Update D33 Training Strategy <Activities per WPED> | 100 hrs | 44 days | Mon 12/4/23 | Tue 2/6/24 | 1819 | 1821 |  | Kimberly Kemp
3069 | 1821 | Future Task |  |  | I-WP122 | Carolyn Hicks | Submit | WP I-WP122 - Update D33 Training Strategy - Submit | 0 hrs | 0 days | Tue 2/6/24 | Tue 2/6/24 | 1820 | 1822 |  | Kimberly Kemp
3070 | 1822 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WP I-WP122 - Update D33 Training Strategy - Department QC | 1 hr | 1 day | Wed 2/7/24 | Wed 2/7/24 | 1821 | 1823 |  | Tommy Werner
3071 | 1823 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WP I-WP122 - Update D33 Training Strategy - Collaborative Review & Update | 10 hrs | 10 days | Thu 2/8/24 | Wed 2/21/24 | 1822 | 1824 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3072 | 1824 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WP I-WP122 - Update D33 Training Strategy - Style Guide Review | 2 hrs | 1 day | Thu 2/22/24 | Thu 2/22/24 | 1823 | 1825 |  | Dusti Kincl
3073 | 1825 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WP I-WP122 - Update D33 Training Strategy - Final Review & Update | 10 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1824 | 1826 |  | Angie Robertson,Jimmy Cox
3074 | 1826 | Future Task |  |  | I-WP122 | Carolyn Hicks | Approve | WP I-WP122 - Update D33 Training Strategy - Approve | 0 hrs | 0 days | Thu 2/29/24 | Thu 2/29/24 | 1825 | 1767 |  | Jimmy Cox
3075 | 1827 | Future Task |  |  | I-WP123 | Carolyn Hicks |  | I-WP123 - Update D112 Training Deployment and Measurement Plan | 149 hrs | 81 days | Wed 11/1/23 | Thu 2/29/24
3076 | 1828 | Future Task |  |  | I-WP123 | Carolyn Hicks | Create | WPED I-WP123 - Update D112 Training Deployment and Measurement Plan - Create | 10 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23 | 1816SS | 1829 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3077 | 1829 | Future Task |  |  | I-WP123 | Carolyn Hicks | Submit | WPED I-WP123 - Update D112 Training Deployment and Measurement Plan - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 1828 | 1830 |  | Carolyn Hicks
3078 | 1830 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WPED I-WP123 - Update D112 Training Deployment and Measurement Plan - Collaborative Review and Update | 10 hrs | 10 days | Thu 11/16/23 | Fri 12/1/23 | 1829 | 1831 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3079 | 1831 | Future Task |  |  | I-WP123 | Carolyn Hicks | Approve | WPED I-WP123 - Update D112 Training Deployment and Measurement Plan - Approve | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 1830 | 1832 |  | Angie Robertson,Jimmy Cox
5698 | 1832 | Future Task |  |  | I-WP123 | Carolyn Hicks | Create | I-WP123 Update D112 Training Deployment and Measurement Plan <Activities per WPED> | 100 hrs | 44 days | Mon 12/4/23 | Tue 2/6/24 | 1831 | 1833 |  | Kimberly Kemp
3080 | 1833 | Future Task |  |  | I-WP123 | Carolyn Hicks | Submit | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Submit | 0 hrs | 0 days | Tue 2/6/24 | Tue 2/6/24 | 1832 | 1834 |  | Kimberly Kemp
3081 | 1834 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Department QC | 1 hr | 1 day | Wed 2/7/24 | Wed 2/7/24 | 1833 | 1835 |  | Tommy Werner
3082 | 1835 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Collaborative Review & Update | 10 hrs | 10 days | Thu 2/8/24 | Wed 2/21/24 | 1834 | 1836 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3083 | 1836 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Style Guide Review | 8 hrs | 1 day | Thu 2/22/24 | Thu 2/22/24 | 1835 | 1837 |  | Tatiana Eubanks
3084 | 1837 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Final Review & Update | 10 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1836 | 1838 |  | Angie Robertson,Jimmy Cox
3085 | 1838 | Future Task |  |  | I-WP123 | Carolyn Hicks | Approve | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Approve | 0 hrs | 0 days | Thu 2/29/24 | Thu 2/29/24 | 1837 | 17671779 |  | Jimmy Cox
6812 | 1839 | Future Task | [5 empty] | Training | 1 hr | 104 days | Tue 7/1/25 | Wed 11/26/25
6813 | 1840 | Future Task |  | RW |  | Carolyn Hicks | Create | Conduct Training | 1 hr | 104 days | Tue 7/1/25 | Wed 11/26/25 | 1 |  | July - Nov 2025 | Carolyn Hicks
3086 | 1841 | Late | [5 empty] | Readiness | 1,433 hrs | 632 days | Mon 5/8/23 | Wed 11/5/25
7183 | 1842 | Future Task |  |  | SG4 | Jimmy Cox | Create | Stage Gate 4: Prepare Stage Gate Checklist | 6 hrs | 5 days | Thu 6/5/25 | Wed 6/11/25 |  | 1843 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7184 | 1843 | Future Task |  |  | SG4 | Jimmy Cox | Create | Stage Gate 4: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Thu 6/12/25 | Wed 6/25/25 | 1842 | 1844FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7185 | 1844 | Future Task |  |  | SG4 | Jimmy Cox | Create | Stage Gate 4: Prepare information package for ESC | 11 hrs | 10 days | Wed 10/15/25 | Tue 10/28/25 | 1843FS+77 days | 1845 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7186 | 1845 | Future Task |  |  | SG4 | Jimmy Cox | Create | Stage Gate 4: Collaborative Review and Update of information package | 11 hrs | 5 days | Wed 10/29/25 | Tue 11/4/25 | 1844 | 1846 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7187 | 1846 | Future Task |  |  | SG4 | Jimmy Cox | Create | Stage Gate 4: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 11/5/25 | Wed 11/5/25 | 1845 |  |  | Dusti Kincl
7159 | 1847 | Future Task |  |  | SG4 | Jimmy Cox | Milestone | Stage Gate 4: Agency Readiness | 0 hrs | 0 days | Mon 11/3/25 | Mon 11/3/25 | 1 |  | November 2025 - ESC | Executive Steering Committee
3098 | 1848 | Future Task |  |  | I-WP117 | Nikki Klein |  | I-WP117 - Role Mapping Handbook | 149 hrs | 193 days | Thu 2/1/24 | Thu 10/31/24
3099 | 1849 | Future Task |  |  | I-WP117 | Carolyn Hicks | Create | WPED I-WP117- Role Mapping Handbook - Create | 10 hrs | 10 days | Thu 2/1/24 | Wed 2/14/24 | 1 | 1850 |  | Carolyn Hicks,Nikki Klein,Felicia Hall
3100 | 1850 | Future Task |  |  | I-WP117 | Carolyn Hicks | Submit | WPED I-WP117 - Role Mapping Handbook - Submit | 0 hrs | 0 days | Wed 2/14/24 | Wed 2/14/24 | 1849 | 1851 |  | Carolyn Hicks
3101 | 1851 | Future Task |  |  | I-WP117 | Carolyn Hicks | Review | WPED I-WP117 - Role Mapping Handbook - Collaborative Review & Update | 10 hrs | 10 days | Thu 2/15/24 | Wed 2/28/24 | 1850 | 1852 |  | Carolyn Hicks,Nikki Klein,Felicia Hall,Angie Robertson
3102 | 1852 | Future Task |  |  | I-WP117 | Carolyn Hicks | Approve | WPED I-WP117 - Role Mapping Handbook - Approve | 0 hrs | 0 days | Wed 2/28/24 | Wed 2/28/24 | 1851 | 1853 |  | Angie Robertson,Jimmy Cox
5700 | 1853 | Future Task |  | RW | I-WP117 | Nikki Klein | Create | I-WP117 Role Mapping Handbook <Activities per WPED> | 100 hrs | 156 days | Thu 2/29/24 | Tue 10/8/24 | 1852110 | 1854,1865SS+40 days |  | Nikki Klein
3103 | 1854 | Future Task |  |  | I-WP117 | Nikki Klein | Submit | WP I-WP117 - Role Mapping Handbook - Submit | 0 hrs | 0 days | Tue 10/8/24 | Tue 10/8/24 | 1853 | 1855 |  | Nikki Klein
3104 | 1855 | Future Task |  |  | I-WP117 | Nikki Klein | Review | WP I-WP117 - Role Mapping Handbook - Department QC | 1 hr | 1 day | Wed 10/9/24 | Wed 10/9/24 | 1854 | 1856 |  | Gabriela Gibson
3105 | 1856 | Future Task |  |  | I-WP117 | Nikki Klein | Review | WP I-WP117 - Role Mapping Handbook - Collaborative Review & Update | 10 hrs | 10 days | Thu 10/10/24 | Wed 10/23/24 | 1855 | 1857 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3106 | 1857 | Future Task |  |  | I-WP117 | Nikki Klein | Review | WP I-WP117 - Role Mapping Handbook - Style Guide Review | 8 hrs | 1 day | Thu 10/24/24 | Thu 10/24/24 | 1856 | 1858 |  | Tatiana Eubanks
3107 | 1858 | Future Task |  |  | I-WP117 | Nikki Klein | Review | WP I-WP117 - Role Mapping Handbook - Final Review & Update | 10 hrs | 5 days | Fri 10/25/24 | Thu 10/31/24 | 1857 | 1859 |  | Angie Robertson,Jimmy Cox
3108 | 1859 | Future Task |  |  | I-WP117 | Nikki Klein | Approve | WP I-WP117 - Role Mapping Handbook - Approve | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 1858 |  |  | Jimmy Cox | Successor - Role Mapping Worksheet 118 | TW (Francisca note: completed on 6/9 -- this doc has the cell color locked)
3109 | 1860 | Future Task | Yes |  | I-WP118 | Nikki Klein |  | I-WP118 - Role Mapping Worksheet | 456 hrs | 135 days | Mon 6/3/24 | Fri 12/13/24
3110 | 1861 | Future Task |  |  | I-WP118 | Carolyn Hicks | Create | WPED I-WP118 - Role Mapping Worksheet - Create | 10 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 1 | 1862 |  | Carolyn Hicks,Nikki Klein,Felicia Hall
3111 | 1862 | Future Task |  |  | I-WP118 | Carolyn Hicks | Submit | WPED I-WP118 - Role Mapping Worksheet - Submit | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 1861 | 1863 |  | Carolyn Hicks
3112 | 1863 | Future Task |  |  | I-WP118 | Carolyn Hicks | Review | WPED I-WP118 - Role Mapping Worksheet - Collaborative Review & Update | 10 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 1862 | 1864 |  | Carolyn Hicks,Nikki Klein,Felicia Hall,Angie Robertson
3113 | 1864 | Future Task |  |  | I-WP118 | Carolyn Hicks | Approve | WPED I-WP118 - Role Mapping Worksheet - Approve | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 1863 | 1865 |  | Angie Robertson,Jimmy Cox
5701 | 1865 | Future Task |  | RW | I-WP118 | Nikki Klein | Create | I-WP118 Role Mapping Worksheet <Activities per WPED> | 400 hrs | 67 days | Wed 8/14/24 | Mon 11/18/24 | 1864,1853SS+40 days,579,1920SS+40 days | 1866 |  | Nikki Klein
3114 | 1866 | Future Task |  |  | I-WP118 | Nikki Klein | Submit | WP I-WP118 - Role Mapping Worksheet - Submit | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 1865 | 1867 |  | Nikki Klein
3115 | 1867 | Future Task |  |  | I-WP118 | Nikki Klein | Review | WP I-WP118 - Role Mapping Worksheet - Department QC | 8 hrs | 1 day | Tue 11/19/24 | Tue 11/19/24 | 1866 | 1868 |  | Gabriela Gibson
3116 | 1868 | Future Task |  |  | I-WP118 | Nikki Klein | Review | WP I-WP118 - Role Mapping Worksheet - Collaborative Review & Update | 10 hrs | 10 days | Wed 11/20/24 | Thu 12/5/24 | 1867 | 1869 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3117 | 1869 | Future Task |  |  | I-WP118 | Nikki Klein | Review | WP I-WP118 - Role Mapping Worksheet - Style Guide Review | 8 hrs | 1 day | Fri 12/6/24 | Fri 12/6/24 | 1868 | 1870 |  | Tatiana Eubanks
3118 | 1870 | Future Task |  |  | I-WP118 | Nikki Klein | Review | WP I-WP118 - Role Mapping Worksheet - Final Review & Update | 10 hrs | 5 days | Mon 12/9/24 | Fri 12/13/24 | 1869 | 1871 |  | Angie Robertson,Jimmy Cox
3119 | 1871 | Future Task |  |  | I-WP118 | Nikki Klein | Approve | WP I-WP118 - Role Mapping Worksheet - Approve | 0 hrs | 0 days | Fri 12/13/24 | Fri 12/13/24 | 1870 | 562561 |  | Jimmy Cox
3120 | 1872 | Future Task |  |  | I-WP119 | Nikki Klein |  | I-WP119 - Change Analysis Tool | 66 hrs | 188 days | Wed 11/1/23 | Wed 7/31/24
3121 | 1873 | Future Task |  |  | I-WP119 | Carolyn Hicks | Create | WPED I-WP119 - Change Analysis Tool - Create | 10 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23 | 1 | 1874 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas
3122 | 1874 | Future Task |  |  | I-WP119 | Carolyn Hicks | Submit | WPED I-WP119 - Change Analysis Tool - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 1873 | 1875 |  | Carolyn Hicks
3123 | 1875 | Future Task |  |  | I-WP119 | Carolyn Hicks | Review | WPED I-WP119 - Change Analysis Tool - Collaborative Review & Update | 10 hrs | 10 days | Thu 11/16/23 | Fri 12/1/23 | 1874 | 1876 |  | Carolyn Hicks,Nikki Klein,Kim York,Angie Robertson,Dora Thomas
3124 | 1876 | Future Task |  |  | I-WP119 | Carolyn Hicks | Approve | WPED I-WP119 - Change Analysis Tool - Approve | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 1875 | 1877 |  | Angie Robertson,Jimmy Cox
6814 | 1877 | Future Task |  | RW | I-WP119 | Nikki Klein | Submit | I-WP119 Change Analysis Tool <Activities per WPED> | 10 hrs | 151 days | Mon 12/4/23 | Mon 7/8/24 | 18761926 | 1878 |  | Nikki Klein
3125 | 1878 | Future Task |  |  | I-WP119 | Nikki Klein | Submit | WP I-WP119 - Change Analysis Tool - Submit | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1877 | 1879 |  | Nikki Klein
3126 | 1879 | Future Task |  |  | I-WP119 | Nikki Klein | Review | WP I-WP119 - Change Analysis Tool - Department QC | 8 hrs | 1 day | Tue 7/9/24 | Tue 7/9/24 | 1878 | 1880 |  | Gabriela Gibson
3127 | 1880 | Future Task |  |  | I-WP119 | Nikki Klein | Review | WP I-WP119 - Change Analysis Tool - Collaborative Review & Update | 10 hrs | 10 days | Wed 7/10/24 | Tue 7/23/24 | 1879 | 1881 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3128 | 1881 | Future Task |  |  | I-WP119 | Nikki Klein | Review | WP I-WP119 - Change Analysis Tool - Style Guide Review | 8 hrs | 1 day | Wed 7/24/24 | Wed 7/24/24 | 1880 | 1882 |  | Tatiana Eubanks
3129 | 1882 | Future Task |  |  | I-WP119 | Nikki Klein | Review | WP I-WP119 - Change Analysis Tool - Final Review & Update | 10 hrs | 5 days | Thu 7/25/24 | Wed 7/31/24 | 1881 | 1883 |  | Angie Robertson,Jimmy Cox
3130 | 1883 | Future Task |  |  | I-WP119 | Nikki Klein | Approve | WP I-WP119 - Change Analysis Tool - Approve | 0 hrs | 0 days | Wed 7/31/24 | Wed 7/31/24 | 1882 |  |  | Jimmy Cox | Successor - Role Mapping Handbook 117 | TW (Francisca note: completed on 6/9 -- this doc has the cell color locked)
3131 | 1884 | Future Task |  |  | I-WP121 | Carolyn Hicks |  | I-WP121 - Update D27 Readiness Plan | 143 hrs | 82 days | Mon 10/2/23 | Wed 1/31/24
3132 | 1885 | Future Task |  |  | I-WP121 | Carolyn Hicks | Create | WPED I-WP121 - Update D27 Readiness Plan - Create | 10 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 1 | 1886 |  | Carolyn Hicks,Nikki Klein
3133 | 1886 | Future Task |  |  | I-WP121 | Carolyn Hicks | Submit | WPED I-WP121 - Update D27 Readiness Plan - Submit | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 1885 | 1887 |  | Carolyn Hicks
3134 | 1887 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WPED I-WP121 - Update D27 Readiness Plan - Collaborative Review & Update | 10 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 1886 | 1888 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas,Angie Robertson
3135 | 1888 | Future Task |  |  | I-WP121 | Carolyn Hicks | Approve | WPED I-WP121 - Update D27 Readiness Plan - Approve | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 1887 | 1889 |  | Angie Robertson,Jimmy Cox
5702 | 1889 | Future Task |  |  | I-WP121 | Carolyn Hicks | Create | I-WP121 Update D27 Readiness Plan <Activities per WPED> | 100 hrs | 45 days | Mon 10/30/23 | Fri 1/5/24 | 1888 | 1890 |  | Nikki Klein
3136 | 1890 | Future Task |  |  | I-WP121 | Carolyn Hicks | Submit | WP I-WP121 - Update D27 Readiness Plan - Submit | 0 hrs | 0 days | Fri 1/5/24 | Fri 1/5/24 | 1889 | 1891 |  | Nikki Klein
3137 | 1891 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WP I-WP121 - Update D27 Readiness Plan - Department QC | 1 hr | 1 day | Mon 1/8/24 | Mon 1/8/24 | 1890 | 1892 |  | Gabriela Gibson
3138 | 1892 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WP I-WP121 - Update D27 Readiness Plan - Collaborative Review & Update | 10 hrs | 10 days | Tue 1/9/24 | Tue 1/23/24 | 1891 | 1893 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3139 | 1893 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WP I-WP121 - Update D27 Readiness Plan - Style Guide Review | 2 hrs | 1 day | Wed 1/24/24 | Wed 1/24/24 | 1892 | 1894 |  | Dusti Kincl
3140 | 1894 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WP I-WP121 - Update D27 Readiness Plan - Final Review & Update | 10 hrs | 5 days | Thu 1/25/24 | Wed 1/31/24 | 1893 | 1895 |  | Angie Robertson,Jimmy Cox
3141 | 1895 | Future Task |  |  | I-WP121 | Carolyn Hicks | Approve | WP I-WP121 - Update D27 Readiness Plan - Approve | 0 hrs | 0 days | Wed 1/31/24 | Wed 1/31/24 | 1894 | 1932 |  | Jimmy Cox | Successor - Change Impact Analysis 119 | TW (Francisca note: completed on 6/9 -- this doc has the cell color locked)
3142 | 1896 | Future Task |  |  | I-WP124 | Carolyn Hicks |  | I-WP124 - Update D62 Workforce Transition Plan | 149 hrs | 82 days | Mon 10/2/23 | Wed 1/31/24
3143 | 1897 | Future Task |  |  | I-WP124 | Carolyn Hicks | Create | WPED I-WP124 - Update D62 Workforce Transition Plan - Create | 10 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 1 | 1898 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas
3144 | 1898 | Future Task |  |  | I-WP124 | Carolyn Hicks | Submit | WPED I-WP124 - Update D62 Workforce Transition Plan - Submit | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 1897 | 1899 |  | Carolyn Hicks
3145 | 1899 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WPED I-WP124 - Update D62 Workforce Transition Plan - Collaborative Review & Update | 10 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 1898 | 1900 |  | Carolyn Hicks,Nikki Klein,Kim York,Angie Robertson,Dora Thomas
3146 | 1900 | Future Task |  |  | I-WP124 | Carolyn Hicks | Approve | WPED I-WP124 - Update D62 Workforce Transition Plan - Approve | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 1899 | 1901 |  | Angie Robertson,Jimmy Cox
5703 | 1901 | Future Task |  |  | I-WP124 | Carolyn Hicks | Create | I-WP124 Update D62 Workforce Transition Plan <Activities per WPED> | 100 hrs | 45 days | Mon 10/30/23 | Fri 1/5/24 | 1900 | 1902 |  | Nikki Klein
3147 | 1902 | Future Task |  |  | I-WP124 | Carolyn Hicks | Submit | WP I-WP124 - Update D62 Workforce Transition Plan - Submit | 0 hrs | 0 days | Fri 1/5/24 | Fri 1/5/24 | 1901 | 1903 |  | Nikki Klein
3148 | 1903 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WP I-WP124 - Update D62 Workforce Transition Plan - Department QC | 1 hr | 1 day | Mon 1/8/24 | Mon 1/8/24 | 1902 | 1904 |  | Gabriela Gibson
3149 | 1904 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WP I-WP124 - Update D62 Workforce Transition Plan - Collaborative Review & Update | 10 hrs | 10 days | Tue 1/9/24 | Tue 1/23/24 | 1903 | 1905 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3150 | 1905 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WP I-WP124 - Update D62 Workforce Transition Plan - Style Guide Review | 8 hrs | 1 day | Wed 1/24/24 | Wed 1/24/24 | 1904 | 1906 |  | Tatiana Eubanks
3151 | 1906 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WP I-WP124 - Update D62 Workforce Transition Plan - Final Review & Update | 10 hrs | 5 days | Thu 1/25/24 | Wed 1/31/24 | 1905 | 1907 |  | Angie Robertson,Jimmy Cox
3152 | 1907 | Future Task |  |  | I-WP124 | Carolyn Hicks | Approve | WP I-WP124 - Update D62 Workforce Transition Plan - Approve | 0 hrs | 0 days | Wed 1/31/24 | Wed 1/31/24 | 1906 |  |  | Jimmy Cox | Successor - Change Impact Analysis 119 | TW (Francisca note: completed on 6/9 -- this doc has the cell color locked)
6777 | 1908 | Late | Yes |  | I-WP126 | Nikki Klein |  | I-WP126 - Readiness Workplan | 358 hrs | 88 days | Mon 5/8/23 | Mon 9/11/23
6778 | 1909 | Complete |  |  | I-WP126 | Carolyn Hicks | Create | WPED I-WP126 - Readiness Workplan - Create | 10 hrs | 10 days | Mon 5/8/23 | Fri 5/19/23 | 1 | 1910 |  | Carolyn Hicks,Nikki Klein,Jordan Nobles
6779 | 1910 | Complete |  |  | I-WP126 | Carolyn Hicks | Submit | WPED I-WP126 - Readiness Workplan - Submit | 0 hrs | 0 days | Fri 5/19/23 | Fri 5/19/23 | 1909 | 1911 |  | Carolyn Hicks
6780 | 1911 | Complete |  |  | I-WP126 | Carolyn Hicks | Review | WPED I-WP126 - Readiness Workplan - Collaborative Review & Update | 7 hrs | 7 days | Mon 5/22/23 | Wed 5/31/23 | 1910 | 1912 |  | Carolyn Hicks,Nikki Klein,Jordan Nobles,Angie Robertson
6781 | 1912 | Complete |  |  | I-WP126 | Carolyn Hicks | Approve | WPED I-WP126 - Readiness Workplan - Approve | 0 hrs | 0 days | Wed 5/31/23 | Wed 5/31/23 | 1911 | 1913FS+2 days |  | Angie Robertson,Jimmy Cox
7164 | 1913 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Create draft RW and roadmap | 72 hrs | 20 days | Mon 6/5/23 | Fri 6/30/23 | 1912FS+2 days | 1914 |  | Nikki Klein,Jordan Nobles,Vincent Cicco
7165 | 1914 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Gather input | 48 hrs | 14 days | Mon 7/3/23 | Fri 7/21/23 | 1913 | 1915SS |  | Carolyn Hicks,Jordan Nobles,Nikki Klein,Kimberly Kemp,Angie Robertson,Jimmy Cox
7166 | 1915 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Review Project Schedule | 24 hrs | 9 days | Mon 7/3/23 | Fri 7/14/23 | 1914SS | 1916 |  | Nikki Klein,Jordan Nobles,Vincent Cicco
7167 | 1916 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Update RW | 60 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 | 1915 | 1917SS |  | Nikki Klein,Jordan Nobles,Vincent Cicco
7162 | 1917 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Update Roadmap | 12 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 | 1916SS | 1918 |  | Jordan Nobles,Vincent Cicco
7163 | 1918 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Confirm RW tasks with Architects | 32 hrs | 13 days | Mon 7/31/23 | Wed 8/16/23 | 1917 | 1919 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Jordan Nobles,Nikki Klein,Kimberly Kemp,Angie Robertson
7161 | 1919 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Finalize RW | 38 hrs | 4 days | Thu 8/17/23 | Tue 8/22/23 | 1918 | 1920SS |  | Nikki Klein,Jordan Nobles,Vincent Cicco
7160 | 1920 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Finalize Roadmap | 4 hrs | 4 days | Thu 8/17/23 | Tue 8/22/23 | 1919SS | 1921,1865SS+40 days |  | Jordan Nobles,Vincent Cicco
6783 | 1921 | Future Task |  |  | I-WP126 | Nikki Klein | Submit | WP I-WP126 - Readiness Workplan - Submit | 0 hrs | 0 days | Tue 8/22/23 | Tue 8/22/23 | 1920 | 1922 |  | Nikki Klein
6784 | 1922 | Future Task |  |  | I-WP126 | Nikki Klein | Review | WP I-WP126 - Readiness Workplan - Department QC | 3 hrs | 1 day | Wed 8/23/23 | Wed 8/23/23 | 1921 | 1923 |  | Gabriela Gibson
6785 | 1923 | Future Task |  |  | I-WP126 | Nikki Klein | Review | WP I-WP126 - Readiness Workplan - Collaborative Review & Update | 18 hrs | 5 days | Thu 8/24/23 | Wed 8/30/23 | 1922 | 1924 |  | Nikki Klein,Carolyn Hicks,Angie Robertson
6786 | 1924 | Future Task |  |  | I-WP126 | Nikki Klein | Review | WP I-WP126 - Readiness Workplan - Style Guide Review | 4 hrs | 1 day | Thu 8/31/23 | Thu 8/31/23 | 1923 | 1925 |  | Dusti Kincl
6787 | 1925 | Future Task |  |  | I-WP126 | Nikki Klein | Review | WP I-WP126 - Readiness Workplan - Final Review & Update | 18 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 1924 | 1926 |  | Nikki Klein,Jordan Nobles,Vincent Cicco
6788 | 1926 | Future Task |  |  | I-WP126 | Nikki Klein | Approve | WP I-WP126 - Readiness Workplan - Approve | 8 hrs | 1 day | Mon 9/11/23 | Mon 9/11/23 | 1925 | 1877 |  | Jimmy Cox,Angie Robertson
7225 | 1927 | Future Task | Yes |  | I-WP128 | Nikki Klein |  | I-WP128 - Agency Readiness Certification | 73 hrs | 124 days | Mon 1/8/24 | Mon 7/1/24
7236 | 1928 | Future Task |  |  | I-WP128 | Carolyn Hicks | Create | WPED I-WP128 - Agency Readiness Certification - Create | 10 hrs | 6 days | Mon 1/8/24 | Tue 1/16/24 |  | 1929 |  | Carolyn Hicks,Nikki Klein,Jordan Nobles,Angie Robertson
7237 | 1929 | Future Task |  |  | I-WP128 | Carolyn Hicks | Submit | WPED I-WP128 - Agency Readiness Certification - Submit | 0 hrs | 0 days | Tue 1/16/24 | Tue 1/16/24 | 1928 | 1930 |  | Carolyn Hicks
7238 | 1930 | Future Task |  |  | I-WP128 | Carolyn Hicks | Review | WPED I-WP128 - Agency Readiness Certification - Collaborative Review & Update | 10 hrs | 10 days | Wed 1/17/24 | Tue 1/30/24 | 1929 | 1931 |  | Angie Robertson,Jimmy Cox
7232 | 1931 | Future Task |  |  | I-WP128 | Carolyn Hicks | Approve | WPED I-WP128 - Agency Readiness Certification - Approve | 0 hrs | 0 days | Tue 1/30/24 | Tue 1/30/24 | 1930 | 1932FS+3 days |  | Jimmy Cox
7233 | 1932 | Future Task |  |  | I-WP128 | Kimberly Kemp | Create | I-WP128 - Agency Readiness Certification <Activities per WPED> | 10 hrs | 88 days | Mon 2/5/24 | Thu 6/6/24 | 1931FS+3 days,1895 | 1933 |  | Nikki Klein,Jordan Nobles
7234 | 1933 | Future Task |  |  | I-WP128 | Nikki Klein | Submit | WP I-WP128 - Agency Readiness Certification - Submit | 0 hrs | 0 days | Thu 6/6/24 | Thu 6/6/24 | 1932 | 1934 |  | Nikki Klein
7235 | 1934 | Future Task |  |  | I-WP128 | Nikki Klein | Review | WP I-WP128 - Agency Readiness Certification - Department QC | 3 hrs | 1 day | Fri 6/7/24 | Fri 6/7/24 | 1933 | 1935 |  | Gabriela Gibson
7230 | 1935 | Future Task |  |  | I-WP128 | Nikki Klein | Review | WP I-WP128 - Agency Readiness Certification - Collaborative Review & Update | 18 hrs | 10 days | Mon 6/10/24 | Fri 6/21/24 | 1934 | 1936 |  | Carolyn Hicks,Nikki Klein
7231 | 1936 | Future Task |  |  | I-WP128 | Nikki Klein | Review | WP I-WP128 - Agency Readiness Certification - Style Guide Review | 4 hrs | 1 day | Mon 6/24/24 | Mon 6/24/24 | 1935 | 1937 |  | Tatiana Eubanks
7229 | 1937 | Future Task |  |  | I-WP128 | Nikki Klein | Review | WP I-WP128 - Agency Readiness Certification - Final Review & Update | 18 hrs | 5 days | Tue 6/25/24 | Mon 7/1/24 | 1936 | 1938 |  | Angie Robertson,Jimmy Cox
7228 | 1938 | Future Task |  |  | I-WP128 | Nikki Klein | Approve | WP I-WP128 - Agency Readiness Certification - Approve | 0 hrs | 0 days | Mon 7/1/24 | Mon 7/1/24 | 1937 | 1284 |  | Jimmy Cox
3 | 1939 | Future Task | [5 empty] | Production Support | 1,863 hrs | 638 days | Mon 1/6/25 | Thu 7/15/27
5850 | 1940 | Future Task | [5 empty] | Hypercare | 517 hrs | 358 days | Mon 1/6/25 | Thu 6/4/26
5852 | 1941 | Future Task |  |  | D664 | Bryan Sohayda |  | D664 - Development of the Hypercare Support Plan | 205 hrs | 106 days | Mon 1/6/25 | Wed 6/4/25
5853 | 1942 | Future Task |  |  | D664 | Bryan Sohayda | Create | DED D664 - Development of the Hypercare Support Plan - Create | 8 hrs | 10 days | Mon 1/6/25 | Fri 1/17/25 | 1 | 1943,2012SS+5 days | 2025-02-03 | Bryan Sohayda
5854 | 1943 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DED D664 - Development of the Hypercare Support Plan - Submit | 0 hrs | 0 days | Fri 1/17/25 | Fri 1/17/25 | 1942 | 1944 |  | Bryan Sohayda,Joy Schneider
5855 | 1944 | Future Task |  |  | D664 | Bryan Sohayda | Review | DED D664 - Development of the Hypercare Support Plan - Collaborative Review | 16 hrs | 10 days | Tue 1/21/25 | Mon 2/3/25 | 1943 | 1945 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5856 | 1945 | Future Task |  |  | D664 | Bryan Sohayda | Approve | DED D664 - Development of the Hypercare Support Plan - Approve | 0 hrs | 0 days | Mon 2/3/25 | Mon 2/3/25 | 1944 | 1946FS+19 days |  | Jimmy Cox
5857 | 1946 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Development of the Hypercare Support Plan | 20 hrs | 50 days | Mon 3/3/25 | Fri 5/9/25 | 1945FS+19 days | 1947SS,1953 |  | Bryan Sohayda,Chetna Dewan
5858 | 1947 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Define and document hypercare support processes and procedures | 20 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1946SS | 1948 |  | Bryan Sohayda,Chetna Dewan
5859 | 1948 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Review hypercare support processes and procedures draft | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1947 | 1949 |  | Bryan Sohayda,Chetna Dewan
5860 | 1949 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Define and document tools used for hypercare support activities | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 1948 | 1950 |  | Bryan Sohayda,Chetna Dewan
5861 | 1950 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Review tools used for hypercare activities draft | 20 hrs | 5 days | Mon 3/31/25 | Fri 4/4/25 | 1949 | 1951 |  | Bryan Sohayda,Chetna Dewan
5862 | 1951 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Determine and document resource capacity and skills needed | 20 hrs | 5 days | Mon 4/7/25 | Fri 4/11/25 | 1950 | 1952 |  | Bryan Sohayda,Chetna Dewan
5863 | 1952 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Review resource capacity and skills needed draft | 20 hrs | 5 days | Mon 4/14/25 | Fri 4/18/25 | 1951 | 1953 |  | Bryan Sohayda,Chetna Dewan
5864 | 1953 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DEL D664 - Development of the Hypercare Support Plan - Draft Submission | 0 hrs | 0 days | Fri 5/9/25 | Fri 5/9/25 | 19461952 | 1954 |  | Bryan Sohayda,Joy Schneider
5865 | 1954 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Pre-Submission Collaborative Review | 12 hrs | 5 days | Mon 5/12/25 | Fri 5/16/25 | 1953 | 1955 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5866 | 1955 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Style Guide Review | 1 hr | 1 day | Mon 5/19/25 | Mon 5/19/25 | 1954 | 1956 |  | Dusti Kincl
5867 | 1956 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Final Collaborative Review | 12 hrs | 5 days | Tue 5/20/25 | Tue 5/27/25 | 1955 | 1957 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5868 | 1957 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Accenture QC | 4 hrs | 2 days | Wed 5/28/25 | Thu 5/29/25 | 1956 | 1958 |  | Joy Schneider
5869 | 1958 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DEL D664 - Development of the Hypercare Support Plan - Submit | 0 hrs | 0 days | Thu 5/29/25 | Thu 5/29/25 | 1957 | 1959 |  | Joy Schneider
5870 | 1959 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Department QC | 4 hrs | 1 day | Fri 5/30/25 | Fri 5/30/25 | 1958 | 1960 |  | Tommy Werner,Gabriela Gibson
5871 | 1960 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Contract Manager Review | 8 hrs | 3 days | Mon 6/2/25 | Wed 6/4/25 | 1959 | 1961 |  | Sean Buchanan
5872 | 1961 | Future Task |  |  | D664 | Bryan Sohayda | Accept | DEL D664 - Development of the Hypercare Support Plan - Accept | 0 hrs | 0 days | Wed 6/4/25 | Wed 6/4/25 | 1960 | 1963 | 2025-06-01 | Sean Buchanan
5873 | 1962 | Future Task |  |  | D680 | Bryan Sohayda |  | D680 - Hypercare Monthly Deliverable – January 2026 | 153 hrs | 85 days | Mon 11/3/25 | Mon 3/9/26
5874 | 1963 | Future Task |  |  | D680-D683 | Bryan Sohayda | Create | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Create | 80 hrs | 10 days | Mon 11/3/25 | Mon 11/17/25 | 1961 | 1964 |  | Bryan Sohayda
5875 | 1964 | Future Task |  |  | D680-D683 | Bryan Sohayda | Submit | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Submit | 0 hrs | 0 days | Mon 11/17/25 | Mon 11/17/25 | 1963 | 1965 |  | Bryan Sohayda,Joy Schneider
5876 | 1965 | Future Task |  |  | D680-D683 | Bryan Sohayda | Review | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Collaborative Review | 20 hrs | 10 days | Tue 11/18/25 | Wed 12/3/25 | 1964 | 1966 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
7150 | 1966 | Future Task |  |  | D680-D683 | Bryan Sohayda | Approve | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Approve | 0 hrs | 0 days | Wed 12/3/25 | Wed 12/3/25 | 1965 | 1967FS+44 days |  | Jimmy Cox
5877 | 1967 | Future Task |  |  | D680 | Bryan Sohayda | Create | Create D680 - Hypercare Monthly Deliverable – January 2026 | 4 hrs | 4 days | Mon 2/9/26 | Thu 2/12/26 | 1966FS+44 days | 1968 |  | Bryan Sohayda
5878 | 1968 | Future Task |  |  | D680 | Bryan Sohayda | Submit | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Draft Submission | 0 hrs | 0 days | Thu 2/12/26 | Thu 2/12/26 | 1967 | 1969 |  | Joy Schneider,Bryan Sohayda
5879 | 1969 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 2/13/26 | Thu 2/19/26 | 1968 | 1970 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5880 | 1970 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Style Guide Review | 1 hr | 1 day | Fri 2/20/26 | Fri 2/20/26 | 1969 | 1971 |  | Dusti Kincl
5881 | 1971 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Final Collaborative Review | 16 hrs | 5 days | Mon 2/23/26 | Fri 2/27/26 | 1970 | 1972 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5882 | 1972 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Accenture QC | 4 hrs | 2 days | Mon 3/2/26 | Tue 3/3/26 | 1971 | 1973 |  | Joy Schneider
5883 | 1973 | Future Task |  |  | D680 | Bryan Sohayda | Submit | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Submit | 0 hrs | 0 days | Tue 3/3/26 | Tue 3/3/26 | 1972 | 1974 |  | Joy Schneider
5884 | 1974 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Department QC | 4 hrs | 1 day | Wed 3/4/26 | Wed 3/4/26 | 1973 | 1975 |  | Tommy Werner
5885 | 1975 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 3/5/26 | Mon 3/9/26 | 1974 | 1976 |  | Sean Buchanan
5886 | 1976 | Future Task |  |  | D680 | Bryan Sohayda | Accept | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Accept | 0 hrs | 0 days | Mon 3/9/26 | Mon 3/9/26 | 1975 | 1978FS-1 day |  | Sean Buchanan
5887 | 1977 | Future Task |  |  | D681 | Bryan Sohayda |  | D681 - Hypercare Monthly Deliverable – February 2026 | 53 hrs | 21 days | Mon 3/9/26 | Mon 4/6/26
5888 | 1978 | Future Task |  |  | D681 | Bryan Sohayda | Create | Create D681 - Hypercare Monthly Deliverable – February 2026 | 4 hrs | 4 days | Mon 3/9/26 | Thu 3/12/26 | 1976FS-1 day | 1979 |  | Bryan Sohayda
5889 | 1979 | Future Task |  |  | D681 | Bryan Sohayda | Submit | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Draft Submission | 0 hrs | 0 days | Thu 3/12/26 | Thu 3/12/26 | 1978 | 1980 |  | Joy Schneider,Bryan Sohayda
5890 | 1980 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 3/13/26 | Thu 3/19/26 | 1979 | 1981 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5891 | 1981 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Style Guide Review | 1 hr | 1 day | Fri 3/20/26 | Fri 3/20/26 | 1980 | 1982 |  | Dusti Kincl
5892 | 1982 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Final Collaborative Review | 16 hrs | 5 days | Mon 3/23/26 | Fri 3/27/26 | 1981 | 1983 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5893 | 1983 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Accenture QC | 4 hrs | 2 days | Mon 3/30/26 | Tue 3/31/26 | 1982 | 1984 |  | Joy Schneider
5894 | 1984 | Future Task |  |  | D681 | Bryan Sohayda | Submit | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Submit | 0 hrs | 0 days | Tue 3/31/26 | Tue 3/31/26 | 1983 | 1985 |  | Joy Schneider
5895 | 1985 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Department QC | 4 hrs | 1 day | Wed 4/1/26 | Wed 4/1/26 | 1984 | 1986 |  | Tommy Werner
5896 | 1986 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 4/2/26 | Mon 4/6/26 | 1985 | 1987 |  | Sean Buchanan
5897 | 1987 | Future Task |  |  | D681 | Bryan Sohayda | Accept | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Accept | 0 hrs | 0 days | Mon 4/6/26 | Mon 4/6/26 | 1986 | 1989 |  | Sean Buchanan
5898 | 1988 | Future Task |  |  | D682 | Bryan Sohayda |  | D682 - Hypercare Monthly Deliverable – March 2026 | 53 hrs | 21 days | Tue 4/7/26 | Tue 5/5/26
5899 | 1989 | Future Task |  |  | D682 | Bryan Sohayda | Create | Create D682 - Hypercare Monthly Deliverable – March 2026 | 4 hrs | 4 days | Tue 4/7/26 | Fri 4/10/26 | 1987 | 1990 |  | Bryan Sohayda
5900 | 1990 | Future Task |  |  | D682 | Bryan Sohayda | Submit | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Draft Submission | 0 hrs | 0 days | Fri 4/10/26 | Fri 4/10/26 | 1989 | 1991 |  | Joy Schneider,Bryan Sohayda
5901 | 1991 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 4/13/26 | Fri 4/17/26 | 1990 | 1992 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5902 | 1992 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Style Guide Review | 1 hr | 1 day | Mon 4/20/26 | Mon 4/20/26 | 1991 | 1993 |  | Dusti Kincl
5903 | 1993 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Final Collaborative Review | 16 hrs | 5 days | Tue 4/21/26 | Mon 4/27/26 | 1992 | 1994 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5904 | 1994 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Accenture QC | 4 hrs | 2 days | Tue 4/28/26 | Wed 4/29/26 | 1993 | 1995 |  | Joy Schneider
5905 | 1995 | Future Task |  |  | D682 | Bryan Sohayda | Submit | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Submit | 0 hrs | 0 days | Wed 4/29/26 | Wed 4/29/26 | 1994 | 1996 |  | Joy Schneider
5906 | 1996 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Department QC | 4 hrs | 1 day | Thu 4/30/26 | Thu 4/30/26 | 1995 | 1997 |  | Tommy Werner
5907 | 1997 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Contract Manager Review | 8 hrs | 3 days | Fri 5/1/26 | Tue 5/5/26 | 1996 | 1998 |  | Sean Buchanan
5908 | 1998 | Future Task |  |  | D682 | Bryan Sohayda | Accept | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Accept | 0 hrs | 0 days | Tue 5/5/26 | Tue 5/5/26 | 1997 | 2000 |  | Sean Buchanan
5909 | 1999 | Future Task |  |  | D683 | Bryan Sohayda |  | D683 - Hypercare Monthly Deliverable – April 2026 | 53 hrs | 21 days | Wed 5/6/26 | Thu 6/4/26
5910 | 2000 | Future Task |  |  | D683 | Bryan Sohayda | Create | Create D683 - Hypercare Monthly Deliverable – April 2026 | 4 hrs | 4 days | Wed 5/6/26 | Mon 5/11/26 | 1998 | 2001 |  | Bryan Sohayda
5911 | 2001 | Future Task |  |  | D683 | Bryan Sohayda | Submit | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Draft Submission | 0 hrs | 0 days | Mon 5/11/26 | Mon 5/11/26 | 2000 | 2002 |  | Joy Schneider,Bryan Sohayda
5912 | 2002 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Tue 5/12/26 | Mon 5/18/26 | 2001 | 2003 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5913 | 2003 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Style Guide Review | 1 hr | 1 day | Tue 5/19/26 | Tue 5/19/26 | 2002 | 2004 |  | Dusti Kincl
5914 | 2004 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Final Collaborative Review | 16 hrs | 5 days | Wed 5/20/26 | Wed 5/27/26 | 2003 | 2005 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5915 | 2005 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Accenture QC | 4 hrs | 2 days | Thu 5/28/26 | Fri 5/29/26 | 2004 | 2006 |  | Joy Schneider
5916 | 2006 | Future Task |  |  | D683 | Bryan Sohayda | Submit | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Submit | 0 hrs | 0 days | Fri 5/29/26 | Fri 5/29/26 | 2005 | 2007 |  | Joy Schneider
5917 | 2007 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Department QC | 4 hrs | 1 day | Mon 6/1/26 | Mon 6/1/26 | 2006 | 2008 |  | Tommy Werner
5918 | 2008 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 6/2/26 | Thu 6/4/26 | 2007 | 2009 |  | Sean Buchanan
5919 | 2009 | Future Task |  |  | D683 | Bryan Sohayda | Accept | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Accept | 0 hrs | 0 days | Thu 6/4/26 | Thu 6/4/26 | 2008 |  |  | Sean Buchanan
5851 | 2010 | Future Task | [5 empty] | Post-Implementation Support | 1,346 hrs | 633 days | Mon 1/13/25 | Thu 7/15/27
5488 | 2011 | Future Task |  |  | D665 | Bryan Sohayda |  | D665 - Updated Post-Implementation Support Plan | 154 hrs | 106 days | Mon 1/13/25 | Wed 6/11/25
5489 | 2012 | Future Task |  |  | D665 | Bryan Sohayda | Create | DED D665 - Updated Post-Implementation Support Plan - Create | 8 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 1942SS+5 days | 2013 |  | Bryan Sohayda
5490 | 2013 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DED D665 - Updated Post-Implementation Support Plan - Submit | 0 hrs | 0 days | Mon 1/27/25 | Mon 1/27/25 | 2012 | 2014 |  | Bryan Sohayda,Joy Schneider
5491 | 2014 | Future Task |  |  | D665 | Bryan Sohayda | Review | DED D665 - Updated Post-Implementation Support Plan - Collaborative Review | 16 hrs | 10 days | Tue 1/28/25 | Mon 2/10/25 | 2013 | 2015 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5492 | 2015 | Future Task |  |  | D665 | Bryan Sohayda | Approve | DED D665 - Updated Post-Implementation Support Plan - Approve | 0 hrs | 0 days | Mon 2/10/25 | Mon 2/10/25 | 2014 | 2016FS+14 days |  | Jimmy Cox
5493 | 2016 | Future Task |  |  | D665 | Bryan Sohayda | Create | Create Post Implementation Support Processes and Procedures | 20 hrs | 15 days | Mon 3/3/25 | Fri 3/21/25 | 2015FS+14 days | 2017 |  | Bryan Sohayda,Chetna Dewan
5494 | 2017 | Future Task |  |  | D665 | Bryan Sohayda | Create | Document Post Implementation Support Tools | 20 hrs | 10 days | Mon 3/24/25 | Fri 4/4/25 | 2016 | 2018 |  | Bryan Sohayda,Chetna Dewan
5495 | 2018 | Future Task |  |  | D665 | Bryan Sohayda | Create | Post-Implementation Support Resource Capacity and Skills | 20 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 2017 | 2019 |  | Bryan Sohayda,Chetna Dewan
5496 | 2019 | Future Task |  |  | D665 | Bryan Sohayda | Create | Full draft review pre-submission | 20 hrs | 20 days | Mon 4/21/25 | Fri 5/16/25 | 2018 | 2020 |  | Bryan Sohayda,Chetna Dewan
5497 | 2020 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DEL D665 - Updated Post-Implementation Support Plan - Draft Submission | 0 hrs | 0 days | Fri 5/16/25 | Fri 5/16/25 | 2019 | 2021 |  | Bryan Sohayda,Joy Schneider
5498 | 2021 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Pre-Submission Collaborative Review | 12 hrs | 5 days | Mon 5/19/25 | Fri 5/23/25 | 2020 | 2022 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5499 | 2022 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Style Guide Review | 1 hr | 1 day | Tue 5/27/25 | Tue 5/27/25 | 2021 | 2023 |  | Dusti Kincl
5500 | 2023 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Final Collaborative Review | 21 hrs | 5 days | Wed 5/28/25 | Tue 6/3/25 | 2022 | 2024 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5501 | 2024 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Accenture QC | 4 hrs | 2 days | Wed 6/4/25 | Thu 6/5/25 | 2023 | 2025 |  | Joy Schneider
5502 | 2025 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DEL D665 - Updated Post-Implementation Support Plan - Submit | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 2024 | 2026 |  | Joy Schneider
5503 | 2026 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Department QC | 4 hrs | 1 day | Fri 6/6/25 | Fri 6/6/25 | 2025 | 2027 |  | Tommy Werner,Gabriela Gibson
5504 | 2027 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Contract Manager Review | 8 hrs | 3 days | Mon 6/9/25 | Wed 6/11/25 | 2026 | 2028 |  | Sean Buchanan
5505 | 2028 | Future Task |  |  | D665 | Bryan Sohayda | Accept | DEL D665 - Updated Post-Implementation Support Plan - Accept | 0 hrs | 0 days | Wed 6/11/25 | Wed 6/11/25 | 2027 |  | 2025-06-01 | Sean Buchanan
5759 | 2029 | Future Task |  |  | D684 | Bryan Sohayda |  | D684 - Post-Implementation Support Monthly Deliverable – May 2026 | 122 hrs | 85 days | Mon 3/2/26 | Mon 6/29/26
5760 | 2030 | Future Task |  |  | D684-D691 | Bryan Sohayda | Create | DED Create - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 8 hrs | 5 days | Mon 3/2/26 | Fri 3/6/26 | 1 | 2031 |  | Bryan Sohayda
5761 | 2031 | Future Task |  |  | D684-D691 | Bryan Sohayda | Submit | DED Submit - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 0 hrs | 0 days | Fri 3/6/26 | Fri 3/6/26 | 2030 | 2032 |  | Bryan Sohayda,Joy Schneider
5762 | 2032 | Future Task |  |  | D684-D691 | Bryan Sohayda | Review | DED Collaborative Review & Accept - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 20 hrs | 10 days | Mon 3/9/26 | Fri 3/20/26 | 2031 | 2033 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5763 | 2033 | Future Task |  |  | D684 | Bryan Sohayda | Create | Create D684 - Post-Implementation Support Monthly Deliverable – May 2026 | 4 hrs | 4 days | Mon 6/1/26 | Thu 6/4/26 | 2032 | 2034 |  | Bryan Sohayda
5764 | 2034 | Future Task |  |  | D684 | Bryan Sohayda | Submit | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Draft Submission | 0 hrs | 0 days | Thu 6/4/26 | Thu 6/4/26 | 2033 | 2035 |  | Joy Schneider,Bryan Sohayda
5765 | 2035 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 6/5/26 | Thu 6/11/26 | 2034 | 2036 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5766 | 2036 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Style Guide Review | 8 hrs | 1 day | Fri 6/12/26 | Fri 6/12/26 | 2035 | 2037 |  | Dusti Kincl
5767 | 2037 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Final Collaborative Review | 20 hrs | 5 days | Mon 6/15/26 | Fri 6/19/26 | 2036 | 2038 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5768 | 2038 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Accenture QC | 16 hrs | 2 days | Mon 6/22/26 | Tue 6/23/26 | 2037 | 2039 |  | Joy Schneider
5769 | 2039 | Future Task |  |  | D684 | Bryan Sohayda | Submit | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Submit | 0 hrs | 0 days | Tue 6/23/26 | Tue 6/23/26 | 2038 | 2040 |  | Joy Schneider
5770 | 2040 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Department QC | 2 hrs | 1 day | Wed 6/24/26 | Wed 6/24/26 | 2039 | 2041 |  | Tommy Werner
5771 | 2041 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Contract Manager Review | 24 hrs | 3 days | Thu 6/25/26 | Mon 6/29/26 | 2040 | 2042 |  | Sean Buchanan
5772 | 2042 | Future Task |  |  | D684 | Bryan Sohayda | Accept | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Accept | 0 hrs | 0 days | Mon 6/29/26 | Mon 6/29/26 | 2041 | 2044 |  | Sean Buchanan
5773 | 2043 | Future Task |  |  | D685 | Bryan Sohayda |  | D685 - Post-Implementation Support Monthly Deliverable – June 2026 | 53 hrs | 21 days | Wed 7/1/26 | Thu 7/30/26
5774 | 2044 | Future Task |  |  | D685 | Bryan Sohayda | Create | Create D685 - Post-Implementation Support Monthly Deliverable – June 2026 | 4 hrs | 4 days | Wed 7/1/26 | Tue 7/7/26 | 2042 | 2045 |  | Bryan Sohayda
5775 | 2045 | Future Task |  |  | D685 | Bryan Sohayda | Submit | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Draft Submission | 0 hrs | 0 days | Tue 7/7/26 | Tue 7/7/26 | 2044 | 2046 |  | Joy Schneider,Bryan Sohayda
5776 | 2046 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Wed 7/8/26 | Tue 7/14/26 | 2045 | 2047 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5777 | 2047 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Style Guide Review | 1 hr | 1 day | Wed 7/15/26 | Wed 7/15/26 | 2046 | 2048 |  | Dusti Kincl
5778 | 2048 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Final Collaborative Review | 16 hrs | 5 days | Thu 7/16/26 | Wed 7/22/26 | 2047 | 2049 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5779 | 2049 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Accenture QC | 4 hrs | 2 days | Thu 7/23/26 | Fri 7/24/26 | 2048 | 2050 |  | Joy Schneider
5780 | 2050 | Future Task |  |  | D685 | Bryan Sohayda | Submit | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Submit | 0 hrs | 0 days | Fri 7/24/26 | Fri 7/24/26 | 2049 | 2051 |  | Joy Schneider
5781 | 2051 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Department QC | 4 hrs | 1 day | Mon 7/27/26 | Mon 7/27/26 | 2050 | 2052 |  | Tommy Werner
5782 | 2052 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 7/28/26 | Thu 7/30/26 | 2051 | 2053 |  | Sean Buchanan
5783 | 2053 | Future Task |  |  | D685 | Bryan Sohayda | Accept | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Accept | 0 hrs | 0 days | Thu 7/30/26 | Thu 7/30/26 | 2052 | 2055 |  | Sean Buchanan
5784 | 2054 | Future Task |  |  | D686 | Bryan Sohayda |  | D686 - Post-Implementation Support Monthly Deliverable – July 2026 | 53 hrs | 21 days | Mon 8/3/26 | Mon 8/31/26
5785 | 2055 | Future Task |  |  | D686 | Bryan Sohayda | Create | Create D686 - Post-Implementation Support Monthly Deliverable – July 2026 | 4 hrs | 4 days | Mon 8/3/26 | Thu 8/6/26 | 2053 | 2056 |  | Bryan Sohayda
5786 | 2056 | Future Task |  |  | D686 | Bryan Sohayda | Submit | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Draft Submission | 0 hrs | 0 days | Thu 8/6/26 | Thu 8/6/26 | 2055 | 2057 |  | Joy Schneider,Bryan Sohayda
5787 | 2057 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 8/7/26 | Thu 8/13/26 | 2056 | 2058 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5788 | 2058 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Style Guide Review | 1 hr | 1 day | Fri 8/14/26 | Fri 8/14/26 | 2057 | 2059 |  | Dusti Kincl
5789 | 2059 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Final Collaborative Review | 16 hrs | 5 days | Mon 8/17/26 | Fri 8/21/26 | 2058 | 2060 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5790 | 2060 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Accenture QC | 4 hrs | 2 days | Mon 8/24/26 | Tue 8/25/26 | 2059 | 2061 |  | Joy Schneider
5791 | 2061 | Future Task |  |  | D686 | Bryan Sohayda | Submit | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Submit | 0 hrs | 0 days | Tue 8/25/26 | Tue 8/25/26 | 2060 | 2062 |  | Joy Schneider
5792 | 2062 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Department QC | 4 hrs | 1 day | Wed 8/26/26 | Wed 8/26/26 | 2061 | 2063 |  | Tommy Werner
5793 | 2063 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 8/27/26 | Mon 8/31/26 | 2062 | 2064 |  | Sean Buchanan
5794 | 2064 | Future Task |  |  | D686 | Bryan Sohayda | Accept | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Accept | 0 hrs | 0 days | Mon 8/31/26 | Mon 8/31/26 | 2063 | 2066 |  | Sean Buchanan
5795 | 2065 | Future Task |  |  | D687 | Bryan Sohayda |  | D687 - Post-Implementation Support Monthly Deliverable – August 2026 | 53 hrs | 21 days | Tue 9/1/26 | Wed 9/30/26
5796 | 2066 | Future Task |  |  | D687 | Bryan Sohayda | Create | Create D687 - Post-Implementation Support Monthly Deliverable – August 2026 | 4 hrs | 4 days | Tue 9/1/26 | Fri 9/4/26 | 2064 | 2067 |  | Bryan Sohayda
5797 | 2067 | Future Task |  |  | D687 | Bryan Sohayda | Submit | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Draft Submission | 0 hrs | 0 days | Fri 9/4/26 | Fri 9/4/26 | 2066 | 2068 |  | Joy Schneider,Bryan Sohayda
5798 | 2068 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Tue 9/8/26 | Mon 9/14/26 | 2067 | 2069 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5799 | 2069 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Style Guide Review | 1 hr | 1 day | Tue 9/15/26 | Tue 9/15/26 | 2068 | 2070 |  | Dusti Kincl
5800 | 2070 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Final Collaborative Review | 16 hrs | 5 days | Wed 9/16/26 | Tue 9/22/26 | 2069 | 2071 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5801 | 2071 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Accenture QC | 4 hrs | 2 days | Wed 9/23/26 | Thu 9/24/26 | 2070 | 2072 |  | Joy Schneider
5802 | 2072 | Future Task |  |  | D687 | Bryan Sohayda | Submit | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Submit | 0 hrs | 0 days | Thu 9/24/26 | Thu 9/24/26 | 2071 | 2073 |  | Joy Schneider
5803 | 2073 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Department QC | 4 hrs | 1 day | Fri 9/25/26 | Fri 9/25/26 | 2072 | 2074 |  | Tommy Werner
5804 | 2074 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Contract Manager Review | 8 hrs | 3 days | Mon 9/28/26 | Wed 9/30/26 | 2073 | 2075 |  | Sean Buchanan
5805 | 2075 | Future Task |  |  | D687 | Bryan Sohayda | Accept | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Accept | 0 hrs | 0 days | Wed 9/30/26 | Wed 9/30/26 | 2074 | 2077 |  | Sean Buchanan
5806 | 2076 | Future Task |  |  | D688 | Bryan Sohayda |  | D688 - Post-Implementation Support Monthly Deliverable – September 2026 | 53 hrs | 21 days | Thu 10/1/26 | Thu 10/29/26
5807 | 2077 | Future Task |  |  | D688 | Bryan Sohayda | Create | Create D688 - Post-Implementation Support Monthly Deliverable – September 2026 | 4 hrs | 4 days | Thu 10/1/26 | Tue 10/6/26 | 2075 | 2078 |  | Bryan Sohayda
5808 | 2078 | Future Task |  |  | D688 | Bryan Sohayda | Submit | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Draft Submission | 0 hrs | 0 days | Tue 10/6/26 | Tue 10/6/26 | 2077 | 2079 |  | Joy Schneider,Bryan Sohayda
5809 | 2079 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Wed 10/7/26 | Tue 10/13/26 | 2078 | 2080 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5810 | 2080 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Style Guide Review | 1 hr | 1 day | Wed 10/14/26 | Wed 10/14/26 | 2079 | 2081 |  | Dusti Kincl
5811 | 2081 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Final Collaborative Review | 16 hrs | 5 days | Thu 10/15/26 | Wed 10/21/26 | 2080 | 2082 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5812 | 2082 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Accenture QC | 4 hrs | 2 days | Thu 10/22/26 | Fri 10/23/26 | 2081 | 2083 |  | Joy Schneider
5813 | 2083 | Future Task |  |  | D688 | Bryan Sohayda | Submit | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Submit | 0 hrs | 0 days | Fri 10/23/26 | Fri 10/23/26 | 2082 | 2084 |  | Joy Schneider
5814 | 2084 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Department QC | 4 hrs | 1 day | Mon 10/26/26 | Mon 10/26/26 | 2083 | 2085 |  | Tommy Werner
5815 | 2085 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 10/27/26 | Thu 10/29/26 | 2084 | 2086 |  | Sean Buchanan
5816 | 2086 | Future Task |  |  | D688 | Bryan Sohayda | Accept | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Accept | 0 hrs | 0 days | Thu 10/29/26 | Thu 10/29/26 | 2085 | 2088 |  | Sean Buchanan
5817 | 2087 | Future Task |  |  | D689 | Bryan Sohayda |  | D689 - Post-Implementation Support Monthly Deliverable – October 2026 | 53 hrs | 18 days | Mon 11/2/26 | Mon 11/30/26
5818 | 2088 | Future Task |  |  | D689 | Bryan Sohayda | Create | Create D689 - Post-Implementation Support Monthly Deliverable – October 2026 | 4 hrs | 4 days | Mon 11/2/26 | Thu 11/5/26 | 2086 | 2089 |  | Bryan Sohayda
5819 | 2089 | Future Task |  |  | D689 | Bryan Sohayda | Submit | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Draft Submission | 0 hrs | 0 days | Thu 11/5/26 | Thu 11/5/26 | 2088 | 2090 |  | Joy Schneider,Bryan Sohayda
5820 | 2090 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Pre-Submission Collaborative Review | 16 hrs | 4 days | Fri 11/6/26 | Thu 11/12/26 | 2089 | 2091 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5821 | 2091 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Style Guide Review | 1 hr | 1 day | Fri 11/13/26 | Fri 11/13/26 | 2090 | 2092 |  | Dusti Kincl
5822 | 2092 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Final Collaborative Review | 16 hrs | 3 days | Mon 11/16/26 | Wed 11/18/26 | 2091 | 2093 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5823 | 2093 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Accenture QC | 4 hrs | 2 days | Thu 11/19/26 | Fri 11/20/26 | 2092 | 2094 |  | Joy Schneider
5824 | 2094 | Future Task |  |  | D689 | Bryan Sohayda | Submit | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Submit | 0 hrs | 0 days | Fri 11/20/26 | Fri 11/20/26 | 2093 | 2095 |  | Joy Schneider
5825 | 2095 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Department QC | 4 hrs | 1 day | Mon 11/23/26 | Mon 11/23/26 | 2094 | 2096 |  | Tommy Werner
5826 | 2096 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 11/24/26 | Mon 11/30/26 | 2095 | 2097 |  | Sean Buchanan
5827 | 2097 | Future Task |  |  | D689 | Bryan Sohayda | Accept | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Accept | 0 hrs | 0 days | Mon 11/30/26 | Mon 11/30/26 | 2096 | 2099 |  | Sean Buchanan
5828 | 2098 | Future Task |  |  | D690 | Bryan Sohayda |  | D690 - Post-Implementation Support Monthly Deliverable – November 2026 | 53 hrs | 21 days | Tue 12/1/26 | Wed 12/30/26
5829 | 2099 | Future Task |  |  | D690 | Bryan Sohayda | Create | Create D690 - Post-Implementation Support Monthly Deliverable – November 2026 | 4 hrs | 4 days | Tue 12/1/26 | Fri 12/4/26 | 2097 | 2100 |  | Bryan Sohayda
5830 | 2100 | Future Task |  |  | D690 | Bryan Sohayda | Submit | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Draft Submission | 0 hrs | 0 days | Fri 12/4/26 | Fri 12/4/26 | 2099 | 2101 |  | Joy Schneider,Bryan Sohayda
5831 | 2101 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 12/7/26 | Fri 12/11/26 | 2100 | 2102 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5832 | 2102 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Style Guide Review | 1 hr | 1 day | Mon 12/14/26 | Mon 12/14/26 | 2101 | 2103 |  | Dusti Kincl
5833 | 2103 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Final Collaborative Review | 16 hrs | 5 days | Tue 12/15/26 | Mon 12/21/26 | 2102 | 2104 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5834 | 2104 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Accenture QC | 4 hrs | 2 days | Tue 12/22/26 | Wed 12/23/26 | 2103 | 2105 |  | Joy Schneider
5835 | 2105 | Future Task |  |  | D690 | Bryan Sohayda | Submit | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Submit | 0 hrs | 0 days | Wed 12/23/26 | Wed 12/23/26 | 2104 | 2106 |  | Joy Schneider
5836 | 2106 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Department QC | 4 hrs | 1 day | Thu 12/24/26 | Thu 12/24/26 | 2105 | 2107 |  | Tommy Werner
5837 | 2107 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Contract Manager Review | 8 hrs | 3 days | Mon 12/28/26 | Wed 12/30/26 | 2106 | 2108 |  | Sean Buchanan
5838 | 2108 | Future Task |  |  | D690 | Bryan Sohayda | Accept | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Accept | 0 hrs | 0 days | Wed 12/30/26 | Wed 12/30/26 | 2107 | 2110 |  | Sean Buchanan
5839 | 2109 | Future Task |  |  | D691 | Bryan Sohayda |  | D691 - Post-Implementation Support Monthly Deliverable – December 2026 | 53 hrs | 21 days | Mon 1/4/27 | Tue 2/2/27
5840 | 2110 | Future Task |  |  | D691 | Bryan Sohayda | Create | Create D691 - Post-Implementation Support Monthly Deliverable – December 2026 | 4 hrs | 4 days | Mon 1/4/27 | Thu 1/7/27 | 2108 | 2111 |  | Bryan Sohayda
5841 | 2111 | Future Task |  |  | D691 | Bryan Sohayda | Submit | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Draft Submission | 0 hrs | 0 days | Thu 1/7/27 | Thu 1/7/27 | 2110 | 2112 |  | Joy Schneider,Bryan Sohayda
5842 | 2112 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 1/8/27 | Thu 1/14/27 | 2111 | 2113 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5843 | 2113 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Style Guide Review | 1 hr | 1 day | Fri 1/15/27 | Fri 1/15/27 | 2112 | 2114 |  | Dusti Kincl
5844 | 2114 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Final Collaborative Review | 16 hrs | 5 days | Tue 1/19/27 | Mon 1/25/27 | 2113 | 2115 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5845 | 2115 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Accenture QC | 4 hrs | 2 days | Tue 1/26/27 | Wed 1/27/27 | 2114 | 2116 |  | Joy Schneider
5846 | 2116 | Future Task |  |  | D691 | Bryan Sohayda | Submit | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Submit | 0 hrs | 0 days | Wed 1/27/27 | Wed 1/27/27 | 2115 | 2117 |  | Joy Schneider
5847 | 2117 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Department QC | 4 hrs | 1 day | Thu 1/28/27 | Thu 1/28/27 | 2116 | 2118 |  | Tommy Werner
5848 | 2118 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Contract Manager Review | 8 hrs | 3 days | Fri 1/29/27 | Tue 2/2/27 | 2117 | 2119 |  | Sean Buchanan
5849 | 2119 | Future Task |  |  | D691 | Bryan Sohayda | Accept | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Accept | 0 hrs | 0 days | Tue 2/2/27 | Tue 2/2/27 | 2118 |  |  | Sean Buchanan
6704 | 2120 | Future Task |  |  | D692 | Stacey Terry |  | D692 - Tax Reporting Support CY 2026 (January 2027) | 179 hrs | 91 days | Mon 10/12/26 | Tue 2/23/27
6705 | 2121 | Future Task |  |  | D692 | Stacey Terry | Create | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Create | 8 hrs | 10 days | Mon 10/12/26 | Fri 10/23/26 | 1 | 2122 | 2026-11-12 | Stacey Terry
6706 | 2122 | Future Task |  |  | D692 | Stacey Terry | Submit | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Submit | 0 hrs | 0 days | Fri 10/23/26 | Fri 10/23/26 | 2121 | 2123 |  | Stacey Terry,Joy Schneider
6707 | 2123 | Future Task |  |  | D692 | Stacey Terry | Review | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Collaborative Review | 20 hrs | 10 days | Mon 10/26/26 | Fri 11/6/26 | 2122 | 2124 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
6708 | 2124 | Future Task |  |  | D692 | Stacey Terry | Approve | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Approve | 0 hrs | 0 days | Fri 11/6/26 | Fri 11/6/26 | 2123 | 2125FS+22 days |  | Jimmy Cox
6709 | 2125 | Future Task |  |  | D692 | Stacey Terry | Create | D692 - Create Tax Reporting Checklist (2026) | 36 hrs | 18 days | Mon 12/14/26 | Fri 1/8/27 | 2124FS+22 days | 2126FS-5 days,2127 |  | Stacey Terry,Yogesh Deshmukh
6710 | 2126 | Future Task |  |  | D692 | Stacey Terry | Create | D692 - Manage Year-end Checklist (2026) | 38 hrs | 19 days | Mon 1/4/27 | Fri 1/29/27 | 2125FS-5 days |  |  | Stacey Terry,Yogesh Deshmukh
6711 | 2127 | Future Task |  |  | D692 | Stacey Terry | Create | D692 - Create initial Year-end Checklist (2027) | 28 hrs | 14 days | Mon 1/11/27 | Fri 1/29/27 | 2125 | 2128 |  | Stacey Terry,Yogesh Deshmukh
6712 | 2128 | Future Task |  |  | D692 | Stacey Terry | Submit | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Draft Submission | 0 hrs | 0 days | Fri 1/29/27 | Fri 1/29/27 | 2127 | 2129 |  | Stacey Terry,Joy Schneider
6713 | 2129 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 2/1/27 | Fri 2/5/27 | 2128 | 2130 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson
6714 | 2130 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Style Guide Review | 1 hr | 1 day | Mon 2/8/27 | Mon 2/8/27 | 2129 | 2131 |  | Dusti Kincl
6715 | 2131 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Final Collaborative Review | 16 hrs | 5 days | Tue 2/9/27 | Mon 2/15/27 | 2130 | 2132 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson
6716 | 2132 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Accenture QC | 4 hrs | 2 days | Tue 2/16/27 | Wed 2/17/27 | 2131 | 2133 |  | Joy Schneider
6717 | 2133 | Future Task |  |  | D692 | Stacey Terry | Submit | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Submit | 0 hrs | 0 days | Wed 2/17/27 | Wed 2/17/27 | 2132 | 2134 |  | Joy Schneider
6718 | 2134 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Department QC | 4 hrs | 1 day | Thu 2/18/27 | Thu 2/18/27 | 2133 | 2135 |  | Tommy Werner,Gabriela Gibson
6719 | 2135 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Contract Manager Review | 8 hrs | 3 days | Fri 2/19/27 | Tue 2/23/27 | 2134 | 2136 |  | Sean Buchanan
6720 | 2136 | Future Task |  |  | D692 | Stacey Terry | Accept | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Accept | 0 hrs | 0 days | Tue 2/23/27 | Tue 2/23/27 | 2135 |  | 2027-02-01 | Sean Buchanan
6721 | 2137 | Future Task |  |  | D693 | Joy Schneider |  | D693 - Exit Transition Completion | 122 hrs | 136 days | Mon 1/4/27 | Thu 7/15/27
6722 | 2138 | Future Task |  |  | D693 | Joy Schneider | Create | DED D693 - Exit Transition Completion - Create | 6 hrs | 10 days | Mon 1/4/27 | Fri 1/15/27 | 2164 | 2139 |  | Joy Schneider,Matt Cole,Mary Punty
6723 | 2139 | Future Task |  |  | D693 | Joy Schneider | Submit | DED D693 - Exit Transition Completion - Submit | 0 hrs | 0 days | Fri 1/15/27 | Fri 1/15/27 | 2138 | 2140 |  | Joy Schneider
6724 | 2140 | Future Task |  |  | D693 | Joy Schneider | Review | DED D693 - Exit Transition Completion - Collaborative Review | 12 hrs | 10 days | Tue 1/19/27 | Mon 2/1/27 | 2139 | 2141 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6725 | 2141 | Future Task |  |  | D693 | Joy Schneider | Approve | DED D693 - Exit Transition Completion - Approve | 0 hrs | 0 days | Mon 2/1/27 | Mon 2/1/27 | 2140 | 2142FS+69 days |  | Jimmy Cox
6726 | 2142 | Future Task |  |  | D693 | Joy Schneider | Create | D693 - Review Status of Exit Transition Work Plan | 45 hrs | 15 days | Mon 5/10/27 | Fri 5/28/27 | 2141FS+69 days | 2143 |  | Joy Schneider,Matt Cole,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
6727 | 2143 | Future Task |  |  | D693 | Joy Schneider | Create | D693 - Obtain Department Sign Off | 30 hrs | 15 days | Tue 6/1/27 | Mon 6/21/27 | 2142 | 2144 |  | Sean Buchanan,Matt Cole
6728 | 2144 | Future Task |  |  | D693 | Joy Schneider | Submit | DEL D693 - Exit Transition Completion - Draft Submission | 0 hrs | 0 days | Mon 6/21/27 | Mon 6/21/27 | 2143 | 2145 |  | Joy Schneider
6729 | 2145 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Pre-Submission Collaborative Review | 6 hrs | 5 days | Tue 6/22/27 | Mon 6/28/27 | 2144 | 2146 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6730 | 2146 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Style Guide Review | 1 hr | 1 day | Tue 6/29/27 | Tue 6/29/27 | 2145 | 2147 |  | Dusti Kincl
6731 | 2147 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Final Collaborative Review | 6 hrs | 5 days | Wed 6/30/27 | Wed 7/7/27 | 2146 | 2148 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6732 | 2148 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Accenture QC | 4 hrs | 2 days | Thu 7/8/27 | Fri 7/9/27 | 2147 | 2149 |  | Joy Schneider
6733 | 2149 | Future Task |  |  | D693 | Joy Schneider | Submit | DEL D693 - Exit Transition Completion - Submit | 0 hrs | 0 days | Fri 7/9/27 | Fri 7/9/27 | 2148 | 2150 |  | Joy Schneider
6734 | 2150 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Department QC | 4 hrs | 1 day | Mon 7/12/27 | Mon 7/12/27 | 2149 | 2151 |  | Tommy Werner
6735 | 2151 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Contract Manager Review | 8 hrs | 3 days | Tue 7/13/27 | Thu 7/15/27 | 2150 | 2152 |  | Sean Buchanan
6736 | 2152 | Future Task |  |  | D693 | Joy Schneider | Accept | DEL D693 - Exit Transition Completion - Accept | 0 hrs | 0 days | Thu 7/15/27 | Thu 7/15/27 | 2151 |  | 2027-07-01 | Sean Buchanan
5655 | 2153 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 - Exit Transition Work Plan | 398 hrs | 121 days | Mon 7/6/26 | Mon 12/28/26
5656 | 2154 | Future Task |  |  | WP428 | Joy Schneider | Create | WPED WP428 - Exit Transition Work Plan - Create | 8 hrs | 10 days | Mon 7/6/26 | Fri 7/17/26 | 1 | 2155 |  | Joy Schneider
5657 | 2155 | Future Task |  |  | WP428 | Joy Schneider | Submit | WPED WP428 - Exit Transition Work Plan - Submit | 0 hrs | 0 days | Fri 7/17/26 | Fri 7/17/26 | 2154 | 2156 |  | Joy Schneider
5658 | 2156 | Future Task |  |  | WP428 | Joy Schneider | Review | WPED WP428 - Exit Transition Work Plan - Review | 16 hrs | 10 days | Mon 7/20/26 | Fri 7/31/26 | 2155 | 2157 |  | Joy Schneider,Jimmy Cox,Angie Robertson,Sean Buchanan
5659 | 2157 | Future Task |  |  | WP428 | Joy Schneider | Approve | WPED WP428 - Exit Transition Work Plan - Approve | 0 hrs | 0 days | Fri 7/31/26 | Fri 7/31/26 | 2156 | 2158FS+41 days |  | Jimmy Cox
5660 | 2158 | Future Task |  |  | WP428 | Joy Schneider | Create | WP428 - Develop Exit Transition Work Plan | 210 hrs | 15 days | Wed 9/30/26 | Tue 10/20/26 | 2157FS+41 days | 2159 |  | Joy Schneider,Stacey Terry,Manojkumar Gurjar,Matt Cole,Angie Robertson,Jimmy Cox,Francisca Li
5661 | 2159 | Future Task |  |  | WP428 | Joy Schneider | Create | WP428 - Determine Entry and Exit Criteria | 120 hrs | 15 days | Wed 10/21/26 | Tue 11/10/26 | 2158 | 2160 |  | Joy Schneider,Matt Cole,Angie Robertson,Jimmy Cox
5662 | 2160 | Future Task |  |  | WP428 | Joy Schneider | Create | WP428 - Review and Confirm Exit Transition Plan | 20 hrs | 15 days | Thu 11/12/26 | Fri 12/4/26 | 2159 | 2161 |  | Jimmy Cox,Angie Robertson,Joy Schneider
5663 | 2161 | Future Task |  |  | WP428 | Joy Schneider | Submit | WP WP428 - Exit Transition Work Plan - Submit | 0 hrs | 0 days | Fri 12/4/26 | Fri 12/4/26 | 2160 | 2162 |  | Joy Schneider
5664 | 2162 | Future Task |  |  | WP428 | Joy Schneider | Review | WP WP428 - Exit Transition Work Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 12/7/26 | Fri 12/18/26 | 2161 | 2163 |  | Joy Schneider,Jimmy Cox,Angie Robertson
5665 | 2163 | Future Task |  |  | WP428 | Joy Schneider | Review | WP WP428 - Exit Transition Work Plan - Final Review & Edits | 12 hrs | 5 days | Mon 12/21/26 | Mon 12/28/26 | 2162 | 2164 |  | Joy Schneider,Jimmy Cox,Angie Robertson
5666 | 2164 | Future Task |  |  | WP428 | Joy Schneider | Approve | WP WP428 - Exit Transition Work Plan - Approve | 0 hrs | 0 days | Mon 12/28/26 | Mon 12/28/26 | 2163 | 2138 |  | Jimmy Cox
4 | 2165 | Late | [5 empty] | Administrative Tasks | 2,020.33 hrs | 1174 days | Mon 5/1/23 | Tue 12/28/27
10 | 2166 | Late | [5 empty] | Administrative Activities | 1,256 hrs | 1152 days | Thu 6/1/23 | Tue 12/28/27
2063 | 2167 | Late |  |  |  | Tommy Werner |  | Budget | 308 hrs | 933 days | Thu 6/1/23 | Mon 2/15/27
2064 | 2168 | Late |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q1 | 14 hrs | 30 days | Thu 6/1/23 | Thu 7/13/23
2065 | 2169 | Late |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Thu 6/1/23 | Wed 6/14/23 |  | 2170,2194SS |  | Tommy Werner,Gabriela Gibson
2066 | 2170 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Thu 6/15/23 | Wed 6/28/23 | 2169 | 2171 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2067 | 2171 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Thu 6/29/23 | Thu 7/13/23 | 2170 | 2172 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2068 | 2172 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Thu 7/13/23 | Thu 7/13/23 | 2171 | 2175 |  | Tommy Werner
2069 | 2173 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q2 | 14 hrs | 30 days | Mon 7/3/23 | Mon 8/14/23
2070 | 2174 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 |  | 2175 |  | Tommy Werner,Gabriela Gibson
2071 | 2175 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 21742172 | 2176 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2072 | 2176 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 2175 | 2177 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2073 | 2177 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 2176 | 2179 |  | Tommy Werner
2074 | 2178 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q3 | 14 hrs | 30 days | Mon 10/2/23 | Mon 11/13/23
2075 | 2179 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 2177 | 2180 |  | Tommy Werner,Gabriela Gibson
2076 | 2180 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 2179 | 2181 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2077 | 2181 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 10/30/23 | Mon 11/13/23 | 2180 | 2182 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2078 | 2182 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 11/13/23 | Mon 11/13/23 | 2181 | 2184 |  | Tommy Werner
2079 | 2183 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q4 | 14 hrs | 30 days | Tue 1/2/24 | Tue 2/13/24
2080 | 2184 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Tue 1/2/24 | Tue 1/16/24 | 2182 | 2185 |  | Tommy Werner,Gabriela Gibson
2081 | 2185 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Wed 1/17/24 | Tue 1/30/24 | 2184 | 2186 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2082 | 2186 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Wed 1/31/24 | Tue 2/13/24 | 2185 | 2187 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2083 | 2187 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Tue 2/13/24 | Tue 2/13/24 | 2186 | 2199 |  | Tommy Werner
2084 | 2188 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 24-25 | 14 hrs | 30 days | Wed 5/1/24 | Wed 6/12/24
2085 | 2189 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 24-25 - Create | 4 hrs | 10 days | Wed 5/1/24 | Tue 5/14/24 | 2197 | 2190 |  | Tommy Werner,Gabriela Gibson
2086 | 2190 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 24-25 - Collaborative Review & Update | 4 hrs | 10 days | Wed 5/15/24 | Wed 5/29/24 | 2189 | 2191 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2087 | 2191 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 24-25 - Final Review & Edit | 6 hrs | 10 days | Thu 5/30/24 | Wed 6/12/24 | 2190 | 2192 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2088 | 2192 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 2191 | 2201 |  | Tommy Werner
2089 | 2193 | Late |  |  |  | Tommy Werner |  | Legislative Budget Request FY 24-25 | 14 hrs | 40 days | Thu 6/1/23 | Thu 7/27/23
2090 | 2194 | Late |  |  |  | Tommy Werner | Create | LBR FY 24-25 - Create | 4 hrs | 20 days | Thu 6/1/23 | Wed 6/28/23 | 2169SS | 2195 |  | Tommy Werner,Gabriela Gibson
2091 | 2195 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 24-25 - Collaborative Review & Update | 4 hrs | 10 days | Thu 6/29/23 | Thu 7/13/23 | 2194 | 2196 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2092 | 2196 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 24-25 - Final Review & Edit | 6 hrs | 10 days | Fri 7/14/23 | Thu 7/27/23 | 2195 | 2197 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2093 | 2197 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | Thu 7/27/23 | Thu 7/27/23 | 2196 | 22242189 |  | Tommy Werner
2094 | 2198 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q1 | 14 hrs | 30 days | Mon 6/3/24 | Mon 7/15/24
2095 | 2199 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 2187 | 22002204 |  | Tommy Werner,Gabriela Gibson
2096 | 2200 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 2199 | 2201 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2097 | 2201 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 22002192 | 2202 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2098 | 2202 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 7/15/24 | Mon 7/15/24 | 2201 | 2205 |  | Tommy Werner
2099 | 2203 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q2 | 14 hrs | 30 days | Mon 7/1/24 | Mon 8/12/24
2100 | 2204 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 2199 | 2205 |  | Tommy Werner,Gabriela Gibson
2101 | 2205 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Tue 7/16/24 | Mon 7/29/24 | 22042202 | 2206 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2102 | 2206 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Tue 7/30/24 | Mon 8/12/24 | 2205 | 2207 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2103 | 2207 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 8/12/24 | Mon 8/12/24 | 2206 | 2209 |  | Tommy Werner
2104 | 2208 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q3 | 14 hrs | 30 days | Tue 10/1/24 | Tue 11/12/24
2105 | 2209 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Tue 10/1/24 | Mon 10/14/24 | 2207 | 2210 |  | Tommy Werner,Gabriela Gibson
2106 | 2210 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Tue 10/15/24 | Mon 10/28/24 | 2209 | 2211 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2107 | 2211 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Tue 10/29/24 | Tue 11/12/24 | 2210 | 2212 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2108 | 2212 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Tue 11/12/24 | Tue 11/12/24 | 2211 | 2214 |  | Tommy Werner
2109 | 2213 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q4 | 14 hrs | 30 days | Thu 1/2/25 | Thu 2/13/25
2110 | 2214 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Thu 1/2/25 | Wed 1/15/25 | 2212 | 2215 |  | Tommy Werner,Gabriela Gibson
2111 | 2215 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Thu 1/16/25 | Thu 1/30/25 | 2214 | 2216 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2112 | 2216 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Fri 1/31/25 | Thu 2/13/25 | 2215 | 2217 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2113 | 2217 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Thu 2/13/25 | Thu 2/13/25 | 2216 | 2229 |  | Tommy Werner
2114 | 2218 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 25-26 | 14 hrs | 30 days | Thu 5/1/25 | Thu 6/12/25
2115 | 2219 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 25-26 - Create | 4 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 2227 | 2220 |  | Tommy Werner,Gabriela Gibson
2116 | 2220 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 25-26 - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/15/25 | Thu 5/29/25 | 2219 | 2221 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2117 | 2221 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 25-26 - Final Review & Edit | 6 hrs | 10 days | Fri 5/30/25 | Thu 6/12/25 | 2220 | 2222 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2118 | 2222 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | Thu 6/12/25 | Thu 6/12/25 | 2221 |  |  | Tommy Werner
2119 | 2223 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 25-26 | 14 hrs | 40 days | Mon 6/3/24 | Mon 7/29/24
2120 | 2224 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 25-26 - Create | 4 hrs | 20 days | Mon 6/3/24 | Fri 6/28/24 | 2197 | 2225 |  | Tommy Werner,Gabriela Gibson
2121 | 2225 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 25-26 - Collaborative Review & Update | 4 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 2224 | 2226 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2122 | 2226 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 25-26 - Final Review & Edit | 6 hrs | 10 days | Tue 7/16/24 | Mon 7/29/24 | 2225 | 2227 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2123 | 2227 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | Mon 7/29/24 | Mon 7/29/24 | 2226 | 22542219 |  | Tommy Werner
2124 | 2228 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q1 | 14 hrs | 30 days | Mon 6/2/25 | Mon 7/14/25
2125 | 2229 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Mon 6/2/25 | Fri 6/13/25 | 2217 | 22302234 |  | Tommy Werner,Gabriela Gibson
2126 | 2230 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Mon 6/16/25 | Fri 6/27/25 | 2229 | 2231 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2127 | 2231 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 6/30/25 | Mon 7/14/25 | 2230 | 2232 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2128 | 2232 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 7/14/25 | Mon 7/14/25 | 2231 | 2235 |  | Tommy Werner
2129 | 2233 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q2 | 14 hrs | 30 days | Tue 7/1/25 | Tue 8/12/25
2130 | 2234 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Tue 7/1/25 | Tue 7/15/25 | 2229 | 2235 |  | Tommy Werner,Gabriela Gibson
2131 | 2235 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Wed 7/16/25 | Tue 7/29/25 | 22342232 | 2236 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2132 | 2236 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Wed 7/30/25 | Tue 8/12/25 | 2235 | 2237 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2133 | 2237 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Tue 8/12/25 | Tue 8/12/25 | 2236 | 2239 |  | Tommy Werner
2134 | 2238 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q3 | 14 hrs | 30 days | Wed 10/1/25 | Wed 11/12/25
2135 | 2239 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Wed 10/1/25 | Tue 10/14/25 | 2237 | 2240 |  | Tommy Werner,Gabriela Gibson
2136 | 2240 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Wed 10/15/25 | Tue 10/28/25 | 2239 | 2241 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2137 | 2241 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Wed 10/29/25 | Wed 11/12/25 | 2240 | 2242 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2138 | 2242 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Wed 11/12/25 | Wed 11/12/25 | 2241 | 2244 |  | Tommy Werner
2139 | 2243 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q4 | 14 hrs | 30 days | Fri 1/2/26 | Fri 2/13/26
2140 | 2244 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Fri 1/2/26 | Thu 1/15/26 | 2242 | 2245 |  | Tommy Werner,Gabriela Gibson
2141 | 2245 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Fri 1/16/26 | Fri 1/30/26 | 2244 | 2246 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2142 | 2246 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 2/2/26 | Fri 2/13/26 | 2245 | 2247 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2143 | 2247 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Fri 2/13/26 | Fri 2/13/26 | 2246 | 2259 |  | Tommy Werner
2144 | 2248 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 26-27 | 14 hrs | 30 days | Fri 5/1/26 | Fri 6/12/26
2145 | 2249 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 26-27 - Create | 4 hrs | 10 days | Fri 5/1/26 | Thu 5/14/26 | 2257 | 2250 |  | Tommy Werner,Gabriela Gibson
2146 | 2250 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 26-27 - Collaborative Review & Update | 4 hrs | 10 days | Fri 5/15/26 | Fri 5/29/26 | 2249 | 2251 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2147 | 2251 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 26-27 - Final Review & Edit | 6 hrs | 10 days | Mon 6/1/26 | Fri 6/12/26 | 2250 | 2252 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2148 | 2252 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | Fri 6/12/26 | Fri 6/12/26 | 2251 |  |  | Tommy Werner
2149 | 2253 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 26-27 | 14 hrs | 40 days | Mon 6/2/25 | Mon 7/28/25
2150 | 2254 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 26-27 - Create | 4 hrs | 20 days | Mon 6/2/25 | Fri 6/27/25 | 2227 | 2255 |  | Tommy Werner,Gabriela Gibson
2151 | 2255 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 26-27 - Collaborative Review & Update | 4 hrs | 10 days | Mon 6/30/25 | Mon 7/14/25 | 2254 | 2256 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2152 | 2256 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 26-27 - Final Review & Edit | 6 hrs | 10 days | Tue 7/15/25 | Mon 7/28/25 | 2255 | 2257 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2153 | 2257 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | Mon 7/28/25 | Mon 7/28/25 | 2256 | 2249 |  | Tommy Werner
2154 | 2258 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q1 | 14 hrs | 30 days | Mon 6/1/26 | Mon 7/13/26
2155 | 2259 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Mon 6/1/26 | Fri 6/12/26 | 2247 | 22602264 |  | Tommy Werner,Gabriela Gibson
2156 | 2260 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Mon 6/15/26 | Fri 6/26/26 | 2259 | 2261 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2157 | 2261 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 6/29/26 | Mon 7/13/26 | 2260 | 2262 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2158 | 2262 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 7/13/26 | Mon 7/13/26 | 2261 | 2265 |  | Tommy Werner
2159 | 2263 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q2 | 14 hrs | 30 days | Wed 7/1/26 | Wed 8/12/26
2160 | 2264 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Wed 7/1/26 | Wed 7/15/26 | 2259 | 2265 |  | Tommy Werner,Gabriela Gibson
2161 | 2265 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Thu 7/16/26 | Wed 7/29/26 | 22642262 | 2266 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2162 | 2266 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Thu 7/30/26 | Wed 8/12/26 | 2265 | 2267 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2163 | 2267 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Wed 8/12/26 | Wed 8/12/26 | 2266 | 2269 |  | Tommy Werner
2164 | 2268 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q3 | 14 hrs | 30 days | Thu 10/1/26 | Thu 11/12/26
2165 | 2269 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Thu 10/1/26 | Wed 10/14/26 | 2267 | 2270 |  | Tommy Werner,Gabriela Gibson
2166 | 2270 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Thu 10/15/26 | Wed 10/28/26 | 2269 | 2271 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2167 | 2271 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Thu 10/29/26 | Thu 11/12/26 | 2270 | 2272 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2168 | 2272 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Thu 11/12/26 | Thu 11/12/26 | 2271 | 2274 |  | Tommy Werner
2169 | 2273 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q4 | 14 hrs | 30 days | Mon 1/4/27 | Mon 2/15/27
2170 | 2274 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Mon 1/4/27 | Fri 1/15/27 | 2272 | 2275 |  | Tommy Werner,Gabriela Gibson
2171 | 2275 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Tue 1/19/27 | Mon 2/1/27 | 2274 | 2276 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2172 | 2276 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Tue 2/2/27 | Mon 2/15/27 | 2275 | 2277 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2173 | 2277 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 2/15/27 | Mon 2/15/27 | 2276 |  |  | Tommy Werner
2174 | 2278 | Future Task | [5 empty] | Project Resources | 948 hrs | 1131 days | Fri 6/30/23 | Tue 12/28/27
2175 | 2279 | Future Task |  |  |  | Tommy Werner |  | Project Management Plan | 462 hrs | 1045 days | Wed 11/1/23 | Tue 12/28/27
2176 | 2280 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2023 | 54 hrs | 38 days | Wed 11/1/23 | Thu 12/28/23
2177 | 2281 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Wed 11/1/23 | Fri 12/1/23 |  | 2282 |  | Joy Schneider,Tommy Werner,Francisca Li,Jenifer Hartsfield,Gabriela Gibson
2178 | 2282 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Mon 12/4/23 | Fri 12/15/23 | 2281 | 2283 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2179 | 2283 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Mon 12/18/23 | Fri 12/22/23 | 2282 | 2284 |  | Jimmy Cox
2180 | 2284 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 4 hrs | 3 days | Tue 12/26/23 | Thu 12/28/23 | 2283 | 2286 |  | Tatiana Eubanks
2181 | 2285 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2024 | 51 hrs | 38 days | Fri 5/3/24 | Wed 6/26/24
2182 | 2286 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Fri 5/3/24 | Fri 5/31/24 | 2284 | 2287 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2183 | 2287 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 2286 | 2288 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2184 | 2288 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Mon 6/17/24 | Fri 6/21/24 | 2287 | 2289 |  | Jimmy Cox
2185 | 2289 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Mon 6/24/24 | Wed 6/26/24 | 2288 | 2291 |  | Tatiana Eubanks
2186 | 2290 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2024 | 51 hrs | 38 days | Mon 11/4/24 | Tue 12/31/24
2187 | 2291 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/4/24 | Wed 12/4/24 | 2289 | 2292 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2188 | 2292 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Thu 12/5/24 | Wed 12/18/24 | 2291 | 2293 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2189 | 2293 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Thu 12/19/24 | Thu 12/26/24 | 2292 | 2294 |  | Jimmy Cox
2190 | 2294 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Fri 12/27/24 | Tue 12/31/24 | 2293 | 2296 |  | Tatiana Eubanks
2191 | 2295 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2025 | 51 hrs | 38 days | Fri 5/2/25 | Wed 6/25/25
2192 | 2296 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Fri 5/2/25 | Fri 5/30/25 | 2294 | 2297 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2193 | 2297 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Mon 6/2/25 | Fri 6/13/25 | 2296 | 2298 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2194 | 2298 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Mon 6/16/25 | Fri 6/20/25 | 2297 | 2299 |  | Jimmy Cox
2195 | 2299 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Mon 6/23/25 | Wed 6/25/25 | 2298 | 2301 |  | Tatiana Eubanks
2196 | 2300 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2025 | 51 hrs | 38 days | Mon 11/3/25 | Tue 12/30/25
2197 | 2301 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/3/25 | Wed 12/3/25 | 2299 | 2302 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2198 | 2302 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Thu 12/4/25 | Wed 12/17/25 | 2301 | 2303 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2199 | 2303 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Thu 12/18/25 | Wed 12/24/25 | 2302 | 2304 |  | Jimmy Cox
2200 | 2304 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Fri 12/26/25 | Tue 12/30/25 | 2303 | 2306 |  | Tatiana Eubanks
2201 | 2305 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2026 | 51 hrs | 38 days | Fri 5/1/26 | Wed 6/24/26
2202 | 2306 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Fri 5/1/26 | Fri 5/29/26 | 2304 | 2307 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2203 | 2307 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Mon 6/1/26 | Fri 6/12/26 | 2306 | 2308 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2204 | 2308 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Mon 6/15/26 | Fri 6/19/26 | 2307 | 2309 |  | Jimmy Cox
2205 | 2309 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Mon 6/22/26 | Wed 6/24/26 | 2308 | 2311 |  | Tatiana Eubanks
2206 | 2310 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2026 | 51 hrs | 38 days | Mon 11/2/26 | Tue 12/29/26
2207 | 2311 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/2/26 | Wed 12/2/26 | 2309 | 2312 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2208 | 2312 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Thu 12/3/26 | Wed 12/16/26 | 2311 | 2313 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2209 | 2313 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Thu 12/17/26 | Wed 12/23/26 | 2312 | 2314 |  | Jimmy Cox
2210 | 2314 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Thu 12/24/26 | Tue 12/29/26 | 2313 | 2316 |  | Tatiana Eubanks
2211 | 2315 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2027 | 51 hrs | 38 days | Mon 5/3/27 | Thu 6/24/27
2212 | 2316 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 5/3/27 | Fri 5/28/27 | 2314 | 2317 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2213 | 2317 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Tue 6/1/27 | Mon 6/14/27 | 2316 | 2318 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2214 | 2318 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Tue 6/15/27 | Mon 6/21/27 | 2317 | 2319 |  | Jimmy Cox
2215 | 2319 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Tue 6/22/27 | Thu 6/24/27 | 2318 | 2321 |  | Tatiana Eubanks
2216 | 2320 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2027 | 51 hrs | 38 days | Mon 11/1/27 | Tue 12/28/27
2217 | 2321 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/1/27 | Wed 12/1/27 | 2319 | 2322 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2218 | 2322 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Thu 12/2/27 | Wed 12/15/27 | 2321 | 2323 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2219 | 2323 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Thu 12/16/27 | Wed 12/22/27 | 2322 | 2324 |  | Jimmy Cox
2220 | 2324 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Thu 12/23/27 | Tue 12/28/27 | 2323 |  |  | Tatiana Eubanks
2221 | 2325 | Future Task |  |  |  | Dusti Kincl |  | Florida PALM Style Guide | 104 hrs | 910 days | Wed 11/1/23 | Mon 6/14/27
2222 | 2326 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 23-24 | 13 hrs | 30 days | Wed 11/1/23 | Fri 12/15/23
2223 | 2327 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Wed 11/1/23 | Wed 11/22/23 |  | 2328 |  | Tatiana Eubanks,Elizabeth Gabert
2224 | 2328 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Mon 11/27/23 | Fri 12/8/23 | 2327 | 2329 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2225 | 2329 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Mon 12/11/23 | Fri 12/15/23 | 2328 | 2331 |  | Jimmy Cox
2226 | 2330 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 23-24 | 13 hrs | 30 days | Wed 5/1/24 | Wed 6/12/24
2227 | 2331 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Wed 5/1/24 | Tue 5/21/24 | 2329 | 2332 |  | Tatiana Eubanks,Elizabeth Gabert
2228 | 2332 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Wed 5/22/24 | Wed 6/5/24 | 2331 | 2333 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2229 | 2333 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Thu 6/6/24 | Wed 6/12/24 | 2332 | 2335 |  | Jimmy Cox
2230 | 2334 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 24-25 | 13 hrs | 30 days | Mon 11/4/24 | Wed 12/18/24
2231 | 2335 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 11/4/24 | Mon 11/25/24 | 2333 | 2336 |  | Tatiana Eubanks,Elizabeth Gabert
2232 | 2336 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Tue 11/26/24 | Wed 12/11/24 | 2335 | 2337 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2233 | 2337 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Thu 12/12/24 | Wed 12/18/24 | 2336 | 2339 |  | Jimmy Cox
2234 | 2338 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 24-25 | 13 hrs | 30 days | Thu 5/1/25 | Thu 6/12/25
2235 | 2339 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Thu 5/1/25 | Wed 5/21/25 | 2337 | 2340 |  | Tatiana Eubanks,Elizabeth Gabert
2236 | 2340 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/22/25 | Thu 6/5/25 | 2339 | 2341 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2237 | 2341 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Fri 6/6/25 | Thu 6/12/25 | 2340 | 2343 |  | Jimmy Cox
2238 | 2342 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 25-26 | 13 hrs | 30 days | Mon 11/3/25 | Wed 12/17/25
2239 | 2343 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 11/3/25 | Mon 11/24/25 | 2341 | 2344 |  | Tatiana Eubanks,Elizabeth Gabert
2240 | 2344 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Tue 11/25/25 | Wed 12/10/25 | 2343 | 2345 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2241 | 2345 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Thu 12/11/25 | Wed 12/17/25 | 2344 | 2347 |  | Jimmy Cox
2242 | 2346 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 25-26 | 13 hrs | 30 days | Mon 4/6/26 | Fri 5/15/26
2243 | 2347 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 4/6/26 | Fri 4/24/26 | 2345 | 2348 |  | Tatiana Eubanks,Elizabeth Gabert
2244 | 2348 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Mon 4/27/26 | Fri 5/8/26 | 2347 | 2349 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2245 | 2349 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Mon 5/11/26 | Fri 5/15/26 | 2348 | 2351 |  | Jimmy Cox
2246 | 2350 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 26-27 | 13 hrs | 30 days | Mon 11/2/26 | Wed 12/16/26
2247 | 2351 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 11/2/26 | Mon 11/23/26 | 2349 | 2352 |  | Tatiana Eubanks,Elizabeth Gabert
2248 | 2352 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Tue 11/24/26 | Wed 12/9/26 | 2351 | 2353 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2249 | 2353 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Thu 12/10/26 | Wed 12/16/26 | 2352 | 2355 |  | Jimmy Cox
2250 | 2354 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 26-27 | 13 hrs | 30 days | Mon 5/3/27 | Mon 6/14/27
2251 | 2355 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 5/3/27 | Fri 5/21/27 | 2353 | 2356 |  | Tatiana Eubanks,Elizabeth Gabert
2252 | 2356 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Mon 5/24/27 | Mon 6/7/27 | 2355 | 2357 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2253 | 2357 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Tue 6/8/27 | Mon 6/14/27 | 2356 |  |  | Jimmy Cox
2254 | 2358 | Future Task | [5 empty] | Project Team Orientation Guide | 238 hrs | 252 days | Fri 6/30/23 | Fri 6/28/24
6683 | 2359 | Future Task |  |  | WP401 | Joy Schneider |  | WP401 - Project Orientation Guide | 88 hrs | 61 days | Fri 6/30/23 | Tue 9/26/23
6684 | 2360 | Future Task |  |  | WP401 | Joy Schneider | Create | WPED WP401 - Project Orientation Guide - Create | 8 hrs | 10 days | Fri 6/30/23 | Fri 7/14/23 | 32 | 2361 |  | Joy Schneider
6685 | 2361 | Future Task |  |  | WP401 | Joy Schneider | Submit | WPED WP401 - Project Orientation Guide - Submit | 0 hrs | 0 days | Fri 7/14/23 | Fri 7/14/23 | 2360 | 2362 |  | Joy Schneider
6686 | 2362 | Future Task |  |  | WP401 | Joy Schneider | Review | WPED WP401 - Project Orientation Guide - Review | 16 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 | 2361 | 2363 |  | Joy Schneider,Jimmy Cox,Angie Robertson,Sean Buchanan
6687 | 2363 | Future Task |  |  | WP401 | Joy Schneider | Approve | WPED WP401 - Project Orientation Guide - Approve | 0 hrs | 0 days | Fri 7/28/23 | Fri 7/28/23 | 2362 | 2364FS+11 days |  | Jimmy Cox
6688 | 2364 | Future Task |  |  | WP401 | Joy Schneider | Create | WP401 - Update Project Team Orientation Guide | 10 hrs | 5 days | Tue 8/15/23 | Mon 8/21/23 | 2363FS+11 days | 2365 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
6689 | 2365 | Future Task |  |  | WP401 | Joy Schneider | Create | WP401 - Project Team Orientation Guide - Collaborative Review & Update | 10 hrs | 5 days | Tue 8/22/23 | Mon 8/28/23 | 2364 | 2366 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
6690 | 2366 | Future Task |  |  | WP401 | Joy Schneider | Create | WP401 - Project Team Orientation Guide - Final Review & Update | 20 hrs | 5 days | Tue 8/29/23 | Tue 9/5/23 | 2365 | 2367 |  | Angie Robertson[25%],Jimmy Cox[25%]
6691 | 2367 | Future Task |  |  | WP401 | Joy Schneider | Submit | WP WP401 - Project Orientation Guide - Submit | 0 hrs | 0 days | Tue 9/5/23 | Tue 9/5/23 | 2366 | 2368 |  | Joy Schneider
6692 | 2368 | Future Task |  |  | WP401 | Joy Schneider | Review | WP WP401 - Project Orientation Guide - Collaborative Review & Update | 12 hrs | 10 days | Wed 9/6/23 | Tue 9/19/23 | 2367 | 2369 |  | Joy Schneider,Jimmy Cox,Angie Robertson
6693 | 2369 | Future Task |  |  | WP401 | Joy Schneider | Review | WP WP401 - Project Orientation Guide - Final Review & Edits | 12 hrs | 5 days | Wed 9/20/23 | Tue 9/26/23 | 2368 | 2370 |  | Joy Schneider,Jimmy Cox,Angie Robertson
6694 | 2370 | Future Task |  |  | WP401 | Joy Schneider | Approve | WP WP401 - Project Orientation Guide - Approve | 0 hrs | 0 days | Tue 9/26/23 | Tue 9/26/23 | 2369 | 2372FS-6 days | 2023-10-01 | Jimmy Cox
2255 | 2371 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q1 | 30 hrs | 15 days | Tue 9/19/23 | Mon 10/9/23
2257 | 2372 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Tue 9/19/23 | Mon 9/25/23 | 2370FS-6 days | 2373 |  | Jenifer Hartsfield,Gabriela Gibson
2258 | 2373 | Future Task |  |  |  | Julian Gotreaux | Review | FPO - Collaborative Review & Update | 10 hrs | 5 days | Tue 9/26/23 | Mon 10/2/23 | 2372 | 2374 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2259 | 2374 | Future Task |  |  |  | Julian Gotreaux | Review | FPO - Final Review & Update | 10 hrs | 5 days | Tue 10/3/23 | Mon 10/9/23 | 2373 | 2376 |  | Angie Robertson,Jimmy Cox
2260 | 2375 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q2 | 40 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23
2261 | 2376 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | Fri 12/1/23 | Thu 12/7/23 | 2374 | 2377 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2262 | 2377 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Fri 12/8/23 | Thu 12/14/23 | 2376 | 2378 |  | Jenifer Hartsfield,Gabriela Gibson
2263 | 2378 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review & Update | 10 hrs | 5 days | Fri 12/15/23 | Thu 12/21/23 | 2377 | 2379 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2264 | 2379 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review & Update | 10 hrs | 5 days | Fri 12/22/23 | Fri 12/29/23 | 2378 | 2381 |  | Angie Robertson,Jimmy Cox
2265 | 2380 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q3 | 40 hrs | 20 days | Fri 3/1/24 | Thu 3/28/24
2266 | 2381 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 2379 | 2382 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2267 | 2382 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Fri 3/8/24 | Thu 3/14/24 | 2381 | 2383 |  | Jenifer Hartsfield,Gabriela Gibson
2268 | 2383 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review & Update | 10 hrs | 5 days | Fri 3/15/24 | Thu 3/21/24 | 2382 | 2384 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2269 | 2384 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review & Update | 10 hrs | 5 days | Fri 3/22/24 | Thu 3/28/24 | 2383 | 2386 |  | Angie Robertson,Jimmy Cox
2270 | 2385 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q4 | 40 hrs | 20 days | Mon 6/3/24 | Fri 6/28/24
2271 | 2386 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | Mon 6/3/24 | Fri 6/7/24 | 2384 | 2387 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2272 | 2387 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Mon 6/10/24 | Fri 6/14/24 | 2386 | 2388 |  | Jenifer Hartsfield,Gabriela Gibson
2273 | 2388 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review & Update | 10 hrs | 5 days | Mon 6/17/24 | Fri 6/21/24 | 2387 | 2389 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2274 | 2389 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review & Update | 10 hrs | 5 days | Mon 6/24/24 | Fri 6/28/24 | 2388 |  |  | Angie Robertson,Jimmy Cox
2275 | 2390 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 23-24 | 28 hrs | 134 days | Mon 7/17/23 | Mon 1/29/24
2276 | 2391 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 23-24 Q1 | 4 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 |  | 23922393 |  | Gabriela Gibson[5%]
2277 | 2392 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 23-24 Q3 | 4 hrs | 10 days | Tue 1/16/24 | Mon 1/29/24 | 2391 | 2399 |  | Gabriela Gibson
2278 | 2393 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 23-24 | 4 hrs | 10 days | Tue 8/15/23 | Mon 8/28/23 | 2391 | 2394 |  | Jenifer Hartsfield
2279 | 2394 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 23-24 | 4 hrs | 10 days | Fri 9/15/23 | Thu 9/28/23 | 2393 | 2395 |  | Tommy Werner
2280 | 2395 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 23-24 | 4 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 2394 | 2396 |  | Gabriela Gibson
2281 | 2396 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 23-24 | 4 hrs | 10 days | Wed 11/15/23 | Thu 11/30/23 | 2395 | 2397 |  | Tommy Werner
2282 | 2397 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 23-24 | 4 hrs | 10 days | Fri 12/15/23 | Fri 12/29/23 | 2396 | 2401 |  | Tommy Werner
2283 | 2398 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 24-25 | 28 hrs | 136 days | Mon 7/15/24 | Wed 1/29/25
2284 | 2399 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 24-25 Q1 | 4 hrs | 10 days | Mon 7/15/24 | Fri 7/26/24 | 2392 | 2400 |  | Gabriela Gibson
2285 | 2400 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 24-25 Q3 | 4 hrs | 10 days | Wed 1/15/25 | Wed 1/29/25 | 2399 | 2407 |  | Gabriela Gibson
2286 | 2401 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 24-25 | 4 hrs | 10 days | Thu 8/15/24 | Wed 8/28/24 | 2397 | 2402 |  | Jenifer Hartsfield
2287 | 2402 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 24-25 | 4 hrs | 10 days | Mon 9/16/24 | Fri 9/27/24 | 2401 | 2403 |  | Tommy Werner
2288 | 2403 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 24-25 | 4 hrs | 10 days | Tue 10/15/24 | Mon 10/28/24 | 2402 | 2404 |  | Gabriela Gibson
2289 | 2404 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 24-25 | 4 hrs | 10 days | Fri 11/15/24 | Mon 12/2/24 | 2403 | 2405 |  | Tommy Werner
2290 | 2405 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 24-25 | 4 hrs | 10 days | Mon 12/16/24 | Mon 12/30/24 | 2404 | 2409 |  | Tommy Werner
2291 | 2406 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 25-26 | 28 hrs | 136 days | Tue 7/15/25 | Thu 1/29/26
2292 | 2407 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 25-26 Q1 | 4 hrs | 10 days | Tue 7/15/25 | Mon 7/28/25 | 2400 | 2408 |  | Gabriela Gibson
2293 | 2408 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 25-26 Q3 | 4 hrs | 10 days | Thu 1/15/26 | Thu 1/29/26 | 2407 | 2415 |  | Gabriela Gibson
2294 | 2409 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 25-26 | 4 hrs | 10 days | Fri 8/15/25 | Thu 8/28/25 | 2405 | 2410 |  | Jenifer Hartsfield
2295 | 2410 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 25-26 | 4 hrs | 10 days | Mon 9/15/25 | Fri 9/26/25 | 2409 | 2411 |  | Tommy Werner
2296 | 2411 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 25-26 | 4 hrs | 10 days | Wed 10/15/25 | Tue 10/28/25 | 2410 | 2412 |  | Gabriela Gibson
2297 | 2412 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 25-26 | 4 hrs | 10 days | Mon 11/17/25 | Tue 12/2/25 | 2411 | 2413 |  | Tommy Werner
2298 | 2413 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 25-26 | 4 hrs | 10 days | Mon 12/15/25 | Mon 12/29/25 | 2412 | 2417 |  | Tommy Werner
2299 | 2414 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 26-27 | 28 hrs | 136 days | Wed 7/15/26 | Fri 1/29/27
2300 | 2415 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 26-27 Q1 | 4 hrs | 10 days | Wed 7/15/26 | Tue 7/28/26 | 2408 | 2416 |  | Gabriela Gibson
2301 | 2416 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 26-27 Q3 | 4 hrs | 10 days | Fri 1/15/27 | Fri 1/29/27 | 2415 |  |  | Gabriela Gibson
2302 | 2417 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 26-27 | 4 hrs | 10 days | Mon 8/17/26 | Fri 8/28/26 | 2413 | 2418 |  | Jenifer Hartsfield
2303 | 2418 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 26-27 | 4 hrs | 10 days | Tue 9/15/26 | Mon 9/28/26 | 2417 | 2419 |  | Tommy Werner
2304 | 2419 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 26-27 | 4 hrs | 10 days | Thu 10/15/26 | Wed 10/28/26 | 2418 | 2420 |  | Gabriela Gibson
2305 | 2420 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 26-27 | 4 hrs | 10 days | Mon 11/16/26 | Tue 12/1/26 | 2419 | 2421 |  | Tommy Werner
2306 | 2421 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 26-27 | 4 hrs | 10 days | Tue 12/15/26 | Tue 12/29/26 | 2420 |  |  | Tommy Werner
2307 | 2422 | Future Task |  |  |  | Julian Gotreaux |  | Access Control | 32 hrs | 965 days | Tue 8/15/23 | Mon 6/14/27
2308 | 2423 | Future Task |  |  |  | Julian Gotreaux |  | SharePoint Access Control | 32 hrs | 965 days | Tue 8/15/23 | Mon 6/14/27
2309 | 2424 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q1 | 2 hrs | 10 days | Tue 8/15/23 | Mon 8/28/23 |  | 2425 |  | Jenifer Hartsfield,Gabriela Gibson
2310 | 2425 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q2 | 2 hrs | 10 days | Wed 11/15/23 | Thu 11/30/23 | 2424 | 2426 |  | Jenifer Hartsfield,Gabriela Gibson
2311 | 2426 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q3 | 2 hrs | 10 days | Thu 2/15/24 | Wed 2/28/24 | 2425 | 2427 |  | Jenifer Hartsfield,Gabriela Gibson
2312 | 2427 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q4 | 2 hrs | 10 days | Wed 5/15/24 | Wed 5/29/24 | 2426 | 2428 |  | Jenifer Hartsfield,Gabriela Gibson
2313 | 2428 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q1 | 2 hrs | 10 days | Thu 8/15/24 | Wed 8/28/24 | 2427 | 2429 |  | Jenifer Hartsfield,Gabriela Gibson
2314 | 2429 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q2 | 2 hrs | 10 days | Fri 11/15/24 | Mon 12/2/24 | 2428 | 2430 |  | Jenifer Hartsfield,Gabriela Gibson
2315 | 2430 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q3 | 2 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 2429 | 2431 |  | Jenifer Hartsfield,Gabriela Gibson
2316 | 2431 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q4 | 2 hrs | 10 days | Thu 5/15/25 | Thu 5/29/25 | 2430 | 2432 |  | Jenifer Hartsfield,Gabriela Gibson
2317 | 2432 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q1 | 2 hrs | 10 days | Fri 8/15/25 | Thu 8/28/25 | 2431 | 2433 |  | Jenifer Hartsfield,Gabriela Gibson
2318 | 2433 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q2 | 2 hrs | 10 days | Mon 11/17/25 | Tue 12/2/25 | 2432 | 2434 |  | Jenifer Hartsfield,Gabriela Gibson
2319 | 2434 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q3 | 2 hrs | 10 days | Mon 2/16/26 | Fri 2/27/26 | 2433 | 2435 |  | Jenifer Hartsfield,Gabriela Gibson
2320 | 2435 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q4 | 2 hrs | 10 days | Fri 5/15/26 | Fri 5/29/26 | 2434 | 2436 |  | Jenifer Hartsfield,Gabriela Gibson
2321 | 2436 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q1 | 2 hrs | 10 days | Mon 8/17/26 | Fri 8/28/26 | 2435 | 2437 |  | Jenifer Hartsfield,Gabriela Gibson
2322 | 2437 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q2 | 2 hrs | 10 days | Mon 11/16/26 | Tue 12/1/26 | 2436 | 2438 |  | Jenifer Hartsfield,Gabriela Gibson
2323 | 2438 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q3 | 2 hrs | 10 days | Mon 2/15/27 | Fri 2/26/27 | 2437 | 2439 |  | Jenifer Hartsfield,Gabriela Gibson
2324 | 2439 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q4 | 2 hrs | 20 days | Mon 5/17/27 | Mon 6/14/27 | 2438 |  |  | Jenifer Hartsfield,Gabriela Gibson
2365 | 2440 | Late | [5 empty] | Proviso Requirements | 764.33 hrs | 1091 days | Mon 5/1/23 | Thu 8/26/27
2366 | 2441 | Future Task |  |  |  | Tommy Werner |  | Monthly Status Reporting | 112 hrs | 241 days | Tue 8/1/23 | Mon 7/15/24
2367 | 2442 | Future Task |  |  |  | Tommy Werner |  | July 2023 Monthly Status Reporting | 16 hrs | 11 days | Tue 8/1/23 | Tue 8/15/23
2368 | 2443 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | Tue 8/1/23 | Thu 8/10/23 |  | 2444SS,2445SS,2446SS |  | Tommy Werner,Gabriela Gibson
2369 | 2444 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 2443SS | 2447 |  | Tommy Werner,Joy Schneider,Francisca Li,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2370 | 2445 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | Tue 8/1/23 | Thu 8/10/23 | 2443SS | 2447 |  | Tommy Werner,Jenifer Hartsfield
2371 | 2446 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 2443SS | 2447 |  | Dusti Kincl,Nikki Klein
2372 | 2447 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Tue 8/15/23 | Tue 8/15/23 | 244624442445 | 2449 |  | Dusti Kincl,Jimmy Cox
2373 | 2448 | Future Task |  |  |  | Tommy Werner |  | August 2023 Monthly Status Reporting | 16 hrs | 10 days | Fri 9/1/23 | Fri 9/15/23
2374 | 2449 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 2447 | 2450SS,2451SS,2452SS,2453 |  | Tommy Werner,Gabriela Gibson
2375 | 2450 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Fri 9/1/23 | Thu 9/14/23 | 2449SS | 2453 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2376 | 2451 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 2449SS | 2453 |  | Tommy Werner,Jenifer Hartsfield
2377 | 2452 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Fri 9/1/23 | Thu 9/14/23 | 2449SS | 2453 |  | Dusti Kincl,Nikki Klein
2378 | 2453 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 9/15/23 | Fri 9/15/23 | 2449245024512450 |  |  | Dusti Kincl,Jimmy Cox
2385 | 2454 | Future Task |  |  |  | Tommy Werner |  | October 2023 Monthly Status Reporting | 16 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23
2386 | 2455 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | Wed 11/1/23 | Thu 11/9/23 |  | 2456SS,2457SS,2458SS,2459 |  | Tommy Werner,Gabriela Gibson
2387 | 2456 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Wed 11/1/23 | Tue 11/14/23 | 2455SS | 2459 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2388 | 2457 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | Wed 11/1/23 | Thu 11/9/23 | 2455SS | 2459 |  | Tommy Werner,Jenifer Hartsfield
2389 | 2458 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Wed 11/1/23 | Tue 11/14/23 | 2455SS | 2459 |  | Dusti Kincl,Nikki Klein
2390 | 2459 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Wed 11/15/23 | Wed 11/15/23 | 2455245624572450 |  |  | Dusti Kincl,Jimmy Cox
2397 | 2460 | Future Task |  |  |  | Tommy Werner |  | December 2023 Monthly Status Reporting | 16 hrs | 9 days | Tue 1/2/24 | Fri 1/12/24
2398 | 2461 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | Tue 1/2/24 | Tue 1/9/24 |  | 2462SS,2465,2463SS,2464SS |  | Tommy Werner,Gabriela Gibson
2399 | 2462 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 8 days | Tue 1/2/24 | Thu 1/11/24 | 2461SS | 2465 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2400 | 2463 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | Tue 1/2/24 | Tue 1/9/24 | 2461SS | 2465 |  | Tommy Werner,Jenifer Hartsfield
2401 | 2464 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 8 days | Tue 1/2/24 | Thu 1/11/24 | 2461SS | 2465 |  | Dusti Kincl,Nikki Klein
2402 | 2465 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 1/12/24 | Fri 1/12/24 | 2461246224632460 |  |  | Dusti Kincl,Jimmy Cox
2409 | 2466 | Future Task |  |  |  | Tommy Werner |  | February 2024 Monthly Status Reporting | 16 hrs | 11 days | Fri 3/1/24 | Fri 3/15/24
2410 | 2467 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | Fri 3/1/24 | Fri 3/8/24 |  | 2468SS,2469SS,2470SS,2471 |  | Tommy Werner,Gabriela Gibson
2411 | 2468 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 2467SS | 2471 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2412 | 2469 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | Fri 3/1/24 | Fri 3/8/24 | 2467SS | 2471 |  | Tommy Werner,Jenifer Hartsfield
2413 | 2470 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 2467SS | 2471 |  | Dusti Kincl,Nikki Klein
2414 | 2471 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 3/15/24 | Fri 3/15/24 | 2467246824692470 |  |  | Dusti Kincl,Jimmy Cox
2421 | 2472 | Future Task |  |  |  | Tommy Werner |  | April 2024 Monthly Status Reporting | 16 hrs | 11 days | Wed 5/1/24 | Wed 5/15/24
2422 | 2473 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | Wed 5/1/24 | Fri 5/10/24 |  | 2474SS,2475SS,2476SS,2477 |  | Tommy Werner,Gabriela Gibson
2423 | 2474 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Wed 5/1/24 | Tue 5/14/24 | 2473SS | 2477 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2424 | 2475 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | Wed 5/1/24 | Fri 5/10/24 | 2473SS | 2477 |  | Tommy Werner,Jenifer Hartsfield
2425 | 2476 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Wed 5/1/24 | Tue 5/14/24 | 2473SS | 2477 |  | Dusti Kincl,Nikki Klein
2426 | 2477 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Wed 5/15/24 | Wed 5/15/24 | 2473247424752470 |  |  | Dusti Kincl,Jimmy Cox
2433 | 2478 | Future Task |  |  |  | Tommy Werner |  | June 2024 Monthly Status Reporting | 16 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24
2434 | 2479 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | Mon 7/1/24 | Wed 7/10/24 |  | 2480SS,2481SS,2482SS |  | Tommy Werner,Gabriela Gibson
2435 | 2480 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 2479SS | 2483 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2436 | 2481 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | Mon 7/1/24 | Wed 7/10/24 | 2479SS | 2483 |  | Tommy Werner,Jenifer Hartsfield
2437 | 2482 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 2479SS | 2483 |  | Dusti Kincl,Nikki Klein
2438 | 2483 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Mon 7/15/24 | Mon 7/15/24 | 248024812482 |  |  | Dusti Kincl,Jimmy Cox
9 | 2484 | Late | [5 empty] | Monthly Performance Reporting | 520.33 hrs | 1091 days | Mon 5/1/23 | Thu 8/26/27
6232 | 2485 | Complete |  |  | D219 | Joy Schneider |  | D219 - Monthly Performance Report (April 2023) | 10.33 hrs | 24 days | Mon 5/1/23 | Fri 6/2/23
6364 | 2486 | Complete |  |  | D219 | Joy Schneider | Create | D219 - Create April 2023 Monthly Performance Report | 2.33 hrs | 7 days | Mon 5/1/23 | Tue 5/9/23 | 1 | 2487 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6233 | 2487 | Complete |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 5/10/23 | Wed 5/10/23 | 2486 | 2488 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6234 | 2488 | Complete |  |  | D219 | Joy Schneider | Submit | DEL D219 - Monthly Performance Report (April 2023) - Submit | 0 hrs | 0 days | Wed 5/10/23 | Wed 5/10/23 | 2487 | 2489 |  | Joy Schneider
6235 | 2489 | Complete |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Department QC | 2 hrs | 14 days | Thu 5/11/23 | Wed 5/31/23 | 2488 | 2490 |  | Gabriela Gibson
6236 | 2490 | Complete |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Contract Manager Review | 2 hrs | 2 days | Thu 6/1/23 | Fri 6/2/23 | 2489 | 2491 |  | Sean Buchanan
6237 | 2491 | Complete |  |  | D219 | Joy Schneider | Accept | DEL D219 - Monthly Performance Report (April 2023) - Accept | 0 hrs | 0 days | Fri 6/2/23 | Fri 6/2/23 | 2490 | 2493FS-2 days |  | Sean Buchanan
6238 | 2492 | Late |  |  | D225 | Joy Schneider |  | D225 - Monthly Performance Report (May 2023) | 10 hrs | 19 days | Thu 6/1/23 | Tue 6/27/23
6365 | 2493 | Late |  |  | D225 | Joy Schneider | Create | D225 - Create May 2023 Monthly Performance Report | 3 hrs | 9 days | Thu 6/1/23 | Tue 6/13/23 | 2491FS-2 days | 2494 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6239 | 2494 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 6/14/23 | Wed 6/14/23 | 2493 | 2495 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6240 | 2495 | Future Task |  |  | D225 | Joy Schneider | Submit | DEL D225 - Monthly Performance Report (May 2023) - Submit | 0 hrs | 0 days | Wed 6/14/23 | Wed 6/14/23 | 2494 | 2496 |  | Joy Schneider
6241 | 2496 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Department QC | 1 hr | 7 days | Thu 6/15/23 | Fri 6/23/23 | 2495 | 2497 |  | Gabriela Gibson
6242 | 2497 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Contract Manager Review | 2 hrs | 2 days | Mon 6/26/23 | Tue 6/27/23 | 2496 | 2498 |  | Sean Buchanan
6243 | 2498 | Future Task |  |  | D225 | Joy Schneider | Accept | DEL D225 - Monthly Performance Report (May 2023) - Accept | 0 hrs | 0 days | Tue 6/27/23 | Tue 6/27/23 | 2497 | 2500 |  | Sean Buchanan
6244 | 2499 | Future Task |  |  | D232 | Joy Schneider |  | D232 - Monthly Performance Report (June 2023) | 10 hrs | 19 days | Mon 7/3/23 | Fri 7/28/23
6366 | 2500 | Future Task |  |  | D232 | Joy Schneider | Create | D232 - Create June 2023 Monthly Performance Report | 3 hrs | 9 days | Mon 7/3/23 | Fri 7/14/23 | 2498 | 2501 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6245 | 2501 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 7/17/23 | Mon 7/17/23 | 2500 | 2502 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6246 | 2502 | Future Task |  |  | D232 | Joy Schneider | Submit | DEL D232 - Monthly Performance Report (June 2023) - Submit | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 2501 | 2503 |  | Joy Schneider
6247 | 2503 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Department QC | 1 hr | 7 days | Tue 7/18/23 | Wed 7/26/23 | 2502 | 2504 |  | Gabriela Gibson
6248 | 2504 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Contract Manager Review | 2 hrs | 2 days | Thu 7/27/23 | Fri 7/28/23 | 2503 | 2505 |  | Sean Buchanan
6249 | 2505 | Future Task |  |  | D232 | Joy Schneider | Accept | DEL D232 - Monthly Performance Report (June 2023) - Accept | 0 hrs | 0 days | Fri 7/28/23 | Fri 7/28/23 | 2504 | 2507 |  | Sean Buchanan
6250 | 2506 | Future Task |  |  | D239 | Joy Schneider |  | D239 - Monthly Performance Report (July 2023) | 10 hrs | 19 days | Tue 8/1/23 | Fri 8/25/23
6367 | 2507 | Future Task |  |  | D239 | Joy Schneider | Create | D239 - Create July 2023 Monthly Performance Report | 3 hrs | 9 days | Tue 8/1/23 | Fri 8/11/23 | 2505 | 2508 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6251 | 2508 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 8/14/23 | Mon 8/14/23 | 2507 | 2509 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6252 | 2509 | Future Task |  |  | D239 | Joy Schneider | Submit | DEL D239 - Monthly Performance Report (July 2023) - Submit | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 2508 | 2510 |  | Joy Schneider
6253 | 2510 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Department QC | 1 hr | 7 days | Tue 8/15/23 | Wed 8/23/23 | 2509 | 2511 |  | Gabriela Gibson
6254 | 2511 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Contract Manager Review | 2 hrs | 2 days | Thu 8/24/23 | Fri 8/25/23 | 2510 | 2512 |  | Sean Buchanan
6255 | 2512 | Future Task |  |  | D239 | Joy Schneider | Accept | DEL D239 - Monthly Performance Report (July 2023) - Accept | 0 hrs | 0 days | Fri 8/25/23 | Fri 8/25/23 | 2511 | 2514 |  | Sean Buchanan
6256 | 2513 | Future Task |  |  | D249 | Joy Schneider |  | D249 - Monthly Performance Report (August 2023) | 10 hrs | 19 days | Fri 9/1/23 | Thu 9/28/23
6368 | 2514 | Future Task |  |  | D249 | Joy Schneider | Create | D249 - Create August 2023 Monthly Performance Report | 3 hrs | 9 days | Fri 9/1/23 | Thu 9/14/23 | 2512 | 2515 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6257 | 2515 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 9/15/23 | Fri 9/15/23 | 2514 | 2516 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6258 | 2516 | Future Task |  |  | D249 | Joy Schneider | Submit | DEL D249 - Monthly Performance Report (August 2023) - Submit | 0 hrs | 0 days | Fri 9/15/23 | Fri 9/15/23 | 2515 | 2517 |  | Joy Schneider
6259 | 2517 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Department QC | 1 hr | 7 days | Mon 9/18/23 | Tue 9/26/23 | 2516 | 2518 |  | Gabriela Gibson
6260 | 2518 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 9/27/23 | Thu 9/28/23 | 2517 | 2519 |  | Sean Buchanan
6261 | 2519 | Future Task |  |  | D249 | Joy Schneider | Accept | DEL D249 - Monthly Performance Report (August 2023) - Accept | 0 hrs | 0 days | Thu 9/28/23 | Thu 9/28/23 | 2518 | 2521 |  | Sean Buchanan
6262 | 2520 | Future Task |  |  | D253 | Joy Schneider |  | D253 - Monthly Performance Report (September 2023) | 10 hrs | 19 days | Mon 10/2/23 | Thu 10/26/23
6369 | 2521 | Future Task |  |  | D253 | Joy Schneider | Create | D253 - Create September 2023 Monthly Performance Report | 3 hrs | 9 days | Mon 10/2/23 | Thu 10/12/23 | 2519 | 2522 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6263 | 2522 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 10/13/23 | Fri 10/13/23 | 2521 | 2523 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6264 | 2523 | Future Task |  |  | D253 | Joy Schneider | Submit | DEL D253 - Monthly Performance Report (September 2023) - Submit | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 2522 | 2524 |  | Joy Schneider
6265 | 2524 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Department QC | 1 hr | 7 days | Mon 10/16/23 | Tue 10/24/23 | 2523 | 2525 |  | Gabriela Gibson
6266 | 2525 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 10/25/23 | Thu 10/26/23 | 2524 | 2526 |  | Sean Buchanan
6267 | 2526 | Future Task |  |  | D253 | Joy Schneider | Accept | DEL D253 - Monthly Performance Report (September 2023) - Accept | 0 hrs | 0 days | Thu 10/26/23 | Thu 10/26/23 | 2525 | 2528 |  | Sean Buchanan
6268 | 2527 | Future Task |  |  | D257 | Joy Schneider |  | D257 - Monthly Performance Report (October 2023) | 10 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23
6370 | 2528 | Future Task |  |  | D257 | Joy Schneider | Create | D257 - Create October 2023 Monthly Performance Report | 3 hrs | 9 days | Wed 11/1/23 | Tue 11/14/23 | 2526 | 2529 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6269 | 2529 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 11/15/23 | Wed 11/15/23 | 2528 | 2530 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6270 | 2530 | Future Task |  |  | D257 | Joy Schneider | Submit | DEL D257 - Monthly Performance Report (October 2023) - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 2529 | 2531 |  | Joy Schneider
6271 | 2531 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Department QC | 1 hr | 7 days | Thu 11/16/23 | Tue 11/28/23 | 2530 | 2532 |  | Gabriela Gibson
6272 | 2532 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 11/29/23 | Thu 11/30/23 | 2531 | 2533 |  | Sean Buchanan
6273 | 2533 | Future Task |  |  | D257 | Joy Schneider | Accept | DEL D257 - Monthly Performance Report (October 2023) - Accept | 0 hrs | 0 days | Thu 11/30/23 | Thu 11/30/23 | 2532 | 2535 |  | Sean Buchanan
6274 | 2534 | Future Task |  |  | D261 | Joy Schneider |  | D261 - Monthly Performance Report (November 2023) | 10 hrs | 19 days | Fri 12/1/23 | Thu 12/28/23
6385 | 2535 | Future Task |  |  | D261 | Joy Schneider | Create | D261 - Create November 2023 Monthly Performance Report | 3 hrs | 9 days | Fri 12/1/23 | Wed 12/13/23 | 2533 | 2536 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6275 | 2536 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 12/14/23 | Thu 12/14/23 | 2535 | 2537 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6276 | 2537 | Future Task |  |  | D261 | Joy Schneider | Submit | DEL D261 - Monthly Performance Report (November 2023) - Submit | 0 hrs | 0 days | Thu 12/14/23 | Thu 12/14/23 | 2536 | 2538 |  | Joy Schneider
6277 | 2538 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Department QC | 1 hr | 7 days | Fri 12/15/23 | Tue 12/26/23 | 2537 | 2539 |  | Gabriela Gibson
6278 | 2539 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 12/27/23 | Thu 12/28/23 | 2538 | 2540 |  | Sean Buchanan
6279 | 2540 | Future Task |  |  | D261 | Joy Schneider | Accept | DEL D261 - Monthly Performance Report (November 2023) - Accept | 0 hrs | 0 days | Thu 12/28/23 | Thu 12/28/23 | 2539 | 2542 |  | Sean Buchanan
6280 | 2541 | Future Task |  |  | D267 | Joy Schneider |  | D267 - Monthly Performance Report (December 2023) | 10 hrs | 19 days | Tue 1/2/24 | Mon 1/29/24
6384 | 2542 | Future Task |  |  | D267 | Joy Schneider | Create | D267 - Create December 2023 Monthly Performance Report | 3 hrs | 9 days | Tue 1/2/24 | Fri 1/12/24 | 2540 | 2543 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6281 | 2543 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 1/16/24 | Tue 1/16/24 | 2542 | 2544 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6282 | 2544 | Future Task |  |  | D267 | Joy Schneider | Submit | DEL D267 - Monthly Performance Report (December 2023) - Submit | 0 hrs | 0 days | Tue 1/16/24 | Tue 1/16/24 | 2543 | 2545 |  | Joy Schneider
6283 | 2545 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Department QC | 1 hr | 7 days | Wed 1/17/24 | Thu 1/25/24 | 2544 | 2546 |  | Gabriela Gibson
6284 | 2546 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Contract Manager Review | 2 hrs | 2 days | Fri 1/26/24 | Mon 1/29/24 | 2545 | 2547 |  | Sean Buchanan
6285 | 2547 | Future Task |  |  | D267 | Joy Schneider | Accept | DEL D267 - Monthly Performance Report (December 2023) - Accept | 0 hrs | 0 days | Mon 1/29/24 | Mon 1/29/24 | 2546 | 2549 |  | Sean Buchanan
6286 | 2548 | Future Task |  |  | D277 | Joy Schneider |  | D277 - Monthly Performance Report (January 2024) | 10 hrs | 19 days | Thu 2/1/24 | Tue 2/27/24
6383 | 2549 | Future Task |  |  | D277 | Joy Schneider | Create | D277 - Create January 2024 Monthly Performance Report | 3 hrs | 9 days | Thu 2/1/24 | Tue 2/13/24 | 2547 | 2550 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6287 | 2550 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 2/14/24 | Wed 2/14/24 | 2549 | 2551 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6288 | 2551 | Future Task |  |  | D277 | Joy Schneider | Submit | DEL D277 - Monthly Performance Report (January 2024) - Submit | 0 hrs | 0 days | Wed 2/14/24 | Wed 2/14/24 | 2550 | 2552 |  | Joy Schneider
6289 | 2552 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Department QC | 1 hr | 7 days | Thu 2/15/24 | Fri 2/23/24 | 2551 | 2553 |  | Gabriela Gibson
6290 | 2553 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Contract Manager Review | 2 hrs | 2 days | Mon 2/26/24 | Tue 2/27/24 | 2552 | 2554 |  | Sean Buchanan
6291 | 2554 | Future Task |  |  | D277 | Joy Schneider | Accept | DEL D277 - Monthly Performance Report (January 2024) - Accept | 0 hrs | 0 days | Tue 2/27/24 | Tue 2/27/24 | 2553 | 2556 |  | Sean Buchanan
6292 | 2555 | Future Task |  |  | D284 | Joy Schneider |  | D284 - Monthly Performance Report (February 2024) | 10 hrs | 19 days | Fri 3/1/24 | Wed 3/27/24
6382 | 2556 | Future Task |  |  | D284 | Joy Schneider | Create | D284 - Create February 2024 Monthly Performance Report | 3 hrs | 9 days | Fri 3/1/24 | Wed 3/13/24 | 2554 | 2557 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6293 | 2557 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 3/14/24 | Thu 3/14/24 | 2556 | 2558 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6294 | 2558 | Future Task |  |  | D284 | Joy Schneider | Submit | DEL D284 - Monthly Performance Report (February 2024) - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 2557 | 2559 |  | Joy Schneider
6295 | 2559 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Department QC | 1 hr | 7 days | Fri 3/15/24 | Mon 3/25/24 | 2558 | 2560 |  | Gabriela Gibson
6296 | 2560 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Contract Manager Review | 2 hrs | 2 days | Tue 3/26/24 | Wed 3/27/24 | 2559 | 2561 |  | Sean Buchanan
6297 | 2561 | Future Task |  |  | D284 | Joy Schneider | Accept | DEL D284 - Monthly Performance Report (February 2024) - Accept | 0 hrs | 0 days | Wed 3/27/24 | Wed 3/27/24 | 2560 | 2563 |  | Sean Buchanan
6298 | 2562 | Future Task |  |  | D288 | Joy Schneider |  | D288 - Monthly Performance Report (March 2024) | 10 hrs | 19 days | Mon 4/1/24 | Thu 4/25/24
6381 | 2563 | Future Task |  |  | D288 | Joy Schneider | Create | D288 - Create March 2024 Monthly Performance Report | 3 hrs | 9 days | Mon 4/1/24 | Thu 4/11/24 | 2561 | 2564 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6299 | 2564 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 4/12/24 | Fri 4/12/24 | 2563 | 2565 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6300 | 2565 | Future Task |  |  | D288 | Joy Schneider | Submit | DEL D288 - Monthly Performance Report (March 2024) - Submit | 0 hrs | 0 days | Fri 4/12/24 | Fri 4/12/24 | 2564 | 2566 |  | Joy Schneider
6301 | 2566 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Department QC | 1 hr | 7 days | Mon 4/15/24 | Tue 4/23/24 | 2565 | 2567 |  | Gabriela Gibson
6302 | 2567 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Contract Manager Review | 2 hrs | 2 days | Wed 4/24/24 | Thu 4/25/24 | 2566 | 2568 |  | Sean Buchanan
6303 | 2568 | Future Task |  |  | D288 | Joy Schneider | Accept | DEL D288 - Monthly Performance Report (March 2024) - Accept | 0 hrs | 0 days | Thu 4/25/24 | Thu 4/25/24 | 2567 | 2570 |  | Sean Buchanan
6304 | 2569 | Future Task |  |  | D296 | Joy Schneider |  | D296 - Monthly Performance Report (April 2024) | 10 hrs | 19 days | Wed 5/1/24 | Tue 5/28/24
6380 | 2570 | Future Task |  |  | D296 | Joy Schneider | Create | D296 - Create April 2024 Monthly Performance Report | 3 hrs | 9 days | Wed 5/1/24 | Mon 5/13/24 | 2568 | 2571 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6305 | 2571 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 5/14/24 | Tue 5/14/24 | 2570 | 2572 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6306 | 2572 | Future Task |  |  | D296 | Joy Schneider | Submit | DEL D296 - Monthly Performance Report (April 2024) - Submit | 0 hrs | 0 days | Tue 5/14/24 | Tue 5/14/24 | 2571 | 2573 |  | Joy Schneider
6307 | 2573 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Department QC | 1 hr | 7 days | Wed 5/15/24 | Thu 5/23/24 | 2572 | 2574 |  | Gabriela Gibson
6308 | 2574 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Contract Manager Review | 2 hrs | 2 days | Fri 5/24/24 | Tue 5/28/24 | 2573 | 2575 |  | Sean Buchanan
6309 | 2575 | Future Task |  |  | D296 | Joy Schneider | Accept | DEL D296 - Monthly Performance Report (April 2024) - Accept | 0 hrs | 0 days | Tue 5/28/24 | Tue 5/28/24 | 2574 | 2577 |  | Sean Buchanan
6310 | 2576 | Future Task |  |  | D302 | Joy Schneider |  | D302 - Monthly Performance Report (May 2024) | 10 hrs | 19 days | Mon 6/3/24 | Thu 6/27/24
6379 | 2577 | Future Task |  |  | D302 | Joy Schneider | Create | D302 - Create May 2024 Monthly Performance Report | 3 hrs | 9 days | Mon 6/3/24 | Thu 6/13/24 | 2575 | 2578 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6311 | 2578 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 6/14/24 | Fri 6/14/24 | 2577 | 2579 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6312 | 2579 | Future Task |  |  | D302 | Joy Schneider | Submit | DEL D302 - Monthly Performance Report (May 2024) - Submit | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 2578 | 2580 |  | Joy Schneider
6313 | 2580 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Department QC | 1 hr | 7 days | Mon 6/17/24 | Tue 6/25/24 | 2579 | 2581 |  | Gabriela Gibson
6314 | 2581 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Contract Manager Review | 2 hrs | 2 days | Wed 6/26/24 | Thu 6/27/24 | 2580 | 2582 |  | Sean Buchanan
6315 | 2582 | Future Task |  |  | D302 | Joy Schneider | Accept | DEL D302 - Monthly Performance Report (May 2024) - Accept | 0 hrs | 0 days | Thu 6/27/24 | Thu 6/27/24 | 2581 | 2584 |  | Sean Buchanan
6316 | 2583 | Future Task |  |  | D311 | Joy Schneider |  | D311 - Monthly Performance Report (June 2024) | 10 hrs | 19 days | Mon 7/1/24 | Fri 7/26/24
6378 | 2584 | Future Task |  |  | D311 | Joy Schneider | Create | D311 - Create June 2024 Monthly Performance Report | 3 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 2582 | 2585 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6317 | 2585 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 7/15/24 | Mon 7/15/24 | 2584 | 2586 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6318 | 2586 | Future Task |  |  | D311 | Joy Schneider | Submit | DEL D311 - Monthly Performance Report (June 2024) - Submit | 0 hrs | 0 days | Mon 7/15/24 | Mon 7/15/24 | 2585 | 2587 |  | Joy Schneider
6319 | 2587 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Department QC | 1 hr | 7 days | Tue 7/16/24 | Wed 7/24/24 | 2586 | 2588 |  | Gabriela Gibson
6320 | 2588 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Contract Manager Review | 2 hrs | 2 days | Thu 7/25/24 | Fri 7/26/24 | 2587 | 2589 |  | Sean Buchanan
6321 | 2589 | Future Task |  |  | D311 | Joy Schneider | Accept | DEL D311 - Monthly Performance Report (June 2024) - Accept | 0 hrs | 0 days | Fri 7/26/24 | Fri 7/26/24 | 2588 | 2591 |  | Sean Buchanan
6322 | 2590 | Future Task |  |  | D319 | Joy Schneider |  | D319 - Monthly Performance Report (July 2024) | 10 hrs | 19 days | Thu 8/1/24 | Tue 8/27/24
6377 | 2591 | Future Task |  |  | D319 | Joy Schneider | Create | D319 - Create July 2024 Monthly Performance Report | 3 hrs | 9 days | Thu 8/1/24 | Tue 8/13/24 | 2589 | 2592 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6323 | 2592 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 8/14/24 | Wed 8/14/24 | 2591 | 2593 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6324 | 2593 | Future Task |  |  | D319 | Joy Schneider | Submit | DEL D319 - Monthly Performance Report (July 2024) - Submit | 0 hrs | 0 days | Wed 8/14/24 | Wed 8/14/24 | 2592 | 2594 |  | Joy Schneider
6325 | 2594 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Department QC | 1 hr | 7 days | Thu 8/15/24 | Fri 8/23/24 | 2593 | 2595 |  | Gabriela Gibson
6326 | 2595 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Contract Manager Review | 2 hrs | 2 days | Mon 8/26/24 | Tue 8/27/24 | 2594 | 2596 |  | Sean Buchanan
6327 | 2596 | Future Task |  |  | D319 | Joy Schneider | Accept | DEL D319 - Monthly Performance Report (July 2024) - Accept | 0 hrs | 0 days | Tue 8/27/24 | Tue 8/27/24 | 2595 | 2598 |  | Sean Buchanan
6328 | 2597 | Future Task |  |  | D328 | Joy Schneider |  | D328 - Monthly Performance Report (August 2024) | 10 hrs | 19 days | Tue 9/3/24 | Fri 9/27/24
6376 | 2598 | Future Task |  |  | D328 | Joy Schneider | Create | D328 - Create August 2024 Monthly Performance Report | 3 hrs | 9 days | Tue 9/3/24 | Fri 9/13/24 | 2596 | 2599 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6329 | 2599 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 9/16/24 | Mon 9/16/24 | 2598 | 2600 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6330 | 2600 | Future Task |  |  | D328 | Joy Schneider | Submit | DEL D328 - Monthly Performance Report (August 2024) - Submit | 0 hrs | 0 days | Mon 9/16/24 | Mon 9/16/24 | 2599 | 2601 |  | Joy Schneider
6331 | 2601 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Department QC | 1 hr | 7 days | Tue 9/17/24 | Wed 9/25/24 | 2600 | 2602 |  | Gabriela Gibson
6332 | 2602 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Contract Manager Review | 2 hrs | 2 days | Thu 9/26/24 | Fri 9/27/24 | 2601 | 2603 |  | Sean Buchanan
6333 | 2603 | Future Task |  |  | D328 | Joy Schneider | Accept | DEL D328 - Monthly Performance Report (August 2024) - Accept | 0 hrs | 0 days | Fri 9/27/24 | Fri 9/27/24 | 2602 | 2605 |  | Sean Buchanan
6334 | 2604 | Future Task |  |  | D334 | Joy Schneider |  | D334 - Monthly Performance Report (September 2024) | 10 hrs | 19 days | Tue 10/1/24 | Fri 10/25/24
6375 | 2605 | Future Task |  |  | D334 | Joy Schneider | Create | D334 - Create September 2024 Monthly Performance Report | 3 hrs | 9 days | Tue 10/1/24 | Fri 10/11/24 | 2603 | 2606 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6335 | 2606 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 10/14/24 | Mon 10/14/24 | 2605 | 2607 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6336 | 2607 | Future Task |  |  | D334 | Joy Schneider | Submit | DEL D334 - Monthly Performance Report (September 2024) - Submit | 0 hrs | 0 days | Mon 10/14/24 | Mon 10/14/24 | 2606 | 2608 |  | Joy Schneider
6337 | 2608 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Department QC | 1 hr | 7 days | Tue 10/15/24 | Wed 10/23/24 | 2607 | 2609 |  | Gabriela Gibson
6338 | 2609 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Contract Manager Review | 2 hrs | 2 days | Thu 10/24/24 | Fri 10/25/24 | 2608 | 2610 |  | Sean Buchanan
6339 | 2610 | Future Task |  |  | D334 | Joy Schneider | Accept | DEL D334 - Monthly Performance Report (September 2024) - Accept | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 2609 | 2612 |  | Sean Buchanan
6340 | 2611 | Future Task |  |  | D342 | Joy Schneider |  | D342 - Monthly Performance Report (October 2024) | 10 hrs | 19 days | Fri 11/1/24 | Mon 12/2/24
6374 | 2612 | Future Task |  |  | D342 | Joy Schneider | Create | D342 - Create October 2024 Monthly Performance Report | 3 hrs | 9 days | Fri 11/1/24 | Thu 11/14/24 | 2610 | 2613 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6341 | 2613 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 11/15/24 | Fri 11/15/24 | 2612 | 2614 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6342 | 2614 | Future Task |  |  | D342 | Joy Schneider | Submit | DEL D342 - Monthly Performance Report (October 2024) - Submit | 0 hrs | 0 days | Fri 11/15/24 | Fri 11/15/24 | 2613 | 2615 |  | Joy Schneider
6343 | 2615 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Department QC | 1 hr | 7 days | Mon 11/18/24 | Tue 11/26/24 | 2614 | 2616 |  | Gabriela Gibson
6344 | 2616 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Contract Manager Review | 2 hrs | 2 days | Wed 11/27/24 | Mon 12/2/24 | 2615 | 2617 |  | Sean Buchanan
6345 | 2617 | Future Task |  |  | D342 | Joy Schneider | Accept | DEL D342 - Monthly Performance Report (October 2024) - Accept | 0 hrs | 0 days | Mon 12/2/24 | Mon 12/2/24 | 2616 | 2619 |  | Sean Buchanan
6346 | 2618 | Future Task |  |  | D347 | Joy Schneider |  | D347 - Monthly Performance Report (November 2024) | 10 hrs | 19 days | Tue 12/3/24 | Mon 12/30/24
6373 | 2619 | Future Task |  |  | D347 | Joy Schneider | Create | D347 - Create November 2024 Monthly Performance Report | 3 hrs | 9 days | Tue 12/3/24 | Fri 12/13/24 | 2617 | 2620 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6347 | 2620 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 12/16/24 | Mon 12/16/24 | 2619 | 2621 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6348 | 2621 | Future Task |  |  | D347 | Joy Schneider | Submit | DEL D347 - Monthly Performance Report (November 2024) - Submit | 0 hrs | 0 days | Mon 12/16/24 | Mon 12/16/24 | 2620 | 2622 |  | Joy Schneider
6349 | 2622 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Department QC | 1 hr | 7 days | Tue 12/17/24 | Thu 12/26/24 | 2621 | 2623 |  | Gabriela Gibson
6350 | 2623 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Contract Manager Review | 2 hrs | 2 days | Fri 12/27/24 | Mon 12/30/24 | 2622 | 2624 |  | Sean Buchanan
6351 | 2624 | Future Task |  |  | D347 | Joy Schneider | Accept | DEL D347 - Monthly Performance Report (November 2024) - Accept | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 2623 | 2626 |  | Sean Buchanan
6352 | 2625 | Future Task |  |  | D353 | Joy Schneider |  | D353 - Monthly Performance Report (December 2024) | 10 hrs | 19 days | Thu 1/2/25 | Wed 1/29/25
6372 | 2626 | Future Task |  |  | D353 | Joy Schneider | Create | D353 - Create December 2024 Monthly Performance Report | 3 hrs | 9 days | Thu 1/2/25 | Tue 1/14/25 | 2624 | 2627 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6353 | 2627 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 1/15/25 | Wed 1/15/25 | 2626 | 2628 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6354 | 2628 | Future Task |  |  | D353 | Joy Schneider | Submit | DEL D353 - Monthly Performance Report (December 2024) - Submit | 0 hrs | 0 days | Wed 1/15/25 | Wed 1/15/25 | 2627 | 2629 |  | Joy Schneider
6355 | 2629 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Department QC | 1 hr | 7 days | Thu 1/16/25 | Mon 1/27/25 | 2628 | 2630 |  | Gabriela Gibson
6356 | 2630 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Contract Manager Review | 2 hrs | 2 days | Tue 1/28/25 | Wed 1/29/25 | 2629 | 2631 |  | Sean Buchanan
6357 | 2631 | Future Task |  |  | D353 | Joy Schneider | Accept | DEL D353 - Monthly Performance Report (December 2024) - Accept | 0 hrs | 0 days | Wed 1/29/25 | Wed 1/29/25 | 2630 | 2633 |  | Sean Buchanan
6358 | 2632 | Future Task |  |  | D359 | Joy Schneider |  | D359 - Monthly Performance Report (January 2025) | 10 hrs | 19 days | Mon 2/3/25 | Thu 2/27/25
6371 | 2633 | Future Task |  |  | D359 | Joy Schneider | Create | D359 - Create January 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 2/3/25 | Thu 2/13/25 | 2631 | 2634 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6359 | 2634 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 2/14/25 | Fri 2/14/25 | 2633 | 2635 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6360 | 2635 | Future Task |  |  | D359 | Joy Schneider | Submit | DEL D359 - Monthly Performance Report (January 2025) - Submit | 0 hrs | 0 days | Fri 2/14/25 | Fri 2/14/25 | 2634 | 2636 |  | Joy Schneider
6361 | 2636 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Department QC | 1 hr | 7 days | Mon 2/17/25 | Tue 2/25/25 | 2635 | 2637 |  | Gabriela Gibson
6362 | 2637 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 2/26/25 | Thu 2/27/25 | 2636 | 2638 |  | Sean Buchanan
6363 | 2638 | Future Task |  |  | D359 | Joy Schneider | Accept | DEL D359 - Monthly Performance Report (January 2025) - Accept | 0 hrs | 0 days | Thu 2/27/25 | Thu 2/27/25 | 2637 | 2640 |  | Sean Buchanan
6386 | 2639 | Future Task |  |  | D362 | Joy Schneider |  | D362 - Monthly Performance Report (February 2025) | 10 hrs | 19 days | Mon 3/3/25 | Thu 3/27/25
6490 | 2640 | Future Task |  |  | D362 | Joy Schneider | Create | D362 - Create February 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 3/3/25 | Thu 3/13/25 | 2638 | 2641 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6387 | 2641 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 3/14/25 | Fri 3/14/25 | 2640 | 2642 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6388 | 2642 | Future Task |  |  | D362 | Joy Schneider | Submit | DEL D362 - Monthly Performance Report (February 2025) - Submit | 0 hrs | 0 days | Fri 3/14/25 | Fri 3/14/25 | 2641 | 2643 |  | Joy Schneider
6389 | 2643 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Department QC | 1 hr | 7 days | Mon 3/17/25 | Tue 3/25/25 | 2642 | 2644 |  | Gabriela Gibson
6390 | 2644 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 3/26/25 | Thu 3/27/25 | 2643 | 2645 |  | Sean Buchanan
6391 | 2645 | Future Task |  |  | D362 | Joy Schneider | Accept | DEL D362 - Monthly Performance Report (February 2025) - Accept | 0 hrs | 0 days | Thu 3/27/25 | Thu 3/27/25 | 2644 | 2647 |  | Sean Buchanan
6392 | 2646 | Future Task |  |  | D364 | Joy Schneider |  | D364 - Monthly Performance Report (March 2025) | 10 hrs | 19 days | Tue 4/1/25 | Fri 4/25/25
6489 | 2647 | Future Task |  |  | D364 | Joy Schneider | Create | D364 - Create March 2025 Monthly Performance Report | 3 hrs | 9 days | Tue 4/1/25 | Fri 4/11/25 | 2645 | 2648 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6393 | 2648 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 4/14/25 | Mon 4/14/25 | 2647 | 2649 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6394 | 2649 | Future Task |  |  | D364 | Joy Schneider | Submit | DEL D364 - Monthly Performance Report (March 2025) - Submit | 0 hrs | 0 days | Mon 4/14/25 | Mon 4/14/25 | 2648 | 2650 |  | Joy Schneider
6395 | 2650 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Department QC | 1 hr | 7 days | Tue 4/15/25 | Wed 4/23/25 | 2649 | 2651 |  | Gabriela Gibson
6396 | 2651 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Contract Manager Review | 2 hrs | 2 days | Thu 4/24/25 | Fri 4/25/25 | 2650 | 2652 |  | Sean Buchanan
6397 | 2652 | Future Task |  |  | D364 | Joy Schneider | Accept | DEL D364 - Monthly Performance Report (March 2025) - Accept | 0 hrs | 0 days | Fri 4/25/25 | Fri 4/25/25 | 2651 | 2654 |  | Sean Buchanan
6398 | 2653 | Future Task |  |  | D366 | Joy Schneider |  | D366 - Monthly Performance Report (April 2025) | 10 hrs | 19 days | Thu 5/1/25 | Wed 5/28/25
6488 | 2654 | Future Task |  |  | D366 | Joy Schneider | Create | D366 - Create April 2025 Monthly Performance Report | 3 hrs | 9 days | Thu 5/1/25 | Tue 5/13/25 | 2652 | 2655 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6399 | 2655 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 5/14/25 | Wed 5/14/25 | 2654 | 2656 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6400 | 2656 | Future Task |  |  | D366 | Joy Schneider | Submit | DEL D366 - Monthly Performance Report (April 2025) - Submit | 0 hrs | 0 days | Wed 5/14/25 | Wed 5/14/25 | 2655 | 2657 |  | Joy Schneider
6401 | 2657 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Department QC | 1 hr | 7 days | Thu 5/15/25 | Fri 5/23/25 | 2656 | 2658 |  | Gabriela Gibson
6402 | 2658 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Contract Manager Review | 2 hrs | 2 days | Tue 5/27/25 | Wed 5/28/25 | 2657 | 2659 |  | Sean Buchanan
6403 | 2659 | Future Task |  |  | D366 | Joy Schneider | Accept | DEL D366 - Monthly Performance Report (April 2025) - Accept | 0 hrs | 0 days | Wed 5/28/25 | Wed 5/28/25 | 2658 | 2661 |  | Sean Buchanan
6404 | 2660 | Future Task |  |  | D367 | Joy Schneider |  | D367 - Monthly Performance Report (May 2025) | 10 hrs | 19 days | Mon 6/2/25 | Thu 6/26/25
6487 | 2661 | Future Task |  |  | D367 | Joy Schneider | Create | D367 - Create May 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 6/2/25 | Thu 6/12/25 | 2659 | 2662 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6405 | 2662 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 6/13/25 | Fri 6/13/25 | 2661 | 2663 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6406 | 2663 | Future Task |  |  | D367 | Joy Schneider | Submit | DEL D367 - Monthly Performance Report (May 2025) - Submit | 0 hrs | 0 days | Fri 6/13/25 | Fri 6/13/25 | 2662 | 2664 |  | Joy Schneider
6407 | 2664 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Department QC | 1 hr | 7 days | Mon 6/16/25 | Tue 6/24/25 | 2663 | 2665 |  | Gabriela Gibson
6408 | 2665 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 6/25/25 | Thu 6/26/25 | 2664 | 2666 |  | Sean Buchanan
6409 | 2666 | Future Task |  |  | D367 | Joy Schneider | Accept | DEL D367 - Monthly Performance Report (May 2025) - Accept | 0 hrs | 0 days | Thu 6/26/25 | Thu 6/26/25 | 2665 | 2668 |  | Sean Buchanan
6410 | 2667 | Future Task |  |  | D368 | Joy Schneider |  | D368 - Monthly Performance Report (June 2025) | 10 hrs | 19 days | Tue 7/1/25 | Mon 7/28/25
6486 | 2668 | Future Task |  |  | D368 | Joy Schneider | Create | D368 - Create June 2025 Monthly Performance Report | 3 hrs | 9 days | Tue 7/1/25 | Mon 7/14/25 | 2666 | 2669 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6411 | 2669 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 7/15/25 | Tue 7/15/25 | 2668 | 2670 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6412 | 2670 | Future Task |  |  | D368 | Joy Schneider | Submit | DEL D368 - Monthly Performance Report (June 2025) - Submit | 0 hrs | 0 days | Tue 7/15/25 | Tue 7/15/25 | 2669 | 2671 |  | Joy Schneider
6413 | 2671 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Department QC | 1 hr | 7 days | Wed 7/16/25 | Thu 7/24/25 | 2670 | 2672 |  | Gabriela Gibson
6414 | 2672 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Contract Manager Review | 2 hrs | 2 days | Fri 7/25/25 | Mon 7/28/25 | 2671 | 2673 |  | Sean Buchanan
6415 | 2673 | Future Task |  |  | D368 | Joy Schneider | Accept | DEL D368 - Monthly Performance Report (June 2025) - Accept | 0 hrs | 0 days | Mon 7/28/25 | Mon 7/28/25 | 2672 | 2675 |  | Sean Buchanan
6416 | 2674 | Future Task |  |  | D369 | Joy Schneider |  | D369 - Monthly Performance Report (July 2025) | 10 hrs | 19 days | Fri 8/1/25 | Wed 8/27/25
6485 | 2675 | Future Task |  |  | D369 | Joy Schneider | Create | D369 - Create July 2025 Monthly Performance Report | 3 hrs | 9 days | Fri 8/1/25 | Wed 8/13/25 | 2673 | 2676 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6417 | 2676 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 8/14/25 | Thu 8/14/25 | 2675 | 2677 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6418 | 2677 | Future Task |  |  | D369 | Joy Schneider | Submit | DEL D369 - Monthly Performance Report (July 2025) - Submit | 0 hrs | 0 days | Thu 8/14/25 | Thu 8/14/25 | 2676 | 2678 |  | Joy Schneider
6419 | 2678 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Department QC | 1 hr | 7 days | Fri 8/15/25 | Mon 8/25/25 | 2677 | 2679 |  | Gabriela Gibson
6420 | 2679 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Contract Manager Review | 2 hrs | 2 days | Tue 8/26/25 | Wed 8/27/25 | 2678 | 2680 |  | Sean Buchanan
6421 | 2680 | Future Task |  |  | D369 | Joy Schneider | Accept | DEL D369 - Monthly Performance Report (July 2025) - Accept | 0 hrs | 0 days | Wed 8/27/25 | Wed 8/27/25 | 2679 | 2682 |  | Sean Buchanan
6422 | 2681 | Future Task |  |  | D370 | Joy Schneider |  | D370 - Monthly Performance Report (August 2025) | 10 hrs | 19 days | Tue 9/2/25 | Fri 9/26/25
6484 | 2682 | Future Task |  |  | D370 | Joy Schneider | Create | D370 - Create August 2025 Monthly Performance Report | 3 hrs | 9 days | Tue 9/2/25 | Fri 9/12/25 | 2680 | 2683 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6423 | 2683 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 9/15/25 | Mon 9/15/25 | 2682 | 2684 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6424 | 2684 | Future Task |  |  | D370 | Joy Schneider | Submit | DEL D370 - Monthly Performance Report (August 2025) - Submit | 0 hrs | 0 days | Mon 9/15/25 | Mon 9/15/25 | 2683 | 2685 |  | Joy Schneider
6425 | 2685 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Department QC | 1 hr | 7 days | Tue 9/16/25 | Wed 9/24/25 | 2684 | 2686 |  | Gabriela Gibson
6426 | 2686 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Contract Manager Review | 2 hrs | 2 days | Thu 9/25/25 | Fri 9/26/25 | 2685 | 2687 |  | Sean Buchanan
6427 | 2687 | Future Task |  |  | D370 | Joy Schneider | Accept | DEL D370 - Monthly Performance Report (August 2025) - Accept | 0 hrs | 0 days | Fri 9/26/25 | Fri 9/26/25 | 2686 | 2689 |  | Sean Buchanan
6428 | 2688 | Future Task |  |  | D371 | Joy Schneider |  | D371 - Monthly Performance Report (September 2025) | 10 hrs | 19 days | Wed 10/1/25 | Mon 10/27/25
6483 | 2689 | Future Task |  |  | D371 | Joy Schneider | Create | D371 - Create September 2025 Monthly Performance Report | 3 hrs | 9 days | Wed 10/1/25 | Mon 10/13/25 | 2687 | 2690 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6429 | 2690 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 10/14/25 | Tue 10/14/25 | 2689 | 2691 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6430 | 2691 | Future Task |  |  | D371 | Joy Schneider | Submit | DEL D371 - Monthly Performance Report (September 2025) - Submit | 0 hrs | 0 days | Tue 10/14/25 | Tue 10/14/25 | 2690 | 2692 |  | Joy Schneider
6431 | 2692 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Department QC | 1 hr | 7 days | Wed 10/15/25 | Thu 10/23/25 | 2691 | 2693 |  | Gabriela Gibson
6432 | 2693 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Contract Manager Review | 2 hrs | 2 days | Fri 10/24/25 | Mon 10/27/25 | 2692 | 2694 |  | Sean Buchanan
6433 | 2694 | Future Task |  |  | D371 | Joy Schneider | Accept | DEL D371 - Monthly Performance Report (September 2025) - Accept | 0 hrs | 0 days | Mon 10/27/25 | Mon 10/27/25 | 2693 | 2696 |  | Sean Buchanan
6434 | 2695 | Future Task |  |  | D373 | Joy Schneider |  | D373 - Monthly Performance Report (October 2025) | 10 hrs | 19 days | Mon 11/3/25 | Tue 12/2/25
6482 | 2696 | Future Task |  |  | D373 | Joy Schneider | Create | D373 - Create October 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 11/3/25 | Fri 11/14/25 | 2694 | 2697 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6435 | 2697 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 11/17/25 | Mon 11/17/25 | 2696 | 2698 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6436 | 2698 | Future Task |  |  | D373 | Joy Schneider | Submit | DEL D373 - Monthly Performance Report (October 2025) - Submit | 0 hrs | 0 days | Mon 11/17/25 | Mon 11/17/25 | 2697 | 2699 |  | Joy Schneider
6437 | 2699 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Department QC | 1 hr | 7 days | Tue 11/18/25 | Wed 11/26/25 | 2698 | 2700 |  | Gabriela Gibson
6438 | 2700 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Contract Manager Review | 2 hrs | 2 days | Mon 12/1/25 | Tue 12/2/25 | 2699 | 2701 |  | Sean Buchanan
6439 | 2701 | Future Task |  |  | D373 | Joy Schneider | Accept | DEL D373 - Monthly Performance Report (October 2025) - Accept | 0 hrs | 0 days | Tue 12/2/25 | Tue 12/2/25 | 2700 | 2703FS-2 days |  | Sean Buchanan
6440 | 2702 | Future Task |  |  | D374 | Joy Schneider |  | D374 - Monthly Performance Report (November 2025) | 10 hrs | 19 days | Mon 12/1/25 | Fri 12/26/25
6481 | 2703 | Future Task |  |  | D374 | Joy Schneider | Create | D374 - Create November 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 12/1/25 | Thu 12/11/25 | 2701FS-2 days | 2704 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6441 | 2704 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 12/12/25 | Fri 12/12/25 | 2703 | 2705 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6442 | 2705 | Future Task |  |  | D374 | Joy Schneider | Submit | DEL D374 - Monthly Performance Report (November 2025) - Submit | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 2704 | 2706 |  | Joy Schneider
6443 | 2706 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Department QC | 1 hr | 7 days | Mon 12/15/25 | Tue 12/23/25 | 2705 | 2707 |  | Gabriela Gibson
6444 | 2707 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 12/24/25 | Fri 12/26/25 | 2706 | 2708 |  | Sean Buchanan
6445 | 2708 | Future Task |  |  | D374 | Joy Schneider | Accept | DEL D374 - Monthly Performance Report (November 2025) - Accept | 0 hrs | 0 days | Fri 12/26/25 | Fri 12/26/25 | 2707 | 2710 |  | Sean Buchanan
6446 | 2709 | Future Task |  |  | D375 | Joy Schneider |  | D375 - Monthly Performance Report (December 2025) | 10 hrs | 19 days | Fri 1/2/26 | Thu 1/29/26
6480 | 2710 | Future Task |  |  | D375 | Joy Schneider | Create | D375 - Create December 2025 Monthly Performance Report | 3 hrs | 9 days | Fri 1/2/26 | Wed 1/14/26 | 2708 | 2711 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6447 | 2711 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 1/15/26 | Thu 1/15/26 | 2710 | 2712 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6448 | 2712 | Future Task |  |  | D375 | Joy Schneider | Submit | DEL D375 - Monthly Performance Report (December 2025) - Submit | 0 hrs | 0 days | Thu 1/15/26 | Thu 1/15/26 | 2711 | 2713 |  | Joy Schneider
6449 | 2713 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Department QC | 1 hr | 7 days | Fri 1/16/26 | Tue 1/27/26 | 2712 | 2714 |  | Gabriela Gibson
6450 | 2714 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 1/28/26 | Thu 1/29/26 | 2713 | 2715 |  | Sean Buchanan
6451 | 2715 | Future Task |  |  | D375 | Joy Schneider | Accept | DEL D375 - Monthly Performance Report (December 2025) - Accept | 0 hrs | 0 days | Thu 1/29/26 | Thu 1/29/26 | 2714 | 2717 |  | Sean Buchanan
6452 | 2716 | Future Task |  |  | D432 | Joy Schneider |  | D432 - Monthly Performance Report (January 2026) | 10 hrs | 19 days | Mon 2/2/26 | Thu 2/26/26
6479 | 2717 | Future Task |  |  | D432 | Joy Schneider | Create | D432 - Create January 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 2/2/26 | Thu 2/12/26 | 2715 | 2718 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6453 | 2718 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 2/13/26 | Fri 2/13/26 | 2717 | 2719 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6454 | 2719 | Future Task |  |  | D432 | Joy Schneider | Submit | DEL D432 - Monthly Performance Report (January 2026) - Submit | 0 hrs | 0 days | Fri 2/13/26 | Fri 2/13/26 | 2718 | 2720 |  | Joy Schneider
6455 | 2720 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Department QC | 1 hr | 7 days | Mon 2/16/26 | Tue 2/24/26 | 2719 | 2721 |  | Gabriela Gibson
6456 | 2721 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 2/25/26 | Thu 2/26/26 | 2720 | 2722 |  | Sean Buchanan
6457 | 2722 | Future Task |  |  | D432 | Joy Schneider | Accept | DEL D432 - Monthly Performance Report (January 2026) - Accept | 0 hrs | 0 days | Thu 2/26/26 | Thu 2/26/26 | 2721 | 2724 |  | Sean Buchanan
6458 | 2723 | Future Task |  |  | D434 | Joy Schneider |  | D434 - Monthly Performance Report (February 2026) | 10 hrs | 19 days | Mon 3/2/26 | Thu 3/26/26
6478 | 2724 | Future Task |  |  | D434 | Joy Schneider | Create | D434 - Create February 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 3/2/26 | Thu 3/12/26 | 2722 | 2725 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6459 | 2725 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 3/13/26 | Fri 3/13/26 | 2724 | 2726 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6460 | 2726 | Future Task |  |  | D434 | Joy Schneider | Submit | DEL D434 - Monthly Performance Report (February 2026) - Submit | 0 hrs | 0 days | Fri 3/13/26 | Fri 3/13/26 | 2725 | 2727 |  | Joy Schneider
6461 | 2727 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Department QC | 1 hr | 7 days | Mon 3/16/26 | Tue 3/24/26 | 2726 | 2728 |  | Gabriela Gibson
6462 | 2728 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 3/25/26 | Thu 3/26/26 | 2727 | 2729 |  | Sean Buchanan
6463 | 2729 | Future Task |  |  | D434 | Joy Schneider | Accept | DEL D434 - Monthly Performance Report (February 2026) - Accept | 0 hrs | 0 days | Thu 3/26/26 | Thu 3/26/26 | 2728 | 2731 |  | Sean Buchanan
6464 | 2730 | Future Task |  |  | D435 | Joy Schneider |  | D435 - Monthly Performance Report (March 2026) | 10 hrs | 19 days | Wed 4/1/26 | Mon 4/27/26
6477 | 2731 | Future Task |  |  | D435 | Joy Schneider | Create | D435 - Create March 2026 Monthly Performance Report | 3 hrs | 9 days | Wed 4/1/26 | Mon 4/13/26 | 2729 | 2732 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6465 | 2732 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 4/14/26 | Tue 4/14/26 | 2731 | 2733 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6466 | 2733 | Future Task |  |  | D435 | Joy Schneider | Submit | DEL D435 - Monthly Performance Report (March 2026) - Submit | 0 hrs | 0 days | Tue 4/14/26 | Tue 4/14/26 | 2732 | 2734 |  | Joy Schneider
6467 | 2734 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Department QC | 1 hr | 7 days | Wed 4/15/26 | Thu 4/23/26 | 2733 | 2735 |  | Gabriela Gibson
6468 | 2735 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Contract Manager Review | 2 hrs | 2 days | Fri 4/24/26 | Mon 4/27/26 | 2734 | 2736 |  | Sean Buchanan
6469 | 2736 | Future Task |  |  | D435 | Joy Schneider | Accept | DEL D435 - Monthly Performance Report (March 2026) - Accept | 0 hrs | 0 days | Mon 4/27/26 | Mon 4/27/26 | 2735 | 2738 |  | Sean Buchanan
6470 | 2737 | Future Task |  |  | D437 | Joy Schneider |  | D437 - Monthly Performance Report (April 2026) | 10 hrs | 19 days | Fri 5/1/26 | Thu 5/28/26
6476 | 2738 | Future Task |  |  | D437 | Joy Schneider | Create | D437 - Create April 2026 Monthly Performance Report | 3 hrs | 9 days | Fri 5/1/26 | Wed 5/13/26 | 2736 | 2739 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6471 | 2739 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 5/14/26 | Thu 5/14/26 | 2738 | 2740 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6472 | 2740 | Future Task |  |  | D437 | Joy Schneider | Submit | DEL D437 - Monthly Performance Report (April 2026) - Submit | 0 hrs | 0 days | Thu 5/14/26 | Thu 5/14/26 | 2739 | 2741 |  | Joy Schneider
6473 | 2741 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Department QC | 1 hr | 7 days | Fri 5/15/26 | Tue 5/26/26 | 2740 | 2742 |  | Gabriela Gibson
6474 | 2742 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 5/27/26 | Thu 5/28/26 | 2741 | 2743 |  | Sean Buchanan
6475 | 2743 | Future Task |  |  | D437 | Joy Schneider | Accept | DEL D437 - Monthly Performance Report (April 2026) - Accept | 0 hrs | 0 days | Thu 5/28/26 | Thu 5/28/26 | 2742 | 2745 |  | Sean Buchanan
6491 | 2744 | Future Task |  |  | D438 | Joy Schneider |  | D438 - Monthly Performance Report (May 2026) | 10 hrs | 19 days | Mon 6/1/26 | Thu 6/25/26
6595 | 2745 | Future Task |  |  | D438 | Joy Schneider | Create | D438 - Create May 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 6/1/26 | Thu 6/11/26 | 2743 | 2746 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6492 | 2746 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 6/12/26 | Fri 6/12/26 | 2745 | 2747 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6493 | 2747 | Future Task |  |  | D438 | Joy Schneider | Submit | DEL D438 - Monthly Performance Report (May 2026) - Submit | 0 hrs | 0 days | Fri 6/12/26 | Fri 6/12/26 | 2746 | 2748 |  | Joy Schneider
6494 | 2748 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Department QC | 1 hr | 7 days | Mon 6/15/26 | Tue 6/23/26 | 2747 | 2749 |  | Gabriela Gibson
6495 | 2749 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 6/24/26 | Thu 6/25/26 | 2748 | 2750 |  | Sean Buchanan
6496 | 2750 | Future Task |  |  | D438 | Joy Schneider | Accept | DEL D438 - Monthly Performance Report (May 2026) - Accept | 0 hrs | 0 days | Thu 6/25/26 | Thu 6/25/26 | 2749 | 2752 |  | Sean Buchanan
6497 | 2751 | Future Task |  |  | D439 | Joy Schneider |  | D439 - Monthly Performance Report (June 2026) | 10 hrs | 19 days | Wed 7/1/26 | Tue 7/28/26
6594 | 2752 | Future Task |  |  | D439 | Joy Schneider | Create | D439 - Create June 2026 Monthly Performance Report | 3 hrs | 9 days | Wed 7/1/26 | Tue 7/14/26 | 2750 | 2753 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6498 | 2753 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 7/15/26 | Wed 7/15/26 | 2752 | 2754 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6499 | 2754 | Future Task |  |  | D439 | Joy Schneider | Submit | DEL D439 - Monthly Performance Report (June 2026) - Submit | 0 hrs | 0 days | Wed 7/15/26 | Wed 7/15/26 | 2753 | 2755 |  | Joy Schneider
6500 | 2755 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Department QC | 1 hr | 7 days | Thu 7/16/26 | Fri 7/24/26 | 2754 | 2756 |  | Gabriela Gibson
6501 | 2756 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 7/27/26 | Tue 7/28/26 | 2755 | 2757 |  | Sean Buchanan
6502 | 2757 | Future Task |  |  | D439 | Joy Schneider | Accept | DEL D439 - Monthly Performance Report (June 2026) - Accept | 0 hrs | 0 days | Tue 7/28/26 | Tue 7/28/26 | 2756 | 2759 |  | Sean Buchanan
6503 | 2758 | Future Task |  |  | D441 | Joy Schneider |  | D441 - Monthly Performance Report (July 2026) | 10 hrs | 19 days | Mon 8/3/26 | Thu 8/27/26
6593 | 2759 | Future Task |  |  | D441 | Joy Schneider | Create | D441 - Create July 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 8/3/26 | Thu 8/13/26 | 2757 | 2760 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6504 | 2760 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 8/14/26 | Fri 8/14/26 | 2759 | 2761 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6505 | 2761 | Future Task |  |  | D441 | Joy Schneider | Submit | DEL D441 - Monthly Performance Report (July 2026) - Submit | 0 hrs | 0 days | Fri 8/14/26 | Fri 8/14/26 | 2760 | 2762 |  | Joy Schneider
6506 | 2762 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Department QC | 1 hr | 7 days | Mon 8/17/26 | Tue 8/25/26 | 2761 | 2763 |  | Gabriela Gibson
6507 | 2763 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 8/26/26 | Thu 8/27/26 | 2762 | 2764 |  | Sean Buchanan
6508 | 2764 | Future Task |  |  | D441 | Joy Schneider | Accept | DEL D441 - Monthly Performance Report (July 2026) - Accept | 0 hrs | 0 days | Thu 8/27/26 | Thu 8/27/26 | 2763 | 2766 |  | Sean Buchanan
6509 | 2765 | Future Task |  |  | D442 | Joy Schneider |  | D442 - Monthly Performance Report (August 2026) | 10 hrs | 19 days | Tue 9/1/26 | Mon 9/28/26
6592 | 2766 | Future Task |  |  | D442 | Joy Schneider | Create | D442 - Create August 2026 Monthly Performance Report | 3 hrs | 9 days | Tue 9/1/26 | Mon 9/14/26 | 2764 | 2767 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6510 | 2767 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 9/15/26 | Tue 9/15/26 | 2766 | 2768 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6511 | 2768 | Future Task |  |  | D442 | Joy Schneider | Submit | DEL D442 - Monthly Performance Report (August 2026) - Submit | 0 hrs | 0 days | Tue 9/15/26 | Tue 9/15/26 | 2767 | 2769 |  | Joy Schneider
6512 | 2769 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Department QC | 1 hr | 7 days | Wed 9/16/26 | Thu 9/24/26 | 2768 | 2770 |  | Gabriela Gibson
6513 | 2770 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Contract Manager Review | 2 hrs | 2 days | Fri 9/25/26 | Mon 9/28/26 | 2769 | 2771 |  | Sean Buchanan
6514 | 2771 | Future Task |  |  | D442 | Joy Schneider | Accept | DEL D442 - Monthly Performance Report (August 2026) - Accept | 0 hrs | 0 days | Mon 9/28/26 | Mon 9/28/26 | 2770 | 2773 |  | Sean Buchanan
6515 | 2772 | Future Task |  |  | D443 | Joy Schneider |  | D443 - Monthly Performance Report (September 2026) | 10 hrs | 19 days | Thu 10/1/26 | Tue 10/27/26
6591 | 2773 | Future Task |  |  | D443 | Joy Schneider | Create | D443 - Create September 2026 Monthly Performance Report | 3 hrs | 9 days | Thu 10/1/26 | Tue 10/13/26 | 2771 | 2774 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6516 | 2774 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 10/14/26 | Wed 10/14/26 | 2773 | 2775 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6517 | 2775 | Future Task |  |  | D443 | Joy Schneider | Submit | DEL D443 - Monthly Performance Report (September 2026) - Submit | 0 hrs | 0 days | Wed 10/14/26 | Wed 10/14/26 | 2774 | 2776 |  | Joy Schneider
6518 | 2776 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Department QC | 1 hr | 7 days | Thu 10/15/26 | Fri 10/23/26 | 2775 | 2777 |  | Gabriela Gibson
6519 | 2777 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 10/26/26 | Tue 10/27/26 | 2776 | 2778 |  | Sean Buchanan
6520 | 2778 | Future Task |  |  | D443 | Joy Schneider | Accept | DEL D443 - Monthly Performance Report (September 2026) - Accept | 0 hrs | 0 days | Tue 10/27/26 | Tue 10/27/26 | 2777 | 2780 |  | Sean Buchanan
6521 | 2779 | Future Task |  |  | D444 | Joy Schneider |  | D444 - Monthly Performance Report (October 2026) | 10 hrs | 19 days | Mon 11/2/26 | Tue 12/1/26
6590 | 2780 | Future Task |  |  | D444 | Joy Schneider | Create | D444 - Create October 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 11/2/26 | Fri 11/13/26 | 2778 | 2781 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6522 | 2781 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 11/16/26 | Mon 11/16/26 | 2780 | 2782 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6523 | 2782 | Future Task |  |  | D444 | Joy Schneider | Submit | DEL D444 - Monthly Performance Report (October 2026) - Submit | 0 hrs | 0 days | Mon 11/16/26 | Mon 11/16/26 | 2781 | 2783 |  | Joy Schneider
6524 | 2783 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Department QC | 1 hr | 7 days | Tue 11/17/26 | Wed 11/25/26 | 2782 | 2784 |  | Gabriela Gibson
6525 | 2784 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 11/30/26 | Tue 12/1/26 | 2783 | 2785 |  | Sean Buchanan
6526 | 2785 | Future Task |  |  | D444 | Joy Schneider | Accept | DEL D444 - Monthly Performance Report (October 2026) - Accept | 0 hrs | 0 days | Tue 12/1/26 | Tue 12/1/26 | 2784 | 2787FS-1 day |  | Sean Buchanan
6527 | 2786 | Future Task |  |  | D445 | Joy Schneider |  | D445 - Monthly Performance Report (November 2026) | 10 hrs | 19 days | Tue 12/1/26 | Mon 12/28/26
6589 | 2787 | Future Task |  |  | D445 | Joy Schneider | Create | D445 - Create November 2026 Monthly Performance Report | 3 hrs | 9 days | Tue 12/1/26 | Fri 12/11/26 | 2785FS-1 day | 2788 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6528 | 2788 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 12/14/26 | Mon 12/14/26 | 2787 | 2789 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6529 | 2789 | Future Task |  |  | D445 | Joy Schneider | Submit | DEL D445 - Monthly Performance Report (November 2026) - Submit | 0 hrs | 0 days | Mon 12/14/26 | Mon 12/14/26 | 2788 | 2790 |  | Joy Schneider
6530 | 2790 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Department QC | 1 hr | 7 days | Tue 12/15/26 | Wed 12/23/26 | 2789 | 2791 |  | Gabriela Gibson
6531 | 2791 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Contract Manager Review | 2 hrs | 2 days | Thu 12/24/26 | Mon 12/28/26 | 2790 | 2792 |  | Sean Buchanan
6532 | 2792 | Future Task |  |  | D445 | Joy Schneider | Accept | DEL D445 - Monthly Performance Report (November 2026) - Accept | 0 hrs | 0 days | Mon 12/28/26 | Mon 12/28/26 | 2791 | 2794 |  | Sean Buchanan
6533 | 2793 | Future Task |  |  | D446 | Joy Schneider |  | D446 - Monthly Performance Report (December 2026) | 10 hrs | 19 days | Mon 1/4/27 | Fri 1/29/27
6588 | 2794 | Future Task |  |  | D446 | Joy Schneider | Create | D446 - Create December 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 1/4/27 | Thu 1/14/27 | 2792 | 2795 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6534 | 2795 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 1/15/27 | Fri 1/15/27 | 2794 | 2796 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6535 | 2796 | Future Task |  |  | D446 | Joy Schneider | Submit | DEL D446 - Monthly Performance Report (December 2026) - Submit | 0 hrs | 0 days | Fri 1/15/27 | Fri 1/15/27 | 2795 | 2797 |  | Joy Schneider
6536 | 2797 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Department QC | 1 hr | 7 days | Tue 1/19/27 | Wed 1/27/27 | 2796 | 2798 |  | Gabriela Gibson
6537 | 2798 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Contract Manager Review | 2 hrs | 2 days | Thu 1/28/27 | Fri 1/29/27 | 2797 | 2799 |  | Sean Buchanan
6538 | 2799 | Future Task |  |  | D446 | Joy Schneider | Accept | DEL D446 - Monthly Performance Report (December 2026) - Accept | 0 hrs | 0 days | Fri 1/29/27 | Fri 1/29/27 | 2798 | 2801 |  | Sean Buchanan
6539 | 2800 | Future Task |  |  | D447 | Joy Schneider |  | D447 - Monthly Performance Report (January 2027) | 10 hrs | 19 days | Mon 2/1/27 | Thu 2/25/27
6587 | 2801 | Future Task |  |  | D447 | Joy Schneider | Create | D447 - Create January 2027 Monthly Performance Report | 3 hrs | 9 days | Mon 2/1/27 | Thu 2/11/27 | 2799 | 2802 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6540 | 2802 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 2/12/27 | Fri 2/12/27 | 2801 | 2803 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6541 | 2803 | Future Task |  |  | D447 | Joy Schneider | Submit | DEL D447 - Monthly Performance Report (January 2027) - Submit | 0 hrs | 0 days | Fri 2/12/27 | Fri 2/12/27 | 2802 | 2804 |  | Joy Schneider
6542 | 2804 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Department QC | 1 hr | 7 days | Mon 2/15/27 | Tue 2/23/27 | 2803 | 2805 |  | Gabriela Gibson
6543 | 2805 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 2/24/27 | Thu 2/25/27 | 2804 | 2806 |  | Sean Buchanan
6544 | 2806 | Future Task |  |  | D447 | Joy Schneider | Accept | DEL D447 - Monthly Performance Report (January 2027) - Accept | 0 hrs | 0 days | Thu 2/25/27 | Thu 2/25/27 | 2805 | 2808 |  | Sean Buchanan
6545 | 2807 | Future Task |  |  | D448 | Joy Schneider |  | D448 - Monthly Performance Report (February 2027) | 10 hrs | 19 days | Mon 3/1/27 | Thu 3/25/27
6586 | 2808 | Future Task |  |  | D448 | Joy Schneider | Create | D448 - Create February 2027 Monthly Performance Report | 3 hrs | 9 days | Mon 3/1/27 | Thu 3/11/27 | 2806 | 2809 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6546 | 2809 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 3/12/27 | Fri 3/12/27 | 2808 | 2810 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6547 | 2810 | Future Task |  |  | D448 | Joy Schneider | Submit | DEL D448 - Monthly Performance Report (February 2027) - Submit | 0 hrs | 0 days | Fri 3/12/27 | Fri 3/12/27 | 2809 | 2811 |  | Joy Schneider
6548 | 2811 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Department QC | 1 hr | 7 days | Mon 3/15/27 | Tue 3/23/27 | 2810 | 2812 |  | Gabriela Gibson
6549 | 2812 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 3/24/27 | Thu 3/25/27 | 2811 | 2813 |  | Sean Buchanan
6550 | 2813 | Future Task |  |  | D448 | Joy Schneider | Accept | DEL D448 - Monthly Performance Report (February 2027) - Accept | 0 hrs | 0 days | Thu 3/25/27 | Thu 3/25/27 | 2812 | 2815 |  | Sean Buchanan
6551 | 2814 | Future Task |  |  | D449 | Joy Schneider |  | D449 - Monthly Performance Report (March 2027) | 10 hrs | 19 days | Thu 4/1/27 | Tue 4/27/27
6585 | 2815 | Future Task |  |  | D449 | Joy Schneider | Create | D449 - Create March 2027 Monthly Performance Report | 3 hrs | 9 days | Thu 4/1/27 | Tue 4/13/27 | 2813 | 2816 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6552 | 2816 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 4/14/27 | Wed 4/14/27 | 2815 | 2817 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6553 | 2817 | Future Task |  |  | D449 | Joy Schneider | Submit | DEL D449 - Monthly Performance Report (March 2027) - Submit | 0 hrs | 0 days | Wed 4/14/27 | Wed 4/14/27 | 2816 | 2818 |  | Joy Schneider
6554 | 2818 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Department QC | 1 hr | 7 days | Thu 4/15/27 | Fri 4/23/27 | 2817 | 2819 |  | Gabriela Gibson
6555 | 2819 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Contract Manager Review | 2 hrs | 2 days | Mon 4/26/27 | Tue 4/27/27 | 2818 | 2820 |  | Sean Buchanan
6556 | 2820 | Future Task |  |  | D449 | Joy Schneider | Accept | DEL D449 - Monthly Performance Report (March 2027) - Accept | 0 hrs | 0 days | Tue 4/27/27 | Tue 4/27/27 | 2819 | 2822 |  | Sean Buchanan
6557 | 2821 | Future Task |  |  | D450 | Joy Schneider |  | D450 - Monthly Performance Report (April 2027) | 10 hrs | 19 days | Mon 5/3/27 | Thu 5/27/27
6584 | 2822 | Future Task |  |  | D450 | Joy Schneider | Create | D450 - Create April 2027 Monthly Performance Report | 3 hrs | 9 days | Mon 5/3/27 | Thu 5/13/27 | 2820 | 2823 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6558 | 2823 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 5/14/27 | Fri 5/14/27 | 2822 | 2824 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6559 | 2824 | Future Task |  |  | D450 | Joy Schneider | Submit | DEL D450 - Monthly Performance Report (April 2027) - Submit | 0 hrs | 0 days | Fri 5/14/27 | Fri 5/14/27 | 2823 | 2825 |  | Joy Schneider
6560 | 2825 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Department QC | 1 hr | 7 days | Mon 5/17/27 | Tue 5/25/27 | 2824 | 2826 |  | Gabriela Gibson
6561 | 2826 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 5/26/27 | Thu 5/27/27 | 2825 | 2827 |  | Sean Buchanan
6562 | 2827 | Future Task |  |  | D450 | Joy Schneider | Accept | DEL D450 - Monthly Performance Report (April 2027) - Accept | 0 hrs | 0 days | Thu 5/27/27 | Thu 5/27/27 | 2826 | 2829 |  | Sean Buchanan
6563 | 2828 | Future Task |  |  | D451 | Joy Schneider |  | D451 - Monthly Performance Report (May 2027) | 10 hrs | 19 days | Tue 6/1/27 | Fri 6/25/27
6583 | 2829 | Future Task |  |  | D451 | Joy Schneider | Create | D451 - Create May 2027 Monthly Performance Report | 3 hrs | 9 days | Tue 6/1/27 | Fri 6/11/27 | 2827 | 2830 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6564 | 2830 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 6/14/27 | Mon 6/14/27 | 2829 | 2831 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6565 | 2831 | Future Task |  |  | D451 | Joy Schneider | Submit | DEL D451 - Monthly Performance Report (May 2027) - Submit | 0 hrs | 0 days | Mon 6/14/27 | Mon 6/14/27 | 2830 | 2832 |  | Joy Schneider
6566 | 2832 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Department QC | 1 hr | 7 days | Tue 6/15/27 | Wed 6/23/27 | 2831 | 2833 |  | Gabriela Gibson
6567 | 2833 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Contract Manager Review | 2 hrs | 2 days | Thu 6/24/27 | Fri 6/25/27 | 2832 | 2834 |  | Sean Buchanan
6568 | 2834 | Future Task |  |  | D451 | Joy Schneider | Accept | DEL D451 - Monthly Performance Report (May 2027) - Accept | 0 hrs | 0 days | Fri 6/25/27 | Fri 6/25/27 | 2833 | 2836 |  | Sean Buchanan
6569 | 2835 | Future Task |  |  | D694 | Joy Schneider |  | D694 - Monthly Performance Report (June 2027) | 10 hrs | 19 days | Thu 7/1/27 | Wed 7/28/27
6582 | 2836 | Future Task |  |  | D694 | Joy Schneider | Create | D694 - Create June 2027 Monthly Performance Report | 3 hrs | 9 days | Thu 7/1/27 | Wed 7/14/27 | 2834 | 2837 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6570 | 2837 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 7/15/27 | Thu 7/15/27 | 2836 | 2838 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6571 | 2838 | Future Task |  |  | D694 | Joy Schneider | Submit | DEL D694 - Monthly Performance Report (June 2027) - Submit | 0 hrs | 0 days | Thu 7/15/27 | Thu 7/15/27 | 2837 | 2839 |  | Joy Schneider
6572 | 2839 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Department QC | 1 hr | 7 days | Fri 7/16/27 | Mon 7/26/27 | 2838 | 2840 |  | Gabriela Gibson
6573 | 2840 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Contract Manager Review | 2 hrs | 2 days | Tue 7/27/27 | Wed 7/28/27 | 2839 | 2841 |  | Sean Buchanan
6574 | 2841 | Future Task |  |  | D694 | Joy Schneider | Accept | DEL D694 - Monthly Performance Report (June 2027) - Accept | 0 hrs | 0 days | Wed 7/28/27 | Wed 7/28/27 | 2840 | 2843 |  | Sean Buchanan
6575 | 2842 | Future Task |  |  | D695 | Joy Schneider |  | D695 - Monthly Performance Report (July 2027) | 10 hrs | 19 days | Mon 8/2/27 | Thu 8/26/27
6581 | 2843 | Future Task |  |  | D695 | Joy Schneider | Create | D695 - Create July 2027 Monthly Performance Report | 3 hrs | 9 days | Mon 8/2/27 | Thu 8/12/27 | 2841 | 2844 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6576 | 2844 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 8/13/27 | Fri 8/13/27 | 2843 | 2845 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6577 | 2845 | Future Task |  |  | D695 | Joy Schneider | Submit | DEL D695 - Monthly Performance Report (July 2027) - Submit | 0 hrs | 0 days | Fri 8/13/27 | Fri 8/13/27 | 2844 | 2846 |  | Joy Schneider
6578 | 2846 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Department QC | 1 hr | 7 days | Mon 8/16/27 | Tue 8/24/27 | 2845 | 2847 |  | Gabriela Gibson
6579 | 2847 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 8/25/27 | Thu 8/26/27 | 2846 | 2848 |  | Sean Buchanan
6580 | 2848 | Future Task |  |  | D695 | Joy Schneider | Accept | DEL D695 - Monthly Performance Report (July 2027) - Accept | 0 hrs | 0 days | Thu 8/26/27 | Thu 8/26/27 | 2847 |  |  | Sean Buchanan
4047 | 2849 | Future Task | [5 empty] | Quarterly Newsletter for DDI of Reporting Functionality | 132 hrs | 658 days | Wed 6/21/23 | Mon 2/2/26
4048 | 2850 | Future Task | [5 empty] | Quarterly Newsletter | 132 hrs | 658 days | Wed 6/21/23 | Mon 2/2/26
4049 | 2851 | Future Task | [5 empty] | Quarterly Newsletter FY 22-23 Q4 | 12 hrs | 17 days | Wed 6/21/23 | Fri 7/14/23
4050 | 2852 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Wed 6/21/23 | Tue 6/27/23 |  | 2853 |  | Jennifer Grant,Jennifer Reeves
4051 | 2853 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Wed 6/28/23 | Wed 7/5/23 | 2852 | 2854 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4052 | 2854 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Thu 7/6/23 | Wed 7/12/23 | 2853 | 2855 |  | Jimmy Cox,Steven Fielder
4053 | 2855 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Thu 7/13/23 | Fri 7/14/23 | 2854 | 2857 |  | Dusti Kincl
4054 | 2856 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q1 | 12 hrs | 17 days | Fri 9/22/23 | Mon 10/16/23
4055 | 2857 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 9/22/23 | Thu 9/28/23 | 2855 | 2858 |  | Jennifer Grant,Jennifer Reeves
4056 | 2858 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 9/29/23 | Thu 10/5/23 | 2857 | 2859 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4057 | 2859 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 10/6/23 | Thu 10/12/23 | 2858 | 2860 |  | Jimmy Cox,Steven Fielder
4058 | 2860 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 10/13/23 | Mon 10/16/23 | 2859 | 2862 |  | Dusti Kincl
4059 | 2861 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q2 | 12 hrs | 17 days | Mon 12/18/23 | Thu 1/11/24
4060 | 2862 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 12/18/23 | Fri 12/22/23 | 2860 | 2863 |  | Jennifer Grant,Jennifer Reeves
4061 | 2863 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Tue 12/26/23 | Tue 1/2/24 | 2862 | 2864 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4062 | 2864 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Wed 1/3/24 | Tue 1/9/24 | 2863 | 2865 |  | Jimmy Cox,Steven Fielder
4063 | 2865 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Wed 1/10/24 | Thu 1/11/24 | 2864 | 2867 |  | Dusti Kincl
4064 | 2866 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q3 | 12 hrs | 17 days | Fri 3/22/24 | Mon 4/15/24
4065 | 2867 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 3/22/24 | Thu 3/28/24 | 2865 | 2868 |  | Jennifer Grant,Jennifer Reeves
4066 | 2868 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 3/29/24 | Thu 4/4/24 | 2867 | 2869 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4067 | 2869 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 4/5/24 | Thu 4/11/24 | 2868 | 2870 |  | Jimmy Cox,Steven Fielder
4068 | 2870 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 4/12/24 | Mon 4/15/24 | 2869 | 2872 |  | Dusti Kincl
4069 | 2871 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q4 | 12 hrs | 17 days | Thu 6/20/24 | Mon 7/15/24
4070 | 2872 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Thu 6/20/24 | Wed 6/26/24 | 2870 | 2873 |  | Jennifer Grant,Jennifer Reeves
4071 | 2873 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Thu 6/27/24 | Wed 7/3/24 | 2872 | 2874 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4072 | 2874 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 7/5/24 | Thu 7/11/24 | 2873 | 2875 |  | Jimmy Cox,Steven Fielder
4073 | 2875 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 7/12/24 | Mon 7/15/24 | 2874 | 2877 |  | Dusti Kincl
4074 | 2876 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q1 | 12 hrs | 17 days | Mon 9/23/24 | Tue 10/15/24
4075 | 2877 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 2875 | 2878 |  | Jennifer Grant,Jennifer Reeves
4076 | 2878 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Mon 9/30/24 | Fri 10/4/24 | 2877 | 2879 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4077 | 2879 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 | 2878 | 2880 |  | Jimmy Cox,Steven Fielder
4078 | 2880 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Mon 10/14/24 | Tue 10/15/24 | 2879 | 2882 |  | Dusti Kincl
4079 | 2881 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q2 | 12 hrs | 17 days | Mon 12/16/24 | Thu 1/9/25
4080 | 2882 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 12/16/24 | Fri 12/20/24 | 2880 | 2883 |  | Jennifer Grant,Jennifer Reeves
4081 | 2883 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Mon 12/23/24 | Mon 12/30/24 | 2882 | 2884 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4082 | 2884 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Tue 12/31/24 | Tue 1/7/25 | 2883 | 2885 |  | Jimmy Cox,Steven Fielder
4083 | 2885 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Wed 1/8/25 | Thu 1/9/25 | 2884 | 2887 |  | Dusti Kincl
4084 | 2886 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q3 | 12 hrs | 17 days | Mon 3/24/25 | Tue 4/15/25
4085 | 2887 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 2885 | 2888 |  | Jennifer Grant,Jennifer Reeves
4086 | 2888 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Mon 3/31/25 | Fri 4/4/25 | 2887 | 2889 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4087 | 2889 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Mon 4/7/25 | Fri 4/11/25 | 2888 | 2890 |  | Jimmy Cox,Steven Fielder
4088 | 2890 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Mon 4/14/25 | Tue 4/15/25 | 2889 | 2892 |  | Dusti Kincl
4089 | 2891 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q4 | 12 hrs | 17 days | Fri 6/20/25 | Tue 7/15/25
4090 | 2892 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 6/20/25 | Thu 6/26/25 | 2890 | 2893 |  | Jennifer Grant,Jennifer Reeves
4091 | 2893 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 6/27/25 | Thu 7/3/25 | 2892 | 2894 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4092 | 2894 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Mon 7/7/25 | Fri 7/11/25 | 2893 | 2895 |  | Jimmy Cox,Steven Fielder
4093 | 2895 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Mon 7/14/25 | Tue 7/15/25 | 2894 | 2897 |  | Dusti Kincl
4094 | 2896 | Future Task | [5 empty] | Quarterly Newsletter FY 25-26 Q1 | 12 hrs | 17 days | Fri 9/26/25 | Mon 10/20/25
4095 | 2897 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 9/26/25 | Thu 10/2/25 | 2895 | 2898 |  | Jennifer Grant,Jennifer Reeves
4096 | 2898 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 10/3/25 | Thu 10/9/25 | 2897 | 2899 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4097 | 2899 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 10/10/25 | Thu 10/16/25 | 2898 | 2900 |  | Jimmy Cox,Steven Fielder
4098 | 2900 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 10/17/25 | Mon 10/20/25 | 2899 | 2902 |  | Dusti Kincl
4099 | 2901 | Future Task | [5 empty] | Quarterly Newsletter FY 25-26 Q2 | 12 hrs | 17 days | Thu 1/8/26 | Mon 2/2/26
4100 | 2902 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Thu 1/8/26 | Wed 1/14/26 | 2900 | 2903 |  | Jennifer Grant,Jennifer Reeves
4101 | 2903 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Thu 1/15/26 | Thu 1/22/26 | 2902 | 2904 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4102 | 2904 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 1/23/26 | Thu 1/29/26 | 2903 | 2905 |  | Jimmy Cox,Steven Fielder
4103 | 2905 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 1/30/26 | Mon 2/2/26 | 2904 |  |  | Dusti Kincl

## RESOURCE ONLY -- 6.9.2023 (hidden)
Unique ID | ID | Status | Critical Path Items | RW | DEL, WP, SG # | Task Coordinator | Task Type | Task Name | Work | Duration | Start | Finish | Predecessors | Successors | Notes | Resource Names | Requested Updates | Requested By
0 | 0 | Late | [5 empty] | Project Schedule (Financials, Payroll, Data Warehouse and Business Intelligence) | 38,733.02 hrs | 1177 days | Wed 4/26/23 | Tue 12/28/27
7152 | 1 | Complete |  |  |  | Jimmy Cox | Milestone | Amendment 8 Executed | 0 hrs | 0 days | Wed 4/26/23 | Wed 4/26/23 |  | 11,34FS+3 days,53FS+47 days,91FS+27 days,112FS+27 days,217,348FS+91 days,190,204,602FS+47 days,72FS+27 days,152,171,230,244,258,335,388,444,466,486,506,526,539,643,686,746,787,814,833,852,894,919,938,1011,1030,1055,1069,1149,1163,1188,1202,1262,1298,135... |  | Jimmy Cox
2 | 2 | Late | [5 empty] | Implementation | 30,525.69 hrs | 699 days | Wed 4/26/23 | Wed 2/4/26
3769 | 3 | Late | [5 empty] | Design | 5,219.11 hrs | 475 days | Wed 4/26/23 | Fri 3/14/25
7172 | 4 | Future Task |  |  | SG1 | Jimmy Cox | Create | Stage Gate 1: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 7/3/23 | Mon 7/10/23 |  | 5 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7170 | 5 | Future Task |  |  | SG1 | Jimmy Cox | Create | Stage Gate 1: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Tue 7/11/23 | Mon 7/24/23 | 4 | 6FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7171 | 6 | Future Task |  |  | SG1 | Jimmy Cox | Create | Stage Gate 1: Prepare information package for ESC | 11 hrs | 10 days | Mon 11/13/23 | Tue 11/28/23 | 5FS+77 days | 7 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7169 | 7 | Future Task |  |  | SG1 | Jimmy Cox | Create | Stage Gate 1: Collaborative Review and Update of information package | 11 hrs | 5 days | Wed 11/29/23 | Tue 12/5/23 | 6 | 8 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7168 | 8 | Future Task |  |  | SG1 | Jimmy Cox | Create | Stage Gate 1: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 12/6/23 | Wed 12/6/23 | 7 |  |  | Dusti Kincl
7155 | 9 | Future Task |  |  | SG1 | Jimmy Cox | Milestone | Stage Gate 1: Ready to Start Build | 0 hrs | 0 days | Mon 10/23/23 | Mon 10/23/23 | 51,61 |  | Nov/Dec 2023 | Jimmy Cox,Angie Robertson,Matt Cole
3793 | 10 | On Schedule | Yes |  | D635 | Joy Schneider |  | D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) | 403 hrs | 38 days | Mon 5/8/23 | Thu 6/29/23
7130 | 11 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Develop Outline of Project Schedule | 2 hrs | 1 day | Mon 5/8/23 | Mon 5/8/23 | 1 | 12SS |  | Joy Schneider,Francisca Li
7131 | 12 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Create New Schedule Tasks Workbook | 4 hrs | 1 day | Mon 5/8/23 | Mon 5/8/23 | 11SS | 13,14,15FS+1 day |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner
7132 | 13 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Gather Tasks from State Architects | 60 hrs | 4 days | Tue 5/9/23 | Fri 5/12/23 | 12 | 23 |  | Julian Gotreaux,Gabriela Gibson,Tommy Werner,Angie Robertson,Deana Metcalf,Carolyn Hicks,Jennifer Reeves,Matthew Breeding
7133 | 14 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Load Amendment 8 Deliverables and Work Products to Project Schedule | 4 hrs | 2 days | Tue 5/9/23 | Wed 5/10/23 | 12 | 23 |  | Joy Schneider,Francisca Li
7134 | 15 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Load Resources into Project Schedule | 8 hrs | 1 day | Wed 5/10/23 | Wed 5/10/23 | 12FS+1 day | 16 |  | Joy Schneider,Francisca Li
7135 | 16 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Add and Refine Work Activities for Amendment 8 Deliverables | 17 hrs | 2 days | Thu 5/11/23 | Fri 5/12/23 | 15 | 17SS+1 day |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole
7136 | 17 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Add Tasks from State Architects | 10 hrs | 1 day | Fri 5/12/23 | Fri 5/12/23 | 16SS+1 day | 18,19 |  | Joy Schneider,Francisca Li
7138 | 18 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Add and Refine Work Activities for Amendment 8 Work Products | 60 hrs | 5 days | Mon 5/15/23 | Fri 5/19/23 | 17 | 23 |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole
7139 | 19 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Project Schedule Working Sessions | 85 hrs | 5 days | Mon 5/15/23 | Fri 5/19/23 | 17 | 20 |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Manojkumar Gurjar,Yogesh Deshmukh,Matt Cole,Angie Robertson,Deana Metcalf,Matthew Breeding,Carolyn Hicks,Jimmy Cox,Jennifer Reeves
7140 | 20 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Refine Work Activities for Non-SSI Deliverables and Work Products | 26 hrs | 5 days | Mon 5/22/23 | Fri 5/26/23 | 19 | 21SS+2 days |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Gabriela Gibson
7141 | 21 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Define Tasks to Assign to Critical Path Column | 25 hrs | 11 days | Wed 5/24/23 | Thu 6/8/23 | 20SS+2 days | 22 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Jimmy Cox,Matt Cole
7142 | 22 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Provide Project Schedule Export Reports and Refine Based on Input | 25 hrs | 9 days | Tue 5/30/23 | Fri 6/9/23 | 21 | 23 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Deana Metcalf,Matthew Breeding,Carlos Luis,Jimmy Cox,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Manojkumar Gurjar,Yogesh Deshmukh,Matt Cole,Jennifer Reeves
7143 | 23 | Future Task |  |  | D635 | Joy Schneider | Create | D635 - Conduct Project Schedule Baseline Prep Meeting | 36 hrs | 1 day | Mon 6/12/23 | Mon 6/12/23 | 22,13,14,18 | 24 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Deana Metcalf,Matthew Breeding,Carolyn Hicks,Jimmy Cox,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole,Gabriela Gibson,Jennifer Reeves
4271 | 24 | Future Task |  |  | D635 | Joy Schneider | Submit | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Draft Submission | 0 hrs | 0 days | Mon 6/12/23 | Mon 6/12/23 | 23 | 25 |  | Joy Schneider
4272 | 25 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Pre-Submission Collaborative Review | 14 hrs | 3 days | Tue 6/13/23 | Thu 6/15/23 | 24 | 26 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Gabriela Gibson,Jenifer Hartsfield,Angie Robertson
4273 | 26 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Style Guide Review | 1 hr | 1 day | Fri 6/16/23 | Fri 6/16/23 | 25 | 27 |  | Dusti Kincl
4274 | 27 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Final Collaborative Review | 10 hrs | 3 days | Mon 6/19/23 | Wed 6/21/23 | 26 | 28 |  | Joy Schneider,Francisca Li,Angie Robertson,Jimmy Cox,Jennifer Reeves,Deana Metcalf,Matthew Breeding,Carolyn Hicks
4275 | 28 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Accenture QC | 4 hrs | 2 days | Thu 6/22/23 | Fri 6/23/23 | 27 | 29 |  | Joy Schneider
4276 | 29 | Future Task |  |  | D635 | Joy Schneider | Submit | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Submit | 0 hrs | 0 days | Fri 6/23/23 | Fri 6/23/23 | 28 | 30 |  | Joy Schneider
4277 | 30 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Department QC | 4 hrs | 1 day | Mon 6/26/23 | Mon 6/26/23 | 29 | 31 |  | Tommy Werner,Gabriela Gibson
4278 | 31 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Contract Manager Review | 8 hrs | 3 days | Tue 6/27/23 | Thu 6/29/23 | 30 | 32 |  | Sean Buchanan
4279 | 32 | Future Task |  |  | D635 | Joy Schneider | Accept | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Accept | 0 hrs | 0 days | Thu 6/29/23 | Thu 6/29/23 | 31 | 2360 | 2023-06-01 | Sean Buchanan
4280 | 33 | Late | Yes |  | D636 | Stacey Terry |  | D636 - Completion of Solution Design (Requirements) Segment I | 309 hrs | 82 days | Mon 5/1/23 | Thu 8/24/23
4308 | 34 | Late |  |  | D636 | Stacey Terry | Create | D636 - Identify Functional Designs (Segment I) | 50 hrs | 10 days | Mon 5/1/23 | Fri 5/12/23 | 1FS+3 days | 35 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4281 | 35 | Late |  |  | D636 | Stacey Terry | Create | DED D636 - Completion of Solution Design (Requirements) Segment I - Create | 8 hrs | 10 days | Mon 5/15/23 | Fri 5/26/23 | 34 | 36 |  | Stacey Terry,Mary Punty
4282 | 36 | Late |  |  | D636 | Stacey Terry | Submit | DED D636 - Completion of Solution Design (Requirements) Segment I - Submit | 0 hrs | 0 days | Fri 5/26/23 | Fri 5/26/23 | 35 | 37 |  | Stacey Terry,Joy Schneider
4283 | 37 | Late |  |  | D636 | Stacey Terry | Review | DED D636 - Completion of Solution Design (Requirements) Segment I - Collaborative Review | 24 hrs | 4 days | Tue 5/30/23 | Fri 6/2/23 | 36 | 38 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4284 | 38 | Late |  |  | D636 | Stacey Terry | Approve | DED D636 - Completion of Solution Design (Requirements) Segment I - Approve | 0 hrs | 0 days | Fri 6/2/23 | Fri 6/2/23 | 37 | 39 |  | Jimmy Cox
4309 | 39 | Future Task |  |  | D636 | Stacey Terry | Create | D636 - Update Deliverable Work Unit Tracker for Functional Designs (Segment I) | 50 hrs | 5 days | Mon 6/5/23 | Fri 6/9/23 | 38 | 40 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4310 | 40 | Future Task |  |  | D636 | Stacey Terry | Create | D636 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment I) | 50 hrs | 4 days | Mon 6/12/23 | Thu 6/15/23 | 39 | 41 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4311 | 41 | Future Task |  | RW-Communication - Segment 1 Workshop? (suggest move to IWP101) | D636 | Stacey Terry | Create | D636 - Create, Review and Approve Functional Design Documents (Segment I) | 50 hrs | 32 days | Fri 6/16/23 | Tue 8/1/23 | 40 | 42FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4312 | 42 | Future Task |  |  | D636 | Stacey Terry | Create | D636 - Create Summary Document | 20 hrs | 11 days | Tue 7/18/23 | Tue 8/1/23 | 41FS-11 days | 43,1587SS,1631SS,1674SS,1499,1544 |  | Deana Metcalf,Stacey Terry,Mary Punty
4285 | 43 | Future Task |  |  | D636 | Stacey Terry | Submit | DEL D636 - Completion of Solution Design (Requirements) Segment I - Draft Submission | 0 hrs | 0 days | Tue 8/1/23 | Tue 8/1/23 | 42 | 44 |  | Stacey Terry,Joy Schneider
4286 | 44 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Wed 8/2/23 | Tue 8/8/23 | 43 | 45 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4287 | 45 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Style Guide Review | 1 hr | 1 day | Wed 8/9/23 | Wed 8/9/23 | 44 | 46 |  | Dusti Kincl
4288 | 46 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Final Collaborative Review | 20 hrs | 5 days | Thu 8/10/23 | Wed 8/16/23 | 45 | 47 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4289 | 47 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Accenture QC | 4 hrs | 2 days | Thu 8/17/23 | Fri 8/18/23 | 46 | 48 |  | Joy Schneider
4290 | 48 | Future Task |  |  | D636 | Stacey Terry | Submit | DEL D636 - Completion of Solution Design (Requirements) Segment I - Submit | 0 hrs | 0 days | Fri 8/18/23 | Fri 8/18/23 | 47 | 491709 |  | Joy Schneider
4291 | 49 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Department QC | 4 hrs | 1 day | Mon 8/21/23 | Mon 8/21/23 | 48 | 50 |  | Tommy Werner,Gabriela Gibson
4292 | 50 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Contract Manager Review | 8 hrs | 3 days | Tue 8/22/23 | Thu 8/24/23 | 49 | 51 |  | Sean Buchanan
4293 | 51 | Future Task |  |  | D636 | Stacey Terry | Accept | DEL D636 - Completion of Solution Design (Requirements) Segment I - Accept | 0 hrs | 0 days | Thu 8/24/23 | Thu 8/24/23 | 50 | 221,580,594,600,9,571 | July 2023 (Aug 2023) | Sean Buchanan
4294 | 52 | Future Task | Yes |  | D637 | Stacey Terry |  | D637 - Completion of Solution Design (Requirements) Segment II | 342 hrs | 96 days | Mon 7/3/23 | Thu 11/16/23
4313 | 53 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Identify Functional Designs (Segment II) | 50 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 1FS+47 days | 54 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4295 | 54 | Future Task |  |  | D637 | Stacey Terry | Create | DED D637 - Completion of Solution Design (Requirements) Segment II - Create | 16 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 53 | 55 |  | Stacey Terry,Mary Punty
4296 | 55 | Future Task |  |  | D637 | Stacey Terry | Submit | DED D637 - Completion of Solution Design (Requirements) Segment II - Submit | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 54 | 56 |  | Stacey Terry,Joy Schneider
4297 | 56 | Future Task |  |  | D637 | Stacey Terry | Review | DED D637 - Completion of Solution Design (Requirements) Segment II - Collaborative Review | 24 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 55 | 57 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4298 | 57 | Future Task |  |  | D637 | Stacey Terry | Approve | DED D637 - Completion of Solution Design (Requirements) Segment II - Approve | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 56 | 58 |  | Jimmy Cox
4314 | 58 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Update Deliverable Work Unit Tracker for Functional Designs (Segment II) | 50 hrs | 4 days | Tue 8/15/23 | Fri 8/18/23 | 57 | 59 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4315 | 59 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment II) | 50 hrs | 5 days | Mon 8/21/23 | Fri 8/25/23 | 58 | 60 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4316 | 60 | Future Task |  | RW-Communication - Segment 2 Workshop? (suggest move to IWP101) | D637 | Stacey Terry | Create | D637 - Create, Review and Approve Functional Design Documents (Segment II) | 50 hrs | 40 days | Mon 8/28/23 | Mon 10/23/23 | 59 | 61FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4317 | 61 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Create Summary Document | 50 hrs | 11 days | Mon 10/9/23 | Mon 10/23/23 | 60FS-11 days | 62,1590SS,1456SS,1634SS+2 days,1677SS+5 days,1502,1547,9 |  | Deana Metcalf,Stacey Terry,Mary Punty
4299 | 62 | Future Task |  |  | D637 | Stacey Terry | Submit | DEL D637 - Completion of Solution Design (Requirements) Segment II - Draft Submission | 0 hrs | 0 days | Mon 10/23/23 | Mon 10/23/23 | 61 | 63 |  | Stacey Terry,Joy Schneider
4300 | 63 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 10/24/23 | Mon 10/30/23 | 62 | 64 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4301 | 64 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Style Guide Review | 1 hr | 1 day | Tue 10/31/23 | Tue 10/31/23 | 63 | 65 |  | Dusti Kincl
4302 | 65 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Final Collaborative Review | 20 hrs | 5 days | Wed 11/1/23 | Tue 11/7/23 | 64 | 66 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4303 | 66 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Accenture QC | 1 hr | 2 days | Wed 11/8/23 | Thu 11/9/23 | 65 | 67 |  | Francisca Li
4304 | 67 | Future Task |  |  | D637 | Stacey Terry | Submit | DEL D637 - Completion of Solution Design (Requirements) Segment II - Submit | 0 hrs | 0 days | Thu 11/9/23 | Thu 11/9/23 | 66 | 68 |  | Joy Schneider
4305 | 68 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Department QC | 2 hrs | 1 day | Mon 11/13/23 | Mon 11/13/23 | 67 | 69 |  | Tommy Werner,Gabriela Gibson
4306 | 69 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Contract Manager Review | 8 hrs | 3 days | Tue 11/14/23 | Thu 11/16/23 | 68 | 70 |  | Sean Buchanan
4307 | 70 | Future Task |  |  | D637 | Stacey Terry | Accept | DEL D637 - Completion of Solution Design (Requirements) Segment II - Accept | 0 hrs | 0 days | Thu 11/16/23 | Thu 11/16/23 | 69 | 580594600571 | October 2023 (Nov 2023) | Sean Buchanan
5585 | 71 | Future Task | Yes |  | D638 | Manojkumar Gurjar |  | D638 - Updated Data Conversion and Migration Strategy | 209 hrs | 80 days | Mon 6/5/23 | Tue 9/26/23
5586 | 72 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | DED D638 - Updated Data Conversion and Migration Strategy - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 73 |  | Manojkumar Gurjar,Kurt Meisner
5587 | 73 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DED D638 - Updated Data Conversion and Migration Strategy - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 72 | 74 |  | Manojkumar Gurjar,Joy Schneider
5588 | 74 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DED D638 - Updated Data Conversion and Migration Strategy - Collaborative Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 73 | 75 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5589 | 75 | Future Task |  |  | D638 | Manojkumar Gurjar | Approve | DED D638 - Updated Data Conversion and Migration Strategy - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 74 | 76 |  | Jimmy Cox
5590 | 76 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | D638 - Define the approach for Data Cleansing | 4 hrs | 14 days | Mon 7/3/23 | Fri 7/21/23 | 75 | 77SS+4 days |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5591 | 77 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | D638 - Define Communication/Collaboration for Data Conversion approach | 4 hrs | 10 days | Mon 7/10/23 | Fri 7/21/23 | 76SS+4 days | 79,78SS |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
7245 | 78 | Future Task |  | RW | D638 | Manojkumar Gurjar | Create | D638 - Create Conversion Approach document | 4 hrs | 10 days | Mon 7/10/23 | Fri 7/21/23 | 77SS | 79 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5592 | 79 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | D638 - Identify Data Conversion Resources | 50 hrs | 10 days | Mon 7/24/23 | Fri 8/4/23 | 77,78 | 80 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer,Jeevan Mahajan,Janmejay Khare
5593 | 80 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | D638 - Updated Data Conversion and Migration Strategy Document | 50 hrs | 19 days | Mon 8/7/23 | Thu 8/31/23 | 79 | 81 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5594 | 81 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DEL D638 - Updated Data Conversion and Migration Strategy - Draft Submission | 0 hrs | 0 days | Thu 8/31/23 | Thu 8/31/23 | 80 | 82 |  | Manojkumar Gurjar,Joy Schneider
5595 | 82 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 81 | 83 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5596 | 83 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Style Guide Review | 1 hr | 1 day | Mon 9/11/23 | Mon 9/11/23 | 82 | 84 |  | Dusti Kincl
5597 | 84 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Final Collaborative Review | 20 hrs | 5 days | Tue 9/12/23 | Mon 9/18/23 | 83 | 85 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5598 | 85 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Accenture QC | 4 hrs | 2 days | Tue 9/19/23 | Wed 9/20/23 | 84 | 86 |  | Joy Schneider
5599 | 86 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DEL D638 - Updated Data Conversion and Migration Strategy - Submit | 0 hrs | 0 days | Wed 9/20/23 | Wed 9/20/23 | 85 | 87 |  | Joy Schneider
5600 | 87 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Department QC | 4 hrs | 1 day | Thu 9/21/23 | Thu 9/21/23 | 86 | 88 |  | Tommy Werner,Gabriela Gibson
5601 | 88 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Contract Manager Review | 8 hrs | 3 days | Fri 9/22/23 | Tue 9/26/23 | 87 | 89 |  | Sean Buchanan
5602 | 89 | Future Task |  |  | D638 | Manojkumar Gurjar | Accept | DEL D638 - Updated Data Conversion and Migration Strategy - Accept | 0 hrs | 0 days | Tue 9/26/23 | Tue 9/26/23 | 88 |  | 2023-10-01 | Sean Buchanan
4375 | 90 | Future Task | Yes |  | D639 | Stacey Terry |  | D639 - Development of Standardized Business Process Models – Payroll | 241 hrs | 94 days | Mon 6/5/23 | Mon 10/16/23
4376 | 91 | Future Task |  |  | D639 | Stacey Terry | Create | DED D639 - Development of Standardized Business Process Models – Payroll - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 92 |  | Stacey Terry,Mary Punty
4377 | 92 | Future Task |  |  | D639 | Stacey Terry | Submit | DED D639 - Development of Standardized Business Process Models – Payroll - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 91 | 93 |  | Stacey Terry,Joy Schneider
4378 | 93 | Future Task |  |  | D639 | Stacey Terry | Review | DED D639 - Development of Standardized Business Process Models – Payroll - Collaborative Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 92 | 94 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4379 | 94 | Future Task |  |  | D639 | Stacey Terry | Approve | DED D639 - Development of Standardized Business Process Models – Payroll - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 93 | 95 |  | Jimmy Cox
4417 | 95 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Identify Payroll Wave Business Processes and Subprocesses | 25 hrs | 5 days | Mon 7/3/23 | Mon 7/10/23 | 94 | 96SS+2 days |  | Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari
4418 | 96 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Update Deliverable Work Unit Tracker for Payroll Wave Business Processes and Subprocesses | 4 hrs | 5 days | Thu 7/6/23 | Wed 7/12/23 | 95SS+2 days | 97 |  | Stacey Terry,Yogesh Deshmukh
4419 | 97 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Review and Confirm Deliverable Work Unit Tracker for Payroll Wave Business Processes and Subprocesses | 20 hrs | 5 days | Thu 7/13/23 | Wed 7/19/23 | 96 | 98SS |  | Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4420 | 98 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Create Payroll Wave Business Process Models | 30 hrs | 30 days | Thu 7/13/23 | Wed 8/23/23 | 97SS | 99 |  | Jimmy Cox,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari,Heather Cleary,Joanne Lane,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Donnie Doctor,Ryan R...
4421 | 99 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Prepare Materials / Conduct Office Hours | 25 hrs | 10 days | Thu 8/24/23 | Thu 9/7/23 | 98 | 100 |  | Jimmy Cox,Angie Robertson,Carolyn Hicks,Dusti Kincl,Kimberly Kemp,Deana Metcalf,Stacey Terry,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Janice Jackson,LaVondria Norton,Robert Hic...
4422 | 100 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Refine Payroll Wave Business Process Models | 20 hrs | 5 days | Fri 9/8/23 | Thu 9/14/23 | 99 | 101 |  | Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari
4423 | 101 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Create Summary Document | 20 hrs | 5 days | Fri 9/15/23 | Thu 9/21/23 | 100 | 102 |  | Deana Metcalf,Stacey Terry,Mary Punty
4380 | 102 | Future Task |  |  | D639 | Stacey Terry | Submit | DEL D639 - Development of Standardized Business Process Models – Payroll - Draft Submission | 0 hrs | 0 days | Thu 9/21/23 | Thu 9/21/23 | 101 | 103 |  | Stacey Terry,Joy Schneider
4381 | 103 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 9/22/23 | Thu 9/28/23 | 102 | 104 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4382 | 104 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Style Guide Review | 1 hr | 1 day | Fri 9/29/23 | Fri 9/29/23 | 103 | 105 |  | Dusti Kincl
4383 | 105 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Final Collaborative Review | 20 hrs | 5 days | Mon 10/2/23 | Fri 10/6/23 | 104 | 106 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4384 | 106 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Accenture QC | 4 hrs | 2 days | Mon 10/9/23 | Tue 10/10/23 | 105 | 107 |  | Joy Schneider
4385 | 107 | Future Task |  |  | D639 | Stacey Terry | Submit | DEL D639 - Development of Standardized Business Process Models – Payroll - Submit | 0 hrs | 0 days | Tue 10/10/23 | Tue 10/10/23 | 106 | 108 |  | Joy Schneider
4386 | 108 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Department QC | 4 hrs | 1 day | Wed 10/11/23 | Wed 10/11/23 | 107 | 109 |  | Tommy Werner,Gabriela Gibson
4387 | 109 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Contract Manager Review | 8 hrs | 3 days | Thu 10/12/23 | Mon 10/16/23 | 108 | 110 |  | Sean Buchanan
4388 | 110 | Future Task |  | RW-Communication | D639 | Stacey Terry | Accept | DEL D639 - Development of Standardized Business Process Models – Payroll - Accept | 0 hrs | 0 days | Mon 10/16/23 | Mon 10/16/23 | 109 | 1853580 | 2023-10-01 | Sean Buchanan
4389 | 111 | Future Task | Yes |  | D640 | Stacey Terry |  | D640 - Development of the Master Data Configuration Workbooks | 311 hrs | 142 days | Mon 6/5/23 | Wed 12/27/23
4390 | 112 | Future Task |  |  | D640 | Stacey Terry | Create | DED D640 - Development of the Master Data Configuration Workbooks - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 113,116SS+9 days |  | Stacey Terry,Mary Punty
4391 | 113 | Future Task |  |  | D640 | Stacey Terry | Submit | DED D640 - Development of the Master Data Configuration Workbooks - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 112 | 114 |  | Stacey Terry,Joy Schneider
4392 | 114 | Future Task |  |  | D640 | Stacey Terry | Review | DED D640 - Development of the Master Data Configuration Workbooks - Collaborative Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 113 | 115 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4393 | 115 | Future Task |  |  | D640 | Stacey Terry | Approve | DED D640 - Development of the Master Data Configuration Workbooks - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 114 |  |  | Jimmy Cox
4424 | 116 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Identify Configuration Inventory | 20 hrs | 10 days | Fri 6/16/23 | Thu 6/29/23 | 112SS+9 days | 117 |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Donnie Doctor,Ryan Raagas,Pooj...
4425 | 117 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Update Design Work Unit Tracker for Configuration | 4 hrs | 5 days | Fri 6/30/23 | Fri 7/7/23 | 116 | 118 |  | Stacey Terry,Yogesh Deshmukh
4426 | 118 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Review and Confirm Design Work Unit Tracker for Configuration | 50 hrs | 4 days | Mon 7/10/23 | Thu 7/13/23 | 117 | 119 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4427 | 119 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Create, Review, and Confirm Configuration Workbooks and Agency Configuration Workbook Templates | 40 hrs | 80 days | Fri 7/14/23 | Fri 11/3/23 | 118 | 120SS+20 days |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Donnie Doctor,Ryan Raagas,Pooj...
4428 | 120 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Configure Application | 40 hrs | 70 days | Fri 8/11/23 | Mon 11/20/23 | 119SS+20 days | 121 |  | Apoorva Panchanadikar,Divya Gupta,Supriya Vaddi,Suyesh Shingare,Purushottam Karambelkar,Ankita Sarang,Yash Jamkhedkar,Sajal Saurabh,Timtim Goel
4429 | 121 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Finalize Configuration Workbooks | 30 hrs | 10 days | Tue 11/21/23 | Wed 12/6/23 | 120 | 122FS-10 days |  | Apoorva Panchanadikar,Divya Gupta,Supriya Vasudevan,Suyesh Shingare,Purushottam Karambelkar,Ankita Sarang,Yash Jamkhedkar,Sajal Saurabh,Timtim Goel,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Jack Je...
4430 | 122 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Create Summary Document | 30 hrs | 7 days | Tue 11/21/23 | Fri 12/1/23 | 121FS-10 days | 123 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Mary Punty
4394 | 123 | Future Task |  |  | D640 | Stacey Terry | Submit | DEL D640 - Development of the Master Data Configuration Workbooks - Draft Submission | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 122 | 124 |  | Stacey Terry,Joy Schneider
4395 | 124 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 12/4/23 | Fri 12/8/23 | 123 | 125 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4396 | 125 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Style Guide Review | 1 hr | 1 day | Mon 12/11/23 | Mon 12/11/23 | 124 | 126 |  | Dusti Kincl
4397 | 126 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Final Collaborative Review | 20 hrs | 5 days | Tue 12/12/23 | Mon 12/18/23 | 125 | 127 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4398 | 127 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Accenture QC | 4 hrs | 2 days | Tue 12/19/23 | Wed 12/20/23 | 126 | 128 |  | Joy Schneider
4399 | 128 | Future Task |  |  | D640 | Stacey Terry | Submit | DEL D640 - Development of the Master Data Configuration Workbooks - Submit | 0 hrs | 0 days | Wed 12/20/23 | Wed 12/20/23 | 127 | 129 |  | Joy Schneider
4400 | 129 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Department QC | 4 hrs | 1 day | Thu 12/21/23 | Thu 12/21/23 | 128 | 130 |  | Tommy Werner,Gabriela Gibson
4401 | 130 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Contract Manager Review | 8 hrs | 3 days | Fri 12/22/23 | Wed 12/27/23 | 129 | 131 |  | Sean Buchanan
4402 | 131 | Future Task |  | RW-Communication | D640 | Stacey Terry | Accept | DEL D640 - Development of the Master Data Configuration Workbooks - Accept | 0 hrs | 0 days | Wed 12/27/23 | Wed 12/27/23 | 130 | 576FS+6 days | 2023-12-01 | Sean Buchanan
4318 | 132 | Future Task |  |  | D641 | Stacey Terry |  | D641 - Completion of Solution Design (Requirements) Segment III | 327 hrs | 96 days | Mon 10/2/23 | Tue 2/20/24
4332 | 133 | Future Task |  |  | D641 | Stacey Terry | Create | Identify Functional Designs (Segment III) | 50 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 1 | 134 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4319 | 134 | Future Task |  |  | D641 | Stacey Terry | Create | DED D641 - Completion of Solution Design (Requirements) Segment III - Create | 16 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 133 | 135 |  | Stacey Terry,Mary Punty
4320 | 135 | Future Task |  |  | D641 | Stacey Terry | Submit | DED D641 - Completion of Solution Design (Requirements) Segment III - Submit | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 134 | 136 |  | Stacey Terry,Joy Schneider
4321 | 136 | Future Task |  |  | D641 | Stacey Terry | Review | DED D641 - Completion of Solution Design (Requirements) Segment III - Collaborative Review | 24 hrs | 10 days | Mon 10/30/23 | Mon 11/13/23 | 135 | 137 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4322 | 137 | Future Task |  |  | D641 | Stacey Terry | Approve | DED D641 - Completion of Solution Design (Requirements) Segment III - Approve | 0 hrs | 0 days | Mon 11/13/23 | Mon 11/13/23 | 136 | 138 |  | Jimmy Cox
4333 | 138 | Future Task |  |  | D641 | Stacey Terry | Create | D641 - Update Deliverable Work Unit Tracker for Functional Designs (Segment III) | 40 hrs | 4 days | Tue 11/14/23 | Fri 11/17/23 | 137 | 139 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4334 | 139 | Future Task |  |  | D641 | Stacey Terry | Create | D641 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment III) | 40 hrs | 5 days | Mon 11/20/23 | Tue 11/28/23 | 138 | 140 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4335 | 140 | Future Task |  | RW-Communication (suggest move to IWP101) | D641 | Stacey Terry | Create | D641 - Create, Review and Approve Functional Design Documents (Segment III) | 50 hrs | 40 days | Wed 11/29/23 | Fri 1/26/24 | 139 | 141FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4336 | 141 | Future Task |  |  | D641 | Stacey Terry | Create | D641 - Create Summary Document | 50 hrs | 11 days | Thu 1/11/24 | Fri 1/26/24 | 140FS-11 days | 142,1593SS,1637SS,1680SS+5 days,1505SS,1550,1459SS |  | Deana Metcalf,Stacey Terry,Mary Punty
4323 | 142 | Future Task |  |  | D641 | Stacey Terry | Submit | DEL D641 - Completion of Solution Design (Requirements) Segment III - Draft Submission | 0 hrs | 0 days | Fri 1/26/24 | Fri 1/26/24 | 141 | 143 |  | Stacey Terry,Joy Schneider
4324 | 143 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 1/29/24 | Fri 2/2/24 | 142 | 144 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4325 | 144 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Style Guide Review | 1 hr | 1 day | Mon 2/5/24 | Mon 2/5/24 | 143 | 145 |  | Dusti Kincl
4326 | 145 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Final Collaborative Review | 20 hrs | 5 days | Tue 2/6/24 | Mon 2/12/24 | 144 | 146 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4327 | 146 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Accenture QC | 4 hrs | 2 days | Tue 2/13/24 | Wed 2/14/24 | 145 | 147 |  | Joy Schneider
4328 | 147 | Future Task |  |  | D641 | Stacey Terry | Submit | DEL D641 - Completion of Solution Design (Requirements) Segment III - Submit | 0 hrs | 0 days | Wed 2/14/24 | Wed 2/14/24 | 146 | 148 |  | Joy Schneider
4329 | 148 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Department QC | 4 hrs | 1 day | Thu 2/15/24 | Thu 2/15/24 | 147 | 149 |  | Tommy Werner,Gabriela Gibson
4330 | 149 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Contract Manager Review | 8 hrs | 3 days | Fri 2/16/24 | Tue 2/20/24 | 148 | 150 |  | Sean Buchanan
4331 | 150 | Future Task |  |  | D641 | Stacey Terry | Accept | DEL D641 - Completion of Solution Design (Requirements) Segment III - Accept | 0 hrs | 0 days | Tue 2/20/24 | Tue 2/20/24 | 149 | 580594600571 | January 2024 (Feb 2024) | Sean Buchanan
4337 | 151 | Future Task | Yes |  | D644 | Stacey Terry |  | D644 - Completion of Solution Design (Requirements) Segment IV | 337 hrs | 85 days | Mon 1/29/24 | Fri 5/24/24
4351 | 152 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Identify Functional Designs (Segment IV) | 50 hrs | 10 days | Mon 1/29/24 | Fri 2/9/24 | 1 | 153 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4338 | 153 | Future Task |  |  | D644 | Stacey Terry | Create | DED D644 - Completion of Solution Design (Requirements) Segment IV - Create | 16 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 152 | 154 |  | Stacey Terry,Mary Punty
4339 | 154 | Future Task |  |  | D644 | Stacey Terry | Submit | DED D644 - Completion of Solution Design (Requirements) Segment IV - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 153 | 155 |  | Stacey Terry,Joy Schneider
4340 | 155 | Future Task |  |  | D644 | Stacey Terry | Review | DED D644 - Completion of Solution Design (Requirements) Segment IV - Collaborative Review | 24 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 154 | 156 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4341 | 156 | Future Task |  |  | D644 | Stacey Terry | Approve | DED D644 - Completion of Solution Design (Requirements) Segment IV - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 155 | 157 |  | Jimmy Cox
4352 | 157 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Update Deliverable Work Unit Tracker for Functional Designs (Segment IV) | 50 hrs | 4 days | Mon 3/11/24 | Thu 3/14/24 | 156 | 158 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4353 | 158 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment IV) | 50 hrs | 4 days | Fri 3/15/24 | Wed 3/20/24 | 157 | 159 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4354 | 159 | Future Task |  | RW-Communication (suggest move to IWP101) | D644 | Stacey Terry | Create | D644 - Create, Review and Approve Functional Design Documents (Segment IV) | 50 hrs | 30 days | Thu 3/21/24 | Wed 5/1/24 | 158 | 160FS-8 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4355 | 160 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Create Summary Document | 40 hrs | 8 days | Mon 4/22/24 | Wed 5/1/24 | 159FS-8 days | 161,1606SS,1650SS,1693SS+5 days,1518SS,1563SS |  | Deana Metcalf,Stacey Terry,Mary Punty
4342 | 161 | Future Task |  |  | D644 | Stacey Terry | Submit | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Draft Submission | 0 hrs | 0 days | Wed 5/1/24 | Wed 5/1/24 | 160 | 162 |  | Stacey Terry,Joy Schneider
4343 | 162 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Pre-Submission Collaborative Review | 20 hrs | 5 days | Thu 5/2/24 | Wed 5/8/24 | 161 | 163594 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4344 | 163 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Style Guide Review | 1 hr | 1 day | Thu 5/9/24 | Thu 5/9/24 | 162 | 164 |  | Dusti Kincl
4345 | 164 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Final Collaborative Review | 20 hrs | 5 days | Fri 5/10/24 | Thu 5/16/24 | 163 | 165 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4346 | 165 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Accenture QC | 4 hrs | 2 days | Fri 5/17/24 | Mon 5/20/24 | 164 | 166 |  | Joy Schneider
4347 | 166 | Future Task |  |  | D644 | Stacey Terry | Submit | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Submit | 0 hrs | 0 days | Mon 5/20/24 | Mon 5/20/24 | 165 | 167 |  | Joy Schneider
4348 | 167 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Department QC | 4 hrs | 1 day | Tue 5/21/24 | Tue 5/21/24 | 166 | 168 |  | Tommy Werner,Gabriela Gibson
4349 | 168 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Contract Manager Review | 8 hrs | 3 days | Wed 5/22/24 | Fri 5/24/24 | 167 | 169 |  | Sean Buchanan
4350 | 169 | Future Task |  |  | D644 | Stacey Terry | Accept | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Accept | 0 hrs | 0 days | Fri 5/24/24 | Fri 5/24/24 | 168 | 580FS+24 days,600,571FS+83 days | April 2024 (May 2024) | Sean Buchanan
4356 | 170 | Future Task | Yes |  | D650 | Stacey Terry |  | D650 - Completion of Solution Design (Requirements) DW/BI | 347 hrs | 160 days | Fri 3/1/24 | Tue 10/15/24
4357 | 171 | Future Task |  |  | D650 | Stacey Terry | Create | DED D650 - Completion of Solution Design (Requirements) DW/BI - Create | 16 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 1 | 172 |  | Stacey Terry,Mary Punty
4358 | 172 | Future Task |  |  | D650 | Stacey Terry | Submit | DED D650 - Completion of Solution Design (Requirements) DW/BI - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 171 | 173 |  | Stacey Terry,Joy Schneider
4359 | 173 | Future Task |  |  | D650 | Stacey Terry | Review | DED D650 - Completion of Solution Design (Requirements) DW/BI - Collaborative Review | 24 hrs | 10 days | Fri 3/15/24 | Thu 3/28/24 | 172 | 174 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4360 | 174 | Future Task |  |  | D650 | Stacey Terry | Approve | DED D650 - Completion of Solution Design (Requirements) DW/BI - Approve | 0 hrs | 0 days | Thu 3/28/24 | Thu 3/28/24 | 173 | 175 |  | Jimmy Cox
4370 | 175 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Identify Functional Designs DW/BI | 50 hrs | 10 days | Fri 3/29/24 | Thu 4/11/24 | 174 | 176 |  | Stacey Terry,Yogesh Deshmukh
4371 | 176 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Update Deliverable Work Unit Tracker for Functional Designs DW/BI | 50 hrs | 10 days | Fri 4/12/24 | Thu 4/25/24 | 175 | 177 |  | Stacey Terry,Yogesh Deshmukh
4372 | 177 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs DW/BI | 50 hrs | 10 days | Fri 4/26/24 | Thu 5/9/24 | 176 | 178 |  | Stacey Terry,Yogesh Deshmukh
4373 | 178 | Future Task |  | RW-Communication | D650 | Stacey Terry | Create | D650 - Create, Review and Approve Functional Design Documents DW/BI | 50 hrs | 82 days | Fri 5/10/24 | Thu 9/5/24 | 177 | 179 |  | Stacey Terry,Yogesh Deshmukh
4374 | 179 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Create Summary Document | 50 hrs | 11 days | Fri 9/6/24 | Fri 9/20/24 | 178 | 180 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4361 | 180 | Future Task |  |  | D650 | Stacey Terry | Submit | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Draft Submission | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 179 | 181 |  | Stacey Terry,Joy Schneider
4362 | 181 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 180 | 182 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4363 | 182 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Style Guide Review | 1 hr | 1 day | Mon 9/30/24 | Mon 9/30/24 | 181 | 183 |  | Dusti Kincl
4364 | 183 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Final Collaborative Review | 20 hrs | 5 days | Tue 10/1/24 | Mon 10/7/24 | 182 | 184 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4365 | 184 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Accenture QC | 4 hrs | 2 days | Tue 10/8/24 | Wed 10/9/24 | 183 | 185 |  | Joy Schneider
4366 | 185 | Future Task |  |  | D650 | Stacey Terry | Submit | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Submit | 0 hrs | 0 days | Wed 10/9/24 | Wed 10/9/24 | 184 | 186 |  | Joy Schneider
4367 | 186 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Department QC | 4 hrs | 1 day | Thu 10/10/24 | Thu 10/10/24 | 185 | 187 |  | Tommy Werner,Gabriela Gibson
4368 | 187 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Contract Manager Review | 8 hrs | 3 days | Fri 10/11/24 | Tue 10/15/24 | 186 | 188 |  | Sean Buchanan
4369 | 188 | Future Task |  |  | D650 | Stacey Terry | Accept | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Accept | 0 hrs | 0 days | Tue 10/15/24 | Tue 10/15/24 | 187 |  | 2024-10-01 | Sean Buchanan
4431 | 189 | Future Task |  |  | WP402 | Stacey Terry |  | WP402 - Requirements Traceability Matrix | 248 hrs | 60 days | Mon 6/19/23 | Tue 9/12/23
4432 | 190 | Future Task |  |  | WP402 | Stacey Terry | Create | WPED WP402 - Requirements Traceability Matrix - Create | 8 hrs | 5 days | Mon 6/19/23 | Fri 6/23/23 | 1 | 191 |  | Stacey Terry,Mary Punty
4433 | 191 | Future Task |  |  | WP402 | Stacey Terry | Submit | WPED WP402 - Requirements Traceability Matrix - Submit | 0 hrs | 0 days | Fri 6/23/23 | Fri 6/23/23 | 190 | 192 |  | Joy Schneider,Stacey Terry
4434 | 192 | Future Task |  |  | WP402 | Stacey Terry | Review | WPED WP402 - Requirements Traceability Matrix - Review | 12 hrs | 5 days | Mon 6/26/23 | Fri 6/30/23 | 191 | 193 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4435 | 193 | Future Task |  |  | WP402 | Stacey Terry | Approve | WPED WP402 - Requirements Traceability Matrix - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 192 | 194 |  | Jimmy Cox
4449 | 194 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Create Requirements Traceability Matrix Template | 2 hrs | 3 days | Mon 7/3/23 | Thu 7/6/23 | 193 | 195 |  | Stacey Terry,Yogesh Deshmukh
4450 | 195 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Populate Requirements Traceability Matrix Template | 160 hrs | 10 days | Fri 7/7/23 | Thu 7/20/23 | 194 | 196 |  | Stacey Terry,Yogesh Deshmukh
4451 | 196 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Create Summary Document | 6 hrs | 2 days | Fri 7/21/23 | Mon 7/24/23 | 195 | 197 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4436 | 197 | Future Task |  |  | WP402 | Stacey Terry | Submit | WP WP402 - Requirements Traceability Matrix - Submit | 0 hrs | 0 days | Mon 7/24/23 | Mon 7/24/23 | 196 | 198 |  | Joy Schneider,Stacey Terry
4437 | 198 | Future Task |  |  | WP402 | Stacey Terry | Review | WP WP402 - Requirements Traceability Matrix - Collaborative Review & Update | 20 hrs | 10 days | Tue 7/25/23 | Mon 8/7/23 | 197 | 199 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4438 | 199 | Future Task |  |  | WP402 | Stacey Terry | Review | WP WP402 - Requirements Traceability Matrix - Final Review & Edits | 20 hrs | 5 days | Tue 8/8/23 | Mon 8/14/23 | 198 | 200 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4439 | 200 | Future Task |  |  | WP402 | Stacey Terry | Approve | WP WP402 - Requirements Traceability Matrix - Approve | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 199 | 727,201FS+5 days | 2023-06-01 | Jimmy Cox
7147 | 201 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Load Requirements in Requirements Traceability Tool | 10 hrs | 5 days | Tue 8/22/23 | Mon 8/28/23 | 200FS+5 days | 202 |  | Mary Punty,Joy Schneider
7148 | 202 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Validate Requirements in Requirements Traceability Tool | 10 hrs | 10 days | Tue 8/29/23 | Tue 9/12/23 | 201 |  |  | Deana Metcalf,Stacey Terry
4440 | 203 | Future Task |  |  | WP403 | Stacey Terry |  | WP403 - RICEFW Inventory | 200 hrs | 64 days | Mon 6/19/23 | Mon 9/18/23
4441 | 204 | Future Task |  |  | WP403 | Stacey Terry | Create | WPED WP403 - RICEFW Inventory - Create | 16 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 1 | 205 |  | Stacey Terry,Mary Punty
4442 | 205 | Future Task |  |  | WP403 | Stacey Terry | Submit | WPED WP403 - RICEFW Inventory - Submit | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 204 | 206 |  | Joy Schneider,Stacey Terry
4443 | 206 | Future Task |  |  | WP403 | Stacey Terry | Review | WPED WP403 - RICEFW Inventory - Review | 24 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 205 | 207 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4444 | 207 | Future Task |  |  | WP403 | Stacey Terry | Approve | WPED WP403 - RICEFW Inventory - Approve | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 206 | 208 |  | Jimmy Cox
4454 | 208 | Future Task |  |  | WP403 | Stacey Terry | Create | WP403 - Create RICEFW Inventory Template | 20 hrs | 5 days | Tue 7/18/23 | Mon 7/24/23 | 207 | 209 |  | Deana Metcalf,Stacey Terry
4455 | 209 | Future Task |  |  | WP403 | Stacey Terry | Create | WP403 - Define and document RICEFW Inventory | 50 hrs | 14 days | Tue 7/25/23 | Fri 8/11/23 | 208 | 210 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4456 | 210 | Future Task |  |  | WP403 | Stacey Terry | Create | WP403 - Populate RICEFW Inventory Template | 20 hrs | 5 days | Mon 8/14/23 | Fri 8/18/23 | 209 | 211 |  | Deana Metcalf,Stacey Terry
4457 | 211 | Future Task |  |  | WP403 | Stacey Terry | Create | WP403 - Create Summary Document | 30 hrs | 5 days | Mon 8/21/23 | Fri 8/25/23 | 210 | 212 |  | Deana Metcalf,Stacey Terry,Mary Punty
4445 | 212 | Future Task |  |  | WP403 | Stacey Terry | Submit | WP WP403 - RICEFW Inventory - Submit | 0 hrs | 0 days | Fri 8/25/23 | Fri 8/25/23 | 211 | 213 |  | Joy Schneider,Stacey Terry
4446 | 213 | Future Task |  |  | WP403 | Stacey Terry | Review | WP WP403 - RICEFW Inventory - Collaborative Review & Update | 20 hrs | 10 days | Mon 8/28/23 | Mon 9/11/23 | 212 | 214 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4447 | 214 | Future Task |  |  | WP403 | Stacey Terry | Review | WP WP403 - RICEFW Inventory - Final Review & Edits | 20 hrs | 5 days | Tue 9/12/23 | Mon 9/18/23 | 213 | 215 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4448 | 215 | Future Task |  |  | WP403 | Stacey Terry | Approve | WP WP403 - RICEFW Inventory - Approve | 0 hrs | 0 days | Mon 9/18/23 | Mon 9/18/23 | 214 |  | 2024-04-01 | Jimmy Cox
5667 | 216 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | WP404 - Data Conversion Inventory | 250 hrs | 127 days | Mon 8/7/23 | Thu 2/8/24
5668 | 217 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WPED WP404 - Data Conversion Inventory - Create | 16 hrs | 10 days | Mon 8/7/23 | Fri 8/18/23 | 1 | 218 |  | Manojkumar Gurjar,Kurt Meisner
5669 | 218 | Future Task |  |  | WP404 | Manojkumar Gurjar | Submit | WPED WP404 - Data Conversion Inventory - Submit | 0 hrs | 0 days | Fri 8/18/23 | Fri 8/18/23 | 217 | 219 |  | Manojkumar Gurjar,Joy Schneider
5670 | 219 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WPED WP404 - Data Conversion Inventory - Review | 24 hrs | 10 days | Mon 8/21/23 | Fri 9/1/23 | 218 | 220 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5671 | 220 | Future Task |  |  | WP404 | Manojkumar Gurjar | Approve | WPED WP404 - Data Conversion Inventory - Approve | 0 hrs | 0 days | Fri 9/1/23 | Fri 9/1/23 | 219 | 221FS+19 days |  | Jimmy Cox
5672 | 221 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WP404 - Create Data Conversion Inventory Template | 50 hrs | 32 days | Mon 10/2/23 | Wed 11/15/23 | 220FS+19 days,51 | 222 |  | Manojkumar Gurjar,Kurt Meisner
5673 | 222 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WP404 - Populate Data Conversion Inventory with RICEFW Inventory conversion items | 50 hrs | 16 days | Thu 11/16/23 | Mon 12/11/23 | 221 | 223 |  | Manojkumar Gurjar,Kurt Meisner
5674 | 223 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WP404 - Identify/confirm Anticipated Source Systems and Legacy Tables | 50 hrs | 20 days | Tue 12/12/23 | Wed 1/10/24 | 222 | 224 |  | Kurt Meisner,Manojkumar Gurjar
5675 | 224 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WP404 - Create Data Conversion Inventory Summary Document | 20 hrs | 5 days | Thu 1/11/24 | Thu 1/18/24 | 223 | 225 |  | Manojkumar Gurjar,Kurt Meisner
5676 | 225 | Future Task |  |  | WP404 | Manojkumar Gurjar | Submit | WP WP404 - Data Conversion Inventory - Submit | 0 hrs | 0 days | Thu 1/18/24 | Thu 1/18/24 | 224 | 226 |  | Manojkumar Gurjar,Joy Schneider
5677 | 226 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WP WP404 - Data Conversion Inventory - Collaborative Review & Update | 20 hrs | 10 days | Fri 1/19/24 | Thu 2/1/24 | 225 | 227 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5678 | 227 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WP WP404 - Data Conversion Inventory - Final Review & Edits | 20 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 226 | 228 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5679 | 228 | Future Task |  |  | WP404 | Manojkumar Gurjar | Approve | WP WP404 - Data Conversion Inventory - Approve | 0 hrs | 0 days | Thu 2/8/24 | Thu 2/8/24 | 227 |  | 2024-01-01 | Jimmy Cox
4458 | 229 | Future Task | Yes |  | WP405 | Stacey Terry |  | WP405 - Security Roles Matrix | 280 hrs | 115 days | Mon 2/19/24 | Tue 7/30/24
4459 | 230 | Future Task |  |  | WP405 | Stacey Terry | Create | WPED WP405 - Security Roles Matrix - Create | 16 hrs | 10 days | Mon 2/19/24 | Fri 3/1/24 | 1 | 231 |  | Stacey Terry,Mary Punty
4460 | 231 | Future Task |  |  | WP405 | Stacey Terry | Submit | WPED WP405 - Security Roles Matrix - Submit | 0 hrs | 0 days | Fri 3/1/24 | Fri 3/1/24 | 230 | 232 |  | Joy Schneider,Stacey Terry
4461 | 232 | Future Task |  |  | WP405 | Stacey Terry | Review | WPED WP405 - Security Roles Matrix - Review | 24 hrs | 10 days | Mon 3/4/24 | Fri 3/15/24 | 231 | 233 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4462 | 233 | Future Task |  |  | WP405 | Stacey Terry | Approve | WPED WP405 - Security Roles Matrix - Approve | 0 hrs | 0 days | Fri 3/15/24 | Fri 3/15/24 | 232 | 234FS+30 days |  | Jimmy Cox
4467 | 234 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Create Security Roles Matrix Template | 20 hrs | 5 days | Mon 4/29/24 | Fri 5/3/24 | 233FS+30 days | 235 |  | Stacey Terry,Yogesh Deshmukh
4468 | 235 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Design, Review, and Confirm Security Roles Matrix | 50 hrs | 20 days | Mon 5/6/24 | Mon 6/3/24 | 234 | 236 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4469 | 236 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Finalize Security Roles Matrix Design | 50 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 235 | 237 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4470 | 237 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Configure Security Roles and Permission Lists | 50 hrs | 15 days | Tue 6/11/24 | Mon 7/1/24 | 236 | 238 |  | Manojkumar Gurjar,Paul Jureidini
4471 | 238 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Create Security Roles Matrix Summary Document | 30 hrs | 5 days | Tue 7/2/24 | Tue 7/9/24 | 237 | 239 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4463 | 239 | Future Task |  |  | WP405 | Stacey Terry | Submit | WP WP405 - Security Roles Matrix - Submit | 0 hrs | 0 days | Tue 7/9/24 | Tue 7/9/24 | 238 | 240 |  | Joy Schneider,Stacey Terry
4464 | 240 | Future Task |  |  | WP405 | Stacey Terry | Review | WP WP405 - Security Roles Matrix - Collaborative Review & Update | 20 hrs | 10 days | Wed 7/10/24 | Tue 7/23/24 | 239 | 241 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4465 | 241 | Future Task |  |  | WP405 | Stacey Terry | Review | WP WP405 - Security Roles Matrix - Final Review & Edits | 20 hrs | 5 days | Wed 7/24/24 | Tue 7/30/24 | 240 | 242 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4466 | 242 | Future Task |  |  | WP405 | Stacey Terry | Approve | WP WP405 - Security Roles Matrix - Approve | 0 hrs | 0 days | Tue 7/30/24 | Tue 7/30/24 | 241 | 579 | 2024-07-01 | Jimmy Cox
5680 | 243 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | WP411 - Batch and Interface Procedures | 109 hrs | 114 days | Mon 9/30/24 | Fri 3/14/25
5681 | 244 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WPED WP411 - Batch and Interface Procedures - Create | 16 hrs | 10 days | Mon 9/30/24 | Fri 10/11/24 | 1 | 245 |  | Manojkumar Gurjar,Kurt Meisner
5682 | 245 | Future Task |  |  | WP411 | Manojkumar Gurjar | Submit | WPED WP411 - Batch and Interface Procedures - Submit | 0 hrs | 0 days | Fri 10/11/24 | Fri 10/11/24 | 244 | 246 |  | Manojkumar Gurjar,Joy Schneider
5683 | 246 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WPED WP411 - Batch and Interface Procedures - Review | 24 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 245 | 247 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5684 | 247 | Future Task |  |  | WP411 | Manojkumar Gurjar | Approve | WPED WP411 - Batch and Interface Procedures - Approve | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 246 | 248FS+22 days |  | Jimmy Cox
6701 | 248 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WP411 - Define Interface Procedures | 3 hrs | 28 days | Mon 12/2/24 | Fri 1/10/25 | 247FS+22 days | 249 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
6702 | 249 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WP411 - Create Batch Flow Diagram | 6 hrs | 9 days | Mon 1/13/25 | Fri 1/24/25 | 248 | 250 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
6703 | 250 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WP411 - Create Batch and Interface Procedures Document | 20 hrs | 20 days | Mon 1/27/25 | Fri 2/21/25 | 249 | 251 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
5685 | 251 | Future Task |  |  | WP411 | Manojkumar Gurjar | Submit | WP WP411 - Batch and Interface Procedures - Submit | 0 hrs | 0 days | Fri 2/21/25 | Fri 2/21/25 | 250 | 252 |  | Manojkumar Gurjar,Joy Schneider
5686 | 252 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WP WP411 - Batch and Interface Procedures - Collaborative Review & Update | 20 hrs | 10 days | Mon 2/24/25 | Fri 3/7/25 | 251 | 253 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5687 | 253 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WP WP411 - Batch and Interface Procedures - Final Review & Edits | 20 hrs | 5 days | Mon 3/10/25 | Fri 3/14/25 | 252 | 254 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5688 | 254 | Future Task |  |  | WP411 | Manojkumar Gurjar | Approve | WP WP411 - Batch and Interface Procedures - Approve | 0 hrs | 0 days | Fri 3/14/25 | Fri 3/14/25 | 253 |  |  | Jimmy Cox
6596 | 255 | Late |  |  | I-WP101 | Deana Metcalf |  | I-WP101 - Update Financials BPMs | 1,053.11 hrs | 299 days | Wed 4/26/23 | Mon 7/1/24
6597 | 256 | Complete |  |  | I-WP101 | Deana Metcalf | Create | Identify BPMs by module | 6 hrs | 3 days | Wed 4/26/23 | Fri 4/28/23 | 1 | 263264 |  | Deana Metcalf,Stacey Terry,Tiffany Porter,Janice Jackson,Brendan Jones
6598 | 257 | Late |  |  | I-WP101 | Deana Metcalf |  | WPED I-WP101 - Update Financials BPMs | 1,015.11 hrs | 274 days | Mon 5/1/23 | Thu 5/30/24
6599 | 258 | Complete |  |  | I-WP101 | Deana Metcalf | Create | WPED I-WP101 - Update Financials BPMs - Create | 3 hrs | 6 days | Mon 5/15/23 | Mon 5/22/23 | 1 | 259 |  | Deana Metcalf
6600 | 259 | Complete |  |  | I-WP101 | Deana Metcalf | Submit | WPED I-WP101 - Update Financials BPMs - Submit | 0 hrs | 0 days | Mon 5/22/23 | Mon 5/22/23 | 258 | 260 |  | Deana Metcalf
6601 | 260 | Complete |  |  | I-WP101 | Deana Metcalf | Review | WPED I-WP101 - Update Financials BPMs - Collaborative Review & Update | 1.11 hrs | 1 day | Tue 5/23/23 | Tue 5/23/23 | 259 | 261 |  | Tiffany Porter,Janice Jackson,Brendan Jones,Angie Robertson,Jimmy Cox,Deana Metcalf
6602 | 261 | Complete |  |  | I-WP101 | Deana Metcalf | Approve | WPED I-WP101 - Update Financials BPMs - Approve | 0 hrs | 0 days | Tue 5/23/23 | Tue 5/23/23 | 260 |  |  | Jimmy Cox
6603 | 262 | Late | Yes |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment I - Financials Wave Business Process Models | 170 hrs | 86 days | Mon 5/1/23 | Wed 8/30/23
6604 | 263 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - May | 20 hrs | 22 days | Mon 5/1/23 | Wed 5/31/23 | 256 | 265 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6605 | 264 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - May | 20 hrs | 22 days | Mon 5/1/23 | Wed 5/31/23 | 256 | 266 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6606 | 265 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - June | 20 hrs | 22 days | Thu 6/1/23 | Fri 6/30/23 | 263 | 267 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6607 | 266 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - June | 20 hrs | 22 days | Thu 6/1/23 | Fri 6/30/23 | 264 | 268 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6608 | 267 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - July | 20 hrs | 20 days | Mon 7/3/23 | Mon 7/31/23 | 265 | 269 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6609 | 268 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - July | 20 hrs | 20 days | Mon 7/3/23 | Mon 7/31/23 | 266 | 269 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6610 | 269 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment I - Submit | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 267268 | 270275276277 |  | Deana Metcalf
6611 | 270 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment I - Collaborative Review & Update | 20 hrs | 4 days | Tue 8/1/23 | Fri 8/4/23 | 269 | 271 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6789 | 271 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment I - Advisory Council Review & Updates | 14 hrs | 12 days | Mon 8/7/23 | Tue 8/22/23 | 270 | 272 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson,Dusti Kincl
6612 | 272 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment I - Style Guide Updates | 2 hrs | 1 day | Wed 8/23/23 | Wed 8/23/23 | 271 | 273 |  | Dusti Kincl
6613 | 273 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment I - Final Review & Update | 14 hrs | 5 days | Thu 8/24/23 | Wed 8/30/23 | 272 | 328 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson,Jimmy Cox
6614 | 274 | Future Task | Yes |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment II - Financials Wave Business Process Models | 270 hrs | 85 days | Tue 8/1/23 | Fri 12/1/23
6615 | 275 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - August | 20 hrs | 23 days | Tue 8/1/23 | Thu 8/31/23 | 269 | 278 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6616 | 276 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - August | 20 hrs | 23 days | Tue 8/1/23 | Thu 8/31/23 | 269 | 279 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6617 | 277 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - August | 20 hrs | 23 days | Tue 8/1/23 | Thu 8/31/23 | 269 | 280 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6618 | 278 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - September | 20 hrs | 20 days | Fri 9/1/23 | Fri 9/29/23 | 275 | 281284285 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6619 | 279 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - September | 20 hrs | 20 days | Fri 9/1/23 | Fri 9/29/23 | 276 | 282 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6620 | 280 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - September | 20 hrs | 20 days | Fri 9/1/23 | Fri 9/29/23 | 277 | 283 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6621 | 281 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - October | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 278 | 286 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6622 | 282 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - October | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 279 | 286 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6623 | 283 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - October | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 280 | 286 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6624 | 284 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment LMC models Impacted by Segment II | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 278 | 286 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6625 | 285 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment PPA models Impacted by Segment II | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 278 | 286 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6626 | 286 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment II - Submit | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 281282283284285 | 287,292FS+2 days,293FS+2 days,294FS+2 days |  | Deana Metcalf
6627 | 287 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment II - Collaborative Review & Update | 20 hrs | 5 days | Mon 10/30/23 | Fri 11/3/23 | 286 | 288 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6790 | 288 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment II - Advisory Council Review & Updates | 14 hrs | 11 days | Mon 11/6/23 | Tue 11/21/23 | 287 | 289 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6628 | 289 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment II - Style Guide Updates | 2 hrs | 1 day | Wed 11/22/23 | Wed 11/22/23 | 288 | 290 |  | Dusti Kincl
6629 | 290 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment II - Final Review & Update | 14 hrs | 5 days | Mon 11/27/23 | Fri 12/1/23 | 289 | 328 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson,Jimmy Cox
6630 | 291 | Future Task | Yes |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment III - Financials Wave Business Process Models | 296 hrs | 85 days | Wed 11/1/23 | Wed 3/6/24
6631 | 292 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - November | 20 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23 | 286FS+2 days | 295 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6632 | 293 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - November | 20 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23 | 286FS+2 days | 296 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6633 | 294 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - November | 20 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23 | 286FS+2 days | 297 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6634 | 295 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - December | 20 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23 | 292 | 298301 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6635 | 296 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - December | 20 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23 | 293 | 299302 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6636 | 297 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - December | 20 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23 | 294 | 300303 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6637 | 298 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - January | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 295 | 304 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6638 | 299 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - January | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 296 | 304 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6639 | 300 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - January | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 297 | 304 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6640 | 301 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior LMC segment models Impacted by Segment III | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 295 | 304 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6641 | 302 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior PPA segment models Impacted by Segment III | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 296 | 304 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6642 | 303 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior TRP segment models Impacted by Segment III | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 297 | 304 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6643 | 304 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment III - Submit | 0 hrs | 0 days | Fri 1/26/24 | Fri 1/26/24 | 2.983e+17 | 305,310FS+3 days,311FS+3 days,312FS+3 days |  | Deana Metcalf
6644 | 305 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment III - Collaborative Review & Update | 20 hrs | 5 days | Mon 1/29/24 | Fri 2/2/24 | 304 | 306 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6792 | 306 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment III - Advisory Council Review & Updates | 20 hrs | 17 days | Mon 2/5/24 | Tue 2/27/24 | 305 | 307 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6645 | 307 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment III - Style Guide Updates | 2 hrs | 1 day | Wed 2/28/24 | Wed 2/28/24 | 306 | 308 |  | Dusti Kincl
6646 | 308 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment III - Final Review & Update | 14 hrs | 5 days | Thu 2/29/24 | Wed 3/6/24 | 307 | 328 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson,Jimmy Cox
6647 | 309 | Future Task | Yes |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment IV - Financials Wave Business Process Models | 275 hrs | 85 days | Thu 2/1/24 | Thu 5/30/24
6648 | 310 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - February | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 304FS+3 days | 313 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6649 | 311 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - February | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 304FS+3 days | 314 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6650 | 312 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - February | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 304FS+3 days | 315 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6651 | 313 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - March | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 310 | 316319 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6652 | 314 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - March | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 311 | 317320 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6653 | 315 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - March | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 312 | 318321 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6654 | 316 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - April | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 313 | 322 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6655 | 317 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - April | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 314 | 322 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6656 | 318 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - April | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 315 | 322 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6657 | 319 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior LMC segment models Impacted by Segment IV | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 313 | 322 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6658 | 320 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior PPA segment models Impacted by Segment IV | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 314 | 322 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6659 | 321 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior TRP segment models Impacted by Segment IV | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 315 | 322 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6660 | 322 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment IV - Submit | 0 hrs | 0 days | Fri 4/26/24 | Fri 4/26/24 | 3.1632e+17 | 323 |  | Deana Metcalf
7203 | 323 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment IV - Advisory Council Review & Updates | 8 hrs | 5 days | Mon 4/29/24 | Fri 5/3/24 | 322 | 324 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6661 | 324 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment IV - Collaborative Review & Update | 10 hrs | 12 days | Mon 5/6/24 | Tue 5/21/24 | 323 | 325 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6662 | 325 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment IV - Style Guide Updates | 2 hrs | 1 day | Wed 5/22/24 | Wed 5/22/24 | 324 | 326 |  | Dusti Kincl
6663 | 326 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment IV - Final Review & Update | 15 hrs | 5 days | Thu 5/23/24 | Thu 5/30/24 | 325 | 328 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson,Jimmy Cox
6664 | 327 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 - Update Financials BPMs Review Tasks | 32 hrs | 22 days | Thu 5/30/24 | Mon 7/1/24
6665 | 328 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | WP I-WP101 - Update Financials BPMs - Submit | 0 hrs | 0 days | Thu 5/30/24 | Thu 5/30/24 | 273290308326 | 329 |  | Deana Metcalf
6666 | 329 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WP I-WP101 - Update Financials BPMs - Department QC | 2 hrs | 1 day | Fri 5/31/24 | Fri 5/31/24 | 328 | 330 |  | Gabriela Gibson
6667 | 330 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WP I-WP101 - Update Financials BPMs - Collaborative Review & Update | 20 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 329 | 331 |  | Deana Metcalf,Stacey Terry,Tiffany Porter,Janice Jackson,Brendan Jones
6668 | 331 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WP I-WP101 - Update Financials BPMs - Style Guide Review | 2 hrs | 1 day | Mon 6/17/24 | Mon 6/17/24 | 330 | 332 |  | Dusti Kincl
6669 | 332 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WP I-WP101 - Update Financials BPMs - Final Review & Update | 8 hrs | 10 days | Tue 6/18/24 | Mon 7/1/24 | 331 | 333 |  | Jimmy Cox,Angie Robertson
6670 | 333 | Future Task |  |  | I-WP101 | Deana Metcalf | Approve | WP I-WP101 - Update Financials BPMs - Approve | 0 hrs | 0 days | Mon 7/1/24 | Mon 7/1/24 | 332 |  |  | Jimmy Cox
6671 | 334 | Future Task |  |  | I-WP125 | Deana Metcalf |  | I-WP125 - Updated D66 Chart of Accounts Design | 214 hrs | 63 days | Mon 6/5/23 | Thu 8/31/23
6672 | 335 | Future Task |  |  | I-WP125 | Deana Metcalf | Create | WPED I-WP125 - Update D66 Chart of Accounts Design - Create | 2 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1 | 336 |  | Deana Metcalf
6673 | 336 | Future Task |  |  | I-WP125 | Deana Metcalf | Submit | WPED I-WP125 - Update D66 Chart of Accounts Design - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 335 | 337 |  | Deana Metcalf
6674 | 337 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WPED I-WP125 - Update D66 Chart of Accounts Design - Collaborative Review & Update | 8 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 336 | 338 |  | Janice Jackson,LaWanda Warren,Robert Hicks,Tommy Werner
6675 | 338 | Future Task |  |  | I-WP125 | Deana Metcalf | Approve | WPED I-WP125 - Update D66 Chart of Accounts Design - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 337 | 339 |  | Angie Robertson,Jimmy Cox
6676 | 339 | Future Task |  | RW | I-WP125 | Deana Metcalf | Create | I-WP125 Update D66 Chart of Accounts Design <Activities per WPED> | 100 hrs | 26 days | Mon 7/3/23 | Tue 8/8/23 | 338 | 340 |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp
6677 | 340 | Future Task |  |  | I-WP125 | Deana Metcalf | Submit | WP I-WP125 - Update D66 Chart of Accounts Design - Submit | 0 hrs | 0 days | Tue 8/8/23 | Tue 8/8/23 | 339 | 341 |  | Janice Jackson
6678 | 341 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WP I-WP125 - Update D66 Chart of Accounts Design - Department QC | 1 hr | 1 day | Wed 8/9/23 | Wed 8/9/23 | 340 | 342 |  | Gabriela Gibson
6679 | 342 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WP I-WP125 - Update D66 Chart of Accounts Design - Collaborative Review & Update | 100 hrs | 10 days | Thu 8/10/23 | Wed 8/23/23 | 341 | 343 |  | Deana Metcalf,Janice Jackson,Jennifer Reeves,Angie Robertson
6680 | 343 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WP I-WP125 - Update D66 Chart of Accounts Design - Style Guide Review | 1 hr | 1 day | Thu 8/24/23 | Thu 8/24/23 | 342 | 344 |  | Tatiana Eubanks
6681 | 344 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WP I-WP125 - Update D66 Chart of Accounts Design - Final Review & Update | 2 hrs | 5 days | Fri 8/25/23 | Thu 8/31/23 | 343 | 345 |  | Angie Robertson,Jimmy Cox
6682 | 345 | Future Task |  |  | I-WP125 | Deana Metcalf | Approve | WP I-WP125 - Update D66 Chart of Accounts Design - Approve | 0 hrs | 0 days | Thu 8/31/23 | Thu 8/31/23 | 344 |  |  | Jimmy Cox
3770 | 346 | Future Task | [5 empty] | Build | 3,763 hrs | 618 days | Mon 7/10/23 | Fri 12/19/25
5534 | 347 | Future Task | Yes |  | D642 | Jarad Hermann |  | D642 - Updated Technical Architecture Design | 169 hrs | 98 days | Tue 9/5/23 | Fri 1/26/24
5535 | 348 | Future Task |  |  | D642 | Jarad Hermann | Create | DED D642 - Updated Technical Architecture Design - Create | 8 hrs | 10 days | Tue 9/5/23 | Mon 9/18/23 | 1FS+91 days | 349 |  | Jarad Hermann,Manojkumar Gurjar
5536 | 349 | Future Task |  |  | D642 | Jarad Hermann | Submit | DED D642 - Updated Technical Architecture Design - Submit | 0 hrs | 0 days | Mon 9/18/23 | Mon 9/18/23 | 348 | 350 |  | Jarad Hermann,Joy Schneider
5537 | 350 | Future Task |  |  | D642 | Jarad Hermann | Review | DED D642 - Updated Technical Architecture Design - Collaborative Review | 24 hrs | 10 days | Tue 9/19/23 | Mon 10/2/23 | 349 | 351 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5538 | 351 | Future Task |  |  | D642 | Jarad Hermann | Approve | DED D642 - Updated Technical Architecture Design - Approve | 0 hrs | 0 days | Mon 10/2/23 | Mon 10/2/23 | 350 | 352FS+21 days |  | Jimmy Cox
5539 | 352 | Future Task |  |  | D642 | Jarad Hermann | Create | D642 - Confirm content to be migrated from D80 | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 351FS+21 days | 353SS,354SS,355SS |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5540 | 353 | Future Task |  |  | D642 | Jarad Hermann | Create | D642 - Review, update, & document run time architecture design | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 352SS | 356 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5541 | 354 | Future Task |  |  | D642 | Jarad Hermann | Create | D642 - Review, update, and document development and operational architecture design | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 352SS | 356 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5542 | 355 | Future Task |  |  | D642 | Jarad Hermann | Create | D642 - Review, update, and document architecture blueprint diagrams | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 352SS | 356 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5543 | 356 | Future Task |  |  | D642 | Jarad Hermann | Submit | DEL D642 - Updated Technical Architecture Design - Draft Submission | 0 hrs | 0 days | Tue 1/2/24 | Tue 1/2/24 | 355353354 | 357 |  | Jarad Hermann,Joy Schneider
5544 | 357 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Pre-Submission Collaborative Review | 20 hrs | 5 days | Wed 1/3/24 | Tue 1/9/24 | 356 | 358 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
5545 | 358 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Style Guide Review | 1 hr | 1 day | Wed 1/10/24 | Wed 1/10/24 | 357 | 359 |  | Dusti Kincl
5546 | 359 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Final Collaborative Review | 20 hrs | 5 days | Thu 1/11/24 | Thu 1/18/24 | 358 | 360 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
5547 | 360 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Accenture QC | 4 hrs | 2 days | Fri 1/19/24 | Mon 1/22/24 | 359 | 361 |  | Joy Schneider
5548 | 361 | Future Task |  |  | D642 | Jarad Hermann | Submit | DEL D642 - Updated Technical Architecture Design - Submit | 0 hrs | 0 days | Mon 1/22/24 | Mon 1/22/24 | 360 | 362 |  | Joy Schneider
5549 | 362 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Department QC | 4 hrs | 1 day | Tue 1/23/24 | Tue 1/23/24 | 361 | 363 |  | Tommy Werner,Gabriela Gibson
5550 | 363 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Contract Manager Review | 8 hrs | 3 days | Wed 1/24/24 | Fri 1/26/24 | 362 | 364 |  | Sean Buchanan
5551 | 364 | Future Task |  |  | D642 | Jarad Hermann | Accept | DEL D642 - Updated Technical Architecture Design - Accept | 0 hrs | 0 days | Fri 1/26/24 | Fri 1/26/24 | 363 |  | 2024-03-01 | Sean Buchanan
4486 | 365 | Future Task | Yes |  | D646 | Manojkumar Gurjar |  | D646 - Completion of Build Segment I | 257 hrs | 156 days | Mon 9/18/23 | Tue 4/30/24
4487 | 366 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | DED D646 - Completion of Build Segment I - Create | 16 hrs | 10 days | Mon 9/18/23 | Fri 9/29/23 |  | 367 |  | Manojkumar Gurjar,Kurt Meisner
4488 | 367 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DED D646 - Completion of Build Segment I - Submit | 0 hrs | 0 days | Fri 9/29/23 | Fri 9/29/23 | 366 | 368 |  | Manojkumar Gurjar,Joy Schneider
4489 | 368 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DED D646 - Completion of Build Segment I - Collaborative Review | 24 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 367 | 369 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4490 | 369 | Future Task |  |  | D646 | Manojkumar Gurjar | Approve | DED D646 - Completion of Build Segment I - Approve | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 368 | 370FS+19 days |  | Jimmy Cox
4500 | 370 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Identify RICEFW items for Build Segment I | 20 hrs | 8 days | Mon 11/13/23 | Wed 11/22/23 | 369FS+19 days | 371 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4501 | 371 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Create Work Unit Tracker for Build Segment I | 20 hrs | 5 days | Mon 11/27/23 | Fri 12/1/23 | 370 | 372 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4502 | 372 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Review, Update and Confirm Work Unit Tracker for Build Segment I | 20 hrs | 10 days | Mon 12/4/23 | Fri 12/15/23 | 371 | 373 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4503 | 373 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Conduct Kick-Off meeting for Build Segment I | 20 hrs | 9 days | Mon 12/18/23 | Fri 12/29/23 | 372 | 374 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4504 | 374 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Build and Unit Test RICEFW for Build Segment I - Group 1 | 20 hrs | 21 days | Tue 1/2/24 | Wed 1/31/24 | 373 | 375 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4505 | 375 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Build and Unit Test RICEFW for Build Segment I - Group 2 | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 374 | 376 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4506 | 376 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Build and Unit Test RICEFW for Build Segment I - Group 3 | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 375 | 377FS-5 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4507 | 377 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Create Summary Document for Build Segment I | 20 hrs | 10 days | Mon 3/25/24 | Fri 4/5/24 | 376FS-5 days | 378 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4491 | 378 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DEL D646 - Completion of Build Segment I - Draft Submission | 0 hrs | 0 days | Fri 4/5/24 | Fri 4/5/24 | 377 | 379 |  | Manojkumar Gurjar,Joy Schneider
4492 | 379 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 4/8/24 | Fri 4/12/24 | 378 | 380 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4493 | 380 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Style Guide Review | 1 hr | 1 day | Mon 4/15/24 | Mon 4/15/24 | 379 | 381 |  | Dusti Kincl
4494 | 381 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Final Collaborative Review | 20 hrs | 5 days | Tue 4/16/24 | Mon 4/22/24 | 380 | 382 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4495 | 382 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Accenture QC | 4 hrs | 2 days | Tue 4/23/24 | Wed 4/24/24 | 381 | 383 |  | Joy Schneider
4496 | 383 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DEL D646 - Completion of Build Segment I - Submit | 0 hrs | 0 days | Wed 4/24/24 | Wed 4/24/24 | 382 | 384 |  | Joy Schneider
4497 | 384 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Department QC | 4 hrs | 1 day | Thu 4/25/24 | Thu 4/25/24 | 383 | 385 |  | Tommy Werner,Gabriela Gibson
4498 | 385 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Contract Manager Review | 8 hrs | 3 days | Fri 4/26/24 | Tue 4/30/24 | 384 | 386 |  | Sean Buchanan
4499 | 386 | Future Task |  |  | D646 | Manojkumar Gurjar | Accept | DEL D646 - Completion of Build Segment I - Accept | 0 hrs | 0 days | Tue 4/30/24 | Tue 4/30/24 | 385 | 594600 | 2024-04-01 | Sean Buchanan
4629 | 387 | Future Task | Yes |  | D647 | Manojkumar Gurjar |  | D647 - Establish DW/BI Environments | 149 hrs | 96 days | Tue 1/2/24 | Wed 5/15/24
4630 | 388 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | DED D647 - Establish DW/BI Environments - Create | 8 hrs | 10 days | Tue 1/2/24 | Tue 1/16/24 | 1 | 389 |  | Jarad Hermann,Manojkumar Gurjar
4631 | 389 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DED D647 - Establish DW/BI Environments - Submit | 0 hrs | 0 days | Tue 1/16/24 | Tue 1/16/24 | 388 | 390 |  | Manojkumar Gurjar,Joy Schneider
4632 | 390 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DED D647 - Establish DW/BI Environments - Collaborative Review | 24 hrs | 10 days | Wed 1/17/24 | Tue 1/30/24 | 389 | 391 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4633 | 391 | Future Task |  |  | D647 | Manojkumar Gurjar | Approve | DED D647 - Establish DW/BI Environments - Approve | 0 hrs | 0 days | Tue 1/30/24 | Tue 1/30/24 | 390 | 392 |  | Jimmy Cox
4643 | 392 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | D647 - Establish DW/BI Environment Connections | 20 hrs | 19 days | Wed 1/31/24 | Mon 2/26/24 | 391 | 393 |  | Jarad Hermann,Manojkumar Gurjar
4644 | 393 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | D647 - Environment build and stand up | 20 hrs | 20 days | Tue 2/27/24 | Mon 3/25/24 | 392 | 394 |  | Jarad Hermann,Manojkumar Gurjar
4645 | 394 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | D647 - Verify access to DW/BI Environments | 20 hrs | 20 days | Tue 3/26/24 | Mon 4/22/24 | 393 | 395 |  | Jarad Hermann,Manojkumar Gurjar
4634 | 395 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DEL D647 - Establish DW/BI Environments - Draft Submission | 0 hrs | 0 days | Mon 4/22/24 | Mon 4/22/24 | 394 | 396 |  | Manojkumar Gurjar,Joy Schneider
4635 | 396 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 4/23/24 | Mon 4/29/24 | 395 | 397 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
4636 | 397 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Style Guide Review | 1 hr | 1 day | Tue 4/30/24 | Tue 4/30/24 | 396 | 398 |  | Dusti Kincl
4637 | 398 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Final Collaborative Review | 20 hrs | 5 days | Wed 5/1/24 | Tue 5/7/24 | 397 | 399 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
4638 | 399 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Accenture QC | 4 hrs | 2 days | Wed 5/8/24 | Thu 5/9/24 | 398 | 400 |  | Joy Schneider
4639 | 400 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DEL D647 - Establish DW/BI Environments - Submit | 0 hrs | 0 days | Thu 5/9/24 | Thu 5/9/24 | 399 | 401 |  | Joy Schneider
4640 | 401 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Department QC | 4 hrs | 1 day | Fri 5/10/24 | Fri 5/10/24 | 400 | 402 |  | Tommy Werner,Gabriela Gibson
4641 | 402 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Contract Manager Review | 8 hrs | 3 days | Mon 5/13/24 | Wed 5/15/24 | 401 | 403 |  | Sean Buchanan
4642 | 403 | Future Task |  |  | D647 | Manojkumar Gurjar | Accept | DEL D647 - Establish DW/BI Environments - Accept | 0 hrs | 0 days | Wed 5/15/24 | Wed 5/15/24 | 402 |  | 2024-05-01 | Sean Buchanan
4508 | 404 | Future Task | Yes |  | D648 | Manojkumar Gurjar |  | D648 - Completion of Build Segment II | 197 hrs | 110 days | Mon 2/12/24 | Tue 7/16/24
4509 | 405 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | DED D648 - Completion of Build Segment II - Create | 16 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 |  | 406 |  | Manojkumar Gurjar,Kurt Meisner
4510 | 406 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DED D648 - Completion of Build Segment II - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 405 | 407 |  | Manojkumar Gurjar,Joy Schneider
4511 | 407 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DED D648 - Completion of Build Segment II - Collaborative Review | 24 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 406 | 408 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4512 | 408 | Future Task |  |  | D648 | Manojkumar Gurjar | Approve | DED D648 - Completion of Build Segment II - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 407 | 409FS+20 days |  | Jimmy Cox
4536 | 409 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Create Work Unit Tracker for Build Segment II | 20 hrs | 7 days | Mon 4/8/24 | Tue 4/16/24 | 408FS+20 days | 410 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4537 | 410 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Review, Update and Confirm Work Unit Tracker for Build Segment II | 20 hrs | 8 days | Wed 4/17/24 | Fri 4/26/24 | 409 | 411 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4538 | 411 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Build and Unit Test RICEFW for Build Segment II - Group 1 | 20 hrs | 19 days | Mon 4/29/24 | Thu 5/23/24 | 410 | 412 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4539 | 412 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Build and Unit Test RICEFW for Build Segment II - Group 2 | 20 hrs | 19 days | Fri 5/24/24 | Thu 6/20/24 | 411 | 413FS-9 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4540 | 413 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Create Summary Document for Build Segment II | 20 hrs | 9 days | Mon 6/10/24 | Thu 6/20/24 | 412FS-9 days | 414 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4513 | 414 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DEL D648 - Completion of Build Segment II - Draft Submission | 0 hrs | 0 days | Thu 6/20/24 | Thu 6/20/24 | 413 | 415 |  | Manojkumar Gurjar,Joy Schneider
4514 | 415 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 6/21/24 | Thu 6/27/24 | 414 | 416 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4515 | 416 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Style Guide Review | 1 hr | 1 day | Fri 6/28/24 | Fri 6/28/24 | 415 | 417 |  | Dusti Kincl
4516 | 417 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Final Collaborative Review | 20 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 416 | 418 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4517 | 418 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Accenture QC | 4 hrs | 2 days | Tue 7/9/24 | Wed 7/10/24 | 417 | 419 |  | Joy Schneider
4518 | 419 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DEL D648 - Completion of Build Segment II - Submit | 0 hrs | 0 days | Wed 7/10/24 | Wed 7/10/24 | 418 | 420 |  | Joy Schneider
4519 | 420 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Department QC | 4 hrs | 1 day | Thu 7/11/24 | Thu 7/11/24 | 419 | 421 |  | Tommy Werner,Gabriela Gibson
4520 | 421 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Contract Manager Review | 8 hrs | 3 days | Fri 7/12/24 | Tue 7/16/24 | 420 | 422 |  | Sean Buchanan
4521 | 422 | Future Task |  |  | D648 | Manojkumar Gurjar | Accept | DEL D648 - Completion of Build Segment II - Accept | 0 hrs | 0 days | Tue 7/16/24 | Tue 7/16/24 | 421 | 600 | 2024-07-01 | Sean Buchanan
4522 | 423 | Future Task | Yes |  | D649 | Manojkumar Gurjar |  | D649 - Completion of Build Segment III | 217 hrs | 124 days | Mon 5/6/24 | Tue 10/29/24
4523 | 424 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | DED D649 - Completion of Build Segment III - Create | 16 hrs | 10 days | Mon 5/6/24 | Fri 5/17/24 |  | 425 |  | Manojkumar Gurjar,Kurt Meisner
4524 | 425 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DED D649 - Completion of Build Segment III - Submit | 0 hrs | 0 days | Fri 5/17/24 | Fri 5/17/24 | 424 | 426 |  | Manojkumar Gurjar,Joy Schneider
4525 | 426 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DED D649 - Completion of Build Segment III - Collaborative Review | 24 hrs | 10 days | Mon 5/20/24 | Mon 6/3/24 | 425 | 427 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4526 | 427 | Future Task |  |  | D649 | Manojkumar Gurjar | Approve | DED D649 - Completion of Build Segment III - Approve | 0 hrs | 0 days | Mon 6/3/24 | Mon 6/3/24 | 426 | 428FS+23 days |  | Jimmy Cox
4541 | 428 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Identify RICEFW items for Build Segment III | 20 hrs | 10 days | Mon 7/8/24 | Fri 7/19/24 | 427FS+23 days | 429 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4542 | 429 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Create Work Unit Tracker for Build Segment III | 20 hrs | 5 days | Mon 7/22/24 | Fri 7/26/24 | 428 | 430 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4543 | 430 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Review, Update and Confirm Work Unit Tracker for Build Segment III | 20 hrs | 10 days | Mon 7/29/24 | Fri 8/9/24 | 429 | 431 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4544 | 431 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Build and Unit Test RICEFW for Build Segment III - Group 1 | 20 hrs | 19 days | Mon 8/12/24 | Fri 9/6/24 | 430 | 432 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4545 | 432 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Build and Unit Test RICEFW for Build Segment III - Group 2 | 20 hrs | 20 days | Mon 9/9/24 | Fri 10/4/24 | 431 | 433FS-10 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4546 | 433 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Create Summary Document for Build Segment III | 20 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 432FS-10 days | 434 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4527 | 434 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DEL D649 - Completion of Build Segment III - Draft Submission | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 433 | 435 |  | Manojkumar Gurjar,Joy Schneider
4528 | 435 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 | 434 | 436 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4529 | 436 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Style Guide Review | 1 hr | 1 day | Mon 10/14/24 | Mon 10/14/24 | 435 | 437 |  | Dusti Kincl
4530 | 437 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Final Collaborative Review | 20 hrs | 5 days | Tue 10/15/24 | Mon 10/21/24 | 436 | 438 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4531 | 438 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Accenture QC | 4 hrs | 2 days | Tue 10/22/24 | Wed 10/23/24 | 437 | 439 |  | Joy Schneider
4532 | 439 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DEL D649 - Completion of Build Segment III - Submit | 0 hrs | 0 days | Wed 10/23/24 | Wed 10/23/24 | 438 | 440 |  | Joy Schneider
4533 | 440 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Department QC | 4 hrs | 1 day | Thu 10/24/24 | Thu 10/24/24 | 439 | 441 |  | Tommy Werner,Gabriela Gibson
4534 | 441 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Contract Manager Review | 8 hrs | 3 days | Fri 10/25/24 | Tue 10/29/24 | 440 | 442 |  | Sean Buchanan
4535 | 442 | Future Task |  |  | D649 | Manojkumar Gurjar | Accept | DEL D649 - Completion of Build Segment III - Accept | 0 hrs | 0 days | Tue 10/29/24 | Tue 10/29/24 | 441 | 600 | 2024-10-01 | Sean Buchanan
4547 | 443 | Future Task | Yes |  | D653 | Manojkumar Gurjar |  | D653 - Completion of Build Segment I DW/BI | 297 hrs | 147 days | Mon 6/3/24 | Thu 1/2/25
4548 | 444 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | DED D653 - Completion of Build Segment I DW/BI - Create | 16 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 1 | 445 |  | Manojkumar Gurjar,Kurt Meisner
4549 | 445 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DED D653 - Completion of Build Segment I DW/BI - Submit | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 444 | 446 |  | Manojkumar Gurjar,Joy Schneider
4550 | 446 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DED D653 - Completion of Build Segment I DW/BI - Collaborative Review | 24 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 445 | 447 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4551 | 447 | Future Task |  |  | D653 | Manojkumar Gurjar | Approve | DED D653 - Completion of Build Segment I DW/BI - Approve | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 446 | 448 |  | Jimmy Cox
4575 | 448 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Identify RICEFW items for Build Segment I DW/BI | 36 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 447 | 449 |  | Manojkumar Gurjar,Kurt Meisner
4576 | 449 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Create Work Unit Tracker for Build Segment I DW/BI | 20 hrs | 5 days | Mon 7/15/24 | Fri 7/19/24 | 448 | 450 |  | Manojkumar Gurjar,Kurt Meisner
4577 | 450 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Review, Update and Confirm Work Unit Tracker for Build Segment I DW/BI | 40 hrs | 10 days | Mon 7/22/24 | Fri 8/2/24 | 449 | 451 |  | Manojkumar Gurjar,Kurt Meisner
4578 | 451 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Conduct Kick-Off meeting for Build Segment I DW/BI | 40 hrs | 5 days | Mon 8/5/24 | Fri 8/9/24 | 450 | 452 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4579 | 452 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Build and Unit Test RICEFW for Build Segment I DW/BI - Group 1 | 20 hrs | 19 days | Mon 8/12/24 | Fri 9/6/24 | 451 | 453 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4580 | 453 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Build and Unit Test RICEFW for Build Segment I DW/BI - Group 2 | 20 hrs | 20 days | Mon 9/9/24 | Fri 10/4/24 | 452 | 454 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4581 | 454 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Build and Unit Test RICEFW for Build Segment I DW/BI - Group 3 | 20 hrs | 20 days | Mon 10/7/24 | Fri 11/1/24 | 453 | 455 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4582 | 455 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Create Summary Document for Build Segment I DW/BI | 4 hrs | 22 days | Mon 11/4/24 | Fri 12/6/24 | 454 | 456 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4552 | 456 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DEL D653 - Completion of Build Segment I DW/BI - Draft Submission | 0 hrs | 0 days | Fri 12/6/24 | Fri 12/6/24 | 455 | 457 |  | Manojkumar Gurjar,Joy Schneider
4553 | 457 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 12/9/24 | Fri 12/13/24 | 456 | 458 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4554 | 458 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Style Guide Review | 1 hr | 1 day | Mon 12/16/24 | Mon 12/16/24 | 457 | 459 |  | Dusti Kincl
4555 | 459 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Final Collaborative Review | 20 hrs | 5 days | Tue 12/17/24 | Mon 12/23/24 | 458 | 460 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4556 | 460 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Accenture QC | 4 hrs | 2 days | Tue 12/24/24 | Thu 12/26/24 | 459 | 461 | Holiday | Joy Schneider
4557 | 461 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DEL D653 - Completion of Build Segment I DW/BI - Submit | 0 hrs | 0 days | Thu 12/26/24 | Thu 12/26/24 | 460 | 462 |  | Joy Schneider
4558 | 462 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Department QC | 4 hrs | 1 day | Fri 12/27/24 | Fri 12/27/24 | 461 | 463 |  | Tommy Werner,Gabriela Gibson
4559 | 463 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Contract Manager Review | 8 hrs | 3 days | Mon 12/30/24 | Thu 1/2/25 | 462 | 464 |  | Sean Buchanan
4560 | 464 | Future Task |  |  | D653 | Manojkumar Gurjar | Accept | DEL D653 - Completion of Build Segment I DW/BI - Accept | 0 hrs | 0 days | Thu 1/2/25 | Thu 1/2/25 | 463 | 600 | 2025-01-01 | Sean Buchanan
4561 | 465 | Future Task | Yes |  | D654 | Manojkumar Gurjar |  | D654 - Completion of Build Segment IV | 217 hrs | 122 days | Mon 8/5/24 | Thu 1/30/25
4562 | 466 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | DED D654 - Completion of Build Segment IV - Create | 16 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 1 | 467 |  | Manojkumar Gurjar,Kurt Meisner
4563 | 467 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DED D654 - Completion of Build Segment IV - Submit | 0 hrs | 0 days | Fri 8/16/24 | Fri 8/16/24 | 466 | 468 |  | Manojkumar Gurjar,Joy Schneider
4564 | 468 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DED D654 - Completion of Build Segment IV - Collaborative Review | 24 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 467 | 469 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4565 | 469 | Future Task |  |  | D654 | Manojkumar Gurjar | Approve | DED D654 - Completion of Build Segment IV - Approve | 0 hrs | 0 days | Fri 8/30/24 | Fri 8/30/24 | 468 | 470FS+24 days |  | Jimmy Cox
4583 | 470 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Identify RICEFW items for Build Segment IV | 20 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 469FS+24 days | 471 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4584 | 471 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Create Work Unit Tracker for Build Segment IV | 20 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 470 | 472 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4585 | 472 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Review, Update and Confirm Work Unit Tracker for Build Segment IV | 20 hrs | 10 days | Mon 10/28/24 | Fri 11/8/24 | 471 | 473 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4586 | 473 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Build and Unit Test RICEFW for Build Segment IV - Group 1 | 20 hrs | 17 days | Tue 11/12/24 | Fri 12/6/24 | 472 | 474 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4587 | 474 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Build and Unit Test RICEFW for Build Segment IV - Group 2 | 20 hrs | 19 days | Mon 12/9/24 | Mon 1/6/25 | 473 | 475FS-14 days,476 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4588 | 475 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Create Summary Document for Build Segment IV | 20 hrs | 13 days | Mon 12/16/24 | Fri 1/3/25 | 474FS-14 days | 476 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4566 | 476 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DEL D654 - Completion of Build Segment IV - Draft Submission | 0 hrs | 0 days | Mon 1/6/25 | Mon 1/6/25 | 474475 | 477 |  | Manojkumar Gurjar,Joy Schneider
4567 | 477 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 1/7/25 | Mon 1/13/25 | 476 | 478 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4568 | 478 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Style Guide Review | 1 hr | 1 day | Tue 1/14/25 | Tue 1/14/25 | 477 | 479 |  | Dusti Kincl
4569 | 479 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Final Collaborative Review | 20 hrs | 5 days | Wed 1/15/25 | Wed 1/22/25 | 478 | 480 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4570 | 480 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Accenture QC | 4 hrs | 2 days | Thu 1/23/25 | Fri 1/24/25 | 479 | 481 |  | Joy Schneider
4571 | 481 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DEL D654 - Completion of Build Segment IV - Submit | 0 hrs | 0 days | Fri 1/24/25 | Fri 1/24/25 | 480 | 482 |  | Joy Schneider
4572 | 482 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Department QC | 4 hrs | 1 day | Mon 1/27/25 | Mon 1/27/25 | 481 | 483 |  | Tommy Werner,Gabriela Gibson
4573 | 483 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Contract Manager Review | 8 hrs | 3 days | Tue 1/28/25 | Thu 1/30/25 | 482 | 484 |  | Sean Buchanan
4574 | 484 | Future Task |  |  | D654 | Manojkumar Gurjar | Accept | DEL D654 - Completion of Build Segment IV - Accept | 0 hrs | 0 days | Thu 1/30/25 | Thu 1/30/25 | 483 | 600 | 2025-01-01 | Sean Buchanan
4589 | 485 | Future Task | Yes |  | D659 | Manojkumar Gurjar |  | D659 - Completion of Build Segment II DW/BI | 219 hrs | 116 days | Mon 9/9/24 | Tue 2/25/25
4590 | 486 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | DED D659 - Completion of Build Segment II DW/BI - Create | 16 hrs | 10 days | Mon 9/9/24 | Fri 9/20/24 | 1 | 487 |  | Manojkumar Gurjar,Kurt Meisner
4591 | 487 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DED D659 - Completion of Build Segment II DW/BI - Submit | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 486 | 488 |  | Manojkumar Gurjar,Joy Schneider
4592 | 488 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DED D659 - Completion of Build Segment II DW/BI - Collaborative Review | 24 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 487 | 489 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4593 | 489 | Future Task |  |  | D659 | Manojkumar Gurjar | Approve | DED D659 - Completion of Build Segment II DW/BI - Approve | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 488 | 490 |  | Jimmy Cox
4603 | 490 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Identify RICEFW items for Build Segment II DW/BI | 40 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 489 | 491 |  | Manojkumar Gurjar,Kurt Meisner
4604 | 491 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Create Work Unit Tracker for Build Segment II DW/BI | 20 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 490 | 492 |  | Manojkumar Gurjar,Kurt Meisner
4605 | 492 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Review, Update and Confirm Work Unit Tracker for Build Segment II DW/BI | 20 hrs | 5 days | Mon 10/28/24 | Fri 11/1/24 | 491 | 493 |  | Manojkumar Gurjar,Kurt Meisner
4606 | 493 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Build and Unit Test RICEFW for Build Segment II DW/BI - Group 1 | 20 hrs | 17 days | Mon 11/4/24 | Wed 11/27/24 | 492 | 494 |  | Manojkumar Gurjar,Kurt Meisner
4607 | 494 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Build and Unit Test RICEFW for Build Segment II DW/BI - Group 2 | 2 hrs | 23 days | Mon 12/2/24 | Fri 1/3/25 | 493 | 495 |  | Manojkumar Gurjar,Kurt Meisner
4608 | 495 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Create Summary Document for Build Segment II DW/BI | 20 hrs | 19 days | Mon 1/6/25 | Fri 1/31/25 | 494 | 496 |  | Manojkumar Gurjar,Kurt Meisner
4594 | 496 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DEL D659 - Completion of Build Segment II DW/BI - Draft Submission | 0 hrs | 0 days | Fri 1/31/25 | Fri 1/31/25 | 495 | 497 |  | Manojkumar Gurjar,Joy Schneider
4595 | 497 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 2/3/25 | Fri 2/7/25 | 496 | 498 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4596 | 498 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Style Guide Review | 1 hr | 1 day | Mon 2/10/25 | Mon 2/10/25 | 497 | 499 |  | Dusti Kincl
4597 | 499 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Final Collaborative Review | 20 hrs | 5 days | Tue 2/11/25 | Mon 2/17/25 | 498 | 500 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4598 | 500 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Accenture QC | 4 hrs | 2 days | Tue 2/18/25 | Wed 2/19/25 | 499 | 501 |  | Joy Schneider
4599 | 501 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DEL D659 - Completion of Build Segment II DW/BI - Submit | 0 hrs | 0 days | Wed 2/19/25 | Wed 2/19/25 | 500 | 502 |  | Joy Schneider
4600 | 502 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Department QC | 4 hrs | 1 day | Thu 2/20/25 | Thu 2/20/25 | 501 | 503 |  | Tommy Werner,Gabriela Gibson
4601 | 503 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Contract Manager Review | 8 hrs | 3 days | Fri 2/21/25 | Tue 2/25/25 | 502 | 504 |  | Sean Buchanan
4602 | 504 | Future Task |  |  | D659 | Manojkumar Gurjar | Accept | DEL D659 - Completion of Build Segment II DW/BI - Accept | 0 hrs | 0 days | Tue 2/25/25 | Tue 2/25/25 | 503 | 600 | 2025-04-01 | Sean Buchanan
4609 | 505 | Future Task | Yes |  | D668 | Manojkumar Gurjar |  | D668 - Completion of Build Segment III DW/BI | 281 hrs | 93 days | Wed 10/30/24 | Mon 3/17/25
4610 | 506 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | DED D668 - Completion of Build Segment III DW/BI - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1 | 507 |  | Manojkumar Gurjar,Kurt Meisner
4611 | 507 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DED D668 - Completion of Build Segment III DW/BI - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 506 | 508 |  | Manojkumar Gurjar,Joy Schneider
4612 | 508 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DED D668 - Completion of Build Segment III DW/BI - Collaborative Review | 24 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 507 | 509 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4613 | 509 | Future Task |  |  | D668 | Manojkumar Gurjar | Approve | DED D668 - Completion of Build Segment III DW/BI - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 508 | 510 |  | Jimmy Cox
4623 | 510 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Identify RICEFW items for Build Segment III DW/BI | 40 hrs | 5 days | Mon 12/2/24 | Fri 12/6/24 | 509 | 511SS+2 days |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4624 | 511 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Create Work Unit Tracker for Build Segment III DW/BI | 40 hrs | 5 days | Wed 12/4/24 | Tue 12/10/24 | 510SS+2 days | 512 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4625 | 512 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Review, Update and Confirm Work Unit Tracker for Build Segment III DW/BI | 24 hrs | 3 days | Wed 12/11/24 | Fri 12/13/24 | 511 | 513 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4626 | 513 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Build and Unit Test RICEFW for Build Segment III DW/BI - Group 1 | 20 hrs | 18 days | Mon 12/16/24 | Fri 1/10/25 | 512 | 514 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4627 | 514 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Build and Unit Test RICEFW for Build Segment III DW/BI - Group 2 | 20 hrs | 18 days | Mon 1/13/25 | Thu 2/6/25 | 513 | 515 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4628 | 515 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Create Summary Document for Build Segment III DW/BI | 40 hrs | 10 days | Fri 2/7/25 | Thu 2/20/25 | 514 | 516 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4614 | 516 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DEL D668 - Completion of Build Segment III DW/BI - Draft Submission | 0 hrs | 0 days | Thu 2/20/25 | Thu 2/20/25 | 515 | 517 |  | Manojkumar Gurjar,Joy Schneider
4615 | 517 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 2/21/25 | Thu 2/27/25 | 516 | 518 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4616 | 518 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Style Guide Review | 1 hr | 1 day | Fri 2/28/25 | Fri 2/28/25 | 517 | 519 |  | Dusti Kincl
4617 | 519 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Final Collaborative Review | 20 hrs | 5 days | Mon 3/3/25 | Fri 3/7/25 | 518 | 520 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4618 | 520 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Accenture QC | 4 hrs | 2 days | Mon 3/10/25 | Tue 3/11/25 | 519 | 521 |  | Joy Schneider
4619 | 521 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DEL D668 - Completion of Build Segment III DW/BI - Submit | 0 hrs | 0 days | Tue 3/11/25 | Tue 3/11/25 | 520 | 522 |  | Joy Schneider
4620 | 522 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Department QC | 4 hrs | 1 day | Wed 3/12/25 | Wed 3/12/25 | 521 | 523 |  | Tommy Werner,Gabriela Gibson
4621 | 523 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Contract Manager Review | 8 hrs | 3 days | Thu 3/13/25 | Mon 3/17/25 | 522 | 524 |  | Sean Buchanan
4622 | 524 | Future Task |  |  | D668 | Manojkumar Gurjar | Accept | DEL D668 - Completion of Build Segment III DW/BI - Accept | 0 hrs | 0 days | Mon 3/17/25 | Mon 3/17/25 | 523 | 600 | 2025-08-01 | Sean Buchanan
4646 | 525 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | WP410 - Integration and Interface Strategy | 160 hrs | 115 days | Mon 7/10/23 | Thu 12/21/23
4647 | 526 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WPED WP410 - Integration and Interface Strategy - Create | 16 hrs | 10 days | Mon 7/10/23 | Fri 7/21/23 | 1 | 527 |  | Manojkumar Gurjar,Kurt Meisner
4648 | 527 | Future Task |  |  | WP410 | Manojkumar Gurjar | Submit | WPED WP410 - Integration and Interface Strategy - Submit | 0 hrs | 0 days | Fri 7/21/23 | Fri 7/21/23 | 526 | 528 |  | Manojkumar Gurjar,Joy Schneider
4649 | 528 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WPED WP410 - Integration and Interface Strategy - Review | 24 hrs | 10 days | Mon 7/24/23 | Fri 8/4/23 | 527 | 529 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4650 | 529 | Future Task |  |  | WP410 | Manojkumar Gurjar | Approve | WPED WP410 - Integration and Interface Strategy - Approve | 0 hrs | 0 days | Fri 8/4/23 | Fri 8/4/23 | 528 | 530FS+20 days |  | Jimmy Cox
4655 | 530 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WP410 - Define Interface and Integration Approach | 20 hrs | 19 days | Tue 9/5/23 | Fri 9/29/23 | 529FS+20 days | 531 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4656 | 531 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WP410 - Create Interface and Integration Architecture Diagram | 20 hrs | 15 days | Mon 10/2/23 | Fri 10/20/23 | 530 | 532533 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4657 | 532 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WP410 - Review and update Interface and Integration Operations | 20 hrs | 19 days | Mon 10/23/23 | Fri 11/17/23 | 531 | 533 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4658 | 533 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WP410 - Finalize the Interface and Integration Strategy Document | 20 hrs | 7 days | Mon 11/20/23 | Thu 11/30/23 | 531532 | 534 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4651 | 534 | Future Task |  |  | WP410 | Manojkumar Gurjar | Submit | WP WP410 - Integration and Interface Strategy - Submit | 0 hrs | 0 days | Thu 11/30/23 | Thu 11/30/23 | 533 | 535 |  | Manojkumar Gurjar,Joy Schneider
4652 | 535 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WP WP410 - Integration and Interface Strategy - Collaborative Review & Update | 20 hrs | 10 days | Fri 12/1/23 | Thu 12/14/23 | 534 | 536 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4653 | 536 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WP WP410 - Integration and Interface Strategy - Final Review & Edits | 20 hrs | 5 days | Fri 12/15/23 | Thu 12/21/23 | 535 | 537 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4654 | 537 | Future Task |  | RW-Communication | WP410 | Manojkumar Gurjar | Approve | WP WP410 - Integration and Interface Strategy - Approve | 0 hrs | 0 days | Thu 12/21/23 | Thu 12/21/23 | 536 | 1081FS+68 days | 2023-11-01 | Jimmy Cox
5603 | 538 | Future Task |  |  | WP426 | Jarad Hermann |  | WP426 - System Infrastructure Capacity Plan | 148 hrs | 72 days | Mon 9/8/25 | Fri 12/19/25
5604 | 539 | Future Task |  |  | WP426 | Jarad Hermann | Create | WPED WP426 - System Infrastructure Capacity Plan - Create | 8 hrs | 10 days | Mon 9/8/25 | Fri 9/19/25 | 1 | 540 |  | Jarad Hermann
5605 | 540 | Future Task |  |  | WP426 | Jarad Hermann | Submit | WPED WP426 - System Infrastructure Capacity Plan - Submit | 0 hrs | 0 days | Fri 9/19/25 | Fri 9/19/25 | 539 | 541 |  | Joy Schneider,Jarad Hermann
5606 | 541 | Future Task |  |  | WP426 | Jarad Hermann | Review | WPED WP426 - System Infrastructure Capacity Plan - Review | 16 hrs | 10 days | Mon 9/22/25 | Fri 10/3/25 | 540 | 542 |  | Jarad Hermann,Jimmy Cox,Angie Robertson,Sean Buchanan
5607 | 542 | Future Task |  |  | WP426 | Jarad Hermann | Approve | WPED WP426 - System Infrastructure Capacity Plan - Approve | 0 hrs | 0 days | Fri 10/3/25 | Fri 10/3/25 | 541 | 543FS+20 days |  | Jimmy Cox
5608 | 543 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Review and refine the FL PALM Capacity Plan (excel doc) | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 542FS+20 days | 544SS,545SS,546SS,547SS |  | Jarad Hermann,Bryan Sohayda
5609 | 544 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Review and refine the FL PALM Capacity Plan (word doc) | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 543SS | 548 |  | Jarad Hermann,Bryan Sohayda
5610 | 545 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Define and document current infrastructure demand | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 543SS | 548 |  | Jarad Hermann,Bryan Sohayda
5611 | 546 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Define and document current infrastructure capacity | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 543SS | 548 |  | Jarad Hermann,Bryan Sohayda
5612 | 547 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Define and document projected infrastructure demand | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 543SS | 548 |  | Jarad Hermann,Bryan Sohayda
5613 | 548 | Future Task |  |  | WP426 | Jarad Hermann | Submit | WP WP426 - System Infrastructure Capacity Plan - Submit | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 547544545546 | 549 |  | Joy Schneider,Jarad Hermann
5614 | 549 | Future Task |  |  | WP426 | Jarad Hermann | Review | WP WP426 - System Infrastructure Capacity Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 12/1/25 | Fri 12/12/25 | 548 | 550 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5615 | 550 | Future Task |  |  | WP426 | Jarad Hermann | Review | WP WP426 - System Infrastructure Capacity Plan - Final Review & Edits | 12 hrs | 5 days | Mon 12/15/25 | Fri 12/19/25 | 549 | 551 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5616 | 551 | Future Task |  |  | WP426 | Jarad Hermann | Approve | WP WP426 - System Infrastructure Capacity Plan - Approve | 0 hrs | 0 days | Fri 12/19/25 | Fri 12/19/25 | 550 |  |  | Jimmy Cox
3868 | 552 | Future Task | [5 empty] | Environment Builds | 137 hrs | 207 days | Mon 8/5/24 | Fri 5/30/25
4203 | 553 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure System Test Environment | 10 hrs | 15 days | Mon 8/5/24 | Fri 8/23/24 | 620 | 554 |  | Manojkumar Gurjar,Jarad Hermann
4204 | 554 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate System Test Environment | 8 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 553 | 651 |  | Manojkumar Gurjar,Jarad Hermann
4195 | 555 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Interface Test Environment | 10 hrs | 14 days | Tue 9/3/24 | Fri 9/20/24 | 1094FS-10 days | 556 |  | Manojkumar Gurjar,Jarad Hermann
4196 | 556 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate Interface Test Environment | 8 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 555 | 796 |  | Manojkumar Gurjar,Jarad Hermann
4197 | 557 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Mock Conversion Test Environment | 10 hrs | 15 days | Mon 8/5/24 | Fri 8/23/24 | 1041 | 558 |  | Manojkumar Gurjar,Jarad Hermann
4198 | 558 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate Mock Conversion Test Environment | 8 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 557 | 630 |  | Manojkumar Gurjar,Jarad Hermann
4199 | 559 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure UAT Test Environment | 10 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1272FS+215 days | 560 |  | Manojkumar Gurjar,Jarad Hermann
4200 | 560 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate UAT Test Environment | 10 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 559 | 562 |  | Manojkumar Gurjar,Jarad Hermann
7246 | 561 | Future Task |  |  |  | Manojkumar Gurjar | Milestone | Confirm Receipt of Agency Role Mapping Worksheet | 0 hrs | 0 days | Mon 3/3/25 | Mon 3/3/25 | 1871 |  |  | Manojkumar Gurjar,Jarad Hermann
4201 | 562 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Load Security Roles to ForgeRock for UAT | 4 hrs | 4 days | Mon 3/3/25 | Thu 3/6/25 | 5601871 | 563 |  | Jarad Hermann
4202 | 563 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Validate Security Roles in ForgeRock for UAT | 5 hrs | 5 days | Fri 3/7/25 | Thu 3/13/25 | 562 | 1274600 |  | Jarad Hermann
4191 | 564 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Dry Run Test Environment | 10 hrs | 14 days | Mon 5/5/25 | Thu 5/22/25 |  | 565 |  | Manojkumar Gurjar,Jarad Hermann
4192 | 565 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate Dry Run Test Environment | 8 hrs | 5 days | Fri 5/23/25 | Fri 5/30/25 | 564 | 837 |  | Manojkumar Gurjar,Jarad Hermann
4193 | 566 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Performance Test Environment | 10 hrs | 15 days | Mon 5/5/25 | Fri 5/23/25 | 1197 | 567 |  | Manojkumar Gurjar,Jarad Hermann
4194 | 567 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate Performance Test Environment | 8 hrs | 4 days | Tue 5/27/25 | Fri 5/30/25 | 566 | 979 |  | Manojkumar Gurjar,Jarad Hermann
4189 | 568 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Disaster Recovery Test Environment | 10 hrs | 15 days | Mon 3/3/25 | Fri 3/21/25 | 1183 | 569 |  | Manojkumar Gurjar,Jarad Hermann
4190 | 569 | Future Task | Yes |  | ENV | Manojkumar Gurjar | Create | Validate Disaster Recovery Test Environment | 8 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 568 | 997FS+1 day |  | Manojkumar Gurjar,Jarad Hermann
6809 | 570 | Future Task | [5 empty] | Other | 1,315 hrs | 290 days | Mon 1/8/24 | Fri 2/28/25
7219 | 571 | Future Task |  |  |  | Stacey Terry | Create | Draft Workflow Configuration Updates | 2 hrs | 3 days | Tue 9/24/24 | Thu 9/26/24 | 51,70,150,169FS+83 days | 572 |  | Stacey Terry,Yogesh Deshmukh
7220 | 572 | Future Task |  |  |  | Stacey Terry | Create | Draft Workflow Management Updates | 2 hrs | 3 days | Fri 9/27/24 | Tue 10/1/24 | 571 | 573 |  | Stacey Terry,Yogesh Deshmukh
7218 | 573 | Future Task |  |  |  | Stacey Terry | Create | Draft Workflow Monitoring Updates | 2 hrs | 3 days | Wed 10/2/24 | Fri 10/4/24 | 572 | 574 |  | Stacey Terry,Yogesh Deshmukh
7221 | 574 | Future Task |  |  |  | Stacey Terry | Create | Review and Confirmation Workflow Administration Guide Updates | 5 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 | 573 | 575 |  | Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Angie Robertson,Jimmy Cox
7217 | 575 | Future Task |  |  |  | Stacey Terry | Create | Approve Updates to Workflow Administration Guide | 0 hrs | 0 days | Fri 10/11/24 | Fri 10/11/24 | 574 | 1387 |  | Jimmy Cox
7144 | 576 | Future Task |  | RW |  | Stacey Terry | Create | Support Agency Configuration Workbook | 20 hrs | 103 days | Mon 1/8/24 | Fri 5/31/24 | 131FS+6 days | 578,577SS+84 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
7222 | 577 | Future Task |  | RW |  | Stacey Terry | Create | Confirm Completeness of Agency Configuration Workbooks | 20 hrs | 39 days | Mon 5/6/24 | Fri 6/28/24 | 576SS+84 days |  |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
7145 | 578 | Future Task |  |  |  | Stacey Terry | Create | Update Configuration Workbooks and Load Agency Configurations | 20 hrs | 64 days | Mon 6/3/24 | Fri 8/30/24 | 576 |  |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
6808 | 579 | Future Task |  |  |  | Stacey Terry | Create | Define User Preferences | 2 hrs | 10 days | Wed 7/31/24 | Tue 8/13/24 | 242 | 1865 |  | Stacey Terry
6810 | 580 | Future Task |  |  |  | Stacey Terry | Create | Create Batch Design/Online | 2 hrs | 22 days | Mon 7/1/24 | Wed 7/31/24 | 51,70,110,150,169FS+24 days | 581 |  | Stacey Terry,Manojkumar Gurjar
6807 | 581 | Future Task |  |  |  | Stacey Terry | Create | Create Batch Design/Interface | 2 hrs | 22 days | Thu 8/1/24 | Fri 8/30/24 | 580 | 582 |  | Stacey Terry,Manojkumar Gurjar
6811 | 582 | Future Task |  |  |  | Stacey Terry | Create | Review and Confirm Batch Design | 2 hrs | 20 days | Tue 9/3/24 | Mon 9/30/24 | 581 | 583 |  | Stacey Terry,Manojkumar Gurjar
7243 | 583 | Future Task |  |  |  | Manojkumar Gurjar | Create | Setup/configure Tidal Batch/ FIN online | 240 hrs | 40 days | Tue 10/1/24 | Tue 11/26/24 | 582 | 584,585SS |  | Rahul Yadav,Carlos Luis
7242 | 584 | Future Task |  |  |  | Manojkumar Gurjar | Create | Setup/Configure Tidal Batch / FIN interfaces | 240 hrs | 40 days | Wed 11/27/24 | Tue 1/28/25 | 583 | 587 |  | Rahul Yadav,Carlos Luis
7241 | 585 | Future Task |  |  |  | Manojkumar Gurjar | Create | Setup/configure Tidal Batch/ Payroll online | 240 hrs | 40 days | Tue 10/1/24 | Tue 11/26/24 | 583SS | 586 |  | Rahul Yadav,Carlos Luis
7240 | 586 | Future Task |  |  |  | Manojkumar Gurjar | Create | Setup/Configure Tidal Batch / Payroll interfaces | 240 hrs | 40 days | Wed 11/27/24 | Tue 1/28/25 | 585 | 587 |  | Rahul Yadav,Carlos Luis
7239 | 587 | Future Task |  |  |  | Manojkumar Gurjar | Create | Review/Finalize Tidal Batch configuration | 276 hrs | 23 days | Wed 1/29/25 | Fri 2/28/25 | 586584 | 1274 |  | Rahul Yadav,Carlos Luis
3771 | 588 | Future Task | [5 empty] | Test | 19,605.58 hrs | 621 days | Mon 7/3/23 | Thu 12/18/25
7173 | 589 | Future Task |  |  | SG2 | Jimmy Cox | Create | Stage Gate 2: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 3/4/24 | Fri 3/8/24 |  | 590 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7174 | 590 | Future Task |  |  | SG2 | Jimmy Cox | Create | Stage Gate 2: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 589 | 591FS+80 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7175 | 591 | Future Task |  |  | SG2 | Jimmy Cox | Create | Stage Gate 2: Prepare information package for ESC | 11 hrs | 10 days | Wed 7/17/24 | Tue 7/30/24 | 590FS+80 days | 592 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7176 | 592 | Future Task |  |  | SG2 | Jimmy Cox | Create | Stage Gate 2: Collaborative Review and Update of information package | 11 hrs | 5 days | Wed 7/31/24 | Tue 8/6/24 | 591 | 593 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7177 | 593 | Future Task |  |  | SG2 | Jimmy Cox | Create | Stage Gate 2: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 8/7/24 | Wed 8/7/24 | 592 |  |  | Dusti Kincl
7153 | 594 | Future Task |  |  | SG2 | Jimmy Cox | Milestone | Stage Gate 2: Ready to Begin System Testing | 0 hrs | 0 days | Wed 5/8/24 | Wed 5/8/24 | 51,70,150,162,386 |  | July/August 2024 | Jimmy Cox,Angie Robertson,Matt Cole
7178 | 595 | Future Task |  |  | SG3 | Jimmy Cox | Create | Stage Gate 3: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 |  | 596 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7179 | 596 | Future Task |  |  | SG3 | Jimmy Cox | Create | Stage Gate 3: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 595 | 597FS+76 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7180 | 597 | Future Task |  |  | SG3 | Jimmy Cox | Create | Stage Gate 3: Prepare information package for ESC | 11 hrs | 10 days | Wed 2/19/25 | Tue 3/4/25 | 596FS+76 days | 598 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7181 | 598 | Future Task |  |  | SG3 | Jimmy Cox | Create | Stage Gate 3: Collaborative Review and Update of information package | 11 hrs | 5 days | Wed 3/5/25 | Tue 3/11/25 | 597 | 599 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7182 | 599 | Future Task |  |  | SG3 | Jimmy Cox | Create | Stage Gate 3: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 3/12/25 | Wed 3/12/25 | 598 |  |  | Dusti Kincl
7154 | 600 | Future Task |  |  | SG3 | Jimmy Cox | Milestone | Stage Gate 3: Ready to Begin UAT | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 51,70,150,169,386,422,442,464,484,504,524,1272,752,692,651,563 |  | March 2025 - ESC | Executive Steering Committee
4662 | 601 | Future Task |  |  | D643 | Stacey Terry |  | D643 - Updated System Testing Plan | 217 hrs | 179 days | Mon 7/3/23 | Tue 3/19/24
4663 | 602 | Future Task |  |  | D643 | Stacey Terry | Create | DED D643 - Updated System Testing Plan - Create | 16 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 1FS+47 days | 603 |  | Stacey Terry,Mary Punty
4664 | 603 | Future Task |  |  | D643 | Stacey Terry | Submit | DED D643 - Updated System Testing Plan - Submit | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 602 | 604 |  | Stacey Terry,Joy Schneider
4665 | 604 | Future Task |  |  | D643 | Stacey Terry | Review | DED D643 - Updated System Testing Plan - Collaborative Review | 24 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 603 | 605 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4666 | 605 | Future Task |  |  | D643 | Stacey Terry | Approve | DED D643 - Updated System Testing Plan - Approve | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 604 | 606FS+80 days |  | Jimmy Cox
4685 | 606 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define System Test approach for Financials and Payroll | 20 hrs | 15 days | Mon 11/27/23 | Fri 12/15/23 | 605FS+80 days | 607 |  | Yogesh Deshmukh,Stacey Terry,Mary Punty,Manojkumar Gurjar,Kurt Meisner,Matt Cole
4686 | 607 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define System Test Cycles for Financials and Payroll | 20 hrs | 9 days | Mon 12/18/23 | Fri 12/29/23 | 606 | 608FS-4 days |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Mary Punty
4687 | 608 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Identify System Test Resources for Financials and Payroll | 20 hrs | 11 days | Tue 12/26/23 | Wed 1/10/24 | 607FS-4 days | 609SS+4 days |  | Stacey Terry,Manojkumar Gurjar,Janice Jackson,Tiffany Porter,Brendan Jones,Jennifer Reeves,Deana Metcalf,Matthew Breeding,Carolyn Hicks
4688 | 609 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define System Test Tools and Test Management processes | 20 hrs | 11 days | Tue 1/2/24 | Wed 1/17/24 | 608SS+4 days | 610FS-2 days |  | Yogesh Deshmukh,Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jennifer Reeves
4689 | 610 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Create Initial List of System Test Scenarios for Financials and Payroll | 20 hrs | 24 days | Tue 1/16/24 | Fri 2/16/24 | 609FS-2 days | 611FS-5 days |  | Yogesh Deshmukh,Stacey Terry,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4690 | 611 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define requirements traceability approach for system testing | 20 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 610FS-5 days | 612 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Mary Punty,Jennifer Reeves
4667 | 612 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 - Updated System Testing Plan - Draft Submission | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 611 | 613 |  | Stacey Terry,Joy Schneider
4668 | 613 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 2/26/24 | Fri 3/1/24 | 612 | 614 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4669 | 614 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Style Guide Review | 1 hr | 1 day | Mon 3/4/24 | Mon 3/4/24 | 613 | 615 |  | Dusti Kincl
4670 | 615 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Final Collaborative Review | 20 hrs | 5 days | Tue 3/5/24 | Mon 3/11/24 | 614 | 616 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4671 | 616 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Accenture QC | 4 hrs | 2 days | Tue 3/12/24 | Wed 3/13/24 | 615 | 617 |  | Joy Schneider
4672 | 617 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 - Updated System Testing Plan - Submit | 0 hrs | 0 days | Wed 3/13/24 | Wed 3/13/24 | 616 | 618 |  | Joy Schneider
4673 | 618 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Department QC | 4 hrs | 1 day | Thu 3/14/24 | Thu 3/14/24 | 617 | 619 |  | Tommy Werner,Gabriela Gibson
4674 | 619 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Contract Manager Review | 8 hrs | 3 days | Fri 3/15/24 | Tue 3/19/24 | 618 | 620 |  | Sean Buchanan
4675 | 620 | Future Task |  |  | D643 | Stacey Terry | Accept | DEL D643 - Updated System Testing Plan - Accept | 0 hrs | 0 days | Tue 3/19/24 | Tue 3/19/24 | 619 | 553,1249FS+101 days | 2024-03-01 | Sean Buchanan
5004 | 621 | Future Task | Yes |  | D651 | Manojkumar Gurjar |  | D651 - Completion of Mock Conversion I | 305 hrs | 90 days | Mon 6/17/24 | Tue 10/22/24
5005 | 622 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | DED D651 - Completion of Mock Conversion I - Create | 16 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 1053FS-47 days | 623 |  | Manojkumar Gurjar,Kurt Meisner
5006 | 623 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DED D651 - Completion of Mock Conversion I - Submit | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 622 | 624 |  | Manojkumar Gurjar,Joy Schneider
5007 | 624 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DED D651 - Completion of Mock Conversion I - Collaborative Review | 24 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 623 | 625 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5008 | 625 | Future Task |  |  | D651 | Manojkumar Gurjar | Approve | DED D651 - Completion of Mock Conversion I - Approve | 0 hrs | 0 days | Mon 7/15/24 | Mon 7/15/24 | 624 | 628FS+19 days,627FS+19 days,626FS+14 days |  | Jimmy Cox
7224 | 626 | Future Task |  | RW | D651 | Manojkumar Gurjar | Create | D651 - Confirm Agency Conversion Build and Unit Test Activities | 20 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 625FS+14 days | 629 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
7207 | 627 | Future Task |  | RW | D651 | Manojkumar Gurjar | Milestone | D651 - Confirm Conversion Files Received | 0 hrs | 0 days | Fri 8/9/24 | Fri 8/9/24 | 625FS+19 days | 629 |  | Matthew Breeding
5018 | 628 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | D651 - Confirm Mock 1 Conversion Test Environment Readiness | 20 hrs | 5 days | Mon 8/12/24 | Fri 8/16/24 | 625FS+19 days | 629 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5019 | 629 | Future Task |  | RW | D651 | Manojkumar Gurjar | Create | D651 - Create Mock 1 Conversion Checklist | 20 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 628627626 | 630 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5020 | 630 | Future Task |  | RW | D651 | Manojkumar Gurjar | Create | D651 - Execute Mock 1 – Conversion | 108 hrs | 9 days | Tue 9/3/24 | Fri 9/13/24 | 62955816991703 | 631 |  | Jeevan Mahajan,Janmejay Khare
5021 | 631 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | D651 - Validate Mock 1 – Conversion | 20 hrs | 5 days | Mon 9/16/24 | Fri 9/20/24 | 630 | 632 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5022 | 632 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | D651 - Conduct Mock 1 - Conversion Test Exit Criteria Review Meeting | 20 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 631 | 633 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5009 | 633 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DEL D651 - Completion of Mock Conversion I - Draft Submission | 0 hrs | 0 days | Fri 9/27/24 | Fri 9/27/24 | 632 | 634 |  | Manojkumar Gurjar,Joy Schneider
5010 | 634 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 9/30/24 | Fri 10/4/24 | 633 | 635 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5011 | 635 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Style Guide Review | 1 hr | 1 day | Mon 10/7/24 | Mon 10/7/24 | 634 | 636 |  | Dusti Kincl
5012 | 636 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Final Collaborative Review | 20 hrs | 5 days | Tue 10/8/24 | Mon 10/14/24 | 635 | 637 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5013 | 637 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Accenture QC | 4 hrs | 2 days | Tue 10/15/24 | Wed 10/16/24 | 636 | 638 |  | Joy Schneider
5014 | 638 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DEL D651 - Completion of Mock Conversion I - Submit | 0 hrs | 0 days | Wed 10/16/24 | Wed 10/16/24 | 637 | 639 |  | Joy Schneider
5015 | 639 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Department QC | 4 hrs | 1 day | Thu 10/17/24 | Thu 10/17/24 | 638 | 640 |  | Tommy Werner,Gabriela Gibson
5016 | 640 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Contract Manager Review | 8 hrs | 3 days | Fri 10/18/24 | Tue 10/22/24 | 639 | 641 |  | Sean Buchanan
5017 | 641 | Future Task |  |  | D651 | Manojkumar Gurjar | Accept | DEL D651 - Completion of Mock Conversion I - Accept | 0 hrs | 0 days | Tue 10/22/24 | Tue 10/22/24 | 640 | 666FS-32 days | 2024-11-01 | Sean Buchanan
4696 | 642 | Future Task | Yes |  | D652 | Stacey Terry |  | D652 - Completion of System Test Segment I | 4,480 hrs | 123 days | Mon 7/8/24 | Thu 1/2/25
4697 | 643 | Future Task |  |  | D652 | Stacey Terry | Create | DED D652 - Completion of System Test Segment I - Create | 16 hrs | 10 days | Mon 7/8/24 | Fri 7/19/24 | 1 | 644 |  | Stacey Terry,Mary Punty
4698 | 644 | Future Task |  |  | D652 | Stacey Terry | Submit | DED D652 - Completion of System Test Segment I - Submit | 0 hrs | 0 days | Fri 7/19/24 | Fri 7/19/24 | 643 | 645 |  | Stacey Terry,Joy Schneider
4699 | 645 | Future Task |  |  | D652 | Stacey Terry | Review | DED D652 - Completion of System Test Segment I - Collaborative Review | 24 hrs | 10 days | Mon 7/22/24 | Fri 8/2/24 | 644 | 646 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4700 | 646 | Future Task |  |  | D652 | Stacey Terry | Approve | DED D652 - Completion of System Test Segment I - Approve | 0 hrs | 0 days | Fri 8/2/24 | Fri 8/2/24 | 645 | 647 |  | Jimmy Cox
4752 | 647 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Create Work Unit Tracker for System Test Segment 1 Execution | 20 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 646 | 648 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4753 | 648 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Review, Update and confirm Work Unit Tracker for System Test Segment 1 Execution | 20 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 647 | 649SS+5 days |  | Mary Punty,Stacey Terry,Deana Metcalf,Janice Jackson,Tiffany Porter,Brendan Jones
4754 | 649 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Confirm System Test Environment Readiness | 20 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 648SS+5 days | 650SS |  | Manojkumar Gurjar,Jarad Hermann
4755 | 650 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Conduct System Test Kick Off Meeting | 30 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 649SS | 651 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4756 | 651 | Future Task | Maybe |  | D652 | Stacey Terry | Create | D652 - Execute System Test Segment 1 | 4,284 hrs | 51 days | Tue 9/17/24 | Wed 11/27/24 | 6501067554 | 652,653FS-3 days,600 |  | Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4757 | 652 | Future Task |  |  | D652 | Stacey Terry | Milestone | D652 - Milestone: System Test Segment 1 Execution Complete | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 651 | 1758 |  | Stacey Terry
4758 | 653 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Create Completion of System Testing Segment 1 Summary Document | 3 hrs | 8 days | Mon 11/25/24 | Fri 12/6/24 | 651FS-3 days | 654SS+3 days,655SS+3 days,656 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4759 | 654 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Conduct System Test Segment 1 Exit Criteria Review Meeting | 3 hrs | 5 days | Mon 12/2/24 | Fri 12/6/24 | 653SS+3 days | 656 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4760 | 655 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Confirm requirements traceability for System Test Segment 1 | 3 hrs | 5 days | Mon 12/2/24 | Fri 12/6/24 | 653SS+3 days | 656 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4701 | 656 | Future Task |  |  | D652 | Stacey Terry | Submit | DEL D652 - Completion of System Test Segment I - Draft Submission | 0 hrs | 0 days | Fri 12/6/24 | Fri 12/6/24 | 653654655 | 657 |  | Stacey Terry,Joy Schneider
4702 | 657 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 12/9/24 | Fri 12/13/24 | 656 | 658 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4703 | 658 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Style Guide Review | 1 hr | 1 day | Mon 12/16/24 | Mon 12/16/24 | 657 | 659 |  | Dusti Kincl
4704 | 659 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Final Collaborative Review | 20 hrs | 5 days | Tue 12/17/24 | Mon 12/23/24 | 658 | 660 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4705 | 660 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Accenture QC | 4 hrs | 2 days | Tue 12/24/24 | Thu 12/26/24 | 659 | 661 |  | Joy Schneider
4706 | 661 | Future Task |  |  | D652 | Stacey Terry | Submit | DEL D652 - Completion of System Test Segment I - Submit | 0 hrs | 0 days | Thu 12/26/24 | Thu 12/26/24 | 660 | 662 |  | Joy Schneider
4707 | 662 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Department QC | 4 hrs | 1 day | Fri 12/27/24 | Fri 12/27/24 | 661 | 663 |  | Tommy Werner,Gabriela Gibson
4708 | 663 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Contract Manager Review | 8 hrs | 3 days | Mon 12/30/24 | Thu 1/2/25 | 662 | 664 |  | Sean Buchanan
4709 | 664 | Future Task |  |  | D652 | Stacey Terry | Accept | DEL D652 - Completion of System Test Segment I - Accept | 0 hrs | 0 days | Thu 1/2/25 | Thu 1/2/25 | 663 |  | 2024-12-01 | Sean Buchanan
4710 | 665 | Future Task | Yes |  | D655 | Manojkumar Gurjar |  | D655 - Completion of Mock Conversion II (System Test Environment) | 237 hrs | 94 days | Mon 9/9/24 | Fri 1/24/25
4711 | 666 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | DED D655 - Completion of Mock Conversion II (System Test Environment) - Create | 16 hrs | 10 days | Mon 9/9/24 | Fri 9/20/24 | 641FS-32 days | 667 |  | Manojkumar Gurjar,Kurt Meisner
4712 | 667 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DED D655 - Completion of Mock Conversion II (System Test Environment) - Submit | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 666 | 668 |  | Manojkumar Gurjar,Joy Schneider
4713 | 668 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DED D655 - Completion of Mock Conversion II (System Test Environment) - Collaborative Review | 24 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 667 | 669 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4714 | 669 | Future Task |  |  | D655 | Manojkumar Gurjar | Approve | DED D655 - Completion of Mock Conversion II (System Test Environment) - Approve | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 668 | 671FS+29 days,670FS+29 days |  | Jimmy Cox
7208 | 670 | Future Task |  | RW | D655 | Manojkumar Gurjar | Milestone | D655 - Confirm Conversion Files Received | 0 hrs | 0 days | Fri 11/15/24 | Fri 11/15/24 | 669FS+29 days | 672 |  | Matthew Breeding
4761 | 671 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | D655 - Confirm Mock 2 Conversion - System Test Environment Readiness | 20 hrs | 4 days | Mon 11/18/24 | Thu 11/21/24 | 669FS+29 days | 672 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4762 | 672 | Future Task |  | RW | D655 | Manojkumar Gurjar | Create | D655 - Create Mock 2 Conversion Checklist (System Test Environment) | 20 hrs | 5 days | Fri 11/22/24 | Mon 12/2/24 | 671670 | 673 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4763 | 673 | Future Task |  | RW | D655 | Manojkumar Gurjar | Create | D655 - Execute Mock 2 – Conversion (System Test Environment) | 60 hrs | 10 days | Tue 12/3/24 | Mon 12/16/24 | 672 | 674 |  | Jeevan Mahajan,Janmejay Khare
4764 | 674 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | D655 - Validate Mock 2 – Conversion (System Test Environment) | 20 hrs | 4 days | Tue 12/17/24 | Fri 12/20/24 | 673 | 675 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4765 | 675 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | D655 - Conduct Mock 2 - Conversion (System Test Environment) Test Exit Criteria Review Meeting | 20 hrs | 5 days | Mon 12/23/24 | Mon 12/30/24 | 674 | 676 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4715 | 676 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Draft Submission | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 675 | 677 |  | Manojkumar Gurjar,Joy Schneider
4716 | 677 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 12/31/24 | Tue 1/7/25 | 676 | 678 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4717 | 678 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Style Guide Review | 1 hr | 1 day | Wed 1/8/25 | Wed 1/8/25 | 677 | 679 |  | Dusti Kincl
4718 | 679 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Final Collaborative Review | 20 hrs | 5 days | Thu 1/9/25 | Wed 1/15/25 | 678 | 680 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4719 | 680 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Accenture QC | 4 hrs | 2 days | Thu 1/16/25 | Fri 1/17/25 | 679 | 681 |  | Joy Schneider
4720 | 681 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Submit | 0 hrs | 0 days | Fri 1/17/25 | Fri 1/17/25 | 680 | 682 |  | Joy Schneider
4721 | 682 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Department QC | 4 hrs | 1 day | Tue 1/21/25 | Tue 1/21/25 | 681 | 683 |  | Tommy Werner,Gabriela Gibson
4722 | 683 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Contract Manager Review | 8 hrs | 3 days | Wed 1/22/25 | Fri 1/24/25 | 682 | 684 |  | Sean Buchanan
4723 | 684 | Future Task |  |  | D655 | Manojkumar Gurjar | Accept | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Accept | 0 hrs | 0 days | Fri 1/24/25 | Fri 1/24/25 | 683 | 707FS-64 days | 2025-01-01 | Sean Buchanan
4724 | 685 | Future Task | Yes |  | D656 | Stacey Terry |  | D656 - Completion of System Test Segment II | 1,814 hrs | 99 days | Mon 10/7/24 | Fri 2/28/25
4725 | 686 | Future Task |  |  | D656 | Stacey Terry | Create | DED D656 - Completion of System Test Segment II - Create | 16 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1 | 687 |  | Stacey Terry,Mary Punty
4726 | 687 | Future Task |  |  | D656 | Stacey Terry | Submit | DED D656 - Completion of System Test Segment II - Submit | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 686 | 688 |  | Stacey Terry,Joy Schneider
4727 | 688 | Future Task |  |  | D656 | Stacey Terry | Review | DED D656 - Completion of System Test Segment II - Collaborative Review | 20 hrs | 10 days | Mon 10/21/24 | Fri 11/1/24 | 687 | 689 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4728 | 689 | Future Task |  |  | D656 | Stacey Terry | Approve | DED D656 - Completion of System Test Segment II - Approve | 0 hrs | 0 days | Fri 11/1/24 | Fri 11/1/24 | 688 | 690 |  | Jimmy Cox
4766 | 690 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Create Work Unit Tracker for System Test Segment 2 Execution | 6 hrs | 9 days | Mon 11/4/24 | Fri 11/15/24 | 689 | 691 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4767 | 691 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Review, Update and confirm Work Unit Tracker for System Test Segment 2 Execution | 20 hrs | 8 days | Mon 11/18/24 | Wed 11/27/24 | 690 | 692 |  | Mary Punty,Stacey Terry,Deana Metcalf,Janice Jackson,Tiffany Porter,Brendan Jones
4768 | 692 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Execute System Test Segment 2 | 1,680 hrs | 40 days | Mon 12/2/24 | Wed 1/29/25 | 691 | 693,694FS-5 days,600 |  | Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4769 | 693 | Future Task |  |  | D656 | Stacey Terry | Milestone | D656 - Milestone: System Test Segment 2 Execution Complete | 0 hrs | 0 days | Wed 1/29/25 | Wed 1/29/25 | 692 |  |  | Stacey Terry
4770 | 694 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Create Completion of System Testing Segment 2 Summary Document | 6 hrs | 10 days | Thu 1/23/25 | Wed 2/5/25 | 692FS-5 days | 695SS+5 days,696SS+5 days,697 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4771 | 695 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Conduct System Test Segment 2 Exit Criteria Review Meeting | 3 hrs | 5 days | Thu 1/30/25 | Wed 2/5/25 | 694SS+5 days | 697 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4772 | 696 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Confirm requirements traceability for System Test Segment 2 | 6 hrs | 5 days | Thu 1/30/25 | Wed 2/5/25 | 694SS+5 days | 697 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4729 | 697 | Future Task |  |  | D656 | Stacey Terry | Submit | DEL D656 - Completion of System Test Segment II - Draft Submission | 0 hrs | 0 days | Wed 2/5/25 | Wed 2/5/25 | 694695696 | 698 |  | Stacey Terry,Joy Schneider
4730 | 698 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Thu 2/6/25 | Wed 2/12/25 | 697 | 699 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4731 | 699 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Style Guide Review | 1 hr | 1 day | Thu 2/13/25 | Thu 2/13/25 | 698 | 700 |  | Dusti Kincl
4732 | 700 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Final Collaborative Review | 20 hrs | 5 days | Fri 2/14/25 | Thu 2/20/25 | 699 | 701 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4733 | 701 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Accenture QC | 4 hrs | 2 days | Fri 2/21/25 | Mon 2/24/25 | 700 | 702 |  | Joy Schneider
4734 | 702 | Future Task |  |  | D656 | Stacey Terry | Submit | DEL D656 - Completion of System Test Segment II - Submit | 0 hrs | 0 days | Mon 2/24/25 | Mon 2/24/25 | 701 | 703 |  | Joy Schneider
4735 | 703 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Department QC | 4 hrs | 1 day | Tue 2/25/25 | Tue 2/25/25 | 702 | 704 |  | Tommy Werner,Gabriela Gibson
4736 | 704 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Contract Manager Review | 8 hrs | 3 days | Wed 2/26/25 | Fri 2/28/25 | 703 | 705 |  | Sean Buchanan
4737 | 705 | Future Task |  |  | D656 | Stacey Terry | Accept | DEL D656 - Completion of System Test Segment II - Accept | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 704 |  | 2025-02-01 | Sean Buchanan
4738 | 706 | Future Task | Yes |  | D657 | Manojkumar Gurjar |  | D657 - Completion of Mock Conversion III (UAT) | 393 hrs | 101 days | Mon 10/21/24 | Tue 3/18/25
4739 | 707 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | DED D657 - Completion of Mock Conversion III (UAT) - Create | 16 hrs | 10 days | Mon 10/21/24 | Fri 11/1/24 | 684FS-64 days | 708 |  | Manojkumar Gurjar,Kurt Meisner
4740 | 708 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DED D657 - Completion of Mock Conversion III (UAT) - Submit | 0 hrs | 0 days | Fri 11/1/24 | Fri 11/1/24 | 707 | 709 |  | Manojkumar Gurjar,Joy Schneider
4741 | 709 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DED D657 - Completion of Mock Conversion III (UAT) - Collaborative Review | 24 hrs | 10 days | Mon 11/4/24 | Mon 11/18/24 | 708 | 710 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4742 | 710 | Future Task |  |  | D657 | Manojkumar Gurjar | Approve | DED D657 - Completion of Mock Conversion III (UAT) - Approve | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 709 | 712FS+24 days,711FS+24 days |  | Jimmy Cox
7209 | 711 | Future Task |  | RW | D657 | Manojkumar Gurjar | Milestone | D657 - Confirm Conversion Files Received | 0 hrs | 0 days | Tue 12/24/24 | Tue 12/24/24 | 710FS+24 days | 713
4773 | 712 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | D657 - Confirm Mock 3 Conversion - UAT Environment Readiness | 2 hrs | 5 days | Thu 12/26/24 | Thu 1/2/25 | 710FS+24 days | 713 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4774 | 713 | Future Task |  | RW | D657 | Manojkumar Gurjar | Create | D657 - Create Mock 3 Conversion Checklist (UAT) | 2 hrs | 6 days | Fri 1/3/25 | Fri 1/10/25 | 712711 | 714 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4775 | 714 | Future Task |  | RW | D657 | Manojkumar Gurjar | Create | D657 - Execute Mock 3 – Conversion (UAT) | 252 hrs | 21 days | Mon 1/13/25 | Tue 2/11/25 | 713 | 715 |  | Jeevan Mahajan,Janmejay Khare
4776 | 715 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | D657 - Validate Mock 3 – Conversion (UAT) | 20 hrs | 4 days | Wed 2/12/25 | Mon 2/17/25 | 714 | 716 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4777 | 716 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | D657 - Conduct Mock 3 - Conversion UAT Exit Criteria Review Meeting | 20 hrs | 4 days | Tue 2/18/25 | Fri 2/21/25 | 715 | 717 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4743 | 717 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DEL D657 - Completion of Mock Conversion III (UAT) - Draft Submission | 0 hrs | 0 days | Fri 2/21/25 | Fri 2/21/25 | 716 | 718 |  | Manojkumar Gurjar,Joy Schneider
4744 | 718 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 717 | 719 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4745 | 719 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Style Guide Review | 1 hr | 1 day | Mon 3/3/25 | Mon 3/3/25 | 718 | 720 |  | Dusti Kincl
4746 | 720 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Final Collaborative Review | 20 hrs | 5 days | Tue 3/4/25 | Mon 3/10/25 | 719 | 721 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4747 | 721 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Accenture QC | 4 hrs | 2 days | Tue 3/11/25 | Wed 3/12/25 | 720 | 722 |  | Joy Schneider
4748 | 722 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DEL D657 - Completion of Mock Conversion III (UAT) - Submit | 0 hrs | 0 days | Wed 3/12/25 | Wed 3/12/25 | 721 | 723 |  | Joy Schneider
4749 | 723 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Department QC | 4 hrs | 1 day | Thu 3/13/25 | Thu 3/13/25 | 722 | 724 |  | Tommy Werner,Gabriela Gibson
4750 | 724 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Contract Manager Review | 8 hrs | 3 days | Fri 3/14/25 | Tue 3/18/25 | 723 | 725 |  | Sean Buchanan
4751 | 725 | Future Task |  |  | D657 | Manojkumar Gurjar | Accept | DEL D657 - Completion of Mock Conversion III (UAT) - Accept | 0 hrs | 0 days | Tue 3/18/25 | Tue 3/18/25 | 724 | 767FS-46 days,1284 | 2025-02-01 | Sean Buchanan
5023 | 726 | Future Task |  |  | D660 | Stacey Terry |  | D660 - Payroll Parallel Testing Plan | 182 hrs | 94 days | Mon 12/2/24 | Tue 4/15/25
5024 | 727 | Future Task |  |  | D660 | Stacey Terry | Create | DED D660 - Payroll Parallel Testing Plan - Create | 16 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 200 | 728 |  | Stacey Terry,Mary Punty
5025 | 728 | Future Task |  |  | D660 | Stacey Terry | Submit | DED D660 - Payroll Parallel Testing Plan - Submit | 0 hrs | 0 days | Fri 12/13/24 | Fri 12/13/24 | 727 | 729,1110SS-4 days |  | Stacey Terry,Joy Schneider
5026 | 729 | Future Task |  |  | D660 | Stacey Terry | Review | DED D660 - Payroll Parallel Testing Plan - Collaborative Review | 24 hrs | 10 days | Mon 12/16/24 | Mon 12/30/24 | 728 | 730 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5027 | 730 | Future Task |  |  | D660 | Stacey Terry | Approve | DED D660 - Payroll Parallel Testing Plan - Approve | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 729 | 731FS+22 days |  | Jimmy Cox
5037 | 731 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Define Payroll Parallel Test approach | 20 hrs | 20 days | Mon 2/3/25 | Fri 2/28/25 | 730FS+22 days | 732FS-5 days |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5038 | 732 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Define Payroll Parallel Test Cycles | 15 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 731FS-5 days | 733 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5039 | 733 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Identify Test Resources for Payroll Parallel Test | 20 hrs | 5 days | Mon 3/3/25 | Fri 3/7/25 | 732 | 734 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5040 | 734 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Define Payroll Parallel Test Tools and Test Management processes | 20 hrs | 5 days | Mon 3/10/25 | Fri 3/14/25 | 733 | 735FS-5 days |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5041 | 735 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Create Initial List of Payroll Parallel Test Scenarios | 20 hrs | 10 days | Mon 3/10/25 | Fri 3/21/25 | 734FS-5 days | 736 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5028 | 736 | Future Task |  |  | D660 | Stacey Terry | Submit | DEL D660 - Payroll Parallel Testing Plan - Draft Submission | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 735 | 737 |  | Stacey Terry,Joy Schneider
5029 | 737 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 736 | 738 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5030 | 738 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Style Guide Review | 1 hr | 1 day | Mon 3/31/25 | Mon 3/31/25 | 737 | 739 |  | Dusti Kincl
5031 | 739 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Final Collaborative Review | 10 hrs | 5 days | Tue 4/1/25 | Mon 4/7/25 | 738 | 740 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5032 | 740 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Accenture QC | 4 hrs | 2 days | Tue 4/8/25 | Wed 4/9/25 | 739 | 741 |  | Joy Schneider
5033 | 741 | Future Task |  |  | D660 | Stacey Terry | Submit | DEL D660 - Payroll Parallel Testing Plan - Submit | 0 hrs | 0 days | Wed 4/9/25 | Wed 4/9/25 | 740 | 742 |  | Joy Schneider
5034 | 742 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Department QC | 4 hrs | 1 day | Thu 4/10/25 | Thu 4/10/25 | 741 | 743 |  | Tommy Werner,Gabriela Gibson
5035 | 743 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Contract Manager Review | 8 hrs | 3 days | Fri 4/11/25 | Tue 4/15/25 | 742 | 744 |  | Sean Buchanan
5036 | 744 | Future Task |  |  | D660 | Stacey Terry | Accept | DEL D660 - Payroll Parallel Testing Plan - Accept | 0 hrs | 0 days | Tue 4/15/25 | Tue 4/15/25 | 743 | 871FS-37 days | 2025-04-01 | Sean Buchanan
4778 | 745 | Future Task | Yes |  | D661 | Stacey Terry |  | D661 - Completion of System Test DW/BI | 547 hrs | 130 days | Mon 10/21/24 | Mon 4/28/25
4779 | 746 | Future Task |  |  | D661 | Stacey Terry | Create | DED D661 - Completion of System Test DW/BI - Create | 16 hrs | 10 days | Mon 10/21/24 | Fri 11/1/24 | 1 | 747 |  | Stacey Terry,Mary Punty
4780 | 747 | Future Task |  |  | D661 | Stacey Terry | Submit | DED D661 - Completion of System Test DW/BI - Submit | 0 hrs | 0 days | Fri 11/1/24 | Fri 11/1/24 | 746 | 748 |  | Stacey Terry,Joy Schneider
4781 | 748 | Future Task |  |  | D661 | Stacey Terry | Review | DED D661 - Completion of System Test DW/BI - Collaborative Review | 24 hrs | 10 days | Mon 11/4/24 | Mon 11/18/24 | 747 | 749 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4782 | 749 | Future Task |  |  | D661 | Stacey Terry | Approve | DED D661 - Completion of System Test DW/BI - Approve | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 748 | 750FS+10 days |  | Jimmy Cox
4820 | 750 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Create Work Unit Tracker for System Test DW/BI Execution | 36 hrs | 9 days | Thu 12/5/24 | Tue 12/17/24 | 749FS+10 days | 751 |  | Manojkumar Gurjar,Mary Punty
4821 | 751 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Review, Update and confirm Work Unit Tracker for System Test DW/BI Execution | 20 hrs | 10 days | Wed 12/18/24 | Thu 1/2/25 | 750 | 752 |  | Manojkumar Gurjar,Mary Punty
4822 | 752 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Execute System Test DW/BI | 360 hrs | 60 days | Fri 1/3/25 | Fri 3/28/25 | 751 | 753,754FS-6 days,600 |  | Jack Jenkins,Anthony Bastidas
4823 | 753 | Future Task |  |  | D661 | Stacey Terry | Milestone | D661 - Milestone: System Test DW/BI Execution Complete | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 752 |  |  | Stacey Terry
4824 | 754 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Create Completion of System Testing DW/BI Summary Document | 4 hrs | 10 days | Fri 3/21/25 | Thu 4/3/25 | 752FS-6 days | 755SS+5 days,757 |  | Manojkumar Gurjar,Mary Punty
4825 | 755 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Conduct System Test DW/BI Exit Criteria Review Meeting | 10 hrs | 5 days | Fri 3/28/25 | Thu 4/3/25 | 754SS+5 days | 756SS,757 |  | Manojkumar Gurjar,Mary Punty
4826 | 756 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Confirm requirements traceability for System Test DW/BI | 20 hrs | 5 days | Fri 3/28/25 | Thu 4/3/25 | 755SS | 757 |  | Manojkumar Gurjar,Mary Punty
4783 | 757 | Future Task |  |  | D661 | Stacey Terry | Submit | DEL D661 - Completion of System Test DW/BI - Draft Submission | 0 hrs | 0 days | Thu 4/3/25 | Thu 4/3/25 | 754755756 | 758 |  | Stacey Terry,Joy Schneider
4784 | 758 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 4/4/25 | Thu 4/10/25 | 757 | 759 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4785 | 759 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Style Guide Review | 1 hr | 1 day | Fri 4/11/25 | Fri 4/11/25 | 758 | 760 |  | Dusti Kincl
4786 | 760 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Final Collaborative Review | 20 hrs | 5 days | Mon 4/14/25 | Fri 4/18/25 | 759 | 761 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4787 | 761 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Accenture QC | 4 hrs | 2 days | Mon 4/21/25 | Tue 4/22/25 | 760 | 762 |  | Joy Schneider
4788 | 762 | Future Task |  |  | D661 | Stacey Terry | Submit | DEL D661 - Completion of System Test DW/BI - Submit | 0 hrs | 0 days | Tue 4/22/25 | Tue 4/22/25 | 761 | 763 |  | Joy Schneider
4789 | 763 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Department QC | 4 hrs | 1 day | Wed 4/23/25 | Wed 4/23/25 | 762 | 764 |  | Tommy Werner,Gabriela Gibson
4790 | 764 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Contract Manager Review | 8 hrs | 3 days | Thu 4/24/25 | Mon 4/28/25 | 763 | 765 |  | Sean Buchanan
4791 | 765 | Future Task |  |  | D661 | Stacey Terry | Accept | DEL D661 - Completion of System Test DW/BI - Accept | 0 hrs | 0 days | Mon 4/28/25 | Mon 4/28/25 | 764 | 1276FS+4 days | 2025-05-01 | Sean Buchanan
4792 | 766 | Future Task | Yes |  | D662 | Manojkumar Gurjar |  | D662 - Completion of Dress Rehearsal (Mock Conversion IV) | 297 hrs | 96 days | Mon 1/13/25 | Wed 5/28/25
4793 | 767 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Create | 16 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 725FS-46 days | 768 |  | Manojkumar Gurjar,Kurt Meisner
4794 | 768 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Submit | 0 hrs | 0 days | Mon 1/27/25 | Mon 1/27/25 | 767 | 769 |  | Manojkumar Gurjar,Joy Schneider
4795 | 769 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Collaborative Review | 24 hrs | 10 days | Tue 1/28/25 | Mon 2/10/25 | 768 | 770 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4796 | 770 | Future Task |  |  | D662 | Manojkumar Gurjar | Approve | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Approve | 0 hrs | 0 days | Mon 2/10/25 | Mon 2/10/25 | 769 | 772FS+24 days,771FS+24 days |  | Jimmy Cox
7210 | 771 | Future Task |  | RW | D662 | Manojkumar Gurjar | Milestone | D662 - Confirm Conversion Files Received | 0 hrs | 0 days | Fri 3/14/25 | Fri 3/14/25 | 770FS+24 days | 773 |  | Matthew Breeding
4827 | 772 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | D662 - Confirm Mock 4 Conversion - (Dress Rehearsal) Environment Readiness | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 770FS+24 days | 773 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4828 | 773 | Future Task |  | RW | D662 | Manojkumar Gurjar | Create | D662 - Create Mock 4 Conversion Checklist (Dress Rehearsal) | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 772771 | 774 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4829 | 774 | Future Task |  | RW | D662 | Manojkumar Gurjar | Create | D662 - Execute Mock 4 – Conversion (Dress Rehearsal) | 120 hrs | 10 days | Mon 3/31/25 | Fri 4/11/25 | 773 | 775 |  | Jeevan Mahajan,Janmejay Khare
4830 | 775 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | D662 - Validate Mock 4 – Conversion (Dress Rehearsal) | 20 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 774 | 776 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4831 | 776 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | D662 - Conduct Mock 4 - Conversion (Dress Rehearsal) Exit Criteria Review Meeting | 20 hrs | 5 days | Mon 4/28/25 | Fri 5/2/25 | 775 | 777 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4797 | 777 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Draft Submission | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 776 | 778 |  | Manojkumar Gurjar,Joy Schneider
4798 | 778 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 5/5/25 | Fri 5/9/25 | 777 | 779 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4799 | 779 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Style Guide Review | 1 hr | 1 day | Mon 5/12/25 | Mon 5/12/25 | 778 | 780 |  | Dusti Kincl
4800 | 780 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Final Collaborative Review | 20 hrs | 5 days | Tue 5/13/25 | Mon 5/19/25 | 779 | 781 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4801 | 781 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Accenture QC | 4 hrs | 2 days | Tue 5/20/25 | Wed 5/21/25 | 780 | 782 |  | Joy Schneider
4802 | 782 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Submit | 0 hrs | 0 days | Wed 5/21/25 | Wed 5/21/25 | 781 | 783 |  | Joy Schneider
4803 | 783 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Department QC | 4 hrs | 1 day | Thu 5/22/25 | Thu 5/22/25 | 782 | 784 |  | Tommy Werner,Gabriela Gibson
4804 | 784 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Contract Manager Review | 8 hrs | 3 days | Fri 5/23/25 | Wed 5/28/25 | 783 | 785 |  | Sean Buchanan
4805 | 785 | Future Task |  |  | D662 | Manojkumar Gurjar | Accept | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Accept | 0 hrs | 0 days | Wed 5/28/25 | Wed 5/28/25 | 784 | 1284 | 2025-05-01 | Sean Buchanan
4806 | 786 | Future Task | Yes |  | D663 | Manojkumar Gurjar |  | D663 - Completion of Interface Testing Segment I | 541.58 hrs | 223 days | Mon 8/12/24 | Mon 6/30/25
4807 | 787 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | DED D663 - Completion of Interface Testing Segment I - Create | 24 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 1 | 788 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4808 | 788 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DED D663 - Completion of Interface Testing Segment I - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 787 | 789 |  | Manojkumar Gurjar,Joy Schneider
4809 | 789 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DED D663 - Completion of Interface Testing Segment I - Collaborative Review | 28 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 788 | 790 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4810 | 790 | Future Task |  |  | D663 | Manojkumar Gurjar | Approve | DED D663 - Completion of Interface Testing Segment I - Approve | 0 hrs | 0 days | Mon 9/9/24 | Mon 9/9/24 | 789 | 792FS+19 days,791FS+15 days |  | Jimmy Cox
7244 | 791 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Confirm Agency Interface Connections Information received | 10 hrs | 9 days | Tue 10/1/24 | Fri 10/11/24 | 790FS+15 days | 793 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4832 | 792 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Create Interface Testing Segment 1 Execution Work Unit Tracker | 30 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 790FS+19 days | 793,797SS,798SS |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4833 | 793 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Review/Confirm Interface Testing Segment 1 Execution Work Unit Tracker | 15 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 792791 | 794 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4834 | 794 | Future Task |  | RW | D663 | Manojkumar Gurjar | Create | D663 - Conduct Interface Testing Segment 1 Readiness Review Meeting | 15 hrs | 5 days | Mon 10/28/24 | Fri 11/1/24 | 793 | 795 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4835 | 795 | Future Task |  | RW | D663 | Manojkumar Gurjar | Create | D663 - Conduct Interface Test Kickoff Meeting with Integration Partners | 3 hrs | 9 days | Mon 11/4/24 | Fri 11/15/24 | 794 | 796 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4836 | 796 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Confirm Interface Test Environment Readiness | 15 hrs | 5 days | Mon 11/18/24 | Fri 11/22/24 | 795556 | 799 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4837 | 797 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Establish Interface Connectivity Segment 1 | 20 hrs | 20 days | Mon 10/7/24 | Fri 11/1/24 | 792SS | 799FS+17 days |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
7223 | 798 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Completed Interface Connection Inventory Files Received | 0 hrs | 0 days | Mon 10/7/24 | Mon 10/7/24 | 792SS | 799FS+17 days |  | Matthew Breeding
4838 | 799 | Future Task |  | RW | D663 | Manojkumar Gurjar | Create | D663 - Execute Interface Testing Segment 1 | 315 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 797FS+17 days,796,798FS+17 days,1660 | 800801 |  | Rahul Yadav,Carlos Luis
4839 | 800 | Future Task |  |  | D663 | Manojkumar Gurjar | Milestone | D663 - Milestone: Interface Testing Segment 1 Complete | 0 hrs | 0 days | Wed 4/30/25 | Wed 4/30/25 | 799 | 803 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4840 | 801 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Conduct Test Exit Criteria Review Meeting | 15 hrs | 5 days | Thu 5/1/25 | Wed 5/7/25 | 799 | 802 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4841 | 802 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Confirm requirements traceability for Interface Testing Segment 1 | 15 hrs | 10 days | Thu 5/8/25 | Wed 5/21/25 | 801 | 803 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4842 | 803 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Create Completion of Interface Testing Segment 1 Summary Document | 1.58 hrs | 10 days | Thu 5/22/25 | Thu 6/5/25 | 802800 | 804 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4811 | 804 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DEL D663 - Completion of Interface Testing Segment I - Draft Submission | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 803 | 805 |  | Manojkumar Gurjar,Joy Schneider
4812 | 805 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Pre-Submission Collaborative Review | 6 hrs | 5 days | Fri 6/6/25 | Thu 6/12/25 | 804 | 806 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4813 | 806 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Style Guide Review | 1 hr | 1 day | Fri 6/13/25 | Fri 6/13/25 | 805 | 807 |  | Dusti Kincl
4814 | 807 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Final Collaborative Review | 12 hrs | 5 days | Mon 6/16/25 | Fri 6/20/25 | 806 | 808 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4815 | 808 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Accenture QC | 4 hrs | 2 days | Mon 6/23/25 | Tue 6/24/25 | 807 | 809 |  | Joy Schneider
4816 | 809 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DEL D663 - Completion of Interface Testing Segment I - Submit | 0 hrs | 0 days | Tue 6/24/25 | Tue 6/24/25 | 808 | 810 |  | Joy Schneider
4817 | 810 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Department QC | 4 hrs | 1 day | Wed 6/25/25 | Wed 6/25/25 | 809 | 811 |  | Tommy Werner,Gabriela Gibson
4818 | 811 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Contract Manager Review | 8 hrs | 3 days | Thu 6/26/25 | Mon 6/30/25 | 810 | 812 |  | Sean Buchanan
4819 | 812 | Future Task |  |  | D663 | Manojkumar Gurjar | Accept | DEL D663 - Completion of Interface Testing Segment I - Accept | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 811 |  | 2025-06-01 | Sean Buchanan
5042 | 813 | Future Task |  |  | D666 | Stacey Terry |  | D666 - Support of UAT Segment I | 111 hrs | 119 days | Mon 1/13/25 | Mon 6/30/25
5043 | 814 | Future Task |  |  | D666 | Stacey Terry | Create | DED D666 - Support of UAT Segment I - Create | 16 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 1 | 815 |  | Stacey Terry,Mary Punty
5044 | 815 | Future Task |  |  | D666 | Stacey Terry | Submit | DED D666 - Support of UAT Segment I - Submit | 0 hrs | 0 days | Mon 1/27/25 | Mon 1/27/25 | 814 | 816 |  | Stacey Terry,Joy Schneider
5045 | 816 | Future Task |  |  | D666 | Stacey Terry | Review | DED D666 - Support of UAT Segment I - Collaborative Review | 24 hrs | 10 days | Tue 1/28/25 | Mon 2/10/25 | 815 | 817 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5046 | 817 | Future Task |  |  | D666 | Stacey Terry | Approve | DED D666 - Support of UAT Segment I - Approve | 0 hrs | 0 days | Mon 2/10/25 | Mon 2/10/25 | 816 | 818FS+24 days |  | Jimmy Cox
5056 | 818 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Identify UAT support resources for UAT Segment 1 | 20 hrs | 11 days | Mon 3/17/25 | Mon 3/31/25 | 817FS+24 days | 819 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5057 | 819 | Future Task |  | RW | D666 | Stacey Terry | Create | D666 - Participate in UAT sessions for UAT Segment 1 | 6 hrs | 43 days | Tue 4/1/25 | Fri 5/30/25 | 818 | 820SS,857 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp
5058 | 820 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Support resolution of UAT issues for UAT Segment 1 | 7 hrs | 42 days | Tue 4/1/25 | Thu 5/29/25 | 819SS | 821FS-4 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
5059 | 821 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Confirm requirements traceability for UAT Segment 1 | 3 hrs | 4 days | Fri 5/23/25 | Thu 5/29/25 | 820FS-4 days | 822SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5060 | 822 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Create UAT Segment 1 Summary Document | 3 hrs | 9 days | Fri 5/23/25 | Thu 6/5/25 | 821SS | 823 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5047 | 823 | Future Task |  |  | D666 | Stacey Terry | Submit | DEL D666 - Support of UAT Segment I - Draft Submission | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 822 | 824 |  | Stacey Terry,Joy Schneider
5048 | 824 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Pre-Submission Collaborative Review | 5 hrs | 5 days | Fri 6/6/25 | Thu 6/12/25 | 823 | 825 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5049 | 825 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Style Guide Review | 1 hr | 1 day | Fri 6/13/25 | Fri 6/13/25 | 824 | 826 |  | Dusti Kincl
5050 | 826 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Final Collaborative Review | 10 hrs | 5 days | Mon 6/16/25 | Fri 6/20/25 | 825 | 827 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5051 | 827 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Accenture QC | 4 hrs | 2 days | Mon 6/23/25 | Tue 6/24/25 | 826 | 828 |  | Joy Schneider
5052 | 828 | Future Task |  |  | D666 | Stacey Terry | Submit | DEL D666 - Support of UAT Segment I - Submit | 0 hrs | 0 days | Tue 6/24/25 | Tue 6/24/25 | 827 | 829 |  | Joy Schneider
5053 | 829 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Department QC | 4 hrs | 1 day | Wed 6/25/25 | Wed 6/25/25 | 828 | 830 |  | Tommy Werner,Gabriela Gibson
5054 | 830 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Contract Manager Review | 8 hrs | 3 days | Thu 6/26/25 | Mon 6/30/25 | 829 | 831 |  | Sean Buchanan
5055 | 831 | Future Task |  |  | D666 | Stacey Terry | Accept | DEL D666 - Support of UAT Segment I - Accept | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 830 |  | 2025-06-01 | Sean Buchanan
5520 | 832 | Future Task | Yes |  | D667 | Stacey Terry |  | D667 - Completion of Mock Go-Lives (Dry Run #1) | 285 hrs | 81 days | Mon 4/7/25 | Wed 7/30/25
5521 | 833 | Future Task |  |  | D667 | Stacey Terry | Create | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Create | 6 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 1 | 834 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5522 | 834 | Future Task |  |  | D667 | Stacey Terry | Submit | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Submit | 0 hrs | 0 days | Fri 4/18/25 | Fri 4/18/25 | 833 | 835 |  | Stacey Terry,Joy Schneider
5523 | 835 | Future Task |  |  | D667 | Stacey Terry | Review | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Collaborative Review | 8 hrs | 10 days | Mon 4/21/25 | Fri 5/2/25 | 834 | 836 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5524 | 836 | Future Task |  |  | D667 | Stacey Terry | Approve | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Approve | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 835 | 837 |  | Jimmy Cox
6697 | 837 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Confirm Mock Go-Live Dry Run #1 Execution Readiness | 3 hrs | 5 days | Mon 6/2/25 | Fri 6/6/25 | 836565 | 838 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6698 | 838 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Execute Mock Go-Live Dry Run #1 | 180 hrs | 10 days | Mon 6/9/25 | Fri 6/20/25 | 837 | 839 |  | Kurt Meisner,Glaiza Barnes,Roxanne Camba
6699 | 839 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Document Mock Go-Live Dry Run Results #1 | 6 hrs | 5 days | Mon 6/23/25 | Fri 6/27/25 | 838 | 840 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6700 | 840 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Create Mock Go-Live Dry Run #1 Summary Document | 6 hrs | 5 days | Mon 6/30/25 | Mon 7/7/25 | 839 | 842,841SS+2 days |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
7204 | 841 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Update Deployment & Contingency Plan based on Mock Go-Live Dry Run #1 results | 3 hrs | 2 days | Wed 7/2/25 | Thu 7/3/25 | 840SS+2 days | 842 |  | Stacey Terry,Mary Punty,Manojkumar Gurjar
5525 | 842 | Future Task |  |  | D667 | Stacey Terry | Submit | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Draft Submission | 0 hrs | 0 days | Mon 7/7/25 | Mon 7/7/25 | 840841 | 843 |  | Stacey Terry,Joy Schneider
5526 | 843 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Pre-Submission Collaborative Review | 28 hrs | 5 days | Tue 7/8/25 | Mon 7/14/25 | 842 | 844 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5527 | 844 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Style Guide Review | 1 hr | 1 day | Tue 7/15/25 | Tue 7/15/25 | 843 | 845 |  | Dusti Kincl
5528 | 845 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Final Collaborative Review | 28 hrs | 5 days | Wed 7/16/25 | Tue 7/22/25 | 844 | 846 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5529 | 846 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Accenture QC | 4 hrs | 2 days | Wed 7/23/25 | Thu 7/24/25 | 845 | 847 |  | Joy Schneider
5530 | 847 | Future Task |  |  | D667 | Stacey Terry | Submit | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Submit | 0 hrs | 0 days | Thu 7/24/25 | Thu 7/24/25 | 846 | 848 |  | Joy Schneider
5531 | 848 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Department QC | 4 hrs | 1 day | Fri 7/25/25 | Fri 7/25/25 | 847 | 849 |  | Tommy Werner,Gabriela Gibson
5532 | 849 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Contract Manager Review | 8 hrs | 3 days | Mon 7/28/25 | Wed 7/30/25 | 848 | 850 |  | Sean Buchanan
5533 | 850 | Future Task |  |  | D667 | Stacey Terry | Accept | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Accept | 0 hrs | 0 days | Wed 7/30/25 | Wed 7/30/25 | 849 | 1284 | 2025-07-01 | Sean Buchanan
5061 | 851 | Future Task |  |  | D669 | Stacey Terry |  | D669 - Support of UAT Segment II | 114 hrs | 97 days | Mon 4/14/25 | Thu 8/28/25
5062 | 852 | Future Task |  |  | D669 | Stacey Terry | Create | DED D669 - Support of UAT Segment II - Create | 2 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 1 | 853 |  | Stacey Terry,Mary Punty
5063 | 853 | Future Task |  |  | D669 | Stacey Terry | Submit | DED D669 - Support of UAT Segment II - Submit | 0 hrs | 0 days | Fri 4/25/25 | Fri 4/25/25 | 852 | 854 |  | Stacey Terry,Joy Schneider
5064 | 854 | Future Task |  |  | D669 | Stacey Terry | Review | DED D669 - Support of UAT Segment II - Collaborative Review | 12 hrs | 10 days | Mon 4/28/25 | Fri 5/9/25 | 853 | 855 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5065 | 855 | Future Task |  |  | D669 | Stacey Terry | Approve | DED D669 - Support of UAT Segment II - Approve | 0 hrs | 0 days | Fri 5/9/25 | Fri 5/9/25 | 854 | 856FS+8 days |  | Jimmy Cox
5075 | 856 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Identify UAT support resources for UAT Segment 2 | 6 hrs | 5 days | Thu 5/22/25 | Thu 5/29/25 | 855FS+8 days | 857 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5076 | 857 | Future Task |  | RW | D669 | Stacey Terry | Create | D669 - Participate in UAT sessions for UAT Segment 2 | 6 hrs | 43 days | Mon 6/2/25 | Thu 7/31/25 | 856819 | 858SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp
5077 | 858 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Support resolution of UAT issues for UAT Segment 2 | 7 hrs | 43 days | Mon 6/2/25 | Thu 7/31/25 | 857SS | 859FS-4 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
5078 | 859 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Confirm requirements traceability for UAT Segment 2 | 3 hrs | 4 days | Mon 7/28/25 | Thu 7/31/25 | 858FS-4 days | 860SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5079 | 860 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Create UAT Segment 2 Summary Document | 21 hrs | 7 days | Mon 7/28/25 | Tue 8/5/25 | 859SS | 861 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5066 | 861 | Future Task |  |  | D669 | Stacey Terry | Submit | DEL D669 - Support of UAT Segment II - Draft Submission | 0 hrs | 0 days | Tue 8/5/25 | Tue 8/5/25 | 860 | 862 |  | Stacey Terry,Joy Schneider
5067 | 862 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Wed 8/6/25 | Tue 8/12/25 | 861 | 863 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5068 | 863 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Style Guide Review | 1 hr | 1 day | Wed 8/13/25 | Wed 8/13/25 | 862 | 864 |  | Dusti Kincl
5069 | 864 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Final Collaborative Review | 20 hrs | 5 days | Thu 8/14/25 | Wed 8/20/25 | 863 | 865 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5070 | 865 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Accenture QC | 4 hrs | 2 days | Thu 8/21/25 | Fri 8/22/25 | 864 | 866 |  | Joy Schneider
5071 | 866 | Future Task |  |  | D669 | Stacey Terry | Submit | DEL D669 - Support of UAT Segment II - Submit | 0 hrs | 0 days | Fri 8/22/25 | Fri 8/22/25 | 865 | 867 |  | Joy Schneider
5072 | 867 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Department QC | 4 hrs | 1 day | Mon 8/25/25 | Mon 8/25/25 | 866 | 868 |  | Tommy Werner,Gabriela Gibson
5073 | 868 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Contract Manager Review | 8 hrs | 3 days | Tue 8/26/25 | Thu 8/28/25 | 867 | 869 |  | Sean Buchanan
5074 | 869 | Future Task |  |  | D669 | Stacey Terry | Accept | DEL D669 - Support of UAT Segment II - Accept | 0 hrs | 0 days | Thu 8/28/25 | Thu 8/28/25 | 868 |  | 2025-08-01 | Sean Buchanan
4843 | 870 | Future Task | Yes |  | D670 | Stacey Terry |  | D670 - Completion of Payroll Parallel Testing | 1,689 hrs | 133 days | Mon 2/24/25 | Fri 8/29/25
4844 | 871 | Future Task |  |  | D670 | Stacey Terry | Create | DED D670 - Completion of Payroll Parallel Testing - Create | 16 hrs | 10 days | Mon 2/24/25 | Fri 3/7/25 | 744FS-37 days | 872 |  | Stacey Terry,Mary Punty
4845 | 872 | Future Task |  |  | D670 | Stacey Terry | Submit | DED D670 - Completion of Payroll Parallel Testing - Submit | 0 hrs | 0 days | Fri 3/7/25 | Fri 3/7/25 | 871 | 873 |  | Stacey Terry,Joy Schneider
4846 | 873 | Future Task |  |  | D670 | Stacey Terry | Review | DED D670 - Completion of Payroll Parallel Testing - Collaborative Review | 24 hrs | 10 days | Mon 3/10/25 | Fri 3/21/25 | 872 | 874 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4847 | 874 | Future Task |  |  | D670 | Stacey Terry | Approve | DED D670 - Completion of Payroll Parallel Testing - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 873 | 875 |  | Jimmy Cox
4955 | 875 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Create Work Unit Tracker for Payroll Parallel Test Execution | 40 hrs | 10 days | Mon 3/24/25 | Fri 4/4/25 | 874 | 876 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty
4956 | 876 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Review, Update and confirm Work Unit Tracker for Payroll Parallel Test Execution | 20 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 875 | 877 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Jennifer Peddicord
4957 | 877 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Confirm Payroll Parallel Test Environment Readiness | 20 hrs | 5 days | Mon 4/21/25 | Fri 4/25/25 | 876 | 878 |  | Manojkumar Gurjar,Jarad Hermann
4958 | 878 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Conduct Parallel Payroll Test Kick Off Meeting | 12 hrs | 5 days | Mon 4/28/25 | Fri 5/2/25 | 877 | 879 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Jennifer Peddicord
4959 | 879 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Execute Parallel Payroll Testing | 1,440 hrs | 60 days | Mon 5/5/25 | Tue 7/29/25 | 878 | 880,881FS-4 days |  | Tim Elmer,Deana Metcalf,Jennifer Peddicord,Rochelle Martin
4960 | 880 | Future Task |  |  | D670 | Stacey Terry | Milestone | D670 - Milestone: Payroll Parallel Test Execution Complete | 0 hrs | 0 days | Tue 7/29/25 | Tue 7/29/25 | 879 | 884 |  | Stacey Terry
4961 | 881 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Conduct Payroll Parallel Test Exit Criteria Review Meeting | 10 hrs | 10 days | Thu 7/24/25 | Wed 8/6/25 | 879FS-4 days | 882SS,883SS,884 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
4962 | 882 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Confirm requirements traceability for Payroll Parallel test | 20 hrs | 10 days | Thu 7/24/25 | Wed 8/6/25 | 881SS | 884 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty
4963 | 883 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Create Completion of Payroll Parallel Test Summary Document | 30 hrs | 10 days | Thu 7/24/25 | Wed 8/6/25 | 881SS | 884 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4848 | 884 | Future Task |  |  | D670 | Stacey Terry | Submit | DEL D670 - Completion of Payroll Parallel Testing - Draft Submission | 0 hrs | 0 days | Wed 8/6/25 | Wed 8/6/25 | 880881883882 | 885 |  | Stacey Terry,Joy Schneider
4849 | 885 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Pre-Submission Collaborative Review | 20 hrs | 5 days | Thu 8/7/25 | Wed 8/13/25 | 884 | 886 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4850 | 886 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Style Guide Review | 1 hr | 1 day | Thu 8/14/25 | Thu 8/14/25 | 885 | 887 |  | Dusti Kincl
4851 | 887 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Final Collaborative Review | 20 hrs | 5 days | Fri 8/15/25 | Thu 8/21/25 | 886 | 888 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4852 | 888 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Accenture QC | 4 hrs | 2 days | Fri 8/22/25 | Mon 8/25/25 | 887 | 889 |  | Joy Schneider
4853 | 889 | Future Task |  |  | D670 | Stacey Terry | Submit | DEL D670 - Completion of Payroll Parallel Testing - Submit | 0 hrs | 0 days | Mon 8/25/25 | Mon 8/25/25 | 888 | 890 |  | Joy Schneider
4854 | 890 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Department QC | 4 hrs | 1 day | Tue 8/26/25 | Tue 8/26/25 | 889 | 891 |  | Tommy Werner,Gabriela Gibson
4855 | 891 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Contract Manager Review | 8 hrs | 3 days | Wed 8/27/25 | Fri 8/29/25 | 890 | 892 |  | Sean Buchanan
4856 | 892 | Future Task |  |  | D670 | Stacey Terry | Accept | DEL D670 - Completion of Payroll Parallel Testing - Accept | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 891 |  | 2025-08-01 | Sean Buchanan
4857 | 893 | Future Task | Yes |  | D671 | Manojkumar Gurjar |  | D671 - Completion of Interface Testing Segment II | 1,217 hrs | 180 days | Mon 2/3/25 | Wed 10/15/25
4858 | 894 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | DED D671 - Completion of Interface Testing Segment II - Create | 6 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1 | 895 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4859 | 895 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DED D671 - Completion of Interface Testing Segment II - Submit | 0 hrs | 0 days | Fri 2/14/25 | Fri 2/14/25 | 894 | 896 |  | Manojkumar Gurjar,Joy Schneider
4860 | 896 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DED D671 - Completion of Interface Testing Segment II - Collaborative Review | 8 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 895 | 897 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4861 | 897 | Future Task |  |  | D671 | Manojkumar Gurjar | Approve | DED D671 - Completion of Interface Testing Segment II - Approve | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 896 | 898FS+20 days |  | Jimmy Cox
4964 | 898 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Create Interface Testing Segment 2 Execution Work Unit Tracker | 6 hrs | 4 days | Mon 3/31/25 | Thu 4/3/25 | 897FS+20 days | 899 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4965 | 899 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Review/Confirm Interface Testing Segment 2 Execution Work Unit Tracker | 6 hrs | 4 days | Fri 4/4/25 | Wed 4/9/25 | 898 | 900 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4966 | 900 | Future Task |  | RW | D671 | Manojkumar Gurjar | Create | D671 - Conduct Interface Testing Segment 2 Readiness Review Meeting | 15 hrs | 5 days | Thu 4/10/25 | Wed 4/16/25 | 899 | 901 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4967 | 901 | Future Task |  | RW | D671 | Manojkumar Gurjar | Create | D671 - Conduct Interface Test Kickoff Meeting with Integration Partners | 30 hrs | 5 days | Thu 4/17/25 | Wed 4/23/25 | 900 | 902 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4968 | 902 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Confirm Interface Test Environment Readiness | 15 hrs | 5 days | Thu 4/24/25 | Wed 4/30/25 | 901 | 903 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4969 | 903 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Establish Interface Connectivity Segment 2 | 20 hrs | 7 days | Thu 5/1/25 | Fri 5/9/25 | 902 | 904 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4970 | 904 | Future Task |  | RW | D671 | Manojkumar Gurjar | Create | D671 - Execute Interface Testing Segment 2 | 936 hrs | 78 days | Mon 5/12/25 | Fri 8/29/25 | 903 | 905 |  | Rahul Yadav,Carlos Luis
4971 | 905 | Future Task |  |  | D671 | Manojkumar Gurjar | Milestone | D671 - Milestone: Interface Testing Segment 2 Complete | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 904 | 906 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4972 | 906 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Conduct Test Exit Criteria Review Meeting | 30 hrs | 5 days | Tue 9/2/25 | Mon 9/8/25 | 905 | 907 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4973 | 907 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Confirm requirements traceability for Interface Testing Segment 2 | 40 hrs | 5 days | Tue 9/9/25 | Mon 9/15/25 | 906 | 908 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4974 | 908 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Create Completion of Interface Testing Segment 2 deliverable (D671) | 40 hrs | 5 days | Tue 9/16/25 | Mon 9/22/25 | 907 | 909 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4862 | 909 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DEL D671 - Completion of Interface Testing Segment II - Draft Submission | 0 hrs | 0 days | Mon 9/22/25 | Mon 9/22/25 | 908 | 910 |  | Manojkumar Gurjar,Joy Schneider
4863 | 910 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Pre-Submission Collaborative Review | 24 hrs | 5 days | Tue 9/23/25 | Mon 9/29/25 | 909 | 911 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4864 | 911 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Style Guide Review | 1 hr | 1 day | Tue 9/30/25 | Tue 9/30/25 | 910 | 912 |  | Dusti Kincl
4865 | 912 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Final Collaborative Review | 24 hrs | 5 days | Wed 10/1/25 | Tue 10/7/25 | 911 | 913 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4866 | 913 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Accenture QC | 4 hrs | 2 days | Wed 10/8/25 | Thu 10/9/25 | 912 | 914 |  | Joy Schneider
4867 | 914 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DEL D671 - Completion of Interface Testing Segment II - Submit | 0 hrs | 0 days | Thu 10/9/25 | Thu 10/9/25 | 913 | 915 |  | Joy Schneider
4868 | 915 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Department QC | 4 hrs | 1 day | Fri 10/10/25 | Fri 10/10/25 | 914 | 916 |  | Tommy Werner,Gabriela Gibson
4869 | 916 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Contract Manager Review | 8 hrs | 3 days | Mon 10/13/25 | Wed 10/15/25 | 915 | 917 |  | Sean Buchanan
4870 | 917 | Future Task |  |  | D671 | Manojkumar Gurjar | Accept | DEL D671 - Completion of Interface Testing Segment II - Accept | 0 hrs | 0 days | Wed 10/15/25 | Wed 10/15/25 | 916 |  | 2025-10-01 | Sean Buchanan
4871 | 918 | Future Task |  |  | D672 | Stacey Terry |  | D672 - Support of UAT Segment III | 116 hrs | 123 days | Tue 6/24/25 | Thu 12/18/25
4872 | 919 | Future Task |  |  | D672 | Stacey Terry | Create | DED D672 - Support of UAT Segment III - Create | 16 hrs | 10 days | Tue 6/24/25 | Tue 7/8/25 | 1 | 920 |  | Stacey Terry,Mary Punty
4873 | 920 | Future Task |  |  | D672 | Stacey Terry | Submit | DED D672 - Support of UAT Segment III - Submit | 0 hrs | 0 days | Tue 7/8/25 | Tue 7/8/25 | 919 | 921 |  | Stacey Terry,Joy Schneider
4874 | 921 | Future Task |  |  | D672 | Stacey Terry | Review | DED D672 - Support of UAT Segment III - Collaborative Review | 24 hrs | 10 days | Wed 7/9/25 | Tue 7/22/25 | 920 | 922 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4875 | 922 | Future Task |  |  | D672 | Stacey Terry | Approve | DED D672 - Support of UAT Segment III - Approve | 0 hrs | 0 days | Tue 7/22/25 | Tue 7/22/25 | 921 | 923 |  | Jimmy Cox
4975 | 923 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Identify UAT support resources for UAT Segment 3 | 6 hrs | 7 days | Wed 7/23/25 | Thu 7/31/25 | 922 | 924 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4976 | 924 | Future Task |  | RW | D672 | Stacey Terry | Create | D672 - Participate in UAT sessions for UAT Segment 3 | 6 hrs | 77 days | Fri 8/1/25 | Wed 11/19/25 | 923 | 925SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp
4977 | 925 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Support resolution of UAT issues for UAT Segment 3 | 7 hrs | 77 days | Fri 8/1/25 | Wed 11/19/25 | 924SS | 926FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
4978 | 926 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Confirm requirements traceability for UAT Segment 3 | 3 hrs | 5 days | Thu 11/13/25 | Wed 11/19/25 | 925FS-5 days | 927SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4979 | 927 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Create UAT Segment 3 Summary Document | 3 hrs | 7 days | Thu 11/13/25 | Fri 11/21/25 | 926SS | 928 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4876 | 928 | Future Task |  |  | D672 | Stacey Terry | Submit | DEL D672 - Support of UAT Segment III - Draft Submission | 0 hrs | 0 days | Fri 11/21/25 | Fri 11/21/25 | 927 | 929 |  | Stacey Terry,Joy Schneider
4877 | 929 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 11/24/25 | Tue 12/2/25 | 928 | 930 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4878 | 930 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Style Guide Review | 1 hr | 1 day | Wed 12/3/25 | Wed 12/3/25 | 929 | 931 |  | Dusti Kincl
4879 | 931 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Final Collaborative Review | 20 hrs | 5 days | Thu 12/4/25 | Wed 12/10/25 | 930 | 932 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4880 | 932 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Accenture QC | 4 hrs | 2 days | Thu 12/11/25 | Fri 12/12/25 | 931 | 933 |  | Francisca Li
4881 | 933 | Future Task |  |  | D672 | Stacey Terry | Submit | DEL D672 - Support of UAT Segment III - Submit | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 932 | 934 |  | Joy Schneider
4882 | 934 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Department QC | 4 hrs | 1 day | Mon 12/15/25 | Mon 12/15/25 | 933 | 935 |  | Tommy Werner,Gabriela Gibson
4883 | 935 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Contract Manager Review | 2 hrs | 3 days | Tue 12/16/25 | Thu 12/18/25 | 934 | 936 |  | Sean Buchanan
4884 | 936 | Future Task |  |  | D672 | Stacey Terry | Accept | DEL D672 - Support of UAT Segment III - Accept | 0 hrs | 0 days | Thu 12/18/25 | Thu 12/18/25 | 935 |  | 2025-11-01 | Sean Buchanan
4885 | 937 | Future Task | Yes |  | D673 | Stacey Terry |  | D673 - Completion of Mock Go-Lives (Dry Run #2) | 366 hrs | 86 days | Mon 7/7/25 | Tue 11/4/25
4886 | 938 | Future Task |  |  | D673 | Stacey Terry | Create | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Create | 24 hrs | 10 days | Mon 7/7/25 | Fri 7/18/25 | 1 | 939 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4887 | 939 | Future Task |  |  | D673 | Stacey Terry | Submit | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Submit | 0 hrs | 0 days | Fri 7/18/25 | Fri 7/18/25 | 938 | 940 |  | Stacey Terry,Joy Schneider
4888 | 940 | Future Task |  |  | D673 | Stacey Terry | Review | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Collaborative Review | 32 hrs | 10 days | Mon 7/21/25 | Fri 8/1/25 | 939 | 941 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4889 | 941 | Future Task |  |  | D673 | Stacey Terry | Approve | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Approve | 0 hrs | 0 days | Fri 8/1/25 | Fri 8/1/25 | 940 | 942FS+20 days |  | Jimmy Cox
4980 | 942 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Confirm Mock Go-Live Dry Run #2 Execution Readiness | 24 hrs | 4 days | Tue 9/2/25 | Fri 9/5/25 | 941FS+20 days | 943 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4981 | 943 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Execute Mock Go-Live Dry Run #2 | 160 hrs | 10 days | Mon 9/8/25 | Fri 9/19/25 | 942 | 944 |  | Kurt Meisner,Glaiza Barnes,Roxanne Camba
4982 | 944 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Document Mock Go-Live Dry Run Results #2 | 30 hrs | 5 days | Mon 9/22/25 | Fri 9/26/25 | 943 | 945 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4983 | 945 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Create Mock Go-Live Dry Run #2 Summary Document | 20 hrs | 10 days | Mon 9/29/25 | Fri 10/10/25 | 944 | 947,946SS+2 days |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
7205 | 946 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Update Deployment & Contingency Plan based on Mock Go-Live Dry Run #2 results | 3 hrs | 2 days | Wed 10/1/25 | Thu 10/2/25 | 945SS+2 days | 947 |  | Stacey Terry,Mary Punty,Manojkumar Gurjar
4890 | 947 | Future Task |  |  | D673 | Stacey Terry | Submit | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Draft Submission | 0 hrs | 0 days | Fri 10/10/25 | Fri 10/10/25 | 945946 | 948 |  | Stacey Terry,Joy Schneider
4891 | 948 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Pre-Submission Collaborative Review | 28 hrs | 5 days | Mon 10/13/25 | Fri 10/17/25 | 947 | 949 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4892 | 949 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Style Guide Review | 1 hr | 1 day | Mon 10/20/25 | Mon 10/20/25 | 948 | 950 |  | Dusti Kincl
4893 | 950 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Final Collaborative Review | 28 hrs | 5 days | Tue 10/21/25 | Mon 10/27/25 | 949 | 951 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4894 | 951 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Accenture QC | 4 hrs | 2 days | Tue 10/28/25 | Wed 10/29/25 | 950 | 952 |  | Joy Schneider
4895 | 952 | Future Task |  |  | D673 | Stacey Terry | Submit | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Submit | 0 hrs | 0 days | Wed 10/29/25 | Wed 10/29/25 | 951 | 953 |  | Joy Schneider
4896 | 953 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Department QC | 4 hrs | 1 day | Thu 10/30/25 | Thu 10/30/25 | 952 | 954 |  | Tommy Werner,Gabriela Gibson
4897 | 954 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Contract Manager Review | 8 hrs | 3 days | Fri 10/31/25 | Tue 11/4/25 | 953 | 955 |  | Sean Buchanan
4898 | 955 | Future Task |  |  | D673 | Stacey Terry | Accept | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Accept | 0 hrs | 0 days | Tue 11/4/25 | Tue 11/4/25 | 954 | 1284 | 2025-11-01 | Sean Buchanan
4899 | 956 | Future Task | Yes |  | D674 | Jarad Hermann |  | D674 - Completion of Penetration Testing | 346 hrs | 164 days | Mon 4/7/25 | Wed 11/26/25
4900 | 957 | Future Task |  |  | D674 | Jarad Hermann | Create | DED D674 - Completion of Penetration Testing - Create | 2 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 1212FS+10 days,1247FS+10 days | 958 | Note: should be in version we go live with | Jarad Hermann,Mary Punty
4901 | 958 | Future Task |  |  | D674 | Jarad Hermann | Submit | DED D674 - Completion of Penetration Testing - Submit | 0 hrs | 0 days | Fri 4/18/25 | Fri 4/18/25 | 957 | 959 |  | Jarad Hermann,Joy Schneider
4902 | 959 | Future Task |  |  | D674 | Jarad Hermann | Review | DED D674 - Completion of Penetration Testing - Collaborative Review | 5 hrs | 10 days | Mon 4/21/25 | Fri 5/2/25 | 958 | 960 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4903 | 960 | Future Task |  |  | D674 | Jarad Hermann | Approve | DED D674 - Completion of Penetration Testing - Approve | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 959 | 961FS+19 days |  | Jimmy Cox
4984 | 961 | Future Task |  |  | D674 | Jarad Hermann | Create | D674 - Execute/Complete Penetration Test | 256 hrs | 64 days | Mon 6/2/25 | Fri 8/29/25 | 960FS+19 days | 962 |  | Vivek Sharma,Matthew Warren
4985 | 962 | Future Task |  |  | D674 | Jarad Hermann | Create | D674 - Review Penetration Test Outcome | 10 hrs | 20 days | Tue 9/2/25 | Mon 9/29/25 | 961 | 963SS |  | Jarad Hermann,Bryan Sohayda
4986 | 963 | Future Task |  |  | D674 | Jarad Hermann | Create | D674 - Remediate Penetration Test | 10 hrs | 44 days | Tue 9/2/25 | Fri 10/31/25 | 962SS | 964SS |  | Jarad Hermann,Bryan Sohayda
4987 | 964 | Future Task |  |  | D674 | Jarad Hermann | Create | D674 - Create Final Pen Testing Results/Remediation Summary Report | 20 hrs | 44 days | Tue 9/2/25 | Fri 10/31/25 | 963SS | 965 |  | Jarad Hermann,Bryan Sohayda
4904 | 965 | Future Task |  |  | D674 | Jarad Hermann | Submit | DEL D674 - Completion of Penetration Testing - Draft Submission | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 964 | 966 |  | Jarad Hermann,Joy Schneider
4905 | 966 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 11/3/25 | Fri 11/7/25 | 965 | 967 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4906 | 967 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Style Guide Review | 1 hr | 1 day | Mon 11/10/25 | Mon 11/10/25 | 966 | 968 |  | Dusti Kincl
4907 | 968 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Final Collaborative Review | 16 hrs | 5 days | Wed 11/12/25 | Tue 11/18/25 | 967 | 969 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4908 | 969 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Accenture QC | 4 hrs | 2 days | Wed 11/19/25 | Thu 11/20/25 | 968 | 970 |  | Joy Schneider
4909 | 970 | Future Task |  |  | D674 | Jarad Hermann | Submit | DEL D674 - Completion of Penetration Testing - Submit | 0 hrs | 0 days | Thu 11/20/25 | Thu 11/20/25 | 969 | 971 |  | Joy Schneider
4910 | 971 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Department QC | 4 hrs | 1 day | Fri 11/21/25 | Fri 11/21/25 | 970 | 972 |  | Tommy Werner,Gabriela Gibson
4911 | 972 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Contract Manager Review | 2 hrs | 3 days | Mon 11/24/25 | Wed 11/26/25 | 971 | 973 |  | Sean Buchanan
4912 | 973 | Future Task |  |  | D674 | Jarad Hermann | Accept | DEL D674 - Completion of Penetration Testing - Accept | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 972 | 1284 | 2025-11-01 | Sean Buchanan
4913 | 974 | Future Task | Yes |  | D675 | Jarad Hermann |  | D675 - Completion of Performance Testing | 824 hrs | 159 days | Mon 4/14/25 | Wed 11/26/25
4914 | 975 | Future Task |  |  | D675 | Jarad Hermann | Create | DED D675 - Completion of Performance Testing - Create | 2 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 1200FS-28 days,1236FS-28 days | 976 |  | Jarad Hermann,Mary Punty
4915 | 976 | Future Task |  |  | D675 | Jarad Hermann | Submit | DED D675 - Completion of Performance Testing - Submit | 0 hrs | 0 days | Fri 4/25/25 | Fri 4/25/25 | 975 | 977 |  | Jarad Hermann,Joy Schneider
4916 | 977 | Future Task |  |  | D675 | Jarad Hermann | Review | DED D675 - Completion of Performance Testing - Collaborative Review | 5 hrs | 10 days | Mon 4/28/25 | Fri 5/9/25 | 976 | 978 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4917 | 978 | Future Task |  |  | D675 | Jarad Hermann | Approve | DED D675 - Completion of Performance Testing - Approve | 0 hrs | 0 days | Fri 5/9/25 | Fri 5/9/25 | 977 | 979 |  | Jimmy Cox
4988 | 979 | Future Task |  |  | D675 | Jarad Hermann | Create | D675 - Execute Performance Testing | 648 hrs | 108 days | Mon 6/2/25 | Fri 10/31/25 | 978567 | 980FS-10 days,983 |  | Vivek Sharma,Matthew Warren,Rob Lazar
4989 | 980 | Future Task |  |  | D675 | Jarad Hermann | Create | D675 - Create Completion of Performance Testing Summary Document | 40 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 979FS-10 days | 981SS,982SS,983 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4990 | 981 | Future Task |  |  | D675 | Jarad Hermann | Create | D675 - Conduct Performance Testing Exit Criteria Review Meeting | 40 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 980SS | 983 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4991 | 982 | Future Task |  |  | D675 | Jarad Hermann | Create | D675 - Confirm requirements traceability for Performance Testing | 40 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 980SS | 983 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4918 | 983 | Future Task |  |  | D675 | Jarad Hermann | Submit | DEL D675 - Completion of Performance Testing - Draft Submission | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 982979980981 | 984 |  | Jarad Hermann,Joy Schneider
4919 | 984 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 11/3/25 | Fri 11/7/25 | 983 | 985 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4920 | 985 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Style Guide Review | 1 hr | 1 day | Mon 11/10/25 | Mon 11/10/25 | 984 | 986 |  | Dusti Kincl
4921 | 986 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Final Collaborative Review | 16 hrs | 5 days | Wed 11/12/25 | Tue 11/18/25 | 985 | 987 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4922 | 987 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Accenture QC | 4 hrs | 2 days | Wed 11/19/25 | Thu 11/20/25 | 986 | 988 |  | Joy Schneider
4923 | 988 | Future Task |  |  | D675 | Jarad Hermann | Submit | DEL D675 - Completion of Performance Testing - Submit | 0 hrs | 0 days | Thu 11/20/25 | Thu 11/20/25 | 987 | 989 |  | Joy Schneider
4924 | 989 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Department QC | 4 hrs | 1 day | Fri 11/21/25 | Fri 11/21/25 | 988 | 990 |  | Tommy Werner,Gabriela Gibson
4925 | 990 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Contract Manager Review | 8 hrs | 3 days | Mon 11/24/25 | Wed 11/26/25 | 989 | 991 |  | Sean Buchanan
4926 | 991 | Future Task |  |  | D675 | Jarad Hermann | Accept | DEL D675 - Completion of Performance Testing - Accept | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 990 | 1284 | 2025-11-01 | Sean Buchanan
4927 | 992 | Future Task | Yes |  | D676 | Jarad Hermann |  | D676 - Completion of Disaster Recovery Testing | 411 hrs | 135 days | Mon 2/3/25 | Tue 8/12/25
4928 | 993 | Future Task |  |  | D676 | Jarad Hermann | Create | DED D676 - Completion of Disaster Recovery Testing - Create | 8 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1224FS-35 days,1186FS-35 days,1173 | 994 |  | Jarad Hermann,Mary Punty
4929 | 994 | Future Task |  |  | D676 | Jarad Hermann | Submit | DED D676 - Completion of Disaster Recovery Testing - Submit | 0 hrs | 0 days | Fri 2/14/25 | Fri 2/14/25 | 993 | 995 |  | Jarad Hermann,Joy Schneider
4930 | 995 | Future Task |  |  | D676 | Jarad Hermann | Review | DED D676 - Completion of Disaster Recovery Testing - Collaborative Review | 20 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 994 | 996 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4931 | 996 | Future Task |  |  | D676 | Jarad Hermann | Approve | DED D676 - Completion of Disaster Recovery Testing - Approve | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 995 | 997 |  | Jimmy Cox
4992 | 997 | Future Task |  |  | D676 | Jarad Hermann | Create | D676 - Execute Disaster Recovery Testing | 256 hrs | 64 days | Tue 4/1/25 | Mon 6/30/25 | 996,569FS+1 day | 998 |  | Vivek Sharma,Matthew Warren
4993 | 998 | Future Task |  |  | D676 | Jarad Hermann | Create | D676 - Create Completion of Disaster Recovery Testing Summary Document | 26 hrs | 13 days | Tue 7/1/25 | Fri 7/18/25 | 997 | 999SS,1000SS,1001 |  | Jarad Hermann,Vivek Sharma
4994 | 999 | Future Task |  |  | D676 | Jarad Hermann | Create | D676 - Conduct Disaster Recovery Testing Exit Criteria Review Meeting | 26 hrs | 13 days | Tue 7/1/25 | Fri 7/18/25 | 998SS | 1001 |  | Jarad Hermann,Vivek Sharma
4995 | 1000 | Future Task |  |  | D676 | Jarad Hermann | Create | D676 - Confirm requirements traceability for Disaster Recovery Testing | 26 hrs | 13 days | Tue 7/1/25 | Fri 7/18/25 | 998SS | 1001 |  | Jarad Hermann,Vivek Sharma
4932 | 1001 | Future Task |  |  | D676 | Jarad Hermann | Submit | DEL D676 - Completion of Disaster Recovery Testing - Draft Submission | 0 hrs | 0 days | Fri 7/18/25 | Fri 7/18/25 | 1000998999 | 1002 |  | Jarad Hermann,Joy Schneider
4933 | 1002 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 7/21/25 | Fri 7/25/25 | 1001 | 1003 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4934 | 1003 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Style Guide Review | 1 hr | 1 day | Mon 7/28/25 | Mon 7/28/25 | 1002 | 1004 |  | Dusti Kincl
4935 | 1004 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Final Collaborative Review | 16 hrs | 5 days | Tue 7/29/25 | Mon 8/4/25 | 1003 | 1005 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4936 | 1005 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Accenture QC | 4 hrs | 2 days | Tue 8/5/25 | Wed 8/6/25 | 1004 | 1006 |  | Joy Schneider
4937 | 1006 | Future Task |  |  | D676 | Jarad Hermann | Submit | DEL D676 - Completion of Disaster Recovery Testing - Submit | 0 hrs | 0 days | Wed 8/6/25 | Wed 8/6/25 | 1005 | 1007 |  | Joy Schneider
4938 | 1007 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Department QC | 4 hrs | 1 day | Thu 8/7/25 | Thu 8/7/25 | 1006 | 1008 |  | Tommy Werner,Jenifer Hartsfield
4939 | 1008 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Contract Manager Review | 8 hrs | 3 days | Fri 8/8/25 | Tue 8/12/25 | 1007 | 1009 |  | Sean Buchanan
4940 | 1009 | Future Task |  |  | D676 | Jarad Hermann | Accept | DEL D676 - Completion of Disaster Recovery Testing - Accept | 0 hrs | 0 days | Tue 8/12/25 | Tue 8/12/25 | 1008 | 1284 | 2025-11-01 | Sean Buchanan
4941 | 1010 | Future Task | Yes |  | D677 | Stacey Terry |  | D677 - Completion of Mock Go-Lives (Dry Run #3) | 402 hrs | 76 days | Mon 8/25/25 | Fri 12/12/25
4942 | 1011 | Future Task |  |  | D677 | Stacey Terry | Create | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Create | 24 hrs | 10 days | Mon 8/25/25 | Mon 9/8/25 | 1 | 1012 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4943 | 1012 | Future Task |  |  | D677 | Stacey Terry | Submit | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Submit | 0 hrs | 0 days | Mon 9/8/25 | Mon 9/8/25 | 1011 | 1013 |  | Stacey Terry,Joy Schneider
4944 | 1013 | Future Task |  |  | D677 | Stacey Terry | Review | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Collaborative Review | 32 hrs | 10 days | Tue 9/9/25 | Mon 9/22/25 | 1012 | 1014 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4945 | 1014 | Future Task |  |  | D677 | Stacey Terry | Approve | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Approve | 0 hrs | 0 days | Mon 9/22/25 | Mon 9/22/25 | 1013 | 1015FS+24 days |  | Jimmy Cox
5000 | 1015 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Confirm Mock Go-Live Dry Run #3 Readiness | 40 hrs | 4 days | Mon 10/27/25 | Thu 10/30/25 | 1014FS+24 days | 1016FS+1 day |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5001 | 1016 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Execute Mock Go-Live Dry Run #3 | 180 hrs | 10 days | Mon 11/3/25 | Mon 11/17/25 | 1015FS+1 day | 1017 |  | Kurt Meisner,Glaiza Barnes,Roxanne Camba
5002 | 1017 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Document Mock Go-Live Dry Run Results #3 | 30 hrs | 3 days | Tue 11/18/25 | Thu 11/20/25 | 1016 | 1018 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5003 | 1018 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Create Mock Go-Live Dry Run #3 Summary Document | 20 hrs | 2 days | Fri 11/21/25 | Mon 11/24/25 | 1017 | 1020,1019SS |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
7206 | 1019 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Update Deployment & Contingency Plan based on Mock Go-Live Dry Run #3 results | 3 hrs | 2 days | Fri 11/21/25 | Mon 11/24/25 | 1018SS | 1020 |  | Stacey Terry,Mary Punty,Manojkumar Gurjar
4946 | 1020 | Future Task |  |  | D677 | Stacey Terry | Submit | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Draft Submission | 0 hrs | 0 days | Mon 11/24/25 | Mon 11/24/25 | 10181019 | 1021 |  | Stacey Terry,Joy Schneider
4947 | 1021 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Pre-Submission Collaborative Review | 28 hrs | 3 days | Tue 11/25/25 | Mon 12/1/25 | 1020 | 1022 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4948 | 1022 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Style Guide Review | 1 hr | 1 day | Tue 12/2/25 | Tue 12/2/25 | 1021 | 1023 |  | Dusti Kincl
4949 | 1023 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Final Collaborative Review | 28 hrs | 3 days | Wed 12/3/25 | Fri 12/5/25 | 1022 | 1024 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4950 | 1024 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Accenture QC | 4 hrs | 1 day | Mon 12/8/25 | Mon 12/8/25 | 1023 | 1025 |  | Joy Schneider
4951 | 1025 | Future Task |  |  | D677 | Stacey Terry | Submit | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Submit | 0 hrs | 0 days | Mon 12/8/25 | Mon 12/8/25 | 1024 | 1026 |  | Joy Schneider
4952 | 1026 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Department QC | 4 hrs | 1 day | Tue 12/9/25 | Tue 12/9/25 | 1025 | 1027 |  | Tommy Werner,Gabriela Gibson
4953 | 1027 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Contract Manager Review | 8 hrs | 3 days | Wed 12/10/25 | Fri 12/12/25 | 1026 | 1028 |  | Sean Buchanan
4954 | 1028 | Future Task |  |  | D677 | Stacey Terry | Accept | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Accept | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 1027 | 1284 | 2025-12-01 | Sean Buchanan
5080 | 1029 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | WP406 - Mock Conversion Testing Plan | 180 hrs | 114 days | Mon 2/12/24 | Mon 7/22/24
5081 | 1030 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WPED WP406 - Mock Conversion Testing Plan - Create | 24 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 1 | 1031 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5082 | 1031 | Future Task |  |  | WP406 | Manojkumar Gurjar | Submit | WPED WP406 - Mock Conversion Testing Plan - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 1030 | 1032 |  | Joy Schneider,Manojkumar Gurjar
5083 | 1032 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WPED WP406 - Mock Conversion Testing Plan - Review | 28 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 1031 | 1033 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5084 | 1033 | Future Task |  |  | WP406 | Manojkumar Gurjar | Approve | WPED WP406 - Mock Conversion Testing Plan - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 1032 | 1034FS+20 days |  | Jimmy Cox
5116 | 1034 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WP406 - Define Mock Conversion Testing Approach | 20 hrs | 10 days | Mon 4/8/24 | Fri 4/19/24 | 1033FS+20 days | 1035 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5117 | 1035 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WP406 - Identify Resources for Mock Conversion Testing | 20 hrs | 10 days | Mon 4/22/24 | Fri 5/3/24 | 1034 | 1036 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5118 | 1036 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WP406 - Define Test Cycles and Scenarios | 20 hrs | 24 days | Mon 5/6/24 | Fri 6/7/24 | 1035 | 1037 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5119 | 1037 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WP406 - Define and review Entry/Exit Criteria for Mock Conversion Testing | 20 hrs | 15 days | Mon 6/10/24 | Fri 6/28/24 | 1036 | 1038 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5085 | 1038 | Future Task |  |  | WP406 | Manojkumar Gurjar | Submit | WP WP406 - Mock Conversion Testing Plan - Submit | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 1037 | 1039 |  | Joy Schneider,Manojkumar Gurjar
5086 | 1039 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WP WP406 - Mock Conversion Testing Plan - Collaborative Review & Update | 24 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 1038 | 1040 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5087 | 1040 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WP WP406 - Mock Conversion Testing Plan - Final Review & Edits | 24 hrs | 5 days | Tue 7/16/24 | Mon 7/22/24 | 1039 | 1041 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5088 | 1041 | Future Task |  | RW-Communication | WP406 | Manojkumar Gurjar | Approve | WP WP406 - Mock Conversion Testing Plan - Approve | 0 hrs | 0 days | Mon 7/22/24 | Mon 7/22/24 | 1040 | 1043FS-45 days,557 | 2024-05-01 | Jimmy Cox
5089 | 1042 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | WP407 - Mock Conversion Scripts | 160 hrs | 67 days | Fri 5/17/24 | Wed 8/21/24
5090 | 1043 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WPED WP407 - Mock Conversion Scripts - Create | 24 hrs | 10 days | Fri 5/17/24 | Fri 5/31/24 | 1041FS-45 days | 1044 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5091 | 1044 | Future Task |  |  | WP407 | Manojkumar Gurjar | Submit | WPED WP407 - Mock Conversion Scripts - Submit | 0 hrs | 0 days | Fri 5/31/24 | Fri 5/31/24 | 1043 | 1045 |  | Joy Schneider,Manojkumar Gurjar
5092 | 1045 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WPED WP407 - Mock Conversion Scripts - Review | 28 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 1044 | 1046 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5093 | 1046 | Future Task |  |  | WP407 | Manojkumar Gurjar | Approve | WPED WP407 - Mock Conversion Scripts - Approve | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 1045 | 1047 |  | Jimmy Cox
5120 | 1047 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WP407 - Create Test Scripts | 20 hrs | 19 days | Mon 6/17/24 | Fri 7/12/24 | 1046 | 1048 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5121 | 1048 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WP407 - Identify System Test Scripts for Mock Conversion Testing | 20 hrs | 8 days | Mon 7/15/24 | Wed 7/24/24 | 1047 | 1049 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5122 | 1049 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WP407 - Review System Test Scripts for Mock Conversion Testing | 20 hrs | 5 days | Thu 7/25/24 | Wed 7/31/24 | 1048 | 1050 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5094 | 1050 | Future Task |  |  | WP407 | Manojkumar Gurjar | Submit | WP WP407 - Mock Conversion Scripts - Submit | 0 hrs | 0 days | Wed 7/31/24 | Wed 7/31/24 | 1049 | 1051 |  | Joy Schneider,Manojkumar Gurjar
5095 | 1051 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WP WP407 - Mock Conversion Scripts - Collaborative Review & Update | 24 hrs | 10 days | Thu 8/1/24 | Wed 8/14/24 | 1050 | 1052 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5096 | 1052 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WP WP407 - Mock Conversion Scripts - Final Review & Edits | 24 hrs | 5 days | Thu 8/15/24 | Wed 8/21/24 | 1051 | 1053 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5097 | 1053 | Future Task |  |  | WP407 | Manojkumar Gurjar | Approve | WP WP407 - Mock Conversion Scripts - Approve | 0 hrs | 0 days | Wed 8/21/24 | Wed 8/21/24 | 1052 | 622FS-47 days | 2024-07-01 | Jimmy Cox
5098 | 1054 | Future Task |  |  | WP408 | Stacey Terry |  | WP408 - System Test Scripts | 188 hrs | 153 days | Mon 2/12/24 | Mon 9/16/24
5099 | 1055 | Future Task |  |  | WP408 | Stacey Terry | Create | WPED WP408 - System Test Scripts - Create | 16 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 1 | 1056 |  | Stacey Terry,Mary Punty
5100 | 1056 | Future Task |  |  | WP408 | Stacey Terry | Submit | WPED WP408 - System Test Scripts - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 1055 | 1057 |  | Joy Schneider,Stacey Terry
5101 | 1057 | Future Task |  |  | WP408 | Stacey Terry | Review | WPED WP408 - System Test Scripts - Review | 12 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 1056 | 1058 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5102 | 1058 | Future Task |  |  | WP408 | Stacey Terry | Approve | WPED WP408 - System Test Scripts - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 1057 | 1059 |  | Jimmy Cox
5123 | 1059 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Create Work Unit Tracker for System Test Preparation | 20 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 1058 | 1060 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5124 | 1060 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Review, update, & confirm Work Unit Tracker for System Test Preparation | 20 hrs | 10 days | Mon 3/25/24 | Fri 4/5/24 | 1059 | 1061FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter
5125 | 1061 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Create System Test Script Template | 30 hrs | 5 days | Mon 4/1/24 | Fri 4/5/24 | 1060FS-5 days | 1062 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5126 | 1062 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Create, Review and Confirm System Test Scripts and Data | 20 hrs | 93 days | Mon 4/8/24 | Fri 8/16/24 | 1061 | 1063 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
5127 | 1063 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Create System Test Script Summary Document | 30 hrs | 5 days | Mon 8/19/24 | Fri 8/23/24 | 1062 | 1064 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5103 | 1064 | Future Task |  |  | WP408 | Stacey Terry | Submit | WP WP408 - System Test Scripts - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 1063 | 1065 |  | Joy Schneider,Stacey Terry
5104 | 1065 | Future Task |  |  | WP408 | Stacey Terry | Review | WP WP408 - System Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1064 | 1066 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5105 | 1066 | Future Task |  |  | WP408 | Stacey Terry | Review | WP WP408 - System Test Scripts - Final Review & Edits | 20 hrs | 5 days | Tue 9/10/24 | Mon 9/16/24 | 1065 | 1067 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5106 | 1067 | Future Task |  |  | WP408 | Stacey Terry | Approve | WP WP408 - System Test Scripts - Approve | 0 hrs | 0 days | Mon 9/16/24 | Mon 9/16/24 | 1066 | 651 | 2024-09-01 | Jimmy Cox
5107 | 1068 | Future Task |  |  | WP409 | Stacey Terry |  | WP409 - Regression Testing Plan | 116 hrs | 78 days | Mon 8/5/24 | Fri 11/22/24
5108 | 1069 | Future Task |  |  | WP409 | Stacey Terry | Create | WPED WP409 - Regression Testing Plan - Create | 2 hrs | 9 days | Mon 8/5/24 | Thu 8/15/24 | 1 | 1070 |  | Stacey Terry,Mary Punty
5109 | 1070 | Future Task |  |  | WP409 | Stacey Terry | Submit | WPED WP409 - Regression Testing Plan - Submit | 0 hrs | 0 days | Thu 8/15/24 | Thu 8/15/24 | 1069 | 1071 |  | Joy Schneider,Stacey Terry
5110 | 1071 | Future Task |  |  | WP409 | Stacey Terry | Review | WPED WP409 - Regression Testing Plan - Review | 24 hrs | 10 days | Fri 8/16/24 | Thu 8/29/24 | 1070 | 1072 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5111 | 1072 | Future Task |  |  | WP409 | Stacey Terry | Approve | WPED WP409 - Regression Testing Plan - Approve | 0 hrs | 0 days | Thu 8/29/24 | Thu 8/29/24 | 1071 | 1073FS+20 days |  | Jimmy Cox
5128 | 1073 | Future Task |  |  | WP409 | Stacey Terry | Create | WP409 - Create Regression Testing Approach/Plan | 20 hrs | 24 days | Mon 9/30/24 | Thu 10/31/24 | 1072FS+20 days | 1074SS+10 days,1076 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5129 | 1074 | Future Task |  |  | WP409 | Stacey Terry | Create | WP409 - Define the scope of the Regression Test suite | 20 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 1073SS+10 days | 1075SS+5 days,1076 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5130 | 1075 | Future Task |  |  | WP409 | Stacey Terry | Create | WP409 - Identify testing resources for Regression Testing | 20 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 1074SS+5 days | 1076 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5112 | 1076 | Future Task |  |  | WP409 | Stacey Terry | Submit | WP WP409 - Regression Testing Plan - Submit | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 107310741075 | 1077 |  | Joy Schneider,Stacey Terry
5113 | 1077 | Future Task |  |  | WP409 | Stacey Terry | Review | WP WP409 - Regression Testing Plan - Collaborative Review & Update | 10 hrs | 10 days | Fri 11/1/24 | Fri 11/15/24 | 1076 | 1078 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5114 | 1078 | Future Task |  |  | WP409 | Stacey Terry | Review | WP WP409 - Regression Testing Plan - Final Review & Edits | 20 hrs | 5 days | Mon 11/18/24 | Fri 11/22/24 | 1077 | 1079 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5115 | 1079 | Future Task |  |  | WP409 | Stacey Terry | Approve | WP WP409 - Regression Testing Plan - Approve | 0 hrs | 0 days | Fri 11/22/24 | Fri 11/22/24 | 1078 | 1123FS-17 days,1135FS+5 days | 2024-12-01 | Jimmy Cox
5257 | 1080 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | WP412 - Interface Testing Plan | 220 hrs | 118 days | Mon 4/1/24 | Mon 9/16/24
5258 | 1081 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WPED WP412 - Interface Testing Plan - Create | 24 hrs | 10 days | Mon 4/1/24 | Fri 4/12/24 | 537FS+68 days | 1082,1096SS+29 days |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5259 | 1082 | Future Task |  |  | WP412 | Manojkumar Gurjar | Submit | WPED WP412 - Interface Testing Plan - Submit | 0 hrs | 0 days | Fri 4/12/24 | Fri 4/12/24 | 1081 | 1083 |  | Joy Schneider,Manojkumar Gurjar
5260 | 1083 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WPED WP412 - Interface Testing Plan - Review | 28 hrs | 10 days | Mon 4/15/24 | Fri 4/26/24 | 1082 | 1084 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5261 | 1084 | Future Task |  |  | WP412 | Manojkumar Gurjar | Approve | WPED WP412 - Interface Testing Plan - Approve | 0 hrs | 0 days | Fri 4/26/24 | Fri 4/26/24 | 1083 | 1085FS+24 days |  | Jimmy Cox
5284 | 1085 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Define Interface Test approach | 20 hrs | 15 days | Mon 6/3/24 | Fri 6/21/24 | 1084FS+24 days | 1086 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5285 | 1086 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Define Interface Test Cycles | 20 hrs | 14 days | Mon 6/24/24 | Fri 7/12/24 | 1085 | 1087 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5286 | 1087 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Identify Test Resources for Interface Testing | 20 hrs | 5 days | Mon 7/15/24 | Fri 7/19/24 | 1086 | 1088 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5287 | 1088 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Define Test Tools and Test Management processes for Interface Testing | 20 hrs | 5 days | Mon 7/22/24 | Fri 7/26/24 | 1087 | 1089 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5288 | 1089 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Create Initial List of Interface Test Scenarios | 20 hrs | 10 days | Mon 7/29/24 | Fri 8/9/24 | 1088 | 1090 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5289 | 1090 | Future Task |  | RW | WP412 | Manojkumar Gurjar | Create | WP412 - Prepare High-level Interface Test Approach for Integration Partners | 20 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 1089 | 1091 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5262 | 1091 | Future Task |  |  | WP412 | Manojkumar Gurjar | Submit | WP WP412 - Interface Testing Plan - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 1090 | 1092 |  | Joy Schneider,Manojkumar Gurjar
5263 | 1092 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WP WP412 - Interface Testing Plan - Collaborative Review & Update | 24 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1091 | 1093 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5264 | 1093 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WP WP412 - Interface Testing Plan - Final Review & Edits | 24 hrs | 5 days | Tue 9/10/24 | Mon 9/16/24 | 1092 | 1094 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5265 | 1094 | Future Task |  |  | WP412 | Manojkumar Gurjar | Approve | WP WP412 - Interface Testing Plan - Approve | 0 hrs | 0 days | Mon 9/16/24 | Mon 9/16/24 | 1093 | 555FS-10 days | 2024-08-01 | Jimmy Cox
5266 | 1095 | Future Task |  |  | WP413 | Stacey Terry |  | WP413 - Interface Test Scripts | 180 hrs | 89 days | Fri 5/10/24 | Mon 9/16/24
5267 | 1096 | Future Task |  |  | WP413 | Stacey Terry | Create | WPED WP413 - Interface Test Scripts - Create | 16 hrs | 10 days | Fri 5/10/24 | Thu 5/23/24 | 1081SS+29 days | 1097 |  | Stacey Terry,Mary Punty
5268 | 1097 | Future Task |  |  | WP413 | Stacey Terry | Submit | WPED WP413 - Interface Test Scripts - Submit | 0 hrs | 0 days | Thu 5/23/24 | Thu 5/23/24 | 1096 | 1098 |  | Joy Schneider,Stacey Terry
5269 | 1098 | Future Task |  |  | WP413 | Stacey Terry | Review | WPED WP413 - Interface Test Scripts - Review | 24 hrs | 10 days | Fri 5/24/24 | Fri 6/7/24 | 1097 | 1099 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5270 | 1099 | Future Task |  |  | WP413 | Stacey Terry | Approve | WPED WP413 - Interface Test Scripts - Approve | 0 hrs | 0 days | Fri 6/7/24 | Fri 6/7/24 | 1098 | 1100 |  | Jimmy Cox
5290 | 1100 | Future Task |  |  | WP413 | Stacey Terry | Create | WP413 - Create Work Unit Tracker for Interface Test Preparation | 20 hrs | 10 days | Mon 6/10/24 | Fri 6/21/24 | 1099 | 1101 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5291 | 1101 | Future Task |  |  | WP413 | Stacey Terry | Create | WP413 - Review, update, & confirm Work Unit Tracker for Interface Test Preparation | 20 hrs | 5 days | Mon 6/24/24 | Fri 6/28/24 | 1100 | 1102 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5292 | 1102 | Future Task |  |  | WP413 | Stacey Terry | Create | WP413 - Create, Review and Confirm Interface Test Scenarios/Scripts and Data | 20 hrs | 24 days | Mon 7/1/24 | Fri 8/2/24 | 1101 | 1103 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5293 | 1103 | Future Task |  |  | WP413 | Stacey Terry | Create | WP413 - Create Interface Test Scripts Summary Document | 20 hrs | 5 days | Mon 8/5/24 | Fri 8/9/24 | 1102 | 1104 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5271 | 1104 | Future Task |  |  | WP413 | Stacey Terry | Submit | WP WP413 - Interface Test Scripts - Submit | 0 hrs | 0 days | Fri 8/9/24 | Fri 8/9/24 | 1103 | 1105 |  | Joy Schneider,Stacey Terry
5272 | 1105 | Future Task |  |  | WP413 | Stacey Terry | Review | WP WP413 - Interface Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 1104 | 1106 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5273 | 1106 | Future Task |  |  | WP413 | Stacey Terry | Review | WP WP413 - Interface Test Scripts - Final Review & Edits | 20 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 1105 | 1107 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5274 | 1107 | Future Task |  |  | WP413 | Stacey Terry | Approve | WP WP413 - Interface Test Scripts - Approve | 0 hrs | 0 days | Fri 8/30/24 | Fri 8/30/24 | 1106 | 1108 | 2024-08-01 | Jimmy Cox
7149 | 1108 | Future Task |  | RW | WP413 | Stacey Terry | Create | Prepare and share Test Scenarios and Scripts with Integration partners | 20 hrs | 10 days | Tue 9/3/24 | Mon 9/16/24 | 1107 |  |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5275 | 1109 | Future Task |  |  | WP414 | Stacey Terry |  | WP414 - Payroll Parallel Test Scripts | 160 hrs | 80 days | Tue 12/10/24 | Thu 4/3/25
5276 | 1110 | Future Task |  |  | WP414 | Stacey Terry | Create | WPED WP414 - Payroll Parallel Test Scripts - Create | 16 hrs | 10 days | Tue 12/10/24 | Mon 12/23/24 | 728SS-4 days | 1111 |  | Stacey Terry,Mary Punty
5277 | 1111 | Future Task |  |  | WP414 | Stacey Terry | Submit | WPED WP414 - Payroll Parallel Test Scripts - Submit | 0 hrs | 0 days | Mon 12/23/24 | Mon 12/23/24 | 1110 | 1112 |  | Joy Schneider,Stacey Terry
5278 | 1112 | Future Task |  |  | WP414 | Stacey Terry | Review | WPED WP414 - Payroll Parallel Test Scripts - Review | 24 hrs | 10 days | Tue 12/24/24 | Wed 1/8/25 | 1111 | 1113 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5279 | 1113 | Future Task |  |  | WP414 | Stacey Terry | Approve | WPED WP414 - Payroll Parallel Test Scripts - Approve | 0 hrs | 0 days | Wed 1/8/25 | Wed 1/8/25 | 1112 | 1114 |  | Jimmy Cox
5295 | 1114 | Future Task |  |  | WP414 | Stacey Terry | Create | WP414 - Create Work Unit Tracker for Payroll Parallel Test Preparation | 20 hrs | 5 days | Thu 1/9/25 | Wed 1/15/25 | 1113 | 1115 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh
5296 | 1115 | Future Task |  |  | WP414 | Stacey Terry | Create | WP414 - Review, update, & confirm Work Unit Tracker for Payroll Parallel Test Preparation | 20 hrs | 10 days | Thu 1/16/25 | Thu 1/30/25 | 1114 | 1116FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
5297 | 1116 | Future Task |  |  | WP414 | Stacey Terry | Create | WP414 - Create, Review and Confirm Payroll Parallel Test Scenarios/Scripts and Data | 20 hrs | 30 days | Fri 1/24/25 | Thu 3/6/25 | 1115FS-5 days | 1117FS-5 days |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Jennifer Peddicord
5298 | 1117 | Future Task |  |  | WP414 | Stacey Terry | Create | WP414 - Create Payroll Parallel Test Script Summary Document | 20 hrs | 10 days | Fri 2/28/25 | Thu 3/13/25 | 1116FS-5 days | 1118 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5280 | 1118 | Future Task |  |  | WP414 | Stacey Terry | Submit | WP WP414 - Payroll Parallel Test Scripts - Submit | 0 hrs | 0 days | Thu 3/13/25 | Thu 3/13/25 | 1117 | 1119 |  | Joy Schneider,Stacey Terry
5281 | 1119 | Future Task |  |  | WP414 | Stacey Terry | Review | WP WP414 - Payroll Parallel Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Fri 3/14/25 | Thu 3/27/25 | 1118 | 1120 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5282 | 1120 | Future Task |  |  | WP414 | Stacey Terry | Review | WP WP414 - Payroll Parallel Test Scripts - Final Review & Edits | 20 hrs | 5 days | Fri 3/28/25 | Thu 4/3/25 | 1119 | 1121 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5283 | 1121 | Future Task |  |  | WP414 | Stacey Terry | Approve | WP WP414 - Payroll Parallel Test Scripts - Approve | 0 hrs | 0 days | Thu 4/3/25 | Thu 4/3/25 | 1120 |  | 2025-03-01 | Jimmy Cox
5131 | 1122 | Future Task |  |  | WP415 | Stacey Terry |  | WP415 - Regression Test Scripts | 140 hrs | 63 days | Wed 10/30/24 | Mon 2/3/25
5132 | 1123 | Future Task |  |  | WP415 | Stacey Terry | Create | WPED WP415 - Regression Test Scripts - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1079FS-17 days | 1124 |  | Stacey Terry,Mary Punty
5133 | 1124 | Future Task |  |  | WP415 | Stacey Terry | Submit | WPED WP415 - Regression Test Scripts - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 1123 | 1125 |  | Joy Schneider,Stacey Terry
5134 | 1125 | Future Task |  |  | WP415 | Stacey Terry | Review | WPED WP415 - Regression Test Scripts - Review | 24 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 1124 | 1126 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5135 | 1126 | Future Task |  |  | WP415 | Stacey Terry | Approve | WPED WP415 - Regression Test Scripts - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1125 | 1127 |  | Jimmy Cox
5221 | 1127 | Future Task |  |  | WP415 | Stacey Terry | Create | WP415 - Create Regression Test Suite | 20 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 1126 | 1128 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5222 | 1128 | Future Task |  |  | WP415 | Stacey Terry | Create | WP415 - Review, update & confirm Regression Test Suite | 20 hrs | 9 days | Mon 12/16/24 | Fri 12/27/24 | 1127 | 1129 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter
5223 | 1129 | Future Task |  |  | WP415 | Stacey Terry | Create | WP415 - Create Regression Test Scripts Summary Document | 20 hrs | 9 days | Mon 12/30/24 | Fri 1/10/25 | 1128 | 1130 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5136 | 1130 | Future Task |  |  | WP415 | Stacey Terry | Submit | WP WP415 - Regression Test Scripts - Submit | 0 hrs | 0 days | Fri 1/10/25 | Fri 1/10/25 | 1129 | 1131 |  | Joy Schneider,Stacey Terry
5137 | 1131 | Future Task |  |  | WP415 | Stacey Terry | Review | WP WP415 - Regression Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 1130 | 1132 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5138 | 1132 | Future Task |  |  | WP415 | Stacey Terry | Review | WP WP415 - Regression Test Scripts - Final Review & Edits | 20 hrs | 5 days | Tue 1/28/25 | Mon 2/3/25 | 1131 | 1133 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5139 | 1133 | Future Task |  |  | WP415 | Stacey Terry | Approve | WP WP415 - Regression Test Scripts - Approve | 0 hrs | 0 days | Mon 2/3/25 | Mon 2/3/25 | 1132 |  | 2024-12-01 | Jimmy Cox
5140 | 1134 | Future Task | Yes |  | WP416 | Stacey Terry |  | WP416 - Completion of Regression Testing | 1,733 hrs | 160 days | Wed 12/4/24 | Tue 7/22/25
5141 | 1135 | Future Task |  |  | WP416 | Stacey Terry | Create | WPED WP416 - Completion of Regression Testing - Create | 16 hrs | 10 days | Wed 12/4/24 | Tue 12/17/24 | 1079FS+5 days | 1136 |  | Stacey Terry,Mary Punty
5142 | 1136 | Future Task |  |  | WP416 | Stacey Terry | Submit | WPED WP416 - Completion of Regression Testing - Submit | 0 hrs | 0 days | Tue 12/17/24 | Tue 12/17/24 | 1135 | 1137 |  | Joy Schneider,Stacey Terry
5143 | 1137 | Future Task |  |  | WP416 | Stacey Terry | Review | WPED WP416 - Completion of Regression Testing - Review | 24 hrs | 10 days | Wed 12/18/24 | Thu 1/2/25 | 1136 | 1138 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5144 | 1138 | Future Task |  |  | WP416 | Stacey Terry | Approve | WPED WP416 - Completion of Regression Testing - Approve | 0 hrs | 0 days | Thu 1/2/25 | Thu 1/2/25 | 1137 | 1139 |  | Jimmy Cox
5224 | 1139 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Create Work Unit Tracker for Regression Test Execution | 20 hrs | 10 days | Fri 1/3/25 | Thu 1/16/25 | 1138 | 1140 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5225 | 1140 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Review, update, and confirm Work Unit Tracker for Regression Test Execution | 20 hrs | 10 days | Fri 1/17/25 | Fri 1/31/25 | 1139 | 1141 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5226 | 1141 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Conduct Regression Test Execution Kickoff Meeting | 20 hrs | 5 days | Mon 2/3/25 | Fri 2/7/25 | 1140 | 1142 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5227 | 1142 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Execute Regression Test | 1,620 hrs | 90 days | Mon 2/10/25 | Mon 6/16/25 | 1141 | 1143 |  | Matthew Culp,Abdel El Bacha,Donnie Doctor
5228 | 1143 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Create Completion of Regression Test Execution Summary Document | 3 hrs | 10 days | Tue 6/17/25 | Mon 6/30/25 | 1142 | 1144 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5145 | 1144 | Future Task |  |  | WP416 | Stacey Terry | Submit | WP WP416 - Completion of Regression Testing - Submit | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 1143 | 1145 |  | Joy Schneider,Stacey Terry
5146 | 1145 | Future Task |  |  | WP416 | Stacey Terry | Review | WP WP416 - Completion of Regression Testing - Collaborative Review & Update | 5 hrs | 10 days | Tue 7/1/25 | Tue 7/15/25 | 1144 | 1146 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5147 | 1146 | Future Task |  |  | WP416 | Stacey Terry | Review | WP WP416 - Completion of Regression Testing - Final Review & Edits | 5 hrs | 5 days | Wed 7/16/25 | Tue 7/22/25 | 1145 | 1147 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5148 | 1147 | Future Task |  |  | WP416 | Stacey Terry | Approve | WP WP416 - Completion of Regression Testing - Approve | 0 hrs | 0 days | Tue 7/22/25 | Tue 7/22/25 | 1146 |  | 2025-06-01 | Jimmy Cox
5149 | 1148 | Future Task |  |  | WP417 | Stacey Terry |  | WP417 - Data Dictionary | 192 hrs | 139 days | Mon 9/23/24 | Fri 4/11/25
5150 | 1149 | Future Task |  |  | WP417 | Stacey Terry | Create | WPED WP417 - Data Dictionary - Create | 16 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 1 | 1150 |  | Stacey Terry,Manojkumar Gurjar
5151 | 1150 | Future Task |  |  | WP417 | Stacey Terry | Submit | WPED WP417 - Data Dictionary - Submit | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 1149 | 1151 |  | Joy Schneider,Stacey Terry
5152 | 1151 | Future Task |  |  | WP417 | Stacey Terry | Review | WPED WP417 - Data Dictionary - Review | 28 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1150 | 1152 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5153 | 1152 | Future Task |  |  | WP417 | Stacey Terry | Approve | WPED WP417 - Data Dictionary - Approve | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 1151 | 1153FS+27 days |  | Jimmy Cox
5229 | 1153 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Update data dictionary with latest tables and data elements as needed - Financials | 20 hrs | 21 days | Mon 12/2/24 | Tue 12/31/24 | 1152FS+27 days | 1154 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5230 | 1154 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Update data dictionary with latest tables and data elements as needed - Payroll | 20 hrs | 21 days | Thu 1/2/25 | Fri 1/31/25 | 1153 | 1155 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5231 | 1155 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Update data dictionary with latest tables and data elements as needed - DW Related | 20 hrs | 20 days | Mon 2/3/25 | Fri 2/28/25 | 1154 | 1156 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5232 | 1156 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Review and confirm data dictionary | 20 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1155 | 1157 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5233 | 1157 | Future Task |  | RW-Communication | WP417 | Stacey Terry | Create | WP417 - Share Data Dictionary | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1156 | 1158 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5154 | 1158 | Future Task |  |  | WP417 | Stacey Terry | Submit | WP WP417 - Data Dictionary - Submit | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1157 | 1159 |  | Joy Schneider,Stacey Terry
5155 | 1159 | Future Task |  |  | WP417 | Stacey Terry | Review | WP WP417 - Data Dictionary - Collaborative Review & Update | 24 hrs | 10 days | Mon 3/24/25 | Fri 4/4/25 | 1158 | 1160 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5156 | 1160 | Future Task |  |  | WP417 | Stacey Terry | Review | WP WP417 - Data Dictionary - Final Review & Edits | 24 hrs | 5 days | Mon 4/7/25 | Fri 4/11/25 | 1159 | 1161 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5157 | 1161 | Future Task |  |  | WP417 | Stacey Terry | Approve | WP WP417 - Data Dictionary - Approve | 0 hrs | 0 days | Fri 4/11/25 | Fri 4/11/25 | 1160 |  | 2025-02-01 | Jimmy Cox
5158 | 1162 | Future Task |  |  | WP418 | Jarad Hermann |  | WP418 - Disaster Recovery Plan | 102 hrs | 106 days | Mon 7/22/24 | Fri 12/20/24
5159 | 1163 | Future Task |  |  | WP418 | Jarad Hermann | Create | WPED WP418 - Disaster Recovery Plan - Create | 2 hrs | 10 days | Mon 7/22/24 | Fri 8/2/24 | 1 | 1164,1175SS+10 days |  | Jarad Hermann
5160 | 1164 | Future Task |  |  | WP418 | Jarad Hermann | Submit | WPED WP418 - Disaster Recovery Plan - Submit | 0 hrs | 0 days | Fri 8/2/24 | Fri 8/2/24 | 1163 | 1165 |  | Joy Schneider,Jarad Hermann
5161 | 1165 | Future Task |  |  | WP418 | Jarad Hermann | Review | WPED WP418 - Disaster Recovery Plan - Review | 16 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 1164 | 1166 |  | Jarad Hermann,Jimmy Cox,Angie Robertson,Sean Buchanan
5162 | 1166 | Future Task |  |  | WP418 | Jarad Hermann | Approve | WPED WP418 - Disaster Recovery Plan - Approve | 0 hrs | 0 days | Fri 8/16/24 | Fri 8/16/24 | 1165 | 1167FS+29 days |  | Jimmy Cox
5234 | 1167 | Future Task |  |  | WP418 | Jarad Hermann | Create | WP418 - Design/Update Disaster Recovery (DR) Plan | 20 hrs | 15 days | Mon 9/30/24 | Fri 10/18/24 | 1166FS+29 days | 1168 |  | Jarad Hermann,Vivek Sharma
5235 | 1168 | Future Task |  |  | WP418 | Jarad Hermann | Create | WP418 - Review Financials Disaster Recovery Plan | 20 hrs | 15 days | Mon 10/21/24 | Fri 11/8/24 | 1167 | 1169 |  | Jarad Hermann,Vivek Sharma
5236 | 1169 | Future Task |  |  | WP418 | Jarad Hermann | Create | WP418 - Create Payroll Disaster Recovery Plan | 20 hrs | 12 days | Tue 11/12/24 | Wed 11/27/24 | 1168 | 1170 |  | Jarad Hermann,Vivek Sharma
5163 | 1170 | Future Task |  |  | WP418 | Jarad Hermann | Submit | WP WP418 - Disaster Recovery Plan - Submit | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1169 | 1171 |  | Joy Schneider,Jarad Hermann
5164 | 1171 | Future Task |  |  | WP418 | Jarad Hermann | Review | WP WP418 - Disaster Recovery Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 1170 | 1172 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5165 | 1172 | Future Task |  |  | WP418 | Jarad Hermann | Review | WP WP418 - Disaster Recovery Plan - Final Review & Edits | 12 hrs | 5 days | Mon 12/16/24 | Fri 12/20/24 | 1171 | 1173 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5166 | 1173 | Future Task |  |  | WP418 | Jarad Hermann | Approve | WP WP418 - Disaster Recovery Plan - Approve | 0 hrs | 0 days | Fri 12/20/24 | Fri 12/20/24 | 1172 | 993 | 2024-11-01 | Jimmy Cox
5167 | 1174 | Future Task |  |  | WP419 | Jarad Hermann |  | WP419 - Disaster Recovery Testing Plan | 116 hrs | 158 days | Mon 8/5/24 | Fri 3/21/25
5168 | 1175 | Future Task |  |  | WP419 | Jarad Hermann | Create | WPED WP419 - Disaster Recovery Testing Plan - Create | 16 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 1163SS+10 days | 1176 |  | Jarad Hermann,Mary Punty
5169 | 1176 | Future Task |  |  | WP419 | Jarad Hermann | Submit | WPED WP419 - Disaster Recovery Testing Plan - Submit | 0 hrs | 0 days | Fri 8/16/24 | Fri 8/16/24 | 1175 | 1177 |  | Joy Schneider,Jarad Hermann
5170 | 1177 | Future Task |  |  | WP419 | Jarad Hermann | Review | WPED WP419 - Disaster Recovery Testing Plan - Review | 20 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 1176 | 1178 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5171 | 1178 | Future Task |  |  | WP419 | Jarad Hermann | Approve | WPED WP419 - Disaster Recovery Testing Plan - Approve | 0 hrs | 0 days | Fri 8/30/24 | Fri 8/30/24 | 1177 | 1179FS+20 days |  | Jimmy Cox
5237 | 1179 | Future Task |  |  | WP419 | Jarad Hermann | Create | WP419 - Define and Document Disaster Recovery Test Tasks including Test Planning, Preparation, Execution, and Closure | 20 hrs | 62 days | Tue 10/1/24 | Tue 12/31/24 | 1178FS+20 days | 1180SS,1214SS+24 days |  | Jarad Hermann,Bryan Sohayda
5238 | 1180 | Future Task |  |  | WP419 | Jarad Hermann | Create | WP419 - Define Disaster Recovery Testing Tools | 20 hrs | 62 days | Tue 10/1/24 | Tue 12/31/24 | 1179SS | 1181 |  | Jarad Hermann,Bryan Sohayda
5239 | 1181 | Future Task |  |  | WP419 | Jarad Hermann | Create | WP419 - Define and Document Disaster Recovery Test Management | 4 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1180 | 1182SS |  | Jarad Hermann,Bryan Sohayda
5240 | 1182 | Future Task |  |  | WP419 | Jarad Hermann | Create | WP419 - Define and Document Disaster Recovery Test Resources and Responsibilities | 4 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1181SS | 1183 |  | Jarad Hermann,Bryan Sohayda
5172 | 1183 | Future Task |  |  | WP419 | Jarad Hermann | Submit | WP WP419 - Disaster Recovery Testing Plan - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 1182 | 1184568 | 2025-02-28 | Joy Schneider,Jarad Hermann
5173 | 1184 | Future Task |  |  | WP419 | Jarad Hermann | Review | WP WP419 - Disaster Recovery Testing Plan - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1183 | 1185 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5174 | 1185 | Future Task |  |  | WP419 | Jarad Hermann | Review | WP WP419 - Disaster Recovery Testing Plan - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1184 | 1186 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5175 | 1186 | Future Task |  |  | WP419 | Jarad Hermann | Approve | WP WP419 - Disaster Recovery Testing Plan - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1185 | 993FS-35 days | 2025-02-01 | Jimmy Cox
5176 | 1187 | Future Task |  |  | WP420 | Jarad Hermann |  | WP420 - Performance Testing Plan | 128 hrs | 172 days | Mon 9/16/24 | Wed 5/21/25
5177 | 1188 | Future Task |  |  | WP420 | Jarad Hermann | Create | WPED WP420 - Performance Testing Plan - Create | 16 hrs | 10 days | Mon 9/16/24 | Fri 9/27/24 | 1 | 1189,1226SS+10 days |  | Jarad Hermann,Mary Punty
5178 | 1189 | Future Task |  |  | WP420 | Jarad Hermann | Submit | WPED WP420 - Performance Testing Plan - Submit | 0 hrs | 0 days | Fri 9/27/24 | Fri 9/27/24 | 1188 | 1190 |  | Joy Schneider,Jarad Hermann
5179 | 1190 | Future Task |  |  | WP420 | Jarad Hermann | Review | WPED WP420 - Performance Testing Plan - Review | 20 hrs | 10 days | Mon 9/30/24 | Fri 10/11/24 | 1189 | 1191 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5180 | 1191 | Future Task |  |  | WP420 | Jarad Hermann | Approve | WPED WP420 - Performance Testing Plan - Approve | 0 hrs | 0 days | Fri 10/11/24 | Fri 10/11/24 | 1190 | 1192FS+32 days,1193SS,1194SS,1195SS,1196SS |  | Jimmy Cox
5241 | 1192 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Identify and establish the projected load of the system | 4 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1191FS+32 days | 1197 |  | Jarad Hermann,Bryan Sohayda
5242 | 1193 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Define test cycles to be included | 20 hrs | 105 days | Mon 10/14/24 | Mon 3/17/25 | 1191SS | 1197 |  | Jarad Hermann,Bryan Sohayda
5243 | 1194 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Define Performance Testing objectives, scope, environments, and metrics | 20 hrs | 105 days | Mon 10/14/24 | Mon 3/17/25 | 1191SS | 1197 |  | Jarad Hermann,Bryan Sohayda
5244 | 1195 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Identify performance testing project team members and responsibilities | 20 hrs | 105 days | Mon 10/14/24 | Mon 3/17/25 | 1191SS | 1197 |  | Jarad Hermann,Bryan Sohayda
5245 | 1196 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Define and document Performance Testing entry and exit criteria | 20 hrs | 105 days | Mon 10/14/24 | Mon 3/17/25 | 1191SS | 1197 |  | Jarad Hermann,Bryan Sohayda
5181 | 1197 | Future Task |  |  | WP420 | Jarad Hermann | Submit | WP WP420 - Performance Testing Plan - Submit | 0 hrs | 0 days | Wed 4/30/25 | Wed 4/30/25 | 1.1961e+19 | 1198566 |  | Joy Schneider,Jarad Hermann
5182 | 1198 | Future Task |  |  | WP420 | Jarad Hermann | Review | WP WP420 - Performance Testing Plan - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 1197 | 1199 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5183 | 1199 | Future Task |  |  | WP420 | Jarad Hermann | Review | WP WP420 - Performance Testing Plan - Final Review & Edits | 4 hrs | 5 days | Thu 5/15/25 | Wed 5/21/25 | 1198 | 1200 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5184 | 1200 | Future Task |  |  | WP420 | Jarad Hermann | Approve | WP WP420 - Performance Testing Plan - Approve | 0 hrs | 0 days | Wed 5/21/25 | Wed 5/21/25 | 1199 | 975FS-28 days | 2025-04-01 | Jimmy Cox
5185 | 1201 | Future Task |  |  | WP421 | Jarad Hermann |  | WP421 - Penetration Testing Plan | 128 hrs | 124 days | Mon 9/23/24 | Fri 3/21/25
5186 | 1202 | Future Task |  |  | WP421 | Jarad Hermann | Create | WPED WP421 - Penetration Testing Plan - Create | 16 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 1 | 1203,1238SS+10 days |  | Jarad Hermann,Mary Punty
5187 | 1203 | Future Task |  |  | WP421 | Jarad Hermann | Submit | WPED WP421 - Penetration Testing Plan - Submit | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 1202 | 1204 |  | Joy Schneider,Jarad Hermann
5188 | 1204 | Future Task |  |  | WP421 | Jarad Hermann | Review | WPED WP421 - Penetration Testing Plan - Review | 20 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1203 | 1205 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5189 | 1205 | Future Task |  |  | WP421 | Jarad Hermann | Approve | WPED WP421 - Penetration Testing Plan - Approve | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 1204 | 1206FS+27 days |  | Jimmy Cox
5246 | 1206 | Future Task |  |  | WP421 | Jarad Hermann | Create | WP421 - Create Penetration Testing Plan/approach | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1205FS+27 days | 1207SS,1208SS,1209 |  | Jarad Hermann,Bryan Sohayda
5247 | 1207 | Future Task |  |  | WP421 | Jarad Hermann | Create | WP421 - Identify resources for Penetration Testing | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1206SS | 1209 |  | Jarad Hermann,Bryan Sohayda
5248 | 1208 | Future Task |  |  | WP421 | Jarad Hermann | Create | WP421 - Define Penetration Testing entry and exit criteria | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1206SS | 1209 |  | Jarad Hermann,Bryan Sohayda
5190 | 1209 | Future Task |  |  | WP421 | Jarad Hermann | Submit | WP WP421 - Penetration Testing Plan - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 120812061207 | 1210 |  | Joy Schneider,Jarad Hermann
5191 | 1210 | Future Task |  |  | WP421 | Jarad Hermann | Review | WP WP421 - Penetration Testing Plan - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1209 | 1211 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5192 | 1211 | Future Task |  |  | WP421 | Jarad Hermann | Review | WP WP421 - Penetration Testing Plan - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1210 | 1212 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5193 | 1212 | Future Task |  |  | WP421 | Jarad Hermann | Approve | WP WP421 - Penetration Testing Plan - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1211 | 957FS+10 days | 2025-02-01 | Jimmy Cox
5194 | 1213 | Future Task |  |  | WP422 | Jarad Hermann |  | WP422 - Disaster Recovery Test Scripts | 128 hrs | 94 days | Mon 11/4/24 | Fri 3/21/25
5195 | 1214 | Future Task |  |  | WP422 | Jarad Hermann | Create | WPED WP422 - Disaster Recovery Test Scripts - Create | 16 hrs | 10 days | Mon 11/4/24 | Mon 11/18/24 | 1179SS+24 days | 1215 |  | Jarad Hermann,Mary Punty
5196 | 1215 | Future Task |  |  | WP422 | Jarad Hermann | Submit | WPED WP422 - Disaster Recovery Test Scripts - Submit | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 1214 | 1216 |  | Joy Schneider,Jarad Hermann
5197 | 1216 | Future Task |  |  | WP422 | Jarad Hermann | Review | WPED WP422 - Disaster Recovery Test Scripts - Review | 20 hrs | 10 days | Tue 11/19/24 | Wed 12/4/24 | 1215 | 1217 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5198 | 1217 | Future Task |  |  | WP422 | Jarad Hermann | Approve | WPED WP422 - Disaster Recovery Test Scripts - Approve | 0 hrs | 0 days | Wed 12/4/24 | Wed 12/4/24 | 1216 | 1218FS+18 days |  | Jimmy Cox
5249 | 1218 | Future Task |  |  | WP422 | Jarad Hermann | Create | WP422 - Finalize Disaster Recovery Test Scripts Inventory | 20 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1217FS+18 days | 1219SS,1220SS,1221 |  | Jarad Hermann,Bryan Sohayda
5250 | 1219 | Future Task |  |  | WP422 | Jarad Hermann | Create | WP422 - Create, review, and confirm DR Test Script Work Unit Tracker | 20 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1218SS | 1221 |  | Jarad Hermann,Bryan Sohayda
5251 | 1220 | Future Task |  |  | WP422 | Jarad Hermann | Create | WP422 - Create, Review and Confirm Disaster Recovery Test Scripts | 20 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1218SS | 1221 |  | Jarad Hermann,Bryan Sohayda
5199 | 1221 | Future Task |  |  | WP422 | Jarad Hermann | Submit | WP WP422 - Disaster Recovery Test Scripts - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 122012181219 | 1222 |  | Joy Schneider,Jarad Hermann
5200 | 1222 | Future Task |  |  | WP422 | Jarad Hermann | Review | WP WP422 - Disaster Recovery Test Scripts - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1221 | 1223 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5201 | 1223 | Future Task |  |  | WP422 | Jarad Hermann | Review | WP WP422 - Disaster Recovery Test Scripts - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1222 | 1224 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5202 | 1224 | Future Task |  |  | WP422 | Jarad Hermann | Approve | WP WP422 - Disaster Recovery Test Scripts - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1223 | 993FS-35 days |  | Jimmy Cox
5203 | 1225 | Future Task |  |  | WP423 | Jarad Hermann |  | WP423 - Performance Test Scripts | 104 hrs | 162 days | Mon 9/30/24 | Wed 5/21/25
5204 | 1226 | Future Task |  |  | WP423 | Jarad Hermann | Create | WPED WP423 - Performance Test Scripts - Create | 16 hrs | 10 days | Mon 9/30/24 | Fri 10/11/24 | 1188SS+10 days | 1227 |  | Jarad Hermann,Mary Punty
5205 | 1227 | Future Task |  |  | WP423 | Jarad Hermann | Submit | WPED WP423 - Performance Test Scripts - Submit | 0 hrs | 0 days | Fri 10/11/24 | Fri 10/11/24 | 1226 | 1228 |  | Joy Schneider,Jarad Hermann
5206 | 1228 | Future Task |  |  | WP423 | Jarad Hermann | Review | WPED WP423 - Performance Test Scripts - Review | 20 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 1227 | 1229 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5207 | 1229 | Future Task |  |  | WP423 | Jarad Hermann | Approve | WPED WP423 - Performance Test Scripts - Approve | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 1228 | 1230FS+22 days |  | Jimmy Cox
5252 | 1230 | Future Task |  |  | WP423 | Jarad Hermann | Create | WP423 - Finalize Performance Test Scripts Inventory | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1229FS+22 days | 1231SS,1232SS,1233 |  | Jarad Hermann,Bryan Sohayda
5253 | 1231 | Future Task |  |  | WP423 | Jarad Hermann | Create | WP423 - Create, review, and confirm Performance Test Script Work Unit Tracker | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1230SS | 1233 |  | Jarad Hermann,Bryan Sohayda
5254 | 1232 | Future Task |  |  | WP423 | Jarad Hermann | Create | WP423 - Create, Review and Confirm Performance Test Scripts | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1230SS | 1233 |  | Jarad Hermann,Bryan Sohayda
5208 | 1233 | Future Task |  |  | WP423 | Jarad Hermann | Submit | WP WP423 - Performance Test Scripts - Submit | 0 hrs | 0 days | Wed 4/30/25 | Wed 4/30/25 | 123212301231 | 1234 |  | Joy Schneider,Jarad Hermann
5209 | 1234 | Future Task |  |  | WP423 | Jarad Hermann | Review | WP WP423 - Performance Test Scripts - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 1233 | 1235 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5210 | 1235 | Future Task |  |  | WP423 | Jarad Hermann | Review | WP WP423 - Performance Test Scripts - Final Review & Edits | 4 hrs | 5 days | Thu 5/15/25 | Wed 5/21/25 | 1234 | 1236 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5211 | 1236 | Future Task |  |  | WP423 | Jarad Hermann | Approve | WP WP423 - Performance Test Scripts - Approve | 0 hrs | 0 days | Wed 5/21/25 | Wed 5/21/25 | 1235 | 975FS-28 days |  | Jimmy Cox
5212 | 1237 | Future Task |  |  | WP424 | Jarad Hermann |  | WP424 - Penetration Test Scripts/Scenarios | 108 hrs | 114 days | Mon 10/7/24 | Fri 3/21/25
5213 | 1238 | Future Task |  |  | WP424 | Jarad Hermann | Create | WPED WP424 - Penetration Test Scripts/Scenarios - Create | 16 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1202SS+10 days | 1239 |  | Jarad Hermann,Mary Punty
5214 | 1239 | Future Task |  |  | WP424 | Jarad Hermann | Submit | WPED WP424 - Penetration Test Scripts/Scenarios - Submit | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 1238 | 1240 |  | Joy Schneider,Jarad Hermann
5215 | 1240 | Future Task |  |  | WP424 | Jarad Hermann | Review | WPED WP424 - Penetration Test Scripts/Scenarios - Review | 20 hrs | 10 days | Mon 10/21/24 | Fri 11/1/24 | 1239 | 1241 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5216 | 1241 | Future Task |  |  | WP424 | Jarad Hermann | Approve | WPED WP424 - Penetration Test Scripts/Scenarios - Approve | 0 hrs | 0 days | Fri 11/1/24 | Fri 11/1/24 | 1240 | 1242FS+17 days |  | Jimmy Cox
5255 | 1242 | Future Task |  |  | WP424 | Jarad Hermann | Create | WP424 - Finalize Penetration Test Scripts Inventory | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1241FS+17 days | 1243SS |  | Jarad Hermann,Bryan Sohayda
5256 | 1243 | Future Task |  |  | WP424 | Jarad Hermann | Create | WP424 - Create, review, and confirm Penetration Test Scripts/Scenarios | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1242SS | 1244 |  | Jarad Hermann,Bryan Sohayda
5217 | 1244 | Future Task |  |  | WP424 | Jarad Hermann | Submit | WP424 - WP WP424 - Penetration Test Scripts/Scenarios - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 1243 | 1245 |  | Joy Schneider,Jarad Hermann
5218 | 1245 | Future Task |  |  | WP424 | Jarad Hermann | Review | WP WP424 - Penetration Test Scripts/Scenarios - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1244 | 1246 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5219 | 1246 | Future Task |  |  | WP424 | Jarad Hermann | Review | WP WP424 - Penetration Test Scripts/Scenarios - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1245 | 1247 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5220 | 1247 | Future Task |  |  | WP424 | Jarad Hermann | Approve | WP WP424 - Penetration Test Scripts/Scenarios - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1246 | 957FS+10 days |  | Jimmy Cox
7247 | 1248 | Future Task |  |  | WP429 | Stacey Terry |  | WP429 - Updated System Testing Plan (BI/DW) | 412 hrs | 80 days | Mon 8/12/24 | Thu 12/5/24
7248 | 1249 | Future Task |  |  | WP429 | Stacey Terry | Create | WPED WP429 - Updated System Testing Plan (BI/DW) - Create | 88 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 620FS+101 days | 1250 |  | Stacey Terry,Mary Punty
7249 | 1250 | Future Task |  |  | WP429 | Stacey Terry | Submit | WPED WP429 - Updated System Testing Plan (BI/DW) - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 1249 | 1251 |  | Joy Schneider,Stacey Terry
7250 | 1251 | Future Task |  |  | WP429 | Stacey Terry | Review | WPED WP429 - Updated System Testing Plan (BI/DW) - Review | 108 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1250 | 1252 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan,Mary Punty
7251 | 1252 | Future Task |  |  | WP429 | Stacey Terry | Approve | WPED WP429 - Updated System Testing Plan (BI/DW) - Approve | 0 hrs | 0 days | Mon 9/9/24 | Mon 9/9/24 | 1251 | 1253 |  | Jimmy Cox
7261 | 1253 | Future Task |  |  | WP429 | Stacey Terry | Create | WP429 - Define System Test approach for DW & BI | 20 hrs | 20 days | Tue 9/10/24 | Mon 10/7/24 | 1252 | 1254SS+10 days |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
7262 | 1254 | Future Task |  |  | WP429 | Stacey Terry | Create | WP429 - Define System Test Cycles for DW & BI | 20 hrs | 15 days | Tue 9/24/24 | Mon 10/14/24 | 1253SS+10 days | 1255SS+5 days |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
7263 | 1255 | Future Task |  |  | WP429 | Stacey Terry | Create | WP429 - Identify System Test Resources for DW & BI | 20 hrs | 10 days | Tue 10/1/24 | Mon 10/14/24 | 1254SS+5 days | 1256 |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
7264 | 1256 | Future Task |  |  | WP429 | Stacey Terry | Create | WP429 - Create Initial List of DW & BI System Test Scenarios | 4 hrs | 20 days | Tue 10/15/24 | Tue 11/12/24 | 1255 | 1257 |  | Jennifer Reeves,Manojkumar Gurjar
7257 | 1257 | Future Task |  |  | WP429 | Stacey Terry | Submit | WP WP429 - Data Dictionary - Submit | 0 hrs | 0 days | Tue 11/12/24 | Tue 11/12/24 | 1256 | 1258 |  | Joy Schneider,Stacey Terry
7258 | 1258 | Future Task |  |  | WP429 | Stacey Terry | Review | WP WP429 - Data Dictionary - Collaborative Review & Update | 96 hrs | 10 days | Wed 11/13/24 | Tue 11/26/24 | 1257 | 1259 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson,Mary Punty
7259 | 1259 | Future Task |  |  | WP429 | Stacey Terry | Review | WP WP429 - Data Dictionary - Final Review & Edits | 56 hrs | 5 days | Wed 11/27/24 | Thu 12/5/24 | 1258 | 1260 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson,Mary Punty
7260 | 1260 | Future Task |  |  | WP429 | Stacey Terry | Approve | WP WP429 - Data Dictionary - Approve | 0 hrs | 0 days | Thu 12/5/24 | Thu 12/5/24 | 1259 |  | 2024-12-01 | Jimmy Cox
5299 | 1261 | Future Task |  |  | I-WP127 | Angie Robertson |  | I-WP127 - User Acceptance Testing Plan | 91 hrs | 159 days | Mon 8/7/23 | Mon 3/25/24
5300 | 1262 | Future Task |  |  | I-WP127 | Angie Robertson | Create | WPED I-WP127 - User Acceptance Testing Plan - Create | 4 hrs | 10 days | Mon 8/7/23 | Fri 8/18/23 | 1 | 1263 |  | Angie Robertson,Jimmy Cox
5301 | 1263 | Future Task |  |  | I-WP127 | Angie Robertson | Submit | WPED I-WP127 - User Acceptance Testing Plan - Submit | 0 hrs | 0 days | Fri 8/18/23 | Fri 8/18/23 | 1262 | 1264 |  | Angie Robertson
5302 | 1264 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WPED I-WP127 - User Acceptance Testing Plan - Collaborative Review & Update | 17 hrs | 10 days | Mon 8/21/23 | Fri 9/1/23 | 1263 | 1265 |  | Carolyn Hicks,Angie Robertson,Matthew Breeding,Jennifer Reeves,Deana Metcalf,Julian Gotreaux,Tommy Werner,Matt Cole,Mary Punty,Stacey Terry
5303 | 1265 | Future Task |  |  | I-WP127 | Angie Robertson | Approve | WPED I-WP127 - User Acceptance Testing Plan - Approve | 0 hrs | 0 days | Fri 9/1/23 | Fri 9/1/23 | 1264 | 1266FS+41 days |  | Jimmy Cox
5310 | 1266 | Future Task |  | RW | I-WP127 | Angie Robertson | Create | Create User Acceptance Plan | 40 hrs | 81 days | Wed 11/1/23 | Thu 2/29/24 | 1265FS+41 days | 1267 |  | Matthew Breeding,Jennifer Reeves,Carolyn Hicks,Deana Metcalf,Angie Robertson
5304 | 1267 | Future Task |  |  | I-WP127 | Angie Robertson | Submit | WP I-WP127 - User Acceptance Testing Plan - Submit | 0 hrs | 0 days | Thu 2/29/24 | Thu 2/29/24 | 1266 | 1268 |  | Angie Robertson
5305 | 1268 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WP I-WP127 - User Acceptance Testing Plan - Department QC | 8 hrs | 1 day | Fri 3/1/24 | Fri 3/1/24 | 1267 | 1269 |  | Gabriela Gibson
5306 | 1269 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WP I-WP127 - User Acceptance Testing Plan - Collaborative Review & Update | 10 hrs | 10 days | Mon 3/4/24 | Fri 3/15/24 | 1268 | 1270 |  | Matthew Breeding,Jennifer Reeves,Carolyn Hicks,Deana Metcalf,Angie Robertson
5307 | 1270 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WP I-WP127 - User Acceptance Testing Plan - Style Guide Review | 2 hrs | 1 day | Mon 3/18/24 | Mon 3/18/24 | 1269 | 1271 |  | Tatiana Eubanks
5308 | 1271 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WP I-WP127 - User Acceptance Testing Plan - Final Review & Update | 10 hrs | 5 days | Tue 3/19/24 | Mon 3/25/24 | 1270 | 1272 |  | Angie Robertson,Jimmy Cox
5309 | 1272 | Future Task |  |  | I-WP127 | Angie Robertson | Approve | WP I-WP127 - User Acceptance Testing Plan - Approve | 0 hrs | 0 days | Mon 3/25/24 | Mon 3/25/24 | 1271 | 1274,559FS+215 days,600 |  | Jimmy Cox
3967 | 1273 | Future Task | [5 empty] | UAT | 1 hr | 163 days | Tue 4/1/25 | Wed 11/19/25
4002 | 1274 | Future Task |  | RW | UAT | Matt Breeding | Create | UAT Testing | 1 hr | 163 days | Tue 4/1/25 | Wed 11/19/25 | 17525631272587 | 1783,1808SS+30 days | Dates to be confirmed in I-WP127 | Jimmy Cox,Angie Robertson
7214 | 1275 | Future Task | [5 empty] | Other | 46 hrs | 15 days | Mon 5/5/25 | Fri 5/23/25
7216 | 1276 | Future Task |  |  |  | Manojkumar Gurjar | Create | Prepare for data migration from FLAIR IW for DW/IW | 6 hrs | 5 days | Mon 5/5/25 | Fri 5/9/25 | 765FS+4 days | 1277 |  | Stacey Terry,Jimmy Cox,Angie Robertson,Matt Cole,Matthew Breeding,Manojkumar Gurjar
7215 | 1277 | Future Task |  |  |  | Manojkumar Gurjar | Create | Validate the IW data migration | 40 hrs | 10 days | Mon 5/12/25 | Fri 5/23/25 | 1276 |  |  | Matthew Breeding,Jennifer Reeves
3772 | 1278 | Future Task | [5 empty] | Deploy | 1,938 hrs | 565 days | Fri 11/3/23 | Wed 2/4/26
7188 | 1279 | Future Task |  |  | SG5 | Jimmy Cox | Create | Stage Gate 5: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 6/30/25 | Mon 7/7/25 |  | 1280 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7189 | 1280 | Future Task |  |  | SG5 | Jimmy Cox | Create | Stage Gate 5: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Tue 7/8/25 | Mon 7/21/25 | 1279 | 1281FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7190 | 1281 | Future Task |  |  | SG5 | Jimmy Cox | Create | Stage Gate 5: Prepare information package for ESC | 11 hrs | 10 days | Fri 11/7/25 | Fri 11/21/25 | 1280FS+77 days | 1282 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7191 | 1282 | Future Task |  |  | SG5 | Jimmy Cox | Create | Stage Gate 5: Collaborative Review and Update of information package | 11 hrs | 5 days | Mon 11/24/25 | Tue 12/2/25 | 1281 | 1283 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7192 | 1283 | Future Task |  |  | SG5 | Jimmy Cox | Create | Stage Gate 5: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 12/3/25 | Wed 12/3/25 | 1282 |  |  | Dusti Kincl
7156 | 1284 | Future Task |  |  | SG5 | Jimmy Cox | Milestone | Stage Gate 5: Deployment Readiness | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 7.2579e+37 |  | December 17, 2025 - ESC | Executive Steering Committee
7193 | 1285 | Future Task |  |  | SG6 | Jimmy Cox | Create | Stage Gate 6: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 7/14/25 | Fri 7/18/25 |  | 1286 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7194 | 1286 | Future Task |  |  | SG6 | Jimmy Cox | Create | Stage Gate 6: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Mon 7/21/25 | Fri 8/1/25 | 1285 | 1287FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7195 | 1287 | Future Task |  |  | SG6 | Jimmy Cox | Create | Stage Gate 6: Prepare information package for ESC | 11 hrs | 10 days | Fri 11/21/25 | Mon 12/8/25 | 1286FS+77 days | 1288 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7196 | 1288 | Future Task |  |  | SG6 | Jimmy Cox | Create | Stage Gate 6: Collaborative Review and Update of information package | 11 hrs | 5 days | Tue 12/9/25 | Mon 12/15/25 | 1287 | 1289 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7197 | 1289 | Future Task |  |  | SG6 | Jimmy Cox | Create | Stage Gate 6: Provide Checklist and information package to the ESC | 1 hr | 1 day | Tue 12/16/25 | Tue 12/16/25 | 1288 |  |  | Dusti Kincl
7157 | 1290 | Future Task |  |  | SG6 | Jimmy Cox | Milestone | Stage Gate 6: Confirm Deployment | 0 hrs | 0 days | Fri 12/19/25 | Fri 12/19/25 | 141814331381 | 1296 | 2025-12-30 | Jimmy Cox,Angie Robertson,Matt Cole
7198 | 1291 | Future Task |  |  | SG7 | Jimmy Cox | Create | Stage Gate 7: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 7/21/25 | Fri 7/25/25 |  | 1292 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7199 | 1292 | Future Task |  |  | SG7 | Jimmy Cox | Create | Stage Gate 7: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Mon 7/28/25 | Fri 8/8/25 | 1291 | 1293FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7200 | 1293 | Future Task |  |  | SG7 | Jimmy Cox | Create | Stage Gate 7: Prepare information package for ESC | 11 hrs | 10 days | Tue 12/2/25 | Mon 12/15/25 | 1292FS+77 days | 1294 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7201 | 1294 | Future Task |  |  | SG7 | Jimmy Cox | Create | Stage Gate 7: Collaborative Review and Update of information package | 11 hrs | 5 days | Tue 12/16/25 | Mon 12/22/25 | 1293 | 1295 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7202 | 1295 | Future Task |  |  | SG7 | Jimmy Cox | Create | Stage Gate 7: Provide Checklist and information package to the ESC | 1 hr | 1 day | Tue 12/23/25 | Tue 12/23/25 | 1294 |  |  | Dusti Kincl
7158 | 1296 | Future Task |  |  | SG7 | Jimmy Cox | Milestone | Stage Gate 7: Go-Live | 0 hrs | 0 days | Fri 12/19/25 | Fri 12/19/25 | 1290 |  | 2026-01-06 | Jimmy Cox,Angie Robertson,Matt Cole
5311 | 1297 | Future Task |  |  | D645 | Mary Punty |  | D645 - Updated Deployment Strategy | 265 hrs | 122 days | Fri 11/3/23 | Tue 4/30/24
5312 | 1298 | Future Task |  |  | D645 | Mary Punty | Create | DED D645 - Updated Deployment Strategy - Create | 16 hrs | 10 days | Fri 11/3/23 | Fri 11/17/23 | 1 | 1299 |  | Mary Punty,Bryan Sohayda
5313 | 1299 | Future Task |  |  | D645 | Mary Punty | Submit | DED D645 - Updated Deployment Strategy - Submit | 0 hrs | 0 days | Fri 11/17/23 | Fri 11/17/23 | 1298 | 1300 |  | Mary Punty,Joy Schneider
5314 | 1300 | Future Task |  |  | D645 | Mary Punty | Review | DED D645 - Updated Deployment Strategy - Collaborative Review | 20 hrs | 10 days | Mon 11/20/23 | Tue 12/5/23 | 1299 | 1301 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5315 | 1301 | Future Task |  |  | D645 | Mary Punty | Approve | DED D645 - Updated Deployment Strategy - Approve | 0 hrs | 0 days | Tue 12/5/23 | Tue 12/5/23 | 1300 | 1302FS+17 days |  | Jimmy Cox
5339 | 1302 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Document assumptions about deployment | 20 hrs | 9 days | Tue 1/2/24 | Fri 1/12/24 | 1301FS+17 days | 1303 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5340 | 1303 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Create Deployment Kickoff Presentation | 20 hrs | 9 days | Tue 1/16/24 | Fri 1/26/24 | 1302 | 1304 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5341 | 1304 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Review Deployment Kickoff Presentation | 20 hrs | 5 days | Mon 1/29/24 | Fri 2/2/24 | 1303 | 1305 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5342 | 1305 | Future Task |  | RW | D645 | Mary Punty | Create | D645 - Describe Deployment Calendar | 20 hrs | 10 days | Mon 2/5/24 | Fri 2/16/24 | 1304 | 1306 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5343 | 1306 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Review Deployment Calendar | 20 hrs | 5 days | Mon 2/19/24 | Fri 2/23/24 | 1305 | 1307 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5344 | 1307 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Describe Cutover Checklist | 20 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 1306 | 1308 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5345 | 1308 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Review Cutover Checklist | 20 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 1307 | 1309 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5346 | 1309 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Finalize Draft - Deployment Strategy | 20 hrs | 5 days | Mon 3/25/24 | Fri 3/29/24 | 1308 | 1310 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5347 | 1310 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Review Draft - Deployment Strategy | 20 hrs | 5 days | Mon 4/1/24 | Fri 4/5/24 | 1309 | 1311 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5316 | 1311 | Future Task |  |  | D645 | Mary Punty | Submit | DEL D645 - Updated Deployment Strategy - Draft Submission | 0 hrs | 0 days | Fri 4/5/24 | Fri 4/5/24 | 1310 | 1312 |  | Mary Punty,Joy Schneider
5317 | 1312 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 4/8/24 | Fri 4/12/24 | 1311 | 1313 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5318 | 1313 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Style Guide Review | 1 hr | 1 day | Mon 4/15/24 | Mon 4/15/24 | 1312 | 1314 |  | Dusti Kincl
5319 | 1314 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Final Collaborative Review | 16 hrs | 5 days | Tue 4/16/24 | Mon 4/22/24 | 1313 | 1315 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5320 | 1315 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Accenture QC | 4 hrs | 2 days | Tue 4/23/24 | Wed 4/24/24 | 1314 | 1316 |  | Joy Schneider
5321 | 1316 | Future Task |  |  | D645 | Mary Punty | Submit | DEL D645 - Updated Deployment Strategy - Submit | 0 hrs | 0 days | Wed 4/24/24 | Wed 4/24/24 | 1315 | 1317 |  | Joy Schneider
5322 | 1317 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Department QC | 4 hrs | 1 day | Thu 4/25/24 | Thu 4/25/24 | 1316 | 1318 |  | Tommy Werner,Gabriela Gibson
5323 | 1318 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Contract Manager Review | 8 hrs | 3 days | Fri 4/26/24 | Tue 4/30/24 | 1317 | 13191321 |  | Sean Buchanan
5324 | 1319 | Future Task |  |  | D645 | Mary Punty | Accept | DEL D645 - Updated Deployment Strategy - Accept | 0 hrs | 0 days | Tue 4/30/24 | Tue 4/30/24 | 1318 |  | 2024-04-01 | Sean Buchanan
5325 | 1320 | Future Task | Yes |  | D658 | Mary Punty |  | D658 - Develop the Deployment and Contingency Plan | 498 hrs | 149 days | Mon 8/26/24 | Mon 3/31/25
5326 | 1321 | Future Task |  |  | D658 | Mary Punty | Create | DED D658 - Develop the Deployment and Contingency Plan - Create | 16 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1318 | 1322 |  | Mary Punty,Bryan Sohayda
5327 | 1322 | Future Task |  |  | D658 | Mary Punty | Submit | DED D658 - Develop the Deployment and Contingency Plan - Submit | 0 hrs | 0 days | Mon 9/9/24 | Mon 9/9/24 | 1321 | 1323 |  | Mary Punty,Joy Schneider
5328 | 1323 | Future Task |  |  | D658 | Mary Punty | Review | DED D658 - Develop the Deployment and Contingency Plan - Collaborative Review | 20 hrs | 10 days | Tue 9/10/24 | Mon 9/23/24 | 1322 | 1324 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5329 | 1324 | Future Task |  |  | D658 | Mary Punty | Approve | DED D658 - Develop the Deployment and Contingency Plan - Approve | 0 hrs | 0 days | Mon 9/23/24 | Mon 9/23/24 | 1323 | 1325FS+24 days |  | Jimmy Cox
5348 | 1325 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Create Deployment and Contingency Plan pitch deck | 18 hrs | 9 days | Mon 10/28/24 | Thu 11/7/24 | 1324FS+24 days | 1326 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5349 | 1326 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review Deployment and Contingency Plan pitch deck | 40 hrs | 4 days | Fri 11/8/24 | Thu 11/14/24 | 1325 | 1327FS+8 days,1331 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5350 | 1327 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Prepare materials for Dec Sponsor Meeting and Review | 25 hrs | 5 days | Wed 11/27/24 | Thu 12/5/24 | 1326FS+8 days | 1328 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5351 | 1328 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Plan for and hold December Sponsor Meeting | 25 hrs | 5 days | Fri 12/6/24 | Thu 12/12/24 | 1327 | 1329FS+11 days |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5352 | 1329 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Gather Deployment and Contingency Plan materials for January ESC Meeting | 35 hrs | 7 days | Tue 12/31/24 | Thu 1/9/25 | 1328FS+11 days | 1330,1335SS |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5353 | 1330 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review Deployment and Contingency Plan materials for January ESC Meeting | 25 hrs | 5 days | Fri 1/10/25 | Thu 1/16/25 | 1329 | 1339 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5354 | 1331 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Identify and document deployment and post-implementation support activities | 20 hrs | 8 days | Fri 11/15/24 | Tue 11/26/24 | 1326 | 1332 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5355 | 1332 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review and document deployment and post-implementation support activities | 25 hrs | 5 days | Wed 11/27/24 | Thu 12/5/24 | 1331 | 1333 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5356 | 1333 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Identify and document timing of cutover activities | 25 hrs | 5 days | Fri 12/6/24 | Thu 12/12/24 | 1332 | 1334 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5357 | 1334 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review and document timing of cutover activities | 25 hrs | 5 days | Fri 12/13/24 | Thu 12/19/24 | 1333 | 1335 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5358 | 1335 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Identify and document contingency scenarios | 20 hrs | 7 days | Tue 12/31/24 | Thu 1/9/25 | 1329SS,1334 | 1336 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5359 | 1336 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review contingency scenarios | 25 hrs | 5 days | Fri 1/10/25 | Thu 1/16/25 | 1335 | 1337 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5360 | 1337 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Define and document the approach to revert changes | 20 hrs | 4 days | Fri 1/17/25 | Thu 1/23/25 | 1336 | 1338 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5361 | 1338 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review the approach to revert changes | 25 hrs | 5 days | Fri 1/24/25 | Thu 1/30/25 | 1337 | 1339 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5362 | 1339 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Gather Deployment and Contingency Plan materials for February ESC Meeting | 25 hrs | 5 days | Fri 1/31/25 | Thu 2/6/25 | 13381330 | 1340 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5363 | 1340 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review Deployment and Contingency Plan materials for February ESC Meeting | 15 hrs | 3 days | Fri 2/7/25 | Tue 2/11/25 | 1339 | 1341FS+12 days |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5364 | 1341 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Confirm approach to Deployment and Contingency | 20 hrs | 5 days | Fri 2/28/25 | Thu 3/6/25 | 1340FS+12 days | 1342 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5330 | 1342 | Future Task |  |  | D658 | Mary Punty | Submit | DEL D658 - Develop the Deployment and Contingency Plan - Draft Submission | 0 hrs | 0 days | Thu 3/6/25 | Thu 3/6/25 | 1341 | 1343 |  | Mary Punty,Joy Schneider
5331 | 1343 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 3/7/25 | Thu 3/13/25 | 1342 | 1344 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5332 | 1344 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Style Guide Review | 1 hr | 1 day | Fri 3/14/25 | Fri 3/14/25 | 1343 | 1345 |  | Dusti Kincl
5333 | 1345 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Final Collaborative Review | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1344 | 1346 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5334 | 1346 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Accenture QC | 4 hrs | 2 days | Mon 3/24/25 | Tue 3/25/25 | 1345 | 1347 |  | Joy Schneider
5335 | 1347 | Future Task |  |  | D658 | Mary Punty | Submit | DEL D658 - Develop the Deployment and Contingency Plan - Submit | 0 hrs | 0 days | Tue 3/25/25 | Tue 3/25/25 | 1346 | 1348 |  | Joy Schneider
5336 | 1348 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Department QC | 4 hrs | 1 day | Wed 3/26/25 | Wed 3/26/25 | 1347 | 1349 |  | Tommy Werner,Gabriela Gibson
5337 | 1349 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Contract Manager Review | 8 hrs | 3 days | Thu 3/27/25 | Mon 3/31/25 | 1348 | 1350 |  | Sean Buchanan
5338 | 1350 | Future Task |  |  | D658 | Mary Punty | Accept | DEL D658 - Develop the Deployment and Contingency Plan - Accept | 0 hrs | 0 days | Mon 3/31/25 | Mon 3/31/25 | 1349 | 1284 | 2025-03-01 | Sean Buchanan
5365 | 1351 | Future Task | Yes |  | D678 | Bryan Sohayda |  | D678 - Final Known Issues & Enhancements Lists | 350 hrs | 86 days | Mon 8/4/25 | Fri 12/5/25
5366 | 1352 | Future Task |  |  | D678 | Bryan Sohayda | Create | DED D678 - Final Known Issues & Enhancements Lists - Create | 16 hrs | 10 days | Mon 8/4/25 | Fri 8/15/25 | 1 | 1353 |  | Mary Punty,Bryan Sohayda
5367 | 1353 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DED D678 - Final Known Issues & Enhancements Lists - Submit | 0 hrs | 0 days | Fri 8/15/25 | Fri 8/15/25 | 1352 | 1354 |  | Bryan Sohayda,Joy Schneider
5368 | 1354 | Future Task |  |  | D678 | Bryan Sohayda | Review | DED D678 - Final Known Issues & Enhancements Lists - Collaborative Review | 20 hrs | 10 days | Mon 8/18/25 | Fri 8/29/25 | 1353 | 1355 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5369 | 1355 | Future Task |  |  | D678 | Bryan Sohayda | Approve | DED D678 - Final Known Issues & Enhancements Lists - Approve | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 1354 | 1356FS+21 days |  | Jimmy Cox
5393 | 1356 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Initial Known Issues & Enhancements Lists | 20 hrs | 22 days | Wed 10/1/25 | Thu 10/30/25 | 1355FS+21 days | 1357SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5394 | 1357 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Review Open SIRs - Candidates for Known Issues List | 25 hrs | 5 days | Wed 10/1/25 | Tue 10/7/25 | 1356SS | 1358,1359SS |  | Bryan Sohayda,Mary Punty,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5395 | 1358 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Finalize Open SIRs - Candidates for Known Issues List | 24 hrs | 4 days | Wed 10/8/25 | Mon 10/13/25 | 1357 | 1360SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5396 | 1359 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Review Open SIRs - Candidates for Known Enhancements List | 30 hrs | 5 days | Wed 10/1/25 | Tue 10/7/25 | 1357SS | 1361 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5397 | 1360 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Finalize Open SIRs - Candidates for Known Enhancements List | 20 hrs | 4 days | Wed 10/8/25 | Mon 10/13/25 | 1358SS | 1361 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5398 | 1361 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Confirm Agreed Upon Known Issues | 30 hrs | 5 days | Tue 10/14/25 | Mon 10/20/25 | 13601359 | 1362SS,1363SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5399 | 1362 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Confirm Agreed Upon Known Enhancements | 30 hrs | 5 days | Tue 10/14/25 | Mon 10/20/25 | 1361SS | 1365 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5400 | 1363 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Create DEL Draft - Wrapper Document and Known Issues/Enhancements Lists | 20 hrs | 5 days | Tue 10/14/25 | Mon 10/20/25 | 1361SS | 1364 |  | Bryan Sohayda,Mary Punty
5401 | 1364 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Review DEL Draft - Wrapper Document and Known Issues/Enhancements Lists | 48 hrs | 8 days | Tue 10/21/25 | Thu 10/30/25 | 1363 | 1365 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5370 | 1365 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DEL D678 - Final Known Issues & Enhancements Lists - Draft Submission | 0 hrs | 0 days | Thu 10/30/25 | Thu 10/30/25 | 13641362 | 1366 |  | Bryan Sohayda,Joy Schneider
5371 | 1366 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 10/31/25 | Thu 11/6/25 | 1365 | 1367 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5372 | 1367 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Style Guide Review | 1 hr | 1 day | Fri 11/7/25 | Fri 11/7/25 | 1366 | 1368 |  | Dusti Kincl
5373 | 1368 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Final Collaborative Review | 16 hrs | 5 days | Mon 11/10/25 | Mon 11/17/25 | 1367 | 1369 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5374 | 1369 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Accenture QC | 4 hrs | 2 days | Tue 11/18/25 | Wed 11/19/25 | 1368 | 1370 |  | Joy Schneider
5375 | 1370 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DEL D678 - Final Known Issues & Enhancements Lists - Submit | 0 hrs | 0 days | Wed 11/19/25 | Wed 11/19/25 | 1369 | 1371 |  | Joy Schneider
5376 | 1371 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Department QC | 4 hrs | 1 day | Thu 11/20/25 | Thu 11/20/25 | 1370 | 1372 |  | Tommy Werner,Gabriela Gibson
5377 | 1372 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Contract Manager Review | 8 hrs | 3 days | Fri 11/21/25 | Tue 11/25/25 | 1371 | 1373 |  | Sean Buchanan
5378 | 1373 | Future Task |  |  | D678 | Bryan Sohayda | Accept | DEL D678 - Final Known Issues & Enhancements Lists - Accept | 0 hrs | 0 days | Tue 11/25/25 | Tue 11/25/25 | 1372 | 1374FS+1 day,1284 | 2025-12-01 | Sean Buchanan
5407 | 1374 | Future Task |  | RW | D678 | Bryan Sohayda | Create | Refresh Known Issues/Enhancements List to Prep for Stage Gate 5 | 18 hrs | 5 days | Mon 12/1/25 | Fri 12/5/25 | 1373FS+1 day |  |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5379 | 1375 | Future Task |  |  | D679 | Stacey Terry |  | D679 - Go-Live of Financials and Payroll Waves | 184 hrs | 82 days | Mon 10/6/25 | Wed 2/4/26
5380 | 1376 | Future Task |  |  | D679 | Stacey Terry | Create | DED D679 - Go-Live of Financials and Payroll Waves - Create | 16 hrs | 10 days | Mon 10/6/25 | Fri 10/17/25 | 1 | 1377 |  | Stacey Terry,Manojkumar Gurjar
5381 | 1377 | Future Task |  |  | D679 | Stacey Terry | Submit | DED D679 - Go-Live of Financials and Payroll Waves - Submit | 0 hrs | 0 days | Fri 10/17/25 | Fri 10/17/25 | 1376 | 1378 |  | Stacey Terry,Joy Schneider
5382 | 1378 | Future Task |  |  | D679 | Stacey Terry | Review | DED D679 - Go-Live of Financials and Payroll Waves - Collaborative Review | 28 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 1377 | 1379 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5383 | 1379 | Future Task |  |  | D679 | Stacey Terry | Approve | DED D679 - Go-Live of Financials and Payroll Waves - Approve | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 1378 | 1380FS+22 days |  | Jimmy Cox
5403 | 1380 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Go-Live of Financials and Payroll Waves | 15 hrs | 5 days | Mon 12/8/25 | Fri 12/12/25 | 1379FS+22 days | 1381 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5404 | 1381 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Document Go-Live Applications Listing | 15 hrs | 5 days | Mon 12/15/25 | Fri 12/19/25 | 1380 | 1385FS+8 days,1290,1382SS |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
7213 | 1382 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Execute Pre-Cutover Activities | 5 hrs | 11 days | Mon 12/15/25 | Tue 12/30/25 | 1381SS | 1383FS-1 day |  | Stacey Terry,Mary Punty,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner
7212 | 1383 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Execute Cutover Activities | 5 hrs | 2 days | Tue 12/30/25 | Wed 12/31/25 | 1382FS-1 day | 1384 |  | Stacey Terry,Mary Punty,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner
7211 | 1384 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Execute Post-Cutover Activities | 5 hrs | 11 days | Fri 1/2/26 | Fri 1/16/26 | 1383 | 1391 |  | Stacey Terry,Mary Punty,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner
5405 | 1385 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Document Go-Live Tasks Completed | 15 hrs | 5 days | Mon 1/5/26 | Fri 1/9/26 | 1381FS+8 days,1765 | 1386SS |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5406 | 1386 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Document Go-List of Agencies Participated | 15 hrs | 5 days | Mon 1/5/26 | Fri 1/9/26 | 1385SS | 1387 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5384 | 1387 | Future Task |  |  | D679 | Stacey Terry | Submit | DEL D679 - Go-Live of Financials and Payroll Waves - Draft Submission | 0 hrs | 0 days | Fri 1/9/26 | Fri 1/9/26 | 1386575 | 1388 |  | Stacey Terry,Joy Schneider
5385 | 1388 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Pre-Submission Collaborative Review | 24 hrs | 5 days | Mon 1/12/26 | Fri 1/16/26 | 1387 | 1389 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5386 | 1389 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Style Guide Review | 1 hr | 1 day | Tue 1/20/26 | Tue 1/20/26 | 1388 | 1390 |  | Dusti Kincl
5387 | 1390 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Final Collaborative Review | 24 hrs | 5 days | Wed 1/21/26 | Tue 1/27/26 | 1389 | 1391 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5388 | 1391 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Accenture QC | 4 hrs | 2 days | Wed 1/28/26 | Thu 1/29/26 | 13901384 | 1392 |  | Joy Schneider
5389 | 1392 | Future Task |  |  | D679 | Stacey Terry | Submit | DEL D679 - Go-Live of Financials and Payroll Waves - Submit | 0 hrs | 0 days | Thu 1/29/26 | Thu 1/29/26 | 1391 | 1393 |  | Joy Schneider
5390 | 1393 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Department QC | 4 hrs | 1 day | Fri 1/30/26 | Fri 1/30/26 | 1392 | 1394 |  | Tommy Werner,Gabriela Gibson
5391 | 1394 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Contract Manager Review | 8 hrs | 3 days | Mon 2/2/26 | Wed 2/4/26 | 1393 | 1395 |  | Sean Buchanan
5392 | 1395 | Future Task |  |  | D679 | Stacey Terry | Accept | DEL D679 - Go-Live of Financials and Payroll Waves - Accept | 0 hrs | 0 days | Wed 2/4/26 | Wed 2/4/26 | 1394 |  | 2026-01-01 | Sean Buchanan
6739 | 1396 | Future Task |  |  | WP425 | Bryan Sohayda |  | WP425 - Production Support Operations Plan | 356 hrs | 129 days | Mon 10/14/24 | Fri 4/18/25
6740 | 1397 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WPED WP425 - Production Support Operations Plan - Create | 8 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 1 | 1398 |  | Bryan Sohayda
6741 | 1398 | Future Task |  |  | WP425 | Bryan Sohayda | Submit | WPED WP425 - Production Support Operations Plan - Submit | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 1397 | 1399 |  | Joy Schneider,Bryan Sohayda
6742 | 1399 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WPED WP425 - Production Support Operations Plan - Review | 16 hrs | 10 days | Mon 10/28/24 | Fri 11/8/24 | 1398 | 1400 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
6743 | 1400 | Future Task |  |  | WP425 | Bryan Sohayda | Approve | WPED WP425 - Production Support Operations Plan - Approve | 0 hrs | 0 days | Fri 11/8/24 | Fri 11/8/24 | 1399 | 1401FS+22 days |  | Jimmy Cox
6744 | 1401 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Update Production Support Operations Plan | 20 hrs | 72 days | Mon 12/16/24 | Fri 3/28/25 | 1400FS+22 days | 1402SS |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6745 | 1402 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Introduction, Overview, Collab taken with partners, team R&R | 20 hrs | 5 days | Mon 12/16/24 | Fri 12/20/24 | 1401SS | 1403FS+8 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6746 | 1403 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document Production Support services provided | 20 hrs | 5 days | Mon 1/6/25 | Fri 1/10/25 | 1402FS+8 days | 1404 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6747 | 1404 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review and provide feedback on Production Support Services Provided draft | 20 hrs | 5 days | Mon 1/13/25 | Fri 1/17/25 | 1403 | 1405 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6748 | 1405 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Create Maintenance Calendar template | 48 hrs | 4 days | Tue 1/21/25 | Fri 1/24/25 | 1404 | 1406 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6749 | 1406 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review Maintenance Calendar template | 20 hrs | 5 days | Mon 1/27/25 | Fri 1/31/25 | 1405 | 1407 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6750 | 1407 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document production support business processes and tools list | 20 hrs | 5 days | Mon 2/3/25 | Fri 2/7/25 | 1406 | 1408 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6751 | 1408 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review and provide feedback on Production Support business processes and tools list draft | 20 hrs | 5 days | Mon 2/10/25 | Fri 2/14/25 | 1407 | 1409 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6752 | 1409 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document production support schedule of activities | 20 hrs | 5 days | Mon 2/17/25 | Fri 2/21/25 | 1408 | 1410 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6753 | 1410 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review and provide feedback on Production Support schedule of activities draft | 20 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 1409 | 1411 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6754 | 1411 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document production support performance expectations | 20 hrs | 5 days | Mon 3/3/25 | Fri 3/7/25 | 1410 | 1412 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6755 | 1412 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review and provide feedback on Production Support performance expectations draft | 20 hrs | 5 days | Mon 3/10/25 | Fri 3/14/25 | 1411 | 1413 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6756 | 1413 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document production support team roles, responsibilities, and staffing | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1412 | 1414 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6757 | 1414 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Full walkthrough of Production Support Operations Plan through facilitated meetings | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 1413 | 1415 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6758 | 1415 | Future Task |  |  | WP425 | Bryan Sohayda | Submit | WP WP425 - Production Support Operations Plan - Submit | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 1414 | 1416 |  | Joy Schneider,Bryan Sohayda
6759 | 1416 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WP WP425 - Production Support Operations Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 3/31/25 | Fri 4/11/25 | 1415 | 1417 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6760 | 1417 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WP WP425 - Production Support Operations Plan - Final Review & Edits | 12 hrs | 5 days | Mon 4/14/25 | Fri 4/18/25 | 1416 | 1418 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6761 | 1418 | Future Task |  |  | WP425 | Bryan Sohayda | Approve | WP WP425 - Production Support Operations Plan - Approve | 0 hrs | 0 days | Fri 4/18/25 | Fri 4/18/25 | 1417 | 1290 | 2025-04-01 | Jimmy Cox
6762 | 1419 | Future Task |  |  | WP427 | Bryan Sohayda |  | WP427 - Production Support Application Configuration Management Plan | 168 hrs | 107 days | Mon 12/2/24 | Fri 5/2/25
6763 | 1420 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WPED WP427 - Production Support Application Configuration Management Plan - Create | 8 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 1 | 1421 |  | Bryan Sohayda
6764 | 1421 | Future Task |  |  | WP427 | Bryan Sohayda | Submit | WPED WP427 - Production Support Application Configuration Management Plan - Submit | 0 hrs | 0 days | Fri 12/13/24 | Fri 12/13/24 | 1420 | 1422 |  | Joy Schneider,Bryan Sohayda
6765 | 1422 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WPED WP427 - Production Support Application Configuration Management Plan - Review | 16 hrs | 10 days | Mon 12/16/24 | Mon 12/30/24 | 1421 | 1423 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
6766 | 1423 | Future Task |  |  | WP427 | Bryan Sohayda | Approve | WPED WP427 - Production Support Application Configuration Management Plan - Approve | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 1422 | 1424FS+22 days |  | Jimmy Cox
6767 | 1424 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Updated Configuration Management Processes for Release and Maintenance | 20 hrs | 50 days | Mon 2/3/25 | Fri 4/11/25 | 1423FS+22 days | 1425SS,1430,1426SS+10 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6768 | 1425 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Define and Document Application Configuration Management Processes for Release and Maintenance | 20 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1424SS | 1426 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6769 | 1426 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Review and confirm Application and Infrastructure Configuration Management Processes for Release and Maintenance | 20 hrs | 5 days | Mon 2/17/25 | Fri 2/21/25 | 1424SS+10 days,1425 | 1427 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6770 | 1427 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Define and document System Configuration Control Process Steps and Diagram | 20 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 1426 | 1428 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6771 | 1428 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Review System Configuration Control Process Steps and Diagram | 20 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1427 | 1429FS+10 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6772 | 1429 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Full draft review pre-submission | 20 hrs | 10 days | Mon 3/31/25 | Fri 4/11/25 | 1428FS+10 days | 1430 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6773 | 1430 | Future Task |  |  | WP427 | Bryan Sohayda | Submit | WP WP427 - Production Support Application Configuration Management Plan - Submit | 0 hrs | 0 days | Fri 4/11/25 | Fri 4/11/25 | 14241429 | 1431 |  | Joy Schneider,Bryan Sohayda
6774 | 1431 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WP WP427 - Production Support Application Configuration Management Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 1430 | 1432 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6775 | 1432 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WP WP427 - Production Support Application Configuration Management Plan - Final Review & Edits | 12 hrs | 5 days | Mon 4/28/25 | Fri 5/2/25 | 1431 | 1433 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6776 | 1433 | Future Task |  |  | WP427 | Bryan Sohayda | Approve | WP WP427 - Production Support Application Configuration Management Plan - Approve | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 1432 | 1290 | 2025-04-01 | Jimmy Cox
2953 | 1434 | Late | [5 empty] | Stakeholder Engagement | 4,324 hrs | 730 days | Mon 5/8/23 | Tue 3/31/26
2972 | 1435 | On Schedule | [5 empty] | Training | 2,890 hrs | 722 days | Thu 5/18/23 | Tue 3/31/26
6906 | 1436 | On Schedule |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 - Data Inventory for Financials and Payroll Wave | 105 hrs | 277 days | Thu 5/18/23 | Fri 6/21/24
6907 | 1437 | On Schedule |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 - Data Inventory for Financials and Payroll Wave | 22 hrs | 277 days | Thu 5/18/23 | Fri 6/21/24
6908 | 1438 | Complete |  |  | I-WP102 | Jennifer Reeves | Create | WPED I-WP102 - Data Inventory for Financials and Payroll Wave - Create | 2 hrs | 10 days | Thu 5/18/23 | Thu 6/1/23 | 1 | 1439 |  | Jennifer Grant,Jennifer Reeves
6909 | 1439 | Complete |  |  | I-WP102 | Jennifer Reeves | Submit | WPED I-WP102 - Data Inventory for Financials and Payroll Wave - Submit | 0 hrs | 0 days | Thu 6/1/23 | Thu 6/1/23 | 1438 | 14401459 |  | Jennifer Grant,Jennifer Reeves
6910 | 1440 | On Schedule |  |  | I-WP102 | Jennifer Reeves | Review | WPED I-WP102 - Data Inventory for Financials and Payroll Wave - Collaborative Review and Update | 8 hrs | 10 days | Fri 6/2/23 | Thu 6/15/23 | 1439 | 1441 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Reeves,Jennifer Grant
6911 | 1441 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | WPED I-WP102 - Data Inventory for Financials and Payroll Wave - Approve | 0 hrs | 0 days | Thu 6/15/23 | Thu 6/15/23 | 1440 | 1450 |  | Jimmy Cox
6912 | 1442 | Future Task |  |  | I-WP102 | Jennifer Reeves | Submit | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Submit | 0 hrs | 0 days | Wed 5/29/24 | Wed 5/29/24 | 1481 | 1443 |  | Jennifer Grant,Jennifer Reeves
6913 | 1443 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Department QC | 2 hrs | 1 day | Thu 5/30/24 | Thu 5/30/24 | 1442 | 1444 |  | Gabriela Gibson
6914 | 1444 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Collaborative Review & Update | 7 hrs | 10 days | Fri 5/31/24 | Thu 6/13/24 | 1443 | 1445 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Nikki Klein,Daylin Reyes,Angie Robertson
6915 | 1445 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Style Guide Review | 1 hr | 1 day | Fri 6/14/24 | Fri 6/14/24 | 1444 | 1446 |  | Tatiana Eubanks
6916 | 1446 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Final Review & Update | 2 hrs | 5 days | Mon 6/17/24 | Fri 6/21/24 | 144514781482 | 1447 |  | Angie Robertson,Jimmy Cox
6917 | 1447 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Approve | 0 hrs | 0 days | Fri 6/21/24 | Fri 6/21/24 | 1446 |  |  | Jimmy Cox
6918 | 1448 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | Data Inventory for Financials and Payroll Wave | 83 hrs | 245 days | Fri 6/16/23 | Wed 6/5/24
6919 | 1449 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment I - Data | 20 hrs | 45 days | Fri 6/16/23 | Fri 8/18/23
6920 | 1450 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create - Data Inventory Format | 7 hrs | 5 days | Fri 6/16/23 | Thu 6/22/23 | 1441 | 1451 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Nikki Klein,Daylin Reyes,Angie Robertson
6921 | 1451 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory Format | 5 hrs | 5 days | Fri 6/23/23 | Thu 6/29/23 | 1450 | 1452 |  | Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Daylin Reyes,Angie Robertson
6922 | 1452 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory Format | 1 hr | 5 days | Fri 6/30/23 | Fri 7/7/23 | 1451 | 1453 |  | Jimmy Cox
6923 | 1453 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | Mon 7/10/23 | Fri 7/28/23 | 1452 | 1454 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6924 | 1454 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 15 days | Mon 7/31/23 | Fri 8/18/23 | 1453 | 1456 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6925 | 1455 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment II - Data | 7 hrs | 20 days | Mon 10/9/23 | Fri 11/3/23
6926 | 1456 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | Mon 10/9/23 | Fri 10/27/23 | 61SS,1454 | 1457 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6927 | 1457 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 5 days | Mon 10/30/23 | Fri 11/3/23 | 1456 | 1459 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6928 | 1458 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment III - Data | 13 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
6929 | 1459 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 1439,1457,141SS | 14601466 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6930 | 1460 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1459 | 14611467 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6931 | 1461 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Functional Teams | 6 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1460 | 1463 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6932 | 1462 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Update & Publish Data Inventory | 18 hrs | 25 days | Fri 2/2/24 | Thu 3/7/24
6933 | 1463 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 5 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1461 | 1464 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6934 | 1464 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1463 | 1465 |  | Jimmy Cox
6935 | 1465 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Coordinate Knowledge Base Update | 2 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1464 | 1478 |  | Jennifer Reeves,Daylin Reyes
6936 | 1466 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create Communication for Data Inventory | 2 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1459 | 1467 |  | Jennifer Grant,Jennifer Reeves
6937 | 1467 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review for Communication for Data Inventory | 2 hrs | 9 days | Fri 2/9/24 | Wed 2/21/24 | 14601466 | 1468 |  | Dusti Kincl,Angie Robertson
6938 | 1468 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Communication | 1 hr | 5 days | Thu 2/22/24 | Wed 2/28/24 | 1467 | 1469 |  | Jimmy Cox
6939 | 1469 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Publish Data Inventory | 4 hrs | 2 days | Thu 2/29/24 | Fri 3/1/24 | 1468 | 1470 |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6940 | 1470 | Future Task |  | RW-Communication | I-WP102 | Jennifer Reeves | Create | I-WP102 Share - Communication for Data Inventory | 1 hr | 2 days | Mon 3/4/24 | Tue 3/5/24 | 1469 | 1472 |  | Dusti Kincl
6941 | 1471 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment IV - Data | 11 hrs | 25 days | Wed 4/10/24 | Tue 5/14/24
6942 | 1472 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 3 hrs | 15 days | Wed 4/10/24 | Tue 4/30/24 | 1470 | 14731479 |  | Jennifer Reeves,Pradeep Koul,Tanya McCarty
6943 | 1473 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 2 hrs | 5 days | Wed 5/1/24 | Tue 5/7/24 | 1472 | 1474 |  | Jennifer Reeves,Matthew Breeding
6944 | 1474 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 6 hrs | 5 days | Wed 5/8/24 | Tue 5/14/24 | 1473 | 1476 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6945 | 1475 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Update & Publish Data Inventory | 14 hrs | 25 days | Wed 5/1/24 | Wed 6/5/24
6946 | 1476 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 3 hrs | 5 days | Wed 5/15/24 | Tue 5/21/24 | 1474 | 1477 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves
6947 | 1477 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory | 2 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1476 | 1478 |  | Angie Robertson,Jimmy Cox
6948 | 1478 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Coordinate Knowledge Base Update | 2 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 14771465 | 1446 |  | Jennifer Reeves,Daylin Reyes
6949 | 1479 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create Communication - Data Inventory | 2 hrs | 5 days | Wed 5/1/24 | Tue 5/7/24 | 1472 | 1480 |  | Jennifer Grant,Jennifer Reeves
6950 | 1480 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Communication for Data Inventory | 2 hrs | 10 days | Wed 5/8/24 | Tue 5/21/24 | 1479 | 1481 |  | Dusti Kincl,Angie Robertson
6951 | 1481 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Communication for Data Inventory | 2 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1480 | 14421482 |  | Jennifer Grant,Jennifer Reeves
6952 | 1482 | Future Task |  | RW-Communication | I-WP102 | Jennifer Reeves | Create | I-WP102 Share Communication for Data Inventory | 1 hr | 2 days | Thu 5/30/24 | Fri 5/31/24 | 1481 | 1446 |  | Dusti Kincl
7039 | 1483 | On Schedule |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 - Accounting Entry Inventory | 271 hrs | 285 days | Thu 5/18/23 | Wed 7/3/24
7040 | 1484 | Complete |  |  | I-WP103 | Jennifer Reeves | Create | WPED I-WP103 - Accounting Entry Inventory - Create | 10 hrs | 10 days | Thu 5/18/23 | Thu 6/1/23 | 1 | 1485 |  | Jennifer Grant,Jennifer Reeves
7041 | 1485 | Complete |  |  | I-WP103 | Jennifer Reeves | Submit | WPED I-WP103 - Accounting Entry Inventory - Submit | 0 hrs | 0 days | Thu 6/1/23 | Thu 6/1/23 | 1484 | 1486 |  | Jennifer Grant,Jennifer Reeves
7042 | 1486 | On Schedule |  |  | I-WP103 | Jennifer Reeves | Review | WPED I-WP103 - Accounting Entry Inventory - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/2/23 | Thu 6/15/23 | 1485 | 1487 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7043 | 1487 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | WPED I-WP103 - Accounting Entry Inventory - Approve | 0 hrs | 0 days | Thu 6/15/23 | Thu 6/15/23 | 1486 | 1496FS+37 days |  | Jimmy Cox
7044 | 1488 | Future Task |  |  | I-WP103 | Jennifer Reeves | Submit | WP I-WP103 - Accounting Entry Inventory - Submit | 0 hrs | 0 days | Mon 6/10/24 | Mon 6/10/24 | 152715001503 | 1489 |  | Jennifer Grant,Jennifer Reeves
7045 | 1489 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP I-WP103 - Accounting Entry Inventory - Department QC | 1 hr | 1 day | Tue 6/11/24 | Tue 6/11/24 | 1488 | 1490 |  | Gabriela Gibson
7046 | 1490 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP I-WP103 - Accounting Entry Inventory - Collaborative Review & Update | 10 hrs | 10 days | Wed 6/12/24 | Tue 6/25/24 | 1489 | 1491 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7047 | 1491 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP I-WP103 - Accounting Entry Inventory - Style Guide Review | 1 hr | 1 day | Wed 6/26/24 | Wed 6/26/24 | 1490 | 1492 |  | Tatiana Eubanks
7048 | 1492 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP I-WP103 - Accounting Entry Inventory - Final Review & Update | 2 hrs | 5 days | Thu 6/27/24 | Wed 7/3/24 | 14911524 | 1493 |  | Angie Robertson,Jimmy Cox
7049 | 1493 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | WP I-WP103 - Accounting Entry Inventory - Approve | 0 hrs | 0 days | Wed 7/3/24 | Wed 7/3/24 | 1492 |  |  | Jimmy Cox
7050 | 1494 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | Accounting Entry Inventory | 237 hrs | 216 days | Wed 8/9/23 | Mon 6/17/24
7051 | 1495 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 1 | 48 hrs | 37 days | Wed 8/9/23 | Fri 9/29/23
7052 | 1496 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Accounting Entry Inventory Format | 10 hrs | 5 days | Wed 8/9/23 | Tue 8/15/23 | 1487FS+37 days | 1497 |  | Jennifer Reeves,Daylin Reyes
7053 | 1497 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory Format | 10 hrs | 6 days | Wed 8/16/23 | Wed 8/23/23 | 1496 | 1498 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7054 | 1498 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory Format | 10 hrs | 5 days | Thu 8/24/23 | Wed 8/30/23 | 1497 | 1499 |  | Jimmy Cox
7055 | 1499 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 16 days | Thu 8/31/23 | Fri 9/22/23 | 1498,42 | 1500 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7056 | 1500 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Mon 9/25/23 | Fri 9/29/23 | 1499 | 1488 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7057 | 1501 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 2 | 18 hrs | 20 days | Tue 10/24/23 | Tue 11/21/23
7058 | 1502 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | Tue 10/24/23 | Tue 11/14/23 | 61 | 1503 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7059 | 1503 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Wed 11/15/23 | Tue 11/21/23 | 1502 | 1488 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7060 | 1504 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 3 | 28 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
7061 | 1505 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 141SS | 15061512 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7062 | 1506 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1505 | 1507 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7063 | 1507 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Functional Teams | 10 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1506 | 1509 |  | Brendan Jones,Janice Jackson,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7064 | 1508 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Update & Publish Accounting Entry Inventory | 54 hrs | 25 days | Fri 2/2/24 | Thu 3/7/24
7065 | 1509 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1507 | 1510 |  | Jennifer Reeves,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson
7066 | 1510 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory | 2 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1509 | 1511 |  | Jimmy Cox
7067 | 1511 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Coordinate Knowledge Base Update | 10 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1510 | 1524 |  | Jennifer Reeves,Daylin Reyes
7068 | 1512 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1505 | 1513 |  | Jennifer Grant,Jennifer Reeves
7069 | 1513 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review for Communication for Accounting Entry Inventory | 10 hrs | 9 days | Fri 2/9/24 | Wed 2/21/24 | 1512 | 1514 |  | Dusti Kincl,Angie Robertson
7070 | 1514 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Thu 2/22/24 | Wed 2/28/24 | 1513 | 1515 |  | Jimmy Cox
7071 | 1515 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Publish - Accounting Entry Inventory | 1 hr | 2 days | Thu 2/29/24 | Fri 3/1/24 | 1514 | 1516 |  | Pradeep Koul,Richard Saltford,Daylin Reyes,Dusti Kincl
7072 | 1516 | Future Task |  | RW-Communication | I-WP103 | Jennifer Reeves | Create | I-WP103 Share - Communication for Accounting Entry Inventory | 1 hr | 2 days | Mon 3/4/24 | Tue 3/5/24 | 1515 | 1518 |  | Dusti Kincl
7073 | 1517 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 4 | 28 hrs | 25 days | Mon 4/22/24 | Fri 5/24/24
7074 | 1518 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | Mon 4/22/24 | Fri 5/10/24 | 160SS,1516 | 15191525 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7075 | 1519 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1518 | 1520 |  | Matthew Breeding,Jennifer Reeves
7076 | 1520 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Functional Teams | 10 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1519 | 1522 |  | Brendan Jones,Janice Jackson,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7077 | 1521 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Update & Publish Accounting Entry Inventory | 61 hrs | 25 days | Mon 5/13/24 | Mon 6/17/24
7078 | 1522 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory | 10 hrs | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1520 | 1523 |  | Jennifer Reeves,Matthew Breeding,Deana Metcalf
7079 | 1523 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory | 10 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1522 | 1524 |  | Jimmy Cox,Angie Robertson
7080 | 1524 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Coordinate Knowledge Base Update | 10 hrs | 5 days | Tue 6/11/24 | Mon 6/17/24 | 15231511 | 1492 |  | Jennifer Reeves,Daylin Reyes
7081 | 1525 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1518 | 1526 |  | Jennifer Grant,Jennifer Reeves
7082 | 1526 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Communication for Accounting Entry Inventory | 10 hrs | 10 days | Mon 5/20/24 | Mon 6/3/24 | 1525 | 1527 |  | Dusti Kincl,Angie Robertson
7083 | 1527 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1526 | 14881528 |  | Jennifer Grant,Jennifer Reeves
7084 | 1528 | Future Task |  | RW-Communication | I-WP103 | Jennifer Reeves | Create | I-WP103 Share Communication for Accounting Entry Inventory | 1 hr | 2 days | Tue 6/11/24 | Wed 6/12/24 | 1527 |  |  | Dusti Kincl
7085 | 1529 | On Schedule |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 - Error Matrix | 113 hrs | 287 days | Thu 5/18/23 | Mon 7/8/24
7086 | 1530 | Complete |  |  | I-WP104 | Jennifer Reeves | Create | WPED I-WP104 - Error Matrix - Create | 9 hrs | 10 days | Thu 5/18/23 | Thu 6/1/23 | 1 | 1531 |  | Jennifer Grant,Jennifer Reeves
7087 | 1531 | Complete |  |  | I-WP104 | Jennifer Reeves | Submit | WPED I-WP104 - Error Matrix - Submit | 0 hrs | 0 days | Thu 6/1/23 | Thu 6/1/23 | 1530 | 1532 |  | Jennifer Grant,Jennifer Reeves
7088 | 1532 | On Schedule |  |  | I-WP104 | Jennifer Reeves | Review | WPED I-WP104 - Error Matrix - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/2/23 | Thu 6/15/23 | 1531 | 15331541 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7089 | 1533 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | WPED I-WP104 - Error Matrix - Approve | 0 hrs | 0 days | Thu 6/15/23 | Thu 6/15/23 | 1532 | 1541 |  | Jimmy Cox
7090 | 1534 | Future Task |  |  | I-WP104 | Jennifer Reeves | Submit | WP I-WP104 - Error Matrix - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 15721573 | 1535 |  | Jennifer Grant,Jennifer Reeves
7091 | 1535 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP I-WP104 - Error Matrix - Department QC | 1 hr | 1 day | Thu 6/13/24 | Thu 6/13/24 | 1534 | 1536 |  | Gabriela Gibson
7092 | 1536 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP I-WP104 - Error Matrix - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1535 | 1537 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7093 | 1537 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP I-WP104 - Error Matrix - Style Guide Review | 1 hr | 1 day | Fri 6/28/24 | Fri 6/28/24 | 1536 | 1538 |  | Tatiana Eubanks
7094 | 1538 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP I-WP104 - Error Matrix - Final Review & Update | 2 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 15371569 | 1539 |  | Angie Robertson,Jimmy Cox
7095 | 1539 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | WP I-WP104 - Error Matrix - Approve | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1538 |  |  | Jimmy Cox
7096 | 1540 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 1 | 15 hrs | 62 days | Fri 6/16/23 | Wed 9/13/23
7097 | 1541 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Error Matrix Format | 2 hrs | 5 days | Fri 6/16/23 | Thu 6/22/23 | 15321533 | 1542 |  | Jennifer Reeves,Daylin Reyes
7098 | 1542 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 5 hrs | 5 days | Fri 6/23/23 | Thu 6/29/23 | 1541 | 1543 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7099 | 1543 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix Format | 1 hr | 5 days | Fri 6/30/23 | Fri 7/7/23 | 1542 | 1544 |  | Jimmy Cox
7100 | 1544 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Wed 8/2/23 | Tue 8/22/23 | 1543,42 | 1545 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7101 | 1545 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 15 days | Wed 8/23/23 | Wed 9/13/23 | 1544 | 1547 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7102 | 1546 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 2 | 7 hrs | 20 days | Tue 10/24/23 | Tue 11/21/23
7103 | 1547 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Tue 10/24/23 | Tue 11/14/23 | 611545 | 1548 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7104 | 1548 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | Wed 11/15/23 | Tue 11/21/23 | 1547 | 1550 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7105 | 1549 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 3 | 13 hrs | 25 days | Mon 1/29/24 | Fri 3/1/24
7106 | 1550 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Mon 1/29/24 | Fri 2/16/24 | 1411548 | 15511557 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7107 | 1551 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | Mon 2/19/24 | Fri 2/23/24 | 1550 | 1552 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7108 | 1552 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Functional Teams | 6 hrs | 5 days | Mon 2/26/24 | Fri 3/1/24 | 1551 | 1554 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7109 | 1553 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Update & Publish Error Matrix | 18 hrs | 25 days | Mon 2/19/24 | Fri 3/22/24
7110 | 1554 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 5 hrs | 5 days | Mon 3/4/24 | Fri 3/8/24 | 1552 | 1555 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7111 | 1555 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix | 1 hr | 5 days | Mon 3/11/24 | Fri 3/15/24 | 1554 | 1556 |  | Jimmy Cox
7112 | 1556 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Coordinate Knowledge Base Update | 2 hrs | 5 days | Mon 3/18/24 | Fri 3/22/24 | 1555 |  |  | Jennifer Reeves,Daylin Reyes
7113 | 1557 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Communication for Error Matrix | 2 hrs | 5 days | Mon 2/19/24 | Fri 2/23/24 | 1550 | 1558 |  | Jennifer Grant,Jennifer Reeves
7114 | 1558 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review for Communication for Error Matrix | 2 hrs | 9 days | Mon 2/26/24 | Thu 3/7/24 | 1557 | 1559 |  | Dusti Kincl,Angie Robertson
7115 | 1559 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Communication for Error Matrix | 1 hr | 5 days | Fri 3/8/24 | Thu 3/14/24 | 1558 | 1560 |  | Jimmy Cox
7116 | 1560 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Publish - Error Matrix | 4 hrs | 2 days | Fri 3/15/24 | Mon 3/18/24 | 1559 | 1561 |  | Pradeep Koul,Richard Saltford,Daylin Reyes,Dusti Kincl
7117 | 1561 | Future Task |  | RW-Communication | I-WP104 | Jennifer Reeves | Create | I-WP104 Share - Communication for Error Matrix | 1 hr | 2 days | Tue 3/19/24 | Wed 3/20/24 | 1560 | 1563 |  | Dusti Kincl
7118 | 1562 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 4 | 13 hrs | 25 days | Mon 4/22/24 | Fri 5/24/24
7119 | 1563 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Mon 4/22/24 | Fri 5/10/24 | 160SS,1561 | 15641570 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7120 | 1564 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1563 | 1565 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7121 | 1565 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Functional Teams | 6 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1564 | 1567 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7122 | 1566 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Update & Publish Error Matrix | 14 hrs | 25 days | Mon 5/13/24 | Mon 6/17/24
7123 | 1567 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 3 hrs | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1565 | 1568 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves
7124 | 1568 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix | 2 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1567 | 1569 |  | Angie Robertson,Jimmy Cox
7125 | 1569 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Coordinate Knowledge Base Update | 2 hrs | 5 days | Tue 6/11/24 | Mon 6/17/24 | 1568 | 1538 |  | Jennifer Reeves,Daylin Reyes
7126 | 1570 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Task Instructions & Communication for Error Matrix | 2 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1563 | 1571 |  | Jennifer Reeves,Nikki Klein
7127 | 1571 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Communication for Error Matrix | 2 hrs | 10 days | Mon 5/20/24 | Mon 6/3/24 | 1570 | 1572 |  | Dusti Kincl,Angie Robertson
7128 | 1572 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Task Instructions & Communication for Error Matrix | 2 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1571 | 15341573 |  | Jennifer Grant,Jennifer Reeves
7129 | 1573 | Future Task |  | RW-Communication | I-WP104 | Jennifer Reeves | Create | I-WP104 Share Communication for Error Matrix | 1 hr | 2 days | Tue 6/11/24 | Wed 6/12/24 | 1572 | 1534 |  | Dusti Kincl
6862 | 1574 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 - Reports Catalogs | 239 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6863 | 1575 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 - Report Catalog | 16 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6864 | 1576 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | WPED I-WP105 - Report Catalog - Create | 2 hrs | 10 days | Fri 6/9/23 | Thu 6/22/23 | 1 | 1577 |  | Jennifer Grant,Jennifer Reeves
6865 | 1577 | Future Task |  |  | I-WP105 | Jennifer Reeves | Submit | WPED I-WP105 - Report Catalog - Submit | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 1576 | 1578 |  | Jennifer Grant,Jennifer Reeves
6866 | 1578 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WPED I-WP105 - Report Catalog - Collaborative Review & Update | 8 hrs | 10 days | Fri 6/23/23 | Fri 7/7/23 | 1577 | 1579 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Reeves,Jennifer Grant
6867 | 1579 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | WPED I-WP105 - Report Catalog - Approve | 0 hrs | 0 days | Fri 7/7/23 | Fri 7/7/23 | 1578 | 1587 |  | Jimmy Cox
6868 | 1580 | Future Task |  |  | I-WP105 | Jennifer Reeves | Submit | WP I-WP105 - Report Catalog - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 16031616 | 1581 |  | Jennifer Grant,Jennifer Reeves
6869 | 1581 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP I-WP105 - Report Catalog - Department QC | 1 hr | 1 day | Thu 6/13/24 | Thu 6/13/24 | 1580 | 1582 |  | Jenifer Hartsfield
6870 | 1582 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP I-WP105 - Report Catalog - Collaborative Review & Update | 2 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1581 | 1583 |  | Jennifer Grant,Jennifer Reeves
6871 | 1583 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP I-WP105 - Report Catalog - Style Guide Review | 1 hr | 1 day | Fri 6/28/24 | Fri 6/28/24 | 1582 | 1584 |  | Tatiana Eubanks
6872 | 1584 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP I-WP105 - Report Catalog - Final Review & Update | 2 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 1583 | 1585 |  | Angie Robertson,Jimmy Cox
6873 | 1585 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | WP I-WP105 - Report Catalog - Approve | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1584 |  |  | Jimmy Cox
6874 | 1586 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 1 - Reports | 35 hrs | 20 days | Tue 7/18/23 | Mon 8/14/23
6875 | 1587 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | Tue 7/18/23 | Mon 8/7/23 | 42SS,1579 | 1588 |  | Pradeep Koul,Tanya McCarty,Stanton Beazley,Jennifer Reeves,Elizabeth Sargent
6876 | 1588 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | Tue 8/8/23 | Mon 8/14/23 | 1587 | 1590 |  | Jennifer Grant,Jennifer Reeves
6877 | 1589 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 2 - Reports | 35 hrs | 20 days | Mon 10/9/23 | Fri 11/3/23
6878 | 1590 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | Mon 10/9/23 | Fri 10/27/23 | 61SS,1588 | 1591 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6879 | 1591 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | Mon 10/30/23 | Fri 11/3/23 | 1590 | 1593 |  | Jennifer Grant,Jennifer Reeves
6880 | 1592 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 3 - Reports | 55 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
6881 | 1593 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 141SS,1591 | 1594 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6882 | 1594 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1593 | 15951601 |  | Jennifer Grant,Jennifer Reeves
6883 | 1595 | Future Task |  |  |  | Jennifer Reeves | Review | I-WP105 Collaborative Review - Functional Teams | 20 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1594 | 1597 |  | Jennifer Grant,Jennifer Reeves,Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
6884 | 1596 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Update & Publish Report Catalog | 41 hrs | 22 days | Fri 2/9/24 | Mon 3/11/24
6885 | 1597 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Report Catalog | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1595 | 1598 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6886 | 1598 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Report Catalog | 2 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1597 | 1599 |  | Jimmy Cox
6887 | 1599 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Coordinate Knowledge Base Update | 18 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1598 | 1600 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6888 | 1600 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Publish - Report Catalog | 4 hrs | 2 days | Fri 3/8/24 | Mon 3/11/24 | 1599 | 1606 |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6889 | 1601 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Create Communication for Report Catalog | 2 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1594 | 1602 |  | Jennifer Grant,Jennifer Reeves
6890 | 1602 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review for Communication | 3 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1601 | 1603 |  | Dusti Kincl,Angie Robertson,Jennifer Reeves
6891 | 1603 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Communication for Report Catalog | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1602 | 15801604 |  | Jimmy Cox
6892 | 1604 | Future Task |  | RW-Communication | I-WP105 | Jennifer Reeves | Create | I-WP105 Share Communication for Report Catalog | 1 hr | 2 days | Fri 3/1/24 | Mon 3/4/24 | 1603 | 1606 |  | Dusti Kincl
6893 | 1605 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 4 - Reports | 32 hrs | 27 days | Mon 4/22/24 | Wed 5/29/24
6894 | 1606 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 10 hrs | 16 days | Mon 4/22/24 | Mon 5/13/24 | 160SS,1604,1600 | 1607 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
6895 | 1607 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 2 hrs | 6 days | Tue 5/14/24 | Tue 5/21/24 | 1606 | 16081614 |  | Jennifer Grant,Jennifer Reeves
6896 | 1608 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Functional Teams | 20 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1607 | 1610 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6897 | 1609 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Update & Publish Report Catalog | 25 hrs | 22 days | Wed 5/22/24 | Fri 6/21/24
6898 | 1610 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Report Catalog | 10 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1608 | 1611 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6899 | 1611 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Report Catalog | 1 hr | 5 days | Thu 6/6/24 | Wed 6/12/24 | 1610 | 1612 |  | Jimmy Cox
6900 | 1612 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Coordinate Knowledge Base Update | 3 hrs | 5 days | Thu 6/13/24 | Wed 6/19/24 | 1611 | 1613 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6901 | 1613 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Publish - Report Catalog | 4 hrs | 2 days | Thu 6/20/24 | Fri 6/21/24 | 1612 |  |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6902 | 1614 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Create Communication for Report Catalog | 2 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1607 | 1615 |  | Jennifer Grant,Jennifer Reeves
6903 | 1615 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review for Communication | 3 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1614 | 1616 |  | Dusti Kincl,Angie Robertson,Jennifer Reeves
6904 | 1616 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Communication for Report Catalog | 1 hr | 5 days | Thu 6/6/24 | Wed 6/12/24 | 1615 | 15801617 |  | Jimmy Cox
6905 | 1617 | Future Task |  | RW-Communication | I-WP105 | Jennifer Reeves | Create | I-WP105 Share Communication for Report Catalog | 1 hr | 2 days | Thu 6/13/24 | Fri 6/14/24 | 1616 |  |  | Dusti Kincl
6953 | 1618 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 - Interface Catalog | 167 hrs | 265 days | Fri 6/9/23 | Wed 6/26/24
6954 | 1619 | Future Task |  |  | I-WP106 | Matt Breeding | Create | WPED I-WP106 - Interface Catalog - Create | 10 hrs | 10 days | Fri 6/9/23 | Thu 6/22/23 | 1 | 1620 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding
6955 | 1620 | Future Task |  |  | I-WP106 | Matt Breeding | Submit | WPED I-WP106 - Interface Catalog - Submit | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 1619 | 1621 |  | Matthew Breeding
6956 | 1621 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WPED I-WP106 - Interface Catalog - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/23/23 | Fri 7/7/23 | 1620 | 1622 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
6957 | 1622 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | WPED I-WP106 - Interface Catalog - Approve | 0 hrs | 0 days | Fri 7/7/23 | Fri 7/7/23 | 1621 | 1631 |  | Jimmy Cox
6958 | 1623 | Future Task |  |  | I-WP106 | Matt Breeding | Submit | WP I-WP106 - Interface Catalog - Submit | 0 hrs | 0 days | Mon 6/3/24 | Mon 6/3/24 | 1659 | 1624 |  | Matthew Breeding
6959 | 1624 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP I-WP106 - Interface Catalog - Department QC | 1 hr | 1 day | Tue 6/4/24 | Tue 6/4/24 | 1623 | 1625 |  | Gabriela Gibson
6960 | 1625 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP I-WP106 - Interface Catalog - Collaborative Review & Update | 10 hrs | 10 days | Wed 6/5/24 | Tue 6/18/24 | 1624 | 1626 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
6961 | 1626 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP I-WP106 - Interface Catalog - Style Guide Review | 2 hrs | 1 day | Wed 6/19/24 | Wed 6/19/24 | 1625 | 1627 |  | Tatiana Eubanks
6962 | 1627 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP I-WP106 - Interface Catalog - Final Review & Update | 10 hrs | 5 days | Thu 6/20/24 | Wed 6/26/24 | 1626 | 1628 |  | Angie Robertson,Jimmy Cox
6963 | 1628 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | WP I-WP106 - Interface Catalog - Approve | 0 hrs | 0 days | Wed 6/26/24 | Wed 6/26/24 | 1627 |  |  | Jimmy Cox
6964 | 1629 | Future Task |  |  | I-WP106 | Matt Breeding |  | Interface Catalog | 124 hrs | 229 days | Tue 7/18/23 | Wed 6/12/24
6965 | 1630 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 1 - Interfaces | 12 hrs | 20 days | Tue 7/18/23 | Mon 8/14/23
6966 | 1631 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Tue 7/18/23 | Mon 8/7/23 | 42SS,1622 | 1632 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6967 | 1632 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Tue 8/8/23 | Mon 8/14/23 | 1631 | 1634 |  | Matthew Breeding
6968 | 1633 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 2 - Interfaces | 12 hrs | 20 days | Wed 10/11/23 | Tue 11/7/23
6969 | 1634 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Wed 10/11/23 | Tue 10/31/23 | 61SS+2 days,1632 | 1635 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6970 | 1635 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Wed 11/1/23 | Tue 11/7/23 | 1634 | 1637 |  | Matthew Breeding
6971 | 1636 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 3 - Interfaces | 22 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
6972 | 1637 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 141SS,1635 | 1638 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6973 | 1638 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1637 | 16391645 |  | Matthew Breeding
6974 | 1639 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Functional Teams | 10 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1638 | 1641 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
6975 | 1640 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Update & Publish Interface Catalog | 45 hrs | 24 days | Fri 2/9/24 | Wed 3/13/24
6976 | 1641 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Interface Catalog | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1639 | 1642 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6977 | 1642 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Interface Catalog | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1641 | 1643 |  | Jimmy Cox
6978 | 1643 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Coordinate Knowledge Base Update | 10 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1642 | 1644 |  | Matthew Breeding,Daylin Reyes
6979 | 1644 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Publish - Interface Catalog | 10 hrs | 2 days | Fri 3/8/24 | Mon 3/11/24 | 1643 | 1648 |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
6980 | 1645 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Create Communication for Interface Catalog | 2 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1638 | 1646 |  | Matthew Breeding,Dusti Kincl
6981 | 1646 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review for Communication for Interface Catalog | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1645 | 1647 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6982 | 1647 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Communication for Interface Catalog | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1646 | 1648 |  | Jimmy Cox
6983 | 1648 | Future Task |  | RW-Communication | I-WP106 | Matt Breeding | Create | I-WP106 Share Communication for Interface Catalog | 1 hr | 2 days | Tue 3/12/24 | Wed 3/13/24 | 16441647 | 1650 |  | Dusti Kincl
6984 | 1649 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 4 - Interfaces | 12 hrs | 20 days | Mon 4/22/24 | Fri 5/17/24
6985 | 1650 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Mon 4/22/24 | Fri 5/10/24 | 160SS,1648 | 16511657 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6986 | 1651 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1650 | 1653 |  | Matthew Breeding
6987 | 1652 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Update & Publish Interface Catalog | 21 hrs | 22 days | Mon 5/13/24 | Wed 6/12/24
6988 | 1653 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Interface Catalog | 10 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1651 | 1654 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6989 | 1654 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Interface Catalog | 1 hr | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1653 | 1655 |  | Jimmy Cox
6990 | 1655 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Coordinate Knowledge Base Update | 2 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1654 | 1656 |  | Matthew Breeding,Daylin Reyes
6991 | 1656 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Publish Interface Catalog | 1 hr | 2 days | Tue 6/11/24 | Wed 6/12/24 | 1655 |  |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
6992 | 1657 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Create Communication for Interface Catalog | 2 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1650 | 1658 |  | Matthew Breeding,Dusti Kincl
6993 | 1658 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review for Communication for Interface Catalog | 3 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1657 | 1659 |  | Dusti Kincl,Angie Robertson,Matthew Breeding
6994 | 1659 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Communication for Interface Catalog | 1 hr | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1658 | 16231660 |  | Jimmy Cox
6995 | 1660 | Future Task |  | RW-Communication | I-WP106 | Matt Breeding | Create | I-WP106 Share Communication for Interface Catalog | 1 hr | 2 days | Tue 6/4/24 | Wed 6/5/24 | 1659 | 799 |  | Dusti Kincl
6996 | 1661 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 - Conversions Inventory | 167 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6997 | 1662 | Future Task |  |  | I-WP107 | Matt Breeding | Create | WPED I-WP107 - Conversions Inventory - Create | 10 hrs | 10 days | Fri 6/9/23 | Thu 6/22/23 | 1 | 1663 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding
6998 | 1663 | Future Task |  |  | I-WP107 | Matt Breeding | Submit | WPED I-WP107 - Conversions Inventory - Submit | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 1662 | 1664 |  | Matthew Breeding
6999 | 1664 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WPED I-WP107 - Conversions Inventory - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/23/23 | Fri 7/7/23 | 1663 | 1665 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7000 | 1665 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | WPED I-WP107 - Conversions Inventory - Approve | 0 hrs | 0 days | Fri 7/7/23 | Fri 7/7/23 | 1664 | 1674 |  | Jimmy Cox
7001 | 1666 | Future Task |  |  | I-WP107 | Matt Breeding | Submit | WP I-WP107 - Conversions Inventory - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 1702 | 1667 |  | Matthew Breeding
7002 | 1667 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP I-WP107 - Conversions Inventory - Department QC | 1 hr | 1 day | Thu 6/13/24 | Thu 6/13/24 | 1666 | 1668 |  | Gabriela Gibson
7003 | 1668 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP I-WP107 - Conversions Inventory - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1667 | 1669 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7004 | 1669 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP I-WP107 - Conversions Inventory - Style Guide Review | 2 hrs | 1 day | Fri 6/28/24 | Fri 6/28/24 | 1668 | 1670 |  | Tatiana Eubanks
7005 | 1670 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP I-WP107 - Conversions Inventory - Final Review & Update | 10 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 1669 | 1671 |  | Angie Robertson,Jimmy Cox
7006 | 1671 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | WP I-WP107 - Conversions Inventory - Approve | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1670 |  |  | Jimmy Cox
7007 | 1672 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Conversions Inventory | 124 hrs | 234 days | Tue 7/18/23 | Wed 6/19/24
7008 | 1673 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment I - Conversions | 11 hrs | 20 days | Tue 7/18/23 | Mon 8/14/23
7009 | 1674 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | Tue 7/18/23 | Mon 8/7/23 | 42SS,1665 | 1675 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7010 | 1675 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 1 hr | 5 days | Tue 8/8/23 | Mon 8/14/23 | 1674 | 1677 |  | Matthew Breeding
7011 | 1676 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment II - Conversions | 15 hrs | 20 days | Mon 10/16/23 | Mon 11/13/23
7012 | 1677 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | Mon 10/16/23 | Fri 11/3/23 | 61SS+5 days,1675 | 1678 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7013 | 1678 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 5 hrs | 5 days | Mon 11/6/23 | Mon 11/13/23 | 1677 | 1680 |  | Matthew Breeding
7014 | 1679 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment III - Conversions | 25 hrs | 25 days | Fri 1/19/24 | Thu 2/22/24
7015 | 1680 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | Fri 1/19/24 | Thu 2/8/24 | 141SS+5 days,1678 | 1681 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7016 | 1681 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 5 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1680 | 16821688 |  | Matthew Breeding
7017 | 1682 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Functional Teams | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1681 | 1684 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
7018 | 1683 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Update & Publish Conversion Catalog | 26 hrs | 27 days | Fri 2/16/24 | Mon 3/25/24
7019 | 1684 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Conversion Catalog | 10 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1682 | 1685 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7020 | 1685 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Conversion Catalog | 1 hr | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1684 | 1686 |  | Jimmy Cox
7021 | 1686 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Coordinate Knowledge Base Update | 2 hrs | 5 days | Fri 3/8/24 | Thu 3/14/24 | 1685 | 1687 |  | Matthew Breeding,Daylin Reyes
7022 | 1687 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Publish - Conversion Catalog | 4 hrs | 5 days | Fri 3/15/24 | Thu 3/21/24 | 1686 | 1691 |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
7023 | 1688 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create Communication for Conversion Catalog | 2 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1681 | 1689 |  | Matthew Breeding,Dusti Kincl
7024 | 1689 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review for Communication for Conversion Catalog | 5 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1688 | 1690 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7025 | 1690 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Communication | 1 hr | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1689 | 1691 |  | Jimmy Cox
7026 | 1691 | Future Task |  | RW-Communication | I-WP107 | Matt Breeding | Create | I-WP107 Share Communication | 1 hr | 2 days | Fri 3/22/24 | Mon 3/25/24 | 16871690 | 1693 |  | Dusti Kincl
7027 | 1692 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment IV - Conversions | 15 hrs | 25 days | Mon 4/29/24 | Mon 6/3/24
7028 | 1693 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create & Maintain - Conversion Catalog | 10 hrs | 15 days | Mon 4/29/24 | Fri 5/17/24 | 160SS+5 days,1691 | 1694 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7029 | 1694 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 1 hr | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1693 | 16951700 |  | Matthew Breeding
7030 | 1695 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Functional Teams | 4 hrs | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1694 | 1697 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
7031 | 1696 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Update & Publish Conversions Catalog | 32 hrs | 17 days | Tue 5/28/24 | Wed 6/19/24
7032 | 1697 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Conversion Catalog | 10 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1695 | 1698 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7033 | 1698 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Conversion Catalog | 1 hr | 5 days | Tue 6/11/24 | Mon 6/17/24 | 1697 | 1699 |  | Jimmy Cox
7034 | 1699 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Publish - Conversion Catalog | 4 hrs | 2 days | Tue 6/18/24 | Wed 6/19/24 | 1698 | 630 |  | Daylin Reyes,Richard Saltford,Pradeep Koul,Dusti Kincl
7035 | 1700 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create Communication for Conversions Catalog | 3 hrs | 2 days | Tue 5/28/24 | Wed 5/29/24 | 1694 | 1701 |  | Dusti Kincl,Pradeep Koul,Richard Barnes
7036 | 1701 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review for Communication for Conversions Catalog | 10 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1700 | 1702 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Nikki Klein,Daylin Reyes,Jennifer Grant
7037 | 1702 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Communication | 3 hrs | 5 days | Thu 6/6/24 | Wed 6/12/24 | 1701 | 16661703 |  | Dusti Kincl,Angie Robertson,Matthew Breeding
7038 | 1703 | Future Task |  | RW-Communication | I-WP107 | Matt Breeding | Create | I-WP107 Share Communication for Conversions Catalog | 1 hr | 5 days | Thu 6/13/24 | Wed 6/19/24 | 1702 | 630 |  | Jimmy Cox
2973 | 1704 | On Schedule |  |  | I-WP108 | Kimberly Kemp |  | I-WP108 - Training Curriculum | 53 hrs | 360 days | Thu 6/1/23 | Thu 10/31/24
2974 | 1705 | On Schedule |  |  | I-WP108 | Carolyn Hicks | Create | WPED I-WP108 - Training Curriculum - Create | 10 hrs | 10 days | Thu 6/1/23 | Wed 6/14/23 | 1 | 1706 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
2975 | 1706 | Future Task |  |  | I-WP108 | Carolyn Hicks | Submit | WPED I-WP108 - Training Curriculum - Submit | 0 hrs | 0 days | Wed 6/14/23 | Wed 6/14/23 | 1705 | 1707 |  | Carolyn Hicks
2976 | 1707 | Future Task |  |  | I-WP108 | Carolyn Hicks | Review | WPED I-WP108 - Training Curriculum - Collaborative Review & Update | 10 hrs | 10 days | Thu 6/15/23 | Wed 6/28/23 | 1706 | 1708 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
2977 | 1708 | Future Task |  |  | I-WP108 | Carolyn Hicks | Approve | WPED I-WP108 - Training Curriculum - Approve | 0 hrs | 0 days | Wed 6/28/23 | Wed 6/28/23 | 1707 | 1709 |  | Angie Robertson,Jimmy Cox
5689 | 1709 | Future Task |  |  | I-WP108 | Kimberly Kemp | Create | I-WP108 Training Curriculum <Activities per WPED> | 10 hrs | 287 days | Mon 8/21/23 | Tue 10/8/24 | 1708,48 | 1710,1721SS+30 days |  | Kimberly Kemp
2978 | 1710 | Future Task |  |  | I-WP108 | Kimberly Kemp | Submit | WP I-WP108 - Training Curriculum - Submit | 0 hrs | 0 days | Tue 10/8/24 | Tue 10/8/24 | 1709 | 1711 |  | Kimberly Kemp
2979 | 1711 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | WP I-WP108 - Training Curriculum - Department QC | 1 hr | 1 day | Wed 10/9/24 | Wed 10/9/24 | 1710 | 1712 |  | Tommy Werner
2980 | 1712 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | WP I-WP108 - Training Curriculum - Collaborative Review & Update | 10 hrs | 10 days | Thu 10/10/24 | Wed 10/23/24 | 1711 | 1713 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
2981 | 1713 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | WP I-WP108 - Training Curriculum - Style Guide Review | 2 hrs | 1 day | Thu 10/24/24 | Thu 10/24/24 | 1712 | 1714 |  | Dusti Kincl
2982 | 1714 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | WP I-WP108 - Training Curriculum - Final Review & Update | 10 hrs | 5 days | Fri 10/25/24 | Thu 10/31/24 | 1713 | 1715 |  | Angie Robertson,Jimmy Cox
2983 | 1715 | Future Task |  | RW | I-WP108 | Kimberly Kemp | Approve | WP I-WP108 - Training Curriculum - Approve | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 1714 | 1721 |  | Jimmy Cox
2984 | 1716 | Future Task |  |  | I-WP109 | Kimberly Kemp |  | I-WP109 - Training Designs | 96 hrs | 567 days | Mon 7/3/23 | Tue 9/30/25
2985 | 1717 | Future Task |  |  | I-WP109 | Carolyn Hicks | Create | WPED I-WP109 - Training Designs - Create | 10 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 1 | 1718 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila
2986 | 1718 | Future Task |  |  | I-WP109 | Carolyn Hicks | Submit | WPED I-WP109 - Training Designs - Submit | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 1717 | 1719 |  | Carolyn Hicks
2987 | 1719 | Future Task |  |  | I-WP109 | Carolyn Hicks | Review | WPED I-WP109 - Training Designs - Collaborative Review & Update | 10 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 1718 | 1720 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
2988 | 1720 | Future Task |  |  | I-WP109 | Carolyn Hicks | Approve | WPED I-WP109 - Training Designs - Approve | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 1719 | 1721 |  | Angie Robertson,Jimmy Cox
5690 | 1721 | Future Task |  |  | I-WP109 | Kimberly Kemp | Create | I-WP109 Training Designs <Activities per WPED> | 40 hrs | 212 days | Fri 11/1/24 | Fri 9/5/25 | 1720,1709SS+30 days,1715 | 1722,1733SS |  | Kimberly Kemp
2989 | 1722 | Future Task |  |  | I-WP109 | Kimberly Kemp | Submit | WP I-WP109 - Training Designs - Submit | 0 hrs | 0 days | Fri 9/5/25 | Fri 9/5/25 | 1721 | 1723 |  | Kimberly Kemp
2990 | 1723 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | WP I-WP109 - Training Designs - Department QC | 8 hrs | 1 day | Mon 9/8/25 | Mon 9/8/25 | 1722 | 1724 |  | Gabriela Gibson
2991 | 1724 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | WP I-WP109 - Training Designs - Collaborative Review & Update | 10 hrs | 10 days | Tue 9/9/25 | Mon 9/22/25 | 1723 | 1725 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
2992 | 1725 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | WP I-WP109 - Training Designs - Style Guide Review | 8 hrs | 1 day | Tue 9/23/25 | Tue 9/23/25 | 1724 | 1726 |  | Tatiana Eubanks
2993 | 1726 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | WP I-WP109 - Training Designs - Final Review & Update | 10 hrs | 5 days | Wed 9/24/25 | Tue 9/30/25 | 1725 | 1727 |  | Angie Robertson,Jimmy Cox
2994 | 1727 | Future Task |  |  | I-WP109 | Kimberly Kemp | Approve | WP I-WP109 - Training Designs - Approve | 0 hrs | 0 days | Tue 9/30/25 | Tue 9/30/25 | 1726 |  |  | Jimmy Cox
2995 | 1728 | Future Task | Yes |  | I-WP110 | Kimberly Kemp |  | I-WP110 - Training Build | 156 hrs | 337 days | Fri 3/1/24 | Mon 6/30/25
2996 | 1729 | Future Task |  |  | I-WP110 | Carolyn Hicks | Create | WPED I-WP110 - Training Build - Create | 10 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 1 | 1730 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
2997 | 1730 | Future Task |  |  | I-WP110 | Carolyn Hicks | Submit | WPED I-WP110 - Training Build - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 1729 | 1731 |  | Carolyn Hicks
2998 | 1731 | Future Task |  |  | I-WP110 | Carolyn Hicks | Review | WPED I-WP110 - Training Build - Collaborative Review & Update | 10 hrs | 10 days | Fri 3/15/24 | Thu 3/28/24 | 1730 | 1732 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
2999 | 1732 | Future Task |  |  | I-WP110 | Carolyn Hicks | Approve | WPED I-WP110 - Training Build - Approve | 0 hrs | 0 days | Thu 3/28/24 | Thu 3/28/24 | 1731 | 1733 |  | Angie Robertson,Jimmy Cox
5691 | 1733 | Future Task |  |  | I-WP110 | Kimberly Kemp | Create | I-WP110 Training Build <Activities per WPED> | 100 hrs | 148 days | Fri 11/1/24 | Thu 6/5/25 | 1732,1721SS | 1734 |  | Kimberly Kemp
3000 | 1734 | Future Task |  |  | I-WP110 | Kimberly Kemp | Submit | WP I-WP110 - Training Build - Submit | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 1733 | 1735 |  | Kimberly Kemp
3001 | 1735 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | WP I-WP110 - Training Build - Department QC | 8 hrs | 1 day | Fri 6/6/25 | Fri 6/6/25 | 1734 | 1736 |  | Gabriela Gibson
3002 | 1736 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | WP I-WP110 - Training Build - Collaborative Review & Update | 10 hrs | 10 days | Mon 6/9/25 | Fri 6/20/25 | 1735 | 1737 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3003 | 1737 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | WP I-WP110 - Training Build - Style Guide Review | 8 hrs | 1 day | Mon 6/23/25 | Mon 6/23/25 | 1736 | 1738 |  | Tatiana Eubanks
3004 | 1738 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | WP I-WP110 - Training Build - Final Review & Update | 10 hrs | 5 days | Tue 6/24/25 | Mon 6/30/25 | 1737 | 1739 |  | Angie Robertson,Jimmy Cox
3005 | 1739 | Future Task |  |  | I-WP110 | Kimberly Kemp | Approve | WP I-WP110 - Training Build - Approve | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 1738 | 1779 |  | Jimmy Cox
3006 | 1740 | Future Task |  |  | I-WP111 | Kimberly Kemp |  | I-WP111 - UAT Training Materials | 129 hrs | 154 days | Thu 8/1/24 | Thu 3/13/25
3007 | 1741 | Future Task |  |  | I-WP111 | Carolyn Hicks | Create | WPED I-WP111 - UAT Training Materials - Create | 10 hrs | 10 days | Thu 8/1/24 | Wed 8/14/24 | 1 | 1742 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila
3008 | 1742 | Future Task |  |  | I-WP111 | Carolyn Hicks | Submit | WPEP I-WP111 - UAT Training Materials - Submit | 0 hrs | 0 days | Wed 8/14/24 | Wed 8/14/24 | 1741 | 1743 |  | Carolyn Hicks
3009 | 1743 | Future Task |  |  | I-WP111 | Carolyn Hicks | Review | WPED I-WP111 - UAT Training Materials - Collaborative Review & Update | 10 hrs | 10 days | Thu 8/15/24 | Wed 8/28/24 | 1742 | 1744 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
3010 | 1744 | Future Task |  |  | I-WP111 | Carolyn Hicks | Approve | WPED I-WP111 - UAT Training Materials - Approve | 0 hrs | 0 days | Wed 8/28/24 | Wed 8/28/24 | 1743 | 1745 |  | Angie Robertson,Jimmy Cox
5692 | 1745 | Future Task |  |  | I-WP111 | Kimberly Kemp | Create | I-WP111 UAT Training Materials <Activities per WPED> | 80 hrs | 117 days | Thu 8/29/24 | Tue 2/18/25 | 1744 | 1746 |  | Kimberly Kemp
3011 | 1746 | Future Task |  |  | I-WP111 | Kimberly Kemp | Submit | WP I-WP111 - UAT Training Materials - Submit | 0 hrs | 0 days | Tue 2/18/25 | Tue 2/18/25 | 1745 | 1747 |  | Kimberly Kemp
3012 | 1747 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | WP I-WP111 - UAT Training Materials - Department QC | 1 hr | 1 day | Wed 2/19/25 | Wed 2/19/25 | 1746 | 1748 |  | Tommy Werner
3013 | 1748 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | WP I-WP111 - UAT Training Materials - Collaborative Review & Update | 10 hrs | 10 days | Thu 2/20/25 | Wed 3/5/25 | 1747 | 1749 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3014 | 1749 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | WP I-WP111 - UAT Training Materials - Style Guide Review | 8 hrs | 1 day | Thu 3/6/25 | Thu 3/6/25 | 1748 | 1750 |  | Tatiana Eubanks
3015 | 1750 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | WP I-WP111 - UAT Training Materials - Final Review & Update | 10 hrs | 5 days | Fri 3/7/25 | Thu 3/13/25 | 1749 | 1751 |  | Angie Robertson,Jimmy Cox
3016 | 1751 | Future Task |  |  | I-WP111 | Kimberly Kemp | Approve | WP I-WP111 - UAT Training Materials - Approve | 0 hrs | 0 days | Thu 3/13/25 | Thu 3/13/25 | 1750 | 1752 |  | Jimmy Cox
3017 | 1752 | Future Task |  |  | I-WP111 | Kimberly Kemp | Milestone | WP I-WP111 - UAT Training Materials - Complete | 0 hrs | 0 days | Thu 3/13/25 | Thu 3/13/25 | 1751 | 1274 |  | Kimberly Kemp
3018 | 1753 | Future Task |  | RW | I-WP112 | Kimberly Kemp |  | I-WP112 - End User Manual | 143 hrs | 210 days | Fri 1/31/25 | Wed 11/26/25
3019 | 1754 | Future Task |  |  | I-WP112 | Carolyn Hicks | Create | WPED I-WP112 - End User Manual - Create | 10 hrs | 10 days | Fri 1/31/25 | Thu 2/13/25 | 1 | 1755 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3020 | 1755 | Future Task |  |  | I-WP112 | Carolyn Hicks | Submit | WPED I-WP112 - End User Manual - Submit | 0 hrs | 0 days | Thu 2/13/25 | Thu 2/13/25 | 1754 | 1756 |  | Carolyn Hicks
3021 | 1756 | Future Task |  |  | I-WP112 | Carolyn Hicks | Review | WPED I-WP112 - End User Manual - Collaborative Review & Update | 10 hrs | 10 days | Fri 2/14/25 | Thu 2/27/25 | 1755 | 1757 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3022 | 1757 | Future Task |  |  | I-WP112 | Carolyn Hicks | Approve | WPED I-WP112 - End User Manual - Approve | 0 hrs | 0 days | Thu 2/27/25 | Thu 2/27/25 | 1756 | 1758 |  | Angie Robertson,Jimmy Cox
5693 | 1758 | Future Task |  |  | I-WP112 | Kimberly Kemp | Create | I-WP112 End User Manual <Activities per WPED> | 100 hrs | 173 days | Fri 2/28/25 | Fri 10/31/25 | 1757652 | 1759 |  | Kimberly Kemp
3023 | 1759 | Future Task |  |  | I-WP112 | Kimberly Kemp | Submit | WP I-WP112 - End User Manual - Submit | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 1758 | 1760 |  | Kimberly Kemp
3024 | 1760 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | WP I-WP112 - End User Manual - Department QC | 1 hr | 1 day | Mon 11/3/25 | Mon 11/3/25 | 1759 | 1761 |  | Tommy Werner
3025 | 1761 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | WP I-WP112 - End User Manual - Collaborative Review & Update | 10 hrs | 10 days | Tue 11/4/25 | Tue 11/18/25 | 1760 | 1762 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3026 | 1762 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | WP I-WP112 - End User Manual - Style Guide Review | 2 hrs | 1 day | Wed 11/19/25 | Wed 11/19/25 | 1761 | 1763 |  | Tatiana Eubanks
3027 | 1763 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | WP I-WP112 - End User Manual - Final Review & Update | 10 hrs | 5 days | Thu 11/20/25 | Wed 11/26/25 | 1762 | 1764 |  | Angie Robertson,Jimmy Cox
3028 | 1764 | Future Task |  |  | I-WP112 | Kimberly Kemp | Approve | WP I-WP112 - End User Manual - Approve | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 1763 | 1765 |  | Jimmy Cox
3029 | 1765 | Future Task |  |  | I-WP112 | Kimberly Kemp | Milestone | WP I-WP112 - End User Manual - Complete | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 1764 | 1385 |  | Kimberly Kemp
3030 | 1766 | Future Task |  |  | I-WP113 | Kimberly Kemp |  | I-WP113 - ILT Training Delivery Plan | 156 hrs | 85 days | Fri 3/1/24 | Fri 6/28/24
3031 | 1767 | Future Task |  |  | I-WP113 | Carolyn Hicks | Create | WPED I-WP113 - ILT Training Delivery Plan - Create | 10 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 18261838 | 1768 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
3032 | 1768 | Future Task |  |  | I-WP113 | Carolyn Hicks | Submit | WPED I-WP113 - ILT Training Delivery Plan - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 1767 | 1769 |  | Carolyn Hicks
3033 | 1769 | Future Task |  |  | I-WP113 | Carolyn Hicks | Review | WPED I-WP113 - ILT Training Delivery Plan - Collaborative Review & Update | 10 hrs | 10 days | Fri 3/15/24 | Thu 3/28/24 | 1768 | 1770 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
3034 | 1770 | Future Task |  |  | I-WP113 | Carolyn Hicks | Approve | WPED I-WP113- ILT Training Delivery Plan - Approve | 0 hrs | 0 days | Thu 3/28/24 | Thu 3/28/24 | 1769 | 1771 |  | Angie Robertson,Jimmy Cox
5694 | 1771 | Future Task |  |  | I-WP113 | Kimberly Kemp | Create | I-WP113 ILT Training Delivery Plan <Activities per WPED> | 100 hrs | 48 days | Fri 3/29/24 | Wed 6/5/24 | 1770 | 1772 |  | Kimberly Kemp
3035 | 1772 | Future Task |  |  | I-WP113 | Kimberly Kemp | Submit | WP I-WP113 - ILT Training Delivery Plan - Submit | 0 hrs | 0 days | Wed 6/5/24 | Wed 6/5/24 | 1771 | 1773 |  | Kimberly Kemp
3036 | 1773 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | WP I-WP113 - ILT Training Delivery Plan - Department QC | 8 hrs | 1 day | Thu 6/6/24 | Thu 6/6/24 | 1772 | 1774 |  | Gabriela Gibson
3037 | 1774 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | WP I-WP113 - ILT Training Delivery Plan - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/7/24 | Thu 6/20/24 | 1773 | 1775 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3038 | 1775 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | WP I-WP113 - ILT Training Delivery Plan - Style Guide Review | 8 hrs | 1 day | Fri 6/21/24 | Fri 6/21/24 | 1774 | 1776 |  | Tatiana Eubanks
3039 | 1776 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | WP I-WP113 - ILT Training Delivery Plan - Final Review & Update | 10 hrs | 5 days | Mon 6/24/24 | Fri 6/28/24 | 1775 | 1777 |  | Angie Robertson,Jimmy Cox
3040 | 1777 | Future Task |  |  | I-WP113 | Kimberly Kemp | Approve | WP I-WP113 - ILT Training Delivery Plan - Approve | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 1776 | 1779 |  | Jimmy Cox
3041 | 1778 | Future Task |  |  | I-WP114 | Kimberly Kemp |  | I-WP114 - Training Measurement Report | 143 hrs | 104 days | Wed 10/29/25 | Tue 3/31/26
3042 | 1779 | Future Task |  |  | I-WP114 | Carolyn Hicks | Create | WPED I-WP114 - Training Measurement Report - Create | 10 hrs | 10 days | Wed 10/29/25 | Wed 11/12/25 | 177717391838 | 1780 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
3043 | 1780 | Future Task |  |  | I-WP114 | Kimberly Kemp | Submit | WPED I-WP114 - Training Measurement Report - Submit | 0 hrs | 0 days | Wed 11/12/25 | Wed 11/12/25 | 1779 | 1781 |  | Carolyn Hicks
3044 | 1781 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WPED I-WP114 - Training Measurement Report - Collaborative Review & Update | 10 hrs | 10 days | Thu 11/13/25 | Wed 11/26/25 | 1780 | 1782 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
3045 | 1782 | Future Task |  |  | I-WP114 | Kimberly Kemp | Approve | WPED I-WP114 - Training Measurement Report - Approve | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 1781 | 1783 |  | Angie Robertson,Jimmy Cox
5695 | 1783 | Future Task |  |  | I-WP114 | Kimberly Kemp | Create | I-WP114 Training Measurement Report <Activities per WPED> | 100 hrs | 67 days | Mon 12/1/25 | Fri 3/6/26 | 17821274 | 1784 |  | Kimberly Kemp
3046 | 1784 | Future Task |  |  | I-WP114 | Kimberly Kemp | Submit | WP I-WP114 - Training Measurement Report - Submit | 0 hrs | 0 days | Fri 3/6/26 | Fri 3/6/26 | 1783 | 1785 |  | Kimberly Kemp
3047 | 1785 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WP I-WP114 - Training Measurement Report - Department QC | 1 hr | 1 day | Mon 3/9/26 | Mon 3/9/26 | 1784 | 1786 |  | Tommy Werner
3048 | 1786 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WP I-WP114 - Training Measurement Report - Collaborative Review & Update | 10 hrs | 10 days | Tue 3/10/26 | Mon 3/23/26 | 1785 | 1787 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3049 | 1787 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WP I-WP114 - Training Measurement Report - Style Guide Review | 2 hrs | 1 day | Tue 3/24/26 | Tue 3/24/26 | 1786 | 1788 |  | Dusti Kincl
3050 | 1788 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WP I-WP114 - Training Measurement Report - Final Review & Update | 10 hrs | 5 days | Wed 3/25/26 | Tue 3/31/26 | 1787 | 1789 |  | Angie Robertson,Jimmy Cox
3051 | 1789 | Future Task |  |  | I-WP114 | Kimberly Kemp | Approve | WP I-WP114 - Training Measurement Report - Approve | 0 hrs | 0 days | Tue 3/31/26 | Tue 3/31/26 | 1788 |  |  | Jimmy Cox
3052 | 1790 | Future Task |  | RW | I-WP115 | Kimberly Kemp |  | I-WP115 - Train the Trainer | 504 hrs | 167 days | Tue 10/1/24 | Fri 5/30/25
3053 | 1791 | Future Task |  |  | I-WP115 | Carolyn Hicks | Create | WPED I-WP115 - Train the Trainer - Create | 10 hrs | 10 days | Tue 10/1/24 | Mon 10/14/24 | 1 | 1792 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila
3054 | 1792 | Future Task |  |  | I-WP115 | Carolyn Hicks | Submit | WPED I-WP115 - Train the Trainer - Submit | 0 hrs | 0 days | Mon 10/14/24 | Mon 10/14/24 | 1791 | 1793 |  | Carolyn Hicks
3055 | 1793 | Future Task |  |  | I-WP115 | Carolyn Hicks | Review | WPED I-WP115 - Train the Trainer - Collaborative Review & Update | 10 hrs | 10 days | Tue 10/15/24 | Mon 10/28/24 | 1792 | 1794 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
3056 | 1794 | Future Task |  |  | I-WP115 | Carolyn Hicks | Approve | WPED I-WP115 - Train the Trainer - Approve | 0 hrs | 0 days | Mon 10/28/24 | Mon 10/28/24 | 1793 | 1795FS+63 days |  | Angie Robertson,Jimmy Cox
5696 | 1795 | Future Task |  |  | I-WP115 | Kimberly Kemp | Create | I-WP115 Train the Trainer <Activities per WPED> | 448 hrs | 56 days | Mon 2/3/25 | Mon 4/21/25 | 1794FS+63 days | 1796FS+11 days |  | Kimberly Kemp
3057 | 1796 | Future Task |  |  | I-WP115 | Kimberly Kemp | Submit | WP I-WP115 - Train the Trainer - Submit | 0 hrs | 0 days | Tue 5/6/25 | Tue 5/6/25 | 1795FS+11 days | 1797 |  | Kimberly Kemp
3058 | 1797 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | WP I-WP115 - Train the Trainer - Department QC | 8 hrs | 1 day | Wed 5/7/25 | Wed 5/7/25 | 1796 | 1798 |  | Gabriela Gibson
3059 | 1798 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | WP I-WP115 - Train the Trainer - Collaborative Review & Update | 10 hrs | 10 days | Thu 5/8/25 | Wed 5/21/25 | 1797 | 1799 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3060 | 1799 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | WP I-WP115 - Train the Trainer - Style Guide Review | 8 hrs | 1 day | Thu 5/22/25 | Thu 5/22/25 | 1798 | 1800 |  | Tatiana Eubanks
3061 | 1800 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | WP I-WP115 - Train the Trainer - Final Review & Update | 10 hrs | 5 days | Fri 5/23/25 | Fri 5/30/25 | 1799 | 1801 |  | Angie Robertson,Jimmy Cox
3062 | 1801 | Future Task |  |  | I-WP115 | Kimberly Kemp | Approve | WP I-WP115 - Train the Trainer - Approve | 0 hrs | 0 days | Fri 5/30/25 | Fri 5/30/25 | 1800 | 1802 |  | Jimmy Cox
3063 | 1802 | Future Task |  |  | I-WP115 | Kimberly Kemp | Milestone | WP I-WP115 - Train the Trainer - Complete | 0 hrs | 0 days | Fri 5/30/25 | Fri 5/30/25 | 1801 |  |  | Kimberly Kemp
3087 | 1803 | Future Task |  | RW | I-WP116 | Kimberly Kemp |  | I-WP116 - User Support Sessions | 156 hrs | 209 days | Mon 6/2/25 | Tue 3/31/26
3088 | 1804 | Future Task |  |  | I-WP116 | Carolyn Hicks | Create | WPED I-WP116 - User Support Sessions - Create | 10 hrs | 10 days | Mon 6/2/25 | Fri 6/13/25 | 1 | 1805 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3089 | 1805 | Future Task |  |  | I-WP116 | Carolyn Hicks | Submit | WPED I-WP116 - User Support Sessions - Submit | 0 hrs | 0 days | Fri 6/13/25 | Fri 6/13/25 | 1804 | 1806 |  | Carolyn Hicks
3090 | 1806 | Future Task |  |  | I-WP116 | Carolyn Hicks | Review | WPED I-WP116 - User Support Sessions - Collaborative Review & Update | 10 hrs | 10 days | Mon 6/16/25 | Fri 6/27/25 | 1805 | 1807 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3091 | 1807 | Future Task |  |  | I-WP116 | Carolyn Hicks | Approve | WPED I-WP116 - User Support Sessions - Approve | 0 hrs | 0 days | Fri 6/27/25 | Fri 6/27/25 | 1806 | 1808 |  | Angie Robertson,Jimmy Cox
5699 | 1808 | Future Task |  |  | I-WP116 | Kimberly Kemp | Create | I-WP116 User Support Sessions <Activities per WPED> | 100 hrs | 172 days | Mon 6/30/25 | Fri 3/6/26 | 1807,1274SS+30 days | 1809 |  | Kimberly Kemp
3092 | 1809 | Future Task |  |  | I-WP116 | Kimberly Kemp | Submit | WP I-WP116 - User Support Sessions - Submit | 0 hrs | 0 days | Fri 3/6/26 | Fri 3/6/26 | 1808 | 1810 |  | Kimberly Kemp
3093 | 1810 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | WP I-WP116 - User Support Sessions - Department QC | 8 hrs | 1 day | Mon 3/9/26 | Mon 3/9/26 | 1809 | 1811 |  | Gabriela Gibson
3094 | 1811 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | WP I-WP116 - User Support Sessions - Collaborative Review & Update | 10 hrs | 10 days | Tue 3/10/26 | Mon 3/23/26 | 1810 | 1812 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3095 | 1812 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | WP I-WP116 - User Support Sessions - Style Guide Review | 8 hrs | 1 day | Tue 3/24/26 | Tue 3/24/26 | 1811 | 1813 |  | Tatiana Eubanks
3096 | 1813 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | WP I-WP116 - User Support Sessions - Final Review & Update | 10 hrs | 5 days | Wed 3/25/26 | Tue 3/31/26 | 1812 | 1814 |  | Angie Robertson,Jimmy Cox
3097 | 1814 | Future Task |  |  | I-WP116 | Kimberly Kemp | Approve | WP I-WP116 - User Support Sessions - Approve | 0 hrs | 0 days | Tue 3/31/26 | Tue 3/31/26 | 1813 |  |  | Jimmy Cox
3064 | 1815 | Future Task |  |  | I-WP122 | Carolyn Hicks |  | I-WP122 - Update D33 Training Strategy | 143 hrs | 81 days | Wed 11/1/23 | Thu 2/29/24
3065 | 1816 | Future Task |  |  | I-WP122 | Carolyn Hicks | Create | WPED I-WP122 - Update D33 Training Strategy - Create | 10 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23 | 1 | 1817,1828SS |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3066 | 1817 | Future Task |  |  | I-WP122 | Carolyn Hicks | Submit | WPED I-WP122 - Update D33 Training Strategy - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 1816 | 1818 |  | Carolyn Hicks
3067 | 1818 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WPED I-WP122 - Update D33 Training Strategy - Collaborative Review & Update | 10 hrs | 10 days | Thu 11/16/23 | Fri 12/1/23 | 1817 | 1819 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3068 | 1819 | Future Task |  |  | I-WP122 | Carolyn Hicks | Approve | WPED I-WP122 - Update D33 Training Strategy - Approve | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 1818 | 1820 |  | Angie Robertson,Jimmy Cox
5697 | 1820 | Future Task |  | RW | I-WP122 | Carolyn Hicks | Create | I-WP122 Update D33 Training Strategy <Activities per WPED> | 100 hrs | 44 days | Mon 12/4/23 | Tue 2/6/24 | 1819 | 1821 |  | Kimberly Kemp
3069 | 1821 | Future Task |  |  | I-WP122 | Carolyn Hicks | Submit | WP I-WP122 - Update D33 Training Strategy - Submit | 0 hrs | 0 days | Tue 2/6/24 | Tue 2/6/24 | 1820 | 1822 |  | Kimberly Kemp
3070 | 1822 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WP I-WP122 - Update D33 Training Strategy - Department QC | 1 hr | 1 day | Wed 2/7/24 | Wed 2/7/24 | 1821 | 1823 |  | Tommy Werner
3071 | 1823 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WP I-WP122 - Update D33 Training Strategy - Collaborative Review & Update | 10 hrs | 10 days | Thu 2/8/24 | Wed 2/21/24 | 1822 | 1824 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3072 | 1824 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WP I-WP122 - Update D33 Training Strategy - Style Guide Review | 2 hrs | 1 day | Thu 2/22/24 | Thu 2/22/24 | 1823 | 1825 |  | Dusti Kincl
3073 | 1825 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WP I-WP122 - Update D33 Training Strategy - Final Review & Update | 10 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1824 | 1826 |  | Angie Robertson,Jimmy Cox
3074 | 1826 | Future Task |  |  | I-WP122 | Carolyn Hicks | Approve | WP I-WP122 - Update D33 Training Strategy - Approve | 0 hrs | 0 days | Thu 2/29/24 | Thu 2/29/24 | 1825 | 1767 |  | Jimmy Cox
3075 | 1827 | Future Task |  |  | I-WP123 | Carolyn Hicks |  | I-WP123 - Update D112 Training Deployment and Measurement Plan | 149 hrs | 81 days | Wed 11/1/23 | Thu 2/29/24
3076 | 1828 | Future Task |  |  | I-WP123 | Carolyn Hicks | Create | WPED I-WP123 - Update D112 Training Deployment and Measurement Plan - Create | 10 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23 | 1816SS | 1829 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3077 | 1829 | Future Task |  |  | I-WP123 | Carolyn Hicks | Submit | WPED I-WP123 - Update D112 Training Deployment and Measurement Plan - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 1828 | 1830 |  | Carolyn Hicks
3078 | 1830 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WPED I-WP123 - Update D112 Training Deployment and Measurement Plan - Collaborative Review and Update | 10 hrs | 10 days | Thu 11/16/23 | Fri 12/1/23 | 1829 | 1831 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3079 | 1831 | Future Task |  |  | I-WP123 | Carolyn Hicks | Approve | WPED I-WP123 - Update D112 Training Deployment and Measurement Plan - Approve | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 1830 | 1832 |  | Angie Robertson,Jimmy Cox
5698 | 1832 | Future Task |  |  | I-WP123 | Carolyn Hicks | Create | I-WP123 Update D112 Training Deployment and Measurement Plan <Activities per WPED> | 100 hrs | 44 days | Mon 12/4/23 | Tue 2/6/24 | 1831 | 1833 |  | Kimberly Kemp
3080 | 1833 | Future Task |  |  | I-WP123 | Carolyn Hicks | Submit | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Submit | 0 hrs | 0 days | Tue 2/6/24 | Tue 2/6/24 | 1832 | 1834 |  | Kimberly Kemp
3081 | 1834 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Department QC | 1 hr | 1 day | Wed 2/7/24 | Wed 2/7/24 | 1833 | 1835 |  | Tommy Werner
3082 | 1835 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Collaborative Review & Update | 10 hrs | 10 days | Thu 2/8/24 | Wed 2/21/24 | 1834 | 1836 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3083 | 1836 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Style Guide Review | 8 hrs | 1 day | Thu 2/22/24 | Thu 2/22/24 | 1835 | 1837 |  | Tatiana Eubanks
3084 | 1837 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Final Review & Update | 10 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1836 | 1838 |  | Angie Robertson,Jimmy Cox
3085 | 1838 | Future Task |  |  | I-WP123 | Carolyn Hicks | Approve | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Approve | 0 hrs | 0 days | Thu 2/29/24 | Thu 2/29/24 | 1837 | 17671779 |  | Jimmy Cox
6812 | 1839 | Future Task | [5 empty] | Training | 1 hr | 104 days | Tue 7/1/25 | Wed 11/26/25
6813 | 1840 | Future Task |  | RW |  | Carolyn Hicks | Create | Conduct Training | 1 hr | 104 days | Tue 7/1/25 | Wed 11/26/25 | 1 |  | July - Nov 2025 | Carolyn Hicks
3086 | 1841 | Late | [5 empty] | Readiness | 1,433 hrs | 632 days | Mon 5/8/23 | Wed 11/5/25
7183 | 1842 | Future Task |  |  | SG4 | Jimmy Cox | Create | Stage Gate 4: Prepare Stage Gate Checklist | 6 hrs | 5 days | Thu 6/5/25 | Wed 6/11/25 |  | 1843 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7184 | 1843 | Future Task |  |  | SG4 | Jimmy Cox | Create | Stage Gate 4: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Thu 6/12/25 | Wed 6/25/25 | 1842 | 1844FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7185 | 1844 | Future Task |  |  | SG4 | Jimmy Cox | Create | Stage Gate 4: Prepare information package for ESC | 11 hrs | 10 days | Wed 10/15/25 | Tue 10/28/25 | 1843FS+77 days | 1845 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7186 | 1845 | Future Task |  |  | SG4 | Jimmy Cox | Create | Stage Gate 4: Collaborative Review and Update of information package | 11 hrs | 5 days | Wed 10/29/25 | Tue 11/4/25 | 1844 | 1846 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7187 | 1846 | Future Task |  |  | SG4 | Jimmy Cox | Create | Stage Gate 4: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 11/5/25 | Wed 11/5/25 | 1845 |  |  | Dusti Kincl
7159 | 1847 | Future Task |  |  | SG4 | Jimmy Cox | Milestone | Stage Gate 4: Agency Readiness | 0 hrs | 0 days | Mon 11/3/25 | Mon 11/3/25 | 1 |  | November 2025 - ESC | Executive Steering Committee
3098 | 1848 | Future Task |  |  | I-WP117 | Nikki Klein |  | I-WP117 - Role Mapping Handbook | 149 hrs | 193 days | Thu 2/1/24 | Thu 10/31/24
3099 | 1849 | Future Task |  |  | I-WP117 | Carolyn Hicks | Create | WPED I-WP117- Role Mapping Handbook - Create | 10 hrs | 10 days | Thu 2/1/24 | Wed 2/14/24 | 1 | 1850 |  | Carolyn Hicks,Nikki Klein,Felicia Hall
3100 | 1850 | Future Task |  |  | I-WP117 | Carolyn Hicks | Submit | WPED I-WP117 - Role Mapping Handbook - Submit | 0 hrs | 0 days | Wed 2/14/24 | Wed 2/14/24 | 1849 | 1851 |  | Carolyn Hicks
3101 | 1851 | Future Task |  |  | I-WP117 | Carolyn Hicks | Review | WPED I-WP117 - Role Mapping Handbook - Collaborative Review & Update | 10 hrs | 10 days | Thu 2/15/24 | Wed 2/28/24 | 1850 | 1852 |  | Carolyn Hicks,Nikki Klein,Felicia Hall,Angie Robertson
3102 | 1852 | Future Task |  |  | I-WP117 | Carolyn Hicks | Approve | WPED I-WP117 - Role Mapping Handbook - Approve | 0 hrs | 0 days | Wed 2/28/24 | Wed 2/28/24 | 1851 | 1853 |  | Angie Robertson,Jimmy Cox
5700 | 1853 | Future Task |  | RW | I-WP117 | Nikki Klein | Create | I-WP117 Role Mapping Handbook <Activities per WPED> | 100 hrs | 156 days | Thu 2/29/24 | Tue 10/8/24 | 1852110 | 1854,1865SS+40 days |  | Nikki Klein
3103 | 1854 | Future Task |  |  | I-WP117 | Nikki Klein | Submit | WP I-WP117 - Role Mapping Handbook - Submit | 0 hrs | 0 days | Tue 10/8/24 | Tue 10/8/24 | 1853 | 1855 |  | Nikki Klein
3104 | 1855 | Future Task |  |  | I-WP117 | Nikki Klein | Review | WP I-WP117 - Role Mapping Handbook - Department QC | 1 hr | 1 day | Wed 10/9/24 | Wed 10/9/24 | 1854 | 1856 |  | Gabriela Gibson
3105 | 1856 | Future Task |  |  | I-WP117 | Nikki Klein | Review | WP I-WP117 - Role Mapping Handbook - Collaborative Review & Update | 10 hrs | 10 days | Thu 10/10/24 | Wed 10/23/24 | 1855 | 1857 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3106 | 1857 | Future Task |  |  | I-WP117 | Nikki Klein | Review | WP I-WP117 - Role Mapping Handbook - Style Guide Review | 8 hrs | 1 day | Thu 10/24/24 | Thu 10/24/24 | 1856 | 1858 |  | Tatiana Eubanks
3107 | 1858 | Future Task |  |  | I-WP117 | Nikki Klein | Review | WP I-WP117 - Role Mapping Handbook - Final Review & Update | 10 hrs | 5 days | Fri 10/25/24 | Thu 10/31/24 | 1857 | 1859 |  | Angie Robertson,Jimmy Cox
3108 | 1859 | Future Task |  |  | I-WP117 | Nikki Klein | Approve | WP I-WP117 - Role Mapping Handbook - Approve | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 1858 |  |  | Jimmy Cox | Successor - Role Mapping Worksheet 118 | TW (open item)
3109 | 1860 | Future Task | Yes |  | I-WP118 | Nikki Klein |  | I-WP118 - Role Mapping Worksheet | 456 hrs | 135 days | Mon 6/3/24 | Fri 12/13/24
3110 | 1861 | Future Task |  |  | I-WP118 | Carolyn Hicks | Create | WPED I-WP118 - Role Mapping Worksheet - Create | 10 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 1 | 1862 |  | Carolyn Hicks,Nikki Klein,Felicia Hall
3111 | 1862 | Future Task |  |  | I-WP118 | Carolyn Hicks | Submit | WPED I-WP118 - Role Mapping Worksheet - Submit | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 1861 | 1863 |  | Carolyn Hicks
3112 | 1863 | Future Task |  |  | I-WP118 | Carolyn Hicks | Review | WPED I-WP118 - Role Mapping Worksheet - Collaborative Review & Update | 10 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 1862 | 1864 |  | Carolyn Hicks,Nikki Klein,Felicia Hall,Angie Robertson
3113 | 1864 | Future Task |  |  | I-WP118 | Carolyn Hicks | Approve | WPED I-WP118 - Role Mapping Worksheet - Approve | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 1863 | 1865 |  | Angie Robertson,Jimmy Cox
5701 | 1865 | Future Task |  | RW | I-WP118 | Nikki Klein | Create | I-WP118 Role Mapping Worksheet <Activities per WPED> | 400 hrs | 67 days | Wed 8/14/24 | Mon 11/18/24 | 1864,1853SS+40 days,579,1920SS+40 days | 1866 |  | Nikki Klein
3114 | 1866 | Future Task |  |  | I-WP118 | Nikki Klein | Submit | WP I-WP118 - Role Mapping Worksheet - Submit | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 1865 | 1867 |  | Nikki Klein
3115 | 1867 | Future Task |  |  | I-WP118 | Nikki Klein | Review | WP I-WP118 - Role Mapping Worksheet - Department QC | 8 hrs | 1 day | Tue 11/19/24 | Tue 11/19/24 | 1866 | 1868 |  | Gabriela Gibson
3116 | 1868 | Future Task |  |  | I-WP118 | Nikki Klein | Review | WP I-WP118 - Role Mapping Worksheet - Collaborative Review & Update | 10 hrs | 10 days | Wed 11/20/24 | Thu 12/5/24 | 1867 | 1869 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3117 | 1869 | Future Task |  |  | I-WP118 | Nikki Klein | Review | WP I-WP118 - Role Mapping Worksheet - Style Guide Review | 8 hrs | 1 day | Fri 12/6/24 | Fri 12/6/24 | 1868 | 1870 |  | Tatiana Eubanks
3118 | 1870 | Future Task |  |  | I-WP118 | Nikki Klein | Review | WP I-WP118 - Role Mapping Worksheet - Final Review & Update | 10 hrs | 5 days | Mon 12/9/24 | Fri 12/13/24 | 1869 | 1871 |  | Angie Robertson,Jimmy Cox
3119 | 1871 | Future Task |  |  | I-WP118 | Nikki Klein | Approve | WP I-WP118 - Role Mapping Worksheet - Approve | 0 hrs | 0 days | Fri 12/13/24 | Fri 12/13/24 | 1870 | 562561 |  | Jimmy Cox
3120 | 1872 | Future Task |  |  | I-WP119 | Nikki Klein |  | I-WP119 - Change Analysis Tool | 66 hrs | 188 days | Wed 11/1/23 | Wed 7/31/24
3121 | 1873 | Future Task |  |  | I-WP119 | Carolyn Hicks | Create | WPED I-WP119 - Change Analysis Tool - Create | 10 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23 | 1 | 1874 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas
3122 | 1874 | Future Task |  |  | I-WP119 | Carolyn Hicks | Submit | WPED I-WP119 - Change Analysis Tool - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 1873 | 1875 |  | Carolyn Hicks
3123 | 1875 | Future Task |  |  | I-WP119 | Carolyn Hicks | Review | WPED I-WP119 - Change Analysis Tool - Collaborative Review & Update | 10 hrs | 10 days | Thu 11/16/23 | Fri 12/1/23 | 1874 | 1876 |  | Carolyn Hicks,Nikki Klein,Kim York,Angie Robertson,Dora Thomas
3124 | 1876 | Future Task |  |  | I-WP119 | Carolyn Hicks | Approve | WPED I-WP119 - Change Analysis Tool - Approve | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 1875 | 1877 |  | Angie Robertson,Jimmy Cox
6814 | 1877 | Future Task |  | RW | I-WP119 | Nikki Klein | Submit | I-WP119 Change Analysis Tool <Activities per WPED> | 10 hrs | 151 days | Mon 12/4/23 | Mon 7/8/24 | 18761926 | 1878 |  | Nikki Klein
3125 | 1878 | Future Task |  |  | I-WP119 | Nikki Klein | Submit | WP I-WP119 - Change Analysis Tool - Submit | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1877 | 1879 |  | Nikki Klein
3126 | 1879 | Future Task |  |  | I-WP119 | Nikki Klein | Review | WP I-WP119 - Change Analysis Tool - Department QC | 8 hrs | 1 day | Tue 7/9/24 | Tue 7/9/24 | 1878 | 1880 |  | Gabriela Gibson
3127 | 1880 | Future Task |  |  | I-WP119 | Nikki Klein | Review | WP I-WP119 - Change Analysis Tool - Collaborative Review & Update | 10 hrs | 10 days | Wed 7/10/24 | Tue 7/23/24 | 1879 | 1881 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3128 | 1881 | Future Task |  |  | I-WP119 | Nikki Klein | Review | WP I-WP119 - Change Analysis Tool - Style Guide Review | 8 hrs | 1 day | Wed 7/24/24 | Wed 7/24/24 | 1880 | 1882 |  | Tatiana Eubanks
3129 | 1882 | Future Task |  |  | I-WP119 | Nikki Klein | Review | WP I-WP119 - Change Analysis Tool - Final Review & Update | 10 hrs | 5 days | Thu 7/25/24 | Wed 7/31/24 | 1881 | 1883 |  | Angie Robertson,Jimmy Cox
3130 | 1883 | Future Task |  |  | I-WP119 | Nikki Klein | Approve | WP I-WP119 - Change Analysis Tool - Approve | 0 hrs | 0 days | Wed 7/31/24 | Wed 7/31/24 | 1882 |  |  | Jimmy Cox | Successor - Role Mapping Handbook 117 | TW (open item)
3131 | 1884 | Future Task |  |  | I-WP121 | Carolyn Hicks |  | I-WP121 - Update D27 Readiness Plan | 143 hrs | 82 days | Mon 10/2/23 | Wed 1/31/24
3132 | 1885 | Future Task |  |  | I-WP121 | Carolyn Hicks | Create | WPED I-WP121 - Update D27 Readiness Plan - Create | 10 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 1 | 1886 |  | Carolyn Hicks,Nikki Klein
3133 | 1886 | Future Task |  |  | I-WP121 | Carolyn Hicks | Submit | WPED I-WP121 - Update D27 Readiness Plan - Submit | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 1885 | 1887 |  | Carolyn Hicks
3134 | 1887 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WPED I-WP121 - Update D27 Readiness Plan - Collaborative Review & Update | 10 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 1886 | 1888 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas,Angie Robertson
3135 | 1888 | Future Task |  |  | I-WP121 | Carolyn Hicks | Approve | WPED I-WP121 - Update D27 Readiness Plan - Approve | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 1887 | 1889 |  | Angie Robertson,Jimmy Cox
5702 | 1889 | Future Task |  |  | I-WP121 | Carolyn Hicks | Create | I-WP121 Update D27 Readiness Plan <Activities per WPED> | 100 hrs | 45 days | Mon 10/30/23 | Fri 1/5/24 | 1888 | 1890 |  | Nikki Klein
3136 | 1890 | Future Task |  |  | I-WP121 | Carolyn Hicks | Submit | WP I-WP121 - Update D27 Readiness Plan - Submit | 0 hrs | 0 days | Fri 1/5/24 | Fri 1/5/24 | 1889 | 1891 |  | Nikki Klein
3137 | 1891 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WP I-WP121 - Update D27 Readiness Plan - Department QC | 1 hr | 1 day | Mon 1/8/24 | Mon 1/8/24 | 1890 | 1892 |  | Gabriela Gibson
3138 | 1892 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WP I-WP121 - Update D27 Readiness Plan - Collaborative Review & Update | 10 hrs | 10 days | Tue 1/9/24 | Tue 1/23/24 | 1891 | 1893 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3139 | 1893 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WP I-WP121 - Update D27 Readiness Plan - Style Guide Review | 2 hrs | 1 day | Wed 1/24/24 | Wed 1/24/24 | 1892 | 1894 |  | Dusti Kincl
3140 | 1894 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WP I-WP121 - Update D27 Readiness Plan - Final Review & Update | 10 hrs | 5 days | Thu 1/25/24 | Wed 1/31/24 | 1893 | 1895 |  | Angie Robertson,Jimmy Cox
3141 | 1895 | Future Task |  |  | I-WP121 | Carolyn Hicks | Approve | WP I-WP121 - Update D27 Readiness Plan - Approve | 0 hrs | 0 days | Wed 1/31/24 | Wed 1/31/24 | 1894 | 1932 |  | Jimmy Cox | Successor - Change Impact Analysis 119 | TW (open item)
3142 | 1896 | Future Task |  |  | I-WP124 | Carolyn Hicks |  | I-WP124 - Update D62 Workforce Transition Plan | 149 hrs | 82 days | Mon 10/2/23 | Wed 1/31/24
3143 | 1897 | Future Task |  |  | I-WP124 | Carolyn Hicks | Create | WPED I-WP124 - Update D62 Workforce Transition Plan - Create | 10 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 1 | 1898 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas
3144 | 1898 | Future Task |  |  | I-WP124 | Carolyn Hicks | Submit | WPED I-WP124 - Update D62 Workforce Transition Plan - Submit | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 1897 | 1899 |  | Carolyn Hicks
3145 | 1899 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WPED I-WP124 - Update D62 Workforce Transition Plan - Collaborative Review & Update | 10 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 1898 | 1900 |  | Carolyn Hicks,Nikki Klein,Kim York,Angie Robertson,Dora Thomas
3146 | 1900 | Future Task |  |  | I-WP124 | Carolyn Hicks | Approve | WPED I-WP124 - Update D62 Workforce Transition Plan - Approve | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 1899 | 1901 |  | Angie Robertson,Jimmy Cox
5703 | 1901 | Future Task |  |  | I-WP124 | Carolyn Hicks | Create | I-WP124 Update D62 Workforce Transition Plan <Activities per WPED> | 100 hrs | 45 days | Mon 10/30/23 | Fri 1/5/24 | 1900 | 1902 |  | Nikki Klein
3147 | 1902 | Future Task |  |  | I-WP124 | Carolyn Hicks | Submit | WP I-WP124 - Update D62 Workforce Transition Plan - Submit | 0 hrs | 0 days | Fri 1/5/24 | Fri 1/5/24 | 1901 | 1903 |  | Nikki Klein
3148 | 1903 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WP I-WP124 - Update D62 Workforce Transition Plan - Department QC | 1 hr | 1 day | Mon 1/8/24 | Mon 1/8/24 | 1902 | 1904 |  | Gabriela Gibson
3149 | 1904 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WP I-WP124 - Update D62 Workforce Transition Plan - Collaborative Review & Update | 10 hrs | 10 days | Tue 1/9/24 | Tue 1/23/24 | 1903 | 1905 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3150 | 1905 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WP I-WP124 - Update D62 Workforce Transition Plan - Style Guide Review | 8 hrs | 1 day | Wed 1/24/24 | Wed 1/24/24 | 1904 | 1906 |  | Tatiana Eubanks
3151 | 1906 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WP I-WP124 - Update D62 Workforce Transition Plan - Final Review & Update | 10 hrs | 5 days | Thu 1/25/24 | Wed 1/31/24 | 1905 | 1907 |  | Angie Robertson,Jimmy Cox
3152 | 1907 | Future Task |  |  | I-WP124 | Carolyn Hicks | Approve | WP I-WP124 - Update D62 Workforce Transition Plan - Approve | 0 hrs | 0 days | Wed 1/31/24 | Wed 1/31/24 | 1906 |  |  | Jimmy Cox | Successor - Change Impact Analysis 119 | TW (open item)
6777 | 1908 | Late | Yes |  | I-WP126 | Nikki Klein |  | I-WP126 - Readiness Workplan | 358 hrs | 88 days | Mon 5/8/23 | Mon 9/11/23
6778 | 1909 | Complete |  |  | I-WP126 | Carolyn Hicks | Create | WPED I-WP126 - Readiness Workplan - Create | 10 hrs | 10 days | Mon 5/8/23 | Fri 5/19/23 | 1 | 1910 |  | Carolyn Hicks,Nikki Klein,Jordan Nobles
6779 | 1910 | Complete |  |  | I-WP126 | Carolyn Hicks | Submit | WPED I-WP126 - Readiness Workplan - Submit | 0 hrs | 0 days | Fri 5/19/23 | Fri 5/19/23 | 1909 | 1911 |  | Carolyn Hicks
6780 | 1911 | Complete |  |  | I-WP126 | Carolyn Hicks | Review | WPED I-WP126 - Readiness Workplan - Collaborative Review & Update | 7 hrs | 7 days | Mon 5/22/23 | Wed 5/31/23 | 1910 | 1912 |  | Carolyn Hicks,Nikki Klein,Jordan Nobles,Angie Robertson
6781 | 1912 | Complete |  |  | I-WP126 | Carolyn Hicks | Approve | WPED I-WP126 - Readiness Workplan - Approve | 0 hrs | 0 days | Wed 5/31/23 | Wed 5/31/23 | 1911 | 1913FS+2 days |  | Angie Robertson,Jimmy Cox
7164 | 1913 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Create draft RW and roadmap | 72 hrs | 20 days | Mon 6/5/23 | Fri 6/30/23 | 1912FS+2 days | 1914 |  | Nikki Klein,Jordan Nobles,Vincent Cicco
7165 | 1914 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Gather input | 48 hrs | 14 days | Mon 7/3/23 | Fri 7/21/23 | 1913 | 1915SS |  | Carolyn Hicks,Jordan Nobles,Nikki Klein,Kimberly Kemp,Angie Robertson,Jimmy Cox
7166 | 1915 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Review Project Schedule | 24 hrs | 9 days | Mon 7/3/23 | Fri 7/14/23 | 1914SS | 1916 |  | Nikki Klein,Jordan Nobles,Vincent Cicco
7167 | 1916 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Update RW | 60 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 | 1915 | 1917SS |  | Nikki Klein,Jordan Nobles,Vincent Cicco
7162 | 1917 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Update Roadmap | 12 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 | 1916SS | 1918 |  | Jordan Nobles,Vincent Cicco
7163 | 1918 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Confirm RW tasks with Architects | 32 hrs | 13 days | Mon 7/31/23 | Wed 8/16/23 | 1917 | 1919 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Jordan Nobles,Nikki Klein,Kimberly Kemp,Angie Robertson
7161 | 1919 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Finalize RW | 38 hrs | 4 days | Thu 8/17/23 | Tue 8/22/23 | 1918 | 1920SS |  | Nikki Klein,Jordan Nobles,Vincent Cicco
7160 | 1920 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Finalize Roadmap | 4 hrs | 4 days | Thu 8/17/23 | Tue 8/22/23 | 1919SS | 1921,1865SS+40 days |  | Jordan Nobles,Vincent Cicco
6783 | 1921 | Future Task |  |  | I-WP126 | Nikki Klein | Submit | WP I-WP126 - Readiness Workplan - Submit | 0 hrs | 0 days | Tue 8/22/23 | Tue 8/22/23 | 1920 | 1922 |  | Nikki Klein
6784 | 1922 | Future Task |  |  | I-WP126 | Nikki Klein | Review | WP I-WP126 - Readiness Workplan - Department QC | 3 hrs | 1 day | Wed 8/23/23 | Wed 8/23/23 | 1921 | 1923 |  | Gabriela Gibson
6785 | 1923 | Future Task |  |  | I-WP126 | Nikki Klein | Review | WP I-WP126 - Readiness Workplan - Collaborative Review & Update | 18 hrs | 5 days | Thu 8/24/23 | Wed 8/30/23 | 1922 | 1924 |  | Nikki Klein,Carolyn Hicks,Angie Robertson
6786 | 1924 | Future Task |  |  | I-WP126 | Nikki Klein | Review | WP I-WP126 - Readiness Workplan - Style Guide Review | 4 hrs | 1 day | Thu 8/31/23 | Thu 8/31/23 | 1923 | 1925 |  | Dusti Kincl
6787 | 1925 | Future Task |  |  | I-WP126 | Nikki Klein | Review | WP I-WP126 - Readiness Workplan - Final Review & Update | 18 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 1924 | 1926 |  | Nikki Klein,Jordan Nobles,Vincent Cicco
6788 | 1926 | Future Task |  |  | I-WP126 | Nikki Klein | Approve | WP I-WP126 - Readiness Workplan - Approve | 8 hrs | 1 day | Mon 9/11/23 | Mon 9/11/23 | 1925 | 1877 |  | Jimmy Cox,Angie Robertson
7225 | 1927 | Future Task | Yes |  | I-WP128 | Nikki Klein |  | I-WP128 - Agency Readiness Certification | 73 hrs | 124 days | Mon 1/8/24 | Mon 7/1/24
7236 | 1928 | Future Task |  |  | I-WP128 | Carolyn Hicks | Create | WPED I-WP128 - Agency Readiness Certification - Create | 10 hrs | 6 days | Mon 1/8/24 | Tue 1/16/24 |  | 1929 |  | Carolyn Hicks,Nikki Klein,Jordan Nobles,Angie Robertson
7237 | 1929 | Future Task |  |  | I-WP128 | Carolyn Hicks | Submit | WPED I-WP128 - Agency Readiness Certification - Submit | 0 hrs | 0 days | Tue 1/16/24 | Tue 1/16/24 | 1928 | 1930 |  | Carolyn Hicks
7238 | 1930 | Future Task |  |  | I-WP128 | Carolyn Hicks | Review | WPED I-WP128 - Agency Readiness Certification - Collaborative Review & Update | 10 hrs | 10 days | Wed 1/17/24 | Tue 1/30/24 | 1929 | 1931 |  | Angie Robertson,Jimmy Cox
7232 | 1931 | Future Task |  |  | I-WP128 | Carolyn Hicks | Approve | WPED I-WP128 - Agency Readiness Certification - Approve | 0 hrs | 0 days | Tue 1/30/24 | Tue 1/30/24 | 1930 | 1932FS+3 days |  | Jimmy Cox
7233 | 1932 | Future Task |  |  | I-WP128 | Kimberly Kemp | Create | I-WP128 - Agency Readiness Certification <Activities per WPED> | 10 hrs | 88 days | Mon 2/5/24 | Thu 6/6/24 | 1931FS+3 days,1895 | 1933 |  | Nikki Klein,Jordan Nobles
7234 | 1933 | Future Task |  |  | I-WP128 | Nikki Klein | Submit | WP I-WP128 - Agency Readiness Certification - Submit | 0 hrs | 0 days | Thu 6/6/24 | Thu 6/6/24 | 1932 | 1934 |  | Nikki Klein
7235 | 1934 | Future Task |  |  | I-WP128 | Nikki Klein | Review | WP I-WP128 - Agency Readiness Certification - Department QC | 3 hrs | 1 day | Fri 6/7/24 | Fri 6/7/24 | 1933 | 1935 |  | Gabriela Gibson
7230 | 1935 | Future Task |  |  | I-WP128 | Nikki Klein | Review | WP I-WP128 - Agency Readiness Certification - Collaborative Review & Update | 18 hrs | 10 days | Mon 6/10/24 | Fri 6/21/24 | 1934 | 1936 |  | Carolyn Hicks,Nikki Klein
7231 | 1936 | Future Task |  |  | I-WP128 | Nikki Klein | Review | WP I-WP128 - Agency Readiness Certification - Style Guide Review | 4 hrs | 1 day | Mon 6/24/24 | Mon 6/24/24 | 1935 | 1937 |  | Tatiana Eubanks
7229 | 1937 | Future Task |  |  | I-WP128 | Nikki Klein | Review | WP I-WP128 - Agency Readiness Certification - Final Review & Update | 18 hrs | 5 days | Tue 6/25/24 | Mon 7/1/24 | 1936 | 1938 |  | Angie Robertson,Jimmy Cox
7228 | 1938 | Future Task |  |  | I-WP128 | Nikki Klein | Approve | WP I-WP128 - Agency Readiness Certification - Approve | 0 hrs | 0 days | Mon 7/1/24 | Mon 7/1/24 | 1937 | 1284 |  | Jimmy Cox
3 | 1939 | Future Task | [5 empty] | Production Support | 1,863 hrs | 638 days | Mon 1/6/25 | Thu 7/15/27
5850 | 1940 | Future Task | [5 empty] | Hypercare | 517 hrs | 358 days | Mon 1/6/25 | Thu 6/4/26
5852 | 1941 | Future Task |  |  | D664 | Bryan Sohayda |  | D664 - Development of the Hypercare Support Plan | 205 hrs | 106 days | Mon 1/6/25 | Wed 6/4/25
5853 | 1942 | Future Task |  |  | D664 | Bryan Sohayda | Create | DED D664 - Development of the Hypercare Support Plan - Create | 8 hrs | 10 days | Mon 1/6/25 | Fri 1/17/25 | 1 | 1943,2012SS+5 days | 2025-02-03 | Bryan Sohayda
5854 | 1943 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DED D664 - Development of the Hypercare Support Plan - Submit | 0 hrs | 0 days | Fri 1/17/25 | Fri 1/17/25 | 1942 | 1944 |  | Bryan Sohayda,Joy Schneider
5855 | 1944 | Future Task |  |  | D664 | Bryan Sohayda | Review | DED D664 - Development of the Hypercare Support Plan - Collaborative Review | 16 hrs | 10 days | Tue 1/21/25 | Mon 2/3/25 | 1943 | 1945 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5856 | 1945 | Future Task |  |  | D664 | Bryan Sohayda | Approve | DED D664 - Development of the Hypercare Support Plan - Approve | 0 hrs | 0 days | Mon 2/3/25 | Mon 2/3/25 | 1944 | 1946FS+19 days |  | Jimmy Cox
5857 | 1946 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Development of the Hypercare Support Plan | 20 hrs | 50 days | Mon 3/3/25 | Fri 5/9/25 | 1945FS+19 days | 1947SS,1953 |  | Bryan Sohayda,Chetna Dewan
5858 | 1947 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Define and document hypercare support processes and procedures | 20 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1946SS | 1948 |  | Bryan Sohayda,Chetna Dewan
5859 | 1948 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Review hypercare support processes and procedures draft | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1947 | 1949 |  | Bryan Sohayda,Chetna Dewan
5860 | 1949 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Define and document tools used for hypercare support activities | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 1948 | 1950 |  | Bryan Sohayda,Chetna Dewan
5861 | 1950 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Review tools used for hypercare activities draft | 20 hrs | 5 days | Mon 3/31/25 | Fri 4/4/25 | 1949 | 1951 |  | Bryan Sohayda,Chetna Dewan
5862 | 1951 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Determine and document resource capacity and skills needed | 20 hrs | 5 days | Mon 4/7/25 | Fri 4/11/25 | 1950 | 1952 |  | Bryan Sohayda,Chetna Dewan
5863 | 1952 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Review resource capacity and skills needed draft | 20 hrs | 5 days | Mon 4/14/25 | Fri 4/18/25 | 1951 | 1953 |  | Bryan Sohayda,Chetna Dewan
5864 | 1953 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DEL D664 - Development of the Hypercare Support Plan - Draft Submission | 0 hrs | 0 days | Fri 5/9/25 | Fri 5/9/25 | 19461952 | 1954 |  | Bryan Sohayda,Joy Schneider
5865 | 1954 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Pre-Submission Collaborative Review | 12 hrs | 5 days | Mon 5/12/25 | Fri 5/16/25 | 1953 | 1955 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5866 | 1955 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Style Guide Review | 1 hr | 1 day | Mon 5/19/25 | Mon 5/19/25 | 1954 | 1956 |  | Dusti Kincl
5867 | 1956 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Final Collaborative Review | 12 hrs | 5 days | Tue 5/20/25 | Tue 5/27/25 | 1955 | 1957 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5868 | 1957 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Accenture QC | 4 hrs | 2 days | Wed 5/28/25 | Thu 5/29/25 | 1956 | 1958 |  | Joy Schneider
5869 | 1958 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DEL D664 - Development of the Hypercare Support Plan - Submit | 0 hrs | 0 days | Thu 5/29/25 | Thu 5/29/25 | 1957 | 1959 |  | Joy Schneider
5870 | 1959 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Department QC | 4 hrs | 1 day | Fri 5/30/25 | Fri 5/30/25 | 1958 | 1960 |  | Tommy Werner,Gabriela Gibson
5871 | 1960 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Contract Manager Review | 8 hrs | 3 days | Mon 6/2/25 | Wed 6/4/25 | 1959 | 1961 |  | Sean Buchanan
5872 | 1961 | Future Task |  |  | D664 | Bryan Sohayda | Accept | DEL D664 - Development of the Hypercare Support Plan - Accept | 0 hrs | 0 days | Wed 6/4/25 | Wed 6/4/25 | 1960 | 1963 | 2025-06-01 | Sean Buchanan
5873 | 1962 | Future Task |  |  | D680 | Bryan Sohayda |  | D680 - Hypercare Monthly Deliverable – January 2026 | 153 hrs | 85 days | Mon 11/3/25 | Mon 3/9/26
5874 | 1963 | Future Task |  |  | D680-D683 | Bryan Sohayda | Create | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Create | 80 hrs | 10 days | Mon 11/3/25 | Mon 11/17/25 | 1961 | 1964 |  | Bryan Sohayda
5875 | 1964 | Future Task |  |  | D680-D683 | Bryan Sohayda | Submit | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Submit | 0 hrs | 0 days | Mon 11/17/25 | Mon 11/17/25 | 1963 | 1965 |  | Bryan Sohayda,Joy Schneider
5876 | 1965 | Future Task |  |  | D680-D683 | Bryan Sohayda | Review | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Collaborative Review | 20 hrs | 10 days | Tue 11/18/25 | Wed 12/3/25 | 1964 | 1966 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
7150 | 1966 | Future Task |  |  | D680-D683 | Bryan Sohayda | Approve | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Approve | 0 hrs | 0 days | Wed 12/3/25 | Wed 12/3/25 | 1965 | 1967FS+44 days |  | Jimmy Cox
5877 | 1967 | Future Task |  |  | D680 | Bryan Sohayda | Create | Create D680 - Hypercare Monthly Deliverable – January 2026 | 4 hrs | 4 days | Mon 2/9/26 | Thu 2/12/26 | 1966FS+44 days | 1968 |  | Bryan Sohayda
5878 | 1968 | Future Task |  |  | D680 | Bryan Sohayda | Submit | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Draft Submission | 0 hrs | 0 days | Thu 2/12/26 | Thu 2/12/26 | 1967 | 1969 |  | Joy Schneider,Bryan Sohayda
5879 | 1969 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 2/13/26 | Thu 2/19/26 | 1968 | 1970 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5880 | 1970 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Style Guide Review | 1 hr | 1 day | Fri 2/20/26 | Fri 2/20/26 | 1969 | 1971 |  | Dusti Kincl
5881 | 1971 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Final Collaborative Review | 16 hrs | 5 days | Mon 2/23/26 | Fri 2/27/26 | 1970 | 1972 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5882 | 1972 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Accenture QC | 4 hrs | 2 days | Mon 3/2/26 | Tue 3/3/26 | 1971 | 1973 |  | Joy Schneider
5883 | 1973 | Future Task |  |  | D680 | Bryan Sohayda | Submit | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Submit | 0 hrs | 0 days | Tue 3/3/26 | Tue 3/3/26 | 1972 | 1974 |  | Joy Schneider
5884 | 1974 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Department QC | 4 hrs | 1 day | Wed 3/4/26 | Wed 3/4/26 | 1973 | 1975 |  | Tommy Werner
5885 | 1975 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 3/5/26 | Mon 3/9/26 | 1974 | 1976 |  | Sean Buchanan
5886 | 1976 | Future Task |  |  | D680 | Bryan Sohayda | Accept | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Accept | 0 hrs | 0 days | Mon 3/9/26 | Mon 3/9/26 | 1975 | 1978FS-1 day |  | Sean Buchanan
5887 | 1977 | Future Task |  |  | D681 | Bryan Sohayda |  | D681 - Hypercare Monthly Deliverable – February 2026 | 53 hrs | 21 days | Mon 3/9/26 | Mon 4/6/26
5888 | 1978 | Future Task |  |  | D681 | Bryan Sohayda | Create | Create D681 - Hypercare Monthly Deliverable – February 2026 | 4 hrs | 4 days | Mon 3/9/26 | Thu 3/12/26 | 1976FS-1 day | 1979 |  | Bryan Sohayda
5889 | 1979 | Future Task |  |  | D681 | Bryan Sohayda | Submit | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Draft Submission | 0 hrs | 0 days | Thu 3/12/26 | Thu 3/12/26 | 1978 | 1980 |  | Joy Schneider,Bryan Sohayda
5890 | 1980 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 3/13/26 | Thu 3/19/26 | 1979 | 1981 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5891 | 1981 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Style Guide Review | 1 hr | 1 day | Fri 3/20/26 | Fri 3/20/26 | 1980 | 1982 |  | Dusti Kincl
5892 | 1982 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Final Collaborative Review | 16 hrs | 5 days | Mon 3/23/26 | Fri 3/27/26 | 1981 | 1983 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5893 | 1983 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Accenture QC | 4 hrs | 2 days | Mon 3/30/26 | Tue 3/31/26 | 1982 | 1984 |  | Joy Schneider
5894 | 1984 | Future Task |  |  | D681 | Bryan Sohayda | Submit | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Submit | 0 hrs | 0 days | Tue 3/31/26 | Tue 3/31/26 | 1983 | 1985 |  | Joy Schneider
5895 | 1985 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Department QC | 4 hrs | 1 day | Wed 4/1/26 | Wed 4/1/26 | 1984 | 1986 |  | Tommy Werner
5896 | 1986 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 4/2/26 | Mon 4/6/26 | 1985 | 1987 |  | Sean Buchanan
5897 | 1987 | Future Task |  |  | D681 | Bryan Sohayda | Accept | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Accept | 0 hrs | 0 days | Mon 4/6/26 | Mon 4/6/26 | 1986 | 1989 |  | Sean Buchanan
5898 | 1988 | Future Task |  |  | D682 | Bryan Sohayda |  | D682 - Hypercare Monthly Deliverable – March 2026 | 53 hrs | 21 days | Tue 4/7/26 | Tue 5/5/26
5899 | 1989 | Future Task |  |  | D682 | Bryan Sohayda | Create | Create D682 - Hypercare Monthly Deliverable – March 2026 | 4 hrs | 4 days | Tue 4/7/26 | Fri 4/10/26 | 1987 | 1990 |  | Bryan Sohayda
5900 | 1990 | Future Task |  |  | D682 | Bryan Sohayda | Submit | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Draft Submission | 0 hrs | 0 days | Fri 4/10/26 | Fri 4/10/26 | 1989 | 1991 |  | Joy Schneider,Bryan Sohayda
5901 | 1991 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 4/13/26 | Fri 4/17/26 | 1990 | 1992 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5902 | 1992 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Style Guide Review | 1 hr | 1 day | Mon 4/20/26 | Mon 4/20/26 | 1991 | 1993 |  | Dusti Kincl
5903 | 1993 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Final Collaborative Review | 16 hrs | 5 days | Tue 4/21/26 | Mon 4/27/26 | 1992 | 1994 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5904 | 1994 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Accenture QC | 4 hrs | 2 days | Tue 4/28/26 | Wed 4/29/26 | 1993 | 1995 |  | Joy Schneider
5905 | 1995 | Future Task |  |  | D682 | Bryan Sohayda | Submit | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Submit | 0 hrs | 0 days | Wed 4/29/26 | Wed 4/29/26 | 1994 | 1996 |  | Joy Schneider
5906 | 1996 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Department QC | 4 hrs | 1 day | Thu 4/30/26 | Thu 4/30/26 | 1995 | 1997 |  | Tommy Werner
5907 | 1997 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Contract Manager Review | 8 hrs | 3 days | Fri 5/1/26 | Tue 5/5/26 | 1996 | 1998 |  | Sean Buchanan
5908 | 1998 | Future Task |  |  | D682 | Bryan Sohayda | Accept | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Accept | 0 hrs | 0 days | Tue 5/5/26 | Tue 5/5/26 | 1997 | 2000 |  | Sean Buchanan
5909 | 1999 | Future Task |  |  | D683 | Bryan Sohayda |  | D683 - Hypercare Monthly Deliverable – April 2026 | 53 hrs | 21 days | Wed 5/6/26 | Thu 6/4/26
5910 | 2000 | Future Task |  |  | D683 | Bryan Sohayda | Create | Create D683 - Hypercare Monthly Deliverable – April 2026 | 4 hrs | 4 days | Wed 5/6/26 | Mon 5/11/26 | 1998 | 2001 |  | Bryan Sohayda
5911 | 2001 | Future Task |  |  | D683 | Bryan Sohayda | Submit | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Draft Submission | 0 hrs | 0 days | Mon 5/11/26 | Mon 5/11/26 | 2000 | 2002 |  | Joy Schneider,Bryan Sohayda
5912 | 2002 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Tue 5/12/26 | Mon 5/18/26 | 2001 | 2003 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5913 | 2003 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Style Guide Review | 1 hr | 1 day | Tue 5/19/26 | Tue 5/19/26 | 2002 | 2004 |  | Dusti Kincl
5914 | 2004 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Final Collaborative Review | 16 hrs | 5 days | Wed 5/20/26 | Wed 5/27/26 | 2003 | 2005 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5915 | 2005 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Accenture QC | 4 hrs | 2 days | Thu 5/28/26 | Fri 5/29/26 | 2004 | 2006 |  | Joy Schneider
5916 | 2006 | Future Task |  |  | D683 | Bryan Sohayda | Submit | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Submit | 0 hrs | 0 days | Fri 5/29/26 | Fri 5/29/26 | 2005 | 2007 |  | Joy Schneider
5917 | 2007 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Department QC | 4 hrs | 1 day | Mon 6/1/26 | Mon 6/1/26 | 2006 | 2008 |  | Tommy Werner
5918 | 2008 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 6/2/26 | Thu 6/4/26 | 2007 | 2009 |  | Sean Buchanan
5919 | 2009 | Future Task |  |  | D683 | Bryan Sohayda | Accept | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Accept | 0 hrs | 0 days | Thu 6/4/26 | Thu 6/4/26 | 2008 |  |  | Sean Buchanan
5851 | 2010 | Future Task | [5 empty] | Post-Implementation Support | 1,346 hrs | 633 days | Mon 1/13/25 | Thu 7/15/27
5488 | 2011 | Future Task |  |  | D665 | Bryan Sohayda |  | D665 - Updated Post-Implementation Support Plan | 154 hrs | 106 days | Mon 1/13/25 | Wed 6/11/25
5489 | 2012 | Future Task |  |  | D665 | Bryan Sohayda | Create | DED D665 - Updated Post-Implementation Support Plan - Create | 8 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 1942SS+5 days | 2013 |  | Bryan Sohayda
5490 | 2013 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DED D665 - Updated Post-Implementation Support Plan - Submit | 0 hrs | 0 days | Mon 1/27/25 | Mon 1/27/25 | 2012 | 2014 |  | Bryan Sohayda,Joy Schneider
5491 | 2014 | Future Task |  |  | D665 | Bryan Sohayda | Review | DED D665 - Updated Post-Implementation Support Plan - Collaborative Review | 16 hrs | 10 days | Tue 1/28/25 | Mon 2/10/25 | 2013 | 2015 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5492 | 2015 | Future Task |  |  | D665 | Bryan Sohayda | Approve | DED D665 - Updated Post-Implementation Support Plan - Approve | 0 hrs | 0 days | Mon 2/10/25 | Mon 2/10/25 | 2014 | 2016FS+14 days |  | Jimmy Cox
5493 | 2016 | Future Task |  |  | D665 | Bryan Sohayda | Create | Create Post Implementation Support Processes and Procedures | 20 hrs | 15 days | Mon 3/3/25 | Fri 3/21/25 | 2015FS+14 days | 2017 |  | Bryan Sohayda,Chetna Dewan
5494 | 2017 | Future Task |  |  | D665 | Bryan Sohayda | Create | Document Post Implementation Support Tools | 20 hrs | 10 days | Mon 3/24/25 | Fri 4/4/25 | 2016 | 2018 |  | Bryan Sohayda,Chetna Dewan
5495 | 2018 | Future Task |  |  | D665 | Bryan Sohayda | Create | Post-Implementation Support Resource Capacity and Skills | 20 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 2017 | 2019 |  | Bryan Sohayda,Chetna Dewan
5496 | 2019 | Future Task |  |  | D665 | Bryan Sohayda | Create | Full draft review pre-submission | 20 hrs | 20 days | Mon 4/21/25 | Fri 5/16/25 | 2018 | 2020 |  | Bryan Sohayda,Chetna Dewan
5497 | 2020 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DEL D665 - Updated Post-Implementation Support Plan - Draft Submission | 0 hrs | 0 days | Fri 5/16/25 | Fri 5/16/25 | 2019 | 2021 |  | Bryan Sohayda,Joy Schneider
5498 | 2021 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Pre-Submission Collaborative Review | 12 hrs | 5 days | Mon 5/19/25 | Fri 5/23/25 | 2020 | 2022 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5499 | 2022 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Style Guide Review | 1 hr | 1 day | Tue 5/27/25 | Tue 5/27/25 | 2021 | 2023 |  | Dusti Kincl
5500 | 2023 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Final Collaborative Review | 21 hrs | 5 days | Wed 5/28/25 | Tue 6/3/25 | 2022 | 2024 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5501 | 2024 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Accenture QC | 4 hrs | 2 days | Wed 6/4/25 | Thu 6/5/25 | 2023 | 2025 |  | Joy Schneider
5502 | 2025 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DEL D665 - Updated Post-Implementation Support Plan - Submit | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 2024 | 2026 |  | Joy Schneider
5503 | 2026 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Department QC | 4 hrs | 1 day | Fri 6/6/25 | Fri 6/6/25 | 2025 | 2027 |  | Tommy Werner,Gabriela Gibson
5504 | 2027 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Contract Manager Review | 8 hrs | 3 days | Mon 6/9/25 | Wed 6/11/25 | 2026 | 2028 |  | Sean Buchanan
5505 | 2028 | Future Task |  |  | D665 | Bryan Sohayda | Accept | DEL D665 - Updated Post-Implementation Support Plan - Accept | 0 hrs | 0 days | Wed 6/11/25 | Wed 6/11/25 | 2027 |  | 2025-06-01 | Sean Buchanan
5759 | 2029 | Future Task |  |  | D684 | Bryan Sohayda |  | D684 - Post-Implementation Support Monthly Deliverable – May 2026 | 122 hrs | 85 days | Mon 3/2/26 | Mon 6/29/26
5760 | 2030 | Future Task |  |  | D684-D691 | Bryan Sohayda | Create | DED Create - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 8 hrs | 5 days | Mon 3/2/26 | Fri 3/6/26 | 1 | 2031 |  | Bryan Sohayda
5761 | 2031 | Future Task |  |  | D684-D691 | Bryan Sohayda | Submit | DED Submit - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 0 hrs | 0 days | Fri 3/6/26 | Fri 3/6/26 | 2030 | 2032 |  | Bryan Sohayda,Joy Schneider
5762 | 2032 | Future Task |  |  | D684-D691 | Bryan Sohayda | Review | DED Collaborative Review & Accept - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 20 hrs | 10 days | Mon 3/9/26 | Fri 3/20/26 | 2031 | 2033 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5763 | 2033 | Future Task |  |  | D684 | Bryan Sohayda | Create | Create D684 - Post-Implementation Support Monthly Deliverable – May 2026 | 4 hrs | 4 days | Mon 6/1/26 | Thu 6/4/26 | 2032 | 2034 |  | Bryan Sohayda
5764 | 2034 | Future Task |  |  | D684 | Bryan Sohayda | Submit | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Draft Submission | 0 hrs | 0 days | Thu 6/4/26 | Thu 6/4/26 | 2033 | 2035 |  | Joy Schneider,Bryan Sohayda
5765 | 2035 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 6/5/26 | Thu 6/11/26 | 2034 | 2036 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5766 | 2036 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Style Guide Review | 8 hrs | 1 day | Fri 6/12/26 | Fri 6/12/26 | 2035 | 2037 |  | Dusti Kincl
5767 | 2037 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Final Collaborative Review | 20 hrs | 5 days | Mon 6/15/26 | Fri 6/19/26 | 2036 | 2038 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5768 | 2038 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Accenture QC | 16 hrs | 2 days | Mon 6/22/26 | Tue 6/23/26 | 2037 | 2039 |  | Joy Schneider
5769 | 2039 | Future Task |  |  | D684 | Bryan Sohayda | Submit | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Submit | 0 hrs | 0 days | Tue 6/23/26 | Tue 6/23/26 | 2038 | 2040 |  | Joy Schneider
5770 | 2040 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Department QC | 2 hrs | 1 day | Wed 6/24/26 | Wed 6/24/26 | 2039 | 2041 |  | Tommy Werner
5771 | 2041 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Contract Manager Review | 24 hrs | 3 days | Thu 6/25/26 | Mon 6/29/26 | 2040 | 2042 |  | Sean Buchanan
5772 | 2042 | Future Task |  |  | D684 | Bryan Sohayda | Accept | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Accept | 0 hrs | 0 days | Mon 6/29/26 | Mon 6/29/26 | 2041 | 2044 |  | Sean Buchanan
5773 | 2043 | Future Task |  |  | D685 | Bryan Sohayda |  | D685 - Post-Implementation Support Monthly Deliverable – June 2026 | 53 hrs | 21 days | Wed 7/1/26 | Thu 7/30/26
5774 | 2044 | Future Task |  |  | D685 | Bryan Sohayda | Create | Create D685 - Post-Implementation Support Monthly Deliverable – June 2026 | 4 hrs | 4 days | Wed 7/1/26 | Tue 7/7/26 | 2042 | 2045 |  | Bryan Sohayda
5775 | 2045 | Future Task |  |  | D685 | Bryan Sohayda | Submit | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Draft Submission | 0 hrs | 0 days | Tue 7/7/26 | Tue 7/7/26 | 2044 | 2046 |  | Joy Schneider,Bryan Sohayda
5776 | 2046 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Wed 7/8/26 | Tue 7/14/26 | 2045 | 2047 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5777 | 2047 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Style Guide Review | 1 hr | 1 day | Wed 7/15/26 | Wed 7/15/26 | 2046 | 2048 |  | Dusti Kincl
5778 | 2048 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Final Collaborative Review | 16 hrs | 5 days | Thu 7/16/26 | Wed 7/22/26 | 2047 | 2049 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5779 | 2049 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Accenture QC | 4 hrs | 2 days | Thu 7/23/26 | Fri 7/24/26 | 2048 | 2050 |  | Joy Schneider
5780 | 2050 | Future Task |  |  | D685 | Bryan Sohayda | Submit | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Submit | 0 hrs | 0 days | Fri 7/24/26 | Fri 7/24/26 | 2049 | 2051 |  | Joy Schneider
5781 | 2051 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Department QC | 4 hrs | 1 day | Mon 7/27/26 | Mon 7/27/26 | 2050 | 2052 |  | Tommy Werner
5782 | 2052 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 7/28/26 | Thu 7/30/26 | 2051 | 2053 |  | Sean Buchanan
5783 | 2053 | Future Task |  |  | D685 | Bryan Sohayda | Accept | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Accept | 0 hrs | 0 days | Thu 7/30/26 | Thu 7/30/26 | 2052 | 2055 |  | Sean Buchanan
5784 | 2054 | Future Task |  |  | D686 | Bryan Sohayda |  | D686 - Post-Implementation Support Monthly Deliverable – July 2026 | 53 hrs | 21 days | Mon 8/3/26 | Mon 8/31/26
5785 | 2055 | Future Task |  |  | D686 | Bryan Sohayda | Create | Create D686 - Post-Implementation Support Monthly Deliverable – July 2026 | 4 hrs | 4 days | Mon 8/3/26 | Thu 8/6/26 | 2053 | 2056 |  | Bryan Sohayda
5786 | 2056 | Future Task |  |  | D686 | Bryan Sohayda | Submit | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Draft Submission | 0 hrs | 0 days | Thu 8/6/26 | Thu 8/6/26 | 2055 | 2057 |  | Joy Schneider,Bryan Sohayda
5787 | 2057 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 8/7/26 | Thu 8/13/26 | 2056 | 2058 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5788 | 2058 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Style Guide Review | 1 hr | 1 day | Fri 8/14/26 | Fri 8/14/26 | 2057 | 2059 |  | Dusti Kincl
5789 | 2059 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Final Collaborative Review | 16 hrs | 5 days | Mon 8/17/26 | Fri 8/21/26 | 2058 | 2060 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5790 | 2060 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Accenture QC | 4 hrs | 2 days | Mon 8/24/26 | Tue 8/25/26 | 2059 | 2061 |  | Joy Schneider
5791 | 2061 | Future Task |  |  | D686 | Bryan Sohayda | Submit | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Submit | 0 hrs | 0 days | Tue 8/25/26 | Tue 8/25/26 | 2060 | 2062 |  | Joy Schneider
5792 | 2062 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Department QC | 4 hrs | 1 day | Wed 8/26/26 | Wed 8/26/26 | 2061 | 2063 |  | Tommy Werner
5793 | 2063 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 8/27/26 | Mon 8/31/26 | 2062 | 2064 |  | Sean Buchanan
5794 | 2064 | Future Task |  |  | D686 | Bryan Sohayda | Accept | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Accept | 0 hrs | 0 days | Mon 8/31/26 | Mon 8/31/26 | 2063 | 2066 |  | Sean Buchanan
5795 | 2065 | Future Task |  |  | D687 | Bryan Sohayda |  | D687 - Post-Implementation Support Monthly Deliverable – August 2026 | 53 hrs | 21 days | Tue 9/1/26 | Wed 9/30/26
5796 | 2066 | Future Task |  |  | D687 | Bryan Sohayda | Create | Create D687 - Post-Implementation Support Monthly Deliverable – August 2026 | 4 hrs | 4 days | Tue 9/1/26 | Fri 9/4/26 | 2064 | 2067 |  | Bryan Sohayda
5797 | 2067 | Future Task |  |  | D687 | Bryan Sohayda | Submit | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Draft Submission | 0 hrs | 0 days | Fri 9/4/26 | Fri 9/4/26 | 2066 | 2068 |  | Joy Schneider,Bryan Sohayda
5798 | 2068 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Tue 9/8/26 | Mon 9/14/26 | 2067 | 2069 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5799 | 2069 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Style Guide Review | 1 hr | 1 day | Tue 9/15/26 | Tue 9/15/26 | 2068 | 2070 |  | Dusti Kincl
5800 | 2070 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Final Collaborative Review | 16 hrs | 5 days | Wed 9/16/26 | Tue 9/22/26 | 2069 | 2071 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5801 | 2071 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Accenture QC | 4 hrs | 2 days | Wed 9/23/26 | Thu 9/24/26 | 2070 | 2072 |  | Joy Schneider
5802 | 2072 | Future Task |  |  | D687 | Bryan Sohayda | Submit | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Submit | 0 hrs | 0 days | Thu 9/24/26 | Thu 9/24/26 | 2071 | 2073 |  | Joy Schneider
5803 | 2073 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Department QC | 4 hrs | 1 day | Fri 9/25/26 | Fri 9/25/26 | 2072 | 2074 |  | Tommy Werner
5804 | 2074 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Contract Manager Review | 8 hrs | 3 days | Mon 9/28/26 | Wed 9/30/26 | 2073 | 2075 |  | Sean Buchanan
5805 | 2075 | Future Task |  |  | D687 | Bryan Sohayda | Accept | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Accept | 0 hrs | 0 days | Wed 9/30/26 | Wed 9/30/26 | 2074 | 2077 |  | Sean Buchanan
5806 | 2076 | Future Task |  |  | D688 | Bryan Sohayda |  | D688 - Post-Implementation Support Monthly Deliverable – September 2026 | 53 hrs | 21 days | Thu 10/1/26 | Thu 10/29/26
5807 | 2077 | Future Task |  |  | D688 | Bryan Sohayda | Create | Create D688 - Post-Implementation Support Monthly Deliverable – September 2026 | 4 hrs | 4 days | Thu 10/1/26 | Tue 10/6/26 | 2075 | 2078 |  | Bryan Sohayda
5808 | 2078 | Future Task |  |  | D688 | Bryan Sohayda | Submit | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Draft Submission | 0 hrs | 0 days | Tue 10/6/26 | Tue 10/6/26 | 2077 | 2079 |  | Joy Schneider,Bryan Sohayda
5809 | 2079 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Wed 10/7/26 | Tue 10/13/26 | 2078 | 2080 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5810 | 2080 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Style Guide Review | 1 hr | 1 day | Wed 10/14/26 | Wed 10/14/26 | 2079 | 2081 |  | Dusti Kincl
5811 | 2081 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Final Collaborative Review | 16 hrs | 5 days | Thu 10/15/26 | Wed 10/21/26 | 2080 | 2082 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5812 | 2082 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Accenture QC | 4 hrs | 2 days | Thu 10/22/26 | Fri 10/23/26 | 2081 | 2083 |  | Joy Schneider
5813 | 2083 | Future Task |  |  | D688 | Bryan Sohayda | Submit | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Submit | 0 hrs | 0 days | Fri 10/23/26 | Fri 10/23/26 | 2082 | 2084 |  | Joy Schneider
5814 | 2084 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Department QC | 4 hrs | 1 day | Mon 10/26/26 | Mon 10/26/26 | 2083 | 2085 |  | Tommy Werner
5815 | 2085 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 10/27/26 | Thu 10/29/26 | 2084 | 2086 |  | Sean Buchanan
5816 | 2086 | Future Task |  |  | D688 | Bryan Sohayda | Accept | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Accept | 0 hrs | 0 days | Thu 10/29/26 | Thu 10/29/26 | 2085 | 2088 |  | Sean Buchanan
5817 | 2087 | Future Task |  |  | D689 | Bryan Sohayda |  | D689 - Post-Implementation Support Monthly Deliverable – October 2026 | 53 hrs | 18 days | Mon 11/2/26 | Mon 11/30/26
5818 | 2088 | Future Task |  |  | D689 | Bryan Sohayda | Create | Create D689 - Post-Implementation Support Monthly Deliverable – October 2026 | 4 hrs | 4 days | Mon 11/2/26 | Thu 11/5/26 | 2086 | 2089 |  | Bryan Sohayda
5819 | 2089 | Future Task |  |  | D689 | Bryan Sohayda | Submit | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Draft Submission | 0 hrs | 0 days | Thu 11/5/26 | Thu 11/5/26 | 2088 | 2090 |  | Joy Schneider,Bryan Sohayda
5820 | 2090 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Pre-Submission Collaborative Review | 16 hrs | 4 days | Fri 11/6/26 | Thu 11/12/26 | 2089 | 2091 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5821 | 2091 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Style Guide Review | 1 hr | 1 day | Fri 11/13/26 | Fri 11/13/26 | 2090 | 2092 |  | Dusti Kincl
5822 | 2092 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Final Collaborative Review | 16 hrs | 3 days | Mon 11/16/26 | Wed 11/18/26 | 2091 | 2093 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5823 | 2093 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Accenture QC | 4 hrs | 2 days | Thu 11/19/26 | Fri 11/20/26 | 2092 | 2094 |  | Joy Schneider
5824 | 2094 | Future Task |  |  | D689 | Bryan Sohayda | Submit | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Submit | 0 hrs | 0 days | Fri 11/20/26 | Fri 11/20/26 | 2093 | 2095 |  | Joy Schneider
5825 | 2095 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Department QC | 4 hrs | 1 day | Mon 11/23/26 | Mon 11/23/26 | 2094 | 2096 |  | Tommy Werner
5826 | 2096 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 11/24/26 | Mon 11/30/26 | 2095 | 2097 |  | Sean Buchanan
5827 | 2097 | Future Task |  |  | D689 | Bryan Sohayda | Accept | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Accept | 0 hrs | 0 days | Mon 11/30/26 | Mon 11/30/26 | 2096 | 2099 |  | Sean Buchanan
5828 | 2098 | Future Task |  |  | D690 | Bryan Sohayda |  | D690 - Post-Implementation Support Monthly Deliverable – November 2026 | 53 hrs | 21 days | Tue 12/1/26 | Wed 12/30/26
5829 | 2099 | Future Task |  |  | D690 | Bryan Sohayda | Create | Create D690 - Post-Implementation Support Monthly Deliverable – November 2026 | 4 hrs | 4 days | Tue 12/1/26 | Fri 12/4/26 | 2097 | 2100 |  | Bryan Sohayda
5830 | 2100 | Future Task |  |  | D690 | Bryan Sohayda | Submit | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Draft Submission | 0 hrs | 0 days | Fri 12/4/26 | Fri 12/4/26 | 2099 | 2101 |  | Joy Schneider,Bryan Sohayda
5831 | 2101 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 12/7/26 | Fri 12/11/26 | 2100 | 2102 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5832 | 2102 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Style Guide Review | 1 hr | 1 day | Mon 12/14/26 | Mon 12/14/26 | 2101 | 2103 |  | Dusti Kincl
5833 | 2103 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Final Collaborative Review | 16 hrs | 5 days | Tue 12/15/26 | Mon 12/21/26 | 2102 | 2104 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5834 | 2104 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Accenture QC | 4 hrs | 2 days | Tue 12/22/26 | Wed 12/23/26 | 2103 | 2105 |  | Joy Schneider
5835 | 2105 | Future Task |  |  | D690 | Bryan Sohayda | Submit | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Submit | 0 hrs | 0 days | Wed 12/23/26 | Wed 12/23/26 | 2104 | 2106 |  | Joy Schneider
5836 | 2106 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Department QC | 4 hrs | 1 day | Thu 12/24/26 | Thu 12/24/26 | 2105 | 2107 |  | Tommy Werner
5837 | 2107 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Contract Manager Review | 8 hrs | 3 days | Mon 12/28/26 | Wed 12/30/26 | 2106 | 2108 |  | Sean Buchanan
5838 | 2108 | Future Task |  |  | D690 | Bryan Sohayda | Accept | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Accept | 0 hrs | 0 days | Wed 12/30/26 | Wed 12/30/26 | 2107 | 2110 |  | Sean Buchanan
5839 | 2109 | Future Task |  |  | D691 | Bryan Sohayda |  | D691 - Post-Implementation Support Monthly Deliverable – December 2026 | 53 hrs | 21 days | Mon 1/4/27 | Tue 2/2/27
5840 | 2110 | Future Task |  |  | D691 | Bryan Sohayda | Create | Create D691 - Post-Implementation Support Monthly Deliverable – December 2026 | 4 hrs | 4 days | Mon 1/4/27 | Thu 1/7/27 | 2108 | 2111 |  | Bryan Sohayda
5841 | 2111 | Future Task |  |  | D691 | Bryan Sohayda | Submit | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Draft Submission | 0 hrs | 0 days | Thu 1/7/27 | Thu 1/7/27 | 2110 | 2112 |  | Joy Schneider,Bryan Sohayda
5842 | 2112 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 1/8/27 | Thu 1/14/27 | 2111 | 2113 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5843 | 2113 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Style Guide Review | 1 hr | 1 day | Fri 1/15/27 | Fri 1/15/27 | 2112 | 2114 |  | Dusti Kincl
5844 | 2114 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Final Collaborative Review | 16 hrs | 5 days | Tue 1/19/27 | Mon 1/25/27 | 2113 | 2115 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5845 | 2115 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Accenture QC | 4 hrs | 2 days | Tue 1/26/27 | Wed 1/27/27 | 2114 | 2116 |  | Joy Schneider
5846 | 2116 | Future Task |  |  | D691 | Bryan Sohayda | Submit | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Submit | 0 hrs | 0 days | Wed 1/27/27 | Wed 1/27/27 | 2115 | 2117 |  | Joy Schneider
5847 | 2117 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Department QC | 4 hrs | 1 day | Thu 1/28/27 | Thu 1/28/27 | 2116 | 2118 |  | Tommy Werner
5848 | 2118 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Contract Manager Review | 8 hrs | 3 days | Fri 1/29/27 | Tue 2/2/27 | 2117 | 2119 |  | Sean Buchanan
5849 | 2119 | Future Task |  |  | D691 | Bryan Sohayda | Accept | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Accept | 0 hrs | 0 days | Tue 2/2/27 | Tue 2/2/27 | 2118 |  |  | Sean Buchanan
6704 | 2120 | Future Task |  |  | D692 | Stacey Terry |  | D692 - Tax Reporting Support CY 2026 (January 2027) | 179 hrs | 91 days | Mon 10/12/26 | Tue 2/23/27
6705 | 2121 | Future Task |  |  | D692 | Stacey Terry | Create | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Create | 8 hrs | 10 days | Mon 10/12/26 | Fri 10/23/26 | 1 | 2122 | 2026-11-12 | Stacey Terry
6706 | 2122 | Future Task |  |  | D692 | Stacey Terry | Submit | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Submit | 0 hrs | 0 days | Fri 10/23/26 | Fri 10/23/26 | 2121 | 2123 |  | Stacey Terry,Joy Schneider
6707 | 2123 | Future Task |  |  | D692 | Stacey Terry | Review | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Collaborative Review | 20 hrs | 10 days | Mon 10/26/26 | Fri 11/6/26 | 2122 | 2124 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
6708 | 2124 | Future Task |  |  | D692 | Stacey Terry | Approve | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Approve | 0 hrs | 0 days | Fri 11/6/26 | Fri 11/6/26 | 2123 | 2125FS+22 days |  | Jimmy Cox
6709 | 2125 | Future Task |  |  | D692 | Stacey Terry | Create | D692 - Create Tax Reporting Checklist (2026) | 36 hrs | 18 days | Mon 12/14/26 | Fri 1/8/27 | 2124FS+22 days | 2126FS-5 days,2127 |  | Stacey Terry,Yogesh Deshmukh
6710 | 2126 | Future Task |  |  | D692 | Stacey Terry | Create | D692 - Manage Year-end Checklist (2026) | 38 hrs | 19 days | Mon 1/4/27 | Fri 1/29/27 | 2125FS-5 days |  |  | Stacey Terry,Yogesh Deshmukh
6711 | 2127 | Future Task |  |  | D692 | Stacey Terry | Create | D692 - Create initial Year-end Checklist (2027) | 28 hrs | 14 days | Mon 1/11/27 | Fri 1/29/27 | 2125 | 2128 |  | Stacey Terry,Yogesh Deshmukh
6712 | 2128 | Future Task |  |  | D692 | Stacey Terry | Submit | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Draft Submission | 0 hrs | 0 days | Fri 1/29/27 | Fri 1/29/27 | 2127 | 2129 |  | Stacey Terry,Joy Schneider
6713 | 2129 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 2/1/27 | Fri 2/5/27 | 2128 | 2130 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson
6714 | 2130 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Style Guide Review | 1 hr | 1 day | Mon 2/8/27 | Mon 2/8/27 | 2129 | 2131 |  | Dusti Kincl
6715 | 2131 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Final Collaborative Review | 16 hrs | 5 days | Tue 2/9/27 | Mon 2/15/27 | 2130 | 2132 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson
6716 | 2132 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Accenture QC | 4 hrs | 2 days | Tue 2/16/27 | Wed 2/17/27 | 2131 | 2133 |  | Joy Schneider
6717 | 2133 | Future Task |  |  | D692 | Stacey Terry | Submit | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Submit | 0 hrs | 0 days | Wed 2/17/27 | Wed 2/17/27 | 2132 | 2134 |  | Joy Schneider
6718 | 2134 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Department QC | 4 hrs | 1 day | Thu 2/18/27 | Thu 2/18/27 | 2133 | 2135 |  | Tommy Werner,Gabriela Gibson
6719 | 2135 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Contract Manager Review | 8 hrs | 3 days | Fri 2/19/27 | Tue 2/23/27 | 2134 | 2136 |  | Sean Buchanan
6720 | 2136 | Future Task |  |  | D692 | Stacey Terry | Accept | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Accept | 0 hrs | 0 days | Tue 2/23/27 | Tue 2/23/27 | 2135 |  | 2027-02-01 | Sean Buchanan
6721 | 2137 | Future Task |  |  | D693 | Joy Schneider |  | D693 - Exit Transition Completion | 122 hrs | 136 days | Mon 1/4/27 | Thu 7/15/27
6722 | 2138 | Future Task |  |  | D693 | Joy Schneider | Create | DED D693 - Exit Transition Completion - Create | 6 hrs | 10 days | Mon 1/4/27 | Fri 1/15/27 | 2164 | 2139 |  | Joy Schneider,Matt Cole,Mary Punty
6723 | 2139 | Future Task |  |  | D693 | Joy Schneider | Submit | DED D693 - Exit Transition Completion - Submit | 0 hrs | 0 days | Fri 1/15/27 | Fri 1/15/27 | 2138 | 2140 |  | Joy Schneider
6724 | 2140 | Future Task |  |  | D693 | Joy Schneider | Review | DED D693 - Exit Transition Completion - Collaborative Review | 12 hrs | 10 days | Tue 1/19/27 | Mon 2/1/27 | 2139 | 2141 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6725 | 2141 | Future Task |  |  | D693 | Joy Schneider | Approve | DED D693 - Exit Transition Completion - Approve | 0 hrs | 0 days | Mon 2/1/27 | Mon 2/1/27 | 2140 | 2142FS+69 days |  | Jimmy Cox
6726 | 2142 | Future Task |  |  | D693 | Joy Schneider | Create | D693 - Review Status of Exit Transition Work Plan | 45 hrs | 15 days | Mon 5/10/27 | Fri 5/28/27 | 2141FS+69 days | 2143 |  | Joy Schneider,Matt Cole,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
6727 | 2143 | Future Task |  |  | D693 | Joy Schneider | Create | D693 - Obtain Department Sign Off | 30 hrs | 15 days | Tue 6/1/27 | Mon 6/21/27 | 2142 | 2144 |  | Sean Buchanan,Matt Cole
6728 | 2144 | Future Task |  |  | D693 | Joy Schneider | Submit | DEL D693 - Exit Transition Completion - Draft Submission | 0 hrs | 0 days | Mon 6/21/27 | Mon 6/21/27 | 2143 | 2145 |  | Joy Schneider
6729 | 2145 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Pre-Submission Collaborative Review | 6 hrs | 5 days | Tue 6/22/27 | Mon 6/28/27 | 2144 | 2146 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6730 | 2146 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Style Guide Review | 1 hr | 1 day | Tue 6/29/27 | Tue 6/29/27 | 2145 | 2147 |  | Dusti Kincl
6731 | 2147 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Final Collaborative Review | 6 hrs | 5 days | Wed 6/30/27 | Wed 7/7/27 | 2146 | 2148 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6732 | 2148 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Accenture QC | 4 hrs | 2 days | Thu 7/8/27 | Fri 7/9/27 | 2147 | 2149 |  | Joy Schneider
6733 | 2149 | Future Task |  |  | D693 | Joy Schneider | Submit | DEL D693 - Exit Transition Completion - Submit | 0 hrs | 0 days | Fri 7/9/27 | Fri 7/9/27 | 2148 | 2150 |  | Joy Schneider
6734 | 2150 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Department QC | 4 hrs | 1 day | Mon 7/12/27 | Mon 7/12/27 | 2149 | 2151 |  | Tommy Werner
6735 | 2151 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Contract Manager Review | 8 hrs | 3 days | Tue 7/13/27 | Thu 7/15/27 | 2150 | 2152 |  | Sean Buchanan
6736 | 2152 | Future Task |  |  | D693 | Joy Schneider | Accept | DEL D693 - Exit Transition Completion - Accept | 0 hrs | 0 days | Thu 7/15/27 | Thu 7/15/27 | 2151 |  | 2027-07-01 | Sean Buchanan
5655 | 2153 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 - Exit Transition Work Plan | 398 hrs | 121 days | Mon 7/6/26 | Mon 12/28/26
5656 | 2154 | Future Task |  |  | WP428 | Joy Schneider | Create | WPED WP428 - Exit Transition Work Plan - Create | 8 hrs | 10 days | Mon 7/6/26 | Fri 7/17/26 | 1 | 2155 |  | Joy Schneider
5657 | 2155 | Future Task |  |  | WP428 | Joy Schneider | Submit | WPED WP428 - Exit Transition Work Plan - Submit | 0 hrs | 0 days | Fri 7/17/26 | Fri 7/17/26 | 2154 | 2156 |  | Joy Schneider
5658 | 2156 | Future Task |  |  | WP428 | Joy Schneider | Review | WPED WP428 - Exit Transition Work Plan - Review | 16 hrs | 10 days | Mon 7/20/26 | Fri 7/31/26 | 2155 | 2157 |  | Joy Schneider,Jimmy Cox,Angie Robertson,Sean Buchanan
5659 | 2157 | Future Task |  |  | WP428 | Joy Schneider | Approve | WPED WP428 - Exit Transition Work Plan - Approve | 0 hrs | 0 days | Fri 7/31/26 | Fri 7/31/26 | 2156 | 2158FS+41 days |  | Jimmy Cox
5660 | 2158 | Future Task |  |  | WP428 | Joy Schneider | Create | WP428 - Develop Exit Transition Work Plan | 210 hrs | 15 days | Wed 9/30/26 | Tue 10/20/26 | 2157FS+41 days | 2159 |  | Joy Schneider,Stacey Terry,Manojkumar Gurjar,Matt Cole,Angie Robertson,Jimmy Cox,Francisca Li
5661 | 2159 | Future Task |  |  | WP428 | Joy Schneider | Create | WP428 - Determine Entry and Exit Criteria | 120 hrs | 15 days | Wed 10/21/26 | Tue 11/10/26 | 2158 | 2160 |  | Joy Schneider,Matt Cole,Angie Robertson,Jimmy Cox
5662 | 2160 | Future Task |  |  | WP428 | Joy Schneider | Create | WP428 - Review and Confirm Exit Transition Plan | 20 hrs | 15 days | Thu 11/12/26 | Fri 12/4/26 | 2159 | 2161 |  | Jimmy Cox,Angie Robertson,Joy Schneider
5663 | 2161 | Future Task |  |  | WP428 | Joy Schneider | Submit | WP WP428 - Exit Transition Work Plan - Submit | 0 hrs | 0 days | Fri 12/4/26 | Fri 12/4/26 | 2160 | 2162 |  | Joy Schneider
5664 | 2162 | Future Task |  |  | WP428 | Joy Schneider | Review | WP WP428 - Exit Transition Work Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 12/7/26 | Fri 12/18/26 | 2161 | 2163 |  | Joy Schneider,Jimmy Cox,Angie Robertson
5665 | 2163 | Future Task |  |  | WP428 | Joy Schneider | Review | WP WP428 - Exit Transition Work Plan - Final Review & Edits | 12 hrs | 5 days | Mon 12/21/26 | Mon 12/28/26 | 2162 | 2164 |  | Joy Schneider,Jimmy Cox,Angie Robertson
5666 | 2164 | Future Task |  |  | WP428 | Joy Schneider | Approve | WP WP428 - Exit Transition Work Plan - Approve | 0 hrs | 0 days | Mon 12/28/26 | Mon 12/28/26 | 2163 | 2138 |  | Jimmy Cox
4 | 2165 | Late | [5 empty] | Administrative Tasks | 2,020.33 hrs | 1174 days | Mon 5/1/23 | Tue 12/28/27
10 | 2166 | Late | [5 empty] | Administrative Activities | 1,256 hrs | 1152 days | Thu 6/1/23 | Tue 12/28/27
2063 | 2167 | Late |  |  |  | Tommy Werner |  | Budget | 308 hrs | 933 days | Thu 6/1/23 | Mon 2/15/27
2064 | 2168 | Late |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q1 | 14 hrs | 30 days | Thu 6/1/23 | Thu 7/13/23
2065 | 2169 | Late |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Thu 6/1/23 | Wed 6/14/23 |  | 2170,2194SS |  | Tommy Werner,Gabriela Gibson
2066 | 2170 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Thu 6/15/23 | Wed 6/28/23 | 2169 | 2171 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2067 | 2171 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Thu 6/29/23 | Thu 7/13/23 | 2170 | 2172 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2068 | 2172 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Thu 7/13/23 | Thu 7/13/23 | 2171 | 2175 |  | Tommy Werner
2069 | 2173 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q2 | 14 hrs | 30 days | Mon 7/3/23 | Mon 8/14/23
2070 | 2174 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 |  | 2175 |  | Tommy Werner,Gabriela Gibson
2071 | 2175 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 21742172 | 2176 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2072 | 2176 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 2175 | 2177 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2073 | 2177 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 2176 | 2179 |  | Tommy Werner
2074 | 2178 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q3 | 14 hrs | 30 days | Mon 10/2/23 | Mon 11/13/23
2075 | 2179 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 2177 | 2180 |  | Tommy Werner,Gabriela Gibson
2076 | 2180 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 2179 | 2181 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2077 | 2181 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 10/30/23 | Mon 11/13/23 | 2180 | 2182 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2078 | 2182 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 11/13/23 | Mon 11/13/23 | 2181 | 2184 |  | Tommy Werner
2079 | 2183 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q4 | 14 hrs | 30 days | Tue 1/2/24 | Tue 2/13/24
2080 | 2184 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Tue 1/2/24 | Tue 1/16/24 | 2182 | 2185 |  | Tommy Werner,Gabriela Gibson
2081 | 2185 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Wed 1/17/24 | Tue 1/30/24 | 2184 | 2186 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2082 | 2186 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Wed 1/31/24 | Tue 2/13/24 | 2185 | 2187 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2083 | 2187 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Tue 2/13/24 | Tue 2/13/24 | 2186 | 2199 |  | Tommy Werner
2084 | 2188 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 24-25 | 14 hrs | 30 days | Wed 5/1/24 | Wed 6/12/24
2085 | 2189 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 24-25 - Create | 4 hrs | 10 days | Wed 5/1/24 | Tue 5/14/24 | 2197 | 2190 |  | Tommy Werner,Gabriela Gibson
2086 | 2190 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 24-25 - Collaborative Review & Update | 4 hrs | 10 days | Wed 5/15/24 | Wed 5/29/24 | 2189 | 2191 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2087 | 2191 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 24-25 - Final Review & Edit | 6 hrs | 10 days | Thu 5/30/24 | Wed 6/12/24 | 2190 | 2192 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2088 | 2192 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 2191 | 2201 |  | Tommy Werner
2089 | 2193 | Late |  |  |  | Tommy Werner |  | Legislative Budget Request FY 24-25 | 14 hrs | 40 days | Thu 6/1/23 | Thu 7/27/23
2090 | 2194 | Late |  |  |  | Tommy Werner | Create | LBR FY 24-25 - Create | 4 hrs | 20 days | Thu 6/1/23 | Wed 6/28/23 | 2169SS | 2195 |  | Tommy Werner,Gabriela Gibson
2091 | 2195 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 24-25 - Collaborative Review & Update | 4 hrs | 10 days | Thu 6/29/23 | Thu 7/13/23 | 2194 | 2196 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2092 | 2196 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 24-25 - Final Review & Edit | 6 hrs | 10 days | Fri 7/14/23 | Thu 7/27/23 | 2195 | 2197 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2093 | 2197 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | Thu 7/27/23 | Thu 7/27/23 | 2196 | 22242189 |  | Tommy Werner
2094 | 2198 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q1 | 14 hrs | 30 days | Mon 6/3/24 | Mon 7/15/24
2095 | 2199 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 2187 | 22002204 |  | Tommy Werner,Gabriela Gibson
2096 | 2200 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 2199 | 2201 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2097 | 2201 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 22002192 | 2202 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2098 | 2202 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 7/15/24 | Mon 7/15/24 | 2201 | 2205 |  | Tommy Werner
2099 | 2203 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q2 | 14 hrs | 30 days | Mon 7/1/24 | Mon 8/12/24
2100 | 2204 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 2199 | 2205 |  | Tommy Werner,Gabriela Gibson
2101 | 2205 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Tue 7/16/24 | Mon 7/29/24 | 22042202 | 2206 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2102 | 2206 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Tue 7/30/24 | Mon 8/12/24 | 2205 | 2207 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2103 | 2207 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 8/12/24 | Mon 8/12/24 | 2206 | 2209 |  | Tommy Werner
2104 | 2208 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q3 | 14 hrs | 30 days | Tue 10/1/24 | Tue 11/12/24
2105 | 2209 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Tue 10/1/24 | Mon 10/14/24 | 2207 | 2210 |  | Tommy Werner,Gabriela Gibson
2106 | 2210 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Tue 10/15/24 | Mon 10/28/24 | 2209 | 2211 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2107 | 2211 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Tue 10/29/24 | Tue 11/12/24 | 2210 | 2212 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2108 | 2212 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Tue 11/12/24 | Tue 11/12/24 | 2211 | 2214 |  | Tommy Werner
2109 | 2213 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q4 | 14 hrs | 30 days | Thu 1/2/25 | Thu 2/13/25
2110 | 2214 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Thu 1/2/25 | Wed 1/15/25 | 2212 | 2215 |  | Tommy Werner,Gabriela Gibson
2111 | 2215 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Thu 1/16/25 | Thu 1/30/25 | 2214 | 2216 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2112 | 2216 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Fri 1/31/25 | Thu 2/13/25 | 2215 | 2217 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2113 | 2217 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Thu 2/13/25 | Thu 2/13/25 | 2216 | 2229 |  | Tommy Werner
2114 | 2218 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 25-26 | 14 hrs | 30 days | Thu 5/1/25 | Thu 6/12/25
2115 | 2219 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 25-26 - Create | 4 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 2227 | 2220 |  | Tommy Werner,Gabriela Gibson
2116 | 2220 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 25-26 - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/15/25 | Thu 5/29/25 | 2219 | 2221 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2117 | 2221 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 25-26 - Final Review & Edit | 6 hrs | 10 days | Fri 5/30/25 | Thu 6/12/25 | 2220 | 2222 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2118 | 2222 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | Thu 6/12/25 | Thu 6/12/25 | 2221 |  |  | Tommy Werner
2119 | 2223 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 25-26 | 14 hrs | 40 days | Mon 6/3/24 | Mon 7/29/24
2120 | 2224 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 25-26 - Create | 4 hrs | 20 days | Mon 6/3/24 | Fri 6/28/24 | 2197 | 2225 |  | Tommy Werner,Gabriela Gibson
2121 | 2225 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 25-26 - Collaborative Review & Update | 4 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 2224 | 2226 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2122 | 2226 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 25-26 - Final Review & Edit | 6 hrs | 10 days | Tue 7/16/24 | Mon 7/29/24 | 2225 | 2227 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2123 | 2227 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | Mon 7/29/24 | Mon 7/29/24 | 2226 | 22542219 |  | Tommy Werner
2124 | 2228 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q1 | 14 hrs | 30 days | Mon 6/2/25 | Mon 7/14/25
2125 | 2229 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Mon 6/2/25 | Fri 6/13/25 | 2217 | 22302234 |  | Tommy Werner,Gabriela Gibson
2126 | 2230 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Mon 6/16/25 | Fri 6/27/25 | 2229 | 2231 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2127 | 2231 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 6/30/25 | Mon 7/14/25 | 2230 | 2232 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2128 | 2232 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 7/14/25 | Mon 7/14/25 | 2231 | 2235 |  | Tommy Werner
2129 | 2233 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q2 | 14 hrs | 30 days | Tue 7/1/25 | Tue 8/12/25
2130 | 2234 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Tue 7/1/25 | Tue 7/15/25 | 2229 | 2235 |  | Tommy Werner,Gabriela Gibson
2131 | 2235 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Wed 7/16/25 | Tue 7/29/25 | 22342232 | 2236 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2132 | 2236 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Wed 7/30/25 | Tue 8/12/25 | 2235 | 2237 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2133 | 2237 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Tue 8/12/25 | Tue 8/12/25 | 2236 | 2239 |  | Tommy Werner
2134 | 2238 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q3 | 14 hrs | 30 days | Wed 10/1/25 | Wed 11/12/25
2135 | 2239 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Wed 10/1/25 | Tue 10/14/25 | 2237 | 2240 |  | Tommy Werner,Gabriela Gibson
2136 | 2240 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Wed 10/15/25 | Tue 10/28/25 | 2239 | 2241 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2137 | 2241 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Wed 10/29/25 | Wed 11/12/25 | 2240 | 2242 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2138 | 2242 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Wed 11/12/25 | Wed 11/12/25 | 2241 | 2244 |  | Tommy Werner
2139 | 2243 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q4 | 14 hrs | 30 days | Fri 1/2/26 | Fri 2/13/26
2140 | 2244 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Fri 1/2/26 | Thu 1/15/26 | 2242 | 2245 |  | Tommy Werner,Gabriela Gibson
2141 | 2245 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Fri 1/16/26 | Fri 1/30/26 | 2244 | 2246 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2142 | 2246 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 2/2/26 | Fri 2/13/26 | 2245 | 2247 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2143 | 2247 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Fri 2/13/26 | Fri 2/13/26 | 2246 | 2259 |  | Tommy Werner
2144 | 2248 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 26-27 | 14 hrs | 30 days | Fri 5/1/26 | Fri 6/12/26
2145 | 2249 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 26-27 - Create | 4 hrs | 10 days | Fri 5/1/26 | Thu 5/14/26 | 2257 | 2250 |  | Tommy Werner,Gabriela Gibson
2146 | 2250 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 26-27 - Collaborative Review & Update | 4 hrs | 10 days | Fri 5/15/26 | Fri 5/29/26 | 2249 | 2251 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2147 | 2251 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 26-27 - Final Review & Edit | 6 hrs | 10 days | Mon 6/1/26 | Fri 6/12/26 | 2250 | 2252 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2148 | 2252 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | Fri 6/12/26 | Fri 6/12/26 | 2251 |  |  | Tommy Werner
2149 | 2253 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 26-27 | 14 hrs | 40 days | Mon 6/2/25 | Mon 7/28/25
2150 | 2254 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 26-27 - Create | 4 hrs | 20 days | Mon 6/2/25 | Fri 6/27/25 | 2227 | 2255 |  | Tommy Werner,Gabriela Gibson
2151 | 2255 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 26-27 - Collaborative Review & Update | 4 hrs | 10 days | Mon 6/30/25 | Mon 7/14/25 | 2254 | 2256 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2152 | 2256 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 26-27 - Final Review & Edit | 6 hrs | 10 days | Tue 7/15/25 | Mon 7/28/25 | 2255 | 2257 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2153 | 2257 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | Mon 7/28/25 | Mon 7/28/25 | 2256 | 2249 |  | Tommy Werner
2154 | 2258 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q1 | 14 hrs | 30 days | Mon 6/1/26 | Mon 7/13/26
2155 | 2259 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Mon 6/1/26 | Fri 6/12/26 | 2247 | 22602264 |  | Tommy Werner,Gabriela Gibson
2156 | 2260 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Mon 6/15/26 | Fri 6/26/26 | 2259 | 2261 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2157 | 2261 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 6/29/26 | Mon 7/13/26 | 2260 | 2262 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2158 | 2262 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 7/13/26 | Mon 7/13/26 | 2261 | 2265 |  | Tommy Werner
2159 | 2263 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q2 | 14 hrs | 30 days | Wed 7/1/26 | Wed 8/12/26
2160 | 2264 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Wed 7/1/26 | Wed 7/15/26 | 2259 | 2265 |  | Tommy Werner,Gabriela Gibson
2161 | 2265 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Thu 7/16/26 | Wed 7/29/26 | 22642262 | 2266 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2162 | 2266 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Thu 7/30/26 | Wed 8/12/26 | 2265 | 2267 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2163 | 2267 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Wed 8/12/26 | Wed 8/12/26 | 2266 | 2269 |  | Tommy Werner
2164 | 2268 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q3 | 14 hrs | 30 days | Thu 10/1/26 | Thu 11/12/26
2165 | 2269 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Thu 10/1/26 | Wed 10/14/26 | 2267 | 2270 |  | Tommy Werner,Gabriela Gibson
2166 | 2270 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Thu 10/15/26 | Wed 10/28/26 | 2269 | 2271 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2167 | 2271 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Thu 10/29/26 | Thu 11/12/26 | 2270 | 2272 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2168 | 2272 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Thu 11/12/26 | Thu 11/12/26 | 2271 | 2274 |  | Tommy Werner
2169 | 2273 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q4 | 14 hrs | 30 days | Mon 1/4/27 | Mon 2/15/27
2170 | 2274 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Mon 1/4/27 | Fri 1/15/27 | 2272 | 2275 |  | Tommy Werner,Gabriela Gibson
2171 | 2275 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Tue 1/19/27 | Mon 2/1/27 | 2274 | 2276 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2172 | 2276 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Tue 2/2/27 | Mon 2/15/27 | 2275 | 2277 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2173 | 2277 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 2/15/27 | Mon 2/15/27 | 2276 |  |  | Tommy Werner
2174 | 2278 | Future Task | [5 empty] | Project Resources | 948 hrs | 1131 days | Fri 6/30/23 | Tue 12/28/27
2175 | 2279 | Future Task |  |  |  | Tommy Werner |  | Project Management Plan | 462 hrs | 1045 days | Wed 11/1/23 | Tue 12/28/27
2176 | 2280 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2023 | 54 hrs | 38 days | Wed 11/1/23 | Thu 12/28/23
2177 | 2281 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Wed 11/1/23 | Fri 12/1/23 |  | 2282 |  | Joy Schneider,Tommy Werner,Francisca Li,Jenifer Hartsfield,Gabriela Gibson
2178 | 2282 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Mon 12/4/23 | Fri 12/15/23 | 2281 | 2283 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2179 | 2283 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Mon 12/18/23 | Fri 12/22/23 | 2282 | 2284 |  | Jimmy Cox
2180 | 2284 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 4 hrs | 3 days | Tue 12/26/23 | Thu 12/28/23 | 2283 | 2286 |  | Tatiana Eubanks
2181 | 2285 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2024 | 51 hrs | 38 days | Fri 5/3/24 | Wed 6/26/24
2182 | 2286 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Fri 5/3/24 | Fri 5/31/24 | 2284 | 2287 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2183 | 2287 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 2286 | 2288 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2184 | 2288 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Mon 6/17/24 | Fri 6/21/24 | 2287 | 2289 |  | Jimmy Cox
2185 | 2289 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Mon 6/24/24 | Wed 6/26/24 | 2288 | 2291 |  | Tatiana Eubanks
2186 | 2290 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2024 | 51 hrs | 38 days | Mon 11/4/24 | Tue 12/31/24
2187 | 2291 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/4/24 | Wed 12/4/24 | 2289 | 2292 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2188 | 2292 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Thu 12/5/24 | Wed 12/18/24 | 2291 | 2293 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2189 | 2293 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Thu 12/19/24 | Thu 12/26/24 | 2292 | 2294 |  | Jimmy Cox
2190 | 2294 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Fri 12/27/24 | Tue 12/31/24 | 2293 | 2296 |  | Tatiana Eubanks
2191 | 2295 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2025 | 51 hrs | 38 days | Fri 5/2/25 | Wed 6/25/25
2192 | 2296 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Fri 5/2/25 | Fri 5/30/25 | 2294 | 2297 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2193 | 2297 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Mon 6/2/25 | Fri 6/13/25 | 2296 | 2298 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2194 | 2298 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Mon 6/16/25 | Fri 6/20/25 | 2297 | 2299 |  | Jimmy Cox
2195 | 2299 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Mon 6/23/25 | Wed 6/25/25 | 2298 | 2301 |  | Tatiana Eubanks
2196 | 2300 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2025 | 51 hrs | 38 days | Mon 11/3/25 | Tue 12/30/25
2197 | 2301 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/3/25 | Wed 12/3/25 | 2299 | 2302 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2198 | 2302 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Thu 12/4/25 | Wed 12/17/25 | 2301 | 2303 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2199 | 2303 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Thu 12/18/25 | Wed 12/24/25 | 2302 | 2304 |  | Jimmy Cox
2200 | 2304 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Fri 12/26/25 | Tue 12/30/25 | 2303 | 2306 |  | Tatiana Eubanks
2201 | 2305 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2026 | 51 hrs | 38 days | Fri 5/1/26 | Wed 6/24/26
2202 | 2306 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Fri 5/1/26 | Fri 5/29/26 | 2304 | 2307 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2203 | 2307 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Mon 6/1/26 | Fri 6/12/26 | 2306 | 2308 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2204 | 2308 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Mon 6/15/26 | Fri 6/19/26 | 2307 | 2309 |  | Jimmy Cox
2205 | 2309 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Mon 6/22/26 | Wed 6/24/26 | 2308 | 2311 |  | Tatiana Eubanks
2206 | 2310 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2026 | 51 hrs | 38 days | Mon 11/2/26 | Tue 12/29/26
2207 | 2311 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/2/26 | Wed 12/2/26 | 2309 | 2312 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2208 | 2312 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Thu 12/3/26 | Wed 12/16/26 | 2311 | 2313 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2209 | 2313 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Thu 12/17/26 | Wed 12/23/26 | 2312 | 2314 |  | Jimmy Cox
2210 | 2314 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Thu 12/24/26 | Tue 12/29/26 | 2313 | 2316 |  | Tatiana Eubanks
2211 | 2315 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2027 | 51 hrs | 38 days | Mon 5/3/27 | Thu 6/24/27
2212 | 2316 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 5/3/27 | Fri 5/28/27 | 2314 | 2317 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2213 | 2317 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Tue 6/1/27 | Mon 6/14/27 | 2316 | 2318 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2214 | 2318 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Tue 6/15/27 | Mon 6/21/27 | 2317 | 2319 |  | Jimmy Cox
2215 | 2319 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Tue 6/22/27 | Thu 6/24/27 | 2318 | 2321 |  | Tatiana Eubanks
2216 | 2320 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2027 | 51 hrs | 38 days | Mon 11/1/27 | Tue 12/28/27
2217 | 2321 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/1/27 | Wed 12/1/27 | 2319 | 2322 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2218 | 2322 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Thu 12/2/27 | Wed 12/15/27 | 2321 | 2323 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2219 | 2323 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Thu 12/16/27 | Wed 12/22/27 | 2322 | 2324 |  | Jimmy Cox
2220 | 2324 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Thu 12/23/27 | Tue 12/28/27 | 2323 |  |  | Tatiana Eubanks
2221 | 2325 | Future Task |  |  |  | Dusti Kincl |  | Florida PALM Style Guide | 104 hrs | 910 days | Wed 11/1/23 | Mon 6/14/27
2222 | 2326 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 23-24 | 13 hrs | 30 days | Wed 11/1/23 | Fri 12/15/23
2223 | 2327 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Wed 11/1/23 | Wed 11/22/23 |  | 2328 |  | Tatiana Eubanks,Elizabeth Gabert
2224 | 2328 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Mon 11/27/23 | Fri 12/8/23 | 2327 | 2329 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2225 | 2329 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Mon 12/11/23 | Fri 12/15/23 | 2328 | 2331 |  | Jimmy Cox
2226 | 2330 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 23-24 | 13 hrs | 30 days | Wed 5/1/24 | Wed 6/12/24
2227 | 2331 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Wed 5/1/24 | Tue 5/21/24 | 2329 | 2332 |  | Tatiana Eubanks,Elizabeth Gabert
2228 | 2332 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Wed 5/22/24 | Wed 6/5/24 | 2331 | 2333 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2229 | 2333 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Thu 6/6/24 | Wed 6/12/24 | 2332 | 2335 |  | Jimmy Cox
2230 | 2334 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 24-25 | 13 hrs | 30 days | Mon 11/4/24 | Wed 12/18/24
2231 | 2335 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 11/4/24 | Mon 11/25/24 | 2333 | 2336 |  | Tatiana Eubanks,Elizabeth Gabert
2232 | 2336 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Tue 11/26/24 | Wed 12/11/24 | 2335 | 2337 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2233 | 2337 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Thu 12/12/24 | Wed 12/18/24 | 2336 | 2339 |  | Jimmy Cox
2234 | 2338 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 24-25 | 13 hrs | 30 days | Thu 5/1/25 | Thu 6/12/25
2235 | 2339 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Thu 5/1/25 | Wed 5/21/25 | 2337 | 2340 |  | Tatiana Eubanks,Elizabeth Gabert
2236 | 2340 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/22/25 | Thu 6/5/25 | 2339 | 2341 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2237 | 2341 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Fri 6/6/25 | Thu 6/12/25 | 2340 | 2343 |  | Jimmy Cox
2238 | 2342 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 25-26 | 13 hrs | 30 days | Mon 11/3/25 | Wed 12/17/25
2239 | 2343 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 11/3/25 | Mon 11/24/25 | 2341 | 2344 |  | Tatiana Eubanks,Elizabeth Gabert
2240 | 2344 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Tue 11/25/25 | Wed 12/10/25 | 2343 | 2345 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2241 | 2345 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Thu 12/11/25 | Wed 12/17/25 | 2344 | 2347 |  | Jimmy Cox
2242 | 2346 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 25-26 | 13 hrs | 30 days | Mon 4/6/26 | Fri 5/15/26
2243 | 2347 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 4/6/26 | Fri 4/24/26 | 2345 | 2348 |  | Tatiana Eubanks,Elizabeth Gabert
2244 | 2348 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Mon 4/27/26 | Fri 5/8/26 | 2347 | 2349 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2245 | 2349 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Mon 5/11/26 | Fri 5/15/26 | 2348 | 2351 |  | Jimmy Cox
2246 | 2350 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 26-27 | 13 hrs | 30 days | Mon 11/2/26 | Wed 12/16/26
2247 | 2351 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 11/2/26 | Mon 11/23/26 | 2349 | 2352 |  | Tatiana Eubanks,Elizabeth Gabert
2248 | 2352 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Tue 11/24/26 | Wed 12/9/26 | 2351 | 2353 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2249 | 2353 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Thu 12/10/26 | Wed 12/16/26 | 2352 | 2355 |  | Jimmy Cox
2250 | 2354 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 26-27 | 13 hrs | 30 days | Mon 5/3/27 | Mon 6/14/27
2251 | 2355 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 5/3/27 | Fri 5/21/27 | 2353 | 2356 |  | Tatiana Eubanks,Elizabeth Gabert
2252 | 2356 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Mon 5/24/27 | Mon 6/7/27 | 2355 | 2357 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2253 | 2357 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Tue 6/8/27 | Mon 6/14/27 | 2356 |  |  | Jimmy Cox
2254 | 2358 | Future Task | [5 empty] | Project Team Orientation Guide | 238 hrs | 252 days | Fri 6/30/23 | Fri 6/28/24
6683 | 2359 | Future Task |  |  | WP401 | Joy Schneider |  | WP401 - Project Orientation Guide | 88 hrs | 61 days | Fri 6/30/23 | Tue 9/26/23
6684 | 2360 | Future Task |  |  | WP401 | Joy Schneider | Create | WPED WP401 - Project Orientation Guide - Create | 8 hrs | 10 days | Fri 6/30/23 | Fri 7/14/23 | 32 | 2361 |  | Joy Schneider
6685 | 2361 | Future Task |  |  | WP401 | Joy Schneider | Submit | WPED WP401 - Project Orientation Guide - Submit | 0 hrs | 0 days | Fri 7/14/23 | Fri 7/14/23 | 2360 | 2362 |  | Joy Schneider
6686 | 2362 | Future Task |  |  | WP401 | Joy Schneider | Review | WPED WP401 - Project Orientation Guide - Review | 16 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 | 2361 | 2363 |  | Joy Schneider,Jimmy Cox,Angie Robertson,Sean Buchanan
6687 | 2363 | Future Task |  |  | WP401 | Joy Schneider | Approve | WPED WP401 - Project Orientation Guide - Approve | 0 hrs | 0 days | Fri 7/28/23 | Fri 7/28/23 | 2362 | 2364FS+11 days |  | Jimmy Cox
6688 | 2364 | Future Task |  |  | WP401 | Joy Schneider | Create | WP401 - Update Project Team Orientation Guide | 10 hrs | 5 days | Tue 8/15/23 | Mon 8/21/23 | 2363FS+11 days | 2365 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
6689 | 2365 | Future Task |  |  | WP401 | Joy Schneider | Create | WP401 - Project Team Orientation Guide - Collaborative Review & Update | 10 hrs | 5 days | Tue 8/22/23 | Mon 8/28/23 | 2364 | 2366 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
6690 | 2366 | Future Task |  |  | WP401 | Joy Schneider | Create | WP401 - Project Team Orientation Guide - Final Review & Update | 20 hrs | 5 days | Tue 8/29/23 | Tue 9/5/23 | 2365 | 2367 |  | Angie Robertson[25%],Jimmy Cox[25%]
6691 | 2367 | Future Task |  |  | WP401 | Joy Schneider | Submit | WP WP401 - Project Orientation Guide - Submit | 0 hrs | 0 days | Tue 9/5/23 | Tue 9/5/23 | 2366 | 2368 |  | Joy Schneider
6692 | 2368 | Future Task |  |  | WP401 | Joy Schneider | Review | WP WP401 - Project Orientation Guide - Collaborative Review & Update | 12 hrs | 10 days | Wed 9/6/23 | Tue 9/19/23 | 2367 | 2369 |  | Joy Schneider,Jimmy Cox,Angie Robertson
6693 | 2369 | Future Task |  |  | WP401 | Joy Schneider | Review | WP WP401 - Project Orientation Guide - Final Review & Edits | 12 hrs | 5 days | Wed 9/20/23 | Tue 9/26/23 | 2368 | 2370 |  | Joy Schneider,Jimmy Cox,Angie Robertson
6694 | 2370 | Future Task |  |  | WP401 | Joy Schneider | Approve | WP WP401 - Project Orientation Guide - Approve | 0 hrs | 0 days | Tue 9/26/23 | Tue 9/26/23 | 2369 | 2372FS-6 days | 2023-10-01 | Jimmy Cox
2255 | 2371 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q1 | 30 hrs | 15 days | Tue 9/19/23 | Mon 10/9/23
2257 | 2372 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Tue 9/19/23 | Mon 9/25/23 | 2370FS-6 days | 2373 |  | Jenifer Hartsfield,Gabriela Gibson
2258 | 2373 | Future Task |  |  |  | Julian Gotreaux | Review | FPO - Collaborative Review & Update | 10 hrs | 5 days | Tue 9/26/23 | Mon 10/2/23 | 2372 | 2374 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2259 | 2374 | Future Task |  |  |  | Julian Gotreaux | Review | FPO - Final Review & Update | 10 hrs | 5 days | Tue 10/3/23 | Mon 10/9/23 | 2373 | 2376 |  | Angie Robertson,Jimmy Cox
2260 | 2375 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q2 | 40 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23
2261 | 2376 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | Fri 12/1/23 | Thu 12/7/23 | 2374 | 2377 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2262 | 2377 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Fri 12/8/23 | Thu 12/14/23 | 2376 | 2378 |  | Jenifer Hartsfield,Gabriela Gibson
2263 | 2378 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review & Update | 10 hrs | 5 days | Fri 12/15/23 | Thu 12/21/23 | 2377 | 2379 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2264 | 2379 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review & Update | 10 hrs | 5 days | Fri 12/22/23 | Fri 12/29/23 | 2378 | 2381 |  | Angie Robertson,Jimmy Cox
2265 | 2380 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q3 | 40 hrs | 20 days | Fri 3/1/24 | Thu 3/28/24
2266 | 2381 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 2379 | 2382 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2267 | 2382 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Fri 3/8/24 | Thu 3/14/24 | 2381 | 2383 |  | Jenifer Hartsfield,Gabriela Gibson
2268 | 2383 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review & Update | 10 hrs | 5 days | Fri 3/15/24 | Thu 3/21/24 | 2382 | 2384 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2269 | 2384 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review & Update | 10 hrs | 5 days | Fri 3/22/24 | Thu 3/28/24 | 2383 | 2386 |  | Angie Robertson,Jimmy Cox
2270 | 2385 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q4 | 40 hrs | 20 days | Mon 6/3/24 | Fri 6/28/24
2271 | 2386 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | Mon 6/3/24 | Fri 6/7/24 | 2384 | 2387 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2272 | 2387 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Mon 6/10/24 | Fri 6/14/24 | 2386 | 2388 |  | Jenifer Hartsfield,Gabriela Gibson
2273 | 2388 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review & Update | 10 hrs | 5 days | Mon 6/17/24 | Fri 6/21/24 | 2387 | 2389 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2274 | 2389 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review & Update | 10 hrs | 5 days | Mon 6/24/24 | Fri 6/28/24 | 2388 |  |  | Angie Robertson,Jimmy Cox
2275 | 2390 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 23-24 | 28 hrs | 134 days | Mon 7/17/23 | Mon 1/29/24
2276 | 2391 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 23-24 Q1 | 4 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 |  | 23922393 |  | Gabriela Gibson[5%]
2277 | 2392 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 23-24 Q3 | 4 hrs | 10 days | Tue 1/16/24 | Mon 1/29/24 | 2391 | 2399 |  | Gabriela Gibson
2278 | 2393 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 23-24 | 4 hrs | 10 days | Tue 8/15/23 | Mon 8/28/23 | 2391 | 2394 |  | Jenifer Hartsfield
2279 | 2394 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 23-24 | 4 hrs | 10 days | Fri 9/15/23 | Thu 9/28/23 | 2393 | 2395 |  | Tommy Werner
2280 | 2395 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 23-24 | 4 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 2394 | 2396 |  | Gabriela Gibson
2281 | 2396 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 23-24 | 4 hrs | 10 days | Wed 11/15/23 | Thu 11/30/23 | 2395 | 2397 |  | Tommy Werner
2282 | 2397 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 23-24 | 4 hrs | 10 days | Fri 12/15/23 | Fri 12/29/23 | 2396 | 2401 |  | Tommy Werner
2283 | 2398 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 24-25 | 28 hrs | 136 days | Mon 7/15/24 | Wed 1/29/25
2284 | 2399 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 24-25 Q1 | 4 hrs | 10 days | Mon 7/15/24 | Fri 7/26/24 | 2392 | 2400 |  | Gabriela Gibson
2285 | 2400 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 24-25 Q3 | 4 hrs | 10 days | Wed 1/15/25 | Wed 1/29/25 | 2399 | 2407 |  | Gabriela Gibson
2286 | 2401 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 24-25 | 4 hrs | 10 days | Thu 8/15/24 | Wed 8/28/24 | 2397 | 2402 |  | Jenifer Hartsfield
2287 | 2402 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 24-25 | 4 hrs | 10 days | Mon 9/16/24 | Fri 9/27/24 | 2401 | 2403 |  | Tommy Werner
2288 | 2403 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 24-25 | 4 hrs | 10 days | Tue 10/15/24 | Mon 10/28/24 | 2402 | 2404 |  | Gabriela Gibson
2289 | 2404 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 24-25 | 4 hrs | 10 days | Fri 11/15/24 | Mon 12/2/24 | 2403 | 2405 |  | Tommy Werner
2290 | 2405 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 24-25 | 4 hrs | 10 days | Mon 12/16/24 | Mon 12/30/24 | 2404 | 2409 |  | Tommy Werner
2291 | 2406 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 25-26 | 28 hrs | 136 days | Tue 7/15/25 | Thu 1/29/26
2292 | 2407 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 25-26 Q1 | 4 hrs | 10 days | Tue 7/15/25 | Mon 7/28/25 | 2400 | 2408 |  | Gabriela Gibson
2293 | 2408 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 25-26 Q3 | 4 hrs | 10 days | Thu 1/15/26 | Thu 1/29/26 | 2407 | 2415 |  | Gabriela Gibson
2294 | 2409 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 25-26 | 4 hrs | 10 days | Fri 8/15/25 | Thu 8/28/25 | 2405 | 2410 |  | Jenifer Hartsfield
2295 | 2410 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 25-26 | 4 hrs | 10 days | Mon 9/15/25 | Fri 9/26/25 | 2409 | 2411 |  | Tommy Werner
2296 | 2411 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 25-26 | 4 hrs | 10 days | Wed 10/15/25 | Tue 10/28/25 | 2410 | 2412 |  | Gabriela Gibson
2297 | 2412 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 25-26 | 4 hrs | 10 days | Mon 11/17/25 | Tue 12/2/25 | 2411 | 2413 |  | Tommy Werner
2298 | 2413 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 25-26 | 4 hrs | 10 days | Mon 12/15/25 | Mon 12/29/25 | 2412 | 2417 |  | Tommy Werner
2299 | 2414 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 26-27 | 28 hrs | 136 days | Wed 7/15/26 | Fri 1/29/27
2300 | 2415 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 26-27 Q1 | 4 hrs | 10 days | Wed 7/15/26 | Tue 7/28/26 | 2408 | 2416 |  | Gabriela Gibson
2301 | 2416 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 26-27 Q3 | 4 hrs | 10 days | Fri 1/15/27 | Fri 1/29/27 | 2415 |  |  | Gabriela Gibson
2302 | 2417 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 26-27 | 4 hrs | 10 days | Mon 8/17/26 | Fri 8/28/26 | 2413 | 2418 |  | Jenifer Hartsfield
2303 | 2418 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 26-27 | 4 hrs | 10 days | Tue 9/15/26 | Mon 9/28/26 | 2417 | 2419 |  | Tommy Werner
2304 | 2419 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 26-27 | 4 hrs | 10 days | Thu 10/15/26 | Wed 10/28/26 | 2418 | 2420 |  | Gabriela Gibson
2305 | 2420 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 26-27 | 4 hrs | 10 days | Mon 11/16/26 | Tue 12/1/26 | 2419 | 2421 |  | Tommy Werner
2306 | 2421 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 26-27 | 4 hrs | 10 days | Tue 12/15/26 | Tue 12/29/26 | 2420 |  |  | Tommy Werner
2307 | 2422 | Future Task |  |  |  | Julian Gotreaux |  | Access Control | 32 hrs | 965 days | Tue 8/15/23 | Mon 6/14/27
2308 | 2423 | Future Task |  |  |  | Julian Gotreaux |  | SharePoint Access Control | 32 hrs | 965 days | Tue 8/15/23 | Mon 6/14/27
2309 | 2424 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q1 | 2 hrs | 10 days | Tue 8/15/23 | Mon 8/28/23 |  | 2425 |  | Jenifer Hartsfield,Gabriela Gibson
2310 | 2425 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q2 | 2 hrs | 10 days | Wed 11/15/23 | Thu 11/30/23 | 2424 | 2426 |  | Jenifer Hartsfield,Gabriela Gibson
2311 | 2426 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q3 | 2 hrs | 10 days | Thu 2/15/24 | Wed 2/28/24 | 2425 | 2427 |  | Jenifer Hartsfield,Gabriela Gibson
2312 | 2427 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q4 | 2 hrs | 10 days | Wed 5/15/24 | Wed 5/29/24 | 2426 | 2428 |  | Jenifer Hartsfield,Gabriela Gibson
2313 | 2428 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q1 | 2 hrs | 10 days | Thu 8/15/24 | Wed 8/28/24 | 2427 | 2429 |  | Jenifer Hartsfield,Gabriela Gibson
2314 | 2429 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q2 | 2 hrs | 10 days | Fri 11/15/24 | Mon 12/2/24 | 2428 | 2430 |  | Jenifer Hartsfield,Gabriela Gibson
2315 | 2430 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q3 | 2 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 2429 | 2431 |  | Jenifer Hartsfield,Gabriela Gibson
2316 | 2431 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q4 | 2 hrs | 10 days | Thu 5/15/25 | Thu 5/29/25 | 2430 | 2432 |  | Jenifer Hartsfield,Gabriela Gibson
2317 | 2432 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q1 | 2 hrs | 10 days | Fri 8/15/25 | Thu 8/28/25 | 2431 | 2433 |  | Jenifer Hartsfield,Gabriela Gibson
2318 | 2433 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q2 | 2 hrs | 10 days | Mon 11/17/25 | Tue 12/2/25 | 2432 | 2434 |  | Jenifer Hartsfield,Gabriela Gibson
2319 | 2434 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q3 | 2 hrs | 10 days | Mon 2/16/26 | Fri 2/27/26 | 2433 | 2435 |  | Jenifer Hartsfield,Gabriela Gibson
2320 | 2435 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q4 | 2 hrs | 10 days | Fri 5/15/26 | Fri 5/29/26 | 2434 | 2436 |  | Jenifer Hartsfield,Gabriela Gibson
2321 | 2436 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q1 | 2 hrs | 10 days | Mon 8/17/26 | Fri 8/28/26 | 2435 | 2437 |  | Jenifer Hartsfield,Gabriela Gibson
2322 | 2437 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q2 | 2 hrs | 10 days | Mon 11/16/26 | Tue 12/1/26 | 2436 | 2438 |  | Jenifer Hartsfield,Gabriela Gibson
2323 | 2438 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q3 | 2 hrs | 10 days | Mon 2/15/27 | Fri 2/26/27 | 2437 | 2439 |  | Jenifer Hartsfield,Gabriela Gibson
2324 | 2439 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q4 | 2 hrs | 20 days | Mon 5/17/27 | Mon 6/14/27 | 2438 |  |  | Jenifer Hartsfield,Gabriela Gibson
2365 | 2440 | Late | [5 empty] | Proviso Requirements | 764.33 hrs | 1091 days | Mon 5/1/23 | Thu 8/26/27
2366 | 2441 | Future Task |  |  |  | Tommy Werner |  | Monthly Status Reporting | 112 hrs | 241 days | Tue 8/1/23 | Mon 7/15/24
2367 | 2442 | Future Task |  |  |  | Tommy Werner |  | July 2023 Monthly Status Reporting | 16 hrs | 11 days | Tue 8/1/23 | Tue 8/15/23
2368 | 2443 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | Tue 8/1/23 | Thu 8/10/23 |  | 2444SS,2445SS,2446SS |  | Tommy Werner,Gabriela Gibson
2369 | 2444 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 2443SS | 2447 |  | Tommy Werner,Joy Schneider,Francisca Li,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2370 | 2445 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | Tue 8/1/23 | Thu 8/10/23 | 2443SS | 2447 |  | Tommy Werner,Jenifer Hartsfield
2371 | 2446 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 2443SS | 2447 |  | Dusti Kincl,Nikki Klein
2372 | 2447 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Tue 8/15/23 | Tue 8/15/23 | 244624442445 | 2449 |  | Dusti Kincl,Jimmy Cox
2373 | 2448 | Future Task |  |  |  | Tommy Werner |  | August 2023 Monthly Status Reporting | 16 hrs | 10 days | Fri 9/1/23 | Fri 9/15/23
2374 | 2449 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 2447 | 2450SS,2451SS,2452SS,2453 |  | Tommy Werner,Gabriela Gibson
2375 | 2450 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Fri 9/1/23 | Thu 9/14/23 | 2449SS | 2453 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2376 | 2451 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 2449SS | 2453 |  | Tommy Werner,Jenifer Hartsfield
2377 | 2452 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Fri 9/1/23 | Thu 9/14/23 | 2449SS | 2453 |  | Dusti Kincl,Nikki Klein
2378 | 2453 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 9/15/23 | Fri 9/15/23 | 2449245024512450 |  |  | Dusti Kincl,Jimmy Cox
2385 | 2454 | Future Task |  |  |  | Tommy Werner |  | October 2023 Monthly Status Reporting | 16 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23
2386 | 2455 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | Wed 11/1/23 | Thu 11/9/23 |  | 2456SS,2457SS,2458SS,2459 |  | Tommy Werner,Gabriela Gibson
2387 | 2456 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Wed 11/1/23 | Tue 11/14/23 | 2455SS | 2459 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2388 | 2457 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | Wed 11/1/23 | Thu 11/9/23 | 2455SS | 2459 |  | Tommy Werner,Jenifer Hartsfield
2389 | 2458 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Wed 11/1/23 | Tue 11/14/23 | 2455SS | 2459 |  | Dusti Kincl,Nikki Klein
2390 | 2459 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Wed 11/15/23 | Wed 11/15/23 | 2455245624572450 |  |  | Dusti Kincl,Jimmy Cox
2397 | 2460 | Future Task |  |  |  | Tommy Werner |  | December 2023 Monthly Status Reporting | 16 hrs | 9 days | Tue 1/2/24 | Fri 1/12/24
2398 | 2461 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | Tue 1/2/24 | Tue 1/9/24 |  | 2462SS,2465,2463SS,2464SS |  | Tommy Werner,Gabriela Gibson
2399 | 2462 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 8 days | Tue 1/2/24 | Thu 1/11/24 | 2461SS | 2465 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2400 | 2463 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | Tue 1/2/24 | Tue 1/9/24 | 2461SS | 2465 |  | Tommy Werner,Jenifer Hartsfield
2401 | 2464 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 8 days | Tue 1/2/24 | Thu 1/11/24 | 2461SS | 2465 |  | Dusti Kincl,Nikki Klein
2402 | 2465 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 1/12/24 | Fri 1/12/24 | 2461246224632460 |  |  | Dusti Kincl,Jimmy Cox
2409 | 2466 | Future Task |  |  |  | Tommy Werner |  | February 2024 Monthly Status Reporting | 16 hrs | 11 days | Fri 3/1/24 | Fri 3/15/24
2410 | 2467 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | Fri 3/1/24 | Fri 3/8/24 |  | 2468SS,2469SS,2470SS,2471 |  | Tommy Werner,Gabriela Gibson
2411 | 2468 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 2467SS | 2471 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2412 | 2469 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | Fri 3/1/24 | Fri 3/8/24 | 2467SS | 2471 |  | Tommy Werner,Jenifer Hartsfield
2413 | 2470 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 2467SS | 2471 |  | Dusti Kincl,Nikki Klein
2414 | 2471 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 3/15/24 | Fri 3/15/24 | 2467246824692470 |  |  | Dusti Kincl,Jimmy Cox
2421 | 2472 | Future Task |  |  |  | Tommy Werner |  | April 2024 Monthly Status Reporting | 16 hrs | 11 days | Wed 5/1/24 | Wed 5/15/24
2422 | 2473 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | Wed 5/1/24 | Fri 5/10/24 |  | 2474SS,2475SS,2476SS,2477 |  | Tommy Werner,Gabriela Gibson
2423 | 2474 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Wed 5/1/24 | Tue 5/14/24 | 2473SS | 2477 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2424 | 2475 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | Wed 5/1/24 | Fri 5/10/24 | 2473SS | 2477 |  | Tommy Werner,Jenifer Hartsfield
2425 | 2476 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Wed 5/1/24 | Tue 5/14/24 | 2473SS | 2477 |  | Dusti Kincl,Nikki Klein
2426 | 2477 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Wed 5/15/24 | Wed 5/15/24 | 2473247424752470 |  |  | Dusti Kincl,Jimmy Cox
2433 | 2478 | Future Task |  |  |  | Tommy Werner |  | June 2024 Monthly Status Reporting | 16 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24
2434 | 2479 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | Mon 7/1/24 | Wed 7/10/24 |  | 2480SS,2481SS,2482SS |  | Tommy Werner,Gabriela Gibson
2435 | 2480 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 2479SS | 2483 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2436 | 2481 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | Mon 7/1/24 | Wed 7/10/24 | 2479SS | 2483 |  | Tommy Werner,Jenifer Hartsfield
2437 | 2482 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 2479SS | 2483 |  | Dusti Kincl,Nikki Klein
2438 | 2483 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Mon 7/15/24 | Mon 7/15/24 | 248024812482 |  |  | Dusti Kincl,Jimmy Cox
9 | 2484 | Late | [5 empty] | Monthly Performance Reporting | 520.33 hrs | 1091 days | Mon 5/1/23 | Thu 8/26/27
6232 | 2485 | Complete |  |  | D219 | Joy Schneider |  | D219 - Monthly Performance Report (April 2023) | 10.33 hrs | 24 days | Mon 5/1/23 | Fri 6/2/23
6364 | 2486 | Complete |  |  | D219 | Joy Schneider | Create | D219 - Create April 2023 Monthly Performance Report | 2.33 hrs | 7 days | Mon 5/1/23 | Tue 5/9/23 | 1 | 2487 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6233 | 2487 | Complete |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 5/10/23 | Wed 5/10/23 | 2486 | 2488 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6234 | 2488 | Complete |  |  | D219 | Joy Schneider | Submit | DEL D219 - Monthly Performance Report (April 2023) - Submit | 0 hrs | 0 days | Wed 5/10/23 | Wed 5/10/23 | 2487 | 2489 |  | Joy Schneider
6235 | 2489 | Complete |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Department QC | 2 hrs | 14 days | Thu 5/11/23 | Wed 5/31/23 | 2488 | 2490 |  | Gabriela Gibson
6236 | 2490 | Complete |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Contract Manager Review | 2 hrs | 2 days | Thu 6/1/23 | Fri 6/2/23 | 2489 | 2491 |  | Sean Buchanan
6237 | 2491 | Complete |  |  | D219 | Joy Schneider | Accept | DEL D219 - Monthly Performance Report (April 2023) - Accept | 0 hrs | 0 days | Fri 6/2/23 | Fri 6/2/23 | 2490 | 2493FS-2 days |  | Sean Buchanan
6238 | 2492 | Late |  |  | D225 | Joy Schneider |  | D225 - Monthly Performance Report (May 2023) | 10 hrs | 19 days | Thu 6/1/23 | Tue 6/27/23
6365 | 2493 | Late |  |  | D225 | Joy Schneider | Create | D225 - Create May 2023 Monthly Performance Report | 3 hrs | 9 days | Thu 6/1/23 | Tue 6/13/23 | 2491FS-2 days | 2494 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6239 | 2494 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 6/14/23 | Wed 6/14/23 | 2493 | 2495 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6240 | 2495 | Future Task |  |  | D225 | Joy Schneider | Submit | DEL D225 - Monthly Performance Report (May 2023) - Submit | 0 hrs | 0 days | Wed 6/14/23 | Wed 6/14/23 | 2494 | 2496 |  | Joy Schneider
6241 | 2496 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Department QC | 1 hr | 7 days | Thu 6/15/23 | Fri 6/23/23 | 2495 | 2497 |  | Gabriela Gibson
6242 | 2497 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Contract Manager Review | 2 hrs | 2 days | Mon 6/26/23 | Tue 6/27/23 | 2496 | 2498 |  | Sean Buchanan
6243 | 2498 | Future Task |  |  | D225 | Joy Schneider | Accept | DEL D225 - Monthly Performance Report (May 2023) - Accept | 0 hrs | 0 days | Tue 6/27/23 | Tue 6/27/23 | 2497 | 2500 |  | Sean Buchanan
6244 | 2499 | Future Task |  |  | D232 | Joy Schneider |  | D232 - Monthly Performance Report (June 2023) | 10 hrs | 19 days | Mon 7/3/23 | Fri 7/28/23
6366 | 2500 | Future Task |  |  | D232 | Joy Schneider | Create | D232 - Create June 2023 Monthly Performance Report | 3 hrs | 9 days | Mon 7/3/23 | Fri 7/14/23 | 2498 | 2501 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6245 | 2501 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 7/17/23 | Mon 7/17/23 | 2500 | 2502 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6246 | 2502 | Future Task |  |  | D232 | Joy Schneider | Submit | DEL D232 - Monthly Performance Report (June 2023) - Submit | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 2501 | 2503 |  | Joy Schneider
6247 | 2503 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Department QC | 1 hr | 7 days | Tue 7/18/23 | Wed 7/26/23 | 2502 | 2504 |  | Gabriela Gibson
6248 | 2504 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Contract Manager Review | 2 hrs | 2 days | Thu 7/27/23 | Fri 7/28/23 | 2503 | 2505 |  | Sean Buchanan
6249 | 2505 | Future Task |  |  | D232 | Joy Schneider | Accept | DEL D232 - Monthly Performance Report (June 2023) - Accept | 0 hrs | 0 days | Fri 7/28/23 | Fri 7/28/23 | 2504 | 2507 |  | Sean Buchanan
6250 | 2506 | Future Task |  |  | D239 | Joy Schneider |  | D239 - Monthly Performance Report (July 2023) | 10 hrs | 19 days | Tue 8/1/23 | Fri 8/25/23
6367 | 2507 | Future Task |  |  | D239 | Joy Schneider | Create | D239 - Create July 2023 Monthly Performance Report | 3 hrs | 9 days | Tue 8/1/23 | Fri 8/11/23 | 2505 | 2508 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6251 | 2508 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 8/14/23 | Mon 8/14/23 | 2507 | 2509 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6252 | 2509 | Future Task |  |  | D239 | Joy Schneider | Submit | DEL D239 - Monthly Performance Report (July 2023) - Submit | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 2508 | 2510 |  | Joy Schneider
6253 | 2510 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Department QC | 1 hr | 7 days | Tue 8/15/23 | Wed 8/23/23 | 2509 | 2511 |  | Gabriela Gibson
6254 | 2511 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Contract Manager Review | 2 hrs | 2 days | Thu 8/24/23 | Fri 8/25/23 | 2510 | 2512 |  | Sean Buchanan
6255 | 2512 | Future Task |  |  | D239 | Joy Schneider | Accept | DEL D239 - Monthly Performance Report (July 2023) - Accept | 0 hrs | 0 days | Fri 8/25/23 | Fri 8/25/23 | 2511 | 2514 |  | Sean Buchanan
6256 | 2513 | Future Task |  |  | D249 | Joy Schneider |  | D249 - Monthly Performance Report (August 2023) | 10 hrs | 19 days | Fri 9/1/23 | Thu 9/28/23
6368 | 2514 | Future Task |  |  | D249 | Joy Schneider | Create | D249 - Create August 2023 Monthly Performance Report | 3 hrs | 9 days | Fri 9/1/23 | Thu 9/14/23 | 2512 | 2515 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6257 | 2515 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 9/15/23 | Fri 9/15/23 | 2514 | 2516 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6258 | 2516 | Future Task |  |  | D249 | Joy Schneider | Submit | DEL D249 - Monthly Performance Report (August 2023) - Submit | 0 hrs | 0 days | Fri 9/15/23 | Fri 9/15/23 | 2515 | 2517 |  | Joy Schneider
6259 | 2517 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Department QC | 1 hr | 7 days | Mon 9/18/23 | Tue 9/26/23 | 2516 | 2518 |  | Gabriela Gibson
6260 | 2518 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 9/27/23 | Thu 9/28/23 | 2517 | 2519 |  | Sean Buchanan
6261 | 2519 | Future Task |  |  | D249 | Joy Schneider | Accept | DEL D249 - Monthly Performance Report (August 2023) - Accept | 0 hrs | 0 days | Thu 9/28/23 | Thu 9/28/23 | 2518 | 2521 |  | Sean Buchanan
6262 | 2520 | Future Task |  |  | D253 | Joy Schneider |  | D253 - Monthly Performance Report (September 2023) | 10 hrs | 19 days | Mon 10/2/23 | Thu 10/26/23
6369 | 2521 | Future Task |  |  | D253 | Joy Schneider | Create | D253 - Create September 2023 Monthly Performance Report | 3 hrs | 9 days | Mon 10/2/23 | Thu 10/12/23 | 2519 | 2522 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6263 | 2522 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 10/13/23 | Fri 10/13/23 | 2521 | 2523 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6264 | 2523 | Future Task |  |  | D253 | Joy Schneider | Submit | DEL D253 - Monthly Performance Report (September 2023) - Submit | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 2522 | 2524 |  | Joy Schneider
6265 | 2524 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Department QC | 1 hr | 7 days | Mon 10/16/23 | Tue 10/24/23 | 2523 | 2525 |  | Gabriela Gibson
6266 | 2525 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 10/25/23 | Thu 10/26/23 | 2524 | 2526 |  | Sean Buchanan
6267 | 2526 | Future Task |  |  | D253 | Joy Schneider | Accept | DEL D253 - Monthly Performance Report (September 2023) - Accept | 0 hrs | 0 days | Thu 10/26/23 | Thu 10/26/23 | 2525 | 2528 |  | Sean Buchanan
6268 | 2527 | Future Task |  |  | D257 | Joy Schneider |  | D257 - Monthly Performance Report (October 2023) | 10 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23
6370 | 2528 | Future Task |  |  | D257 | Joy Schneider | Create | D257 - Create October 2023 Monthly Performance Report | 3 hrs | 9 days | Wed 11/1/23 | Tue 11/14/23 | 2526 | 2529 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6269 | 2529 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 11/15/23 | Wed 11/15/23 | 2528 | 2530 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6270 | 2530 | Future Task |  |  | D257 | Joy Schneider | Submit | DEL D257 - Monthly Performance Report (October 2023) - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 2529 | 2531 |  | Joy Schneider
6271 | 2531 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Department QC | 1 hr | 7 days | Thu 11/16/23 | Tue 11/28/23 | 2530 | 2532 |  | Gabriela Gibson
6272 | 2532 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 11/29/23 | Thu 11/30/23 | 2531 | 2533 |  | Sean Buchanan
6273 | 2533 | Future Task |  |  | D257 | Joy Schneider | Accept | DEL D257 - Monthly Performance Report (October 2023) - Accept | 0 hrs | 0 days | Thu 11/30/23 | Thu 11/30/23 | 2532 | 2535 |  | Sean Buchanan
6274 | 2534 | Future Task |  |  | D261 | Joy Schneider |  | D261 - Monthly Performance Report (November 2023) | 10 hrs | 19 days | Fri 12/1/23 | Thu 12/28/23
6385 | 2535 | Future Task |  |  | D261 | Joy Schneider | Create | D261 - Create November 2023 Monthly Performance Report | 3 hrs | 9 days | Fri 12/1/23 | Wed 12/13/23 | 2533 | 2536 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6275 | 2536 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 12/14/23 | Thu 12/14/23 | 2535 | 2537 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6276 | 2537 | Future Task |  |  | D261 | Joy Schneider | Submit | DEL D261 - Monthly Performance Report (November 2023) - Submit | 0 hrs | 0 days | Thu 12/14/23 | Thu 12/14/23 | 2536 | 2538 |  | Joy Schneider
6277 | 2538 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Department QC | 1 hr | 7 days | Fri 12/15/23 | Tue 12/26/23 | 2537 | 2539 |  | Gabriela Gibson
6278 | 2539 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 12/27/23 | Thu 12/28/23 | 2538 | 2540 |  | Sean Buchanan
6279 | 2540 | Future Task |  |  | D261 | Joy Schneider | Accept | DEL D261 - Monthly Performance Report (November 2023) - Accept | 0 hrs | 0 days | Thu 12/28/23 | Thu 12/28/23 | 2539 | 2542 |  | Sean Buchanan
6280 | 2541 | Future Task |  |  | D267 | Joy Schneider |  | D267 - Monthly Performance Report (December 2023) | 10 hrs | 19 days | Tue 1/2/24 | Mon 1/29/24
6384 | 2542 | Future Task |  |  | D267 | Joy Schneider | Create | D267 - Create December 2023 Monthly Performance Report | 3 hrs | 9 days | Tue 1/2/24 | Fri 1/12/24 | 2540 | 2543 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6281 | 2543 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 1/16/24 | Tue 1/16/24 | 2542 | 2544 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6282 | 2544 | Future Task |  |  | D267 | Joy Schneider | Submit | DEL D267 - Monthly Performance Report (December 2023) - Submit | 0 hrs | 0 days | Tue 1/16/24 | Tue 1/16/24 | 2543 | 2545 |  | Joy Schneider
6283 | 2545 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Department QC | 1 hr | 7 days | Wed 1/17/24 | Thu 1/25/24 | 2544 | 2546 |  | Gabriela Gibson
6284 | 2546 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Contract Manager Review | 2 hrs | 2 days | Fri 1/26/24 | Mon 1/29/24 | 2545 | 2547 |  | Sean Buchanan
6285 | 2547 | Future Task |  |  | D267 | Joy Schneider | Accept | DEL D267 - Monthly Performance Report (December 2023) - Accept | 0 hrs | 0 days | Mon 1/29/24 | Mon 1/29/24 | 2546 | 2549 |  | Sean Buchanan
6286 | 2548 | Future Task |  |  | D277 | Joy Schneider |  | D277 - Monthly Performance Report (January 2024) | 10 hrs | 19 days | Thu 2/1/24 | Tue 2/27/24
6383 | 2549 | Future Task |  |  | D277 | Joy Schneider | Create | D277 - Create January 2024 Monthly Performance Report | 3 hrs | 9 days | Thu 2/1/24 | Tue 2/13/24 | 2547 | 2550 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6287 | 2550 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 2/14/24 | Wed 2/14/24 | 2549 | 2551 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6288 | 2551 | Future Task |  |  | D277 | Joy Schneider | Submit | DEL D277 - Monthly Performance Report (January 2024) - Submit | 0 hrs | 0 days | Wed 2/14/24 | Wed 2/14/24 | 2550 | 2552 |  | Joy Schneider
6289 | 2552 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Department QC | 1 hr | 7 days | Thu 2/15/24 | Fri 2/23/24 | 2551 | 2553 |  | Gabriela Gibson
6290 | 2553 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Contract Manager Review | 2 hrs | 2 days | Mon 2/26/24 | Tue 2/27/24 | 2552 | 2554 |  | Sean Buchanan
6291 | 2554 | Future Task |  |  | D277 | Joy Schneider | Accept | DEL D277 - Monthly Performance Report (January 2024) - Accept | 0 hrs | 0 days | Tue 2/27/24 | Tue 2/27/24 | 2553 | 2556 |  | Sean Buchanan
6292 | 2555 | Future Task |  |  | D284 | Joy Schneider |  | D284 - Monthly Performance Report (February 2024) | 10 hrs | 19 days | Fri 3/1/24 | Wed 3/27/24
6382 | 2556 | Future Task |  |  | D284 | Joy Schneider | Create | D284 - Create February 2024 Monthly Performance Report | 3 hrs | 9 days | Fri 3/1/24 | Wed 3/13/24 | 2554 | 2557 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6293 | 2557 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 3/14/24 | Thu 3/14/24 | 2556 | 2558 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6294 | 2558 | Future Task |  |  | D284 | Joy Schneider | Submit | DEL D284 - Monthly Performance Report (February 2024) - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 2557 | 2559 |  | Joy Schneider
6295 | 2559 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Department QC | 1 hr | 7 days | Fri 3/15/24 | Mon 3/25/24 | 2558 | 2560 |  | Gabriela Gibson
6296 | 2560 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Contract Manager Review | 2 hrs | 2 days | Tue 3/26/24 | Wed 3/27/24 | 2559 | 2561 |  | Sean Buchanan
6297 | 2561 | Future Task |  |  | D284 | Joy Schneider | Accept | DEL D284 - Monthly Performance Report (February 2024) - Accept | 0 hrs | 0 days | Wed 3/27/24 | Wed 3/27/24 | 2560 | 2563 |  | Sean Buchanan
6298 | 2562 | Future Task |  |  | D288 | Joy Schneider |  | D288 - Monthly Performance Report (March 2024) | 10 hrs | 19 days | Mon 4/1/24 | Thu 4/25/24
6381 | 2563 | Future Task |  |  | D288 | Joy Schneider | Create | D288 - Create March 2024 Monthly Performance Report | 3 hrs | 9 days | Mon 4/1/24 | Thu 4/11/24 | 2561 | 2564 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6299 | 2564 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 4/12/24 | Fri 4/12/24 | 2563 | 2565 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6300 | 2565 | Future Task |  |  | D288 | Joy Schneider | Submit | DEL D288 - Monthly Performance Report (March 2024) - Submit | 0 hrs | 0 days | Fri 4/12/24 | Fri 4/12/24 | 2564 | 2566 |  | Joy Schneider
6301 | 2566 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Department QC | 1 hr | 7 days | Mon 4/15/24 | Tue 4/23/24 | 2565 | 2567 |  | Gabriela Gibson
6302 | 2567 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Contract Manager Review | 2 hrs | 2 days | Wed 4/24/24 | Thu 4/25/24 | 2566 | 2568 |  | Sean Buchanan
6303 | 2568 | Future Task |  |  | D288 | Joy Schneider | Accept | DEL D288 - Monthly Performance Report (March 2024) - Accept | 0 hrs | 0 days | Thu 4/25/24 | Thu 4/25/24 | 2567 | 2570 |  | Sean Buchanan
6304 | 2569 | Future Task |  |  | D296 | Joy Schneider |  | D296 - Monthly Performance Report (April 2024) | 10 hrs | 19 days | Wed 5/1/24 | Tue 5/28/24
6380 | 2570 | Future Task |  |  | D296 | Joy Schneider | Create | D296 - Create April 2024 Monthly Performance Report | 3 hrs | 9 days | Wed 5/1/24 | Mon 5/13/24 | 2568 | 2571 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6305 | 2571 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 5/14/24 | Tue 5/14/24 | 2570 | 2572 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6306 | 2572 | Future Task |  |  | D296 | Joy Schneider | Submit | DEL D296 - Monthly Performance Report (April 2024) - Submit | 0 hrs | 0 days | Tue 5/14/24 | Tue 5/14/24 | 2571 | 2573 |  | Joy Schneider
6307 | 2573 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Department QC | 1 hr | 7 days | Wed 5/15/24 | Thu 5/23/24 | 2572 | 2574 |  | Gabriela Gibson
6308 | 2574 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Contract Manager Review | 2 hrs | 2 days | Fri 5/24/24 | Tue 5/28/24 | 2573 | 2575 |  | Sean Buchanan
6309 | 2575 | Future Task |  |  | D296 | Joy Schneider | Accept | DEL D296 - Monthly Performance Report (April 2024) - Accept | 0 hrs | 0 days | Tue 5/28/24 | Tue 5/28/24 | 2574 | 2577 |  | Sean Buchanan
6310 | 2576 | Future Task |  |  | D302 | Joy Schneider |  | D302 - Monthly Performance Report (May 2024) | 10 hrs | 19 days | Mon 6/3/24 | Thu 6/27/24
6379 | 2577 | Future Task |  |  | D302 | Joy Schneider | Create | D302 - Create May 2024 Monthly Performance Report | 3 hrs | 9 days | Mon 6/3/24 | Thu 6/13/24 | 2575 | 2578 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6311 | 2578 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 6/14/24 | Fri 6/14/24 | 2577 | 2579 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6312 | 2579 | Future Task |  |  | D302 | Joy Schneider | Submit | DEL D302 - Monthly Performance Report (May 2024) - Submit | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 2578 | 2580 |  | Joy Schneider
6313 | 2580 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Department QC | 1 hr | 7 days | Mon 6/17/24 | Tue 6/25/24 | 2579 | 2581 |  | Gabriela Gibson
6314 | 2581 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Contract Manager Review | 2 hrs | 2 days | Wed 6/26/24 | Thu 6/27/24 | 2580 | 2582 |  | Sean Buchanan
6315 | 2582 | Future Task |  |  | D302 | Joy Schneider | Accept | DEL D302 - Monthly Performance Report (May 2024) - Accept | 0 hrs | 0 days | Thu 6/27/24 | Thu 6/27/24 | 2581 | 2584 |  | Sean Buchanan
6316 | 2583 | Future Task |  |  | D311 | Joy Schneider |  | D311 - Monthly Performance Report (June 2024) | 10 hrs | 19 days | Mon 7/1/24 | Fri 7/26/24
6378 | 2584 | Future Task |  |  | D311 | Joy Schneider | Create | D311 - Create June 2024 Monthly Performance Report | 3 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 2582 | 2585 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6317 | 2585 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 7/15/24 | Mon 7/15/24 | 2584 | 2586 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6318 | 2586 | Future Task |  |  | D311 | Joy Schneider | Submit | DEL D311 - Monthly Performance Report (June 2024) - Submit | 0 hrs | 0 days | Mon 7/15/24 | Mon 7/15/24 | 2585 | 2587 |  | Joy Schneider
6319 | 2587 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Department QC | 1 hr | 7 days | Tue 7/16/24 | Wed 7/24/24 | 2586 | 2588 |  | Gabriela Gibson
6320 | 2588 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Contract Manager Review | 2 hrs | 2 days | Thu 7/25/24 | Fri 7/26/24 | 2587 | 2589 |  | Sean Buchanan
6321 | 2589 | Future Task |  |  | D311 | Joy Schneider | Accept | DEL D311 - Monthly Performance Report (June 2024) - Accept | 0 hrs | 0 days | Fri 7/26/24 | Fri 7/26/24 | 2588 | 2591 |  | Sean Buchanan
6322 | 2590 | Future Task |  |  | D319 | Joy Schneider |  | D319 - Monthly Performance Report (July 2024) | 10 hrs | 19 days | Thu 8/1/24 | Tue 8/27/24
6377 | 2591 | Future Task |  |  | D319 | Joy Schneider | Create | D319 - Create July 2024 Monthly Performance Report | 3 hrs | 9 days | Thu 8/1/24 | Tue 8/13/24 | 2589 | 2592 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6323 | 2592 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 8/14/24 | Wed 8/14/24 | 2591 | 2593 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6324 | 2593 | Future Task |  |  | D319 | Joy Schneider | Submit | DEL D319 - Monthly Performance Report (July 2024) - Submit | 0 hrs | 0 days | Wed 8/14/24 | Wed 8/14/24 | 2592 | 2594 |  | Joy Schneider
6325 | 2594 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Department QC | 1 hr | 7 days | Thu 8/15/24 | Fri 8/23/24 | 2593 | 2595 |  | Gabriela Gibson
6326 | 2595 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Contract Manager Review | 2 hrs | 2 days | Mon 8/26/24 | Tue 8/27/24 | 2594 | 2596 |  | Sean Buchanan
6327 | 2596 | Future Task |  |  | D319 | Joy Schneider | Accept | DEL D319 - Monthly Performance Report (July 2024) - Accept | 0 hrs | 0 days | Tue 8/27/24 | Tue 8/27/24 | 2595 | 2598 |  | Sean Buchanan
6328 | 2597 | Future Task |  |  | D328 | Joy Schneider |  | D328 - Monthly Performance Report (August 2024) | 10 hrs | 19 days | Tue 9/3/24 | Fri 9/27/24
6376 | 2598 | Future Task |  |  | D328 | Joy Schneider | Create | D328 - Create August 2024 Monthly Performance Report | 3 hrs | 9 days | Tue 9/3/24 | Fri 9/13/24 | 2596 | 2599 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6329 | 2599 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 9/16/24 | Mon 9/16/24 | 2598 | 2600 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6330 | 2600 | Future Task |  |  | D328 | Joy Schneider | Submit | DEL D328 - Monthly Performance Report (August 2024) - Submit | 0 hrs | 0 days | Mon 9/16/24 | Mon 9/16/24 | 2599 | 2601 |  | Joy Schneider
6331 | 2601 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Department QC | 1 hr | 7 days | Tue 9/17/24 | Wed 9/25/24 | 2600 | 2602 |  | Gabriela Gibson
6332 | 2602 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Contract Manager Review | 2 hrs | 2 days | Thu 9/26/24 | Fri 9/27/24 | 2601 | 2603 |  | Sean Buchanan
6333 | 2603 | Future Task |  |  | D328 | Joy Schneider | Accept | DEL D328 - Monthly Performance Report (August 2024) - Accept | 0 hrs | 0 days | Fri 9/27/24 | Fri 9/27/24 | 2602 | 2605 |  | Sean Buchanan
6334 | 2604 | Future Task |  |  | D334 | Joy Schneider |  | D334 - Monthly Performance Report (September 2024) | 10 hrs | 19 days | Tue 10/1/24 | Fri 10/25/24
6375 | 2605 | Future Task |  |  | D334 | Joy Schneider | Create | D334 - Create September 2024 Monthly Performance Report | 3 hrs | 9 days | Tue 10/1/24 | Fri 10/11/24 | 2603 | 2606 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6335 | 2606 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 10/14/24 | Mon 10/14/24 | 2605 | 2607 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6336 | 2607 | Future Task |  |  | D334 | Joy Schneider | Submit | DEL D334 - Monthly Performance Report (September 2024) - Submit | 0 hrs | 0 days | Mon 10/14/24 | Mon 10/14/24 | 2606 | 2608 |  | Joy Schneider
6337 | 2608 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Department QC | 1 hr | 7 days | Tue 10/15/24 | Wed 10/23/24 | 2607 | 2609 |  | Gabriela Gibson
6338 | 2609 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Contract Manager Review | 2 hrs | 2 days | Thu 10/24/24 | Fri 10/25/24 | 2608 | 2610 |  | Sean Buchanan
6339 | 2610 | Future Task |  |  | D334 | Joy Schneider | Accept | DEL D334 - Monthly Performance Report (September 2024) - Accept | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 2609 | 2612 |  | Sean Buchanan
6340 | 2611 | Future Task |  |  | D342 | Joy Schneider |  | D342 - Monthly Performance Report (October 2024) | 10 hrs | 19 days | Fri 11/1/24 | Mon 12/2/24
6374 | 2612 | Future Task |  |  | D342 | Joy Schneider | Create | D342 - Create October 2024 Monthly Performance Report | 3 hrs | 9 days | Fri 11/1/24 | Thu 11/14/24 | 2610 | 2613 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6341 | 2613 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 11/15/24 | Fri 11/15/24 | 2612 | 2614 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6342 | 2614 | Future Task |  |  | D342 | Joy Schneider | Submit | DEL D342 - Monthly Performance Report (October 2024) - Submit | 0 hrs | 0 days | Fri 11/15/24 | Fri 11/15/24 | 2613 | 2615 |  | Joy Schneider
6343 | 2615 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Department QC | 1 hr | 7 days | Mon 11/18/24 | Tue 11/26/24 | 2614 | 2616 |  | Gabriela Gibson
6344 | 2616 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Contract Manager Review | 2 hrs | 2 days | Wed 11/27/24 | Mon 12/2/24 | 2615 | 2617 |  | Sean Buchanan
6345 | 2617 | Future Task |  |  | D342 | Joy Schneider | Accept | DEL D342 - Monthly Performance Report (October 2024) - Accept | 0 hrs | 0 days | Mon 12/2/24 | Mon 12/2/24 | 2616 | 2619 |  | Sean Buchanan
6346 | 2618 | Future Task |  |  | D347 | Joy Schneider |  | D347 - Monthly Performance Report (November 2024) | 10 hrs | 19 days | Tue 12/3/24 | Mon 12/30/24
6373 | 2619 | Future Task |  |  | D347 | Joy Schneider | Create | D347 - Create November 2024 Monthly Performance Report | 3 hrs | 9 days | Tue 12/3/24 | Fri 12/13/24 | 2617 | 2620 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6347 | 2620 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 12/16/24 | Mon 12/16/24 | 2619 | 2621 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6348 | 2621 | Future Task |  |  | D347 | Joy Schneider | Submit | DEL D347 - Monthly Performance Report (November 2024) - Submit | 0 hrs | 0 days | Mon 12/16/24 | Mon 12/16/24 | 2620 | 2622 |  | Joy Schneider
6349 | 2622 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Department QC | 1 hr | 7 days | Tue 12/17/24 | Thu 12/26/24 | 2621 | 2623 |  | Gabriela Gibson
6350 | 2623 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Contract Manager Review | 2 hrs | 2 days | Fri 12/27/24 | Mon 12/30/24 | 2622 | 2624 |  | Sean Buchanan
6351 | 2624 | Future Task |  |  | D347 | Joy Schneider | Accept | DEL D347 - Monthly Performance Report (November 2024) - Accept | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 2623 | 2626 |  | Sean Buchanan
6352 | 2625 | Future Task |  |  | D353 | Joy Schneider |  | D353 - Monthly Performance Report (December 2024) | 10 hrs | 19 days | Thu 1/2/25 | Wed 1/29/25
6372 | 2626 | Future Task |  |  | D353 | Joy Schneider | Create | D353 - Create December 2024 Monthly Performance Report | 3 hrs | 9 days | Thu 1/2/25 | Tue 1/14/25 | 2624 | 2627 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6353 | 2627 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 1/15/25 | Wed 1/15/25 | 2626 | 2628 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6354 | 2628 | Future Task |  |  | D353 | Joy Schneider | Submit | DEL D353 - Monthly Performance Report (December 2024) - Submit | 0 hrs | 0 days | Wed 1/15/25 | Wed 1/15/25 | 2627 | 2629 |  | Joy Schneider
6355 | 2629 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Department QC | 1 hr | 7 days | Thu 1/16/25 | Mon 1/27/25 | 2628 | 2630 |  | Gabriela Gibson
6356 | 2630 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Contract Manager Review | 2 hrs | 2 days | Tue 1/28/25 | Wed 1/29/25 | 2629 | 2631 |  | Sean Buchanan
6357 | 2631 | Future Task |  |  | D353 | Joy Schneider | Accept | DEL D353 - Monthly Performance Report (December 2024) - Accept | 0 hrs | 0 days | Wed 1/29/25 | Wed 1/29/25 | 2630 | 2633 |  | Sean Buchanan
6358 | 2632 | Future Task |  |  | D359 | Joy Schneider |  | D359 - Monthly Performance Report (January 2025) | 10 hrs | 19 days | Mon 2/3/25 | Thu 2/27/25
6371 | 2633 | Future Task |  |  | D359 | Joy Schneider | Create | D359 - Create January 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 2/3/25 | Thu 2/13/25 | 2631 | 2634 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6359 | 2634 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 2/14/25 | Fri 2/14/25 | 2633 | 2635 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6360 | 2635 | Future Task |  |  | D359 | Joy Schneider | Submit | DEL D359 - Monthly Performance Report (January 2025) - Submit | 0 hrs | 0 days | Fri 2/14/25 | Fri 2/14/25 | 2634 | 2636 |  | Joy Schneider
6361 | 2636 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Department QC | 1 hr | 7 days | Mon 2/17/25 | Tue 2/25/25 | 2635 | 2637 |  | Gabriela Gibson
6362 | 2637 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 2/26/25 | Thu 2/27/25 | 2636 | 2638 |  | Sean Buchanan
6363 | 2638 | Future Task |  |  | D359 | Joy Schneider | Accept | DEL D359 - Monthly Performance Report (January 2025) - Accept | 0 hrs | 0 days | Thu 2/27/25 | Thu 2/27/25 | 2637 | 2640 |  | Sean Buchanan
6386 | 2639 | Future Task |  |  | D362 | Joy Schneider |  | D362 - Monthly Performance Report (February 2025) | 10 hrs | 19 days | Mon 3/3/25 | Thu 3/27/25
6490 | 2640 | Future Task |  |  | D362 | Joy Schneider | Create | D362 - Create February 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 3/3/25 | Thu 3/13/25 | 2638 | 2641 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6387 | 2641 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 3/14/25 | Fri 3/14/25 | 2640 | 2642 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6388 | 2642 | Future Task |  |  | D362 | Joy Schneider | Submit | DEL D362 - Monthly Performance Report (February 2025) - Submit | 0 hrs | 0 days | Fri 3/14/25 | Fri 3/14/25 | 2641 | 2643 |  | Joy Schneider
6389 | 2643 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Department QC | 1 hr | 7 days | Mon 3/17/25 | Tue 3/25/25 | 2642 | 2644 |  | Gabriela Gibson
6390 | 2644 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 3/26/25 | Thu 3/27/25 | 2643 | 2645 |  | Sean Buchanan
6391 | 2645 | Future Task |  |  | D362 | Joy Schneider | Accept | DEL D362 - Monthly Performance Report (February 2025) - Accept | 0 hrs | 0 days | Thu 3/27/25 | Thu 3/27/25 | 2644 | 2647 |  | Sean Buchanan
6392 | 2646 | Future Task |  |  | D364 | Joy Schneider |  | D364 - Monthly Performance Report (March 2025) | 10 hrs | 19 days | Tue 4/1/25 | Fri 4/25/25
6489 | 2647 | Future Task |  |  | D364 | Joy Schneider | Create | D364 - Create March 2025 Monthly Performance Report | 3 hrs | 9 days | Tue 4/1/25 | Fri 4/11/25 | 2645 | 2648 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6393 | 2648 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 4/14/25 | Mon 4/14/25 | 2647 | 2649 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6394 | 2649 | Future Task |  |  | D364 | Joy Schneider | Submit | DEL D364 - Monthly Performance Report (March 2025) - Submit | 0 hrs | 0 days | Mon 4/14/25 | Mon 4/14/25 | 2648 | 2650 |  | Joy Schneider
6395 | 2650 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Department QC | 1 hr | 7 days | Tue 4/15/25 | Wed 4/23/25 | 2649 | 2651 |  | Gabriela Gibson
6396 | 2651 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Contract Manager Review | 2 hrs | 2 days | Thu 4/24/25 | Fri 4/25/25 | 2650 | 2652 |  | Sean Buchanan
6397 | 2652 | Future Task |  |  | D364 | Joy Schneider | Accept | DEL D364 - Monthly Performance Report (March 2025) - Accept | 0 hrs | 0 days | Fri 4/25/25 | Fri 4/25/25 | 2651 | 2654 |  | Sean Buchanan
6398 | 2653 | Future Task |  |  | D366 | Joy Schneider |  | D366 - Monthly Performance Report (April 2025) | 10 hrs | 19 days | Thu 5/1/25 | Wed 5/28/25
6488 | 2654 | Future Task |  |  | D366 | Joy Schneider | Create | D366 - Create April 2025 Monthly Performance Report | 3 hrs | 9 days | Thu 5/1/25 | Tue 5/13/25 | 2652 | 2655 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6399 | 2655 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 5/14/25 | Wed 5/14/25 | 2654 | 2656 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6400 | 2656 | Future Task |  |  | D366 | Joy Schneider | Submit | DEL D366 - Monthly Performance Report (April 2025) - Submit | 0 hrs | 0 days | Wed 5/14/25 | Wed 5/14/25 | 2655 | 2657 |  | Joy Schneider
6401 | 2657 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Department QC | 1 hr | 7 days | Thu 5/15/25 | Fri 5/23/25 | 2656 | 2658 |  | Gabriela Gibson
6402 | 2658 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Contract Manager Review | 2 hrs | 2 days | Tue 5/27/25 | Wed 5/28/25 | 2657 | 2659 |  | Sean Buchanan
6403 | 2659 | Future Task |  |  | D366 | Joy Schneider | Accept | DEL D366 - Monthly Performance Report (April 2025) - Accept | 0 hrs | 0 days | Wed 5/28/25 | Wed 5/28/25 | 2658 | 2661 |  | Sean Buchanan
6404 | 2660 | Future Task |  |  | D367 | Joy Schneider |  | D367 - Monthly Performance Report (May 2025) | 10 hrs | 19 days | Mon 6/2/25 | Thu 6/26/25
6487 | 2661 | Future Task |  |  | D367 | Joy Schneider | Create | D367 - Create May 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 6/2/25 | Thu 6/12/25 | 2659 | 2662 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6405 | 2662 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 6/13/25 | Fri 6/13/25 | 2661 | 2663 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6406 | 2663 | Future Task |  |  | D367 | Joy Schneider | Submit | DEL D367 - Monthly Performance Report (May 2025) - Submit | 0 hrs | 0 days | Fri 6/13/25 | Fri 6/13/25 | 2662 | 2664 |  | Joy Schneider
6407 | 2664 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Department QC | 1 hr | 7 days | Mon 6/16/25 | Tue 6/24/25 | 2663 | 2665 |  | Gabriela Gibson
6408 | 2665 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 6/25/25 | Thu 6/26/25 | 2664 | 2666 |  | Sean Buchanan
6409 | 2666 | Future Task |  |  | D367 | Joy Schneider | Accept | DEL D367 - Monthly Performance Report (May 2025) - Accept | 0 hrs | 0 days | Thu 6/26/25 | Thu 6/26/25 | 2665 | 2668 |  | Sean Buchanan
6410 | 2667 | Future Task |  |  | D368 | Joy Schneider |  | D368 - Monthly Performance Report (June 2025) | 10 hrs | 19 days | Tue 7/1/25 | Mon 7/28/25
6486 | 2668 | Future Task |  |  | D368 | Joy Schneider | Create | D368 - Create June 2025 Monthly Performance Report | 3 hrs | 9 days | Tue 7/1/25 | Mon 7/14/25 | 2666 | 2669 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6411 | 2669 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 7/15/25 | Tue 7/15/25 | 2668 | 2670 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6412 | 2670 | Future Task |  |  | D368 | Joy Schneider | Submit | DEL D368 - Monthly Performance Report (June 2025) - Submit | 0 hrs | 0 days | Tue 7/15/25 | Tue 7/15/25 | 2669 | 2671 |  | Joy Schneider
6413 | 2671 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Department QC | 1 hr | 7 days | Wed 7/16/25 | Thu 7/24/25 | 2670 | 2672 |  | Gabriela Gibson
6414 | 2672 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Contract Manager Review | 2 hrs | 2 days | Fri 7/25/25 | Mon 7/28/25 | 2671 | 2673 |  | Sean Buchanan
6415 | 2673 | Future Task |  |  | D368 | Joy Schneider | Accept | DEL D368 - Monthly Performance Report (June 2025) - Accept | 0 hrs | 0 days | Mon 7/28/25 | Mon 7/28/25 | 2672 | 2675 |  | Sean Buchanan
6416 | 2674 | Future Task |  |  | D369 | Joy Schneider |  | D369 - Monthly Performance Report (July 2025) | 10 hrs | 19 days | Fri 8/1/25 | Wed 8/27/25
6485 | 2675 | Future Task |  |  | D369 | Joy Schneider | Create | D369 - Create July 2025 Monthly Performance Report | 3 hrs | 9 days | Fri 8/1/25 | Wed 8/13/25 | 2673 | 2676 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6417 | 2676 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 8/14/25 | Thu 8/14/25 | 2675 | 2677 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6418 | 2677 | Future Task |  |  | D369 | Joy Schneider | Submit | DEL D369 - Monthly Performance Report (July 2025) - Submit | 0 hrs | 0 days | Thu 8/14/25 | Thu 8/14/25 | 2676 | 2678 |  | Joy Schneider
6419 | 2678 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Department QC | 1 hr | 7 days | Fri 8/15/25 | Mon 8/25/25 | 2677 | 2679 |  | Gabriela Gibson
6420 | 2679 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Contract Manager Review | 2 hrs | 2 days | Tue 8/26/25 | Wed 8/27/25 | 2678 | 2680 |  | Sean Buchanan
6421 | 2680 | Future Task |  |  | D369 | Joy Schneider | Accept | DEL D369 - Monthly Performance Report (July 2025) - Accept | 0 hrs | 0 days | Wed 8/27/25 | Wed 8/27/25 | 2679 | 2682 |  | Sean Buchanan
6422 | 2681 | Future Task |  |  | D370 | Joy Schneider |  | D370 - Monthly Performance Report (August 2025) | 10 hrs | 19 days | Tue 9/2/25 | Fri 9/26/25
6484 | 2682 | Future Task |  |  | D370 | Joy Schneider | Create | D370 - Create August 2025 Monthly Performance Report | 3 hrs | 9 days | Tue 9/2/25 | Fri 9/12/25 | 2680 | 2683 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6423 | 2683 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 9/15/25 | Mon 9/15/25 | 2682 | 2684 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6424 | 2684 | Future Task |  |  | D370 | Joy Schneider | Submit | DEL D370 - Monthly Performance Report (August 2025) - Submit | 0 hrs | 0 days | Mon 9/15/25 | Mon 9/15/25 | 2683 | 2685 |  | Joy Schneider
6425 | 2685 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Department QC | 1 hr | 7 days | Tue 9/16/25 | Wed 9/24/25 | 2684 | 2686 |  | Gabriela Gibson
6426 | 2686 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Contract Manager Review | 2 hrs | 2 days | Thu 9/25/25 | Fri 9/26/25 | 2685 | 2687 |  | Sean Buchanan
6427 | 2687 | Future Task |  |  | D370 | Joy Schneider | Accept | DEL D370 - Monthly Performance Report (August 2025) - Accept | 0 hrs | 0 days | Fri 9/26/25 | Fri 9/26/25 | 2686 | 2689 |  | Sean Buchanan
6428 | 2688 | Future Task |  |  | D371 | Joy Schneider |  | D371 - Monthly Performance Report (September 2025) | 10 hrs | 19 days | Wed 10/1/25 | Mon 10/27/25
6483 | 2689 | Future Task |  |  | D371 | Joy Schneider | Create | D371 - Create September 2025 Monthly Performance Report | 3 hrs | 9 days | Wed 10/1/25 | Mon 10/13/25 | 2687 | 2690 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6429 | 2690 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 10/14/25 | Tue 10/14/25 | 2689 | 2691 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6430 | 2691 | Future Task |  |  | D371 | Joy Schneider | Submit | DEL D371 - Monthly Performance Report (September 2025) - Submit | 0 hrs | 0 days | Tue 10/14/25 | Tue 10/14/25 | 2690 | 2692 |  | Joy Schneider
6431 | 2692 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Department QC | 1 hr | 7 days | Wed 10/15/25 | Thu 10/23/25 | 2691 | 2693 |  | Gabriela Gibson
6432 | 2693 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Contract Manager Review | 2 hrs | 2 days | Fri 10/24/25 | Mon 10/27/25 | 2692 | 2694 |  | Sean Buchanan
6433 | 2694 | Future Task |  |  | D371 | Joy Schneider | Accept | DEL D371 - Monthly Performance Report (September 2025) - Accept | 0 hrs | 0 days | Mon 10/27/25 | Mon 10/27/25 | 2693 | 2696 |  | Sean Buchanan
6434 | 2695 | Future Task |  |  | D373 | Joy Schneider |  | D373 - Monthly Performance Report (October 2025) | 10 hrs | 19 days | Mon 11/3/25 | Tue 12/2/25
6482 | 2696 | Future Task |  |  | D373 | Joy Schneider | Create | D373 - Create October 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 11/3/25 | Fri 11/14/25 | 2694 | 2697 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6435 | 2697 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 11/17/25 | Mon 11/17/25 | 2696 | 2698 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6436 | 2698 | Future Task |  |  | D373 | Joy Schneider | Submit | DEL D373 - Monthly Performance Report (October 2025) - Submit | 0 hrs | 0 days | Mon 11/17/25 | Mon 11/17/25 | 2697 | 2699 |  | Joy Schneider
6437 | 2699 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Department QC | 1 hr | 7 days | Tue 11/18/25 | Wed 11/26/25 | 2698 | 2700 |  | Gabriela Gibson
6438 | 2700 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Contract Manager Review | 2 hrs | 2 days | Mon 12/1/25 | Tue 12/2/25 | 2699 | 2701 |  | Sean Buchanan
6439 | 2701 | Future Task |  |  | D373 | Joy Schneider | Accept | DEL D373 - Monthly Performance Report (October 2025) - Accept | 0 hrs | 0 days | Tue 12/2/25 | Tue 12/2/25 | 2700 | 2703FS-2 days |  | Sean Buchanan
6440 | 2702 | Future Task |  |  | D374 | Joy Schneider |  | D374 - Monthly Performance Report (November 2025) | 10 hrs | 19 days | Mon 12/1/25 | Fri 12/26/25
6481 | 2703 | Future Task |  |  | D374 | Joy Schneider | Create | D374 - Create November 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 12/1/25 | Thu 12/11/25 | 2701FS-2 days | 2704 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6441 | 2704 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 12/12/25 | Fri 12/12/25 | 2703 | 2705 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6442 | 2705 | Future Task |  |  | D374 | Joy Schneider | Submit | DEL D374 - Monthly Performance Report (November 2025) - Submit | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 2704 | 2706 |  | Joy Schneider
6443 | 2706 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Department QC | 1 hr | 7 days | Mon 12/15/25 | Tue 12/23/25 | 2705 | 2707 |  | Gabriela Gibson
6444 | 2707 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 12/24/25 | Fri 12/26/25 | 2706 | 2708 |  | Sean Buchanan
6445 | 2708 | Future Task |  |  | D374 | Joy Schneider | Accept | DEL D374 - Monthly Performance Report (November 2025) - Accept | 0 hrs | 0 days | Fri 12/26/25 | Fri 12/26/25 | 2707 | 2710 |  | Sean Buchanan
6446 | 2709 | Future Task |  |  | D375 | Joy Schneider |  | D375 - Monthly Performance Report (December 2025) | 10 hrs | 19 days | Fri 1/2/26 | Thu 1/29/26
6480 | 2710 | Future Task |  |  | D375 | Joy Schneider | Create | D375 - Create December 2025 Monthly Performance Report | 3 hrs | 9 days | Fri 1/2/26 | Wed 1/14/26 | 2708 | 2711 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6447 | 2711 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 1/15/26 | Thu 1/15/26 | 2710 | 2712 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6448 | 2712 | Future Task |  |  | D375 | Joy Schneider | Submit | DEL D375 - Monthly Performance Report (December 2025) - Submit | 0 hrs | 0 days | Thu 1/15/26 | Thu 1/15/26 | 2711 | 2713 |  | Joy Schneider
6449 | 2713 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Department QC | 1 hr | 7 days | Fri 1/16/26 | Tue 1/27/26 | 2712 | 2714 |  | Gabriela Gibson
6450 | 2714 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 1/28/26 | Thu 1/29/26 | 2713 | 2715 |  | Sean Buchanan
6451 | 2715 | Future Task |  |  | D375 | Joy Schneider | Accept | DEL D375 - Monthly Performance Report (December 2025) - Accept | 0 hrs | 0 days | Thu 1/29/26 | Thu 1/29/26 | 2714 | 2717 |  | Sean Buchanan
6452 | 2716 | Future Task |  |  | D432 | Joy Schneider |  | D432 - Monthly Performance Report (January 2026) | 10 hrs | 19 days | Mon 2/2/26 | Thu 2/26/26
6479 | 2717 | Future Task |  |  | D432 | Joy Schneider | Create | D432 - Create January 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 2/2/26 | Thu 2/12/26 | 2715 | 2718 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6453 | 2718 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 2/13/26 | Fri 2/13/26 | 2717 | 2719 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6454 | 2719 | Future Task |  |  | D432 | Joy Schneider | Submit | DEL D432 - Monthly Performance Report (January 2026) - Submit | 0 hrs | 0 days | Fri 2/13/26 | Fri 2/13/26 | 2718 | 2720 |  | Joy Schneider
6455 | 2720 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Department QC | 1 hr | 7 days | Mon 2/16/26 | Tue 2/24/26 | 2719 | 2721 |  | Gabriela Gibson
6456 | 2721 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 2/25/26 | Thu 2/26/26 | 2720 | 2722 |  | Sean Buchanan
6457 | 2722 | Future Task |  |  | D432 | Joy Schneider | Accept | DEL D432 - Monthly Performance Report (January 2026) - Accept | 0 hrs | 0 days | Thu 2/26/26 | Thu 2/26/26 | 2721 | 2724 |  | Sean Buchanan
6458 | 2723 | Future Task |  |  | D434 | Joy Schneider |  | D434 - Monthly Performance Report (February 2026) | 10 hrs | 19 days | Mon 3/2/26 | Thu 3/26/26
6478 | 2724 | Future Task |  |  | D434 | Joy Schneider | Create | D434 - Create February 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 3/2/26 | Thu 3/12/26 | 2722 | 2725 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6459 | 2725 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 3/13/26 | Fri 3/13/26 | 2724 | 2726 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6460 | 2726 | Future Task |  |  | D434 | Joy Schneider | Submit | DEL D434 - Monthly Performance Report (February 2026) - Submit | 0 hrs | 0 days | Fri 3/13/26 | Fri 3/13/26 | 2725 | 2727 |  | Joy Schneider
6461 | 2727 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Department QC | 1 hr | 7 days | Mon 3/16/26 | Tue 3/24/26 | 2726 | 2728 |  | Gabriela Gibson
6462 | 2728 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 3/25/26 | Thu 3/26/26 | 2727 | 2729 |  | Sean Buchanan
6463 | 2729 | Future Task |  |  | D434 | Joy Schneider | Accept | DEL D434 - Monthly Performance Report (February 2026) - Accept | 0 hrs | 0 days | Thu 3/26/26 | Thu 3/26/26 | 2728 | 2731 |  | Sean Buchanan
6464 | 2730 | Future Task |  |  | D435 | Joy Schneider |  | D435 - Monthly Performance Report (March 2026) | 10 hrs | 19 days | Wed 4/1/26 | Mon 4/27/26
6477 | 2731 | Future Task |  |  | D435 | Joy Schneider | Create | D435 - Create March 2026 Monthly Performance Report | 3 hrs | 9 days | Wed 4/1/26 | Mon 4/13/26 | 2729 | 2732 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6465 | 2732 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 4/14/26 | Tue 4/14/26 | 2731 | 2733 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6466 | 2733 | Future Task |  |  | D435 | Joy Schneider | Submit | DEL D435 - Monthly Performance Report (March 2026) - Submit | 0 hrs | 0 days | Tue 4/14/26 | Tue 4/14/26 | 2732 | 2734 |  | Joy Schneider
6467 | 2734 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Department QC | 1 hr | 7 days | Wed 4/15/26 | Thu 4/23/26 | 2733 | 2735 |  | Gabriela Gibson
6468 | 2735 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Contract Manager Review | 2 hrs | 2 days | Fri 4/24/26 | Mon 4/27/26 | 2734 | 2736 |  | Sean Buchanan
6469 | 2736 | Future Task |  |  | D435 | Joy Schneider | Accept | DEL D435 - Monthly Performance Report (March 2026) - Accept | 0 hrs | 0 days | Mon 4/27/26 | Mon 4/27/26 | 2735 | 2738 |  | Sean Buchanan
6470 | 2737 | Future Task |  |  | D437 | Joy Schneider |  | D437 - Monthly Performance Report (April 2026) | 10 hrs | 19 days | Fri 5/1/26 | Thu 5/28/26
6476 | 2738 | Future Task |  |  | D437 | Joy Schneider | Create | D437 - Create April 2026 Monthly Performance Report | 3 hrs | 9 days | Fri 5/1/26 | Wed 5/13/26 | 2736 | 2739 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6471 | 2739 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 5/14/26 | Thu 5/14/26 | 2738 | 2740 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6472 | 2740 | Future Task |  |  | D437 | Joy Schneider | Submit | DEL D437 - Monthly Performance Report (April 2026) - Submit | 0 hrs | 0 days | Thu 5/14/26 | Thu 5/14/26 | 2739 | 2741 |  | Joy Schneider
6473 | 2741 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Department QC | 1 hr | 7 days | Fri 5/15/26 | Tue 5/26/26 | 2740 | 2742 |  | Gabriela Gibson
6474 | 2742 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 5/27/26 | Thu 5/28/26 | 2741 | 2743 |  | Sean Buchanan
6475 | 2743 | Future Task |  |  | D437 | Joy Schneider | Accept | DEL D437 - Monthly Performance Report (April 2026) - Accept | 0 hrs | 0 days | Thu 5/28/26 | Thu 5/28/26 | 2742 | 2745 |  | Sean Buchanan
6491 | 2744 | Future Task |  |  | D438 | Joy Schneider |  | D438 - Monthly Performance Report (May 2026) | 10 hrs | 19 days | Mon 6/1/26 | Thu 6/25/26
6595 | 2745 | Future Task |  |  | D438 | Joy Schneider | Create | D438 - Create May 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 6/1/26 | Thu 6/11/26 | 2743 | 2746 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6492 | 2746 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 6/12/26 | Fri 6/12/26 | 2745 | 2747 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6493 | 2747 | Future Task |  |  | D438 | Joy Schneider | Submit | DEL D438 - Monthly Performance Report (May 2026) - Submit | 0 hrs | 0 days | Fri 6/12/26 | Fri 6/12/26 | 2746 | 2748 |  | Joy Schneider
6494 | 2748 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Department QC | 1 hr | 7 days | Mon 6/15/26 | Tue 6/23/26 | 2747 | 2749 |  | Gabriela Gibson
6495 | 2749 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 6/24/26 | Thu 6/25/26 | 2748 | 2750 |  | Sean Buchanan
6496 | 2750 | Future Task |  |  | D438 | Joy Schneider | Accept | DEL D438 - Monthly Performance Report (May 2026) - Accept | 0 hrs | 0 days | Thu 6/25/26 | Thu 6/25/26 | 2749 | 2752 |  | Sean Buchanan
6497 | 2751 | Future Task |  |  | D439 | Joy Schneider |  | D439 - Monthly Performance Report (June 2026) | 10 hrs | 19 days | Wed 7/1/26 | Tue 7/28/26
6594 | 2752 | Future Task |  |  | D439 | Joy Schneider | Create | D439 - Create June 2026 Monthly Performance Report | 3 hrs | 9 days | Wed 7/1/26 | Tue 7/14/26 | 2750 | 2753 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6498 | 2753 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 7/15/26 | Wed 7/15/26 | 2752 | 2754 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6499 | 2754 | Future Task |  |  | D439 | Joy Schneider | Submit | DEL D439 - Monthly Performance Report (June 2026) - Submit | 0 hrs | 0 days | Wed 7/15/26 | Wed 7/15/26 | 2753 | 2755 |  | Joy Schneider
6500 | 2755 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Department QC | 1 hr | 7 days | Thu 7/16/26 | Fri 7/24/26 | 2754 | 2756 |  | Gabriela Gibson
6501 | 2756 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 7/27/26 | Tue 7/28/26 | 2755 | 2757 |  | Sean Buchanan
6502 | 2757 | Future Task |  |  | D439 | Joy Schneider | Accept | DEL D439 - Monthly Performance Report (June 2026) - Accept | 0 hrs | 0 days | Tue 7/28/26 | Tue 7/28/26 | 2756 | 2759 |  | Sean Buchanan
6503 | 2758 | Future Task |  |  | D441 | Joy Schneider |  | D441 - Monthly Performance Report (July 2026) | 10 hrs | 19 days | Mon 8/3/26 | Thu 8/27/26
6593 | 2759 | Future Task |  |  | D441 | Joy Schneider | Create | D441 - Create July 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 8/3/26 | Thu 8/13/26 | 2757 | 2760 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6504 | 2760 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 8/14/26 | Fri 8/14/26 | 2759 | 2761 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6505 | 2761 | Future Task |  |  | D441 | Joy Schneider | Submit | DEL D441 - Monthly Performance Report (July 2026) - Submit | 0 hrs | 0 days | Fri 8/14/26 | Fri 8/14/26 | 2760 | 2762 |  | Joy Schneider
6506 | 2762 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Department QC | 1 hr | 7 days | Mon 8/17/26 | Tue 8/25/26 | 2761 | 2763 |  | Gabriela Gibson
6507 | 2763 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 8/26/26 | Thu 8/27/26 | 2762 | 2764 |  | Sean Buchanan
6508 | 2764 | Future Task |  |  | D441 | Joy Schneider | Accept | DEL D441 - Monthly Performance Report (July 2026) - Accept | 0 hrs | 0 days | Thu 8/27/26 | Thu 8/27/26 | 2763 | 2766 |  | Sean Buchanan
6509 | 2765 | Future Task |  |  | D442 | Joy Schneider |  | D442 - Monthly Performance Report (August 2026) | 10 hrs | 19 days | Tue 9/1/26 | Mon 9/28/26
6592 | 2766 | Future Task |  |  | D442 | Joy Schneider | Create | D442 - Create August 2026 Monthly Performance Report | 3 hrs | 9 days | Tue 9/1/26 | Mon 9/14/26 | 2764 | 2767 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6510 | 2767 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 9/15/26 | Tue 9/15/26 | 2766 | 2768 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6511 | 2768 | Future Task |  |  | D442 | Joy Schneider | Submit | DEL D442 - Monthly Performance Report (August 2026) - Submit | 0 hrs | 0 days | Tue 9/15/26 | Tue 9/15/26 | 2767 | 2769 |  | Joy Schneider
6512 | 2769 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Department QC | 1 hr | 7 days | Wed 9/16/26 | Thu 9/24/26 | 2768 | 2770 |  | Gabriela Gibson
6513 | 2770 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Contract Manager Review | 2 hrs | 2 days | Fri 9/25/26 | Mon 9/28/26 | 2769 | 2771 |  | Sean Buchanan
6514 | 2771 | Future Task |  |  | D442 | Joy Schneider | Accept | DEL D442 - Monthly Performance Report (August 2026) - Accept | 0 hrs | 0 days | Mon 9/28/26 | Mon 9/28/26 | 2770 | 2773 |  | Sean Buchanan
6515 | 2772 | Future Task |  |  | D443 | Joy Schneider |  | D443 - Monthly Performance Report (September 2026) | 10 hrs | 19 days | Thu 10/1/26 | Tue 10/27/26
6591 | 2773 | Future Task |  |  | D443 | Joy Schneider | Create | D443 - Create September 2026 Monthly Performance Report | 3 hrs | 9 days | Thu 10/1/26 | Tue 10/13/26 | 2771 | 2774 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6516 | 2774 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 10/14/26 | Wed 10/14/26 | 2773 | 2775 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6517 | 2775 | Future Task |  |  | D443 | Joy Schneider | Submit | DEL D443 - Monthly Performance Report (September 2026) - Submit | 0 hrs | 0 days | Wed 10/14/26 | Wed 10/14/26 | 2774 | 2776 |  | Joy Schneider
6518 | 2776 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Department QC | 1 hr | 7 days | Thu 10/15/26 | Fri 10/23/26 | 2775 | 2777 |  | Gabriela Gibson
6519 | 2777 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 10/26/26 | Tue 10/27/26 | 2776 | 2778 |  | Sean Buchanan
6520 | 2778 | Future Task |  |  | D443 | Joy Schneider | Accept | DEL D443 - Monthly Performance Report (September 2026) - Accept | 0 hrs | 0 days | Tue 10/27/26 | Tue 10/27/26 | 2777 | 2780 |  | Sean Buchanan
6521 | 2779 | Future Task |  |  | D444 | Joy Schneider |  | D444 - Monthly Performance Report (October 2026) | 10 hrs | 19 days | Mon 11/2/26 | Tue 12/1/26
6590 | 2780 | Future Task |  |  | D444 | Joy Schneider | Create | D444 - Create October 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 11/2/26 | Fri 11/13/26 | 2778 | 2781 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6522 | 2781 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 11/16/26 | Mon 11/16/26 | 2780 | 2782 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6523 | 2782 | Future Task |  |  | D444 | Joy Schneider | Submit | DEL D444 - Monthly Performance Report (October 2026) - Submit | 0 hrs | 0 days | Mon 11/16/26 | Mon 11/16/26 | 2781 | 2783 |  | Joy Schneider
6524 | 2783 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Department QC | 1 hr | 7 days | Tue 11/17/26 | Wed 11/25/26 | 2782 | 2784 |  | Gabriela Gibson
6525 | 2784 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 11/30/26 | Tue 12/1/26 | 2783 | 2785 |  | Sean Buchanan
6526 | 2785 | Future Task |  |  | D444 | Joy Schneider | Accept | DEL D444 - Monthly Performance Report (October 2026) - Accept | 0 hrs | 0 days | Tue 12/1/26 | Tue 12/1/26 | 2784 | 2787FS-1 day |  | Sean Buchanan
6527 | 2786 | Future Task |  |  | D445 | Joy Schneider |  | D445 - Monthly Performance Report (November 2026) | 10 hrs | 19 days | Tue 12/1/26 | Mon 12/28/26
6589 | 2787 | Future Task |  |  | D445 | Joy Schneider | Create | D445 - Create November 2026 Monthly Performance Report | 3 hrs | 9 days | Tue 12/1/26 | Fri 12/11/26 | 2785FS-1 day | 2788 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6528 | 2788 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 12/14/26 | Mon 12/14/26 | 2787 | 2789 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6529 | 2789 | Future Task |  |  | D445 | Joy Schneider | Submit | DEL D445 - Monthly Performance Report (November 2026) - Submit | 0 hrs | 0 days | Mon 12/14/26 | Mon 12/14/26 | 2788 | 2790 |  | Joy Schneider
6530 | 2790 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Department QC | 1 hr | 7 days | Tue 12/15/26 | Wed 12/23/26 | 2789 | 2791 |  | Gabriela Gibson
6531 | 2791 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Contract Manager Review | 2 hrs | 2 days | Thu 12/24/26 | Mon 12/28/26 | 2790 | 2792 |  | Sean Buchanan
6532 | 2792 | Future Task |  |  | D445 | Joy Schneider | Accept | DEL D445 - Monthly Performance Report (November 2026) - Accept | 0 hrs | 0 days | Mon 12/28/26 | Mon 12/28/26 | 2791 | 2794 |  | Sean Buchanan
6533 | 2793 | Future Task |  |  | D446 | Joy Schneider |  | D446 - Monthly Performance Report (December 2026) | 10 hrs | 19 days | Mon 1/4/27 | Fri 1/29/27
6588 | 2794 | Future Task |  |  | D446 | Joy Schneider | Create | D446 - Create December 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 1/4/27 | Thu 1/14/27 | 2792 | 2795 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6534 | 2795 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 1/15/27 | Fri 1/15/27 | 2794 | 2796 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6535 | 2796 | Future Task |  |  | D446 | Joy Schneider | Submit | DEL D446 - Monthly Performance Report (December 2026) - Submit | 0 hrs | 0 days | Fri 1/15/27 | Fri 1/15/27 | 2795 | 2797 |  | Joy Schneider
6536 | 2797 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Department QC | 1 hr | 7 days | Tue 1/19/27 | Wed 1/27/27 | 2796 | 2798 |  | Gabriela Gibson
6537 | 2798 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Contract Manager Review | 2 hrs | 2 days | Thu 1/28/27 | Fri 1/29/27 | 2797 | 2799 |  | Sean Buchanan
6538 | 2799 | Future Task |  |  | D446 | Joy Schneider | Accept | DEL D446 - Monthly Performance Report (December 2026) - Accept | 0 hrs | 0 days | Fri 1/29/27 | Fri 1/29/27 | 2798 | 2801 |  | Sean Buchanan
6539 | 2800 | Future Task |  |  | D447 | Joy Schneider |  | D447 - Monthly Performance Report (January 2027) | 10 hrs | 19 days | Mon 2/1/27 | Thu 2/25/27
6587 | 2801 | Future Task |  |  | D447 | Joy Schneider | Create | D447 - Create January 2027 Monthly Performance Report | 3 hrs | 9 days | Mon 2/1/27 | Thu 2/11/27 | 2799 | 2802 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6540 | 2802 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 2/12/27 | Fri 2/12/27 | 2801 | 2803 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6541 | 2803 | Future Task |  |  | D447 | Joy Schneider | Submit | DEL D447 - Monthly Performance Report (January 2027) - Submit | 0 hrs | 0 days | Fri 2/12/27 | Fri 2/12/27 | 2802 | 2804 |  | Joy Schneider
6542 | 2804 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Department QC | 1 hr | 7 days | Mon 2/15/27 | Tue 2/23/27 | 2803 | 2805 |  | Gabriela Gibson
6543 | 2805 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 2/24/27 | Thu 2/25/27 | 2804 | 2806 |  | Sean Buchanan
6544 | 2806 | Future Task |  |  | D447 | Joy Schneider | Accept | DEL D447 - Monthly Performance Report (January 2027) - Accept | 0 hrs | 0 days | Thu 2/25/27 | Thu 2/25/27 | 2805 | 2808 |  | Sean Buchanan
6545 | 2807 | Future Task |  |  | D448 | Joy Schneider |  | D448 - Monthly Performance Report (February 2027) | 10 hrs | 19 days | Mon 3/1/27 | Thu 3/25/27
6586 | 2808 | Future Task |  |  | D448 | Joy Schneider | Create | D448 - Create February 2027 Monthly Performance Report | 3 hrs | 9 days | Mon 3/1/27 | Thu 3/11/27 | 2806 | 2809 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6546 | 2809 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 3/12/27 | Fri 3/12/27 | 2808 | 2810 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6547 | 2810 | Future Task |  |  | D448 | Joy Schneider | Submit | DEL D448 - Monthly Performance Report (February 2027) - Submit | 0 hrs | 0 days | Fri 3/12/27 | Fri 3/12/27 | 2809 | 2811 |  | Joy Schneider
6548 | 2811 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Department QC | 1 hr | 7 days | Mon 3/15/27 | Tue 3/23/27 | 2810 | 2812 |  | Gabriela Gibson
6549 | 2812 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 3/24/27 | Thu 3/25/27 | 2811 | 2813 |  | Sean Buchanan
6550 | 2813 | Future Task |  |  | D448 | Joy Schneider | Accept | DEL D448 - Monthly Performance Report (February 2027) - Accept | 0 hrs | 0 days | Thu 3/25/27 | Thu 3/25/27 | 2812 | 2815 |  | Sean Buchanan
6551 | 2814 | Future Task |  |  | D449 | Joy Schneider |  | D449 - Monthly Performance Report (March 2027) | 10 hrs | 19 days | Thu 4/1/27 | Tue 4/27/27
6585 | 2815 | Future Task |  |  | D449 | Joy Schneider | Create | D449 - Create March 2027 Monthly Performance Report | 3 hrs | 9 days | Thu 4/1/27 | Tue 4/13/27 | 2813 | 2816 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6552 | 2816 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 4/14/27 | Wed 4/14/27 | 2815 | 2817 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6553 | 2817 | Future Task |  |  | D449 | Joy Schneider | Submit | DEL D449 - Monthly Performance Report (March 2027) - Submit | 0 hrs | 0 days | Wed 4/14/27 | Wed 4/14/27 | 2816 | 2818 |  | Joy Schneider
6554 | 2818 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Department QC | 1 hr | 7 days | Thu 4/15/27 | Fri 4/23/27 | 2817 | 2819 |  | Gabriela Gibson
6555 | 2819 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Contract Manager Review | 2 hrs | 2 days | Mon 4/26/27 | Tue 4/27/27 | 2818 | 2820 |  | Sean Buchanan
6556 | 2820 | Future Task |  |  | D449 | Joy Schneider | Accept | DEL D449 - Monthly Performance Report (March 2027) - Accept | 0 hrs | 0 days | Tue 4/27/27 | Tue 4/27/27 | 2819 | 2822 |  | Sean Buchanan
6557 | 2821 | Future Task |  |  | D450 | Joy Schneider |  | D450 - Monthly Performance Report (April 2027) | 10 hrs | 19 days | Mon 5/3/27 | Thu 5/27/27
6584 | 2822 | Future Task |  |  | D450 | Joy Schneider | Create | D450 - Create April 2027 Monthly Performance Report | 3 hrs | 9 days | Mon 5/3/27 | Thu 5/13/27 | 2820 | 2823 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6558 | 2823 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 5/14/27 | Fri 5/14/27 | 2822 | 2824 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6559 | 2824 | Future Task |  |  | D450 | Joy Schneider | Submit | DEL D450 - Monthly Performance Report (April 2027) - Submit | 0 hrs | 0 days | Fri 5/14/27 | Fri 5/14/27 | 2823 | 2825 |  | Joy Schneider
6560 | 2825 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Department QC | 1 hr | 7 days | Mon 5/17/27 | Tue 5/25/27 | 2824 | 2826 |  | Gabriela Gibson
6561 | 2826 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 5/26/27 | Thu 5/27/27 | 2825 | 2827 |  | Sean Buchanan
6562 | 2827 | Future Task |  |  | D450 | Joy Schneider | Accept | DEL D450 - Monthly Performance Report (April 2027) - Accept | 0 hrs | 0 days | Thu 5/27/27 | Thu 5/27/27 | 2826 | 2829 |  | Sean Buchanan
6563 | 2828 | Future Task |  |  | D451 | Joy Schneider |  | D451 - Monthly Performance Report (May 2027) | 10 hrs | 19 days | Tue 6/1/27 | Fri 6/25/27
6583 | 2829 | Future Task |  |  | D451 | Joy Schneider | Create | D451 - Create May 2027 Monthly Performance Report | 3 hrs | 9 days | Tue 6/1/27 | Fri 6/11/27 | 2827 | 2830 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6564 | 2830 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 6/14/27 | Mon 6/14/27 | 2829 | 2831 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6565 | 2831 | Future Task |  |  | D451 | Joy Schneider | Submit | DEL D451 - Monthly Performance Report (May 2027) - Submit | 0 hrs | 0 days | Mon 6/14/27 | Mon 6/14/27 | 2830 | 2832 |  | Joy Schneider
6566 | 2832 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Department QC | 1 hr | 7 days | Tue 6/15/27 | Wed 6/23/27 | 2831 | 2833 |  | Gabriela Gibson
6567 | 2833 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Contract Manager Review | 2 hrs | 2 days | Thu 6/24/27 | Fri 6/25/27 | 2832 | 2834 |  | Sean Buchanan
6568 | 2834 | Future Task |  |  | D451 | Joy Schneider | Accept | DEL D451 - Monthly Performance Report (May 2027) - Accept | 0 hrs | 0 days | Fri 6/25/27 | Fri 6/25/27 | 2833 | 2836 |  | Sean Buchanan
6569 | 2835 | Future Task |  |  | D694 | Joy Schneider |  | D694 - Monthly Performance Report (June 2027) | 10 hrs | 19 days | Thu 7/1/27 | Wed 7/28/27
6582 | 2836 | Future Task |  |  | D694 | Joy Schneider | Create | D694 - Create June 2027 Monthly Performance Report | 3 hrs | 9 days | Thu 7/1/27 | Wed 7/14/27 | 2834 | 2837 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6570 | 2837 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 7/15/27 | Thu 7/15/27 | 2836 | 2838 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6571 | 2838 | Future Task |  |  | D694 | Joy Schneider | Submit | DEL D694 - Monthly Performance Report (June 2027) - Submit | 0 hrs | 0 days | Thu 7/15/27 | Thu 7/15/27 | 2837 | 2839 |  | Joy Schneider
6572 | 2839 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Department QC | 1 hr | 7 days | Fri 7/16/27 | Mon 7/26/27 | 2838 | 2840 |  | Gabriela Gibson
6573 | 2840 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Contract Manager Review | 2 hrs | 2 days | Tue 7/27/27 | Wed 7/28/27 | 2839 | 2841 |  | Sean Buchanan
6574 | 2841 | Future Task |  |  | D694 | Joy Schneider | Accept | DEL D694 - Monthly Performance Report (June 2027) - Accept | 0 hrs | 0 days | Wed 7/28/27 | Wed 7/28/27 | 2840 | 2843 |  | Sean Buchanan
6575 | 2842 | Future Task |  |  | D695 | Joy Schneider |  | D695 - Monthly Performance Report (July 2027) | 10 hrs | 19 days | Mon 8/2/27 | Thu 8/26/27
6581 | 2843 | Future Task |  |  | D695 | Joy Schneider | Create | D695 - Create July 2027 Monthly Performance Report | 3 hrs | 9 days | Mon 8/2/27 | Thu 8/12/27 | 2841 | 2844 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6576 | 2844 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 8/13/27 | Fri 8/13/27 | 2843 | 2845 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6577 | 2845 | Future Task |  |  | D695 | Joy Schneider | Submit | DEL D695 - Monthly Performance Report (July 2027) - Submit | 0 hrs | 0 days | Fri 8/13/27 | Fri 8/13/27 | 2844 | 2846 |  | Joy Schneider
6578 | 2846 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Department QC | 1 hr | 7 days | Mon 8/16/27 | Tue 8/24/27 | 2845 | 2847 |  | Gabriela Gibson
6579 | 2847 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 8/25/27 | Thu 8/26/27 | 2846 | 2848 |  | Sean Buchanan
6580 | 2848 | Future Task |  |  | D695 | Joy Schneider | Accept | DEL D695 - Monthly Performance Report (July 2027) - Accept | 0 hrs | 0 days | Thu 8/26/27 | Thu 8/26/27 | 2847 |  |  | Sean Buchanan
4047 | 2849 | Future Task | [5 empty] | Quarterly Newsletter for DDI of Reporting Functionality | 132 hrs | 658 days | Wed 6/21/23 | Mon 2/2/26
4048 | 2850 | Future Task | [5 empty] | Quarterly Newsletter | 132 hrs | 658 days | Wed 6/21/23 | Mon 2/2/26
4049 | 2851 | Future Task | [5 empty] | Quarterly Newsletter FY 22-23 Q4 | 12 hrs | 17 days | Wed 6/21/23 | Fri 7/14/23
4050 | 2852 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Wed 6/21/23 | Tue 6/27/23 |  | 2853 |  | Jennifer Grant,Jennifer Reeves
4051 | 2853 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Wed 6/28/23 | Wed 7/5/23 | 2852 | 2854 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4052 | 2854 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Thu 7/6/23 | Wed 7/12/23 | 2853 | 2855 |  | Jimmy Cox,Steven Fielder
4053 | 2855 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Thu 7/13/23 | Fri 7/14/23 | 2854 | 2857 |  | Dusti Kincl
4054 | 2856 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q1 | 12 hrs | 17 days | Fri 9/22/23 | Mon 10/16/23
4055 | 2857 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 9/22/23 | Thu 9/28/23 | 2855 | 2858 |  | Jennifer Grant,Jennifer Reeves
4056 | 2858 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 9/29/23 | Thu 10/5/23 | 2857 | 2859 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4057 | 2859 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 10/6/23 | Thu 10/12/23 | 2858 | 2860 |  | Jimmy Cox,Steven Fielder
4058 | 2860 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 10/13/23 | Mon 10/16/23 | 2859 | 2862 |  | Dusti Kincl
4059 | 2861 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q2 | 12 hrs | 17 days | Mon 12/18/23 | Thu 1/11/24
4060 | 2862 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 12/18/23 | Fri 12/22/23 | 2860 | 2863 |  | Jennifer Grant,Jennifer Reeves
4061 | 2863 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Tue 12/26/23 | Tue 1/2/24 | 2862 | 2864 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4062 | 2864 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Wed 1/3/24 | Tue 1/9/24 | 2863 | 2865 |  | Jimmy Cox,Steven Fielder
4063 | 2865 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Wed 1/10/24 | Thu 1/11/24 | 2864 | 2867 |  | Dusti Kincl
4064 | 2866 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q3 | 12 hrs | 17 days | Fri 3/22/24 | Mon 4/15/24
4065 | 2867 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 3/22/24 | Thu 3/28/24 | 2865 | 2868 |  | Jennifer Grant,Jennifer Reeves
4066 | 2868 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 3/29/24 | Thu 4/4/24 | 2867 | 2869 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4067 | 2869 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 4/5/24 | Thu 4/11/24 | 2868 | 2870 |  | Jimmy Cox,Steven Fielder
4068 | 2870 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 4/12/24 | Mon 4/15/24 | 2869 | 2872 |  | Dusti Kincl
4069 | 2871 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q4 | 12 hrs | 17 days | Thu 6/20/24 | Mon 7/15/24
4070 | 2872 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Thu 6/20/24 | Wed 6/26/24 | 2870 | 2873 |  | Jennifer Grant,Jennifer Reeves
4071 | 2873 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Thu 6/27/24 | Wed 7/3/24 | 2872 | 2874 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4072 | 2874 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 7/5/24 | Thu 7/11/24 | 2873 | 2875 |  | Jimmy Cox,Steven Fielder
4073 | 2875 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 7/12/24 | Mon 7/15/24 | 2874 | 2877 |  | Dusti Kincl
4074 | 2876 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q1 | 12 hrs | 17 days | Mon 9/23/24 | Tue 10/15/24
4075 | 2877 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 2875 | 2878 |  | Jennifer Grant,Jennifer Reeves
4076 | 2878 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Mon 9/30/24 | Fri 10/4/24 | 2877 | 2879 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4077 | 2879 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 | 2878 | 2880 |  | Jimmy Cox,Steven Fielder
4078 | 2880 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Mon 10/14/24 | Tue 10/15/24 | 2879 | 2882 |  | Dusti Kincl
4079 | 2881 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q2 | 12 hrs | 17 days | Mon 12/16/24 | Thu 1/9/25
4080 | 2882 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 12/16/24 | Fri 12/20/24 | 2880 | 2883 |  | Jennifer Grant,Jennifer Reeves
4081 | 2883 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Mon 12/23/24 | Mon 12/30/24 | 2882 | 2884 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4082 | 2884 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Tue 12/31/24 | Tue 1/7/25 | 2883 | 2885 |  | Jimmy Cox,Steven Fielder
4083 | 2885 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Wed 1/8/25 | Thu 1/9/25 | 2884 | 2887 |  | Dusti Kincl
4084 | 2886 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q3 | 12 hrs | 17 days | Mon 3/24/25 | Tue 4/15/25
4085 | 2887 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 2885 | 2888 |  | Jennifer Grant,Jennifer Reeves
4086 | 2888 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Mon 3/31/25 | Fri 4/4/25 | 2887 | 2889 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4087 | 2889 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Mon 4/7/25 | Fri 4/11/25 | 2888 | 2890 |  | Jimmy Cox,Steven Fielder
4088 | 2890 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Mon 4/14/25 | Tue 4/15/25 | 2889 | 2892 |  | Dusti Kincl
4089 | 2891 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q4 | 12 hrs | 17 days | Fri 6/20/25 | Tue 7/15/25
4090 | 2892 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 6/20/25 | Thu 6/26/25 | 2890 | 2893 |  | Jennifer Grant,Jennifer Reeves
4091 | 2893 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 6/27/25 | Thu 7/3/25 | 2892 | 2894 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4092 | 2894 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Mon 7/7/25 | Fri 7/11/25 | 2893 | 2895 |  | Jimmy Cox,Steven Fielder
4093 | 2895 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Mon 7/14/25 | Tue 7/15/25 | 2894 | 2897 |  | Dusti Kincl
4094 | 2896 | Future Task | [5 empty] | Quarterly Newsletter FY 25-26 Q1 | 12 hrs | 17 days | Fri 9/26/25 | Mon 10/20/25
4095 | 2897 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 9/26/25 | Thu 10/2/25 | 2895 | 2898 |  | Jennifer Grant,Jennifer Reeves
4096 | 2898 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 10/3/25 | Thu 10/9/25 | 2897 | 2899 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4097 | 2899 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 10/10/25 | Thu 10/16/25 | 2898 | 2900 |  | Jimmy Cox,Steven Fielder
4098 | 2900 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 10/17/25 | Mon 10/20/25 | 2899 | 2902 |  | Dusti Kincl
4099 | 2901 | Future Task | [5 empty] | Quarterly Newsletter FY 25-26 Q2 | 12 hrs | 17 days | Thu 1/8/26 | Mon 2/2/26
4100 | 2902 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Thu 1/8/26 | Wed 1/14/26 | 2900 | 2903 |  | Jennifer Grant,Jennifer Reeves
4101 | 2903 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Thu 1/15/26 | Thu 1/22/26 | 2902 | 2904 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4102 | 2904 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 1/23/26 | Thu 1/29/26 | 2903 | 2905 |  | Jimmy Cox,Steven Fielder
4103 | 2905 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 1/30/26 | Mon 2/2/26 | 2904 |  |  | Dusti Kincl

## DO NOT EDIT - Prior 6.9.2023 (hidden)
Unique ID | ID | Status | Critical Path | RW | DEL, WP, SG # | Task Coordinator | Task Type | Task Name | Work | Duration | Start | Finish | Predecessors | Successors | Notes | Resource Names | Requested Updates | Requested By
0 | 0 | Late | [5 empty] | Project Schedule (Financials, Payroll, Data Warehouse and Business Intelligence) | 24,153.91 hrs | 1177 days | Wed 4/26/23 | Tue 12/28/27
7152 | 1 | Complete |  |  |  | Jimmy Cox |  | Amendment 8 Executed | 0 hrs | 0 days | Wed 4/26/23 | Wed 4/26/23 |  | 11,34FS+3 days,53FS+47 days,90FS+27 days,111FS+27 days,216,347FS+91 days,189FS+27 days,203FS+27 days,589FS+47 days,72FS+27 days,151,170,229,243,257,334,387,443,465,485,505,525,538,642,684,743,783,808,827,845,887,912,931,1003,1021,1046,1060,1140,1154,117... |  | Jimmy Cox
2 | 2 | Late | [5 empty] | Implementation | 16,137.58 hrs | 699 days | Wed 4/26/23 | Wed 2/4/26
3769 | 3 | Late | [5 empty] | Design | 5,127 hrs | 475 days | Wed 4/26/23 | Fri 3/14/25
7172 | 4 | Future Task |  |  | SG1 | Jimmy Cox |  | Stage Gate 1: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 7/3/23 | Mon 7/10/23 |  | 5 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7170 | 5 | Future Task |  |  | SG1 | Jimmy Cox |  | Stage Gate 1: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Tue 7/11/23 | Mon 7/24/23 | 4 | 6FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7171 | 6 | Future Task |  |  | SG1 | Jimmy Cox |  | Stage Gate 1: Prepare information package for ESC | 11 hrs | 10 days | Mon 11/13/23 | Tue 11/28/23 | 5FS+77 days | 7 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder | This date, as displayed, starts after the milestone for Stage Gate 1 (10/23/23). Please adjust Milestone (Unique ID 7155) to be in November / December. Note from Joy on 6/6: this task begins on 7/3 and the fifth step in the set of SG tasks ends on 12/6 | Angie
7169 | 7 | Future Task |  |  | SG1 | Jimmy Cox |  | Stage Gate 1: Collaborative Review and Update of information package | 11 hrs | 5 days | Wed 11/29/23 | Tue 12/5/23 | 6 | 8 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7168 | 8 | Future Task |  |  | SG1 | Jimmy Cox |  | Stage Gate 1: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 12/6/23 | Wed 12/6/23 | 7 |  |  | Dusti Kincl
7155 | 9 | Future Task |  |  | SG1 | Jimmy Cox | Milestone | Stage Gate 1: Ready to Start Build | 0 hrs | 0 days | Mon 10/23/23 | Mon 10/23/23 | 51,61 |  | Nov/Dec 2023 | Jimmy Cox,Angie Robertson,Matt Cole | See comment above. Note from Joy on 6/6: date is based on current preds. We will baseline on the last business day of December and then adjust to auto schedule to allow the team to see shifting dates. | Angie
3793 | 10 | Late |  |  | D635 | Joy Schneider |  | D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) | 448 hrs | 38 days | Mon 5/8/23 | Thu 6/29/23
7130 | 11 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Develop Outline of Project Schedule | 2 hrs | 1 day | Mon 5/8/23 | Mon 5/8/23 | 1 | 12SS |  | Joy Schneider,Francisca Li
7131 | 12 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Create New Schedule Tasks Workbook | 4 hrs | 1 day | Mon 5/8/23 | Mon 5/8/23 | 11SS | 13,14,15FS+1 day |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner
7132 | 13 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Gather Tasks from State Architects | 60 hrs | 4 days | Tue 5/9/23 | Fri 5/12/23 | 12 | 23 |  | Julian Gotreaux,Gabriela Gibson,Tommy Werner,Angie Robertson,Deana Metcalf,Carolyn Hicks,Jennifer Reeves,Matthew Breeding
7133 | 14 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Load Amendment 8 Deliverables and Work Products to Project Schedule | 4 hrs | 2 days | Tue 5/9/23 | Wed 5/10/23 | 12 | 23 |  | Joy Schneider,Francisca Li
7134 | 15 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Load Resources into Project Schedule | 8 hrs | 1 day | Wed 5/10/23 | Wed 5/10/23 | 12FS+1 day | 16 |  | Joy Schneider,Francisca Li
7135 | 16 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Add and Refine Work Activities for Amendment 8 Deliverables | 17 hrs | 2 days | Thu 5/11/23 | Fri 5/12/23 | 15 | 17SS+1 day |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole
7136 | 17 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Add Tasks from State Architects | 10 hrs | 1 day | Fri 5/12/23 | Fri 5/12/23 | 16SS+1 day | 18,19 |  | Joy Schneider,Francisca Li
7138 | 18 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Add and Refine Work Activities for Amendment 8 Work Products | 60 hrs | 5 days | Mon 5/15/23 | Fri 5/19/23 | 17 | 23 |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole
7139 | 19 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Project Schedule Working Sessions | 85 hrs | 5 days | Mon 5/15/23 | Fri 5/19/23 | 17 | 20 |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Manojkumar Gurjar,Yogesh Deshmukh,Matt Cole,Angie Robertson,Deana Metcalf,Matthew Breeding,Carolyn Hicks,Jimmy Cox,Jennifer Reeves
7140 | 20 | Complete |  |  | D635 | Joy Schneider | Create | D635 - Refine Work Activities for Non-SSI Deliverables and Work Products | 26 hrs | 5 days | Mon 5/22/23 | Fri 5/26/23 | 19 | 21SS+2 days |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Gabriela Gibson
7141 | 21 | Late |  |  | D635 | Joy Schneider | Create | D635 - Define Tasks to Assign to Critical Path Column | 25 hrs | 3 days | Wed 5/24/23 | Fri 5/26/23 | 20SS+2 days | 22 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Jimmy Cox,Matt Cole
7142 | 22 | Late |  |  | D635 | Joy Schneider | Create | D635 - Provide Project Schedule Export Reports and Refine Based on Input | 70 hrs | 9 days | Tue 5/30/23 | Fri 6/9/23 | 21 | 23 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Deana Metcalf,Matthew Breeding,Carlos Luis,Jimmy Cox,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Manojkumar Gurjar,Yogesh Deshmukh,Matt Cole,Jennifer Reeves
7143 | 23 | Future Task |  |  | D635 | Joy Schneider | Create | D635 - Conduct Project Schedule Baseline Prep Meeting | 36 hrs | 1 day | Mon 6/12/23 | Mon 6/12/23 | 22,13,14,18 | 24 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Deana Metcalf,Matthew Breeding,Carolyn Hicks,Jimmy Cox,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole,Gabriela Gibson,Jennifer Reeves
4271 | 24 | Future Task |  |  | D635 | Joy Schneider | Submit | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Draft Submission | 0 hrs | 0 days | Mon 6/12/23 | Mon 6/12/23 | 23 | 25 |  | Joy Schneider
4272 | 25 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Pre-Submission Collaborative Review | 14 hrs | 3 days | Tue 6/13/23 | Thu 6/15/23 | 24 | 26 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Gabriela Gibson,Jenifer Hartsfield,Angie Robertson
4273 | 26 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Style Guide Review | 1 hr | 1 day | Fri 6/16/23 | Fri 6/16/23 | 25 | 27 |  | Dusti Kincl
4274 | 27 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Final Collaborative Review | 10 hrs | 3 days | Mon 6/19/23 | Wed 6/21/23 | 26 | 28 |  | Joy Schneider,Francisca Li,Angie Robertson,Jimmy Cox,Jennifer Reeves,Deana Metcalf,Matthew Breeding,Carolyn Hicks
4275 | 28 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Accenture QC | 4 hrs | 2 days | Thu 6/22/23 | Fri 6/23/23 | 27 | 29 |  | Joy Schneider
4276 | 29 | Future Task |  |  | D635 | Joy Schneider | Submit | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Submit | 0 hrs | 0 days | Fri 6/23/23 | Fri 6/23/23 | 28 | 30 |  | Joy Schneider
4277 | 30 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Department QC | 4 hrs | 1 day | Mon 6/26/23 | Mon 6/26/23 | 29 | 31 |  | Tommy Werner,Gabriela Gibson
4278 | 31 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Contract Manager Review | 8 hrs | 3 days | Tue 6/27/23 | Thu 6/29/23 | 30 | 32 |  | Sean Buchanan
4279 | 32 | Future Task |  |  | D635 | Joy Schneider | Accept | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Accept | 0 hrs | 0 days | Thu 6/29/23 | Thu 6/29/23 | 31 | 2320 | 2023-06-01 | Sean Buchanan
4280 | 33 | Late |  |  | D636 | Stacey Terry |  | D636 - Completion of Solution Design (Requirements) Segment I | 309 hrs | 82 days | Mon 5/1/23 | Thu 8/24/23
4308 | 34 | Late |  |  | D636 | Stacey Terry | Create | D636 - Identify Functional Designs (Segment I) | 50 hrs | 10 days | Mon 5/1/23 | Fri 5/12/23 | 1FS+3 days | 35 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4281 | 35 | Late |  |  | D636 | Stacey Terry | Create | DED D636 - Completion of Solution Design (Requirements) Segment I - Create | 8 hrs | 10 days | Mon 5/15/23 | Fri 5/26/23 | 34 | 36 |  | Stacey Terry,Mary Punty
4282 | 36 | Late |  |  | D636 | Stacey Terry | Submit | DED D636 - Completion of Solution Design (Requirements) Segment I - Submit | 0 hrs | 0 days | Fri 5/26/23 | Fri 5/26/23 | 35 | 37 |  | Stacey Terry,Joy Schneider
4283 | 37 | Late |  |  | D636 | Stacey Terry | Review | DED D636 - Completion of Solution Design (Requirements) Segment I - Collaborative Review | 24 hrs | 4 days | Tue 5/30/23 | Fri 6/2/23 | 36 | 38 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4284 | 38 | Late |  |  | D636 | Stacey Terry | Approve | DED D636 - Completion of Solution Design (Requirements) Segment I - Approve | 0 hrs | 0 days | Fri 6/2/23 | Fri 6/2/23 | 37 | 39 |  | Jimmy Cox
4309 | 39 | Future Task |  |  | D636 | Stacey Terry | Create | D636 - Update Deliverable Work Unit Tracker for Functional Designs (Segment I) | 50 hrs | 5 days | Mon 6/5/23 | Fri 6/9/23 | 38 | 40 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4310 | 40 | Future Task |  |  | D636 | Stacey Terry | Create | D636 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment I) | 50 hrs | 4 days | Mon 6/12/23 | Thu 6/15/23 | 39 | 41 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4311 | 41 | Future Task |  |  | D636 | Stacey Terry | Create | D636 - Create, Review and Approve Functional Design Documents (Segment I) | 50 hrs | 32 days | Fri 6/16/23 | Tue 8/1/23 | 40 | 42FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis... | RW/Communication - Segment 1 Workshop? | NK
4312 | 42 | Future Task |  |  | D636 | Stacey Terry | Create | D636 - Create Summary Document | 20 hrs | 11 days | Tue 7/18/23 | Tue 8/1/23 | 41FS-11 days | 43,1559SS,1603SS,1646SS,1471,1516 |  | Deana Metcalf,Stacey Terry,Mary Punty
4285 | 43 | Future Task |  |  | D636 | Stacey Terry | Submit | DEL D636 - Completion of Solution Design (Requirements) Segment I - Draft Submission | 0 hrs | 0 days | Tue 8/1/23 | Tue 8/1/23 | 42 | 44 |  | Stacey Terry,Joy Schneider
4286 | 44 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Wed 8/2/23 | Tue 8/8/23 | 43 | 45 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4287 | 45 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Style Guide Review | 1 hr | 1 day | Wed 8/9/23 | Wed 8/9/23 | 44 | 46 |  | Dusti Kincl
4288 | 46 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Final Collaborative Review | 20 hrs | 5 days | Thu 8/10/23 | Wed 8/16/23 | 45 | 47 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4289 | 47 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Accenture QC | 4 hrs | 2 days | Thu 8/17/23 | Fri 8/18/23 | 46 | 48 |  | Joy Schneider
4290 | 48 | Future Task |  |  | D636 | Stacey Terry | Submit | DEL D636 - Completion of Solution Design (Requirements) Segment I - Submit | 0 hrs | 0 days | Fri 8/18/23 | Fri 8/18/23 | 47 | 491681 |  | Joy Schneider
4291 | 49 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Department QC | 4 hrs | 1 day | Mon 8/21/23 | Mon 8/21/23 | 48 | 50 |  | Tommy Werner,Gabriela Gibson
4292 | 50 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Contract Manager Review | 8 hrs | 3 days | Tue 8/22/23 | Thu 8/24/23 | 49 | 51 |  | Sean Buchanan
4293 | 51 | Future Task |  |  | D636 | Stacey Terry | Accept | DEL D636 - Completion of Solution Design (Requirements) Segment I - Accept | 0 hrs | 0 days | Thu 8/24/23 | Thu 8/24/23 | 50 | 220,572,581,587,9 | July 2023 (Aug 2023) | Sean Buchanan
4294 | 52 | Future Task |  |  | D637 | Stacey Terry |  | D637 - Completion of Solution Design (Requirements) Segment II | 342 hrs | 96 days | Mon 7/3/23 | Thu 11/16/23
4313 | 53 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Identify Functional Designs (Segment II) | 50 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 1FS+47 days | 54 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4295 | 54 | Future Task |  |  | D637 | Stacey Terry | Create | DED D637 - Completion of Solution Design (Requirements) Segment II - Create | 16 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 53 | 55 |  | Stacey Terry,Mary Punty
4296 | 55 | Future Task |  |  | D637 | Stacey Terry | Submit | DED D637 - Completion of Solution Design (Requirements) Segment II - Submit | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 54 | 56 |  | Stacey Terry,Joy Schneider
4297 | 56 | Future Task |  |  | D637 | Stacey Terry | Review | DED D637 - Completion of Solution Design (Requirements) Segment II - Collaborative Review | 24 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 55 | 57 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4298 | 57 | Future Task |  |  | D637 | Stacey Terry | Approve | DED D637 - Completion of Solution Design (Requirements) Segment II - Approve | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 56 | 58 |  | Jimmy Cox
4314 | 58 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Update Deliverable Work Unit Tracker for Functional Designs (Segment II) | 50 hrs | 4 days | Tue 8/15/23 | Fri 8/18/23 | 57 | 59 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4315 | 59 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment II) | 50 hrs | 5 days | Mon 8/21/23 | Fri 8/25/23 | 58 | 60 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4316 | 60 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Create, Review and Approve Functional Design Documents (Segment II) | 50 hrs | 40 days | Mon 8/28/23 | Mon 10/23/23 | 59 | 61FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis... | RW/Communication - Segment 1 Workshop? | NK
4317 | 61 | Future Task |  |  | D637 | Stacey Terry | Create | D637 - Create Summary Document | 50 hrs | 11 days | Mon 10/9/23 | Mon 10/23/23 | 60FS-11 days | 62,1562SS,1428SS,1606SS+2 days,1649SS+5 days,1474,1519,9 |  | Deana Metcalf,Stacey Terry,Mary Punty
4299 | 62 | Future Task |  |  | D637 | Stacey Terry | Submit | DEL D637 - Completion of Solution Design (Requirements) Segment II - Draft Submission | 0 hrs | 0 days | Mon 10/23/23 | Mon 10/23/23 | 61 | 63 |  | Stacey Terry,Joy Schneider
4300 | 63 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 10/24/23 | Mon 10/30/23 | 62 | 64 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4301 | 64 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Style Guide Review | 1 hr | 1 day | Tue 10/31/23 | Tue 10/31/23 | 63 | 65 |  | Dusti Kincl
4302 | 65 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Final Collaborative Review | 20 hrs | 5 days | Wed 11/1/23 | Tue 11/7/23 | 64 | 66 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4303 | 66 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Accenture QC | 1 hr | 2 days | Wed 11/8/23 | Thu 11/9/23 | 65 | 67 |  | Francisca Li
4304 | 67 | Future Task |  |  | D637 | Stacey Terry | Submit | DEL D637 - Completion of Solution Design (Requirements) Segment II - Submit | 0 hrs | 0 days | Thu 11/9/23 | Thu 11/9/23 | 66 | 68 |  | Joy Schneider
4305 | 68 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Department QC | 2 hrs | 1 day | Mon 11/13/23 | Mon 11/13/23 | 67 | 69 |  | Tommy Werner,Gabriela Gibson
4306 | 69 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Contract Manager Review | 8 hrs | 3 days | Tue 11/14/23 | Thu 11/16/23 | 68 | 70 |  | Sean Buchanan
4307 | 70 | Future Task |  |  | D637 | Stacey Terry | Accept | DEL D637 - Completion of Solution Design (Requirements) Segment II - Accept | 0 hrs | 0 days | Thu 11/16/23 | Thu 11/16/23 | 69 | 572581587 | October 2023 (Nov 2023) | Sean Buchanan
5585 | 71 | Future Task | Maybe |  | D638 | Manojkumar Gurjar |  | D638 - Updated Data Conversion and Migration Strategy | 213 hrs | 80 days | Mon 6/5/23 | Tue 9/26/23
5586 | 72 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | DED D638 - Updated Data Conversion and Migration Strategy - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 73 |  | Manojkumar Gurjar,Kurt Meisner
5587 | 73 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DED D638 - Updated Data Conversion and Migration Strategy - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 72 | 74 |  | Manojkumar Gurjar,Joy Schneider
5588 | 74 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DED D638 - Updated Data Conversion and Migration Strategy - Collaborative Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 73 | 75 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5589 | 75 | Future Task |  |  | D638 | Manojkumar Gurjar | Approve | DED D638 - Updated Data Conversion and Migration Strategy - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 74 | 76 |  | Jimmy Cox
5590 | 76 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | D638 - Define the approach for Data Cleansing | 8 hrs | 14 days | Mon 7/3/23 | Fri 7/21/23 | 75 | 77SS+4 days |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5591 | 77 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | D638 - Define Communication/Collaboration for Data Conversion approach | 8 hrs | 10 days | Mon 7/10/23 | Fri 7/21/23 | 76SS+4 days | 78 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5592 | 78 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | D638 - Identify Data Conversion Resources | 50 hrs | 10 days | Mon 7/24/23 | Fri 8/4/23 | 77 | 79 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer,Jeevan Mahajan,Janmejay Khare
5593 | 79 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | D638 - Updated Data Conversion and Migration Strategy Document | 50 hrs | 19 days | Mon 8/7/23 | Thu 8/31/23 | 78 | 80 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5594 | 80 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DEL D638 - Updated Data Conversion and Migration Strategy - Draft Submission | 0 hrs | 0 days | Thu 8/31/23 | Thu 8/31/23 | 79 | 81 |  | Manojkumar Gurjar,Joy Schneider
5595 | 81 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 80 | 82 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5596 | 82 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Style Guide Review | 1 hr | 1 day | Mon 9/11/23 | Mon 9/11/23 | 81 | 83 |  | Dusti Kincl
5597 | 83 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Final Collaborative Review | 20 hrs | 5 days | Tue 9/12/23 | Mon 9/18/23 | 82 | 84 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5598 | 84 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Accenture QC | 4 hrs | 2 days | Tue 9/19/23 | Wed 9/20/23 | 83 | 85 |  | Joy Schneider
5599 | 85 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DEL D638 - Updated Data Conversion and Migration Strategy - Submit | 0 hrs | 0 days | Wed 9/20/23 | Wed 9/20/23 | 84 | 86 |  | Joy Schneider
5600 | 86 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Department QC | 4 hrs | 1 day | Thu 9/21/23 | Thu 9/21/23 | 85 | 87 |  | Tommy Werner,Gabriela Gibson
5601 | 87 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Contract Manager Review | 8 hrs | 3 days | Fri 9/22/23 | Tue 9/26/23 | 86 | 88 |  | Sean Buchanan
5602 | 88 | Future Task |  |  | D638 | Manojkumar Gurjar | Accept | DEL D638 - Updated Data Conversion and Migration Strategy - Accept | 0 hrs | 0 days | Tue 9/26/23 | Tue 9/26/23 | 87 |  | 2023-10-01 | Sean Buchanan | RW/Communication to share Conversion Approach? Agencies did not have any agency specific conversions in CMS wave, so this is new for them. | NK
4375 | 89 | Future Task |  |  | D639 | Stacey Terry |  | D639 - Development of Standardized Business Process Models – Payroll | 241 hrs | 94 days | Mon 6/5/23 | Mon 10/16/23
4376 | 90 | Future Task |  |  | D639 | Stacey Terry | Create | DED D639 - Development of Standardized Business Process Models – Payroll - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 91 |  | Stacey Terry,Mary Punty
4377 | 91 | Future Task |  |  | D639 | Stacey Terry | Submit | DED D639 - Development of Standardized Business Process Models – Payroll - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 90 | 92 |  | Stacey Terry,Joy Schneider
4378 | 92 | Future Task |  |  | D639 | Stacey Terry | Review | DED D639 - Development of Standardized Business Process Models – Payroll - Collaborative Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 91 | 93 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4379 | 93 | Future Task |  |  | D639 | Stacey Terry | Approve | DED D639 - Development of Standardized Business Process Models – Payroll - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 92 | 94 |  | Jimmy Cox
4417 | 94 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Identify Payroll Wave Business Processes and Subprocesses | 25 hrs | 5 days | Mon 7/3/23 | Mon 7/10/23 | 93 | 95SS+2 days |  | Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari
4418 | 95 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Update Deliverable Work Unit Tracker for Payroll Wave Business Processes and Subprocesses | 4 hrs | 5 days | Thu 7/6/23 | Wed 7/12/23 | 94SS+2 days | 96 |  | Stacey Terry,Yogesh Deshmukh
4419 | 96 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Review and Confirm Deliverable Work Unit Tracker for Payroll Wave Business Processes and Subprocesses | 20 hrs | 5 days | Thu 7/13/23 | Wed 7/19/23 | 95 | 97SS |  | Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4420 | 97 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Create Payroll Wave Business Process Models | 30 hrs | 30 days | Thu 7/13/23 | Wed 8/23/23 | 96SS | 98 |  | Jimmy Cox,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari,Heather Cleary,Joanne Lane,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Donnie Doctor,Ryan R...
4421 | 98 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Prepare Materials / Conduct Office Hours | 25 hrs | 10 days | Thu 8/24/23 | Thu 9/7/23 | 97 | 99 |  | Jimmy Cox,Angie Robertson,Carolyn Hicks,Dusti Kincl,Kimberly Kemp,Deana Metcalf,Stacey Terry,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Janice Jackson,LaVondria Norton,Robert Hic...
4422 | 99 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Refine Payroll Wave Business Process Models | 20 hrs | 5 days | Fri 9/8/23 | Thu 9/14/23 | 98 | 100 |  | Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari
4423 | 100 | Future Task |  |  | D639 | Stacey Terry | Create | D639 - Create Summary Document | 20 hrs | 5 days | Fri 9/15/23 | Thu 9/21/23 | 99 | 101 |  | Deana Metcalf,Stacey Terry,Mary Punty
4380 | 101 | Future Task |  |  | D639 | Stacey Terry | Submit | DEL D639 - Development of Standardized Business Process Models – Payroll - Draft Submission | 0 hrs | 0 days | Thu 9/21/23 | Thu 9/21/23 | 100 | 102 |  | Stacey Terry,Joy Schneider
4381 | 102 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 9/22/23 | Thu 9/28/23 | 101 | 103 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4382 | 103 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Style Guide Review | 1 hr | 1 day | Fri 9/29/23 | Fri 9/29/23 | 102 | 104 |  | Dusti Kincl
4383 | 104 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Final Collaborative Review | 20 hrs | 5 days | Mon 10/2/23 | Fri 10/6/23 | 103 | 105 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4384 | 105 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Accenture QC | 4 hrs | 2 days | Mon 10/9/23 | Tue 10/10/23 | 104 | 106 |  | Joy Schneider
4385 | 106 | Future Task |  |  | D639 | Stacey Terry | Submit | DEL D639 - Development of Standardized Business Process Models – Payroll - Submit | 0 hrs | 0 days | Tue 10/10/23 | Tue 10/10/23 | 105 | 107 |  | Joy Schneider
4386 | 107 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Department QC | 4 hrs | 1 day | Wed 10/11/23 | Wed 10/11/23 | 106 | 108 |  | Tommy Werner,Gabriela Gibson
4387 | 108 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Contract Manager Review | 8 hrs | 3 days | Thu 10/12/23 | Mon 10/16/23 | 107 | 109 |  | Sean Buchanan
4388 | 109 | Future Task |  |  | D639 | Stacey Terry | Accept | DEL D639 - Development of Standardized Business Process Models – Payroll - Accept | 0 hrs | 0 days | Mon 10/16/23 | Mon 10/16/23 | 108 | 1825572 | 2023-10-01 | Sean Buchanan | RW/Comms? | NK
4389 | 110 | Future Task |  |  | D640 | Stacey Terry |  | D640 - Development of the Master Data Configuration Workbooks | 311 hrs | 142 days | Mon 6/5/23 | Wed 12/27/23
4390 | 111 | Future Task |  |  | D640 | Stacey Terry | Create | DED D640 - Development of the Master Data Configuration Workbooks - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 112,115SS+9 days |  | Stacey Terry,Mary Punty
4391 | 112 | Future Task |  |  | D640 | Stacey Terry | Submit | DED D640 - Development of the Master Data Configuration Workbooks - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 111 | 113 |  | Stacey Terry,Joy Schneider
4392 | 113 | Future Task |  |  | D640 | Stacey Terry | Review | DED D640 - Development of the Master Data Configuration Workbooks - Collaborative Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 112 | 114 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4393 | 114 | Future Task |  |  | D640 | Stacey Terry | Approve | DED D640 - Development of the Master Data Configuration Workbooks - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 113 |  |  | Jimmy Cox
4424 | 115 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Identify Configuration Inventory | 20 hrs | 10 days | Fri 6/16/23 | Thu 6/29/23 | 111SS+9 days | 116 |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Donnie Doctor,Ryan Raagas,Pooj... | This first task is set to begin before the DED approves. This should begin after. Note from Joy: no change made, this work has started. | Angie
4425 | 116 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Update Design Work Unit Tracker for Configuration | 4 hrs | 5 days | Fri 6/30/23 | Fri 7/7/23 | 115 | 117 |  | Stacey Terry,Yogesh Deshmukh
4426 | 117 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Review and Confirm Design Work Unit Tracker for Configuration | 50 hrs | 4 days | Mon 7/10/23 | Thu 7/13/23 | 116 | 118 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4427 | 118 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Create, Review, and Confirm Configuration Workbooks and Agency Configuration Workbook Templates | 40 hrs | 80 days | Fri 7/14/23 | Fri 11/3/23 | 117 | 119SS+20 days |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Donnie Doctor,Ryan Raagas,Pooj...
4428 | 119 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Configure Application | 40 hrs | 70 days | Fri 8/11/23 | Mon 11/20/23 | 118SS+20 days | 120 |  | Apoorva Panchanadikar,Divya Gupta,Supriya Vaddi,Suyesh Shingare,Purushottam Karambelkar,Ankita Sarang,Yash Jamkhedkar,Sajal Saurabh,Timtim Goel
4429 | 120 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Finalize Configuration Workbooks | 30 hrs | 10 days | Tue 11/21/23 | Wed 12/6/23 | 119 | 121FS-10 days |  | Apoorva Panchanadikar,Divya Gupta,Supriya Vasudevan,Suyesh Shingare,Purushottam Karambelkar,Ankita Sarang,Yash Jamkhedkar,Sajal Saurabh,Timtim Goel,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Jack Je...
4430 | 121 | Future Task |  |  | D640 | Stacey Terry | Create | D640 - Create Summary Document | 30 hrs | 7 days | Tue 11/21/23 | Fri 12/1/23 | 120FS-10 days | 122 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Mary Punty
4394 | 122 | Future Task |  |  | D640 | Stacey Terry | Submit | DEL D640 - Development of the Master Data Configuration Workbooks - Draft Submission | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 121 | 123 |  | Stacey Terry,Joy Schneider
4395 | 123 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 12/4/23 | Fri 12/8/23 | 122 | 124 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4396 | 124 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Style Guide Review | 1 hr | 1 day | Mon 12/11/23 | Mon 12/11/23 | 123 | 125 |  | Dusti Kincl
4397 | 125 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Final Collaborative Review | 20 hrs | 5 days | Tue 12/12/23 | Mon 12/18/23 | 124 | 126 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4398 | 126 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Accenture QC | 4 hrs | 2 days | Tue 12/19/23 | Wed 12/20/23 | 125 | 127 |  | Joy Schneider
4399 | 127 | Future Task |  |  | D640 | Stacey Terry | Submit | DEL D640 - Development of the Master Data Configuration Workbooks - Submit | 0 hrs | 0 days | Wed 12/20/23 | Wed 12/20/23 | 126 | 128 |  | Joy Schneider
4400 | 128 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Department QC | 4 hrs | 1 day | Thu 12/21/23 | Thu 12/21/23 | 127 | 129 |  | Tommy Werner,Gabriela Gibson
4401 | 129 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Contract Manager Review | 8 hrs | 3 days | Fri 12/22/23 | Wed 12/27/23 | 128 | 130 |  | Sean Buchanan
4402 | 130 | Future Task |  |  | D640 | Stacey Terry | Accept | DEL D640 - Development of the Master Data Configuration Workbooks - Accept | 0 hrs | 0 days | Wed 12/27/23 | Wed 12/27/23 | 129 | 569FS+6 days | 2023-12-01 | Sean Buchanan | RW - Agencies to complete their Agency Config Workbook | NK
4318 | 131 | Future Task |  |  | D641 | Stacey Terry |  | D641 - Completion of Solution Design (Requirements) Segment III | 327 hrs | 96 days | Mon 10/2/23 | Tue 2/20/24
4332 | 132 | Future Task |  |  | D641 | Stacey Terry | Create | Identify Functional Designs (Segment III) | 50 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 1 | 133 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4319 | 133 | Future Task |  |  | D641 | Stacey Terry | Create | DED D641 - Completion of Solution Design (Requirements) Segment III - Create | 16 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 132 | 134 |  | Stacey Terry,Mary Punty
4320 | 134 | Future Task |  |  | D641 | Stacey Terry | Submit | DED D641 - Completion of Solution Design (Requirements) Segment III - Submit | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 133 | 135 |  | Stacey Terry,Joy Schneider
4321 | 135 | Future Task |  |  | D641 | Stacey Terry | Review | DED D641 - Completion of Solution Design (Requirements) Segment III - Collaborative Review | 24 hrs | 10 days | Mon 10/30/23 | Mon 11/13/23 | 134 | 136 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4322 | 136 | Future Task |  |  | D641 | Stacey Terry | Approve | DED D641 - Completion of Solution Design (Requirements) Segment III - Approve | 0 hrs | 0 days | Mon 11/13/23 | Mon 11/13/23 | 135 | 137 |  | Jimmy Cox
4333 | 137 | Future Task |  |  | D641 | Stacey Terry | Create | D641 - Update Deliverable Work Unit Tracker for Functional Designs (Segment III) | 40 hrs | 4 days | Tue 11/14/23 | Fri 11/17/23 | 136 | 138 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4334 | 138 | Future Task |  |  | D641 | Stacey Terry | Create | D641 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment III) | 40 hrs | 5 days | Mon 11/20/23 | Tue 11/28/23 | 137 | 139 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4335 | 139 | Future Task |  |  | D641 | Stacey Terry | Create | D641 - Create, Review and Approve Functional Design Documents (Segment III) | 50 hrs | 40 days | Wed 11/29/23 | Fri 1/26/24 | 138 | 140FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis... | RW/Comms? | NK
4336 | 140 | Future Task |  |  | D641 | Stacey Terry | Create | D641 - Create Summary Document | 50 hrs | 11 days | Thu 1/11/24 | Fri 1/26/24 | 139FS-11 days | 141,1565SS,1609SS,1652SS+5 days,1477SS,1522 |  | Deana Metcalf,Stacey Terry,Mary Punty
4323 | 141 | Future Task |  |  | D641 | Stacey Terry | Submit | DEL D641 - Completion of Solution Design (Requirements) Segment III - Draft Submission | 0 hrs | 0 days | Fri 1/26/24 | Fri 1/26/24 | 140 | 142 |  | Stacey Terry,Joy Schneider
4324 | 142 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 1/29/24 | Fri 2/2/24 | 141 | 143 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4325 | 143 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Style Guide Review | 1 hr | 1 day | Mon 2/5/24 | Mon 2/5/24 | 142 | 144 |  | Dusti Kincl
4326 | 144 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Final Collaborative Review | 20 hrs | 5 days | Tue 2/6/24 | Mon 2/12/24 | 143 | 145 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4327 | 145 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Accenture QC | 4 hrs | 2 days | Tue 2/13/24 | Wed 2/14/24 | 144 | 146 |  | Joy Schneider
4328 | 146 | Future Task |  |  | D641 | Stacey Terry | Submit | DEL D641 - Completion of Solution Design (Requirements) Segment III - Submit | 0 hrs | 0 days | Wed 2/14/24 | Wed 2/14/24 | 145 | 147 |  | Joy Schneider
4329 | 147 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Department QC | 4 hrs | 1 day | Thu 2/15/24 | Thu 2/15/24 | 146 | 148 |  | Tommy Werner,Gabriela Gibson
4330 | 148 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Contract Manager Review | 8 hrs | 3 days | Fri 2/16/24 | Tue 2/20/24 | 147 | 149 |  | Sean Buchanan
4331 | 149 | Future Task |  |  | D641 | Stacey Terry | Accept | DEL D641 - Completion of Solution Design (Requirements) Segment III - Accept | 0 hrs | 0 days | Tue 2/20/24 | Tue 2/20/24 | 148 | 572581587 | January 2024 (Feb 2024) | Sean Buchanan
4337 | 150 | Future Task |  |  | D644 | Stacey Terry |  | D644 - Completion of Solution Design (Requirements) Segment IV | 337 hrs | 85 days | Mon 1/29/24 | Fri 5/24/24
4351 | 151 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Identify Functional Designs (Segment IV) | 50 hrs | 10 days | Mon 1/29/24 | Fri 2/9/24 | 1 | 152 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4338 | 152 | Future Task |  |  | D644 | Stacey Terry | Create | DED D644 - Completion of Solution Design (Requirements) Segment IV - Create | 16 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 151 | 153 |  | Stacey Terry,Mary Punty
4339 | 153 | Future Task |  |  | D644 | Stacey Terry | Submit | DED D644 - Completion of Solution Design (Requirements) Segment IV - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 152 | 154 |  | Stacey Terry,Joy Schneider
4340 | 154 | Future Task |  |  | D644 | Stacey Terry | Review | DED D644 - Completion of Solution Design (Requirements) Segment IV - Collaborative Review | 24 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 153 | 155 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4341 | 155 | Future Task |  |  | D644 | Stacey Terry | Approve | DED D644 - Completion of Solution Design (Requirements) Segment IV - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 154 | 156 |  | Jimmy Cox
4352 | 156 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Update Deliverable Work Unit Tracker for Functional Designs (Segment IV) | 50 hrs | 4 days | Mon 3/11/24 | Thu 3/14/24 | 155 | 157 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4353 | 157 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment IV) | 50 hrs | 4 days | Fri 3/15/24 | Wed 3/20/24 | 156 | 158 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4354 | 158 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Create, Review and Approve Functional Design Documents (Segment IV) | 50 hrs | 30 days | Thu 3/21/24 | Wed 5/1/24 | 157 | 159FS-8 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis... | RW/Comms? | NK
4355 | 159 | Future Task |  |  | D644 | Stacey Terry | Create | D644 - Create Summary Document | 40 hrs | 8 days | Mon 4/22/24 | Wed 5/1/24 | 158FS-8 days | 160,1578SS,1622SS,1665SS+5 days,1490SS,1535SS |  | Deana Metcalf,Stacey Terry,Mary Punty
4342 | 160 | Future Task |  |  | D644 | Stacey Terry | Submit | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Draft Submission | 0 hrs | 0 days | Wed 5/1/24 | Wed 5/1/24 | 159 | 161 |  | Stacey Terry,Joy Schneider
4343 | 161 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Pre-Submission Collaborative Review | 20 hrs | 5 days | Thu 5/2/24 | Wed 5/8/24 | 160 | 162581 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4344 | 162 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Style Guide Review | 1 hr | 1 day | Thu 5/9/24 | Thu 5/9/24 | 161 | 163 |  | Dusti Kincl
4345 | 163 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Final Collaborative Review | 20 hrs | 5 days | Fri 5/10/24 | Thu 5/16/24 | 162 | 164 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4346 | 164 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Accenture QC | 4 hrs | 2 days | Fri 5/17/24 | Mon 5/20/24 | 163 | 165 |  | Joy Schneider
4347 | 165 | Future Task |  |  | D644 | Stacey Terry | Submit | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Submit | 0 hrs | 0 days | Mon 5/20/24 | Mon 5/20/24 | 164 | 166 |  | Joy Schneider
4348 | 166 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Department QC | 4 hrs | 1 day | Tue 5/21/24 | Tue 5/21/24 | 165 | 167 |  | Tommy Werner,Gabriela Gibson
4349 | 167 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Contract Manager Review | 8 hrs | 3 days | Wed 5/22/24 | Fri 5/24/24 | 166 | 168 |  | Sean Buchanan
4350 | 168 | Future Task |  |  | D644 | Stacey Terry | Accept | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Accept | 0 hrs | 0 days | Fri 5/24/24 | Fri 5/24/24 | 167 | 572FS+24 days,587 | April 2024 (May 2024) | Sean Buchanan
4356 | 169 | Future Task |  |  | D650 | Stacey Terry |  | D650 - Completion of Solution Design (Requirements) DW/BI | 347 hrs | 160 days | Fri 3/1/24 | Tue 10/15/24
4357 | 170 | Future Task |  |  | D650 | Stacey Terry | Create | DED D650 - Completion of Solution Design (Requirements) DW/BI - Create | 16 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 1 | 171 |  | Stacey Terry,Mary Punty
4358 | 171 | Future Task |  |  | D650 | Stacey Terry | Submit | DED D650 - Completion of Solution Design (Requirements) DW/BI - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 170 | 172 |  | Stacey Terry,Joy Schneider
4359 | 172 | Future Task |  |  | D650 | Stacey Terry | Review | DED D650 - Completion of Solution Design (Requirements) DW/BI - Collaborative Review | 24 hrs | 10 days | Fri 3/15/24 | Thu 3/28/24 | 171 | 173 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4360 | 173 | Future Task |  |  | D650 | Stacey Terry | Approve | DED D650 - Completion of Solution Design (Requirements) DW/BI - Approve | 0 hrs | 0 days | Thu 3/28/24 | Thu 3/28/24 | 172 | 174 |  | Jimmy Cox
4370 | 174 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Identify Functional Designs DW/BI | 50 hrs | 10 days | Fri 3/29/24 | Thu 4/11/24 | 173 | 175 |  | Stacey Terry,Yogesh Deshmukh
4371 | 175 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Update Deliverable Work Unit Tracker for Functional Designs DW/BI | 50 hrs | 10 days | Fri 4/12/24 | Thu 4/25/24 | 174 | 176 |  | Stacey Terry,Yogesh Deshmukh
4372 | 176 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Review and Confirm Deliverable Work Unit Tracker for Functional Designs DW/BI | 50 hrs | 10 days | Fri 4/26/24 | Thu 5/9/24 | 175 | 177 |  | Stacey Terry,Yogesh Deshmukh
4373 | 177 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Create, Review and Approve Functional Design Documents DW/BI | 50 hrs | 82 days | Fri 5/10/24 | Thu 9/5/24 | 176 | 178 |  | Stacey Terry,Yogesh Deshmukh | RW/Comms? | NK
4374 | 178 | Future Task |  |  | D650 | Stacey Terry | Create | D650 - Create Summary Document | 50 hrs | 11 days | Fri 9/6/24 | Fri 9/20/24 | 177 | 179 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4361 | 179 | Future Task |  |  | D650 | Stacey Terry | Submit | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Draft Submission | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 178 | 180 |  | Stacey Terry,Joy Schneider
4362 | 180 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 179 | 181 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4363 | 181 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Style Guide Review | 1 hr | 1 day | Mon 9/30/24 | Mon 9/30/24 | 180 | 182 |  | Dusti Kincl
4364 | 182 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Final Collaborative Review | 20 hrs | 5 days | Tue 10/1/24 | Mon 10/7/24 | 181 | 183 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4365 | 183 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Accenture QC | 4 hrs | 2 days | Tue 10/8/24 | Wed 10/9/24 | 182 | 184 |  | Joy Schneider
4366 | 184 | Future Task |  |  | D650 | Stacey Terry | Submit | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Submit | 0 hrs | 0 days | Wed 10/9/24 | Wed 10/9/24 | 183 | 185 |  | Joy Schneider
4367 | 185 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Department QC | 4 hrs | 1 day | Thu 10/10/24 | Thu 10/10/24 | 184 | 186 |  | Tommy Werner,Gabriela Gibson
4368 | 186 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Contract Manager Review | 8 hrs | 3 days | Fri 10/11/24 | Tue 10/15/24 | 185 | 187 |  | Sean Buchanan
4369 | 187 | Future Task |  |  | D650 | Stacey Terry | Accept | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Accept | 0 hrs | 0 days | Tue 10/15/24 | Tue 10/15/24 | 186 |  | 2024-10-01 | Sean Buchanan
4431 | 188 | Future Task |  |  | WP402 | Stacey Terry |  | WP402 - Requirements Traceability Matrix | 98 hrs | 55 days | Mon 6/5/23 | Mon 8/21/23
4432 | 189 | Future Task |  |  | WP402 | Stacey Terry | Create | WPED WP402 - Requirements Traceability Matrix - Create | 8 hrs | 5 days | Mon 6/5/23 | Fri 6/9/23 | 1FS+27 days | 190 |  | Stacey Terry,Mary Punty
4433 | 190 | Future Task |  |  | WP402 | Stacey Terry | Submit | WPED WP402 - Requirements Traceability Matrix - Submit | 0 hrs | 0 days | Fri 6/9/23 | Fri 6/9/23 | 189 | 191 |  | Joy Schneider,Stacey Terry
4434 | 191 | Future Task |  |  | WP402 | Stacey Terry | Review | WPED WP402 - Requirements Traceability Matrix - Review | 12 hrs | 5 days | Mon 6/12/23 | Fri 6/16/23 | 190 | 192 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4435 | 192 | Future Task |  |  | WP402 | Stacey Terry | Approve | WPED WP402 - Requirements Traceability Matrix - Approve | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 191 | 193 |  | Jimmy Cox
4449 | 193 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Create Requirements Traceability Matrix Template | 2 hrs | 3 days | Mon 6/19/23 | Wed 6/21/23 | 192 | 194 |  | Stacey Terry,Yogesh Deshmukh
4450 | 194 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Populate Requirements Traceability Matrix Template | 10 hrs | 5 days | Thu 6/22/23 | Wed 6/28/23 | 193 | 195 |  | Stacey Terry,Yogesh Deshmukh
4451 | 195 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Create Summary Document | 6 hrs | 2 days | Thu 6/29/23 | Fri 6/30/23 | 194 | 196 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4436 | 196 | Future Task |  |  | WP402 | Stacey Terry | Submit | WP WP402 - Requirements Traceability Matrix - Submit | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 195 | 197 |  | Joy Schneider,Stacey Terry
4437 | 197 | Future Task |  |  | WP402 | Stacey Terry | Review | WP WP402 - Requirements Traceability Matrix - Collaborative Review & Update | 20 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 196 | 198 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4438 | 198 | Future Task |  |  | WP402 | Stacey Terry | Review | WP WP402 - Requirements Traceability Matrix - Final Review & Edits | 20 hrs | 5 days | Tue 7/18/23 | Mon 7/24/23 | 197 | 199 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4439 | 199 | Future Task |  |  | WP402 | Stacey Terry | Approve | WP WP402 - Requirements Traceability Matrix - Approve | 0 hrs | 0 days | Mon 7/24/23 | Mon 7/24/23 | 198 | 365,404,423,724,200FS+5 days | 2023-06-01 | Jimmy Cox
7147 | 200 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Load Requirements in Requirements Traceability Tool | 10 hrs | 5 days | Tue 8/1/23 | Mon 8/7/23 | 199FS+5 days | 201 |  | Mary Punty,Joy Schneider
7148 | 201 | Future Task |  |  | WP402 | Stacey Terry | Create | WP402 - Validate Requirements in Requirements Traceability Tool | 10 hrs | 10 days | Tue 8/8/23 | Mon 8/21/23 | 200 |  |  | Deana Metcalf,Stacey Terry
4440 | 202 | Future Task |  |  | WP403 | Stacey Terry |  | WP403 - RICEFW Inventory | 200 hrs | 64 days | Mon 6/5/23 | Fri 9/1/23
4441 | 203 | Future Task |  |  | WP403 | Stacey Terry | Create | WPED WP403 - RICEFW Inventory - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 204 |  | Stacey Terry,Mary Punty
4442 | 204 | Future Task |  |  | WP403 | Stacey Terry | Submit | WPED WP403 - RICEFW Inventory - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 203 | 205 |  | Joy Schneider,Stacey Terry
4443 | 205 | Future Task |  |  | WP403 | Stacey Terry | Review | WPED WP403 - RICEFW Inventory - Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 204 | 206 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4444 | 206 | Future Task |  |  | WP403 | Stacey Terry | Approve | WPED WP403 - RICEFW Inventory - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 205 | 207 |  | Jimmy Cox
4454 | 207 | Future Task |  |  | WP403 | Stacey Terry | Create | WP403 - Create RICEFW Inventory Template | 20 hrs | 5 days | Mon 7/3/23 | Mon 7/10/23 | 206 | 208 |  | Deana Metcalf,Stacey Terry
4455 | 208 | Future Task |  |  | WP403 | Stacey Terry | Create | WP403 - Define and document RICEFW Inventory | 50 hrs | 14 days | Tue 7/11/23 | Fri 7/28/23 | 207 | 209 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4456 | 209 | Future Task |  |  | WP403 | Stacey Terry | Create | WP403 - Populate RICEFW Inventory Template | 20 hrs | 5 days | Mon 7/31/23 | Fri 8/4/23 | 208 | 210 |  | Deana Metcalf,Stacey Terry
4457 | 210 | Future Task |  |  | WP403 | Stacey Terry | Create | WP403 - Create Summary Document | 30 hrs | 5 days | Mon 8/7/23 | Fri 8/11/23 | 209 | 211 |  | Deana Metcalf,Stacey Terry,Mary Punty
4445 | 211 | Future Task |  |  | WP403 | Stacey Terry | Submit | WP WP403 - RICEFW Inventory - Submit | 0 hrs | 0 days | Fri 8/11/23 | Fri 8/11/23 | 210 | 212 |  | Joy Schneider,Stacey Terry
4446 | 212 | Future Task |  |  | WP403 | Stacey Terry | Review | WP WP403 - RICEFW Inventory - Collaborative Review & Update | 20 hrs | 10 days | Mon 8/14/23 | Fri 8/25/23 | 211 | 213 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4447 | 213 | Future Task |  |  | WP403 | Stacey Terry | Review | WP WP403 - RICEFW Inventory - Final Review & Edits | 20 hrs | 5 days | Mon 8/28/23 | Fri 9/1/23 | 212 | 214 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4448 | 214 | Future Task |  |  | WP403 | Stacey Terry | Approve | WP WP403 - RICEFW Inventory - Approve | 0 hrs | 0 days | Fri 9/1/23 | Fri 9/1/23 | 213 |  | 2024-04-01 | Jimmy Cox
5667 | 215 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | WP404 - Data Conversion Inventory | 250 hrs | 127 days | Mon 8/7/23 | Thu 2/8/24
5668 | 216 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WPED WP404 - Data Conversion Inventory - Create | 16 hrs | 10 days | Mon 8/7/23 | Fri 8/18/23 | 1 | 217 |  | Manojkumar Gurjar,Kurt Meisner
5669 | 217 | Future Task |  |  | WP404 | Manojkumar Gurjar | Submit | WPED WP404 - Data Conversion Inventory - Submit | 0 hrs | 0 days | Fri 8/18/23 | Fri 8/18/23 | 216 | 218 |  | Manojkumar Gurjar,Joy Schneider
5670 | 218 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WPED WP404 - Data Conversion Inventory - Review | 24 hrs | 10 days | Mon 8/21/23 | Fri 9/1/23 | 217 | 219 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5671 | 219 | Future Task |  |  | WP404 | Manojkumar Gurjar | Approve | WPED WP404 - Data Conversion Inventory - Approve | 0 hrs | 0 days | Fri 9/1/23 | Fri 9/1/23 | 218 | 220FS+19 days |  | Jimmy Cox
5672 | 220 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WP404 - Create Data Conversion Inventory Template | 50 hrs | 32 days | Mon 10/2/23 | Wed 11/15/23 | 219FS+19 days,51 | 221 |  | Manojkumar Gurjar,Kurt Meisner
5673 | 221 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WP404 - Populate Data Conversion Inventory with RICEFW Inventory conversion items | 50 hrs | 16 days | Thu 11/16/23 | Mon 12/11/23 | 220 | 222 |  | Manojkumar Gurjar,Kurt Meisner
5674 | 222 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WP404 - Identify/confirm Anticipated Source Systems and Legacy Tables | 50 hrs | 20 days | Tue 12/12/23 | Wed 1/10/24 | 221 | 223 |  | Kurt Meisner,Manojkumar Gurjar
5675 | 223 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WP404 - Create Data Conversion Inventory Summary Document | 20 hrs | 5 days | Thu 1/11/24 | Thu 1/18/24 | 222 | 224 |  | Manojkumar Gurjar,Kurt Meisner
5676 | 224 | Future Task |  |  | WP404 | Manojkumar Gurjar | Submit | WP WP404 - Data Conversion Inventory - Submit | 0 hrs | 0 days | Thu 1/18/24 | Thu 1/18/24 | 223 | 225 |  | Manojkumar Gurjar,Joy Schneider
5677 | 225 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WP WP404 - Data Conversion Inventory - Collaborative Review & Update | 20 hrs | 10 days | Fri 1/19/24 | Thu 2/1/24 | 224 | 226 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5678 | 226 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WP WP404 - Data Conversion Inventory - Final Review & Edits | 20 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 225 | 227 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5679 | 227 | Future Task |  |  | WP404 | Manojkumar Gurjar | Approve | WP WP404 - Data Conversion Inventory - Approve | 0 hrs | 0 days | Thu 2/8/24 | Thu 2/8/24 | 226 |  | 2024-01-01 | Jimmy Cox
4458 | 228 | Future Task |  |  | WP405 | Stacey Terry |  | WP405 - Security Roles Matrix | 280 hrs | 115 days | Mon 2/19/24 | Tue 7/30/24
4459 | 229 | Future Task |  |  | WP405 | Stacey Terry | Create | WPED WP405 - Security Roles Matrix - Create | 16 hrs | 10 days | Mon 2/19/24 | Fri 3/1/24 | 1 | 230 |  | Stacey Terry,Mary Punty
4460 | 230 | Future Task |  |  | WP405 | Stacey Terry | Submit | WPED WP405 - Security Roles Matrix - Submit | 0 hrs | 0 days | Fri 3/1/24 | Fri 3/1/24 | 229 | 231 |  | Joy Schneider,Stacey Terry
4461 | 231 | Future Task |  |  | WP405 | Stacey Terry | Review | WPED WP405 - Security Roles Matrix - Review | 24 hrs | 10 days | Mon 3/4/24 | Fri 3/15/24 | 230 | 232 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4462 | 232 | Future Task |  |  | WP405 | Stacey Terry | Approve | WPED WP405 - Security Roles Matrix - Approve | 0 hrs | 0 days | Fri 3/15/24 | Fri 3/15/24 | 231 | 233FS+30 days |  | Jimmy Cox
4467 | 233 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Create Security Roles Matrix Template | 20 hrs | 5 days | Mon 4/29/24 | Fri 5/3/24 | 232FS+30 days | 234 |  | Stacey Terry,Yogesh Deshmukh
4468 | 234 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Design, Review, and Confirm Security Roles Matrix | 50 hrs | 20 days | Mon 5/6/24 | Mon 6/3/24 | 233 | 235 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4469 | 235 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Finalize Security Roles Matrix Design | 50 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 234 | 236 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4470 | 236 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Configure Security Roles and Permission Lists | 50 hrs | 15 days | Tue 6/11/24 | Mon 7/1/24 | 235 | 237 |  | Manojkumar Gurjar,Paul Jureidini
4471 | 237 | Future Task |  |  | WP405 | Stacey Terry | Create | WP405 - Create Security Roles Matrix Summary Document | 30 hrs | 5 days | Tue 7/2/24 | Tue 7/9/24 | 236 | 238 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4463 | 238 | Future Task |  |  | WP405 | Stacey Terry | Submit | WP WP405 - Security Roles Matrix - Submit | 0 hrs | 0 days | Tue 7/9/24 | Tue 7/9/24 | 237 | 239 |  | Joy Schneider,Stacey Terry
4464 | 239 | Future Task |  |  | WP405 | Stacey Terry | Review | WP WP405 - Security Roles Matrix - Collaborative Review & Update | 20 hrs | 10 days | Wed 7/10/24 | Tue 7/23/24 | 238 | 240 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4465 | 240 | Future Task |  |  | WP405 | Stacey Terry | Review | WP WP405 - Security Roles Matrix - Final Review & Edits | 20 hrs | 5 days | Wed 7/24/24 | Tue 7/30/24 | 239 | 241 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4466 | 241 | Future Task |  |  | WP405 | Stacey Terry | Approve | WP WP405 - Security Roles Matrix - Approve | 0 hrs | 0 days | Tue 7/30/24 | Tue 7/30/24 | 240 | 571 | 2024-07-01 | Jimmy Cox
5680 | 242 | Future Task | Maybe |  | WP411 | Manojkumar Gurjar |  | WP411 - Batch and Interface Procedures | 109 hrs | 114 days | Mon 9/30/24 | Fri 3/14/25
5681 | 243 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WPED WP411 - Batch and Interface Procedures - Create | 16 hrs | 10 days | Mon 9/30/24 | Fri 10/11/24 | 1 | 244 |  | Manojkumar Gurjar,Kurt Meisner
5682 | 244 | Future Task |  |  | WP411 | Manojkumar Gurjar | Submit | WPED WP411 - Batch and Interface Procedures - Submit | 0 hrs | 0 days | Fri 10/11/24 | Fri 10/11/24 | 243 | 245 |  | Manojkumar Gurjar,Joy Schneider
5683 | 245 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WPED WP411 - Batch and Interface Procedures - Review | 24 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 244 | 246 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5684 | 246 | Future Task |  |  | WP411 | Manojkumar Gurjar | Approve | WPED WP411 - Batch and Interface Procedures - Approve | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 245 | 247FS+22 days |  | Jimmy Cox
6701 | 247 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WP411 - Define Interface Procedures | 3 hrs | 28 days | Mon 12/2/24 | Fri 1/10/25 | 246FS+22 days | 248 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
6702 | 248 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WP411 - Create Batch Flow Diagram | 6 hrs | 9 days | Mon 1/13/25 | Fri 1/24/25 | 247 | 249 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
6703 | 249 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WP411 - Create Batch and Interface Procedures Document | 20 hrs | 20 days | Mon 1/27/25 | Fri 2/21/25 | 248 | 250 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
5685 | 250 | Future Task |  |  | WP411 | Manojkumar Gurjar | Submit | WP WP411 - Batch and Interface Procedures - Submit | 0 hrs | 0 days | Fri 2/21/25 | Fri 2/21/25 | 249 | 251 |  | Manojkumar Gurjar,Joy Schneider
5686 | 251 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WP WP411 - Batch and Interface Procedures - Collaborative Review & Update | 20 hrs | 10 days | Mon 2/24/25 | Fri 3/7/25 | 250 | 252 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5687 | 252 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WP WP411 - Batch and Interface Procedures - Final Review & Edits | 20 hrs | 5 days | Mon 3/10/25 | Fri 3/14/25 | 251 | 253 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5688 | 253 | Future Task |  |  | WP411 | Manojkumar Gurjar | Approve | WP WP411 - Batch and Interface Procedures - Approve | 0 hrs | 0 days | Fri 3/14/25 | Fri 3/14/25 | 252 |  |  | Jimmy Cox
6596 | 254 | Late |  |  | I-WP101 | Deana Metcalf |  | I-WP101 - Update Financials BPMs | 1,062 hrs | 299 days | Wed 4/26/23 | Mon 7/1/24
6597 | 255 | Complete |  |  | I-WP101 | Deana Metcalf | Create | Identify BPMs by module | 6 hrs | 3 days | Wed 4/26/23 | Fri 4/28/23 | 1 | 262263 |  | Deana Metcalf,Stacey Terry,Tiffany Porter,Janice Jackson,Brendan Jones
6598 | 256 | Late |  |  | I-WP101 | Deana Metcalf |  | WPED I-WP101 - Update Financials BPMs | 1,024 hrs | 274 days | Mon 5/1/23 | Thu 5/30/24
6599 | 257 | Complete |  |  | I-WP101 | Deana Metcalf | Create | WPED I-WP101 - Update Financials BPMs - Create | 3 hrs | 6 days | Mon 5/15/23 | Mon 5/22/23 | 1 | 258 |  | Deana Metcalf
6600 | 258 | Complete |  |  | I-WP101 | Deana Metcalf | Submit | WPED I-WP101 - Update Financials BPMs - Submit | 0 hrs | 0 days | Mon 5/22/23 | Mon 5/22/23 | 257 | 259 |  | Deana Metcalf
6601 | 259 | Late |  |  | I-WP101 | Deana Metcalf | Review | WPED I-WP101 - Update Financials BPMs - Collaborative Review & Update | 10 hrs | 9 days | Tue 5/23/23 | Mon 6/5/23 | 258 | 260 |  | Tiffany Porter,Janice Jackson,Brendan Jones,Angie Robertson,Jimmy Cox,Deana Metcalf | Finished 5/24/23 | TW
6602 | 260 | Future Task |  |  | I-WP101 | Deana Metcalf | Approve | WPED I-WP101 - Update Financials BPMs - Approve | 0 hrs | 0 days | Mon 6/5/23 | Mon 6/5/23 | 259 |  |  | Jimmy Cox | Successor U-6604 | TW
6603 | 261 | Late |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 1 - Financials Wave Business Process Models | 170 hrs | 86 days | Mon 5/1/23 | Wed 8/30/23 |  |  |  |  | Whese WPs would be same RW/Comms as the Segment Deliverables. | NK
6604 | 262 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - May | 20 hrs | 22 days | Mon 5/1/23 | Wed 5/31/23 | 255 | 264 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6605 | 263 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - May | 20 hrs | 22 days | Mon 5/1/23 | Wed 5/31/23 | 255 | 265 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6606 | 264 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - June | 20 hrs | 22 days | Thu 6/1/23 | Fri 6/30/23 | 262 | 266 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6607 | 265 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - June | 20 hrs | 22 days | Thu 6/1/23 | Fri 6/30/23 | 263 | 267 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6608 | 266 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - July | 20 hrs | 20 days | Mon 7/3/23 | Mon 7/31/23 | 264 | 268 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6609 | 267 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - July | 20 hrs | 20 days | Mon 7/3/23 | Mon 7/31/23 | 265 | 268 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6610 | 268 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 1 - Submit | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 266267 | 269274275276 |  | Deana Metcalf
6611 | 269 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 1 - Collaborative Review & Update | 20 hrs | 4 days | Tue 8/1/23 | Fri 8/4/23 | 268 | 270 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6789 | 270 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 1 - Advisory Council Review & Updates | 14 hrs | 12 days | Mon 8/7/23 | Tue 8/22/23 | 269 | 271 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson,Dusti Kincl
6612 | 271 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 1 - Style Guide Updates | 2 hrs | 1 day | Wed 8/23/23 | Wed 8/23/23 | 270 | 272 |  | Dusti Kincl
6613 | 272 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 1 - Final Review & Update | 14 hrs | 5 days | Thu 8/24/23 | Wed 8/30/23 | 271 | 327 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson,Jimmy Cox
6614 | 273 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 2 - Financials Wave Business Process Models | 270 hrs | 85 days | Tue 8/1/23 | Fri 12/1/23
6615 | 274 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - August | 20 hrs | 23 days | Tue 8/1/23 | Thu 8/31/23 | 268 | 277 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6616 | 275 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - August | 20 hrs | 23 days | Tue 8/1/23 | Thu 8/31/23 | 268 | 278 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6617 | 276 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - August | 20 hrs | 23 days | Tue 8/1/23 | Thu 8/31/23 | 268 | 279 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6618 | 277 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - September | 20 hrs | 20 days | Fri 9/1/23 | Fri 9/29/23 | 274 | 280283284 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6619 | 278 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - September | 20 hrs | 20 days | Fri 9/1/23 | Fri 9/29/23 | 275 | 281 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6620 | 279 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - September | 20 hrs | 20 days | Fri 9/1/23 | Fri 9/29/23 | 276 | 282 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6621 | 280 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - October | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 277 | 285 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6622 | 281 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - October | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 278 | 285 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6623 | 282 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - October | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 279 | 285 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6624 | 283 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment LMC models Impacted by Segment 2 | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 277 | 285 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6625 | 284 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment PPA models Impacted by Segment 2 | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 277 | 285 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6626 | 285 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 2 - Submit | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 280281282283284 | 286,291FS+2 days,292FS+2 days,293FS+2 days |  | Deana Metcalf
6627 | 286 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Collaborative Review & Update | 20 hrs | 5 days | Mon 10/30/23 | Fri 11/3/23 | 285 | 287 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6790 | 287 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Advisory Council Review & Updates | 14 hrs | 11 days | Mon 11/6/23 | Tue 11/21/23 | 286 | 288 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6628 | 288 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Style Guide Updates | 2 hrs | 1 day | Wed 11/22/23 | Wed 11/22/23 | 287 | 289 |  | Dusti Kincl
6629 | 289 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Final Review & Update | 14 hrs | 5 days | Mon 11/27/23 | Fri 12/1/23 | 288 | 327 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson,Jimmy Cox
6630 | 290 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 3 - Financials Wave Business Process Models | 296 hrs | 85 days | Wed 11/1/23 | Wed 3/6/24
6631 | 291 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - November | 20 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23 | 285FS+2 days | 294 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6632 | 292 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - November | 20 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23 | 285FS+2 days | 295 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6633 | 293 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - November | 20 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23 | 285FS+2 days | 296 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6634 | 294 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - December | 20 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23 | 291 | 297300 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6635 | 295 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - December | 20 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23 | 292 | 298301 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6636 | 296 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - December | 20 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23 | 293 | 299302 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6637 | 297 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - January | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 294 | 303 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6638 | 298 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - January | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 295 | 303 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6639 | 299 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - January | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 296 | 303 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6640 | 300 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior LMC segment models Impacted by Segment 3 | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 294 | 303 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6641 | 301 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior PPA segment models Impacted by Segment 3 | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 295 | 303 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6642 | 302 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior TRP segment models Impacted by Segment 3 | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 296 | 303 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6643 | 303 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 3 - Submit | 0 hrs | 0 days | Fri 1/26/24 | Fri 1/26/24 | 2.973e+17 | 304,309FS+3 days,310FS+3 days,311FS+3 days |  | Deana Metcalf
6644 | 304 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Collaborative Review & Update | 20 hrs | 5 days | Mon 1/29/24 | Fri 2/2/24 | 303 | 305 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6792 | 305 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Advisory Council Review & Updates | 20 hrs | 17 days | Mon 2/5/24 | Tue 2/27/24 | 304 | 306 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6645 | 306 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Style Guide Updates | 2 hrs | 1 day | Wed 2/28/24 | Wed 2/28/24 | 305 | 307 |  | Dusti Kincl
6646 | 307 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Final Review & Update | 14 hrs | 5 days | Thu 2/29/24 | Wed 3/6/24 | 306 | 327 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson,Jimmy Cox
6647 | 308 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 4 - Financials Wave Business Process Models | 275 hrs | 85 days | Thu 2/1/24 | Thu 5/30/24
6648 | 309 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - February | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 303FS+3 days | 312 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6649 | 310 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - February | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 303FS+3 days | 313 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6650 | 311 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - February | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 303FS+3 days | 314 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6651 | 312 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - March | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 309 | 315318 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6652 | 313 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - March | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 310 | 316319 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6653 | 314 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - March | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 311 | 317320 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6654 | 315 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - April | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 312 | 321 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6655 | 316 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - April | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 313 | 321 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6656 | 317 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - April | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 314 | 321 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6657 | 318 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior LMC segment models Impacted by Segment 4 | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 312 | 321 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6658 | 319 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior PPA segment models Impacted by Segment 4 | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 313 | 321 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6659 | 320 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior TRP segment models Impacted by Segment 4 | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 314 | 321 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6660 | 321 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 4 - Submit | 0 hrs | 0 days | Fri 4/26/24 | Fri 4/26/24 | 3.1532e+17 | 322 |  | Deana Metcalf
7203 | 322 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Advisory Council Review & Updates | 8 hrs | 5 days | Mon 4/29/24 | Fri 5/3/24 | 321 | 323 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6661 | 323 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Collaborative Review & Update | 10 hrs | 12 days | Mon 5/6/24 | Tue 5/21/24 | 322 | 324 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6662 | 324 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Style Guide Updates | 2 hrs | 1 day | Wed 5/22/24 | Wed 5/22/24 | 323 | 325 |  | Dusti Kincl
6663 | 325 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Final Review & Update | 15 hrs | 5 days | Thu 5/23/24 | Thu 5/30/24 | 324 | 327 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson,Jimmy Cox
6664 | 326 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 - Update Financials BPMs Review Tasks | 32 hrs | 22 days | Thu 5/30/24 | Mon 7/1/24
6665 | 327 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | WP I-WP101 - Update Financials BPMs - Submit | 0 hrs | 0 days | Thu 5/30/24 | Thu 5/30/24 | 272289307325 | 328 |  | Deana Metcalf
6666 | 328 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WP I-WP101 - Update Financials BPMs - Department QC | 2 hrs | 1 day | Fri 5/31/24 | Fri 5/31/24 | 327 | 329 |  | Gabriela Gibson
6667 | 329 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WP I-WP101 - Update Financials BPMs - Collaborative Review & Update | 20 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 328 | 330 |  | Deana Metcalf,Stacey Terry,Tiffany Porter,Janice Jackson,Brendan Jones
6668 | 330 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WP I-WP101 - Update Financials BPMs - Style Guide Review | 2 hrs | 1 day | Mon 6/17/24 | Mon 6/17/24 | 329 | 331 |  | Dusti Kincl
6669 | 331 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WP I-WP101 - Update Financials BPMs - Final Review & Update | 8 hrs | 10 days | Tue 6/18/24 | Mon 7/1/24 | 330 | 332 |  | Jimmy Cox,Angie Robertson
6670 | 332 | Future Task |  |  | I-WP101 | Deana Metcalf | Approve | WP I-WP101 - Update Financials BPMs - Approve | 0 hrs | 0 days | Mon 7/1/24 | Mon 7/1/24 | 331 |  |  | Jimmy Cox
6671 | 333 | Future Task |  |  | I-WP125 | Deana Metcalf |  | I-WP125 - Updated D66 Chart of Accounts Design | 214 hrs | 63 days | Mon 6/5/23 | Thu 8/31/23
6672 | 334 | Future Task |  |  | I-WP125 | Deana Metcalf | Create | WPED I-WP125 - Update D66 Chart of Accounts Design - Create | 2 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1 | 335 |  | Deana Metcalf
6673 | 335 | Future Task |  |  | I-WP125 | Deana Metcalf | Submit | WPED I-WP125 - Update D66 Chart of Accounts Design - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 334 | 336 |  | Deana Metcalf
6674 | 336 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WPED I-WP125 - Update D66 Chart of Accounts Design - Collaborative Review & Update | 8 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 335 | 337 |  | Janice Jackson,LaWanda Warren,Robert Hicks,Tommy Werner
6675 | 337 | Future Task |  |  | I-WP125 | Deana Metcalf | Approve | WPED I-WP125 - Update D66 Chart of Accounts Design - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 336 | 338 |  | Angie Robertson,Jimmy Cox
6676 | 338 | Future Task |  |  | I-WP125 | Deana Metcalf | Create | I-WP125 Update D66 Chart of Accounts Design <Activities per WPED> | 100 hrs | 26 days | Mon 7/3/23 | Tue 8/8/23 | 337 | 339 |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp
6677 | 339 | Future Task |  |  | I-WP125 | Deana Metcalf | Submit | WP I-WP125 - Update D66 Chart of Accounts Design - Submit | 0 hrs | 0 days | Tue 8/8/23 | Tue 8/8/23 | 338 | 340 |  | Janice Jackson
6678 | 340 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WP I-WP125 - Update D66 Chart of Accounts Design - Department QC | 1 hr | 1 day | Wed 8/9/23 | Wed 8/9/23 | 339 | 341 |  | Gabriela Gibson
6679 | 341 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WP I-WP125 - Update D66 Chart of Accounts Design - Collaborative Review & Update | 100 hrs | 10 days | Thu 8/10/23 | Wed 8/23/23 | 340 | 342 |  | Deana Metcalf,Janice Jackson,Jennifer Reeves,Angie Robertson
6680 | 342 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WP I-WP125 - Update D66 Chart of Accounts Design - Style Guide Review | 1 hr | 1 day | Thu 8/24/23 | Thu 8/24/23 | 341 | 343 |  | Tatiana Eubanks
6681 | 343 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WP I-WP125 - Update D66 Chart of Accounts Design - Final Review & Update | 2 hrs | 5 days | Fri 8/25/23 | Thu 8/31/23 | 342 | 344 |  | Angie Robertson,Jimmy Cox | RW/Comms | NK
6682 | 344 | Future Task |  |  | I-WP125 | Deana Metcalf | Approve | WP I-WP125 - Update D66 Chart of Accounts Design - Approve | 0 hrs | 0 days | Thu 8/31/23 | Thu 8/31/23 | 343 |  |  | Jimmy Cox
3770 | 345 | Future Task | [5 empty] | Build | 2,496 hrs | 618 days | Mon 7/10/23 | Fri 12/19/25
5534 | 346 | Future Task | Maybe |  | D642 | Jarad Hermann |  | D642 - Updated Technical Architecture Design | 169 hrs | 98 days | Tue 9/5/23 | Fri 1/26/24
5535 | 347 | Future Task |  |  | D642 | Jarad Hermann | Create | DED D642 - Updated Technical Architecture Design - Create | 8 hrs | 10 days | Tue 9/5/23 | Mon 9/18/23 | 1FS+91 days | 348 |  | Jarad Hermann,Manojkumar Gurjar
5536 | 348 | Future Task |  |  | D642 | Jarad Hermann | Submit | DED D642 - Updated Technical Architecture Design - Submit | 0 hrs | 0 days | Mon 9/18/23 | Mon 9/18/23 | 347 | 349 |  | Jarad Hermann,Joy Schneider
5537 | 349 | Future Task |  |  | D642 | Jarad Hermann | Review | DED D642 - Updated Technical Architecture Design - Collaborative Review | 24 hrs | 10 days | Tue 9/19/23 | Mon 10/2/23 | 348 | 350 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5538 | 350 | Future Task |  |  | D642 | Jarad Hermann | Approve | DED D642 - Updated Technical Architecture Design - Approve | 0 hrs | 0 days | Mon 10/2/23 | Mon 10/2/23 | 349 | 351FS+21 days |  | Jimmy Cox
5539 | 351 | Future Task |  |  | D642 | Jarad Hermann | Create | D642 - Confirm content to be migrated from D80 | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 350FS+21 days | 352SS,353SS,354SS |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5540 | 352 | Future Task |  |  | D642 | Jarad Hermann | Create | D642 - Review, update, & document run time architecture design | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 351SS | 355 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5541 | 353 | Future Task |  |  | D642 | Jarad Hermann | Create | D642 - Review, update, and document development and operational architecture design | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 351SS | 355 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5542 | 354 | Future Task |  |  | D642 | Jarad Hermann | Create | D642 - Review, update, and document architecture blueprint diagrams | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 351SS | 355 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5543 | 355 | Future Task |  |  | D642 | Jarad Hermann | Submit | DEL D642 - Updated Technical Architecture Design - Draft Submission | 0 hrs | 0 days | Tue 1/2/24 | Tue 1/2/24 | 354352353 | 356 |  | Jarad Hermann,Joy Schneider
5544 | 356 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Pre-Submission Collaborative Review | 20 hrs | 5 days | Wed 1/3/24 | Tue 1/9/24 | 355 | 357 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
5545 | 357 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Style Guide Review | 1 hr | 1 day | Wed 1/10/24 | Wed 1/10/24 | 356 | 358 |  | Dusti Kincl
5546 | 358 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Final Collaborative Review | 20 hrs | 5 days | Thu 1/11/24 | Thu 1/18/24 | 357 | 359 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
5547 | 359 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Accenture QC | 4 hrs | 2 days | Fri 1/19/24 | Mon 1/22/24 | 358 | 360 |  | Joy Schneider
5548 | 360 | Future Task |  |  | D642 | Jarad Hermann | Submit | DEL D642 - Updated Technical Architecture Design - Submit | 0 hrs | 0 days | Mon 1/22/24 | Mon 1/22/24 | 359 | 361 |  | Joy Schneider
5549 | 361 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Department QC | 4 hrs | 1 day | Tue 1/23/24 | Tue 1/23/24 | 360 | 362 |  | Tommy Werner,Gabriela Gibson
5550 | 362 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Contract Manager Review | 8 hrs | 3 days | Wed 1/24/24 | Fri 1/26/24 | 361 | 363 |  | Sean Buchanan
5551 | 363 | Future Task |  |  | D642 | Jarad Hermann | Accept | DEL D642 - Updated Technical Architecture Design - Accept | 0 hrs | 0 days | Fri 1/26/24 | Fri 1/26/24 | 362 |  | 2024-03-01 | Sean Buchanan
4486 | 364 | Future Task | Maybe |  | D646 | Manojkumar Gurjar |  | D646 - Completion of Build Segment I | 257 hrs | 156 days | Mon 9/18/23 | Tue 4/30/24
4487 | 365 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | DED D646 - Completion of Build Segment I - Create | 16 hrs | 10 days | Mon 9/18/23 | Fri 9/29/23 | 199 | 366 |  | Manojkumar Gurjar,Kurt Meisner
4488 | 366 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DED D646 - Completion of Build Segment I - Submit | 0 hrs | 0 days | Fri 9/29/23 | Fri 9/29/23 | 365 | 367 |  | Manojkumar Gurjar,Joy Schneider
4489 | 367 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DED D646 - Completion of Build Segment I - Collaborative Review | 24 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 366 | 368 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4490 | 368 | Future Task |  |  | D646 | Manojkumar Gurjar | Approve | DED D646 - Completion of Build Segment I - Approve | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 367 | 369FS+19 days |  | Jimmy Cox
4500 | 369 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Identify RICEFW items for Build Segment I | 20 hrs | 8 days | Mon 11/13/23 | Wed 11/22/23 | 368FS+19 days | 370 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4501 | 370 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Create Work Unit Tracker for Build Segment I | 20 hrs | 5 days | Mon 11/27/23 | Fri 12/1/23 | 369 | 371 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4502 | 371 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Review, Update and Confirm Work Unit Tracker for Build Segment I | 20 hrs | 10 days | Mon 12/4/23 | Fri 12/15/23 | 370 | 372 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4503 | 372 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Conduct Kick-Off meeting for Build Segment I | 20 hrs | 9 days | Mon 12/18/23 | Fri 12/29/23 | 371 | 373 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4504 | 373 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Build and Unit Test RICEFW for Build Segment I - Group 1 | 20 hrs | 21 days | Tue 1/2/24 | Wed 1/31/24 | 372 | 374 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4505 | 374 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Build and Unit Test RICEFW for Build Segment I - Group 2 | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 373 | 375 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4506 | 375 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Build and Unit Test RICEFW for Build Segment I - Group 3 | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 374 | 376FS-5 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4507 | 376 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | D646 - Create Summary Document for Build Segment I | 20 hrs | 10 days | Mon 3/25/24 | Fri 4/5/24 | 375FS-5 days | 377 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4491 | 377 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DEL D646 - Completion of Build Segment I - Draft Submission | 0 hrs | 0 days | Fri 4/5/24 | Fri 4/5/24 | 376 | 378 |  | Manojkumar Gurjar,Joy Schneider
4492 | 378 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 4/8/24 | Fri 4/12/24 | 377 | 379 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4493 | 379 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Style Guide Review | 1 hr | 1 day | Mon 4/15/24 | Mon 4/15/24 | 378 | 380 |  | Dusti Kincl
4494 | 380 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Final Collaborative Review | 20 hrs | 5 days | Tue 4/16/24 | Mon 4/22/24 | 379 | 381 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4495 | 381 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Accenture QC | 4 hrs | 2 days | Tue 4/23/24 | Wed 4/24/24 | 380 | 382 |  | Joy Schneider
4496 | 382 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DEL D646 - Completion of Build Segment I - Submit | 0 hrs | 0 days | Wed 4/24/24 | Wed 4/24/24 | 381 | 383 |  | Joy Schneider
4497 | 383 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Department QC | 4 hrs | 1 day | Thu 4/25/24 | Thu 4/25/24 | 382 | 384 |  | Tommy Werner,Gabriela Gibson
4498 | 384 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Contract Manager Review | 8 hrs | 3 days | Fri 4/26/24 | Tue 4/30/24 | 383 | 385 |  | Sean Buchanan
4499 | 385 | Future Task |  |  | D646 | Manojkumar Gurjar | Accept | DEL D646 - Completion of Build Segment I - Accept | 0 hrs | 0 days | Tue 4/30/24 | Tue 4/30/24 | 384 | 581587 | 2024-04-01 | Sean Buchanan
4629 | 386 | Future Task | Maybe |  | D647 | Manojkumar Gurjar |  | D647 - Establish DW/BI Environments | 149 hrs | 116 days | Mon 11/6/23 | Tue 4/23/24
4630 | 387 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | DED D647 - Establish DW/BI Environments - Create | 8 hrs | 10 days | Mon 11/6/23 | Mon 11/20/23 | 1 | 388 |  | Jarad Hermann,Manojkumar Gurjar
4631 | 388 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DED D647 - Establish DW/BI Environments - Submit | 0 hrs | 0 days | Mon 11/20/23 | Mon 11/20/23 | 387 | 389 |  | Manojkumar Gurjar,Joy Schneider
4632 | 389 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DED D647 - Establish DW/BI Environments - Collaborative Review | 24 hrs | 10 days | Tue 11/21/23 | Wed 12/6/23 | 388 | 390 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4633 | 390 | Future Task |  |  | D647 | Manojkumar Gurjar | Approve | DED D647 - Establish DW/BI Environments - Approve | 0 hrs | 0 days | Wed 12/6/23 | Wed 12/6/23 | 389 | 391FS+20 days |  | Jimmy Cox
4643 | 391 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | D647 - Establish DW/BI Environment Connections | 20 hrs | 19 days | Mon 1/8/24 | Fri 2/2/24 | 390FS+20 days | 392 |  | Jarad Hermann,Manojkumar Gurjar
4644 | 392 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | D647 - Environment build and stand up | 20 hrs | 20 days | Mon 2/5/24 | Fri 3/1/24 | 391 | 393 |  | Jarad Hermann,Manojkumar Gurjar
4645 | 393 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | D647 - Verify access to DW/BI Environments | 20 hrs | 20 days | Mon 3/4/24 | Fri 3/29/24 | 392 | 394 |  | Jarad Hermann,Manojkumar Gurjar
4634 | 394 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DEL D647 - Establish DW/BI Environments - Draft Submission | 0 hrs | 0 days | Fri 3/29/24 | Fri 3/29/24 | 393 | 395 |  | Manojkumar Gurjar,Joy Schneider
4635 | 395 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 4/1/24 | Fri 4/5/24 | 394 | 396 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
4636 | 396 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Style Guide Review | 1 hr | 1 day | Mon 4/8/24 | Mon 4/8/24 | 395 | 397 |  | Dusti Kincl
4637 | 397 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Final Collaborative Review | 20 hrs | 5 days | Tue 4/9/24 | Mon 4/15/24 | 396 | 398 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
4638 | 398 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Accenture QC | 4 hrs | 2 days | Tue 4/16/24 | Wed 4/17/24 | 397 | 399 |  | Joy Schneider
4639 | 399 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DEL D647 - Establish DW/BI Environments - Submit | 0 hrs | 0 days | Wed 4/17/24 | Wed 4/17/24 | 398 | 400 |  | Joy Schneider
4640 | 400 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Department QC | 4 hrs | 1 day | Thu 4/18/24 | Thu 4/18/24 | 399 | 401 |  | Tommy Werner,Gabriela Gibson
4641 | 401 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Contract Manager Review | 8 hrs | 3 days | Fri 4/19/24 | Tue 4/23/24 | 400 | 402 |  | Sean Buchanan
4642 | 402 | Future Task |  |  | D647 | Manojkumar Gurjar | Accept | DEL D647 - Establish DW/BI Environments - Accept | 0 hrs | 0 days | Tue 4/23/24 | Tue 4/23/24 | 401 |  | 2024-05-01 | Sean Buchanan
4508 | 403 | Future Task | Maybe |  | D648 | Manojkumar Gurjar |  | D648 - Completion of Build Segment II | 197 hrs | 110 days | Mon 2/12/24 | Tue 7/16/24
4509 | 404 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | DED D648 - Completion of Build Segment II - Create | 16 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 199 | 405 |  | Manojkumar Gurjar,Kurt Meisner
4510 | 405 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DED D648 - Completion of Build Segment II - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 404 | 406 |  | Manojkumar Gurjar,Joy Schneider
4511 | 406 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DED D648 - Completion of Build Segment II - Collaborative Review | 24 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 405 | 407 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4512 | 407 | Future Task |  |  | D648 | Manojkumar Gurjar | Approve | DED D648 - Completion of Build Segment II - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 406 | 408FS+20 days |  | Jimmy Cox
4536 | 408 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Create Work Unit Tracker for Build Segment II | 20 hrs | 7 days | Mon 4/8/24 | Tue 4/16/24 | 407FS+20 days | 409 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4537 | 409 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Review, Update and Confirm Work Unit Tracker for Build Segment II | 20 hrs | 8 days | Wed 4/17/24 | Fri 4/26/24 | 408 | 410 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4538 | 410 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Build and Unit Test RICEFW for Build Segment II - Group 1 | 20 hrs | 19 days | Mon 4/29/24 | Thu 5/23/24 | 409 | 411 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4539 | 411 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Build and Unit Test RICEFW for Build Segment II - Group 2 | 20 hrs | 19 days | Fri 5/24/24 | Thu 6/20/24 | 410 | 412FS-9 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4540 | 412 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | D648 - Create Summary Document for Build Segment II | 20 hrs | 9 days | Mon 6/10/24 | Thu 6/20/24 | 411FS-9 days | 413 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4513 | 413 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DEL D648 - Completion of Build Segment II - Draft Submission | 0 hrs | 0 days | Thu 6/20/24 | Thu 6/20/24 | 412 | 414 |  | Manojkumar Gurjar,Joy Schneider
4514 | 414 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 6/21/24 | Thu 6/27/24 | 413 | 415 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4515 | 415 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Style Guide Review | 1 hr | 1 day | Fri 6/28/24 | Fri 6/28/24 | 414 | 416 |  | Dusti Kincl
4516 | 416 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Final Collaborative Review | 20 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 415 | 417 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4517 | 417 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Accenture QC | 4 hrs | 2 days | Tue 7/9/24 | Wed 7/10/24 | 416 | 418 |  | Joy Schneider
4518 | 418 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DEL D648 - Completion of Build Segment II - Submit | 0 hrs | 0 days | Wed 7/10/24 | Wed 7/10/24 | 417 | 419 |  | Joy Schneider
4519 | 419 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Department QC | 4 hrs | 1 day | Thu 7/11/24 | Thu 7/11/24 | 418 | 420 |  | Tommy Werner,Gabriela Gibson
4520 | 420 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Contract Manager Review | 8 hrs | 3 days | Fri 7/12/24 | Tue 7/16/24 | 419 | 421 |  | Sean Buchanan
4521 | 421 | Future Task |  |  | D648 | Manojkumar Gurjar | Accept | DEL D648 - Completion of Build Segment II - Accept | 0 hrs | 0 days | Tue 7/16/24 | Tue 7/16/24 | 420 | 587 | 2024-07-01 | Sean Buchanan
4522 | 422 | Future Task | Maybe |  | D649 | Manojkumar Gurjar |  | D649 - Completion of Build Segment III | 217 hrs | 124 days | Mon 5/6/24 | Tue 10/29/24
4523 | 423 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | DED D649 - Completion of Build Segment III - Create | 16 hrs | 10 days | Mon 5/6/24 | Fri 5/17/24 | 199 | 424 |  | Manojkumar Gurjar,Kurt Meisner
4524 | 424 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DED D649 - Completion of Build Segment III - Submit | 0 hrs | 0 days | Fri 5/17/24 | Fri 5/17/24 | 423 | 425 |  | Manojkumar Gurjar,Joy Schneider
4525 | 425 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DED D649 - Completion of Build Segment III - Collaborative Review | 24 hrs | 10 days | Mon 5/20/24 | Mon 6/3/24 | 424 | 426 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4526 | 426 | Future Task |  |  | D649 | Manojkumar Gurjar | Approve | DED D649 - Completion of Build Segment III - Approve | 0 hrs | 0 days | Mon 6/3/24 | Mon 6/3/24 | 425 | 427FS+23 days |  | Jimmy Cox
4541 | 427 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Identify RICEFW items for Build Segment III | 20 hrs | 10 days | Mon 7/8/24 | Fri 7/19/24 | 426FS+23 days | 428 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4542 | 428 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Create Work Unit Tracker for Build Segment III | 20 hrs | 5 days | Mon 7/22/24 | Fri 7/26/24 | 427 | 429 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4543 | 429 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Review, Update and Confirm Work Unit Tracker for Build Segment III | 20 hrs | 10 days | Mon 7/29/24 | Fri 8/9/24 | 428 | 430 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4544 | 430 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Build and Unit Test RICEFW for Build Segment III - Group 1 | 20 hrs | 19 days | Mon 8/12/24 | Fri 9/6/24 | 429 | 431 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4545 | 431 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Build and Unit Test RICEFW for Build Segment III - Group 2 | 20 hrs | 20 days | Mon 9/9/24 | Fri 10/4/24 | 430 | 432FS-10 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4546 | 432 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | D649 - Create Summary Document for Build Segment III | 20 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 431FS-10 days | 433 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4527 | 433 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DEL D649 - Completion of Build Segment III - Draft Submission | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 432 | 434 |  | Manojkumar Gurjar,Joy Schneider
4528 | 434 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 | 433 | 435 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4529 | 435 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Style Guide Review | 1 hr | 1 day | Mon 10/14/24 | Mon 10/14/24 | 434 | 436 |  | Dusti Kincl
4530 | 436 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Final Collaborative Review | 20 hrs | 5 days | Tue 10/15/24 | Mon 10/21/24 | 435 | 437 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4531 | 437 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Accenture QC | 4 hrs | 2 days | Tue 10/22/24 | Wed 10/23/24 | 436 | 438 |  | Joy Schneider
4532 | 438 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DEL D649 - Completion of Build Segment III - Submit | 0 hrs | 0 days | Wed 10/23/24 | Wed 10/23/24 | 437 | 439 |  | Joy Schneider
4533 | 439 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Department QC | 4 hrs | 1 day | Thu 10/24/24 | Thu 10/24/24 | 438 | 440 |  | Tommy Werner,Gabriela Gibson
4534 | 440 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Contract Manager Review | 8 hrs | 3 days | Fri 10/25/24 | Tue 10/29/24 | 439 | 441 |  | Sean Buchanan
4535 | 441 | Future Task |  |  | D649 | Manojkumar Gurjar | Accept | DEL D649 - Completion of Build Segment III - Accept | 0 hrs | 0 days | Tue 10/29/24 | Tue 10/29/24 | 440 | 587 | 2024-10-01 | Sean Buchanan
4547 | 442 | Future Task | Maybe |  | D653 | Manojkumar Gurjar |  | D653 - Completion of Build Segment I DW/BI | 297 hrs | 147 days | Mon 6/3/24 | Thu 1/2/25
4548 | 443 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | DED D653 - Completion of Build Segment I DW/BI - Create | 16 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 1 | 444 |  | Manojkumar Gurjar,Kurt Meisner
4549 | 444 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DED D653 - Completion of Build Segment I DW/BI - Submit | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 443 | 445 |  | Manojkumar Gurjar,Joy Schneider
4550 | 445 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DED D653 - Completion of Build Segment I DW/BI - Collaborative Review | 24 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 444 | 446 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4551 | 446 | Future Task |  |  | D653 | Manojkumar Gurjar | Approve | DED D653 - Completion of Build Segment I DW/BI - Approve | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 445 | 447 |  | Jimmy Cox
4575 | 447 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Identify RICEFW items for Build Segment I DW/BI | 36 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 446 | 448 |  | Manojkumar Gurjar,Kurt Meisner
4576 | 448 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Create Work Unit Tracker for Build Segment I DW/BI | 20 hrs | 5 days | Mon 7/15/24 | Fri 7/19/24 | 447 | 449 |  | Manojkumar Gurjar,Kurt Meisner
4577 | 449 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Review, Update and Confirm Work Unit Tracker for Build Segment I DW/BI | 40 hrs | 10 days | Mon 7/22/24 | Fri 8/2/24 | 448 | 450 |  | Manojkumar Gurjar,Kurt Meisner
4578 | 450 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Conduct Kick-Off meeting for Build Segment I DW/BI | 40 hrs | 5 days | Mon 8/5/24 | Fri 8/9/24 | 449 | 451 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4579 | 451 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Build and Unit Test RICEFW for Build Segment I DW/BI - Group 1 | 20 hrs | 19 days | Mon 8/12/24 | Fri 9/6/24 | 450 | 452 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4580 | 452 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Build and Unit Test RICEFW for Build Segment I DW/BI - Group 2 | 20 hrs | 20 days | Mon 9/9/24 | Fri 10/4/24 | 451 | 453 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4581 | 453 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Build and Unit Test RICEFW for Build Segment I DW/BI - Group 3 | 20 hrs | 20 days | Mon 10/7/24 | Fri 11/1/24 | 452 | 454 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4582 | 454 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | D653 - Create Summary Document for Build Segment I DW/BI | 4 hrs | 22 days | Mon 11/4/24 | Fri 12/6/24 | 453 | 455 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4552 | 455 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DEL D653 - Completion of Build Segment I DW/BI - Draft Submission | 0 hrs | 0 days | Fri 12/6/24 | Fri 12/6/24 | 454 | 456 |  | Manojkumar Gurjar,Joy Schneider
4553 | 456 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 12/9/24 | Fri 12/13/24 | 455 | 457 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4554 | 457 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Style Guide Review | 1 hr | 1 day | Mon 12/16/24 | Mon 12/16/24 | 456 | 458 |  | Dusti Kincl
4555 | 458 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Final Collaborative Review | 20 hrs | 5 days | Tue 12/17/24 | Mon 12/23/24 | 457 | 459 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4556 | 459 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Accenture QC | 4 hrs | 2 days | Tue 12/24/24 | Thu 12/26/24 | 458 | 460 | Holiday | Joy Schneider
4557 | 460 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DEL D653 - Completion of Build Segment I DW/BI - Submit | 0 hrs | 0 days | Thu 12/26/24 | Thu 12/26/24 | 459 | 461 |  | Joy Schneider
4558 | 461 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Department QC | 4 hrs | 1 day | Fri 12/27/24 | Fri 12/27/24 | 460 | 462 |  | Tommy Werner,Gabriela Gibson
4559 | 462 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Contract Manager Review | 8 hrs | 3 days | Mon 12/30/24 | Thu 1/2/25 | 461 | 463 |  | Sean Buchanan
4560 | 463 | Future Task |  |  | D653 | Manojkumar Gurjar | Accept | DEL D653 - Completion of Build Segment I DW/BI - Accept | 0 hrs | 0 days | Thu 1/2/25 | Thu 1/2/25 | 462 | 587 | 2025-01-01 | Sean Buchanan
4561 | 464 | Future Task | Maybe |  | D654 | Manojkumar Gurjar |  | D654 - Completion of Build Segment IV | 217 hrs | 122 days | Mon 8/5/24 | Thu 1/30/25
4562 | 465 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | DED D654 - Completion of Build Segment IV - Create | 16 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 1 | 466 |  | Manojkumar Gurjar,Kurt Meisner
4563 | 466 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DED D654 - Completion of Build Segment IV - Submit | 0 hrs | 0 days | Fri 8/16/24 | Fri 8/16/24 | 465 | 467 |  | Manojkumar Gurjar,Joy Schneider
4564 | 467 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DED D654 - Completion of Build Segment IV - Collaborative Review | 24 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 466 | 468 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4565 | 468 | Future Task |  |  | D654 | Manojkumar Gurjar | Approve | DED D654 - Completion of Build Segment IV - Approve | 0 hrs | 0 days | Fri 8/30/24 | Fri 8/30/24 | 467 | 469FS+24 days |  | Jimmy Cox
4583 | 469 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Identify RICEFW items for Build Segment IV | 20 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 468FS+24 days | 470 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4584 | 470 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Create Work Unit Tracker for Build Segment IV | 20 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 469 | 471 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4585 | 471 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Review, Update and Confirm Work Unit Tracker for Build Segment IV | 20 hrs | 10 days | Mon 10/28/24 | Fri 11/8/24 | 470 | 472 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4586 | 472 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Build and Unit Test RICEFW for Build Segment IV - Group 1 | 20 hrs | 17 days | Tue 11/12/24 | Fri 12/6/24 | 471 | 473 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4587 | 473 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Build and Unit Test RICEFW for Build Segment IV - Group 2 | 20 hrs | 19 days | Mon 12/9/24 | Mon 1/6/25 | 472 | 474FS-14 days,475 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4588 | 474 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | D654 - Create Summary Document for Build Segment IV | 20 hrs | 13 days | Mon 12/16/24 | Fri 1/3/25 | 473FS-14 days | 475 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4566 | 475 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DEL D654 - Completion of Build Segment IV - Draft Submission | 0 hrs | 0 days | Mon 1/6/25 | Mon 1/6/25 | 473474 | 476 |  | Manojkumar Gurjar,Joy Schneider
4567 | 476 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 1/7/25 | Mon 1/13/25 | 475 | 477 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4568 | 477 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Style Guide Review | 1 hr | 1 day | Tue 1/14/25 | Tue 1/14/25 | 476 | 478 |  | Dusti Kincl
4569 | 478 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Final Collaborative Review | 20 hrs | 5 days | Wed 1/15/25 | Wed 1/22/25 | 477 | 479 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4570 | 479 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Accenture QC | 4 hrs | 2 days | Thu 1/23/25 | Fri 1/24/25 | 478 | 480 |  | Joy Schneider
4571 | 480 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DEL D654 - Completion of Build Segment IV - Submit | 0 hrs | 0 days | Fri 1/24/25 | Fri 1/24/25 | 479 | 481 |  | Joy Schneider
4572 | 481 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Department QC | 4 hrs | 1 day | Mon 1/27/25 | Mon 1/27/25 | 480 | 482 |  | Tommy Werner,Gabriela Gibson
4573 | 482 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Contract Manager Review | 8 hrs | 3 days | Tue 1/28/25 | Thu 1/30/25 | 481 | 483 |  | Sean Buchanan
4574 | 483 | Future Task |  |  | D654 | Manojkumar Gurjar | Accept | DEL D654 - Completion of Build Segment IV - Accept | 0 hrs | 0 days | Thu 1/30/25 | Thu 1/30/25 | 482 | 587 | 2025-01-01 | Sean Buchanan
4589 | 484 | Future Task | Maybe |  | D659 | Manojkumar Gurjar |  | D659 - Completion of Build Segment II DW/BI | 219 hrs | 116 days | Mon 9/9/24 | Tue 2/25/25
4590 | 485 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | DED D659 - Completion of Build Segment II DW/BI - Create | 16 hrs | 10 days | Mon 9/9/24 | Fri 9/20/24 | 1 | 486 |  | Manojkumar Gurjar,Kurt Meisner
4591 | 486 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DED D659 - Completion of Build Segment II DW/BI - Submit | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 485 | 487 |  | Manojkumar Gurjar,Joy Schneider
4592 | 487 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DED D659 - Completion of Build Segment II DW/BI - Collaborative Review | 24 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 486 | 488 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4593 | 488 | Future Task |  |  | D659 | Manojkumar Gurjar | Approve | DED D659 - Completion of Build Segment II DW/BI - Approve | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 487 | 489 |  | Jimmy Cox
4603 | 489 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Identify RICEFW items for Build Segment II DW/BI | 40 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 488 | 490 |  | Manojkumar Gurjar,Kurt Meisner
4604 | 490 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Create Work Unit Tracker for Build Segment II DW/BI | 20 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 489 | 491 |  | Manojkumar Gurjar,Kurt Meisner
4605 | 491 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Review, Update and Confirm Work Unit Tracker for Build Segment II DW/BI | 20 hrs | 5 days | Mon 10/28/24 | Fri 11/1/24 | 490 | 492 |  | Manojkumar Gurjar,Kurt Meisner
4606 | 492 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Build and Unit Test RICEFW for Build Segment II DW/BI - Group 1 | 20 hrs | 17 days | Mon 11/4/24 | Wed 11/27/24 | 491 | 493 |  | Manojkumar Gurjar,Kurt Meisner
4607 | 493 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Build and Unit Test RICEFW for Build Segment II DW/BI - Group 2 | 2 hrs | 23 days | Mon 12/2/24 | Fri 1/3/25 | 492 | 494 |  | Manojkumar Gurjar,Kurt Meisner
4608 | 494 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | D659 - Create Summary Document for Build Segment II DW/BI | 20 hrs | 19 days | Mon 1/6/25 | Fri 1/31/25 | 493 | 495 |  | Manojkumar Gurjar,Kurt Meisner
4594 | 495 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DEL D659 - Completion of Build Segment II DW/BI - Draft Submission | 0 hrs | 0 days | Fri 1/31/25 | Fri 1/31/25 | 494 | 496 |  | Manojkumar Gurjar,Joy Schneider
4595 | 496 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 2/3/25 | Fri 2/7/25 | 495 | 497 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4596 | 497 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Style Guide Review | 1 hr | 1 day | Mon 2/10/25 | Mon 2/10/25 | 496 | 498 |  | Dusti Kincl
4597 | 498 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Final Collaborative Review | 20 hrs | 5 days | Tue 2/11/25 | Mon 2/17/25 | 497 | 499 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4598 | 499 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Accenture QC | 4 hrs | 2 days | Tue 2/18/25 | Wed 2/19/25 | 498 | 500 |  | Joy Schneider
4599 | 500 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DEL D659 - Completion of Build Segment II DW/BI - Submit | 0 hrs | 0 days | Wed 2/19/25 | Wed 2/19/25 | 499 | 501 |  | Joy Schneider
4600 | 501 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Department QC | 4 hrs | 1 day | Thu 2/20/25 | Thu 2/20/25 | 500 | 502 |  | Tommy Werner,Gabriela Gibson
4601 | 502 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Contract Manager Review | 8 hrs | 3 days | Fri 2/21/25 | Tue 2/25/25 | 501 | 503 |  | Sean Buchanan
4602 | 503 | Future Task |  |  | D659 | Manojkumar Gurjar | Accept | DEL D659 - Completion of Build Segment II DW/BI - Accept | 0 hrs | 0 days | Tue 2/25/25 | Tue 2/25/25 | 502 | 587 | 2025-04-01 | Sean Buchanan
4609 | 504 | Future Task | Maybe |  | D668 | Manojkumar Gurjar |  | D668 - Completion of Build Segment III DW/BI | 281 hrs | 93 days | Wed 10/30/24 | Mon 3/17/25
4610 | 505 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | DED D668 - Completion of Build Segment III DW/BI - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1 | 506 |  | Manojkumar Gurjar,Kurt Meisner
4611 | 506 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DED D668 - Completion of Build Segment III DW/BI - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 505 | 507 |  | Manojkumar Gurjar,Joy Schneider
4612 | 507 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DED D668 - Completion of Build Segment III DW/BI - Collaborative Review | 24 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 506 | 508 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4613 | 508 | Future Task |  |  | D668 | Manojkumar Gurjar | Approve | DED D668 - Completion of Build Segment III DW/BI - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 507 | 509 |  | Jimmy Cox
4623 | 509 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Identify RICEFW items for Build Segment III DW/BI | 40 hrs | 5 days | Mon 12/2/24 | Fri 12/6/24 | 508 | 510SS+2 days |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4624 | 510 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Create Work Unit Tracker for Build Segment III DW/BI | 40 hrs | 5 days | Wed 12/4/24 | Tue 12/10/24 | 509SS+2 days | 511 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4625 | 511 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Review, Update and Confirm Work Unit Tracker for Build Segment III DW/BI | 24 hrs | 3 days | Wed 12/11/24 | Fri 12/13/24 | 510 | 512 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4626 | 512 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Build and Unit Test RICEFW for Build Segment III DW/BI - Group 1 | 20 hrs | 18 days | Mon 12/16/24 | Fri 1/10/25 | 511 | 513 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4627 | 513 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Build and Unit Test RICEFW for Build Segment III DW/BI - Group 2 | 20 hrs | 18 days | Mon 1/13/25 | Thu 2/6/25 | 512 | 514 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4628 | 514 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | D668 - Create Summary Document for Build Segment III DW/BI | 40 hrs | 10 days | Fri 2/7/25 | Thu 2/20/25 | 513 | 515 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4614 | 515 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DEL D668 - Completion of Build Segment III DW/BI - Draft Submission | 0 hrs | 0 days | Thu 2/20/25 | Thu 2/20/25 | 514 | 516 |  | Manojkumar Gurjar,Joy Schneider
4615 | 516 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 2/21/25 | Thu 2/27/25 | 515 | 517 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4616 | 517 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Style Guide Review | 1 hr | 1 day | Fri 2/28/25 | Fri 2/28/25 | 516 | 518 |  | Dusti Kincl
4617 | 518 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Final Collaborative Review | 20 hrs | 5 days | Mon 3/3/25 | Fri 3/7/25 | 517 | 519 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4618 | 519 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Accenture QC | 4 hrs | 2 days | Mon 3/10/25 | Tue 3/11/25 | 518 | 520 |  | Joy Schneider
4619 | 520 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DEL D668 - Completion of Build Segment III DW/BI - Submit | 0 hrs | 0 days | Tue 3/11/25 | Tue 3/11/25 | 519 | 521 |  | Joy Schneider
4620 | 521 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Department QC | 4 hrs | 1 day | Wed 3/12/25 | Wed 3/12/25 | 520 | 522 |  | Tommy Werner,Gabriela Gibson
4621 | 522 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Contract Manager Review | 8 hrs | 3 days | Thu 3/13/25 | Mon 3/17/25 | 521 | 523 |  | Sean Buchanan
4622 | 523 | Future Task |  |  | D668 | Manojkumar Gurjar | Accept | DEL D668 - Completion of Build Segment III DW/BI - Accept | 0 hrs | 0 days | Mon 3/17/25 | Mon 3/17/25 | 522 | 587 | 2025-08-01 | Sean Buchanan
4646 | 524 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | WP410 - Integration and Interface Strategy | 160 hrs | 115 days | Mon 7/10/23 | Thu 12/21/23
4647 | 525 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WPED WP410 - Integration and Interface Strategy - Create | 16 hrs | 10 days | Mon 7/10/23 | Fri 7/21/23 | 1 | 526 |  | Manojkumar Gurjar,Kurt Meisner
4648 | 526 | Future Task |  |  | WP410 | Manojkumar Gurjar | Submit | WPED WP410 - Integration and Interface Strategy - Submit | 0 hrs | 0 days | Fri 7/21/23 | Fri 7/21/23 | 525 | 527 |  | Manojkumar Gurjar,Joy Schneider
4649 | 527 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WPED WP410 - Integration and Interface Strategy - Review | 24 hrs | 10 days | Mon 7/24/23 | Fri 8/4/23 | 526 | 528 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4650 | 528 | Future Task |  |  | WP410 | Manojkumar Gurjar | Approve | WPED WP410 - Integration and Interface Strategy - Approve | 0 hrs | 0 days | Fri 8/4/23 | Fri 8/4/23 | 527 | 529FS+20 days |  | Jimmy Cox
4655 | 529 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WP410 - Define Interface and Integration Approach | 20 hrs | 19 days | Tue 9/5/23 | Fri 9/29/23 | 528FS+20 days | 530 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4656 | 530 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WP410 - Create Interface and Integration Architecture Diagram | 20 hrs | 15 days | Mon 10/2/23 | Fri 10/20/23 | 529 | 531532 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4657 | 531 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WP410 - Review and update Interface and Integration Operations | 20 hrs | 19 days | Mon 10/23/23 | Fri 11/17/23 | 530 | 532 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4658 | 532 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WP410 - Finalize the Interface and Integration Strategy Document | 20 hrs | 7 days | Mon 11/20/23 | Thu 11/30/23 | 530531 | 533 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4651 | 533 | Future Task |  |  | WP410 | Manojkumar Gurjar | Submit | WP WP410 - Integration and Interface Strategy - Submit | 0 hrs | 0 days | Thu 11/30/23 | Thu 11/30/23 | 532 | 534 |  | Manojkumar Gurjar,Joy Schneider
4652 | 534 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WP WP410 - Integration and Interface Strategy - Collaborative Review & Update | 20 hrs | 10 days | Fri 12/1/23 | Thu 12/14/23 | 533 | 535 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4653 | 535 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WP WP410 - Integration and Interface Strategy - Final Review & Edits | 20 hrs | 5 days | Fri 12/15/23 | Thu 12/21/23 | 534 | 536 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4654 | 536 | Future Task |  |  | WP410 | Manojkumar Gurjar | Approve | WP WP410 - Integration and Interface Strategy - Approve | 0 hrs | 0 days | Thu 12/21/23 | Thu 12/21/23 | 535 | 1072FS+68 days | 2023-11-01 | Jimmy Cox | RW/Comms - Update Interface Approach to share with agencies? | NK
5603 | 537 | Future Task |  |  | WP426 | Jarad Hermann |  | WP426 - System Infrastructure Capacity Plan | 148 hrs | 72 days | Mon 9/8/25 | Fri 12/19/25
5604 | 538 | Future Task |  |  | WP426 | Jarad Hermann | Create | WPED WP426 - System Infrastructure Capacity Plan - Create | 8 hrs | 10 days | Mon 9/8/25 | Fri 9/19/25 | 1 | 539 |  | Jarad Hermann
5605 | 539 | Future Task |  |  | WP426 | Jarad Hermann | Submit | WPED WP426 - System Infrastructure Capacity Plan - Submit | 0 hrs | 0 days | Fri 9/19/25 | Fri 9/19/25 | 538 | 540 |  | Joy Schneider,Jarad Hermann
5606 | 540 | Future Task |  |  | WP426 | Jarad Hermann | Review | WPED WP426 - System Infrastructure Capacity Plan - Review | 16 hrs | 10 days | Mon 9/22/25 | Fri 10/3/25 | 539 | 541 |  | Jarad Hermann,Jimmy Cox,Angie Robertson,Sean Buchanan
5607 | 541 | Future Task |  |  | WP426 | Jarad Hermann | Approve | WPED WP426 - System Infrastructure Capacity Plan - Approve | 0 hrs | 0 days | Fri 10/3/25 | Fri 10/3/25 | 540 | 542FS+20 days |  | Jimmy Cox
5608 | 542 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Review and refine the FL PALM Capacity Plan (excel doc) | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 541FS+20 days | 543SS,544SS,545SS,546SS |  | Jarad Hermann,Bryan Sohayda
5609 | 543 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Review and refine the FL PALM Capacity Plan (word doc) | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 542SS | 547 |  | Jarad Hermann,Bryan Sohayda
5610 | 544 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Define and document current infrastructure demand | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 542SS | 547 |  | Jarad Hermann,Bryan Sohayda
5611 | 545 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Define and document current infrastructure capacity | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 542SS | 547 |  | Jarad Hermann,Bryan Sohayda
5612 | 546 | Future Task |  |  | WP426 | Jarad Hermann | Create | WP426 - Define and document projected infrastructure demand | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 542SS | 547 |  | Jarad Hermann,Bryan Sohayda
5613 | 547 | Future Task |  |  | WP426 | Jarad Hermann | Submit | WP WP426 - System Infrastructure Capacity Plan - Submit | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 546543544545 | 548 |  | Joy Schneider,Jarad Hermann
5614 | 548 | Future Task |  |  | WP426 | Jarad Hermann | Review | WP WP426 - System Infrastructure Capacity Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 12/1/25 | Fri 12/12/25 | 547 | 549 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5615 | 549 | Future Task |  |  | WP426 | Jarad Hermann | Review | WP WP426 - System Infrastructure Capacity Plan - Final Review & Edits | 12 hrs | 5 days | Mon 12/15/25 | Fri 12/19/25 | 548 | 550 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5616 | 550 | Future Task |  |  | WP426 | Jarad Hermann | Approve | WP WP426 - System Infrastructure Capacity Plan - Approve | 0 hrs | 0 days | Fri 12/19/25 | Fri 12/19/25 | 549 |  |  | Jimmy Cox
3868 | 551 | Future Task | [5 empty] | Environment Builds | 137 hrs | 207 days | Mon 8/5/24 | Fri 5/30/25 |  |  |  |  | Is this related to a WP? Note from Joy: no | TW
4203 | 552 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure System Test Environment | 10 hrs | 15 days | Mon 8/5/24 | Fri 8/23/24 | 607 | 553 |  | Manojkumar Gurjar,Jarad Hermann | Is this the correct naming convention? Note from Joy: yes | TW
4204 | 553 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Validate System Test Environment | 8 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 552 | 650 |  | Manojkumar Gurjar,Jarad Hermann
4195 | 554 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Interface Test Environment | 10 hrs | 14 days | Tue 9/3/24 | Fri 9/20/24 | 1085FS-10 days | 555 |  | Manojkumar Gurjar,Jarad Hermann
4196 | 555 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Validate Interface Test Environment | 8 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 554 | 791 |  | Manojkumar Gurjar,Jarad Hermann
4197 | 556 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Mock Conversion Test Environment | 10 hrs | 15 days | Mon 8/5/24 | Fri 8/23/24 | 1032 | 557 |  | Manojkumar Gurjar,Jarad Hermann
4198 | 557 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Validate Mock Conversion Test Environment | 8 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 556 | 629 |  | Manojkumar Gurjar,Jarad Hermann
4199 | 558 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure UAT Test Environment | 10 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1250FS+46 days | 559 |  | Manojkumar Gurjar,Jarad Hermann
4200 | 559 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Validate UAT Test Environment | 10 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 558 | 560 |  | Manojkumar Gurjar,Jarad Hermann | RW? Do agencies need to do any validation? | NK
4201 | 560 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Load Security Roles to ForgeRock for UAT | 4 hrs | 4 days | Mon 3/3/25 | Thu 3/6/25 | 5591843 | 561 |  | Jarad Hermann | Add 0 day task to confirm receipt of Agency Role Mapping Worksheet | NK and AR
4202 | 561 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Validate Security Roles in ForgeRock for UAT | 5 hrs | 5 days | Fri 3/7/25 | Thu 3/13/25 | 560 | 1252587 |  | Jarad Hermann | RW? Do agencies need to do any validation? | NK
4191 | 562 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Dry Run Test Environment | 10 hrs | 14 days | Mon 5/5/25 | Thu 5/22/25 |  | 563 |  | Manojkumar Gurjar,Jarad Hermann
4192 | 563 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Validate Dry Run Test Environment | 8 hrs | 5 days | Fri 5/23/25 | Fri 5/30/25 | 562 | 831 |  | Manojkumar Gurjar,Jarad Hermann
4193 | 564 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Performance Test Environment | 10 hrs | 15 days | Mon 5/5/25 | Fri 5/23/25 | 1188 | 565 |  | Manojkumar Gurjar,Jarad Hermann
4194 | 565 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Validate Performance Test Environment | 8 hrs | 4 days | Tue 5/27/25 | Fri 5/30/25 | 564 | 971 |  | Manojkumar Gurjar,Jarad Hermann
4189 | 566 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Configure Disaster Recovery Test Environment | 10 hrs | 15 days | Mon 3/3/25 | Fri 3/21/25 | 1174 | 567 |  | Manojkumar Gurjar,Jarad Hermann
4190 | 567 | Future Task |  |  | ENV | Manojkumar Gurjar | Create | Validate Disaster Recovery Test Environment | 8 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 566 | 989FS+1 day |  | Manojkumar Gurjar,Jarad Hermann
6809 | 568 | Future Task | [5 empty] | Other | 48 hrs | 187 days | Mon 1/8/24 | Mon 9/30/24 |  |  |  |  | Discuss | Angie
7144 | 569 | Future Task |  |  |  | Stacey Terry | Create | Support Agency Configuration Workbook | 20 hrs | 103 days | Mon 1/8/24 | Fri 5/31/24 | 130FS+6 days | 570 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty | RW - Agency Config Workbook | NK
7145 | 570 | Future Task |  |  |  | Stacey Terry | Create | Load Agency Configuration Workbook | 20 hrs | 64 days | Mon 6/3/24 | Fri 8/30/24 | 569 |  |  | Stacey Terry,Yogesh Deshmukh,Mary Punty | 1. Add a new task after task 577. New task: "Confirm completeness of agency configuration workbooks" Start May 6, 2024, End June 28, 2024 2. Task 578 - Update task name to "Update configuration workbooks and load agency configurations" | Mary/Stacey
6808 | 571 | Future Task |  |  |  | Stacey Terry | Create | Define User Preferences | 2 hrs | 10 days | Wed 7/31/24 | Tue 8/13/24 | 241 | 1837 |  | Stacey Terry
6810 | 572 | Future Task |  |  |  | Stacey Terry | Create | Create Batch Design/Online | 2 hrs | 22 days | Mon 7/1/24 | Wed 7/31/24 | 51,70,109,149,168FS+24 days | 573 |  | Stacey Terry,Manojkumar Gurjar
6807 | 573 | Future Task |  |  |  | Stacey Terry | Create | Create Batch Design/Interface | 2 hrs | 22 days | Thu 8/1/24 | Fri 8/30/24 | 572 | 574 |  | Stacey Terry,Manojkumar Gurjar
6811 | 574 | Future Task |  |  |  | Stacey Terry | Create | Review and Confirm Batch Design | 2 hrs | 20 days | Tue 9/3/24 | Mon 9/30/24 | 573 |  |  | Stacey Terry,Manojkumar Gurjar | Make the successor the UAT Testing | Angie
3771 | 575 | Future Task | [5 empty] | Test | 6,591.58 hrs | 617 days | Mon 7/3/23 | Fri 12/12/25
7173 | 576 | Future Task |  |  | SG2 | Jimmy Cox |  | Stage Gate 2: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 3/4/24 | Fri 3/8/24 |  | 577 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7174 | 577 | Future Task |  |  | SG2 | Jimmy Cox |  | Stage Gate 2: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 576 | 578FS+80 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7175 | 578 | Future Task |  |  | SG2 | Jimmy Cox |  | Stage Gate 2: Prepare information package for ESC | 11 hrs | 10 days | Wed 7/17/24 | Tue 7/30/24 | 577FS+80 days | 579 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder | This date, as displayed, starts after the milestone for Stage Gate 2 (5/8/24). Please adjust Milestone (Unique ID 7153) to be in July / August 2024. Note from Joy on 6/6: SG prep tasks begin on 3/4 and end on 8/7. Current date of SG is based on current preds. We will baseline on the last business day of August 2024 and then adjust to auto schedule to allow the team to see shifting dates. | Angie
7176 | 579 | Future Task |  |  | SG2 | Jimmy Cox |  | Stage Gate 2: Collaborative Review and Update of information package | 11 hrs | 5 days | Wed 7/31/24 | Tue 8/6/24 | 578 | 580 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7177 | 580 | Future Task |  |  | SG2 | Jimmy Cox |  | Stage Gate 2: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 8/7/24 | Wed 8/7/24 | 579 |  |  | Dusti Kincl
7153 | 581 | Future Task |  |  | SG2 | Jimmy Cox | Milestone | Stage Gate 2: Ready to Begin System Testing | 0 hrs | 0 days | Wed 5/8/24 | Wed 5/8/24 | 51,70,149,161,385 |  | July/August 2024 | Jimmy Cox,Angie Robertson,Matt Cole
7178 | 582 | Future Task |  |  | SG3 | Jimmy Cox |  | Stage Gate 3: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 |  | 583 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7179 | 583 | Future Task |  |  | SG3 | Jimmy Cox |  | Stage Gate 3: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 582 | 584FS+76 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7180 | 584 | Future Task |  |  | SG3 | Jimmy Cox |  | Stage Gate 3: Prepare information package for ESC | 11 hrs | 10 days | Wed 2/19/25 | Tue 3/4/25 | 583FS+76 days | 585 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7181 | 585 | Future Task |  |  | SG3 | Jimmy Cox |  | Stage Gate 3: Collaborative Review and Update of information package | 11 hrs | 5 days | Wed 3/5/25 | Tue 3/11/25 | 584 | 586 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7182 | 586 | Future Task |  |  | SG3 | Jimmy Cox |  | Stage Gate 3: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 3/12/25 | Wed 3/12/25 | 585 |  |  | Dusti Kincl
7154 | 587 | Future Task |  |  | SG3 | Jimmy Cox | Milestone | Stage Gate 3: Ready to Begin UAT | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 51,70,149,168,385,421,441,463,483,503,523,1250,749,690,650,561 |  | March 2025 - ESC | Jimmy Cox,Angie Robertson,Matt Cole | This Milestone (Stage Gate) is to be approved by the ESC. We should show ESC as the Resource Name, instead of Jimmy, me, and Matt. | Angie
4662 | 588 | Future Task |  |  | D643 | Stacey Terry |  | D643 - Updated System Testing Plan | 343 hrs | 361 days | Mon 7/3/23 | Fri 12/6/24
4663 | 589 | Future Task |  |  | D643 | Stacey Terry | Create | DED D643 - Updated System Testing Plan - Create | 16 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 1FS+47 days | 590 |  | Stacey Terry,Mary Punty
4664 | 590 | Future Task |  |  | D643 | Stacey Terry | Submit | DED D643 - Updated System Testing Plan - Submit | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 589 | 591 |  | Stacey Terry,Joy Schneider
4665 | 591 | Future Task |  |  | D643 | Stacey Terry | Review | DED D643 - Updated System Testing Plan - Collaborative Review | 24 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 590 | 592 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4666 | 592 | Future Task |  |  | D643 | Stacey Terry | Approve | DED D643 - Updated System Testing Plan - Approve | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 591 | 593FS+80 days |  | Jimmy Cox
4685 | 593 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define System Test approach for Financials and Payroll | 20 hrs | 15 days | Mon 11/27/23 | Fri 12/15/23 | 592FS+80 days | 594 |  | Yogesh Deshmukh,Stacey Terry,Mary Punty,Manojkumar Gurjar,Kurt Meisner,Matt Cole
4686 | 594 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define System Test Cycles for Financials and Payroll | 20 hrs | 9 days | Mon 12/18/23 | Fri 12/29/23 | 593 | 595FS-4 days |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Mary Punty
4687 | 595 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Identify System Test Resources for Financials and Payroll | 20 hrs | 11 days | Tue 12/26/23 | Wed 1/10/24 | 594FS-4 days | 596SS+4 days |  | Stacey Terry,Manojkumar Gurjar,Janice Jackson,Tiffany Porter,Brendan Jones,Jennifer Reeves,Deana Metcalf,Matthew Breeding,Carolyn Hicks
4688 | 596 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define System Test Tools and Test Management processes | 20 hrs | 11 days | Tue 1/2/24 | Wed 1/17/24 | 595SS+4 days | 597FS-2 days |  | Yogesh Deshmukh,Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jennifer Reeves
4689 | 597 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Create Initial List of System Test Scenarios for Financials and Payroll | 20 hrs | 24 days | Tue 1/16/24 | Fri 2/16/24 | 596FS-2 days | 598FS-5 days |  | Yogesh Deshmukh,Stacey Terry,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4690 | 598 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define requirements traceability approach for system testing | 20 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 597FS-5 days | 599 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Mary Punty,Jennifer Reeves
4667 | 599 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 - Updated System Testing Plan - Draft Submission | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 598 | 600 |  | Stacey Terry,Joy Schneider
4668 | 600 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 2/26/24 | Fri 3/1/24 | 599 | 601 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4669 | 601 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Style Guide Review | 1 hr | 1 day | Mon 3/4/24 | Mon 3/4/24 | 600 | 602 |  | Dusti Kincl
4670 | 602 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Final Collaborative Review | 20 hrs | 5 days | Tue 3/5/24 | Mon 3/11/24 | 601 | 603 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4671 | 603 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Accenture QC | 4 hrs | 2 days | Tue 3/12/24 | Wed 3/13/24 | 602 | 604 |  | Joy Schneider
4672 | 604 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 - Updated System Testing Plan - Submit | 0 hrs | 0 days | Wed 3/13/24 | Wed 3/13/24 | 603 | 605 |  | Joy Schneider
4673 | 605 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Department QC | 4 hrs | 1 day | Thu 3/14/24 | Thu 3/14/24 | 604 | 606 |  | Tommy Werner,Gabriela Gibson
4674 | 606 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Contract Manager Review | 8 hrs | 3 days | Fri 3/15/24 | Tue 3/19/24 | 605 | 607 |  | Sean Buchanan
4675 | 607 | Future Task |  |  | D643 | Stacey Terry | Accept | DEL D643 - Updated System Testing Plan - Accept | 0 hrs | 0 days | Tue 3/19/24 | Tue 3/19/24 | 606 | 608FS+101 days,552 | 2024-03-01 | Sean Buchanan
4691 | 608 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Update DED D643 to include the system testing plan for DW and BI | 20 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 607FS+101 days | 609FS+9 days |  | Mary Punty,Stacey Terry | The DW/BI tasks associated with the System Test Plan should be in a separate Work Product, not part of D643. Attachment 2 includes only one payment point, which aligns with the submission inclusive of the Financials/Payroll. The DW/BI work is essential, but should be it's own Work Product. | Angie Note from Joy on 6/8 - this work will move to a new WP that is only DW/BI.
4692 | 609 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define System Test approach for DW & BI | 20 hrs | 20 days | Mon 9/9/24 | Fri 10/4/24 | 608FS+9 days | 610SS+10 days |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
4693 | 610 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Define System Test Cycles for DW & BI | 20 hrs | 15 days | Mon 9/23/24 | Fri 10/11/24 | 609SS+10 days | 611SS+5 days |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
4694 | 611 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Identify System Test Resources for DW & BI | 20 hrs | 10 days | Mon 9/30/24 | Fri 10/11/24 | 610SS+5 days | 612 |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
4695 | 612 | Future Task |  |  | D643 | Stacey Terry | Create | D643 - Create Initial List of DW & BI System Test Scenarios | 4 hrs | 20 days | Mon 10/14/24 | Fri 11/8/24 | 611 | 613 |  | Jennifer Reeves,Manojkumar Gurjar
4676 | 613 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 2.0 - Updated System Testing Plan - Draft Submission | 0 hrs | 0 days | Fri 11/8/24 | Fri 11/8/24 | 612 | 614 |  | Stacey Terry,Joy Schneider
4677 | 614 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Pre-Submission Collaborative Review | 5 hrs | 5 days | Tue 11/12/24 | Mon 11/18/24 | 613 | 615 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4678 | 615 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Style Guide Review | 1 hr | 1 day | Tue 11/19/24 | Tue 11/19/24 | 614 | 616 |  | Dusti Kincl
4679 | 616 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Final Collaborative Review | 20 hrs | 5 days | Wed 11/20/24 | Tue 11/26/24 | 615 | 617 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4680 | 617 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Accenture QC | 4 hrs | 2 days | Wed 11/27/24 | Mon 12/2/24 | 616 | 618 |  | Joy Schneider
4681 | 618 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 2.0 - Updated System Testing Plan - Submit | 0 hrs | 0 days | Mon 12/2/24 | Mon 12/2/24 | 617 | 619 |  | Joy Schneider
4682 | 619 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Department QC | 4 hrs | 1 day | Tue 12/3/24 | Tue 12/3/24 | 618 | 620 |  | Tommy Werner,Gabriela Gibson
4683 | 620 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Contract Manager Review | 8 hrs | 3 days | Wed 12/4/24 | Fri 12/6/24 | 619 | 621 |  | Sean Buchanan
4684 | 621 | Future Task |  |  | D643 | Stacey Terry | Accept | DEL D643 2.0 - Updated System Testing Plan - Accept | 0 hrs | 0 days | Fri 12/6/24 | Fri 12/6/24 | 620 |  |  | Sean Buchanan
5004 | 622 | Future Task | Maybe |  | D651 | Manojkumar Gurjar |  | D651 - Completion of Mock Conversion I | 197 hrs | 90 days | Mon 6/17/24 | Tue 10/22/24
5005 | 623 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | DED D651 - Completion of Mock Conversion I - Create | 16 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 1044FS-47 days | 624 |  | Manojkumar Gurjar,Kurt Meisner
5006 | 624 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DED D651 - Completion of Mock Conversion I - Submit | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 623 | 625 |  | Manojkumar Gurjar,Joy Schneider
5007 | 625 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DED D651 - Completion of Mock Conversion I - Collaborative Review | 24 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 624 | 626 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5008 | 626 | Future Task |  |  | D651 | Manojkumar Gurjar | Approve | DED D651 - Completion of Mock Conversion I - Approve | 0 hrs | 0 days | Mon 7/15/24 | Mon 7/15/24 | 625 | 627FS+19 days |  | Jimmy Cox
5018 | 627 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | D651 - Confirm Mock 1 Conversion Test Environment Readiness | 20 hrs | 5 days | Mon 8/12/24 | Fri 8/16/24 | 626FS+19 days | 628 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5019 | 628 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | D651 - Create Mock 1 Conversion Checklist | 20 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 627 | 629 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5020 | 629 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | D651 - Execute Mock 1 – Conversion | 20 hrs | 9 days | Tue 9/3/24 | Fri 9/13/24 | 628557 | 630 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5021 | 630 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | D651 - Validate Mock 1 – Conversion | 20 hrs | 5 days | Mon 9/16/24 | Fri 9/20/24 | 629 | 631 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5022 | 631 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | D651 - Conduct Mock 1 - Conversion Test Exit Criteria Review Meeting | 20 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 630 | 632 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5009 | 632 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DEL D651 - Completion of Mock Conversion I - Draft Submission | 0 hrs | 0 days | Fri 9/27/24 | Fri 9/27/24 | 631 | 633 |  | Manojkumar Gurjar,Joy Schneider
5010 | 633 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 9/30/24 | Fri 10/4/24 | 632 | 634 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5011 | 634 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Style Guide Review | 1 hr | 1 day | Mon 10/7/24 | Mon 10/7/24 | 633 | 635 |  | Dusti Kincl
5012 | 635 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Final Collaborative Review | 20 hrs | 5 days | Tue 10/8/24 | Mon 10/14/24 | 634 | 636 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5013 | 636 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Accenture QC | 4 hrs | 2 days | Tue 10/15/24 | Wed 10/16/24 | 635 | 637 |  | Joy Schneider
5014 | 637 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DEL D651 - Completion of Mock Conversion I - Submit | 0 hrs | 0 days | Wed 10/16/24 | Wed 10/16/24 | 636 | 638 |  | Joy Schneider
5015 | 638 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Department QC | 4 hrs | 1 day | Thu 10/17/24 | Thu 10/17/24 | 637 | 639 |  | Tommy Werner,Gabriela Gibson
5016 | 639 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Contract Manager Review | 8 hrs | 3 days | Fri 10/18/24 | Tue 10/22/24 | 638 | 640 |  | Sean Buchanan
5017 | 640 | Future Task |  |  | D651 | Manojkumar Gurjar | Accept | DEL D651 - Completion of Mock Conversion I - Accept | 0 hrs | 0 days | Tue 10/22/24 | Tue 10/22/24 | 639 | 665FS-32 days | 2024-11-01 | Sean Buchanan
4696 | 641 | Future Task | Maybe |  | D652 | Stacey Terry |  | D652 - Completion of System Test Segment I | 206 hrs | 123 days | Mon 7/8/24 | Thu 1/2/25
4697 | 642 | Future Task |  |  | D652 | Stacey Terry | Create | DED D652 - Completion of System Test Segment I - Create | 16 hrs | 10 days | Mon 7/8/24 | Fri 7/19/24 | 1 | 643 |  | Stacey Terry,Mary Punty
4698 | 643 | Future Task |  |  | D652 | Stacey Terry | Submit | DED D652 - Completion of System Test Segment I - Submit | 0 hrs | 0 days | Fri 7/19/24 | Fri 7/19/24 | 642 | 644 |  | Stacey Terry,Joy Schneider
4699 | 644 | Future Task |  |  | D652 | Stacey Terry | Review | DED D652 - Completion of System Test Segment I - Collaborative Review | 24 hrs | 10 days | Mon 7/22/24 | Fri 8/2/24 | 643 | 645 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4700 | 645 | Future Task |  |  | D652 | Stacey Terry | Approve | DED D652 - Completion of System Test Segment I - Approve | 0 hrs | 0 days | Fri 8/2/24 | Fri 8/2/24 | 644 | 646 |  | Jimmy Cox
4752 | 646 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Create Work Unit Tracker for System Test Segment 1 Execution | 20 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 645 | 647 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4753 | 647 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Review, Update and confirm Work Unit Tracker for System Test Segment 1 Execution | 20 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 646 | 648SS+5 days |  | Mary Punty,Stacey Terry,Deana Metcalf,Janice Jackson,Tiffany Porter,Brendan Jones
4754 | 648 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Confirm System Test Environment Readiness | 20 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 647SS+5 days | 649SS |  | Manojkumar Gurjar,Jarad Hermann
4755 | 649 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Conduct System Test Kick Off Meeting | 30 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 648SS | 650 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4756 | 650 | Future Task | Maybe |  | D652 | Stacey Terry | Create | D652 - Execute System Test Segment 1 | 10 hrs | 51 days | Tue 9/17/24 | Wed 11/27/24 | 6491058553 | 651,652FS-3 days,587 |  | Yogesh Deshmukh,Stacey Terry,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4757 | 651 | Future Task |  |  | D652 | Stacey Terry | Milestone | D652 - Milestone: System Test Segment 1 Execution Complete | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 650 | 1730 |  | Stacey Terry | Why are these Milestones? What is the rationale or downstream benefit to including as Milestones? (Would like to have some common expectation for when something should be a Milestone.) | Angie
4758 | 652 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Create Completion of System Testing Segment 1 Summary Document | 3 hrs | 8 days | Mon 11/25/24 | Fri 12/6/24 | 650FS-3 days | 653SS+3 days,654SS+3 days,655 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4759 | 653 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Conduct System Test Segment 1 Exit Criteria Review Meeting | 3 hrs | 5 days | Mon 12/2/24 | Fri 12/6/24 | 652SS+3 days | 655 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4760 | 654 | Future Task |  |  | D652 | Stacey Terry | Create | D652 - Confirm requirements traceability for System Test Segment 1 | 3 hrs | 5 days | Mon 12/2/24 | Fri 12/6/24 | 652SS+3 days | 655 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4701 | 655 | Future Task |  |  | D652 | Stacey Terry | Submit | DEL D652 - Completion of System Test Segment I - Draft Submission | 0 hrs | 0 days | Fri 12/6/24 | Fri 12/6/24 | 652653654 | 656 |  | Stacey Terry,Joy Schneider
4702 | 656 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 12/9/24 | Fri 12/13/24 | 655 | 657 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4703 | 657 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Style Guide Review | 1 hr | 1 day | Mon 12/16/24 | Mon 12/16/24 | 656 | 658 |  | Dusti Kincl
4704 | 658 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Final Collaborative Review | 20 hrs | 5 days | Tue 12/17/24 | Mon 12/23/24 | 657 | 659 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4705 | 659 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Accenture QC | 4 hrs | 2 days | Tue 12/24/24 | Thu 12/26/24 | 658 | 660 |  | Joy Schneider
4706 | 660 | Future Task |  |  | D652 | Stacey Terry | Submit | DEL D652 - Completion of System Test Segment I - Submit | 0 hrs | 0 days | Thu 12/26/24 | Thu 12/26/24 | 659 | 661 |  | Joy Schneider
4707 | 661 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Department QC | 4 hrs | 1 day | Fri 12/27/24 | Fri 12/27/24 | 660 | 662 |  | Tommy Werner,Gabriela Gibson
4708 | 662 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Contract Manager Review | 8 hrs | 3 days | Mon 12/30/24 | Thu 1/2/25 | 661 | 663 |  | Sean Buchanan
4709 | 663 | Future Task |  |  | D652 | Stacey Terry | Accept | DEL D652 - Completion of System Test Segment I - Accept | 0 hrs | 0 days | Thu 1/2/25 | Thu 1/2/25 | 662 |  | 2024-12-01 | Sean Buchanan
4710 | 664 | Future Task | Maybe |  | D655 | Manojkumar Gurjar |  | D655 - Completion of Mock Conversion II (System Test Environment) | 197 hrs | 94 days | Mon 9/9/24 | Fri 1/24/25
4711 | 665 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | DED D655 - Completion of Mock Conversion II (System Test Environment) - Create | 16 hrs | 10 days | Mon 9/9/24 | Fri 9/20/24 | 640FS-32 days | 666 |  | Manojkumar Gurjar,Kurt Meisner
4712 | 666 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DED D655 - Completion of Mock Conversion II (System Test Environment) - Submit | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 665 | 667 |  | Manojkumar Gurjar,Joy Schneider
4713 | 667 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DED D655 - Completion of Mock Conversion II (System Test Environment) - Collaborative Review | 24 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 666 | 668 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4714 | 668 | Future Task |  |  | D655 | Manojkumar Gurjar | Approve | DED D655 - Completion of Mock Conversion II (System Test Environment) - Approve | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 667 | 669FS+29 days |  | Jimmy Cox
4761 | 669 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | D655 - Confirm Mock 2 Conversion - System Test Environment Readiness | 20 hrs | 4 days | Mon 11/18/24 | Thu 11/21/24 | 668FS+29 days | 670 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4762 | 670 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | D655 - Create Mock 2 Conversion Checklist (System Test Environment) | 20 hrs | 5 days | Fri 11/22/24 | Mon 12/2/24 | 669 | 671 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4763 | 671 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | D655 - Execute Mock 2 – Conversion (System Test Environment) | 20 hrs | 10 days | Tue 12/3/24 | Mon 12/16/24 | 670 | 672 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4764 | 672 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | D655 - Validate Mock 2 – Conversion (System Test Environment) | 20 hrs | 4 days | Tue 12/17/24 | Fri 12/20/24 | 671 | 673 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4765 | 673 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | D655 - Conduct Mock 2 - Conversion (System Test Environment) Test Exit Criteria Review Meeting | 20 hrs | 5 days | Mon 12/23/24 | Mon 12/30/24 | 672 | 674 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4715 | 674 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Draft Submission | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 673 | 675 |  | Manojkumar Gurjar,Joy Schneider
4716 | 675 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 12/31/24 | Tue 1/7/25 | 674 | 676 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4717 | 676 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Style Guide Review | 1 hr | 1 day | Wed 1/8/25 | Wed 1/8/25 | 675 | 677 |  | Dusti Kincl
4718 | 677 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Final Collaborative Review | 20 hrs | 5 days | Thu 1/9/25 | Wed 1/15/25 | 676 | 678 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4719 | 678 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Accenture QC | 4 hrs | 2 days | Thu 1/16/25 | Fri 1/17/25 | 677 | 679 |  | Joy Schneider
4720 | 679 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Submit | 0 hrs | 0 days | Fri 1/17/25 | Fri 1/17/25 | 678 | 680 |  | Joy Schneider
4721 | 680 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Department QC | 4 hrs | 1 day | Tue 1/21/25 | Tue 1/21/25 | 679 | 681 |  | Tommy Werner,Gabriela Gibson
4722 | 681 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Contract Manager Review | 8 hrs | 3 days | Wed 1/22/25 | Fri 1/24/25 | 680 | 682 |  | Sean Buchanan
4723 | 682 | Future Task |  |  | D655 | Manojkumar Gurjar | Accept | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Accept | 0 hrs | 0 days | Fri 1/24/25 | Fri 1/24/25 | 681 | 705FS-64 days | 2025-01-01 | Sean Buchanan
4724 | 683 | Future Task |  |  | D656 | Stacey Terry |  | D656 - Completion of System Test Segment II | 154 hrs | 99 days | Mon 10/7/24 | Fri 2/28/25
4725 | 684 | Future Task |  |  | D656 | Stacey Terry | Create | DED D656 - Completion of System Test Segment II - Create | 16 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1 | 685 |  | Stacey Terry,Mary Punty
4726 | 685 | Future Task |  |  | D656 | Stacey Terry | Submit | DED D656 - Completion of System Test Segment II - Submit | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 684 | 686 |  | Stacey Terry,Joy Schneider
4727 | 686 | Future Task |  |  | D656 | Stacey Terry | Review | DED D656 - Completion of System Test Segment II - Collaborative Review | 20 hrs | 10 days | Mon 10/21/24 | Fri 11/1/24 | 685 | 687 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4728 | 687 | Future Task |  |  | D656 | Stacey Terry | Approve | DED D656 - Completion of System Test Segment II - Approve | 0 hrs | 0 days | Fri 11/1/24 | Fri 11/1/24 | 686 | 688 |  | Jimmy Cox
4766 | 688 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Create Work Unit Tracker for System Test Segment 2 Execution | 6 hrs | 9 days | Mon 11/4/24 | Fri 11/15/24 | 687 | 689 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4767 | 689 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Review, Update and confirm Work Unit Tracker for System Test Segment 2 Execution | 20 hrs | 8 days | Mon 11/18/24 | Wed 11/27/24 | 688 | 690 |  | Mary Punty,Stacey Terry,Deana Metcalf,Janice Jackson,Tiffany Porter,Brendan Jones
4768 | 690 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Execute System Test Segment 2 | 20 hrs | 40 days | Mon 12/2/24 | Wed 1/29/25 | 689 | 691,692FS-5 days,587 |  | Yogesh Deshmukh,Stacey Terry,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4769 | 691 | Future Task |  |  | D656 | Stacey Terry | Milestone | D656 - Milestone: System Test Segment 2 Execution Complete | 0 hrs | 0 days | Wed 1/29/25 | Wed 1/29/25 | 690 |  |  | Stacey Terry | Why are these Milestones? What is the rationale or downstream benefit to including as Milestones? (Would like to have some common expectation for when something should be a Milestone.) | Angie
4770 | 692 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Create Completion of System Testing Segment 2 Summary Document | 6 hrs | 10 days | Thu 1/23/25 | Wed 2/5/25 | 690FS-5 days | 693SS+5 days,694SS+5 days,695 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4771 | 693 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Conduct System Test Segment 2 Exit Criteria Review Meeting | 3 hrs | 5 days | Thu 1/30/25 | Wed 2/5/25 | 692SS+5 days | 695 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4772 | 694 | Future Task |  |  | D656 | Stacey Terry | Create | D656 - Confirm requirements traceability for System Test Segment 2 | 6 hrs | 5 days | Thu 1/30/25 | Wed 2/5/25 | 692SS+5 days | 695 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4729 | 695 | Future Task |  |  | D656 | Stacey Terry | Submit | DEL D656 - Completion of System Test Segment II - Draft Submission | 0 hrs | 0 days | Wed 2/5/25 | Wed 2/5/25 | 692693694 | 696 |  | Stacey Terry,Joy Schneider
4730 | 696 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Thu 2/6/25 | Wed 2/12/25 | 695 | 697 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4731 | 697 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Style Guide Review | 1 hr | 1 day | Thu 2/13/25 | Thu 2/13/25 | 696 | 698 |  | Dusti Kincl
4732 | 698 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Final Collaborative Review | 20 hrs | 5 days | Fri 2/14/25 | Thu 2/20/25 | 697 | 699 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4733 | 699 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Accenture QC | 4 hrs | 2 days | Fri 2/21/25 | Mon 2/24/25 | 698 | 700 |  | Joy Schneider
4734 | 700 | Future Task |  |  | D656 | Stacey Terry | Submit | DEL D656 - Completion of System Test Segment II - Submit | 0 hrs | 0 days | Mon 2/24/25 | Mon 2/24/25 | 699 | 701 |  | Joy Schneider
4735 | 701 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Department QC | 4 hrs | 1 day | Tue 2/25/25 | Tue 2/25/25 | 700 | 702 |  | Tommy Werner,Gabriela Gibson
4736 | 702 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Contract Manager Review | 8 hrs | 3 days | Wed 2/26/25 | Fri 2/28/25 | 701 | 703 |  | Sean Buchanan
4737 | 703 | Future Task |  |  | D656 | Stacey Terry | Accept | DEL D656 - Completion of System Test Segment II - Accept | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 702 |  | 2025-02-01 | Sean Buchanan
4738 | 704 | Future Task | Maybe |  | D657 | Manojkumar Gurjar |  | D657 - Completion of Mock Conversion III (UAT) | 151 hrs | 101 days | Mon 10/21/24 | Tue 3/18/25 |  |  |  |  | RW? What cycles of Mock Conversion are agencies expected to participate? | NK
4739 | 705 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | DED D657 - Completion of Mock Conversion III (UAT) - Create | 16 hrs | 10 days | Mon 10/21/24 | Fri 11/1/24 | 682FS-64 days | 706 |  | Manojkumar Gurjar,Kurt Meisner
4740 | 706 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DED D657 - Completion of Mock Conversion III (UAT) - Submit | 0 hrs | 0 days | Fri 11/1/24 | Fri 11/1/24 | 705 | 707 |  | Manojkumar Gurjar,Joy Schneider
4741 | 707 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DED D657 - Completion of Mock Conversion III (UAT) - Collaborative Review | 24 hrs | 10 days | Mon 11/4/24 | Mon 11/18/24 | 706 | 708 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4742 | 708 | Future Task |  |  | D657 | Manojkumar Gurjar | Approve | DED D657 - Completion of Mock Conversion III (UAT) - Approve | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 707 | 709FS+24 days |  | Jimmy Cox
4773 | 709 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | D657 - Confirm Mock 3 Conversion - UAT Environment Readiness | 2 hrs | 5 days | Thu 12/26/24 | Thu 1/2/25 | 708FS+24 days | 710 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4774 | 710 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | D657 - Create Mock 3 Conversion Checklist (UAT) | 2 hrs | 6 days | Fri 1/3/25 | Fri 1/10/25 | 709 | 711 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4775 | 711 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | D657 - Execute Mock 3 – Conversion (UAT) | 10 hrs | 21 days | Mon 1/13/25 | Tue 2/11/25 | 710 | 712 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4776 | 712 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | D657 - Validate Mock 3 – Conversion (UAT) | 20 hrs | 4 days | Wed 2/12/25 | Mon 2/17/25 | 711 | 713 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4777 | 713 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | D657 - Conduct Mock 3 - Conversion UAT Exit Criteria Review Meeting | 20 hrs | 4 days | Tue 2/18/25 | Fri 2/21/25 | 712 | 714 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4743 | 714 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DEL D657 - Completion of Mock Conversion III (UAT) - Draft Submission | 0 hrs | 0 days | Fri 2/21/25 | Fri 2/21/25 | 713 | 715 |  | Manojkumar Gurjar,Joy Schneider
4744 | 715 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 714 | 716 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4745 | 716 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Style Guide Review | 1 hr | 1 day | Mon 3/3/25 | Mon 3/3/25 | 715 | 717 |  | Dusti Kincl
4746 | 717 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Final Collaborative Review | 20 hrs | 5 days | Tue 3/4/25 | Mon 3/10/25 | 716 | 718 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4747 | 718 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Accenture QC | 4 hrs | 2 days | Tue 3/11/25 | Wed 3/12/25 | 717 | 719 |  | Joy Schneider
4748 | 719 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DEL D657 - Completion of Mock Conversion III (UAT) - Submit | 0 hrs | 0 days | Wed 3/12/25 | Wed 3/12/25 | 718 | 720 |  | Joy Schneider
4749 | 720 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Department QC | 4 hrs | 1 day | Thu 3/13/25 | Thu 3/13/25 | 719 | 721 |  | Tommy Werner,Gabriela Gibson
4750 | 721 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Contract Manager Review | 8 hrs | 3 days | Fri 3/14/25 | Tue 3/18/25 | 720 | 722 |  | Sean Buchanan
4751 | 722 | Future Task |  |  | D657 | Manojkumar Gurjar | Accept | DEL D657 - Completion of Mock Conversion III (UAT) - Accept | 0 hrs | 0 days | Tue 3/18/25 | Tue 3/18/25 | 721 | 764FS-46 days,1259 | 2025-02-01 | Sean Buchanan
5023 | 723 | Future Task |  |  | D660 | Stacey Terry |  | D660 - Payroll Parallel Testing Plan | 182 hrs | 94 days | Mon 12/2/24 | Tue 4/15/25
5024 | 724 | Future Task |  |  | D660 | Stacey Terry | Create | DED D660 - Payroll Parallel Testing Plan - Create | 16 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 199 | 725 |  | Stacey Terry,Mary Punty
5025 | 725 | Future Task |  |  | D660 | Stacey Terry | Submit | DED D660 - Payroll Parallel Testing Plan - Submit | 0 hrs | 0 days | Fri 12/13/24 | Fri 12/13/24 | 724 | 726,1101SS-4 days |  | Stacey Terry,Joy Schneider
5026 | 726 | Future Task |  |  | D660 | Stacey Terry | Review | DED D660 - Payroll Parallel Testing Plan - Collaborative Review | 24 hrs | 10 days | Mon 12/16/24 | Mon 12/30/24 | 725 | 727 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5027 | 727 | Future Task |  |  | D660 | Stacey Terry | Approve | DED D660 - Payroll Parallel Testing Plan - Approve | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 726 | 728FS+22 days |  | Jimmy Cox
5037 | 728 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Define Payroll Parallel Test approach | 20 hrs | 20 days | Mon 2/3/25 | Fri 2/28/25 | 727FS+22 days | 729FS-5 days |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5038 | 729 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Define Payroll Parallel Test Cycles | 15 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 728FS-5 days | 730 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5039 | 730 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Identify Test Resources for Payroll Parallel Test | 20 hrs | 5 days | Mon 3/3/25 | Fri 3/7/25 | 729 | 731 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5040 | 731 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Define Payroll Parallel Test Tools and Test Management processes | 20 hrs | 5 days | Mon 3/10/25 | Fri 3/14/25 | 730 | 732FS-5 days |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5041 | 732 | Future Task |  |  | D660 | Stacey Terry | Create | D660 - Create Initial List of Payroll Parallel Test Scenarios | 20 hrs | 10 days | Mon 3/10/25 | Fri 3/21/25 | 731FS-5 days | 733 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5028 | 733 | Future Task |  |  | D660 | Stacey Terry | Submit | DEL D660 - Payroll Parallel Testing Plan - Draft Submission | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 732 | 734 |  | Stacey Terry,Joy Schneider
5029 | 734 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 733 | 735 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5030 | 735 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Style Guide Review | 1 hr | 1 day | Mon 3/31/25 | Mon 3/31/25 | 734 | 736 |  | Dusti Kincl
5031 | 736 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Final Collaborative Review | 10 hrs | 5 days | Tue 4/1/25 | Mon 4/7/25 | 735 | 737 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5032 | 737 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Accenture QC | 4 hrs | 2 days | Tue 4/8/25 | Wed 4/9/25 | 736 | 738 |  | Joy Schneider
5033 | 738 | Future Task |  |  | D660 | Stacey Terry | Submit | DEL D660 - Payroll Parallel Testing Plan - Submit | 0 hrs | 0 days | Wed 4/9/25 | Wed 4/9/25 | 737 | 739 |  | Joy Schneider
5034 | 739 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Department QC | 4 hrs | 1 day | Thu 4/10/25 | Thu 4/10/25 | 738 | 740 |  | Tommy Werner,Gabriela Gibson
5035 | 740 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Contract Manager Review | 8 hrs | 3 days | Fri 4/11/25 | Tue 4/15/25 | 739 | 741 |  | Sean Buchanan
5036 | 741 | Future Task |  |  | D660 | Stacey Terry | Accept | DEL D660 - Payroll Parallel Testing Plan - Accept | 0 hrs | 0 days | Tue 4/15/25 | Tue 4/15/25 | 740 | 864FS-37 days | 2025-04-01 | Sean Buchanan
4778 | 742 | Future Task |  |  | D661 | Stacey Terry |  | D661 - Completion of System Test DW/BI | 207 hrs | 120 days | Mon 11/4/24 | Mon 4/28/25
4779 | 743 | Future Task |  |  | D661 | Stacey Terry | Create | DED D661 - Completion of System Test DW/BI - Create | 16 hrs | 10 days | Mon 11/4/24 | Mon 11/18/24 | 1 | 744 |  | Stacey Terry,Mary Punty | This should be earlier than immediately before work begins. Note from Joy on 6/7: worked with the team to confirm no date changes as a result of the timing on identifying test scripts aligned to this deliverable and ability to define the work unit tracker details | Angie Note from 6/8 - with new approach, we will pull forward. PMO to confirm dates with Mary.
4780 | 744 | Future Task |  |  | D661 | Stacey Terry | Submit | DED D661 - Completion of System Test DW/BI - Submit | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 743 | 745 |  | Stacey Terry,Joy Schneider
4781 | 745 | Future Task |  |  | D661 | Stacey Terry | Review | DED D661 - Completion of System Test DW/BI - Collaborative Review | 24 hrs | 10 days | Tue 11/19/24 | Wed 12/4/24 | 744 | 746 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4782 | 746 | Future Task |  |  | D661 | Stacey Terry | Approve | DED D661 - Completion of System Test DW/BI - Approve | 0 hrs | 0 days | Wed 12/4/24 | Wed 12/4/24 | 745 | 747 |  | Jimmy Cox
4820 | 747 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Create Work Unit Tracker for System Test DW/BI Execution | 36 hrs | 9 days | Thu 12/5/24 | Tue 12/17/24 | 746 | 748 |  | Manojkumar Gurjar,Mary Punty
4821 | 748 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Review, Update and confirm Work Unit Tracker for System Test DW/BI Execution | 20 hrs | 10 days | Wed 12/18/24 | Thu 1/2/25 | 747 | 749 |  | Manojkumar Gurjar,Mary Punty
4822 | 749 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Execute System Test DW/BI | 20 hrs | 60 days | Fri 1/3/25 | Fri 3/28/25 | 748 | 750,751FS-6 days,587 |  | Manojkumar Gurjar,Mary Punty
4823 | 750 | Future Task |  |  | D661 | Stacey Terry | Milestone | D661 - Milestone: System Test DW/BI Execution Complete | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 749 |  |  | Stacey Terry | Why are these Milestones? What is the rationale or downstream benefit to including as Milestones? (Would like to have some common expectation for when something should be a Milestone.) | Angie
4824 | 751 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Create Completion of System Testing DW/BI Summary Document | 4 hrs | 10 days | Fri 3/21/25 | Thu 4/3/25 | 749FS-6 days | 752SS+5 days,754 |  | Manojkumar Gurjar,Mary Punty
4825 | 752 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Conduct System Test DW/BI Exit Criteria Review Meeting | 10 hrs | 5 days | Fri 3/28/25 | Thu 4/3/25 | 751SS+5 days | 753SS,754 |  | Manojkumar Gurjar,Mary Punty
4826 | 753 | Future Task |  |  | D661 | Stacey Terry | Create | D661 - Confirm requirements traceability for System Test DW/BI | 20 hrs | 5 days | Fri 3/28/25 | Thu 4/3/25 | 752SS | 754 |  | Manojkumar Gurjar,Mary Punty
4783 | 754 | Future Task |  |  | D661 | Stacey Terry | Submit | DEL D661 - Completion of System Test DW/BI - Draft Submission | 0 hrs | 0 days | Thu 4/3/25 | Thu 4/3/25 | 751752753 | 755 |  | Stacey Terry,Joy Schneider
4784 | 755 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 4/4/25 | Thu 4/10/25 | 754 | 756 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4785 | 756 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Style Guide Review | 1 hr | 1 day | Fri 4/11/25 | Fri 4/11/25 | 755 | 757 |  | Dusti Kincl
4786 | 757 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Final Collaborative Review | 20 hrs | 5 days | Mon 4/14/25 | Fri 4/18/25 | 756 | 758 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4787 | 758 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Accenture QC | 4 hrs | 2 days | Mon 4/21/25 | Tue 4/22/25 | 757 | 759 |  | Joy Schneider
4788 | 759 | Future Task |  |  | D661 | Stacey Terry | Submit | DEL D661 - Completion of System Test DW/BI - Submit | 0 hrs | 0 days | Tue 4/22/25 | Tue 4/22/25 | 758 | 760 |  | Joy Schneider
4789 | 760 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Department QC | 4 hrs | 1 day | Wed 4/23/25 | Wed 4/23/25 | 759 | 761 |  | Tommy Werner,Gabriela Gibson
4790 | 761 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Contract Manager Review | 8 hrs | 3 days | Thu 4/24/25 | Mon 4/28/25 | 760 | 762 |  | Sean Buchanan
4791 | 762 | Future Task |  |  | D661 | Stacey Terry | Accept | DEL D661 - Completion of System Test DW/BI - Accept | 0 hrs | 0 days | Mon 4/28/25 | Mon 4/28/25 | 761 |  | 2025-05-01 | Sean Buchanan
4792 | 763 | Future Task | Maybe |  | D662 | Manojkumar Gurjar |  | D662 - Completion of Dress Rehearsal (Mock Conversion IV) | 197 hrs | 96 days | Mon 1/13/25 | Wed 5/28/25
4793 | 764 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Create | 16 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 722FS-46 days | 765 |  | Manojkumar Gurjar,Kurt Meisner
4794 | 765 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Submit | 0 hrs | 0 days | Mon 1/27/25 | Mon 1/27/25 | 764 | 766 |  | Manojkumar Gurjar,Joy Schneider
4795 | 766 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Collaborative Review | 24 hrs | 10 days | Tue 1/28/25 | Mon 2/10/25 | 765 | 767 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4796 | 767 | Future Task |  |  | D662 | Manojkumar Gurjar | Approve | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Approve | 0 hrs | 0 days | Mon 2/10/25 | Mon 2/10/25 | 766 | 768FS+24 days |  | Jimmy Cox
4827 | 768 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | D662 - Confirm Mock 4 Conversion - (Dress Rehearsal) Environment Readiness | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 767FS+24 days | 769 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4828 | 769 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | D662 - Create Mock 4 Conversion Checklist (Dress Rehearsal) | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 768 | 770 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4829 | 770 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | D662 - Execute Mock 4 – Conversion (Dress Rehearsal) | 20 hrs | 10 days | Mon 3/31/25 | Fri 4/11/25 | 769 | 771 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4830 | 771 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | D662 - Validate Mock 4 – Conversion (Dress Rehearsal) | 20 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 770 | 772 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4831 | 772 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | D662 - Conduct Mock 4 - Conversion (Dress Rehearsal) Exit Criteria Review Meeting | 20 hrs | 5 days | Mon 4/28/25 | Fri 5/2/25 | 771 | 773 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4797 | 773 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Draft Submission | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 772 | 774 |  | Manojkumar Gurjar,Joy Schneider
4798 | 774 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 5/5/25 | Fri 5/9/25 | 773 | 775 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4799 | 775 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Style Guide Review | 1 hr | 1 day | Mon 5/12/25 | Mon 5/12/25 | 774 | 776 |  | Dusti Kincl
4800 | 776 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Final Collaborative Review | 20 hrs | 5 days | Tue 5/13/25 | Mon 5/19/25 | 775 | 777 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4801 | 777 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Accenture QC | 4 hrs | 2 days | Tue 5/20/25 | Wed 5/21/25 | 776 | 778 |  | Joy Schneider
4802 | 778 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Submit | 0 hrs | 0 days | Wed 5/21/25 | Wed 5/21/25 | 777 | 779 |  | Joy Schneider
4803 | 779 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Department QC | 4 hrs | 1 day | Thu 5/22/25 | Thu 5/22/25 | 778 | 780 |  | Tommy Werner,Gabriela Gibson
4804 | 780 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Contract Manager Review | 8 hrs | 3 days | Fri 5/23/25 | Wed 5/28/25 | 779 | 781 |  | Sean Buchanan
4805 | 781 | Future Task |  |  | D662 | Manojkumar Gurjar | Accept | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Accept | 0 hrs | 0 days | Wed 5/28/25 | Wed 5/28/25 | 780 | 1259 | 2025-05-01 | Sean Buchanan
4806 | 782 | Future Task |  |  | D663 | Manojkumar Gurjar |  | D663 - Completion of Interface Testing Segment I | 236.58 hrs | 223 days | Mon 8/12/24 | Mon 6/30/25
4807 | 783 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | DED D663 - Completion of Interface Testing Segment I - Create | 24 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 1 | 784 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4808 | 784 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DED D663 - Completion of Interface Testing Segment I - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 783 | 785 |  | Manojkumar Gurjar,Joy Schneider
4809 | 785 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DED D663 - Completion of Interface Testing Segment I - Collaborative Review | 28 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 784 | 786 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4810 | 786 | Future Task |  |  | D663 | Manojkumar Gurjar | Approve | DED D663 - Completion of Interface Testing Segment I - Approve | 0 hrs | 0 days | Mon 9/9/24 | Mon 9/9/24 | 785 | 787FS+19 days |  | Jimmy Cox
4832 | 787 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Create Interface Testing Segment 1 Execution Work Unit Tracker | 30 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 786FS+19 days | 788,792SS |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4833 | 788 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Review/Confirm Interface Testing Segment 1 Execution Work Unit Tracker | 15 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 787 | 789 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4834 | 789 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Conduct Interface Testing Segment 1 Readiness Review Meeting | 15 hrs | 5 days | Mon 10/28/24 | Fri 11/1/24 | 788 | 790 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4835 | 790 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Conduct Interface Test Kickoff Meeting with Integration Partners | 3 hrs | 9 days | Mon 11/4/24 | Fri 11/15/24 | 789 | 791 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty | RW? | NK
4836 | 791 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Confirm Interface Test Environment Readiness | 15 hrs | 5 days | Mon 11/18/24 | Fri 11/22/24 | 790555 | 793 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4837 | 792 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Establish Interface Connectivity Segment 1 | 20 hrs | 20 days | Mon 10/7/24 | Fri 11/1/24 | 787SS | 793FS+17 days |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4838 | 793 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Execute Interface Testing Segment 1 | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 792FS+17 days,791 | 794795 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4839 | 794 | Future Task |  |  | D663 | Manojkumar Gurjar | Milestone | D663 - Milestone: Interface Testing Segment 1 Complete | 0 hrs | 0 days | Wed 4/30/25 | Wed 4/30/25 | 793 | 797 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty | Why are these Milestones? What is the rationale or downstream benefit to including as Milestones? (Would like to have some common expectation for when something should be a Milestone.) | Angie
4840 | 795 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Conduct Test Exit Criteria Review Meeting | 15 hrs | 5 days | Thu 5/1/25 | Wed 5/7/25 | 793 | 796 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4841 | 796 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Confirm requirements traceability for Interface Testing Segment 1 | 15 hrs | 10 days | Thu 5/8/25 | Wed 5/21/25 | 795 | 797 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4842 | 797 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | D663 - Create Completion of Interface Testing Segment 1 Summary Document | 1.58 hrs | 10 days | Thu 5/22/25 | Thu 6/5/25 | 796794 | 798 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4811 | 798 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DEL D663 - Completion of Interface Testing Segment I - Draft Submission | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 797 | 799 |  | Manojkumar Gurjar,Joy Schneider
4812 | 799 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Pre-Submission Collaborative Review | 6 hrs | 5 days | Fri 6/6/25 | Thu 6/12/25 | 798 | 800 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4813 | 800 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Style Guide Review | 1 hr | 1 day | Fri 6/13/25 | Fri 6/13/25 | 799 | 801 |  | Dusti Kincl
4814 | 801 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Final Collaborative Review | 12 hrs | 5 days | Mon 6/16/25 | Fri 6/20/25 | 800 | 802 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4815 | 802 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Accenture QC | 4 hrs | 2 days | Mon 6/23/25 | Tue 6/24/25 | 801 | 803 |  | Joy Schneider
4816 | 803 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DEL D663 - Completion of Interface Testing Segment I - Submit | 0 hrs | 0 days | Tue 6/24/25 | Tue 6/24/25 | 802 | 804 |  | Joy Schneider
4817 | 804 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Department QC | 4 hrs | 1 day | Wed 6/25/25 | Wed 6/25/25 | 803 | 805 |  | Tommy Werner,Gabriela Gibson
4818 | 805 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Contract Manager Review | 8 hrs | 3 days | Thu 6/26/25 | Mon 6/30/25 | 804 | 806 |  | Sean Buchanan
4819 | 806 | Future Task |  |  | D663 | Manojkumar Gurjar | Accept | DEL D663 - Completion of Interface Testing Segment I - Accept | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 805 |  | 2025-06-01 | Sean Buchanan
5042 | 807 | Future Task |  |  | D666 | Stacey Terry |  | D666 - Support of UAT Segment I | 111 hrs | 119 days | Mon 1/13/25 | Mon 6/30/25 |  |  |  |  | RW - Agencies in UAT | NK
5043 | 808 | Future Task |  |  | D666 | Stacey Terry | Create | DED D666 - Support of UAT Segment I - Create | 16 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 1 | 809 |  | Stacey Terry,Mary Punty
5044 | 809 | Future Task |  |  | D666 | Stacey Terry | Submit | DED D666 - Support of UAT Segment I - Submit | 0 hrs | 0 days | Mon 1/27/25 | Mon 1/27/25 | 808 | 810 |  | Stacey Terry,Joy Schneider
5045 | 810 | Future Task |  |  | D666 | Stacey Terry | Review | DED D666 - Support of UAT Segment I - Collaborative Review | 24 hrs | 10 days | Tue 1/28/25 | Mon 2/10/25 | 809 | 811 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5046 | 811 | Future Task |  |  | D666 | Stacey Terry | Approve | DED D666 - Support of UAT Segment I - Approve | 0 hrs | 0 days | Mon 2/10/25 | Mon 2/10/25 | 810 | 812FS+24 days |  | Jimmy Cox
5056 | 812 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Identify UAT support resources for UAT Segment 1 | 20 hrs | 11 days | Mon 3/17/25 | Mon 3/31/25 | 811FS+24 days | 813 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5057 | 813 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Participate in UAT sessions for UAT Segment 1 | 6 hrs | 43 days | Tue 4/1/25 | Fri 5/30/25 | 812 | 814SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp
5058 | 814 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Support resolution of UAT issues for UAT Segment 1 | 7 hrs | 42 days | Tue 4/1/25 | Thu 5/29/25 | 813SS | 815FS-4 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
5059 | 815 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Confirm requirements traceability for UAT Segment 1 | 3 hrs | 4 days | Fri 5/23/25 | Thu 5/29/25 | 814FS-4 days | 816SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5060 | 816 | Future Task |  |  | D666 | Stacey Terry | Create | D666 - Create UAT Segment 1 Summary Document | 3 hrs | 9 days | Fri 5/23/25 | Thu 6/5/25 | 815SS | 817 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5047 | 817 | Future Task |  |  | D666 | Stacey Terry | Submit | DEL D666 - Support of UAT Segment I - Draft Submission | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 816 | 818 |  | Stacey Terry,Joy Schneider
5048 | 818 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Pre-Submission Collaborative Review | 5 hrs | 5 days | Fri 6/6/25 | Thu 6/12/25 | 817 | 819 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5049 | 819 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Style Guide Review | 1 hr | 1 day | Fri 6/13/25 | Fri 6/13/25 | 818 | 820 |  | Dusti Kincl
5050 | 820 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Final Collaborative Review | 10 hrs | 5 days | Mon 6/16/25 | Fri 6/20/25 | 819 | 821 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5051 | 821 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Accenture QC | 4 hrs | 2 days | Mon 6/23/25 | Tue 6/24/25 | 820 | 822 |  | Joy Schneider
5052 | 822 | Future Task |  |  | D666 | Stacey Terry | Submit | DEL D666 - Support of UAT Segment I - Submit | 0 hrs | 0 days | Tue 6/24/25 | Tue 6/24/25 | 821 | 823 |  | Joy Schneider
5053 | 823 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Department QC | 4 hrs | 1 day | Wed 6/25/25 | Wed 6/25/25 | 822 | 824 |  | Tommy Werner,Gabriela Gibson
5054 | 824 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Contract Manager Review | 8 hrs | 3 days | Thu 6/26/25 | Mon 6/30/25 | 823 | 825 |  | Sean Buchanan
5055 | 825 | Future Task |  |  | D666 | Stacey Terry | Accept | DEL D666 - Support of UAT Segment I - Accept | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 824 |  | 2025-06-01 | Sean Buchanan
5520 | 826 | Future Task | Maybe |  | D667 | Stacey Terry |  | D667 - Completion of Mock Go-Lives (Dry Run #1) | 108 hrs | 81 days | Mon 4/7/25 | Wed 7/30/25
5521 | 827 | Future Task |  |  | D667 | Stacey Terry | Create | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Create | 6 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 1 | 828 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5522 | 828 | Future Task |  |  | D667 | Stacey Terry | Submit | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Submit | 0 hrs | 0 days | Fri 4/18/25 | Fri 4/18/25 | 827 | 829 |  | Stacey Terry,Joy Schneider
5523 | 829 | Future Task |  |  | D667 | Stacey Terry | Review | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Collaborative Review | 8 hrs | 10 days | Mon 4/21/25 | Fri 5/2/25 | 828 | 830 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5524 | 830 | Future Task |  |  | D667 | Stacey Terry | Approve | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Approve | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 829 | 831 |  | Jimmy Cox
6697 | 831 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Confirm Mock Go-Live Dry Run #1 Execution Readiness | 3 hrs | 5 days | Mon 6/2/25 | Fri 6/6/25 | 830563 | 832 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6698 | 832 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Execute Mock Go-Live Dry Run #1 | 6 hrs | 10 days | Mon 6/9/25 | Fri 6/20/25 | 831 | 833 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6699 | 833 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Document Mock Go-Live Dry Run Results #1 | 6 hrs | 5 days | Mon 6/23/25 | Fri 6/27/25 | 832 | 834 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6700 | 834 | Future Task |  |  | D667 | Stacey Terry | Create | D667 - Create Mock Go-Live Dry Run #1 Summary Document | 6 hrs | 5 days | Mon 6/30/25 | Mon 7/7/25 | 833 | 835 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5525 | 835 | Future Task |  |  | D667 | Stacey Terry | Submit | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Draft Submission | 0 hrs | 0 days | Mon 7/7/25 | Mon 7/7/25 | 834 | 836 |  | Stacey Terry,Joy Schneider
5526 | 836 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Pre-Submission Collaborative Review | 28 hrs | 5 days | Tue 7/8/25 | Mon 7/14/25 | 835 | 837 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5527 | 837 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Style Guide Review | 1 hr | 1 day | Tue 7/15/25 | Tue 7/15/25 | 836 | 838 |  | Dusti Kincl
5528 | 838 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Final Collaborative Review | 28 hrs | 5 days | Wed 7/16/25 | Tue 7/22/25 | 837 | 839 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5529 | 839 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Accenture QC | 4 hrs | 2 days | Wed 7/23/25 | Thu 7/24/25 | 838 | 840 |  | Joy Schneider
5530 | 840 | Future Task |  |  | D667 | Stacey Terry | Submit | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Submit | 0 hrs | 0 days | Thu 7/24/25 | Thu 7/24/25 | 839 | 841 |  | Joy Schneider
5531 | 841 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Department QC | 4 hrs | 1 day | Fri 7/25/25 | Fri 7/25/25 | 840 | 842 |  | Tommy Werner,Gabriela Gibson
5532 | 842 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Contract Manager Review | 8 hrs | 3 days | Mon 7/28/25 | Wed 7/30/25 | 841 | 843 |  | Sean Buchanan
5533 | 843 | Future Task |  |  | D667 | Stacey Terry | Accept | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Accept | 0 hrs | 0 days | Wed 7/30/25 | Wed 7/30/25 | 842 | 1259 | 2025-07-01 | Sean Buchanan
5061 | 844 | Future Task |  |  | D669 | Stacey Terry |  | D669 - Support of UAT Segment II | 132 hrs | 97 days | Mon 4/14/25 | Thu 8/28/25 |  |  |  |  | RW - Agencies in UAT | NK
5062 | 845 | Future Task |  |  | D669 | Stacey Terry | Create | DED D669 - Support of UAT Segment II - Create | 2 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 1 | 846 |  | Stacey Terry,Mary Punty
5063 | 846 | Future Task |  |  | D669 | Stacey Terry | Submit | DED D669 - Support of UAT Segment II - Submit | 0 hrs | 0 days | Fri 4/25/25 | Fri 4/25/25 | 845 | 847 |  | Stacey Terry,Joy Schneider
5064 | 847 | Future Task |  |  | D669 | Stacey Terry | Review | DED D669 - Support of UAT Segment II - Collaborative Review | 12 hrs | 10 days | Mon 4/28/25 | Fri 5/9/25 | 846 | 848 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5065 | 848 | Future Task |  |  | D669 | Stacey Terry | Approve | DED D669 - Support of UAT Segment II - Approve | 0 hrs | 0 days | Fri 5/9/25 | Fri 5/9/25 | 847 | 849FS+29 days |  | Jimmy Cox
5075 | 849 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Identify UAT support resources for UAT Segment 2 | 6 hrs | 5 days | Mon 6/23/25 | Fri 6/27/25 | 848FS+29 days | 850 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5076 | 850 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Participate in UAT sessions for UAT Segment 2 | 6 hrs | 23 days | Mon 6/30/25 | Thu 7/31/25 | 849 | 851SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp | This should start when Segment 1 support ends, not after the segment 1 deliverable is accepted | AR
5077 | 851 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Support resolution of UAT issues for UAT Segment 2 | 7 hrs | 23 days | Mon 6/30/25 | Thu 7/31/25 | 850SS | 852FS-4 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
5078 | 852 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Confirm requirements traceability for UAT Segment 2 | 21 hrs | 7 days | Mon 7/28/25 | Tue 8/5/25 | 851FS-4 days | 853SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5079 | 853 | Future Task |  |  | D669 | Stacey Terry | Create | D669 - Create UAT Segment 2 Summary Document | 21 hrs | 7 days | Mon 7/28/25 | Tue 8/5/25 | 852SS | 854 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5066 | 854 | Future Task |  |  | D669 | Stacey Terry | Submit | DEL D669 - Support of UAT Segment II - Draft Submission | 0 hrs | 0 days | Tue 8/5/25 | Tue 8/5/25 | 853 | 855 |  | Stacey Terry,Joy Schneider
5067 | 855 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Wed 8/6/25 | Tue 8/12/25 | 854 | 856 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5068 | 856 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Style Guide Review | 1 hr | 1 day | Wed 8/13/25 | Wed 8/13/25 | 855 | 857 |  | Dusti Kincl
5069 | 857 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Final Collaborative Review | 20 hrs | 5 days | Thu 8/14/25 | Wed 8/20/25 | 856 | 858 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5070 | 858 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Accenture QC | 4 hrs | 2 days | Thu 8/21/25 | Fri 8/22/25 | 857 | 859 |  | Joy Schneider
5071 | 859 | Future Task |  |  | D669 | Stacey Terry | Submit | DEL D669 - Support of UAT Segment II - Submit | 0 hrs | 0 days | Fri 8/22/25 | Fri 8/22/25 | 858 | 860 |  | Joy Schneider
5072 | 860 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Department QC | 4 hrs | 1 day | Mon 8/25/25 | Mon 8/25/25 | 859 | 861 |  | Tommy Werner,Gabriela Gibson
5073 | 861 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Contract Manager Review | 8 hrs | 3 days | Tue 8/26/25 | Thu 8/28/25 | 860 | 862 |  | Sean Buchanan
5074 | 862 | Future Task |  |  | D669 | Stacey Terry | Accept | DEL D669 - Support of UAT Segment II - Accept | 0 hrs | 0 days | Thu 8/28/25 | Thu 8/28/25 | 861 |  | 2025-08-01 | Sean Buchanan
4843 | 863 | Future Task |  |  | D670 | Stacey Terry |  | D670 - Completion of Payroll Parallel Testing | 254 hrs | 133 days | Mon 2/24/25 | Fri 8/29/25
4844 | 864 | Future Task |  |  | D670 | Stacey Terry | Create | DED D670 - Completion of Payroll Parallel Testing - Create | 16 hrs | 10 days | Mon 2/24/25 | Fri 3/7/25 | 741FS-37 days | 865 |  | Stacey Terry,Mary Punty
4845 | 865 | Future Task |  |  | D670 | Stacey Terry | Submit | DED D670 - Completion of Payroll Parallel Testing - Submit | 0 hrs | 0 days | Fri 3/7/25 | Fri 3/7/25 | 864 | 866 |  | Stacey Terry,Joy Schneider
4846 | 866 | Future Task |  |  | D670 | Stacey Terry | Review | DED D670 - Completion of Payroll Parallel Testing - Collaborative Review | 24 hrs | 10 days | Mon 3/10/25 | Fri 3/21/25 | 865 | 867 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4847 | 867 | Future Task |  |  | D670 | Stacey Terry | Approve | DED D670 - Completion of Payroll Parallel Testing - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 866 | 868 |  | Jimmy Cox
4955 | 868 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Create Work Unit Tracker for Payroll Parallel Test Execution | 40 hrs | 10 days | Mon 3/24/25 | Fri 4/4/25 | 867 | 869 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty
4956 | 869 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Review, Update and confirm Work Unit Tracker for Payroll Parallel Test Execution | 20 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 868 | 870 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Jennifer Peddicord
4957 | 870 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Confirm Payroll Parallel Test Environment Readiness | 20 hrs | 5 days | Mon 4/21/25 | Fri 4/25/25 | 869 | 871 |  | Manojkumar Gurjar,Jarad Hermann
4958 | 871 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Conduct Parallel Payroll Test Kick Off Meeting | 12 hrs | 5 days | Mon 4/28/25 | Fri 5/2/25 | 870 | 872 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Jennifer Peddicord
4959 | 872 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Execute Parallel Payroll Testing | 5 hrs | 60 days | Mon 5/5/25 | Tue 7/29/25 | 871 | 873,874FS-4 days |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
4960 | 873 | Future Task |  |  | D670 | Stacey Terry | Milestone | D670 - Milestone: Payroll Parallel Test Execution Complete | 0 hrs | 0 days | Tue 7/29/25 | Tue 7/29/25 | 872 | 877 |  | Stacey Terry | Why are these Milestones? What is the rationale or downstream benefit to including as Milestones? (Would like to have some common expectation for when something should be a Milestone.) | Angie
4961 | 874 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Conduct Payroll Parallel Test Exit Criteria Review Meeting | 10 hrs | 10 days | Thu 7/24/25 | Wed 8/6/25 | 872FS-4 days | 875SS,876SS,877 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
4962 | 875 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Confirm requirements traceability for Payroll Parallel test | 20 hrs | 10 days | Thu 7/24/25 | Wed 8/6/25 | 874SS | 877 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty
4963 | 876 | Future Task |  |  | D670 | Stacey Terry | Create | D670 - Create Completion of Payroll Parallel Test Summary Document | 30 hrs | 10 days | Thu 7/24/25 | Wed 8/6/25 | 874SS | 877 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4848 | 877 | Future Task |  |  | D670 | Stacey Terry | Submit | DEL D670 - Completion of Payroll Parallel Testing - Draft Submission | 0 hrs | 0 days | Wed 8/6/25 | Wed 8/6/25 | 873874876875 | 878 |  | Stacey Terry,Joy Schneider
4849 | 878 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Pre-Submission Collaborative Review | 20 hrs | 5 days | Thu 8/7/25 | Wed 8/13/25 | 877 | 879 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4850 | 879 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Style Guide Review | 1 hr | 1 day | Thu 8/14/25 | Thu 8/14/25 | 878 | 880 |  | Dusti Kincl
4851 | 880 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Final Collaborative Review | 20 hrs | 5 days | Fri 8/15/25 | Thu 8/21/25 | 879 | 881 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4852 | 881 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Accenture QC | 4 hrs | 2 days | Fri 8/22/25 | Mon 8/25/25 | 880 | 882 |  | Joy Schneider
4853 | 882 | Future Task |  |  | D670 | Stacey Terry | Submit | DEL D670 - Completion of Payroll Parallel Testing - Submit | 0 hrs | 0 days | Mon 8/25/25 | Mon 8/25/25 | 881 | 883 |  | Joy Schneider
4854 | 883 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Department QC | 4 hrs | 1 day | Tue 8/26/25 | Tue 8/26/25 | 882 | 884 |  | Tommy Werner,Gabriela Gibson
4855 | 884 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Contract Manager Review | 8 hrs | 3 days | Wed 8/27/25 | Fri 8/29/25 | 883 | 885 |  | Sean Buchanan
4856 | 885 | Future Task |  |  | D670 | Stacey Terry | Accept | DEL D670 - Completion of Payroll Parallel Testing - Accept | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 884 |  | 2025-08-01 | Sean Buchanan
4857 | 886 | Future Task |  |  | D671 | Manojkumar Gurjar |  | D671 - Completion of Interface Testing Segment II | 291 hrs | 180 days | Mon 2/3/25 | Wed 10/15/25
4858 | 887 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | DED D671 - Completion of Interface Testing Segment II - Create | 6 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1 | 888 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4859 | 888 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DED D671 - Completion of Interface Testing Segment II - Submit | 0 hrs | 0 days | Fri 2/14/25 | Fri 2/14/25 | 887 | 889 |  | Manojkumar Gurjar,Joy Schneider
4860 | 889 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DED D671 - Completion of Interface Testing Segment II - Collaborative Review | 8 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 888 | 890 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4861 | 890 | Future Task |  |  | D671 | Manojkumar Gurjar | Approve | DED D671 - Completion of Interface Testing Segment II - Approve | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 889 | 891FS+20 days |  | Jimmy Cox
4964 | 891 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Create Interface Testing Segment 2 Execution Work Unit Tracker | 6 hrs | 4 days | Mon 3/31/25 | Thu 4/3/25 | 890FS+20 days | 892 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4965 | 892 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Review/Confirm Interface Testing Segment 2 Execution Work Unit Tracker | 6 hrs | 4 days | Fri 4/4/25 | Wed 4/9/25 | 891 | 893 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4966 | 893 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Conduct Interface Testing Segment 2 Readiness Review Meeting | 15 hrs | 5 days | Thu 4/10/25 | Wed 4/16/25 | 892 | 894 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4967 | 894 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Conduct Interface Test Kickoff Meeting with Integration Partners | 30 hrs | 5 days | Thu 4/17/25 | Wed 4/23/25 | 893 | 895 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty | RW | NK
4968 | 895 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Confirm Interface Test Environment Readiness | 15 hrs | 5 days | Thu 4/24/25 | Wed 4/30/25 | 894 | 896 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4969 | 896 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Establish Interface Connectivity Segment 2 | 20 hrs | 7 days | Thu 5/1/25 | Fri 5/9/25 | 895 | 897 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4970 | 897 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Execute Interface Testing Segment 2 | 10 hrs | 78 days | Mon 5/12/25 | Fri 8/29/25 | 896 | 898 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4971 | 898 | Future Task |  |  | D671 | Manojkumar Gurjar | Milestone | D671 - Milestone: Interface Testing Segment 2 Complete | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 897 | 899 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty | Why are these Milestones? What is the rationale or downstream benefit to including as Milestones? (Would like to have some common expectation for when something should be a Milestone.) | Angie
4972 | 899 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Conduct Test Exit Criteria Review Meeting | 30 hrs | 5 days | Tue 9/2/25 | Mon 9/8/25 | 898 | 900 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4973 | 900 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Confirm requirements traceability for Interface Testing Segment 2 | 40 hrs | 5 days | Tue 9/9/25 | Mon 9/15/25 | 899 | 901 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4974 | 901 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | D671 - Create Completion of Interface Testing Segment 2 deliverable (D671) | 40 hrs | 5 days | Tue 9/16/25 | Mon 9/22/25 | 900 | 902 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4862 | 902 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DEL D671 - Completion of Interface Testing Segment II - Draft Submission | 0 hrs | 0 days | Mon 9/22/25 | Mon 9/22/25 | 901 | 903 |  | Manojkumar Gurjar,Joy Schneider
4863 | 903 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Pre-Submission Collaborative Review | 24 hrs | 5 days | Tue 9/23/25 | Mon 9/29/25 | 902 | 904 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4864 | 904 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Style Guide Review | 1 hr | 1 day | Tue 9/30/25 | Tue 9/30/25 | 903 | 905 |  | Dusti Kincl
4865 | 905 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Final Collaborative Review | 24 hrs | 5 days | Wed 10/1/25 | Tue 10/7/25 | 904 | 906 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4866 | 906 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Accenture QC | 4 hrs | 2 days | Wed 10/8/25 | Thu 10/9/25 | 905 | 907 |  | Joy Schneider
4867 | 907 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DEL D671 - Completion of Interface Testing Segment II - Submit | 0 hrs | 0 days | Thu 10/9/25 | Thu 10/9/25 | 906 | 908 |  | Joy Schneider
4868 | 908 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Department QC | 4 hrs | 1 day | Fri 10/10/25 | Fri 10/10/25 | 907 | 909 |  | Tommy Werner,Gabriela Gibson
4869 | 909 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Contract Manager Review | 8 hrs | 3 days | Mon 10/13/25 | Wed 10/15/25 | 908 | 910 |  | Sean Buchanan
4870 | 910 | Future Task |  |  | D671 | Manojkumar Gurjar | Accept | DEL D671 - Completion of Interface Testing Segment II - Accept | 0 hrs | 0 days | Wed 10/15/25 | Wed 10/15/25 | 909 |  | 2025-10-01 | Sean Buchanan
4871 | 911 | Future Task |  |  | D672 | Stacey Terry |  | D672 - Support of UAT Segment III | 122 hrs | 91 days | Mon 7/21/25 | Wed 11/26/25 |  |  |  |  | RW - Agencies in UAT | NK
4872 | 912 | Future Task |  |  | D672 | Stacey Terry | Create | DED D672 - Support of UAT Segment III - Create | 16 hrs | 10 days | Mon 7/21/25 | Fri 8/1/25 | 1 | 913 |  | Stacey Terry,Mary Punty
4873 | 913 | Future Task |  |  | D672 | Stacey Terry | Submit | DED D672 - Support of UAT Segment III - Submit | 0 hrs | 0 days | Fri 8/1/25 | Fri 8/1/25 | 912 | 914 |  | Stacey Terry,Joy Schneider
4874 | 914 | Future Task |  |  | D672 | Stacey Terry | Review | DED D672 - Support of UAT Segment III - Collaborative Review | 24 hrs | 10 days | Mon 8/4/25 | Fri 8/15/25 | 913 | 915 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4875 | 915 | Future Task |  |  | D672 | Stacey Terry | Approve | DED D672 - Support of UAT Segment III - Approve | 0 hrs | 0 days | Fri 8/15/25 | Fri 8/15/25 | 914 | 916FS+24 days |  | Jimmy Cox
4975 | 916 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Identify UAT support resources for UAT Segment 3 | 12 hrs | 7 days | Mon 9/22/25 | Tue 9/30/25 | 915FS+24 days | 917 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4976 | 917 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Participate in UAT sessions for UAT Segment 3 | 6 hrs | 21 days | Wed 10/1/25 | Wed 10/29/25 | 916 | 918SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp | There is a gap between the Segment II "support" (Unique ID 5076) above and this date. They should be continguous. | AR
4977 | 918 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Support resolution of UAT issues for UAT Segment 3 | 7 hrs | 21 days | Wed 10/1/25 | Wed 10/29/25 | 917SS | 919FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
4978 | 919 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Confirm requirements traceability for UAT Segment 3 | 3 hrs | 7 days | Thu 10/23/25 | Fri 10/31/25 | 918FS-5 days | 920SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4979 | 920 | Future Task |  |  | D672 | Stacey Terry | Create | D672 - Create UAT Segment 3 Summary Document | 3 hrs | 7 days | Thu 10/23/25 | Fri 10/31/25 | 919SS | 921 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4876 | 921 | Future Task |  |  | D672 | Stacey Terry | Submit | DEL D672 - Support of UAT Segment III - Draft Submission | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 920 | 922 |  | Stacey Terry,Joy Schneider
4877 | 922 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 11/3/25 | Fri 11/7/25 | 921 | 923 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4878 | 923 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Style Guide Review | 1 hr | 1 day | Mon 11/10/25 | Mon 11/10/25 | 922 | 924 |  | Dusti Kincl
4879 | 924 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Final Collaborative Review | 20 hrs | 5 days | Wed 11/12/25 | Tue 11/18/25 | 923 | 925 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4880 | 925 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Accenture QC | 4 hrs | 2 days | Wed 11/19/25 | Thu 11/20/25 | 924 | 926 |  | Francisca Li
4881 | 926 | Future Task |  |  | D672 | Stacey Terry | Submit | DEL D672 - Support of UAT Segment III - Submit | 0 hrs | 0 days | Thu 11/20/25 | Thu 11/20/25 | 925 | 927 |  | Joy Schneider
4882 | 927 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Department QC | 4 hrs | 1 day | Fri 11/21/25 | Fri 11/21/25 | 926 | 928 |  | Tommy Werner,Gabriela Gibson
4883 | 928 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Contract Manager Review | 2 hrs | 3 days | Mon 11/24/25 | Wed 11/26/25 | 927 | 929 |  | Sean Buchanan
4884 | 929 | Future Task |  |  | D672 | Stacey Terry | Accept | DEL D672 - Support of UAT Segment III - Accept | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 928 |  | 2025-11-01 | Sean Buchanan
4885 | 930 | Future Task |  |  | D673 | Stacey Terry |  | D673 - Completion of Mock Go-Lives (Dry Run #2) | 223 hrs | 86 days | Mon 7/7/25 | Tue 11/4/25
4886 | 931 | Future Task |  |  | D673 | Stacey Terry | Create | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Create | 24 hrs | 10 days | Mon 7/7/25 | Fri 7/18/25 | 1 | 932 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4887 | 932 | Future Task |  |  | D673 | Stacey Terry | Submit | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Submit | 0 hrs | 0 days | Fri 7/18/25 | Fri 7/18/25 | 931 | 933 |  | Stacey Terry,Joy Schneider
4888 | 933 | Future Task |  |  | D673 | Stacey Terry | Review | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Collaborative Review | 32 hrs | 10 days | Mon 7/21/25 | Fri 8/1/25 | 932 | 934 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4889 | 934 | Future Task |  |  | D673 | Stacey Terry | Approve | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Approve | 0 hrs | 0 days | Fri 8/1/25 | Fri 8/1/25 | 933 | 935FS+20 days |  | Jimmy Cox
4980 | 935 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Confirm Mock Go-Live Dry Run #2 Execution Readiness | 24 hrs | 4 days | Tue 9/2/25 | Fri 9/5/25 | 934FS+20 days | 936 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4981 | 936 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Execute Mock Go-Live Dry Run #2 | 20 hrs | 10 days | Mon 9/8/25 | Fri 9/19/25 | 935 | 937 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4982 | 937 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Document Mock Go-Live Dry Run Results #2 | 30 hrs | 5 days | Mon 9/22/25 | Fri 9/26/25 | 936 | 938 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4983 | 938 | Future Task |  |  | D673 | Stacey Terry | Create | D673 - Create Mock Go-Live Dry Run #2 Summary Document | 20 hrs | 10 days | Mon 9/29/25 | Fri 10/10/25 | 937 | 939 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4890 | 939 | Future Task |  |  | D673 | Stacey Terry | Submit | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Draft Submission | 0 hrs | 0 days | Fri 10/10/25 | Fri 10/10/25 | 938 | 940 |  | Stacey Terry,Joy Schneider
4891 | 940 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Pre-Submission Collaborative Review | 28 hrs | 5 days | Mon 10/13/25 | Fri 10/17/25 | 939 | 941 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4892 | 941 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Style Guide Review | 1 hr | 1 day | Mon 10/20/25 | Mon 10/20/25 | 940 | 942 |  | Dusti Kincl
4893 | 942 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Final Collaborative Review | 28 hrs | 5 days | Tue 10/21/25 | Mon 10/27/25 | 941 | 943 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4894 | 943 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Accenture QC | 4 hrs | 2 days | Tue 10/28/25 | Wed 10/29/25 | 942 | 944 |  | Joy Schneider
4895 | 944 | Future Task |  |  | D673 | Stacey Terry | Submit | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Submit | 0 hrs | 0 days | Wed 10/29/25 | Wed 10/29/25 | 943 | 945 |  | Joy Schneider
4896 | 945 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Department QC | 4 hrs | 1 day | Thu 10/30/25 | Thu 10/30/25 | 944 | 946 |  | Tommy Werner,Gabriela Gibson
4897 | 946 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Contract Manager Review | 8 hrs | 3 days | Fri 10/31/25 | Tue 11/4/25 | 945 | 947 |  | Sean Buchanan
4898 | 947 | Future Task |  |  | D673 | Stacey Terry | Accept | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Accept | 0 hrs | 0 days | Tue 11/4/25 | Tue 11/4/25 | 946 | 1259 | 2025-11-01 | Sean Buchanan
4899 | 948 | Future Task |  |  | D674 | Jarad Hermann |  | D674 - Completion of Penetration Testing | 100 hrs | 164 days | Mon 4/7/25 | Wed 11/26/25
4900 | 949 | Future Task |  |  | D674 | Jarad Hermann | Create | DED D674 - Completion of Penetration Testing - Create | 2 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 1203FS+10 days,1238FS+10 days | 950 | Note: should be in version we go live with | Jarad Hermann,Mary Punty
4901 | 950 | Future Task |  |  | D674 | Jarad Hermann | Submit | DED D674 - Completion of Penetration Testing - Submit | 0 hrs | 0 days | Fri 4/18/25 | Fri 4/18/25 | 949 | 951 |  | Jarad Hermann,Joy Schneider
4902 | 951 | Future Task |  |  | D674 | Jarad Hermann | Review | DED D674 - Completion of Penetration Testing - Collaborative Review | 5 hrs | 10 days | Mon 4/21/25 | Fri 5/2/25 | 950 | 952 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4903 | 952 | Future Task |  |  | D674 | Jarad Hermann | Approve | DED D674 - Completion of Penetration Testing - Approve | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 951 | 953FS+19 days |  | Jimmy Cox
4984 | 953 | Future Task |  |  | D674 | Jarad Hermann | Create | D674 - Execute/Complete Penetration Test | 10 hrs | 64 days | Mon 6/2/25 | Fri 8/29/25 | 952FS+19 days | 954 |  | Jarad Hermann,Bryan Sohayda
4985 | 954 | Future Task |  |  | D674 | Jarad Hermann | Create | D674 - Review Penetration Test Outcome | 10 hrs | 20 days | Tue 9/2/25 | Mon 9/29/25 | 953 | 955SS |  | Jarad Hermann,Bryan Sohayda
4986 | 955 | Future Task |  |  | D674 | Jarad Hermann | Create | D674 - Remediate Penetration Test | 10 hrs | 44 days | Tue 9/2/25 | Fri 10/31/25 | 954SS | 956SS |  | Jarad Hermann,Bryan Sohayda
4987 | 956 | Future Task |  |  | D674 | Jarad Hermann | Create | D674 - Create Final Pen Testing Results/Remediation Summary Report | 20 hrs | 44 days | Tue 9/2/25 | Fri 10/31/25 | 955SS | 957 |  | Jarad Hermann,Bryan Sohayda
4904 | 957 | Future Task |  |  | D674 | Jarad Hermann | Submit | DEL D674 - Completion of Penetration Testing - Draft Submission | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 956 | 958 |  | Jarad Hermann,Joy Schneider
4905 | 958 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 11/3/25 | Fri 11/7/25 | 957 | 959 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4906 | 959 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Style Guide Review | 1 hr | 1 day | Mon 11/10/25 | Mon 11/10/25 | 958 | 960 |  | Dusti Kincl
4907 | 960 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Final Collaborative Review | 16 hrs | 5 days | Wed 11/12/25 | Tue 11/18/25 | 959 | 961 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4908 | 961 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Accenture QC | 4 hrs | 2 days | Wed 11/19/25 | Thu 11/20/25 | 960 | 962 |  | Joy Schneider
4909 | 962 | Future Task |  |  | D674 | Jarad Hermann | Submit | DEL D674 - Completion of Penetration Testing - Submit | 0 hrs | 0 days | Thu 11/20/25 | Thu 11/20/25 | 961 | 963 |  | Joy Schneider
4910 | 963 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Department QC | 4 hrs | 1 day | Fri 11/21/25 | Fri 11/21/25 | 962 | 964 |  | Tommy Werner,Gabriela Gibson
4911 | 964 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Contract Manager Review | 2 hrs | 3 days | Mon 11/24/25 | Wed 11/26/25 | 963 | 965 |  | Sean Buchanan
4912 | 965 | Future Task |  |  | D674 | Jarad Hermann | Accept | DEL D674 - Completion of Penetration Testing - Accept | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 964 | 1259 | 2025-11-01 | Sean Buchanan
4913 | 966 | Future Task |  |  | D675 | Jarad Hermann |  | D675 - Completion of Performance Testing | 180 hrs | 159 days | Mon 4/14/25 | Wed 11/26/25
4914 | 967 | Future Task |  |  | D675 | Jarad Hermann | Create | DED D675 - Completion of Performance Testing - Create | 2 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 1191FS-28 days,1227FS-28 days | 968 |  | Jarad Hermann,Mary Punty
4915 | 968 | Future Task |  |  | D675 | Jarad Hermann | Submit | DED D675 - Completion of Performance Testing - Submit | 0 hrs | 0 days | Fri 4/25/25 | Fri 4/25/25 | 967 | 969 |  | Jarad Hermann,Joy Schneider
4916 | 969 | Future Task |  |  | D675 | Jarad Hermann | Review | DED D675 - Completion of Performance Testing - Collaborative Review | 5 hrs | 10 days | Mon 4/28/25 | Fri 5/9/25 | 968 | 970 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4917 | 970 | Future Task |  |  | D675 | Jarad Hermann | Approve | DED D675 - Completion of Performance Testing - Approve | 0 hrs | 0 days | Fri 5/9/25 | Fri 5/9/25 | 969 | 971 |  | Jimmy Cox
4988 | 971 | Future Task |  |  | D675 | Jarad Hermann | Create | D675 - Execute Performance Testing | 4 hrs | 108 days | Mon 6/2/25 | Fri 10/31/25 | 970565 | 972FS-10 days,975 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4989 | 972 | Future Task |  |  | D675 | Jarad Hermann | Create | D675 - Create Completion of Performance Testing Summary Document | 40 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 971FS-10 days | 973SS,974SS,975 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4990 | 973 | Future Task |  |  | D675 | Jarad Hermann | Create | D675 - Conduct Performance Testing Exit Criteria Review Meeting | 40 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 972SS | 975 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4991 | 974 | Future Task |  |  | D675 | Jarad Hermann | Create | D675 - Confirm requirements traceability for Performance Testing | 40 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 972SS | 975 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4918 | 975 | Future Task |  |  | D675 | Jarad Hermann | Submit | DEL D675 - Completion of Performance Testing - Draft Submission | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 974971972973 | 976 |  | Jarad Hermann,Joy Schneider
4919 | 976 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 11/3/25 | Fri 11/7/25 | 975 | 977 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4920 | 977 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Style Guide Review | 1 hr | 1 day | Mon 11/10/25 | Mon 11/10/25 | 976 | 978 |  | Dusti Kincl
4921 | 978 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Final Collaborative Review | 16 hrs | 5 days | Wed 11/12/25 | Tue 11/18/25 | 977 | 979 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4922 | 979 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Accenture QC | 4 hrs | 2 days | Wed 11/19/25 | Thu 11/20/25 | 978 | 980 |  | Joy Schneider
4923 | 980 | Future Task |  |  | D675 | Jarad Hermann | Submit | DEL D675 - Completion of Performance Testing - Submit | 0 hrs | 0 days | Thu 11/20/25 | Thu 11/20/25 | 979 | 981 |  | Joy Schneider
4924 | 981 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Department QC | 4 hrs | 1 day | Fri 11/21/25 | Fri 11/21/25 | 980 | 982 |  | Tommy Werner,Gabriela Gibson
4925 | 982 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Contract Manager Review | 8 hrs | 3 days | Mon 11/24/25 | Wed 11/26/25 | 981 | 983 |  | Sean Buchanan
4926 | 983 | Future Task |  |  | D675 | Jarad Hermann | Accept | DEL D675 - Completion of Performance Testing - Accept | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 982 | 1259 | 2025-11-01 | Sean Buchanan
4927 | 984 | Future Task |  |  | D676 | Jarad Hermann |  | D676 - Completion of Disaster Recovery Testing | 158 hrs | 135 days | Mon 2/3/25 | Tue 8/12/25
4928 | 985 | Future Task |  |  | D676 | Jarad Hermann | Create | DED D676 - Completion of Disaster Recovery Testing - Create | 8 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1215FS-35 days,1177FS-35 days,1164 | 986 |  | Jarad Hermann,Mary Punty
4929 | 986 | Future Task |  |  | D676 | Jarad Hermann | Submit | DED D676 - Completion of Disaster Recovery Testing - Submit | 0 hrs | 0 days | Fri 2/14/25 | Fri 2/14/25 | 985 | 987 |  | Jarad Hermann,Joy Schneider
4930 | 987 | Future Task |  |  | D676 | Jarad Hermann | Review | DED D676 - Completion of Disaster Recovery Testing - Collaborative Review | 20 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 986 | 988 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4931 | 988 | Future Task |  |  | D676 | Jarad Hermann | Approve | DED D676 - Completion of Disaster Recovery Testing - Approve | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 987 | 989 |  | Jimmy Cox
4992 | 989 | Future Task |  |  | D676 | Jarad Hermann | Create | D676 - Execute Disaster Recovery Testing | 3 hrs | 64 days | Tue 4/1/25 | Mon 6/30/25 | 988,567FS+1 day | 990 |  | Jarad Hermann,Vivek Sharma,Stacey Terry
4993 | 990 | Future Task |  |  | D676 | Jarad Hermann | Create | D676 - Create Completion of Disaster Recovery Testing Summary Document | 26 hrs | 13 days | Tue 7/1/25 | Fri 7/18/25 | 989 | 991SS,992SS,993 |  | Jarad Hermann,Vivek Sharma
4994 | 991 | Future Task |  |  | D676 | Jarad Hermann | Create | D676 - Conduct Disaster Recovery Testing Exit Criteria Review Meeting | 26 hrs | 13 days | Tue 7/1/25 | Fri 7/18/25 | 990SS | 993 |  | Jarad Hermann,Vivek Sharma
4995 | 992 | Future Task |  |  | D676 | Jarad Hermann | Create | D676 - Confirm requirements traceability for Disaster Recovery Testing | 26 hrs | 13 days | Tue 7/1/25 | Fri 7/18/25 | 990SS | 993 |  | Jarad Hermann,Vivek Sharma
4932 | 993 | Future Task |  |  | D676 | Jarad Hermann | Submit | DEL D676 - Completion of Disaster Recovery Testing - Draft Submission | 0 hrs | 0 days | Fri 7/18/25 | Fri 7/18/25 | 992990991 | 994 |  | Jarad Hermann,Joy Schneider
4933 | 994 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 7/21/25 | Fri 7/25/25 | 993 | 995 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4934 | 995 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Style Guide Review | 1 hr | 1 day | Mon 7/28/25 | Mon 7/28/25 | 994 | 996 |  | Dusti Kincl
4935 | 996 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Final Collaborative Review | 16 hrs | 5 days | Tue 7/29/25 | Mon 8/4/25 | 995 | 997 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4936 | 997 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Accenture QC | 4 hrs | 2 days | Tue 8/5/25 | Wed 8/6/25 | 996 | 998 |  | Joy Schneider
4937 | 998 | Future Task |  |  | D676 | Jarad Hermann | Submit | DEL D676 - Completion of Disaster Recovery Testing - Submit | 0 hrs | 0 days | Wed 8/6/25 | Wed 8/6/25 | 997 | 999 |  | Joy Schneider
4938 | 999 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Department QC | 4 hrs | 1 day | Thu 8/7/25 | Thu 8/7/25 | 998 | 1000 |  | Tommy Werner,Jenifer Hartsfield
4939 | 1000 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Contract Manager Review | 8 hrs | 3 days | Fri 8/8/25 | Tue 8/12/25 | 999 | 1001 |  | Sean Buchanan
4940 | 1001 | Future Task |  |  | D676 | Jarad Hermann | Accept | DEL D676 - Completion of Disaster Recovery Testing - Accept | 0 hrs | 0 days | Tue 8/12/25 | Tue 8/12/25 | 1000 | 1259 | 2025-11-01 | Sean Buchanan
4941 | 1002 | Future Task |  |  | D677 | Stacey Terry |  | D677 - Completion of Mock Go-Lives (Dry Run #3) | 229 hrs | 76 days | Mon 8/25/25 | Fri 12/12/25
4942 | 1003 | Future Task |  |  | D677 | Stacey Terry | Create | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Create | 24 hrs | 10 days | Mon 8/25/25 | Mon 9/8/25 | 1 | 1004 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4943 | 1004 | Future Task |  |  | D677 | Stacey Terry | Submit | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Submit | 0 hrs | 0 days | Mon 9/8/25 | Mon 9/8/25 | 1003 | 1005 |  | Stacey Terry,Joy Schneider
4944 | 1005 | Future Task |  |  | D677 | Stacey Terry | Review | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Collaborative Review | 32 hrs | 10 days | Tue 9/9/25 | Mon 9/22/25 | 1004 | 1006 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4945 | 1006 | Future Task |  |  | D677 | Stacey Terry | Approve | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Approve | 0 hrs | 0 days | Mon 9/22/25 | Mon 9/22/25 | 1005 | 1007FS+24 days |  | Jimmy Cox
5000 | 1007 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Confirm Mock Go-Live Dry Run #3 Readiness | 40 hrs | 4 days | Mon 10/27/25 | Thu 10/30/25 | 1006FS+24 days | 1008FS+1 day |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5001 | 1008 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Execute Mock Go-Live Dry Run #3 | 10 hrs | 10 days | Mon 11/3/25 | Mon 11/17/25 | 1007FS+1 day | 1009 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5002 | 1009 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Document Mock Go-Live Dry Run Results #3 | 30 hrs | 3 days | Tue 11/18/25 | Thu 11/20/25 | 1008 | 1010 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5003 | 1010 | Future Task |  |  | D677 | Stacey Terry | Create | D677 - Create Mock Go-Live Dry Run #3 Summary Document | 20 hrs | 2 days | Fri 11/21/25 | Mon 11/24/25 | 1009 | 1011 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
4946 | 1011 | Future Task |  |  | D677 | Stacey Terry | Submit | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Draft Submission | 0 hrs | 0 days | Mon 11/24/25 | Mon 11/24/25 | 1010 | 1012 |  | Stacey Terry,Joy Schneider
4947 | 1012 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Pre-Submission Collaborative Review | 28 hrs | 3 days | Tue 11/25/25 | Mon 12/1/25 | 1011 | 1013 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4948 | 1013 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Style Guide Review | 1 hr | 1 day | Tue 12/2/25 | Tue 12/2/25 | 1012 | 1014 |  | Dusti Kincl
4949 | 1014 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Final Collaborative Review | 28 hrs | 3 days | Wed 12/3/25 | Fri 12/5/25 | 1013 | 1015 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4950 | 1015 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Accenture QC | 4 hrs | 1 day | Mon 12/8/25 | Mon 12/8/25 | 1014 | 1016 |  | Joy Schneider
4951 | 1016 | Future Task |  |  | D677 | Stacey Terry | Submit | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Submit | 0 hrs | 0 days | Mon 12/8/25 | Mon 12/8/25 | 1015 | 1017 |  | Joy Schneider
4952 | 1017 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Department QC | 4 hrs | 1 day | Tue 12/9/25 | Tue 12/9/25 | 1016 | 1018 |  | Tommy Werner,Gabriela Gibson
4953 | 1018 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Contract Manager Review | 8 hrs | 3 days | Wed 12/10/25 | Fri 12/12/25 | 1017 | 1019 |  | Sean Buchanan
4954 | 1019 | Future Task |  |  | D677 | Stacey Terry | Accept | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Accept | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 1018 | 1259 | 2025-12-01 | Sean Buchanan
5080 | 1020 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | WP406 - Mock Conversion Testing Plan | 180 hrs | 114 days | Mon 2/12/24 | Mon 7/22/24 |  |  |  |  | RW? Is this something that is shared with agencies? | NK
5081 | 1021 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WPED WP406 - Mock Conversion Testing Plan - Create | 24 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 1 | 1022 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5082 | 1022 | Future Task |  |  | WP406 | Manojkumar Gurjar | Submit | WPED WP406 - Mock Conversion Testing Plan - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 1021 | 1023 |  | Joy Schneider,Manojkumar Gurjar
5083 | 1023 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WPED WP406 - Mock Conversion Testing Plan - Review | 28 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 1022 | 1024 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5084 | 1024 | Future Task |  |  | WP406 | Manojkumar Gurjar | Approve | WPED WP406 - Mock Conversion Testing Plan - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 1023 | 1025FS+20 days |  | Jimmy Cox
5116 | 1025 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WP406 - Define Mock Conversion Testing Approach | 20 hrs | 10 days | Mon 4/8/24 | Fri 4/19/24 | 1024FS+20 days | 1026 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5117 | 1026 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WP406 - Identify Resources for Mock Conversion Testing | 20 hrs | 10 days | Mon 4/22/24 | Fri 5/3/24 | 1025 | 1027 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5118 | 1027 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WP406 - Define Test Cycles and Scenarios | 20 hrs | 24 days | Mon 5/6/24 | Fri 6/7/24 | 1026 | 1028 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5119 | 1028 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WP406 - Define and review Entry/Exit Criteria for Mock Conversion Testing | 20 hrs | 15 days | Mon 6/10/24 | Fri 6/28/24 | 1027 | 1029 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5085 | 1029 | Future Task |  |  | WP406 | Manojkumar Gurjar | Submit | WP WP406 - Mock Conversion Testing Plan - Submit | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 1028 | 1030 |  | Joy Schneider,Manojkumar Gurjar
5086 | 1030 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WP WP406 - Mock Conversion Testing Plan - Collaborative Review & Update | 24 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 1029 | 1031 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5087 | 1031 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WP WP406 - Mock Conversion Testing Plan - Final Review & Edits | 24 hrs | 5 days | Tue 7/16/24 | Mon 7/22/24 | 1030 | 1032 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5088 | 1032 | Future Task |  |  | WP406 | Manojkumar Gurjar | Approve | WP WP406 - Mock Conversion Testing Plan - Approve | 0 hrs | 0 days | Mon 7/22/24 | Mon 7/22/24 | 1031 | 1034FS-45 days,556 | 2024-05-01 | Jimmy Cox
5089 | 1033 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | WP407 - Mock Conversion Scripts | 160 hrs | 67 days | Fri 5/17/24 | Wed 8/21/24
5090 | 1034 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WPED WP407 - Mock Conversion Scripts - Create | 24 hrs | 10 days | Fri 5/17/24 | Fri 5/31/24 | 1032FS-45 days | 1035 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5091 | 1035 | Future Task |  |  | WP407 | Manojkumar Gurjar | Submit | WPED WP407 - Mock Conversion Scripts - Submit | 0 hrs | 0 days | Fri 5/31/24 | Fri 5/31/24 | 1034 | 1036 |  | Joy Schneider,Manojkumar Gurjar
5092 | 1036 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WPED WP407 - Mock Conversion Scripts - Review | 28 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 1035 | 1037 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5093 | 1037 | Future Task |  |  | WP407 | Manojkumar Gurjar | Approve | WPED WP407 - Mock Conversion Scripts - Approve | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 1036 | 1038 |  | Jimmy Cox
5120 | 1038 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WP407 - Create Test Scripts | 20 hrs | 19 days | Mon 6/17/24 | Fri 7/12/24 | 1037 | 1039 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5121 | 1039 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WP407 - Identify System Test Scripts for Mock Conversion Testing | 20 hrs | 8 days | Mon 7/15/24 | Wed 7/24/24 | 1038 | 1040 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5122 | 1040 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WP407 - Review System Test Scripts for Mock Conversion Testing | 20 hrs | 5 days | Thu 7/25/24 | Wed 7/31/24 | 1039 | 1041 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5094 | 1041 | Future Task |  |  | WP407 | Manojkumar Gurjar | Submit | WP WP407 - Mock Conversion Scripts - Submit | 0 hrs | 0 days | Wed 7/31/24 | Wed 7/31/24 | 1040 | 1042 |  | Joy Schneider,Manojkumar Gurjar
5095 | 1042 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WP WP407 - Mock Conversion Scripts - Collaborative Review & Update | 24 hrs | 10 days | Thu 8/1/24 | Wed 8/14/24 | 1041 | 1043 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5096 | 1043 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WP WP407 - Mock Conversion Scripts - Final Review & Edits | 24 hrs | 5 days | Thu 8/15/24 | Wed 8/21/24 | 1042 | 1044 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5097 | 1044 | Future Task |  |  | WP407 | Manojkumar Gurjar | Approve | WP WP407 - Mock Conversion Scripts - Approve | 0 hrs | 0 days | Wed 8/21/24 | Wed 8/21/24 | 1043 | 623FS-47 days | 2024-07-01 | Jimmy Cox
5098 | 1045 | Future Task |  |  | WP408 | Stacey Terry |  | WP408 - System Test Scripts | 188 hrs | 153 days | Mon 2/12/24 | Mon 9/16/24
5099 | 1046 | Future Task |  |  | WP408 | Stacey Terry | Create | WPED WP408 - System Test Scripts - Create | 16 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 1 | 1047 |  | Stacey Terry,Mary Punty
5100 | 1047 | Future Task |  |  | WP408 | Stacey Terry | Submit | WPED WP408 - System Test Scripts - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 1046 | 1048 |  | Joy Schneider,Stacey Terry
5101 | 1048 | Future Task |  |  | WP408 | Stacey Terry | Review | WPED WP408 - System Test Scripts - Review | 12 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 1047 | 1049 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5102 | 1049 | Future Task |  |  | WP408 | Stacey Terry | Approve | WPED WP408 - System Test Scripts - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 1048 | 1050 |  | Jimmy Cox
5123 | 1050 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Create Work Unit Tracker for System Test Preparation | 20 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 1049 | 1051 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5124 | 1051 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Review, update, & confirm Work Unit Tracker for System Test Preparation | 20 hrs | 10 days | Mon 3/25/24 | Fri 4/5/24 | 1050 | 1052FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter
5125 | 1052 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Create System Test Script Template | 30 hrs | 5 days | Mon 4/1/24 | Fri 4/5/24 | 1051FS-5 days | 1053 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5126 | 1053 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Create, Review and Confirm System Test Scripts and Data | 20 hrs | 93 days | Mon 4/8/24 | Fri 8/16/24 | 1052 | 1054 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
5127 | 1054 | Future Task |  |  | WP408 | Stacey Terry | Create | WP408 - Create System Test Script Summary Document | 30 hrs | 5 days | Mon 8/19/24 | Fri 8/23/24 | 1053 | 1055 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5103 | 1055 | Future Task |  |  | WP408 | Stacey Terry | Submit | WP WP408 - System Test Scripts - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 1054 | 1056 |  | Joy Schneider,Stacey Terry
5104 | 1056 | Future Task |  |  | WP408 | Stacey Terry | Review | WP WP408 - System Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1055 | 1057 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5105 | 1057 | Future Task |  |  | WP408 | Stacey Terry | Review | WP WP408 - System Test Scripts - Final Review & Edits | 20 hrs | 5 days | Tue 9/10/24 | Mon 9/16/24 | 1056 | 1058 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5106 | 1058 | Future Task |  |  | WP408 | Stacey Terry | Approve | WP WP408 - System Test Scripts - Approve | 0 hrs | 0 days | Mon 9/16/24 | Mon 9/16/24 | 1057 | 650 | 2024-09-01 | Jimmy Cox
5107 | 1059 | Future Task |  |  | WP409 | Stacey Terry |  | WP409 - Regression Testing Plan | 116 hrs | 78 days | Mon 8/5/24 | Fri 11/22/24
5108 | 1060 | Future Task |  |  | WP409 | Stacey Terry | Create | WPED WP409 - Regression Testing Plan - Create | 2 hrs | 9 days | Mon 8/5/24 | Thu 8/15/24 | 1 | 1061 |  | Stacey Terry,Mary Punty
5109 | 1061 | Future Task |  |  | WP409 | Stacey Terry | Submit | WPED WP409 - Regression Testing Plan - Submit | 0 hrs | 0 days | Thu 8/15/24 | Thu 8/15/24 | 1060 | 1062 |  | Joy Schneider,Stacey Terry
5110 | 1062 | Future Task |  |  | WP409 | Stacey Terry | Review | WPED WP409 - Regression Testing Plan - Review | 24 hrs | 10 days | Fri 8/16/24 | Thu 8/29/24 | 1061 | 1063 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5111 | 1063 | Future Task |  |  | WP409 | Stacey Terry | Approve | WPED WP409 - Regression Testing Plan - Approve | 0 hrs | 0 days | Thu 8/29/24 | Thu 8/29/24 | 1062 | 1064FS+20 days |  | Jimmy Cox
5128 | 1064 | Future Task |  |  | WP409 | Stacey Terry | Create | WP409 - Create Regression Testing Approach/Plan | 20 hrs | 24 days | Mon 9/30/24 | Thu 10/31/24 | 1063FS+20 days | 1065SS+10 days,1067 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5129 | 1065 | Future Task |  |  | WP409 | Stacey Terry | Create | WP409 - Define the scope of the Regression Test suite | 20 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 1064SS+10 days | 1066SS+5 days,1067 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5130 | 1066 | Future Task |  |  | WP409 | Stacey Terry | Create | WP409 - Identify testing resources for Regression Testing | 20 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 1065SS+5 days | 1067 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5112 | 1067 | Future Task |  |  | WP409 | Stacey Terry | Submit | WP WP409 - Regression Testing Plan - Submit | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 106410651066 | 1068 |  | Joy Schneider,Stacey Terry
5113 | 1068 | Future Task |  |  | WP409 | Stacey Terry | Review | WP WP409 - Regression Testing Plan - Collaborative Review & Update | 10 hrs | 10 days | Fri 11/1/24 | Fri 11/15/24 | 1067 | 1069 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5114 | 1069 | Future Task |  |  | WP409 | Stacey Terry | Review | WP WP409 - Regression Testing Plan - Final Review & Edits | 20 hrs | 5 days | Mon 11/18/24 | Fri 11/22/24 | 1068 | 1070 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5115 | 1070 | Future Task |  |  | WP409 | Stacey Terry | Approve | WP WP409 - Regression Testing Plan - Approve | 0 hrs | 0 days | Fri 11/22/24 | Fri 11/22/24 | 1069 | 1114FS-17 days,1126FS+5 days | 2024-12-01 | Jimmy Cox
5257 | 1071 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | WP412 - Interface Testing Plan | 220 hrs | 118 days | Mon 4/1/24 | Mon 9/16/24 |  |  |  |  | RW - share with agencies? | NK
5258 | 1072 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WPED WP412 - Interface Testing Plan - Create | 24 hrs | 10 days | Mon 4/1/24 | Fri 4/12/24 | 536FS+68 days | 1073,1087SS+29 days |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5259 | 1073 | Future Task |  |  | WP412 | Manojkumar Gurjar | Submit | WPED WP412 - Interface Testing Plan - Submit | 0 hrs | 0 days | Fri 4/12/24 | Fri 4/12/24 | 1072 | 1074 |  | Joy Schneider,Manojkumar Gurjar
5260 | 1074 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WPED WP412 - Interface Testing Plan - Review | 28 hrs | 10 days | Mon 4/15/24 | Fri 4/26/24 | 1073 | 1075 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5261 | 1075 | Future Task |  |  | WP412 | Manojkumar Gurjar | Approve | WPED WP412 - Interface Testing Plan - Approve | 0 hrs | 0 days | Fri 4/26/24 | Fri 4/26/24 | 1074 | 1076FS+24 days |  | Jimmy Cox
5284 | 1076 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Define Interface Test approach | 20 hrs | 15 days | Mon 6/3/24 | Fri 6/21/24 | 1075FS+24 days | 1077 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5285 | 1077 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Define Interface Test Cycles | 20 hrs | 14 days | Mon 6/24/24 | Fri 7/12/24 | 1076 | 1078 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5286 | 1078 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Identify Test Resources for Interface Testing | 20 hrs | 5 days | Mon 7/15/24 | Fri 7/19/24 | 1077 | 1079 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5287 | 1079 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Define Test Tools and Test Management processes for Interface Testing | 20 hrs | 5 days | Mon 7/22/24 | Fri 7/26/24 | 1078 | 1080 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5288 | 1080 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WP412 - Create Initial List of Interface Test Scenarios | 20 hrs | 10 days | Mon 7/29/24 | Fri 8/9/24 | 1079 | 1081 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5289 | 1081 | Future Task |  | RW | WP412 | Manojkumar Gurjar | Create | WP412 - Prepare High-level Interface Test Approach for Integration Partners | 20 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 1080 | 1082 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5262 | 1082 | Future Task |  |  | WP412 | Manojkumar Gurjar | Submit | WP WP412 - Interface Testing Plan - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 1081 | 1083 |  | Joy Schneider,Manojkumar Gurjar
5263 | 1083 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WP WP412 - Interface Testing Plan - Collaborative Review & Update | 24 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1082 | 1084 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5264 | 1084 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WP WP412 - Interface Testing Plan - Final Review & Edits | 24 hrs | 5 days | Tue 9/10/24 | Mon 9/16/24 | 1083 | 1085 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5265 | 1085 | Future Task |  |  | WP412 | Manojkumar Gurjar | Approve | WP WP412 - Interface Testing Plan - Approve | 0 hrs | 0 days | Mon 9/16/24 | Mon 9/16/24 | 1084 | 554FS-10 days | 2024-08-01 | Jimmy Cox
5266 | 1086 | Future Task |  |  | WP413 | Stacey Terry |  | WP413 - Interface Test Scripts | 180 hrs | 89 days | Fri 5/10/24 | Mon 9/16/24
5267 | 1087 | Future Task |  |  | WP413 | Stacey Terry | Create | WPED WP413 - Interface Test Scripts - Create | 16 hrs | 10 days | Fri 5/10/24 | Thu 5/23/24 | 1072SS+29 days | 1088 |  | Stacey Terry,Mary Punty
5268 | 1088 | Future Task |  |  | WP413 | Stacey Terry | Submit | WPED WP413 - Interface Test Scripts - Submit | 0 hrs | 0 days | Thu 5/23/24 | Thu 5/23/24 | 1087 | 1089 |  | Joy Schneider,Stacey Terry
5269 | 1089 | Future Task |  |  | WP413 | Stacey Terry | Review | WPED WP413 - Interface Test Scripts - Review | 24 hrs | 10 days | Fri 5/24/24 | Fri 6/7/24 | 1088 | 1090 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5270 | 1090 | Future Task |  |  | WP413 | Stacey Terry | Approve | WPED WP413 - Interface Test Scripts - Approve | 0 hrs | 0 days | Fri 6/7/24 | Fri 6/7/24 | 1089 | 1091 |  | Jimmy Cox
5290 | 1091 | Future Task |  |  | WP413 | Stacey Terry | Create | WP413 - Create Work Unit Tracker for Interface Test Preparation | 20 hrs | 10 days | Mon 6/10/24 | Fri 6/21/24 | 1090 | 1092 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5291 | 1092 | Future Task |  |  | WP413 | Stacey Terry | Create | WP413 - Review, update, & confirm Work Unit Tracker for Interface Test Preparation | 20 hrs | 5 days | Mon 6/24/24 | Fri 6/28/24 | 1091 | 1093 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5292 | 1093 | Future Task |  |  | WP413 | Stacey Terry | Create | WP413 - Create, Review and Confirm Interface Test Scenarios/Scripts and Data | 20 hrs | 24 days | Mon 7/1/24 | Fri 8/2/24 | 1092 | 1094 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5293 | 1094 | Future Task |  |  | WP413 | Stacey Terry | Create | WP413 - Create Interface Test Scripts Summary Document | 20 hrs | 5 days | Mon 8/5/24 | Fri 8/9/24 | 1093 | 1095 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5271 | 1095 | Future Task |  |  | WP413 | Stacey Terry | Submit | WP WP413 - Interface Test Scripts - Submit | 0 hrs | 0 days | Fri 8/9/24 | Fri 8/9/24 | 1094 | 1096 |  | Joy Schneider,Stacey Terry
5272 | 1096 | Future Task |  |  | WP413 | Stacey Terry | Review | WP WP413 - Interface Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 1095 | 1097 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5273 | 1097 | Future Task |  |  | WP413 | Stacey Terry | Review | WP WP413 - Interface Test Scripts - Final Review & Edits | 20 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 1096 | 1098 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5274 | 1098 | Future Task |  |  | WP413 | Stacey Terry | Approve | WP WP413 - Interface Test Scripts - Approve | 0 hrs | 0 days | Fri 8/30/24 | Fri 8/30/24 | 1097 | 1099 | 2024-08-01 | Jimmy Cox
7149 | 1099 | Future Task |  | RW | WP413 | Stacey Terry | Create | Prepare and share Test Scenarios and Scripts with Integration partners | 20 hrs | 10 days | Tue 9/3/24 | Mon 9/16/24 | 1098 |  |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5275 | 1100 | Future Task |  |  | WP414 | Stacey Terry |  | WP414 - Payroll Parallel Test Scripts | 160 hrs | 80 days | Tue 12/10/24 | Thu 4/3/25
5276 | 1101 | Future Task |  |  | WP414 | Stacey Terry | Create | WPED WP414 - Payroll Parallel Test Scripts - Create | 16 hrs | 10 days | Tue 12/10/24 | Mon 12/23/24 | 725SS-4 days | 1102 |  | Stacey Terry,Mary Punty
5277 | 1102 | Future Task |  |  | WP414 | Stacey Terry | Submit | WPED WP414 - Payroll Parallel Test Scripts - Submit | 0 hrs | 0 days | Mon 12/23/24 | Mon 12/23/24 | 1101 | 1103 |  | Joy Schneider,Stacey Terry
5278 | 1103 | Future Task |  |  | WP414 | Stacey Terry | Review | WPED WP414 - Payroll Parallel Test Scripts - Review | 24 hrs | 10 days | Tue 12/24/24 | Wed 1/8/25 | 1102 | 1104 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5279 | 1104 | Future Task |  |  | WP414 | Stacey Terry | Approve | WPED WP414 - Payroll Parallel Test Scripts - Approve | 0 hrs | 0 days | Wed 1/8/25 | Wed 1/8/25 | 1103 | 1105 |  | Jimmy Cox
5295 | 1105 | Future Task |  |  | WP414 | Stacey Terry | Create | WP414 - Create Work Unit Tracker for Payroll Parallel Test Preparation | 20 hrs | 5 days | Thu 1/9/25 | Wed 1/15/25 | 1104 | 1106 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh
5296 | 1106 | Future Task |  |  | WP414 | Stacey Terry | Create | WP414 - Review, update, & confirm Work Unit Tracker for Payroll Parallel Test Preparation | 20 hrs | 10 days | Thu 1/16/25 | Thu 1/30/25 | 1105 | 1107FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
5297 | 1107 | Future Task |  |  | WP414 | Stacey Terry | Create | WP414 - Create, Review and Confirm Payroll Parallel Test Scenarios/Scripts and Data | 20 hrs | 30 days | Fri 1/24/25 | Thu 3/6/25 | 1106FS-5 days | 1108FS-5 days |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Jennifer Peddicord
5298 | 1108 | Future Task |  |  | WP414 | Stacey Terry | Create | WP414 - Create Payroll Parallel Test Script Summary Document | 20 hrs | 10 days | Fri 2/28/25 | Thu 3/13/25 | 1107FS-5 days | 1109 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5280 | 1109 | Future Task |  |  | WP414 | Stacey Terry | Submit | WP WP414 - Payroll Parallel Test Scripts - Submit | 0 hrs | 0 days | Thu 3/13/25 | Thu 3/13/25 | 1108 | 1110 |  | Joy Schneider,Stacey Terry
5281 | 1110 | Future Task |  |  | WP414 | Stacey Terry | Review | WP WP414 - Payroll Parallel Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Fri 3/14/25 | Thu 3/27/25 | 1109 | 1111 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5282 | 1111 | Future Task |  |  | WP414 | Stacey Terry | Review | WP WP414 - Payroll Parallel Test Scripts - Final Review & Edits | 20 hrs | 5 days | Fri 3/28/25 | Thu 4/3/25 | 1110 | 1112 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5283 | 1112 | Future Task |  |  | WP414 | Stacey Terry | Approve | WP WP414 - Payroll Parallel Test Scripts - Approve | 0 hrs | 0 days | Thu 4/3/25 | Thu 4/3/25 | 1111 |  | 2025-03-01 | Jimmy Cox
5131 | 1113 | Future Task |  |  | WP415 | Stacey Terry |  | WP415 - Regression Test Scripts | 140 hrs | 63 days | Wed 10/30/24 | Mon 2/3/25
5132 | 1114 | Future Task |  |  | WP415 | Stacey Terry | Create | WPED WP415 - Regression Test Scripts - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1070FS-17 days | 1115 |  | Stacey Terry,Mary Punty
5133 | 1115 | Future Task |  |  | WP415 | Stacey Terry | Submit | WPED WP415 - Regression Test Scripts - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 1114 | 1116 |  | Joy Schneider,Stacey Terry
5134 | 1116 | Future Task |  |  | WP415 | Stacey Terry | Review | WPED WP415 - Regression Test Scripts - Review | 24 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 1115 | 1117 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5135 | 1117 | Future Task |  |  | WP415 | Stacey Terry | Approve | WPED WP415 - Regression Test Scripts - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1116 | 1118 |  | Jimmy Cox
5221 | 1118 | Future Task |  |  | WP415 | Stacey Terry | Create | WP415 - Create Regression Test Suite | 20 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 1117 | 1119 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5222 | 1119 | Future Task |  |  | WP415 | Stacey Terry | Create | WP415 - Review, update & confirm Regression Test Suite | 20 hrs | 9 days | Mon 12/16/24 | Fri 12/27/24 | 1118 | 1120 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter
5223 | 1120 | Future Task |  |  | WP415 | Stacey Terry | Create | WP415 - Create Regression Test Scripts Summary Document | 20 hrs | 9 days | Mon 12/30/24 | Fri 1/10/25 | 1119 | 1121 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5136 | 1121 | Future Task |  |  | WP415 | Stacey Terry | Submit | WP WP415 - Regression Test Scripts - Submit | 0 hrs | 0 days | Fri 1/10/25 | Fri 1/10/25 | 1120 | 1122 |  | Joy Schneider,Stacey Terry
5137 | 1122 | Future Task |  |  | WP415 | Stacey Terry | Review | WP WP415 - Regression Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 1121 | 1123 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5138 | 1123 | Future Task |  |  | WP415 | Stacey Terry | Review | WP WP415 - Regression Test Scripts - Final Review & Edits | 20 hrs | 5 days | Tue 1/28/25 | Mon 2/3/25 | 1122 | 1124 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5139 | 1124 | Future Task |  |  | WP415 | Stacey Terry | Approve | WP WP415 - Regression Test Scripts - Approve | 0 hrs | 0 days | Mon 2/3/25 | Mon 2/3/25 | 1123 |  | 2024-12-01 | Jimmy Cox
5140 | 1125 | Future Task |  |  | WP416 | Stacey Terry |  | WP416 - Completion of Regression Testing | 123 hrs | 160 days | Wed 12/4/24 | Tue 7/22/25
5141 | 1126 | Future Task |  |  | WP416 | Stacey Terry | Create | WPED WP416 - Completion of Regression Testing - Create | 16 hrs | 10 days | Wed 12/4/24 | Tue 12/17/24 | 1070FS+5 days | 1127 |  | Stacey Terry,Mary Punty
5142 | 1127 | Future Task |  |  | WP416 | Stacey Terry | Submit | WPED WP416 - Completion of Regression Testing - Submit | 0 hrs | 0 days | Tue 12/17/24 | Tue 12/17/24 | 1126 | 1128 |  | Joy Schneider,Stacey Terry
5143 | 1128 | Future Task |  |  | WP416 | Stacey Terry | Review | WPED WP416 - Completion of Regression Testing - Review | 24 hrs | 10 days | Wed 12/18/24 | Thu 1/2/25 | 1127 | 1129 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5144 | 1129 | Future Task |  |  | WP416 | Stacey Terry | Approve | WPED WP416 - Completion of Regression Testing - Approve | 0 hrs | 0 days | Thu 1/2/25 | Thu 1/2/25 | 1128 | 1130 |  | Jimmy Cox
5224 | 1130 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Create Work Unit Tracker for Regression Test Execution | 20 hrs | 10 days | Fri 1/3/25 | Thu 1/16/25 | 1129 | 1131 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5225 | 1131 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Review, update, and confirm Work Unit Tracker for Regression Test Execution | 20 hrs | 10 days | Fri 1/17/25 | Fri 1/31/25 | 1130 | 1132 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5226 | 1132 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Conduct Regression Test Execution Kickoff Meeting | 20 hrs | 5 days | Mon 2/3/25 | Fri 2/7/25 | 1131 | 1133 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5227 | 1133 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Execute Regression Test | 10 hrs | 90 days | Mon 2/10/25 | Mon 6/16/25 | 1132 | 1134 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Matthew Culp,Abdel El Bacha,Donnie Doctor
5228 | 1134 | Future Task |  |  | WP416 | Stacey Terry | Create | WP416 - Create Completion of Regression Test Execution Summary Document | 3 hrs | 10 days | Tue 6/17/25 | Mon 6/30/25 | 1133 | 1135 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5145 | 1135 | Future Task |  |  | WP416 | Stacey Terry | Submit | WP WP416 - Completion of Regression Testing - Submit | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 1134 | 1136 |  | Joy Schneider,Stacey Terry
5146 | 1136 | Future Task |  |  | WP416 | Stacey Terry | Review | WP WP416 - Completion of Regression Testing - Collaborative Review & Update | 5 hrs | 10 days | Tue 7/1/25 | Tue 7/15/25 | 1135 | 1137 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5147 | 1137 | Future Task |  |  | WP416 | Stacey Terry | Review | WP WP416 - Completion of Regression Testing - Final Review & Edits | 5 hrs | 5 days | Wed 7/16/25 | Tue 7/22/25 | 1136 | 1138 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5148 | 1138 | Future Task |  |  | WP416 | Stacey Terry | Approve | WP WP416 - Completion of Regression Testing - Approve | 0 hrs | 0 days | Tue 7/22/25 | Tue 7/22/25 | 1137 |  | 2025-06-01 | Jimmy Cox
5149 | 1139 | Future Task |  |  | WP417 | Stacey Terry |  | WP417 - Data Dictionary | 192 hrs | 139 days | Mon 9/23/24 | Fri 4/11/25
5150 | 1140 | Future Task |  |  | WP417 | Stacey Terry | Create | WPED WP417 - Data Dictionary - Create | 16 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 1 | 1141 |  | Stacey Terry,Manojkumar Gurjar
5151 | 1141 | Future Task |  |  | WP417 | Stacey Terry | Submit | WPED WP417 - Data Dictionary - Submit | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 1140 | 1142 |  | Joy Schneider,Stacey Terry
5152 | 1142 | Future Task |  |  | WP417 | Stacey Terry | Review | WPED WP417 - Data Dictionary - Review | 28 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1141 | 1143 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5153 | 1143 | Future Task |  |  | WP417 | Stacey Terry | Approve | WPED WP417 - Data Dictionary - Approve | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 1142 | 1144FS+27 days |  | Jimmy Cox
5229 | 1144 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Update data dictionary with latest tables and data elements as needed - Financials | 20 hrs | 21 days | Mon 12/2/24 | Tue 12/31/24 | 1143FS+27 days | 1145 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5230 | 1145 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Update data dictionary with latest tables and data elements as needed - Payroll | 20 hrs | 21 days | Thu 1/2/25 | Fri 1/31/25 | 1144 | 1146 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5231 | 1146 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Update data dictionary with latest tables and data elements as needed - DW Related | 20 hrs | 20 days | Mon 2/3/25 | Fri 2/28/25 | 1145 | 1147 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5232 | 1147 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Review and confirm data dictionary | 20 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1146 | 1148 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5233 | 1148 | Future Task |  |  | WP417 | Stacey Terry | Create | WP417 - Share Data Dictionary | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1147 | 1149 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews | RW/Comms? | NK
5154 | 1149 | Future Task |  |  | WP417 | Stacey Terry | Submit | WP WP417 - Data Dictionary - Submit | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1148 | 1150 |  | Joy Schneider,Stacey Terry
5155 | 1150 | Future Task |  |  | WP417 | Stacey Terry | Review | WP WP417 - Data Dictionary - Collaborative Review & Update | 24 hrs | 10 days | Mon 3/24/25 | Fri 4/4/25 | 1149 | 1151 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5156 | 1151 | Future Task |  |  | WP417 | Stacey Terry | Review | WP WP417 - Data Dictionary - Final Review & Edits | 24 hrs | 5 days | Mon 4/7/25 | Fri 4/11/25 | 1150 | 1152 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5157 | 1152 | Future Task |  |  | WP417 | Stacey Terry | Approve | WP WP417 - Data Dictionary - Approve | 0 hrs | 0 days | Fri 4/11/25 | Fri 4/11/25 | 1151 |  | 2025-02-01 | Jimmy Cox
5158 | 1153 | Future Task |  |  | WP418 | Jarad Hermann |  | WP418 - Disaster Recovery Plan | 102 hrs | 106 days | Mon 7/22/24 | Fri 12/20/24
5159 | 1154 | Future Task |  |  | WP418 | Jarad Hermann | Create | WPED WP418 - Disaster Recovery Plan - Create | 2 hrs | 10 days | Mon 7/22/24 | Fri 8/2/24 | 1 | 1155,1166SS+10 days |  | Jarad Hermann
5160 | 1155 | Future Task |  |  | WP418 | Jarad Hermann | Submit | WPED WP418 - Disaster Recovery Plan - Submit | 0 hrs | 0 days | Fri 8/2/24 | Fri 8/2/24 | 1154 | 1156 |  | Joy Schneider,Jarad Hermann
5161 | 1156 | Future Task |  |  | WP418 | Jarad Hermann | Review | WPED WP418 - Disaster Recovery Plan - Review | 16 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 1155 | 1157 |  | Jarad Hermann,Jimmy Cox,Angie Robertson,Sean Buchanan
5162 | 1157 | Future Task |  |  | WP418 | Jarad Hermann | Approve | WPED WP418 - Disaster Recovery Plan - Approve | 0 hrs | 0 days | Fri 8/16/24 | Fri 8/16/24 | 1156 | 1158FS+29 days |  | Jimmy Cox
5234 | 1158 | Future Task |  |  | WP418 | Jarad Hermann | Create | WP418 - Design/Update Disaster Recovery (DR) Plan | 20 hrs | 15 days | Mon 9/30/24 | Fri 10/18/24 | 1157FS+29 days | 1159 |  | Jarad Hermann,Vivek Sharma
5235 | 1159 | Future Task |  |  | WP418 | Jarad Hermann | Create | WP418 - Review Financials Disaster Recovery Plan | 20 hrs | 15 days | Mon 10/21/24 | Fri 11/8/24 | 1158 | 1160 |  | Jarad Hermann,Vivek Sharma
5236 | 1160 | Future Task |  |  | WP418 | Jarad Hermann | Create | WP418 - Create Payroll Disaster Recovery Plan | 20 hrs | 12 days | Tue 11/12/24 | Wed 11/27/24 | 1159 | 1161 |  | Jarad Hermann,Vivek Sharma
5163 | 1161 | Future Task |  |  | WP418 | Jarad Hermann | Submit | WP WP418 - Disaster Recovery Plan - Submit | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1160 | 1162 |  | Joy Schneider,Jarad Hermann
5164 | 1162 | Future Task |  |  | WP418 | Jarad Hermann | Review | WP WP418 - Disaster Recovery Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 1161 | 1163 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5165 | 1163 | Future Task |  |  | WP418 | Jarad Hermann | Review | WP WP418 - Disaster Recovery Plan - Final Review & Edits | 12 hrs | 5 days | Mon 12/16/24 | Fri 12/20/24 | 1162 | 1164 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5166 | 1164 | Future Task |  |  | WP418 | Jarad Hermann | Approve | WP WP418 - Disaster Recovery Plan - Approve | 0 hrs | 0 days | Fri 12/20/24 | Fri 12/20/24 | 1163 | 985 | 2024-11-01 | Jimmy Cox
5167 | 1165 | Future Task |  |  | WP419 | Jarad Hermann |  | WP419 - Disaster Recovery Testing Plan | 116 hrs | 158 days | Mon 8/5/24 | Fri 3/21/25
5168 | 1166 | Future Task |  |  | WP419 | Jarad Hermann | Create | WPED WP419 - Disaster Recovery Testing Plan - Create | 16 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 1154SS+10 days | 1167 |  | Jarad Hermann,Mary Punty
5169 | 1167 | Future Task |  |  | WP419 | Jarad Hermann | Submit | WPED WP419 - Disaster Recovery Testing Plan - Submit | 0 hrs | 0 days | Fri 8/16/24 | Fri 8/16/24 | 1166 | 1168 |  | Joy Schneider,Jarad Hermann
5170 | 1168 | Future Task |  |  | WP419 | Jarad Hermann | Review | WPED WP419 - Disaster Recovery Testing Plan - Review | 20 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 1167 | 1169 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5171 | 1169 | Future Task |  |  | WP419 | Jarad Hermann | Approve | WPED WP419 - Disaster Recovery Testing Plan - Approve | 0 hrs | 0 days | Fri 8/30/24 | Fri 8/30/24 | 1168 | 1170FS+20 days |  | Jimmy Cox
5237 | 1170 | Future Task |  |  | WP419 | Jarad Hermann | Create | WP419 - Define and Document Disaster Recovery Test Tasks including Test Planning, Preparation, Execution, and Closure | 20 hrs | 62 days | Tue 10/1/24 | Tue 12/31/24 | 1169FS+20 days | 1171SS,1205SS+24 days |  | Jarad Hermann,Bryan Sohayda
5238 | 1171 | Future Task |  |  | WP419 | Jarad Hermann | Create | WP419 - Define Disaster Recovery Testing Tools | 20 hrs | 62 days | Tue 10/1/24 | Tue 12/31/24 | 1170SS | 1172 |  | Jarad Hermann,Bryan Sohayda
5239 | 1172 | Future Task |  |  | WP419 | Jarad Hermann | Create | WP419 - Define and Document Disaster Recovery Test Management | 4 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1171 | 1173SS |  | Jarad Hermann,Bryan Sohayda
5240 | 1173 | Future Task |  |  | WP419 | Jarad Hermann | Create | WP419 - Define and Document Disaster Recovery Test Resources and Responsibilities | 4 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1172SS | 1174 |  | Jarad Hermann,Bryan Sohayda
5172 | 1174 | Future Task |  |  | WP419 | Jarad Hermann | Submit | WP WP419 - Disaster Recovery Testing Plan - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 1173 | 1175566 | 2025-02-28 | Joy Schneider,Jarad Hermann
5173 | 1175 | Future Task |  |  | WP419 | Jarad Hermann | Review | WP WP419 - Disaster Recovery Testing Plan - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1174 | 1176 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5174 | 1176 | Future Task |  |  | WP419 | Jarad Hermann | Review | WP WP419 - Disaster Recovery Testing Plan - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1175 | 1177 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5175 | 1177 | Future Task |  |  | WP419 | Jarad Hermann | Approve | WP WP419 - Disaster Recovery Testing Plan - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1176 | 985FS-35 days | 2025-02-01 | Jimmy Cox
5176 | 1178 | Future Task |  |  | WP420 | Jarad Hermann |  | WP420 - Performance Testing Plan | 128 hrs | 172 days | Mon 9/16/24 | Wed 5/21/25
5177 | 1179 | Future Task |  |  | WP420 | Jarad Hermann | Create | WPED WP420 - Performance Testing Plan - Create | 16 hrs | 10 days | Mon 9/16/24 | Fri 9/27/24 | 1 | 1180,1217SS+10 days |  | Jarad Hermann,Mary Punty
5178 | 1180 | Future Task |  |  | WP420 | Jarad Hermann | Submit | WPED WP420 - Performance Testing Plan - Submit | 0 hrs | 0 days | Fri 9/27/24 | Fri 9/27/24 | 1179 | 1181 |  | Joy Schneider,Jarad Hermann
5179 | 1181 | Future Task |  |  | WP420 | Jarad Hermann | Review | WPED WP420 - Performance Testing Plan - Review | 20 hrs | 10 days | Mon 9/30/24 | Fri 10/11/24 | 1180 | 1182 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5180 | 1182 | Future Task |  |  | WP420 | Jarad Hermann | Approve | WPED WP420 - Performance Testing Plan - Approve | 0 hrs | 0 days | Fri 10/11/24 | Fri 10/11/24 | 1181 | 1183FS+32 days,1184SS,1185SS,1186SS,1187SS |  | Jimmy Cox
5241 | 1183 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Identify and establish the projected load of the system | 4 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1182FS+32 days | 1188 |  | Jarad Hermann,Bryan Sohayda
5242 | 1184 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Define test cycles to be included | 20 hrs | 105 days | Mon 10/14/24 | Mon 3/17/25 | 1182SS | 1188 |  | Jarad Hermann,Bryan Sohayda
5243 | 1185 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Define Performance Testing objectives, scope, environments, and metrics | 20 hrs | 105 days | Mon 10/14/24 | Mon 3/17/25 | 1182SS | 1188 |  | Jarad Hermann,Bryan Sohayda
5244 | 1186 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Identify performance testing project team members and responsibilities | 20 hrs | 105 days | Mon 10/14/24 | Mon 3/17/25 | 1182SS | 1188 |  | Jarad Hermann,Bryan Sohayda
5245 | 1187 | Future Task |  |  | WP420 | Jarad Hermann | Create | WP420 - Define and document Performance Testing entry and exit criteria | 20 hrs | 105 days | Mon 10/14/24 | Mon 3/17/25 | 1182SS | 1188 |  | Jarad Hermann,Bryan Sohayda
5181 | 1188 | Future Task |  |  | WP420 | Jarad Hermann | Submit | WP WP420 - Performance Testing Plan - Submit | 0 hrs | 0 days | Wed 4/30/25 | Wed 4/30/25 | 1.1871e+19 | 1189564 |  | Joy Schneider,Jarad Hermann
5182 | 1189 | Future Task |  |  | WP420 | Jarad Hermann | Review | WP WP420 - Performance Testing Plan - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 1188 | 1190 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5183 | 1190 | Future Task |  |  | WP420 | Jarad Hermann | Review | WP WP420 - Performance Testing Plan - Final Review & Edits | 4 hrs | 5 days | Thu 5/15/25 | Wed 5/21/25 | 1189 | 1191 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5184 | 1191 | Future Task |  |  | WP420 | Jarad Hermann | Approve | WP WP420 - Performance Testing Plan - Approve | 0 hrs | 0 days | Wed 5/21/25 | Wed 5/21/25 | 1190 | 967FS-28 days | 2025-04-01 | Jimmy Cox
5185 | 1192 | Future Task |  |  | WP421 | Jarad Hermann |  | WP421 - Penetration Testing Plan | 128 hrs | 124 days | Mon 9/23/24 | Fri 3/21/25
5186 | 1193 | Future Task |  |  | WP421 | Jarad Hermann | Create | WPED WP421 - Penetration Testing Plan - Create | 16 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 1 | 1194,1229SS+10 days |  | Jarad Hermann,Mary Punty
5187 | 1194 | Future Task |  |  | WP421 | Jarad Hermann | Submit | WPED WP421 - Penetration Testing Plan - Submit | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 1193 | 1195 |  | Joy Schneider,Jarad Hermann
5188 | 1195 | Future Task |  |  | WP421 | Jarad Hermann | Review | WPED WP421 - Penetration Testing Plan - Review | 20 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1194 | 1196 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5189 | 1196 | Future Task |  |  | WP421 | Jarad Hermann | Approve | WPED WP421 - Penetration Testing Plan - Approve | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 1195 | 1197FS+27 days |  | Jimmy Cox
5246 | 1197 | Future Task |  |  | WP421 | Jarad Hermann | Create | WP421 - Create Penetration Testing Plan/approach | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1196FS+27 days | 1198SS,1199SS,1200 |  | Jarad Hermann,Bryan Sohayda
5247 | 1198 | Future Task |  |  | WP421 | Jarad Hermann | Create | WP421 - Identify resources for Penetration Testing | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1197SS | 1200 |  | Jarad Hermann,Bryan Sohayda
5248 | 1199 | Future Task |  |  | WP421 | Jarad Hermann | Create | WP421 - Define Penetration Testing entry and exit criteria | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1197SS | 1200 |  | Jarad Hermann,Bryan Sohayda
5190 | 1200 | Future Task |  |  | WP421 | Jarad Hermann | Submit | WP WP421 - Penetration Testing Plan - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 119911971198 | 1201 |  | Joy Schneider,Jarad Hermann
5191 | 1201 | Future Task |  |  | WP421 | Jarad Hermann | Review | WP WP421 - Penetration Testing Plan - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1200 | 1202 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5192 | 1202 | Future Task |  |  | WP421 | Jarad Hermann | Review | WP WP421 - Penetration Testing Plan - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1201 | 1203 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5193 | 1203 | Future Task |  |  | WP421 | Jarad Hermann | Approve | WP WP421 - Penetration Testing Plan - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1202 | 949FS+10 days | 2025-02-01 | Jimmy Cox
5194 | 1204 | Future Task |  |  | WP422 | Jarad Hermann |  | WP422 - Disaster Recovery Test Scripts | 128 hrs | 94 days | Mon 11/4/24 | Fri 3/21/25
5195 | 1205 | Future Task |  |  | WP422 | Jarad Hermann | Create | WPED WP422 - Disaster Recovery Test Scripts - Create | 16 hrs | 10 days | Mon 11/4/24 | Mon 11/18/24 | 1170SS+24 days | 1206 |  | Jarad Hermann,Mary Punty
5196 | 1206 | Future Task |  |  | WP422 | Jarad Hermann | Submit | WPED WP422 - Disaster Recovery Test Scripts - Submit | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 1205 | 1207 |  | Joy Schneider,Jarad Hermann
5197 | 1207 | Future Task |  |  | WP422 | Jarad Hermann | Review | WPED WP422 - Disaster Recovery Test Scripts - Review | 20 hrs | 10 days | Tue 11/19/24 | Wed 12/4/24 | 1206 | 1208 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5198 | 1208 | Future Task |  |  | WP422 | Jarad Hermann | Approve | WPED WP422 - Disaster Recovery Test Scripts - Approve | 0 hrs | 0 days | Wed 12/4/24 | Wed 12/4/24 | 1207 | 1209FS+18 days |  | Jimmy Cox
5249 | 1209 | Future Task |  |  | WP422 | Jarad Hermann | Create | WP422 - Finalize Disaster Recovery Test Scripts Inventory | 20 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1208FS+18 days | 1210SS,1211SS,1212 |  | Jarad Hermann,Bryan Sohayda
5250 | 1210 | Future Task |  |  | WP422 | Jarad Hermann | Create | WP422 - Create, review, and confirm DR Test Script Work Unit Tracker | 20 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1209SS | 1212 |  | Jarad Hermann,Bryan Sohayda
5251 | 1211 | Future Task |  |  | WP422 | Jarad Hermann | Create | WP422 - Create, Review and Confirm Disaster Recovery Test Scripts | 20 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1209SS | 1212 |  | Jarad Hermann,Bryan Sohayda
5199 | 1212 | Future Task |  |  | WP422 | Jarad Hermann | Submit | WP WP422 - Disaster Recovery Test Scripts - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 121112091210 | 1213 |  | Joy Schneider,Jarad Hermann
5200 | 1213 | Future Task |  |  | WP422 | Jarad Hermann | Review | WP WP422 - Disaster Recovery Test Scripts - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1212 | 1214 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5201 | 1214 | Future Task |  |  | WP422 | Jarad Hermann | Review | WP WP422 - Disaster Recovery Test Scripts - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1213 | 1215 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5202 | 1215 | Future Task |  |  | WP422 | Jarad Hermann | Approve | WP WP422 - Disaster Recovery Test Scripts - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1214 | 985FS-35 days |  | Jimmy Cox
5203 | 1216 | Future Task |  |  | WP423 | Jarad Hermann |  | WP423 - Performance Test Scripts | 104 hrs | 162 days | Mon 9/30/24 | Wed 5/21/25
5204 | 1217 | Future Task |  |  | WP423 | Jarad Hermann | Create | WPED WP423 - Performance Test Scripts - Create | 16 hrs | 10 days | Mon 9/30/24 | Fri 10/11/24 | 1179SS+10 days | 1218 |  | Jarad Hermann,Mary Punty
5205 | 1218 | Future Task |  |  | WP423 | Jarad Hermann | Submit | WPED WP423 - Performance Test Scripts - Submit | 0 hrs | 0 days | Fri 10/11/24 | Fri 10/11/24 | 1217 | 1219 |  | Joy Schneider,Jarad Hermann
5206 | 1219 | Future Task |  |  | WP423 | Jarad Hermann | Review | WPED WP423 - Performance Test Scripts - Review | 20 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 1218 | 1220 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5207 | 1220 | Future Task |  |  | WP423 | Jarad Hermann | Approve | WPED WP423 - Performance Test Scripts - Approve | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 1219 | 1221FS+22 days |  | Jimmy Cox
5252 | 1221 | Future Task |  |  | WP423 | Jarad Hermann | Create | WP423 - Finalize Performance Test Scripts Inventory | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1220FS+22 days | 1222SS,1223SS,1224 |  | Jarad Hermann,Bryan Sohayda
5253 | 1222 | Future Task |  |  | WP423 | Jarad Hermann | Create | WP423 - Create, review, and confirm Performance Test Script Work Unit Tracker | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1221SS | 1224 |  | Jarad Hermann,Bryan Sohayda
5254 | 1223 | Future Task |  |  | WP423 | Jarad Hermann | Create | WP423 - Create, Review and Confirm Performance Test Scripts | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1221SS | 1224 |  | Jarad Hermann,Bryan Sohayda
5208 | 1224 | Future Task |  |  | WP423 | Jarad Hermann | Submit | WP WP423 - Performance Test Scripts - Submit | 0 hrs | 0 days | Wed 4/30/25 | Wed 4/30/25 | 122312211222 | 1225 |  | Joy Schneider,Jarad Hermann
5209 | 1225 | Future Task |  |  | WP423 | Jarad Hermann | Review | WP WP423 - Performance Test Scripts - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 1224 | 1226 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5210 | 1226 | Future Task |  |  | WP423 | Jarad Hermann | Review | WP WP423 - Performance Test Scripts - Final Review & Edits | 4 hrs | 5 days | Thu 5/15/25 | Wed 5/21/25 | 1225 | 1227 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5211 | 1227 | Future Task |  |  | WP423 | Jarad Hermann | Approve | WP WP423 - Performance Test Scripts - Approve | 0 hrs | 0 days | Wed 5/21/25 | Wed 5/21/25 | 1226 | 967FS-28 days |  | Jimmy Cox
5212 | 1228 | Future Task |  |  | WP424 | Jarad Hermann |  | WP424 - Penetration Test Scripts/Scenarios | 108 hrs | 114 days | Mon 10/7/24 | Fri 3/21/25
5213 | 1229 | Future Task |  |  | WP424 | Jarad Hermann | Create | WPED WP424 - Penetration Test Scripts/Scenarios - Create | 16 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1193SS+10 days | 1230 |  | Jarad Hermann,Mary Punty
5214 | 1230 | Future Task |  |  | WP424 | Jarad Hermann | Submit | WPED WP424 - Penetration Test Scripts/Scenarios - Submit | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 1229 | 1231 |  | Joy Schneider,Jarad Hermann
5215 | 1231 | Future Task |  |  | WP424 | Jarad Hermann | Review | WPED WP424 - Penetration Test Scripts/Scenarios - Review | 20 hrs | 10 days | Mon 10/21/24 | Fri 11/1/24 | 1230 | 1232 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5216 | 1232 | Future Task |  |  | WP424 | Jarad Hermann | Approve | WPED WP424 - Penetration Test Scripts/Scenarios - Approve | 0 hrs | 0 days | Fri 11/1/24 | Fri 11/1/24 | 1231 | 1233FS+17 days |  | Jimmy Cox
5255 | 1233 | Future Task |  |  | WP424 | Jarad Hermann | Create | WP424 - Finalize Penetration Test Scripts Inventory | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1232FS+17 days | 1234SS |  | Jarad Hermann,Bryan Sohayda
5256 | 1234 | Future Task |  |  | WP424 | Jarad Hermann | Create | WP424 - Create, review, and confirm Penetration Test Scripts/Scenarios | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1233SS | 1235 |  | Jarad Hermann,Bryan Sohayda
5217 | 1235 | Future Task |  |  | WP424 | Jarad Hermann | Submit | WP424 - WP WP424 - Penetration Test Scripts/Scenarios - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 1234 | 1236 |  | Joy Schneider,Jarad Hermann
5218 | 1236 | Future Task |  |  | WP424 | Jarad Hermann | Review | WP WP424 - Penetration Test Scripts/Scenarios - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1235 | 1237 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5219 | 1237 | Future Task |  |  | WP424 | Jarad Hermann | Review | WP WP424 - Penetration Test Scripts/Scenarios - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1236 | 1238 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5220 | 1238 | Future Task |  |  | WP424 | Jarad Hermann | Approve | WP WP424 - Penetration Test Scripts/Scenarios - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1237 | 949FS+10 days |  | Jimmy Cox
5299 | 1239 | Future Task |  |  | I-WP127 | Angie Robertson |  | I-WP127 - User Acceptance Testing Plan | 61 hrs | 77 days | Mon 8/5/24 | Thu 11/21/24 |  |  |  |  | RW? | NK
5300 | 1240 | Future Task |  |  | I-WP127 | Angie Robertson | Create | WPED I-WP127 - User Acceptance Testing Plan - Create | 4 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 1 | 1241 |  | Angie Robertson,Jimmy Cox | Change the year to 2023 | Angie
5301 | 1241 | Future Task |  |  | I-WP127 | Angie Robertson | Submit | WPED I-WP127 - User Acceptance Testing Plan - Submit | 0 hrs | 0 days | Fri 8/16/24 | Fri 8/16/24 | 1240 | 1242 |  | Angie Robertson | Change the year to 2023 | Angie
5302 | 1242 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WPED I-WP127 - User Acceptance Testing Plan - Collaborative Review & Update | 17 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 1241 | 1243 |  | Carolyn Hicks,Angie Robertson,Matthew Breeding,Jennifer Reeves,Deana Metcalf,Julian Gotreaux,Tommy Werner,Matt Cole,Mary Punty,Stacey Terry | Change the year to 2023 | Angie
5303 | 1243 | Future Task |  |  | I-WP127 | Angie Robertson | Approve | WPED I-WP127 - User Acceptance Testing Plan - Approve | 0 hrs | 0 days | Fri 8/30/24 | Fri 8/30/24 | 1242 | 1244 |  | Jimmy Cox | Change the year to 2023 | Angie
5310 | 1244 | Future Task |  |  | I-WP127 | Angie Robertson | Create | Create User Acceptance Plan | 10 hrs | 40 days | Tue 9/3/24 | Mon 10/28/24 | 1243 | 1245 |  | Matthew Breeding,Jennifer Reeves,Carolyn Hicks,Deana Metcalf,Angie Robertson | Change to 11/1/23 - 2/29/24 | Angie
5304 | 1245 | Future Task |  |  | I-WP127 | Angie Robertson | Submit | WP I-WP127 - User Acceptance Testing Plan - Submit | 0 hrs | 0 days | Mon 10/28/24 | Mon 10/28/24 | 1244 | 1246 |  | Matthew Breeding | Change Resource Name to me Change to 2/29/24 | Angie
5305 | 1246 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WP I-WP127 - User Acceptance Testing Plan - Department QC | 8 hrs | 1 day | Tue 10/29/24 | Tue 10/29/24 | 1245 | 1247 |  | Gabriela Gibson | Adjust based on new "Submit" date | Angie
5306 | 1247 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WP I-WP127 - User Acceptance Testing Plan - Collaborative Review & Update | 10 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1246 | 1248 |  | Matthew Breeding,Jennifer Reeves,Carolyn Hicks,Deana Metcalf,Angie Robertson | Adjust based on new "Submit" date | Angie
5307 | 1248 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WP I-WP127 - User Acceptance Testing Plan - Style Guide Review | 2 hrs | 1 day | Thu 11/14/24 | Thu 11/14/24 | 1247 | 1249 |  | Tatiana Eubanks | Adjust based on new "Submit" date | Angie
5308 | 1249 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WP I-WP127 - User Acceptance Testing Plan - Final Review & Update | 10 hrs | 5 days | Fri 11/15/24 | Thu 11/21/24 | 1248 | 1250 |  | Angie Robertson,Jimmy Cox | Adjust based on new "Submit" date | Angie
5309 | 1250 | Future Task |  |  | I-WP127 | Angie Robertson | Approve | WP I-WP127 - User Acceptance Testing Plan - Approve | 0 hrs | 0 days | Thu 11/21/24 | Thu 11/21/24 | 1249 | 1252,558FS+46 days,587 |  | Jimmy Cox | Change to 3/31/24 Note from Joy on 6/6: based on the other I-WP127 date changes, this date would be 3/25/24. Are we okay with that or should we add five days somewhere to meet this date? Note: the create task is already 81 days with 41 days of lag between the WPED approval and the start of the WP creation. | Angie
3967 | 1251 | Future Task | [5 empty] | UAT | 1 hr | 163 days | Tue 4/1/25 | Wed 11/19/25
4002 | 1252 | Future Task |  |  | UAT | Matt Breeding | Create | UAT Testing | 1 hr | 163 days | Tue 4/1/25 | Wed 11/19/25 | 17245611250 | 1755,1813SS+30 days |  | Jimmy Cox,Angie Robertson | Add a Note that this will be updated with the results / timeline confirmed in the UAT Testing Plan | Angie
3772 | 1253 | Future Task | [5 empty] | Deploy | 1,923 hrs | 565 days | Fri 11/3/23 | Wed 2/4/26
7188 | 1254 | Future Task |  |  | SG5 | Jimmy Cox |  | Stage Gate 5: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 6/30/25 | Mon 7/7/25 |  | 1255 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7189 | 1255 | Future Task |  |  | SG5 | Jimmy Cox |  | Stage Gate 5: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Tue 7/8/25 | Mon 7/21/25 | 1254 | 1256FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7190 | 1256 | Future Task |  |  | SG5 | Jimmy Cox |  | Stage Gate 5: Prepare information package for ESC | 11 hrs | 10 days | Fri 11/7/25 | Fri 11/21/25 | 1255FS+77 days | 1257 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7191 | 1257 | Future Task |  |  | SG5 | Jimmy Cox |  | Stage Gate 5: Collaborative Review and Update of information package | 11 hrs | 5 days | Mon 11/24/25 | Tue 12/2/25 | 1256 | 1258 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7192 | 1258 | Future Task |  |  | SG5 | Jimmy Cox |  | Stage Gate 5: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 12/3/25 | Wed 12/3/25 | 1257 |  |  | Dusti Kincl
7156 | 1259 | Future Task |  |  | SG5 | Jimmy Cox | Milestone | Stage Gate 5: Deployment Readiness | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 7.2278e+33 |  | December 17, 2025 - ESC | Jimmy Cox,Angie Robertson,Matt Cole | This Milestone (Stage Gate) is to be approved by the ESC. We should show ESC as the Resource Name, instead of Jimmy, me, and Matt. | Angie
7193 | 1260 | Future Task |  |  | SG6 | Jimmy Cox |  | Stage Gate 6: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 7/14/25 | Fri 7/18/25 |  | 1261 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7194 | 1261 | Future Task |  |  | SG6 | Jimmy Cox |  | Stage Gate 6: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Mon 7/21/25 | Fri 8/1/25 | 1260 | 1262FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7195 | 1262 | Future Task |  |  | SG6 | Jimmy Cox |  | Stage Gate 6: Prepare information package for ESC | 11 hrs | 10 days | Fri 11/21/25 | Mon 12/8/25 | 1261FS+77 days | 1263 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7196 | 1263 | Future Task |  |  | SG6 | Jimmy Cox |  | Stage Gate 6: Collaborative Review and Update of information package | 11 hrs | 5 days | Tue 12/9/25 | Mon 12/15/25 | 1262 | 1264 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7197 | 1264 | Future Task |  |  | SG6 | Jimmy Cox |  | Stage Gate 6: Provide Checklist and information package to the ESC | 1 hr | 1 day | Tue 12/16/25 | Tue 12/16/25 | 1263 |  |  | Dusti Kincl
7157 | 1265 | Future Task |  |  | SG6 | Jimmy Cox | Milestone | Stage Gate 6: Confirm Deployment | 0 hrs | 0 days | Fri 12/19/25 | Fri 12/19/25 | 139014051356 | 1271 | 2025-12-30 | Jimmy Cox,Angie Robertson,Matt Cole
7198 | 1266 | Future Task |  |  | SG7 | Jimmy Cox |  | Stage Gate 7: Prepare Stage Gate Checklist | 6 hrs | 5 days | Mon 7/21/25 | Fri 7/25/25 |  | 1267 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7199 | 1267 | Future Task |  |  | SG7 | Jimmy Cox |  | Stage Gate 7: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Mon 7/28/25 | Fri 8/8/25 | 1266 | 1268FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7200 | 1268 | Future Task |  |  | SG7 | Jimmy Cox |  | Stage Gate 7: Prepare information package for ESC | 11 hrs | 10 days | Tue 12/2/25 | Mon 12/15/25 | 1267FS+77 days | 1269 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7201 | 1269 | Future Task |  |  | SG7 | Jimmy Cox |  | Stage Gate 7: Collaborative Review and Update of information package | 11 hrs | 5 days | Tue 12/16/25 | Mon 12/22/25 | 1268 | 1270 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7202 | 1270 | Future Task |  |  | SG7 | Jimmy Cox |  | Stage Gate 7: Provide Checklist and information package to the ESC | 1 hr | 1 day | Tue 12/23/25 | Tue 12/23/25 | 1269 |  |  | Dusti Kincl
7158 | 1271 | Future Task |  |  | SG7 | Jimmy Cox | Milestone | Stage Gate 7: Go-Live | 0 hrs | 0 days | Fri 12/19/25 | Fri 12/19/25 | 1265 |  | 2026-01-06 | Jimmy Cox,Angie Robertson,Matt Cole | The previous task is after this date. We need to have the "prepare" task series be before the milestone. Note from Joy on 6/6: SG prep tasks begin on 7/21/25 and ends on 12/23/25. Current date of SG is based on current preds. We will baseline on January 6, 2026 and then adjust to auto schedule to allow the team to see shifting dates. | Angie
5311 | 1272 | Future Task |  |  | D645 | Mary Punty |  | D645 - Updated Deployment Strategy | 265 hrs | 122 days | Fri 11/3/23 | Tue 4/30/24
5312 | 1273 | Future Task |  |  | D645 | Mary Punty | Create | DED D645 - Updated Deployment Strategy - Create | 16 hrs | 10 days | Fri 11/3/23 | Fri 11/17/23 | 1 | 1274 |  | Mary Punty,Bryan Sohayda
5313 | 1274 | Future Task |  |  | D645 | Mary Punty | Submit | DED D645 - Updated Deployment Strategy - Submit | 0 hrs | 0 days | Fri 11/17/23 | Fri 11/17/23 | 1273 | 1275 |  | Mary Punty,Joy Schneider
5314 | 1275 | Future Task |  |  | D645 | Mary Punty | Review | DED D645 - Updated Deployment Strategy - Collaborative Review | 20 hrs | 10 days | Mon 11/20/23 | Tue 12/5/23 | 1274 | 1276 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5315 | 1276 | Future Task |  |  | D645 | Mary Punty | Approve | DED D645 - Updated Deployment Strategy - Approve | 0 hrs | 0 days | Tue 12/5/23 | Tue 12/5/23 | 1275 | 1277FS+17 days |  | Jimmy Cox
5339 | 1277 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Document assumptions about deployment | 20 hrs | 9 days | Tue 1/2/24 | Fri 1/12/24 | 1276FS+17 days | 1278 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5340 | 1278 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Create Deployment Kickoff Presentation | 20 hrs | 9 days | Tue 1/16/24 | Fri 1/26/24 | 1277 | 1279 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5341 | 1279 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Review Deployment Kickoff Presentation | 20 hrs | 5 days | Mon 1/29/24 | Fri 2/2/24 | 1278 | 1280 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5342 | 1280 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Describe Deployment Calendar | 20 hrs | 10 days | Mon 2/5/24 | Fri 2/16/24 | 1279 | 1281 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5343 | 1281 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Review Deployment Calendar | 20 hrs | 5 days | Mon 2/19/24 | Fri 2/23/24 | 1280 | 1282 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5344 | 1282 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Describe Cutover Checklist | 20 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 1281 | 1283 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5345 | 1283 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Review Cutover Checklist | 20 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 1282 | 1284 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5346 | 1284 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Finalize Draft - Deployment Strategy | 20 hrs | 5 days | Mon 3/25/24 | Fri 3/29/24 | 1283 | 1285 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5347 | 1285 | Future Task |  |  | D645 | Mary Punty | Create | D645 - Review Draft - Deployment Strategy | 20 hrs | 5 days | Mon 4/1/24 | Fri 4/5/24 | 1284 | 1286 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5316 | 1286 | Future Task |  |  | D645 | Mary Punty | Submit | DEL D645 - Updated Deployment Strategy - Draft Submission | 0 hrs | 0 days | Fri 4/5/24 | Fri 4/5/24 | 1285 | 1287 |  | Mary Punty,Joy Schneider
5317 | 1287 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 4/8/24 | Fri 4/12/24 | 1286 | 1288 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5318 | 1288 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Style Guide Review | 1 hr | 1 day | Mon 4/15/24 | Mon 4/15/24 | 1287 | 1289 |  | Dusti Kincl
5319 | 1289 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Final Collaborative Review | 16 hrs | 5 days | Tue 4/16/24 | Mon 4/22/24 | 1288 | 1290 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5320 | 1290 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Accenture QC | 4 hrs | 2 days | Tue 4/23/24 | Wed 4/24/24 | 1289 | 1291 |  | Joy Schneider
5321 | 1291 | Future Task |  |  | D645 | Mary Punty | Submit | DEL D645 - Updated Deployment Strategy - Submit | 0 hrs | 0 days | Wed 4/24/24 | Wed 4/24/24 | 1290 | 1292 |  | Joy Schneider
5322 | 1292 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Department QC | 4 hrs | 1 day | Thu 4/25/24 | Thu 4/25/24 | 1291 | 1293 |  | Tommy Werner,Gabriela Gibson
5323 | 1293 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Contract Manager Review | 8 hrs | 3 days | Fri 4/26/24 | Tue 4/30/24 | 1292 | 12941296 |  | Sean Buchanan
5324 | 1294 | Future Task |  |  | D645 | Mary Punty | Accept | DEL D645 - Updated Deployment Strategy - Accept | 0 hrs | 0 days | Tue 4/30/24 | Tue 4/30/24 | 1293 |  | 2024-04-01 | Sean Buchanan
5325 | 1295 | Future Task |  |  | D658 | Mary Punty |  | D658 - Develop the Deployment and Contingency Plan | 498 hrs | 149 days | Mon 8/26/24 | Mon 3/31/25 |  |  |  |  | There are lots of "create" tasks already defined below. This seems very detailed considering the DED has not been created or approved. Note from Joy: team has reviewed tasks and confirmed these are realistic inital tasks, which will be refined through the DED. | Angie
5326 | 1296 | Future Task |  |  | D658 | Mary Punty | Create | DED D658 - Develop the Deployment and Contingency Plan - Create | 16 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1293 | 1297 |  | Mary Punty,Bryan Sohayda
5327 | 1297 | Future Task |  |  | D658 | Mary Punty | Submit | DED D658 - Develop the Deployment and Contingency Plan - Submit | 0 hrs | 0 days | Mon 9/9/24 | Mon 9/9/24 | 1296 | 1298 |  | Mary Punty,Joy Schneider
5328 | 1298 | Future Task |  |  | D658 | Mary Punty | Review | DED D658 - Develop the Deployment and Contingency Plan - Collaborative Review | 20 hrs | 10 days | Tue 9/10/24 | Mon 9/23/24 | 1297 | 1299 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5329 | 1299 | Future Task |  |  | D658 | Mary Punty | Approve | DED D658 - Develop the Deployment and Contingency Plan - Approve | 0 hrs | 0 days | Mon 9/23/24 | Mon 9/23/24 | 1298 | 1300FS+24 days |  | Jimmy Cox
5348 | 1300 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Create Deployment and Contingency Plan pitch deck | 18 hrs | 9 days | Mon 10/28/24 | Thu 11/7/24 | 1299FS+24 days | 1301 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5349 | 1301 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review Deployment and Contingency Plan pitch deck | 40 hrs | 4 days | Fri 11/8/24 | Thu 11/14/24 | 1300 | 1302FS+8 days,1306 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5350 | 1302 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Prepare materials for Dec Sponsor Meeting and Review | 25 hrs | 5 days | Wed 11/27/24 | Thu 12/5/24 | 1301FS+8 days | 1303 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5351 | 1303 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Plan for and hold December Sponsor Meeting | 25 hrs | 5 days | Fri 12/6/24 | Thu 12/12/24 | 1302 | 1304FS+11 days |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5352 | 1304 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Gather Deployment and Contingency Plan materials for January ESC Meeting | 35 hrs | 7 days | Tue 12/31/24 | Thu 1/9/25 | 1303FS+11 days | 1305,1310SS |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5353 | 1305 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review Deployment and Contingency Plan materials for January ESC Meeting | 25 hrs | 5 days | Fri 1/10/25 | Thu 1/16/25 | 1304 | 1314 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5354 | 1306 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Identify and document deployment and post-implementation support activities | 20 hrs | 8 days | Fri 11/15/24 | Tue 11/26/24 | 1301 | 1307 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5355 | 1307 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review and document deployment and post-implementation support activities | 25 hrs | 5 days | Wed 11/27/24 | Thu 12/5/24 | 1306 | 1308 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5356 | 1308 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Identify and document timing of cutover activities | 25 hrs | 5 days | Fri 12/6/24 | Thu 12/12/24 | 1307 | 1309 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5357 | 1309 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review and document timing of cutover activities | 25 hrs | 5 days | Fri 12/13/24 | Thu 12/19/24 | 1308 | 1310 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5358 | 1310 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Identify and document contingency scenarios | 20 hrs | 7 days | Tue 12/31/24 | Thu 1/9/25 | 1304SS,1309 | 1311 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5359 | 1311 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review contingency scenarios | 25 hrs | 5 days | Fri 1/10/25 | Thu 1/16/25 | 1310 | 1312 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5360 | 1312 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Define and document the approach to revert changes | 20 hrs | 4 days | Fri 1/17/25 | Thu 1/23/25 | 1311 | 1313 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5361 | 1313 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review the approach to revert changes | 25 hrs | 5 days | Fri 1/24/25 | Thu 1/30/25 | 1312 | 1314 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5362 | 1314 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Gather Deployment and Contingency Plan materials for February ESC Meeting | 25 hrs | 5 days | Fri 1/31/25 | Thu 2/6/25 | 13131305 | 1315 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5363 | 1315 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Review Deployment and Contingency Plan materials for February ESC Meeting | 15 hrs | 3 days | Fri 2/7/25 | Tue 2/11/25 | 1314 | 1316FS+12 days |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5364 | 1316 | Future Task |  |  | D658 | Mary Punty | Create | D658 - Confirm approach to Deployment and Contingency | 20 hrs | 5 days | Fri 2/28/25 | Thu 3/6/25 | 1315FS+12 days | 1317 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5330 | 1317 | Future Task |  |  | D658 | Mary Punty | Submit | DEL D658 - Develop the Deployment and Contingency Plan - Draft Submission | 0 hrs | 0 days | Thu 3/6/25 | Thu 3/6/25 | 1316 | 1318 |  | Mary Punty,Joy Schneider
5331 | 1318 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 3/7/25 | Thu 3/13/25 | 1317 | 1319 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5332 | 1319 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Style Guide Review | 1 hr | 1 day | Fri 3/14/25 | Fri 3/14/25 | 1318 | 1320 |  | Dusti Kincl
5333 | 1320 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Final Collaborative Review | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1319 | 1321 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5334 | 1321 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Accenture QC | 4 hrs | 2 days | Mon 3/24/25 | Tue 3/25/25 | 1320 | 1322 |  | Joy Schneider
5335 | 1322 | Future Task |  |  | D658 | Mary Punty | Submit | DEL D658 - Develop the Deployment and Contingency Plan - Submit | 0 hrs | 0 days | Tue 3/25/25 | Tue 3/25/25 | 1321 | 1323 |  | Joy Schneider
5336 | 1323 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Department QC | 4 hrs | 1 day | Wed 3/26/25 | Wed 3/26/25 | 1322 | 1324 |  | Tommy Werner,Gabriela Gibson
5337 | 1324 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Contract Manager Review | 8 hrs | 3 days | Thu 3/27/25 | Mon 3/31/25 | 1323 | 1325 |  | Sean Buchanan
5338 | 1325 | Future Task |  |  | D658 | Mary Punty | Accept | DEL D658 - Develop the Deployment and Contingency Plan - Accept | 0 hrs | 0 days | Mon 3/31/25 | Mon 3/31/25 | 1324 | 1259 | 2025-03-01 | Sean Buchanan
5365 | 1326 | Future Task |  |  | D678 | Bryan Sohayda |  | D678 - Final Known Issues & Enhancements Lists | 350 hrs | 86 days | Mon 8/4/25 | Fri 12/5/25 |  |  |  |  | RW? - will this be shared with agencies? | NK
5366 | 1327 | Future Task |  |  | D678 | Bryan Sohayda | Create | DED D678 - Final Known Issues & Enhancements Lists - Create | 16 hrs | 10 days | Mon 8/4/25 | Fri 8/15/25 | 1 | 1328 |  | Mary Punty,Bryan Sohayda
5367 | 1328 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DED D678 - Final Known Issues & Enhancements Lists - Submit | 0 hrs | 0 days | Fri 8/15/25 | Fri 8/15/25 | 1327 | 1329 |  | Bryan Sohayda,Joy Schneider
5368 | 1329 | Future Task |  |  | D678 | Bryan Sohayda | Review | DED D678 - Final Known Issues & Enhancements Lists - Collaborative Review | 20 hrs | 10 days | Mon 8/18/25 | Fri 8/29/25 | 1328 | 1330 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5369 | 1330 | Future Task |  |  | D678 | Bryan Sohayda | Approve | DED D678 - Final Known Issues & Enhancements Lists - Approve | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 1329 | 1331FS+21 days |  | Jimmy Cox
5393 | 1331 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Initial Known Issues & Enhancements Lists | 20 hrs | 22 days | Wed 10/1/25 | Thu 10/30/25 | 1330FS+21 days | 1332SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5394 | 1332 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Review Open SIRs - Candidates for Known Issues List | 25 hrs | 5 days | Wed 10/1/25 | Tue 10/7/25 | 1331SS | 1333,1334SS |  | Bryan Sohayda,Mary Punty,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5395 | 1333 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Finalize Open SIRs - Candidates for Known Issues List | 24 hrs | 4 days | Wed 10/8/25 | Mon 10/13/25 | 1332 | 1335SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5396 | 1334 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Review Open SIRs - Candidates for Known Enhancements List | 30 hrs | 5 days | Wed 10/1/25 | Tue 10/7/25 | 1332SS | 1336 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5397 | 1335 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Finalize Open SIRs - Candidates for Known Enhancements List | 20 hrs | 4 days | Wed 10/8/25 | Mon 10/13/25 | 1333SS | 1336 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5398 | 1336 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Confirm Agreed Upon Known Issues | 30 hrs | 5 days | Tue 10/14/25 | Mon 10/20/25 | 13351334 | 1337SS,1338SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5399 | 1337 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Confirm Agreed Upon Known Enhancements | 30 hrs | 5 days | Tue 10/14/25 | Mon 10/20/25 | 1336SS | 1340 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5400 | 1338 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Create DEL Draft - Wrapper Document and Known Issues/Enhancements Lists | 20 hrs | 5 days | Tue 10/14/25 | Mon 10/20/25 | 1336SS | 1339 |  | Bryan Sohayda,Mary Punty
5401 | 1339 | Future Task |  |  | D678 | Bryan Sohayda | Create | D678 - Review DEL Draft - Wrapper Document and Known Issues/Enhancements Lists | 48 hrs | 8 days | Tue 10/21/25 | Thu 10/30/25 | 1338 | 1340 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5370 | 1340 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DEL D678 - Final Known Issues & Enhancements Lists - Draft Submission | 0 hrs | 0 days | Thu 10/30/25 | Thu 10/30/25 | 13391337 | 1341 |  | Bryan Sohayda,Joy Schneider
5371 | 1341 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 10/31/25 | Thu 11/6/25 | 1340 | 1342 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5372 | 1342 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Style Guide Review | 1 hr | 1 day | Fri 11/7/25 | Fri 11/7/25 | 1341 | 1343 |  | Dusti Kincl
5373 | 1343 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Final Collaborative Review | 16 hrs | 5 days | Mon 11/10/25 | Mon 11/17/25 | 1342 | 1344 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5374 | 1344 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Accenture QC | 4 hrs | 2 days | Tue 11/18/25 | Wed 11/19/25 | 1343 | 1345 |  | Joy Schneider
5375 | 1345 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DEL D678 - Final Known Issues & Enhancements Lists - Submit | 0 hrs | 0 days | Wed 11/19/25 | Wed 11/19/25 | 1344 | 1346 |  | Joy Schneider
5376 | 1346 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Department QC | 4 hrs | 1 day | Thu 11/20/25 | Thu 11/20/25 | 1345 | 1347 |  | Tommy Werner,Gabriela Gibson
5377 | 1347 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Contract Manager Review | 8 hrs | 3 days | Fri 11/21/25 | Tue 11/25/25 | 1346 | 1348 |  | Sean Buchanan
5378 | 1348 | Future Task |  |  | D678 | Bryan Sohayda | Accept | DEL D678 - Final Known Issues & Enhancements Lists - Accept | 0 hrs | 0 days | Tue 11/25/25 | Tue 11/25/25 | 1347 | 1349FS+1 day,1259 | 2025-12-01 | Sean Buchanan
5407 | 1349 | Future Task |  |  | D678 | Bryan Sohayda | Create | Refresh Known Issues/Enhancements List to Prep for Stage Gate 5 | 18 hrs | 5 days | Mon 12/1/25 | Fri 12/5/25 | 1348FS+1 day |  |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5379 | 1350 | Future Task |  |  | D679 | Stacey Terry |  | D679 - Go-Live of Financials and Payroll Waves | 169 hrs | 82 days | Mon 10/6/25 | Wed 2/4/26
5380 | 1351 | Future Task |  |  | D679 | Stacey Terry | Create | DED D679 - Go-Live of Financials and Payroll Waves - Create | 16 hrs | 10 days | Mon 10/6/25 | Fri 10/17/25 | 1 | 1352 |  | Stacey Terry,Manojkumar Gurjar
5381 | 1352 | Future Task |  |  | D679 | Stacey Terry | Submit | DED D679 - Go-Live of Financials and Payroll Waves - Submit | 0 hrs | 0 days | Fri 10/17/25 | Fri 10/17/25 | 1351 | 1353 |  | Stacey Terry,Joy Schneider
5382 | 1353 | Future Task |  |  | D679 | Stacey Terry | Review | DED D679 - Go-Live of Financials and Payroll Waves - Collaborative Review | 28 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 1352 | 1354 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5383 | 1354 | Future Task |  |  | D679 | Stacey Terry | Approve | DED D679 - Go-Live of Financials and Payroll Waves - Approve | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 1353 | 1355FS+22 days |  | Jimmy Cox
5403 | 1355 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Go-Live of Financials and Payroll Waves | 15 hrs | 5 days | Mon 12/8/25 | Fri 12/12/25 | 1354FS+22 days | 1356 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5404 | 1356 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Document Go-Live Applications Listing | 15 hrs | 5 days | Mon 12/15/25 | Fri 12/19/25 | 1355 | 1357FS+8 days,1265 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5405 | 1357 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Document Go-Live Tasks completed | 15 hrs | 5 days | Mon 1/5/26 | Fri 1/9/26 | 1356FS+8 days | 1358SS |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5406 | 1358 | Future Task |  |  | D679 | Stacey Terry | Create | D679 - Document Go-List of Agencies Participated | 15 hrs | 5 days | Mon 1/5/26 | Fri 1/9/26 | 1357SS | 1359 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5384 | 1359 | Future Task |  |  | D679 | Stacey Terry | Submit | DEL D679 - Go-Live of Financials and Payroll Waves - Draft Submission | 0 hrs | 0 days | Fri 1/9/26 | Fri 1/9/26 | 1358 | 1360 |  | Stacey Terry,Joy Schneider
5385 | 1360 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Pre-Submission Collaborative Review | 24 hrs | 5 days | Mon 1/12/26 | Fri 1/16/26 | 1359 | 1361 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5386 | 1361 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Style Guide Review | 1 hr | 1 day | Tue 1/20/26 | Tue 1/20/26 | 1360 | 1362 |  | Dusti Kincl
5387 | 1362 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Final Collaborative Review | 24 hrs | 5 days | Wed 1/21/26 | Tue 1/27/26 | 1361 | 1363 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5388 | 1363 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Accenture QC | 4 hrs | 2 days | Wed 1/28/26 | Thu 1/29/26 | 1362 | 1364 |  | Joy Schneider
5389 | 1364 | Future Task |  |  | D679 | Stacey Terry | Submit | DEL D679 - Go-Live of Financials and Payroll Waves - Submit | 0 hrs | 0 days | Thu 1/29/26 | Thu 1/29/26 | 1363 | 1365 |  | Joy Schneider
5390 | 1365 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Department QC | 4 hrs | 1 day | Fri 1/30/26 | Fri 1/30/26 | 1364 | 1366 |  | Tommy Werner,Gabriela Gibson
5391 | 1366 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Contract Manager Review | 8 hrs | 3 days | Mon 2/2/26 | Wed 2/4/26 | 1365 | 1367 |  | Sean Buchanan
5392 | 1367 | Future Task |  |  | D679 | Stacey Terry | Accept | DEL D679 - Go-Live of Financials and Payroll Waves - Accept | 0 hrs | 0 days | Wed 2/4/26 | Wed 2/4/26 | 1366 |  | 2026-01-01 | Sean Buchanan
6739 | 1368 | Future Task | Maybe |  | WP425 | Bryan Sohayda |  | WP425 - Production Support Operations Plan | 356 hrs | 129 days | Mon 10/14/24 | Fri 4/18/25
6740 | 1369 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WPED WP425 - Production Support Operations Plan - Create | 8 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 1 | 1370 |  | Bryan Sohayda
6741 | 1370 | Future Task |  |  | WP425 | Bryan Sohayda | Submit | WPED WP425 - Production Support Operations Plan - Submit | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 1369 | 1371 |  | Joy Schneider,Bryan Sohayda
6742 | 1371 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WPED WP425 - Production Support Operations Plan - Review | 16 hrs | 10 days | Mon 10/28/24 | Fri 11/8/24 | 1370 | 1372 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
6743 | 1372 | Future Task |  |  | WP425 | Bryan Sohayda | Approve | WPED WP425 - Production Support Operations Plan - Approve | 0 hrs | 0 days | Fri 11/8/24 | Fri 11/8/24 | 1371 | 1373FS+22 days |  | Jimmy Cox
6744 | 1373 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Update Production Support Operations Plan | 20 hrs | 72 days | Mon 12/16/24 | Fri 3/28/25 | 1372FS+22 days | 1374SS |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6745 | 1374 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Introduction, Overview, Collab taken with partners, team R&R | 20 hrs | 5 days | Mon 12/16/24 | Fri 12/20/24 | 1373SS | 1375FS+8 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6746 | 1375 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document Production Support services provided | 20 hrs | 5 days | Mon 1/6/25 | Fri 1/10/25 | 1374FS+8 days | 1376 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6747 | 1376 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review and provide feedback on Production Support Services Provided draft | 20 hrs | 5 days | Mon 1/13/25 | Fri 1/17/25 | 1375 | 1377 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6748 | 1377 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Create Maintenance Calendar template | 48 hrs | 4 days | Tue 1/21/25 | Fri 1/24/25 | 1376 | 1378 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6749 | 1378 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review Maintenance Calendar template | 20 hrs | 5 days | Mon 1/27/25 | Fri 1/31/25 | 1377 | 1379 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6750 | 1379 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document production support business processes and tools list | 20 hrs | 5 days | Mon 2/3/25 | Fri 2/7/25 | 1378 | 1380 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6751 | 1380 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review and provide feedback on Production Support business processes and tools list draft | 20 hrs | 5 days | Mon 2/10/25 | Fri 2/14/25 | 1379 | 1381 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6752 | 1381 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document production support schedule of activities | 20 hrs | 5 days | Mon 2/17/25 | Fri 2/21/25 | 1380 | 1382 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6753 | 1382 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review and provide feedback on Production Support schedule of activities draft | 20 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 1381 | 1383 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6754 | 1383 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document production support performance expectations | 20 hrs | 5 days | Mon 3/3/25 | Fri 3/7/25 | 1382 | 1384 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6755 | 1384 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Review and provide feedback on Production Support performance expectations draft | 20 hrs | 5 days | Mon 3/10/25 | Fri 3/14/25 | 1383 | 1385 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6756 | 1385 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Define and document production support team roles, responsibilities, and staffing | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1384 | 1386 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6757 | 1386 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WP425 - Full walkthrough of Production Support Operations Plan through facilitated meetings | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 1385 | 1387 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6758 | 1387 | Future Task |  |  | WP425 | Bryan Sohayda | Submit | WP WP425 - Production Support Operations Plan - Submit | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 1386 | 1388 |  | Joy Schneider,Bryan Sohayda
6759 | 1388 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WP WP425 - Production Support Operations Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 3/31/25 | Fri 4/11/25 | 1387 | 1389 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6760 | 1389 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WP WP425 - Production Support Operations Plan - Final Review & Edits | 12 hrs | 5 days | Mon 4/14/25 | Fri 4/18/25 | 1388 | 1390 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6761 | 1390 | Future Task |  |  | WP425 | Bryan Sohayda | Approve | WP WP425 - Production Support Operations Plan - Approve | 0 hrs | 0 days | Fri 4/18/25 | Fri 4/18/25 | 1389 | 1265 | 2025-04-01 | Jimmy Cox
6762 | 1391 | Future Task | Maybe |  | WP427 | Bryan Sohayda |  | WP427 - Production Support Application Configuration Management Plan | 168 hrs | 107 days | Mon 12/2/24 | Fri 5/2/25
6763 | 1392 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WPED WP427 - Production Support Application Configuration Management Plan - Create | 8 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 1 | 1393 |  | Bryan Sohayda
6764 | 1393 | Future Task |  |  | WP427 | Bryan Sohayda | Submit | WPED WP427 - Production Support Application Configuration Management Plan - Submit | 0 hrs | 0 days | Fri 12/13/24 | Fri 12/13/24 | 1392 | 1394 |  | Joy Schneider,Bryan Sohayda
6765 | 1394 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WPED WP427 - Production Support Application Configuration Management Plan - Review | 16 hrs | 10 days | Mon 12/16/24 | Mon 12/30/24 | 1393 | 1395 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
6766 | 1395 | Future Task |  |  | WP427 | Bryan Sohayda | Approve | WPED WP427 - Production Support Application Configuration Management Plan - Approve | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 1394 | 1396FS+22 days |  | Jimmy Cox
6767 | 1396 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Updated Configuration Management Processes for Release and Maintenance | 20 hrs | 50 days | Mon 2/3/25 | Fri 4/11/25 | 1395FS+22 days | 1397SS,1402,1398SS+10 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6768 | 1397 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Define and Document Application Configuration Management Processes for Release and Maintenance | 20 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1396SS | 1398 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6769 | 1398 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Review and confirm Application and Infrastructure Configuration Management Processes for Release and Maintenance | 20 hrs | 5 days | Mon 2/17/25 | Fri 2/21/25 | 1396SS+10 days,1397 | 1399 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6770 | 1399 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Define and document System Configuration Control Process Steps and Diagram | 20 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 1398 | 1400 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6771 | 1400 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Review System Configuration Control Process Steps and Diagram | 20 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1399 | 1401FS+10 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6772 | 1401 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WP427 - Full draft review pre-submission | 20 hrs | 10 days | Mon 3/31/25 | Fri 4/11/25 | 1400FS+10 days | 1402 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6773 | 1402 | Future Task |  |  | WP427 | Bryan Sohayda | Submit | WP WP427 - Production Support Application Configuration Management Plan - Submit | 0 hrs | 0 days | Fri 4/11/25 | Fri 4/11/25 | 13961401 | 1403 |  | Joy Schneider,Bryan Sohayda
6774 | 1403 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WP WP427 - Production Support Application Configuration Management Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 1402 | 1404 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6775 | 1404 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WP WP427 - Production Support Application Configuration Management Plan - Final Review & Edits | 12 hrs | 5 days | Mon 4/28/25 | Fri 5/2/25 | 1403 | 1405 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6776 | 1405 | Future Task |  |  | WP427 | Bryan Sohayda | Approve | WP WP427 - Production Support Application Configuration Management Plan - Approve | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 1404 | 1265 | 2025-04-01 | Jimmy Cox
2953 | 1406 | Late | [5 empty] | Stakeholder Engagement | 3,989 hrs | 936 days | Mon 5/8/23 | Tue 1/26/27
2972 | 1407 | On Schedule | [5 empty] | Training | 2,336 hrs | 928 days | Thu 5/18/23 | Tue 1/26/27
6906 | 1408 | On Schedule |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 - Data Inventory for Financials and Payroll Wave | 105 hrs | 277 days | Thu 5/18/23 | Fri 6/21/24
6907 | 1409 | On Schedule |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 - Data Inventory for Financials and Payroll Wave | 22 hrs | 277 days | Thu 5/18/23 | Fri 6/21/24
6908 | 1410 | Complete |  |  | I-WP102 | Jennifer Reeves | Create | WPED I-WP102 - Data Inventory for Financials and Payroll Wave - Create | 2 hrs | 10 days | Thu 5/18/23 | Thu 6/1/23 | 1 | 1411 |  | Jennifer Grant,Jennifer Reeves
6909 | 1411 | Complete |  |  | I-WP102 | Jennifer Reeves | Submit | WPED I-WP102 - Data Inventory for Financials and Payroll Wave - Submit | 0 hrs | 0 days | Thu 6/1/23 | Thu 6/1/23 | 1410 | 1412 |  | Jennifer Grant,Jennifer Reeves | Successor UID-6929 | TW
6910 | 1412 | On Schedule |  |  | I-WP102 | Jennifer Reeves | Review | WPED I-WP102 - Data Inventory for Financials and Payroll Wave - Collaborative Review and Update | 8 hrs | 10 days | Fri 6/2/23 | Thu 6/15/23 | 1411 | 1413 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Reeves,Jennifer Grant
6911 | 1413 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | WPED I-WP102 - Data Inventory for Financials and Payroll Wave - Approve | 0 hrs | 0 days | Thu 6/15/23 | Thu 6/15/23 | 1412 | 1422 |  | Jimmy Cox
6912 | 1414 | Future Task |  |  | I-WP102 | Jennifer Reeves | Submit | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Submit | 0 hrs | 0 days | Wed 5/29/24 | Wed 5/29/24 | 1453 | 1415 |  | Jennifer Grant,Jennifer Reeves
6913 | 1415 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Department QC | 2 hrs | 1 day | Thu 5/30/24 | Thu 5/30/24 | 1414 | 1416 |  | Gabriela Gibson
6914 | 1416 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Collaborative Review & Update | 7 hrs | 10 days | Fri 5/31/24 | Thu 6/13/24 | 1415 | 1417 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Nikki Klein,Daylin Reyes,Angie Robertson
6915 | 1417 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Style Guide Review | 1 hr | 1 day | Fri 6/14/24 | Fri 6/14/24 | 1416 | 1418 |  | Tatiana Eubanks
6916 | 1418 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Final Review & Update | 2 hrs | 5 days | Mon 6/17/24 | Fri 6/21/24 | 1417 | 1419 |  | Angie Robertson,Jimmy Cox
6917 | 1419 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | WP I-WP102 - Data Inventory for Financials and Payroll Wave - Approve | 0 hrs | 0 days | Fri 6/21/24 | Fri 6/21/24 | 1418 |  |  | Jimmy Cox
6918 | 1420 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | Data Inventory for Financials and Payroll Wave | 83 hrs | 245 days | Fri 6/16/23 | Wed 6/5/24
6919 | 1421 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 1 - Data | 20 hrs | 45 days | Fri 6/16/23 | Fri 8/18/23 |  |  |  |  | Change Segment 1 to Segment I
6920 | 1422 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create - Data Inventory Format | 7 hrs | 5 days | Fri 6/16/23 | Thu 6/22/23 | 1413 | 1423 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Nikki Klein,Daylin Reyes,Angie Robertson
6921 | 1423 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory Format | 5 hrs | 5 days | Fri 6/23/23 | Thu 6/29/23 | 1422 | 1424 |  | Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Daylin Reyes,Angie Robertson
6922 | 1424 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory Format | 1 hr | 5 days | Fri 6/30/23 | Fri 7/7/23 | 1423 | 1425 |  | Jimmy Cox
6923 | 1425 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | Mon 7/10/23 | Fri 7/28/23 | 1424 | 1426 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6924 | 1426 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 15 days | Mon 7/31/23 | Fri 8/18/23 | 1425 |  |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes | Successor UID-6926 | TW
6925 | 1427 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 2 - Data | 7 hrs | 20 days | Mon 10/9/23 | Fri 11/3/23 |  |  |  |  | Change Segment 2 to Segment II
6926 | 1428 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | Mon 10/9/23 | Fri 10/27/23 | 61SS | 1429 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6927 | 1429 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 5 days | Mon 10/30/23 | Fri 11/3/23 | 1428 |  |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes | Successor UID - 6929 | TW
6928 | 1430 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 3 - Data | 13 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24 |  |  |  |  | Change Segment 3 to Segment III
6929 | 1431 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 1 | 14321438 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves | Change Predecessor to 4336ss (Remove 1, and keep UID-6927) | TW
6930 | 1432 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1431 | 14331439 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6931 | 1433 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Functional Teams | 6 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1432 | 1435 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6932 | 1434 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Update & Publish Data Inventory | 18 hrs | 25 days | Fri 2/2/24 | Thu 3/7/24
6933 | 1435 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 5 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1433 | 1436 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6934 | 1436 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1435 | 1437 |  | Jimmy Cox
6935 | 1437 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Coordinate Knowledge Base Update | 2 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1436 |  |  | Jennifer Reeves,Daylin Reyes | Successor UID-6948 | TW
6936 | 1438 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create Communication for Data Inventory | 2 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1431 |  |  | Jennifer Grant,Jennifer Reeves | Successor UID-6937 | TW
6937 | 1439 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review for Communication for Data Inventory | 2 hrs | 9 days | Fri 2/9/24 | Wed 2/21/24 | 1432 | 1440 |  | Dusti Kincl,Angie Robertson
6938 | 1440 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Communication | 1 hr | 5 days | Thu 2/22/24 | Wed 2/28/24 | 1439 | 1441 |  | Jimmy Cox
6939 | 1441 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Publish Data Inventory | 4 hrs | 2 days | Thu 2/29/24 | Fri 3/1/24 | 1440 | 1442 |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6940 | 1442 | Future Task |  | RW-Communication | I-WP102 | Jennifer Reeves | Create | I-WP102 Share - Communication for Data Inventory | 1 hr | 2 days | Mon 3/4/24 | Tue 3/5/24 | 1441 |  |  | Dusti Kincl | Successor UID-6942 | TW
6941 | 1443 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 4 - Data | 11 hrs | 25 days | Wed 4/10/24 | Tue 5/14/24 |  |  |  |  | Change Segment 4 to Segment IV
6942 | 1444 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 3 hrs | 15 days | Wed 4/10/24 | Tue 4/30/24 | 1 | 14451451 |  | Jennifer Reeves,Pradeep Koul,Tanya McCarty | Remove Predecessor 1 | TW
6943 | 1445 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 2 hrs | 5 days | Wed 5/1/24 | Tue 5/7/24 | 1444 | 1446 |  | Jennifer Reeves,Matthew Breeding
6944 | 1446 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 6 hrs | 5 days | Wed 5/8/24 | Tue 5/14/24 | 1445 | 1448 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6945 | 1447 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Update & Publish Data Inventory | 14 hrs | 25 days | Wed 5/1/24 | Wed 6/5/24
6946 | 1448 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 3 hrs | 5 days | Wed 5/15/24 | Tue 5/21/24 | 1446 | 1449 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves
6947 | 1449 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory | 2 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1448 | 1450 |  | Angie Robertson,Jimmy Cox
6948 | 1450 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Coordinate Knowledge Base Update | 2 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1449 |  |  | Jennifer Reeves,Daylin Reyes | Successor UID-6916 | TW
6949 | 1451 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create Communication - Data Inventory | 2 hrs | 5 days | Wed 5/1/24 | Tue 5/7/24 | 1444 | 1452 |  | Jennifer Grant,Jennifer Reeves
6950 | 1452 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Communication for Data Inventory | 2 hrs | 10 days | Wed 5/8/24 | Tue 5/21/24 | 1451 | 1453 |  | Dusti Kincl,Angie Robertson
6951 | 1453 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Communication for Data Inventory | 2 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1452 | 14141454 |  | Jennifer Grant,Jennifer Reeves
6952 | 1454 | Future Task |  | RW-Communication | I-WP102 | Jennifer Reeves | Create | I-WP102 Share Communication for Data Inventory | 1 hr | 2 days | Thu 5/30/24 | Fri 5/31/24 | 1453 |  |  | Dusti Kincl | Successor UID-6916 | TW
7039 | 1455 | On Schedule |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 - Accounting Entry Inventory | 271 hrs | 285 days | Thu 5/18/23 | Wed 7/3/24
7040 | 1456 | Complete |  |  | I-WP103 | Jennifer Reeves | Create | WPED I-WP103 - Accounting Entry Inventory - Create | 10 hrs | 10 days | Thu 5/18/23 | Thu 6/1/23 | 1 | 1457 |  | Jennifer Grant,Jennifer Reeves
7041 | 1457 | Complete |  |  | I-WP103 | Jennifer Reeves | Submit | WPED I-WP103 - Accounting Entry Inventory - Submit | 0 hrs | 0 days | Thu 6/1/23 | Thu 6/1/23 | 1456 | 1458 |  | Jennifer Grant,Jennifer Reeves
7042 | 1458 | On Schedule |  |  | I-WP103 | Jennifer Reeves | Review | WPED I-WP103 - Accounting Entry Inventory - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/2/23 | Thu 6/15/23 | 1457 | 1459 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7043 | 1459 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | WPED I-WP103 - Accounting Entry Inventory - Approve | 0 hrs | 0 days | Thu 6/15/23 | Thu 6/15/23 | 1458 | 1468FS+37 days |  | Jimmy Cox
7044 | 1460 | Future Task |  |  | I-WP103 | Jennifer Reeves | Submit | WP I-WP103 - Accounting Entry Inventory - Submit | 0 hrs | 0 days | Mon 6/10/24 | Mon 6/10/24 | 1499 | 1461 |  | Jennifer Grant,Jennifer Reeves
7045 | 1461 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP I-WP103 - Accounting Entry Inventory - Department QC | 1 hr | 1 day | Tue 6/11/24 | Tue 6/11/24 | 1460 | 1462 |  | Gabriela Gibson
7046 | 1462 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP I-WP103 - Accounting Entry Inventory - Collaborative Review & Update | 10 hrs | 10 days | Wed 6/12/24 | Tue 6/25/24 | 1461 | 1463 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7047 | 1463 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP I-WP103 - Accounting Entry Inventory - Style Guide Review | 1 hr | 1 day | Wed 6/26/24 | Wed 6/26/24 | 1462 | 1464 |  | Tatiana Eubanks
7048 | 1464 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP I-WP103 - Accounting Entry Inventory - Final Review & Update | 2 hrs | 5 days | Thu 6/27/24 | Wed 7/3/24 | 1463 | 1465 |  | Angie Robertson,Jimmy Cox
7049 | 1465 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | WP I-WP103 - Accounting Entry Inventory - Approve | 0 hrs | 0 days | Wed 7/3/24 | Wed 7/3/24 | 1464 |  |  | Jimmy Cox
7050 | 1466 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | Accounting Entry Inventory | 237 hrs | 216 days | Wed 8/9/23 | Mon 6/17/24
7051 | 1467 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 1 | 48 hrs | 37 days | Wed 8/9/23 | Fri 9/29/23
7052 | 1468 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Accounting Entry Inventory Format | 10 hrs | 5 days | Wed 8/9/23 | Tue 8/15/23 | 1459FS+37 days | 1469 |  | Jennifer Reeves,Daylin Reyes
7053 | 1469 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory Format | 10 hrs | 6 days | Wed 8/16/23 | Wed 8/23/23 | 1468 | 1470 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7054 | 1470 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory Format | 10 hrs | 5 days | Thu 8/24/23 | Wed 8/30/23 | 1469 | 1471 |  | Jimmy Cox
7055 | 1471 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 16 days | Thu 8/31/23 | Fri 9/22/23 | 1470,42 | 1472 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7056 | 1472 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Mon 9/25/23 | Fri 9/29/23 | 1471 |  |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes | Successor UID-7044 | TW
7057 | 1473 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 2 | 18 hrs | 20 days | Tue 10/24/23 | Tue 11/21/23
7058 | 1474 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | Tue 10/24/23 | Tue 11/14/23 | 61 | 1475 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7059 | 1475 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Wed 11/15/23 | Tue 11/21/23 | 1474 |  |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes | Successor UID-7044 | TW
7060 | 1476 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 3 | 28 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
7061 | 1477 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 140SS | 14781484 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7062 | 1478 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1477 | 1479 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7063 | 1479 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Functional Teams | 10 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1478 | 1481 |  | Brendan Jones,Janice Jackson,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7064 | 1480 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Update & Publish Accounting Entry Inventory | 54 hrs | 25 days | Fri 2/2/24 | Thu 3/7/24
7065 | 1481 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1479 | 1482 |  | Jennifer Reeves,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson
7066 | 1482 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory | 2 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1481 | 1483 |  | Jimmy Cox
7067 | 1483 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Coordinate Knowledge Base Update | 10 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1482 |  |  | Jennifer Reeves,Daylin Reyes | Successor UID-7080 | TW
7068 | 1484 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1477 | 1485 |  | Jennifer Grant,Jennifer Reeves
7069 | 1485 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review for Communication for Accounting Entry Inventory | 10 hrs | 9 days | Fri 2/9/24 | Wed 2/21/24 | 1484 | 1486 |  | Dusti Kincl,Angie Robertson
7070 | 1486 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Thu 2/22/24 | Wed 2/28/24 | 1485 | 1487 |  | Jimmy Cox
7071 | 1487 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Publish - Accounting Entry Inventory | 1 hr | 2 days | Thu 2/29/24 | Fri 3/1/24 | 1486 | 1488 |  | Pradeep Koul,Richard Saltford,Daylin Reyes,Dusti Kincl
7072 | 1488 | Future Task |  | RW-Communication | I-WP103 | Jennifer Reeves | Create | I-WP103 Share - Communication for Accounting Entry Inventory | 1 hr | 2 days | Mon 3/4/24 | Tue 3/5/24 | 1487 |  |  | Dusti Kincl | Successor UID-7074 | TW
7073 | 1489 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 4 | 28 hrs | 25 days | Mon 4/22/24 | Fri 5/24/24
7074 | 1490 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | Mon 4/22/24 | Fri 5/10/24 | 159SS | 14911497 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7075 | 1491 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1490 | 1492 |  | Matthew Breeding,Jennifer Reeves
7076 | 1492 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Functional Teams | 10 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1491 | 1494 |  | Brendan Jones,Janice Jackson,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7077 | 1493 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Update & Publish Accounting Entry Inventory | 61 hrs | 25 days | Mon 5/13/24 | Mon 6/17/24
7078 | 1494 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory | 10 hrs | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1492 | 1495 |  | Jennifer Reeves,Matthew Breeding,Deana Metcalf
7079 | 1495 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory | 10 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1494 | 1496 |  | Jimmy Cox,Angie Robertson
7080 | 1496 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Coordinate Knowledge Base Update | 10 hrs | 5 days | Tue 6/11/24 | Mon 6/17/24 | 1495 |  |  | Jennifer Reeves,Daylin Reyes | Successor TBD | TW
7081 | 1497 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1490 | 1498 |  | Jennifer Grant,Jennifer Reeves
7082 | 1498 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Communication for Accounting Entry Inventory | 10 hrs | 10 days | Mon 5/20/24 | Mon 6/3/24 | 1497 | 1499 |  | Dusti Kincl,Angie Robertson
7083 | 1499 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1498 | 14601500 |  | Jennifer Grant,Jennifer Reeves
7084 | 1500 | Future Task |  | RW-Communication | I-WP103 | Jennifer Reeves | Create | I-WP103 Share Communication for Accounting Entry Inventory | 1 hr | 2 days | Tue 6/11/24 | Wed 6/12/24 | 1499 |  |  | Dusti Kincl
7085 | 1501 | On Schedule |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 - Error Matrix | 113 hrs | 287 days | Thu 5/18/23 | Mon 7/8/24
7086 | 1502 | Complete |  |  | I-WP104 | Jennifer Reeves | Create | WPED I-WP104 - Error Matrix - Create | 9 hrs | 10 days | Thu 5/18/23 | Thu 6/1/23 | 1 | 1503 |  | Jennifer Grant,Jennifer Reeves
7087 | 1503 | Complete |  |  | I-WP104 | Jennifer Reeves | Submit | WPED I-WP104 - Error Matrix - Submit | 0 hrs | 0 days | Thu 6/1/23 | Thu 6/1/23 | 1502 | 1504 |  | Jennifer Grant,Jennifer Reeves
7088 | 1504 | On Schedule |  |  | I-WP104 | Jennifer Reeves | Review | WPED I-WP104 - Error Matrix - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/2/23 | Thu 6/15/23 | 1503 | 15051513 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7089 | 1505 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | WPED I-WP104 - Error Matrix - Approve | 0 hrs | 0 days | Thu 6/15/23 | Thu 6/15/23 | 1504 |  |  | Jimmy Cox | Successor - UID 7097 | TW
7090 | 1506 | Future Task |  |  | I-WP104 | Jennifer Reeves | Submit | WP I-WP104 - Error Matrix - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 15441545 | 1507 |  | Jennifer Grant,Jennifer Reeves
7091 | 1507 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP I-WP104 - Error Matrix - Department QC | 1 hr | 1 day | Thu 6/13/24 | Thu 6/13/24 | 1506 | 1508 |  | Gabriela Gibson
7092 | 1508 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP I-WP104 - Error Matrix - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1507 | 1509 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7093 | 1509 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP I-WP104 - Error Matrix - Style Guide Review | 1 hr | 1 day | Fri 6/28/24 | Fri 6/28/24 | 1508 | 1510 |  | Tatiana Eubanks
7094 | 1510 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP I-WP104 - Error Matrix - Final Review & Update | 2 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 1509 | 1511 |  | Angie Robertson,Jimmy Cox
7095 | 1511 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | WP I-WP104 - Error Matrix - Approve | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1510 |  |  | Jimmy Cox
7096 | 1512 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 1 | 15 hrs | 62 days | Fri 6/16/23 | Wed 9/13/23
7097 | 1513 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Error Matrix Format | 2 hrs | 5 days | Fri 6/16/23 | Thu 6/22/23 | 1504 | 1514 |  | Jennifer Reeves,Daylin Reyes
7098 | 1514 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 5 hrs | 5 days | Fri 6/23/23 | Thu 6/29/23 | 1513 | 1515 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7099 | 1515 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix Format | 1 hr | 5 days | Fri 6/30/23 | Fri 7/7/23 | 1514 | 1516 |  | Jimmy Cox
7100 | 1516 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Wed 8/2/23 | Tue 8/22/23 | 1515,42 | 1517 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7101 | 1517 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 15 days | Wed 8/23/23 | Wed 9/13/23 | 1516 |  |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes | Successor - UID 7103 | TW
7102 | 1518 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 2 | 7 hrs | 20 days | Tue 10/24/23 | Tue 11/21/23
7103 | 1519 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Tue 10/24/23 | Tue 11/14/23 | 61 | 1520 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7104 | 1520 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | Wed 11/15/23 | Tue 11/21/23 | 1519 |  |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes | Successor - UID 7106 | TW
7105 | 1521 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 3 | 13 hrs | 25 days | Mon 1/29/24 | Fri 3/1/24
7106 | 1522 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Mon 1/29/24 | Fri 2/16/24 | 140 | 15231529 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7107 | 1523 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | Mon 2/19/24 | Fri 2/23/24 | 1522 | 1524 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7108 | 1524 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Functional Teams | 6 hrs | 5 days | Mon 2/26/24 | Fri 3/1/24 | 1523 | 1526 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7109 | 1525 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Update & Publish Error Matrix | 18 hrs | 25 days | Mon 2/19/24 | Fri 3/22/24
7110 | 1526 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 5 hrs | 5 days | Mon 3/4/24 | Fri 3/8/24 | 1524 | 1527 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7111 | 1527 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix | 1 hr | 5 days | Mon 3/11/24 | Fri 3/15/24 | 1526 | 1528 |  | Jimmy Cox
7112 | 1528 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Coordinate Knowledge Base Update | 2 hrs | 5 days | Mon 3/18/24 | Fri 3/22/24 | 1527 |  |  | Jennifer Reeves,Daylin Reyes | Successor - UID 7111 6/7 note from Joy - did not action per 6/7 meeting | TW
7113 | 1529 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Communication for Error Matrix | 2 hrs | 5 days | Mon 2/19/24 | Fri 2/23/24 | 1522 | 1530 |  | Jennifer Grant,Jennifer Reeves
7114 | 1530 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review for Communication for Error Matrix | 2 hrs | 9 days | Mon 2/26/24 | Thu 3/7/24 | 1529 | 1531 |  | Dusti Kincl,Angie Robertson
7115 | 1531 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Communication for Error Matrix | 1 hr | 5 days | Fri 3/8/24 | Thu 3/14/24 | 1530 | 1532 |  | Jimmy Cox
7116 | 1532 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Publish - Error Matrix | 4 hrs | 2 days | Fri 3/15/24 | Mon 3/18/24 | 1531 | 1533 |  | Pradeep Koul,Richard Saltford,Daylin Reyes,Dusti Kincl
7117 | 1533 | Future Task |  | RW-Communication | I-WP104 | Jennifer Reeves | Create | I-WP104 Share - Communication for Error Matrix | 1 hr | 2 days | Tue 3/19/24 | Wed 3/20/24 | 1532 |  |  | Dusti Kincl | Successor - UID 7119 | TW
7118 | 1534 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 4 | 13 hrs | 25 days | Mon 4/22/24 | Fri 5/24/24
7119 | 1535 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Mon 4/22/24 | Fri 5/10/24 | 159SS | 15361542 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7120 | 1536 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1535 | 1537 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7121 | 1537 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Functional Teams | 6 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1536 | 1539 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7122 | 1538 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Update & Publish Error Matrix | 14 hrs | 25 days | Mon 5/13/24 | Mon 6/17/24
7123 | 1539 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 3 hrs | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1537 | 1540 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves
7124 | 1540 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix | 2 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1539 | 1541 |  | Angie Robertson,Jimmy Cox
7125 | 1541 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Coordinate Knowledge Base Update | 2 hrs | 5 days | Tue 6/11/24 | Mon 6/17/24 | 1540 |  |  | Jennifer Reeves,Daylin Reyes | Successor TBD | TW
7126 | 1542 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Task Instructions & Communication for Error Matrix | 2 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1535 | 1543 |  | Jennifer Reeves,Nikki Klein
7127 | 1543 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Communication for Error Matrix | 2 hrs | 10 days | Mon 5/20/24 | Mon 6/3/24 | 1542 | 1544 |  | Dusti Kincl,Angie Robertson
7128 | 1544 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Task Instructions & Communication for Error Matrix | 2 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1543 | 15061545 |  | Jennifer Grant,Jennifer Reeves
7129 | 1545 | Future Task |  | RW-Communication | I-WP104 | Jennifer Reeves | Create | I-WP104 Share Communication for Error Matrix | 1 hr | 2 days | Tue 6/11/24 | Wed 6/12/24 | 1544 | 1506 |  | Dusti Kincl
6862 | 1546 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 - Maintain Catalogs | 239 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24 |  |  |  |  | Do we need this header? This appears to be a header that includes the three I-WPs for maintaining catalogs (reports, interfaces, and conversions). Since they each have their own number, I recommend removing this header. | Angie
6863 | 1547 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 - Report Catalog | 16 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6864 | 1548 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | WPED I-WP105 - Report Catalog - Create | 2 hrs | 10 days | Fri 6/9/23 | Thu 6/22/23 | 1 | 1549 |  | Jennifer Grant,Jennifer Reeves
6865 | 1549 | Future Task |  |  | I-WP105 | Jennifer Reeves | Submit | WPED I-WP105 - Report Catalog - Submit | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 1548 | 1550 |  | Jennifer Grant,Jennifer Reeves
6866 | 1550 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WPED I-WP105 - Report Catalog - Collaborative Review & Update | 8 hrs | 10 days | Fri 6/23/23 | Fri 7/7/23 | 1549 | 1551 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Reeves,Jennifer Grant
6867 | 1551 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | WPED I-WP105 - Report Catalog - Approve | 0 hrs | 0 days | Fri 7/7/23 | Fri 7/7/23 | 1550 |  |  | Jimmy Cox | Successor UID - 6875 | TW
6868 | 1552 | Future Task |  |  | I-WP105 | Jennifer Reeves | Submit | WP I-WP105 - Report Catalog - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 15751588 | 1553 |  | Jennifer Grant,Jennifer Reeves
6869 | 1553 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP I-WP105 - Report Catalog - Department QC | 1 hr | 1 day | Thu 6/13/24 | Thu 6/13/24 | 1552 | 1554 |  | Jenifer Hartsfield
6870 | 1554 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP I-WP105 - Report Catalog - Collaborative Review & Update | 2 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1553 | 1555 |  | Jennifer Grant,Jennifer Reeves
6871 | 1555 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP I-WP105 - Report Catalog - Style Guide Review | 1 hr | 1 day | Fri 6/28/24 | Fri 6/28/24 | 1554 | 1556 |  | Tatiana Eubanks
6872 | 1556 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP I-WP105 - Report Catalog - Final Review & Update | 2 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 1555 | 1557 |  | Angie Robertson,Jimmy Cox
6873 | 1557 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | WP I-WP105 - Report Catalog - Approve | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1556 |  |  | Jimmy Cox
6874 | 1558 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 1 - Reports | 35 hrs | 20 days | Tue 7/18/23 | Mon 8/14/23
6875 | 1559 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | Tue 7/18/23 | Mon 8/7/23 | 42SS | 1560 |  | Pradeep Koul,Tanya McCarty,Stanton Beazley,Jennifer Reeves,Elizabeth Sargent
6876 | 1560 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | Tue 8/8/23 | Mon 8/14/23 | 1559 |  |  | Jennifer Grant,Jennifer Reeves | Successor UID - 6878 | TW
6877 | 1561 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 2 - Reports | 35 hrs | 20 days | Mon 10/9/23 | Fri 11/3/23
6878 | 1562 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | Mon 10/9/23 | Fri 10/27/23 | 61SS | 1563 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6879 | 1563 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | Mon 10/30/23 | Fri 11/3/23 | 1562 |  |  | Jennifer Grant,Jennifer Reeves | Successor UID - 6881 | TW
6880 | 1564 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 3 - Reports | 55 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
6881 | 1565 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 140SS | 1566 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6882 | 1566 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1565 | 15671573 |  | Jennifer Grant,Jennifer Reeves
6883 | 1567 | Future Task |  |  |  | Jennifer Reeves | Review | I-WP105 Collaborative Review - Functional Teams | 20 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1566 | 1569 |  | Jennifer Grant,Jennifer Reeves,Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
6884 | 1568 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Update & Publish Report Catalog | 41 hrs | 22 days | Fri 2/9/24 | Mon 3/11/24
6885 | 1569 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Report Catalog | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1567 | 1570 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6886 | 1570 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Report Catalog | 2 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1569 | 1571 |  | Jimmy Cox
6887 | 1571 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Coordinate Knowledge Base Update | 18 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1570 | 1572 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6888 | 1572 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Publish - Report Catalog | 4 hrs | 2 days | Fri 3/8/24 | Mon 3/11/24 | 1571 |  |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes | Successor UID - 686894 | TW
6889 | 1573 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Create Communication for Report Catalog | 2 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1566 | 1574 |  | Jennifer Grant,Jennifer Reeves
6890 | 1574 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review for Communication | 3 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1573 | 1575 |  | Dusti Kincl,Angie Robertson,Jennifer Reeves
6891 | 1575 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Communication for Report Catalog | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1574 | 15521576 |  | Jimmy Cox
6892 | 1576 | Future Task |  | RW-Communication | I-WP105 | Jennifer Reeves | Create | I-WP105 Share Communication for Report Catalog | 1 hr | 2 days | Fri 3/1/24 | Mon 3/4/24 | 1575 |  |  | Dusti Kincl | Successor UID - 6894 | TW
6893 | 1577 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 4 - Reports | 32 hrs | 27 days | Mon 4/22/24 | Wed 5/29/24
6894 | 1578 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 10 hrs | 16 days | Mon 4/22/24 | Mon 5/13/24 | 159SS | 1579 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
6895 | 1579 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 2 hrs | 6 days | Tue 5/14/24 | Tue 5/21/24 | 1578 | 15801586 |  | Jennifer Grant,Jennifer Reeves
6896 | 1580 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Functional Teams | 20 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1579 | 1582 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6897 | 1581 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Update & Publish Report Catalog | 25 hrs | 22 days | Wed 5/22/24 | Fri 6/21/24
6898 | 1582 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Report Catalog | 10 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1580 | 1583 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6899 | 1583 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Report Catalog | 1 hr | 5 days | Thu 6/6/24 | Wed 6/12/24 | 1582 | 1584 |  | Jimmy Cox
6900 | 1584 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Coordinate Knowledge Base Update | 3 hrs | 5 days | Thu 6/13/24 | Wed 6/19/24 | 1583 | 1585 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6901 | 1585 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Publish - Report Catalog | 4 hrs | 2 days | Thu 6/20/24 | Fri 6/21/24 | 1584 |  |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6902 | 1586 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Create Communication for Report Catalog | 2 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1579 | 1587 |  | Jennifer Grant,Jennifer Reeves
6903 | 1587 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review for Communication | 3 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1586 | 1588 |  | Dusti Kincl,Angie Robertson,Jennifer Reeves
6904 | 1588 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Communication for Report Catalog | 1 hr | 5 days | Thu 6/6/24 | Wed 6/12/24 | 1587 | 15521589 |  | Jimmy Cox
6905 | 1589 | Future Task |  | RW-Communication | I-WP105 | Jennifer Reeves | Create | I-WP105 Share Communication for Report Catalog | 1 hr | 2 days | Thu 6/13/24 | Fri 6/14/24 | 1588 |  |  | Dusti Kincl
6953 | 1590 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 - Interface Catalog | 167 hrs | 265 days | Fri 6/9/23 | Wed 6/26/24
6954 | 1591 | Future Task |  |  | I-WP106 | Matt Breeding | Create | WPED I-WP106 - Interface Catalog - Create | 10 hrs | 10 days | Fri 6/9/23 | Thu 6/22/23 | 1 | 1592 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding
6955 | 1592 | Future Task |  |  | I-WP106 | Matt Breeding | Submit | WPED I-WP106 - Interface Catalog - Submit | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 1591 | 1593 |  | Matthew Breeding
6956 | 1593 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WPED I-WP106 - Interface Catalog - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/23/23 | Fri 7/7/23 | 1592 | 1594 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
6957 | 1594 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | WPED I-WP106 - Interface Catalog - Approve | 0 hrs | 0 days | Fri 7/7/23 | Fri 7/7/23 | 1593 |  |  | Jimmy Cox | Successor UID - 6966 | TW
6958 | 1595 | Future Task |  |  | I-WP106 | Matt Breeding | Submit | WP I-WP106 - Interface Catalog - Submit | 0 hrs | 0 days | Mon 6/3/24 | Mon 6/3/24 | 1631 | 1596 |  | Matthew Breeding | This series of submit and review tasks should be after the create tasks below. | Angie
6959 | 1596 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP I-WP106 - Interface Catalog - Department QC | 1 hr | 1 day | Tue 6/4/24 | Tue 6/4/24 | 1595 | 1597 |  | Gabriela Gibson
6960 | 1597 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP I-WP106 - Interface Catalog - Collaborative Review & Update | 10 hrs | 10 days | Wed 6/5/24 | Tue 6/18/24 | 1596 | 1598 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
6961 | 1598 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP I-WP106 - Interface Catalog - Style Guide Review | 2 hrs | 1 day | Wed 6/19/24 | Wed 6/19/24 | 1597 | 1599 |  | Tatiana Eubanks
6962 | 1599 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP I-WP106 - Interface Catalog - Final Review & Update | 10 hrs | 5 days | Thu 6/20/24 | Wed 6/26/24 | 1598 | 1600 |  | Angie Robertson,Jimmy Cox
6963 | 1600 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | WP I-WP106 - Interface Catalog - Approve | 0 hrs | 0 days | Wed 6/26/24 | Wed 6/26/24 | 1599 |  |  | Jimmy Cox
6964 | 1601 | Future Task |  |  | I-WP106 | Matt Breeding |  | Interface Catalog | 124 hrs | 229 days | Tue 7/18/23 | Wed 6/12/24
6965 | 1602 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 1 - Interfaces | 12 hrs | 20 days | Tue 7/18/23 | Mon 8/14/23
6966 | 1603 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Tue 7/18/23 | Mon 8/7/23 | 42SS | 1604 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6967 | 1604 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Tue 8/8/23 | Mon 8/14/23 | 1603 |  |  | Matthew Breeding | Successor UID - 6969 | TW
6968 | 1605 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 2 - Interfaces | 12 hrs | 20 days | Wed 10/11/23 | Tue 11/7/23
6969 | 1606 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Wed 10/11/23 | Tue 10/31/23 | 61SS+2 days | 1607 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6970 | 1607 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Wed 11/1/23 | Tue 11/7/23 | 1606 |  |  | Matthew Breeding | Successor UID - 6972 | TW
6971 | 1608 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 3 - Interfaces | 22 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
6972 | 1609 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 140SS | 1610 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6973 | 1610 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1609 | 16111617 |  | Matthew Breeding
6974 | 1611 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Functional Teams | 10 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1610 | 1613 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
6975 | 1612 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Update & Publish Interface Catalog | 45 hrs | 24 days | Fri 2/9/24 | Wed 3/13/24
6976 | 1613 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Interface Catalog | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1611 | 1614 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6977 | 1614 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Interface Catalog | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1613 | 1615 |  | Jimmy Cox
6978 | 1615 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Coordinate Knowledge Base Update | 10 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1614 | 1616 |  | Matthew Breeding,Daylin Reyes
6979 | 1616 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Publish - Interface Catalog | 10 hrs | 2 days | Fri 3/8/24 | Mon 3/11/24 | 1615 | 1620 |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
6980 | 1617 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Create Communication for Interface Catalog | 2 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1610 | 1618 |  | Matthew Breeding,Dusti Kincl
6981 | 1618 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review for Communication for Interface Catalog | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1617 | 1619 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6982 | 1619 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Communication for Interface Catalog | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1618 |  |  | Jimmy Cox | Successor UID - 6983 | TW
6983 | 1620 | Future Task |  | RW-Communication | I-WP106 | Matt Breeding | Create | I-WP106 Share Communication for Interface Catalog | 1 hr | 2 days | Tue 3/12/24 | Wed 3/13/24 | 1616 |  |  | Dusti Kincl | Successor UID - 6985 | TW
6984 | 1621 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 4 - Interfaces | 12 hrs | 20 days | Mon 4/22/24 | Fri 5/17/24
6985 | 1622 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Mon 4/22/24 | Fri 5/10/24 | 159SS | 16231629 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6986 | 1623 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1622 | 1625 |  | Matthew Breeding
6987 | 1624 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Update & Publish Interface Catalog | 21 hrs | 22 days | Mon 5/13/24 | Wed 6/12/24
6988 | 1625 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Interface Catalog | 10 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1623 | 1626 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6989 | 1626 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Interface Catalog | 1 hr | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1625 | 1627 |  | Jimmy Cox
6990 | 1627 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Coordinate Knowledge Base Update | 2 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1626 | 1628 |  | Matthew Breeding,Daylin Reyes
6991 | 1628 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Publish Interface Catalog | 1 hr | 2 days | Tue 6/11/24 | Wed 6/12/24 | 1627 |  |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
6992 | 1629 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Create Communication for Interface Catalog | 2 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1622 | 1630 |  | Matthew Breeding,Dusti Kincl
6993 | 1630 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review for Communication for Interface Catalog | 3 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1629 | 1631 |  | Dusti Kincl,Angie Robertson,Matthew Breeding
6994 | 1631 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Communication for Interface Catalog | 1 hr | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1630 | 15951632 |  | Jimmy Cox
6995 | 1632 | Future Task |  | RW-Communication | I-WP106 | Matt Breeding | Create | I-WP106 Share Communication for Interface Catalog | 1 hr | 2 days | Tue 6/4/24 | Wed 6/5/24 | 1631 |  |  | Dusti Kincl | Successor UID - 4838 (We may need something earlier) | TW
6996 | 1633 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 - Conversions Inventory | 167 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6997 | 1634 | Future Task |  |  | I-WP107 | Matt Breeding | Create | WPED I-WP107 - Conversions Inventory - Create | 10 hrs | 10 days | Fri 6/9/23 | Thu 6/22/23 | 1 | 1635 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding
6998 | 1635 | Future Task |  |  | I-WP107 | Matt Breeding | Submit | WPED I-WP107 - Conversions Inventory - Submit | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 1634 | 1636 |  | Matthew Breeding
6999 | 1636 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WPED I-WP107 - Conversions Inventory - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/23/23 | Fri 7/7/23 | 1635 | 1637 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7000 | 1637 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | WPED I-WP107 - Conversions Inventory - Approve | 0 hrs | 0 days | Fri 7/7/23 | Fri 7/7/23 | 1636 |  |  | Jimmy Cox | Successor UID - 7009
7001 | 1638 | Future Task |  |  | I-WP107 | Matt Breeding | Submit | WP I-WP107 - Conversions Inventory - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 1674 | 1639 |  | Matthew Breeding
7002 | 1639 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP I-WP107 - Conversions Inventory - Department QC | 1 hr | 1 day | Thu 6/13/24 | Thu 6/13/24 | 1638 | 1640 |  | Gabriela Gibson
7003 | 1640 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP I-WP107 - Conversions Inventory - Collaborative Review & Update | 10 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1639 | 1641 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7004 | 1641 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP I-WP107 - Conversions Inventory - Style Guide Review | 2 hrs | 1 day | Fri 6/28/24 | Fri 6/28/24 | 1640 | 1642 |  | Tatiana Eubanks
7005 | 1642 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP I-WP107 - Conversions Inventory - Final Review & Update | 10 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 1641 | 1643 |  | Angie Robertson,Jimmy Cox
7006 | 1643 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | WP I-WP107 - Conversions Inventory - Approve | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1642 |  |  | Jimmy Cox
7007 | 1644 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Conversions Inventory | 124 hrs | 234 days | Tue 7/18/23 | Wed 6/19/24
7008 | 1645 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 1 - Conversions | 11 hrs | 20 days | Tue 7/18/23 | Mon 8/14/23
7009 | 1646 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | Tue 7/18/23 | Mon 8/7/23 | 42SS | 1647 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7010 | 1647 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 1 hr | 5 days | Tue 8/8/23 | Mon 8/14/23 | 1646 |  |  | Matthew Breeding | Successor - UID 7012 | TW
7011 | 1648 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 2 - Conversions | 15 hrs | 20 days | Mon 10/16/23 | Mon 11/13/23
7012 | 1649 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | Mon 10/16/23 | Fri 11/3/23 | 61SS+5 days | 1650 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7013 | 1650 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 5 hrs | 5 days | Mon 11/6/23 | Mon 11/13/23 | 1649 |  |  | Matthew Breeding | Successor - UID 7015 | TW
7014 | 1651 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 3 - Conversions | 25 hrs | 25 days | Fri 1/19/24 | Thu 2/22/24
7015 | 1652 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | Fri 1/19/24 | Thu 2/8/24 | 140SS+5 days | 1653 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7016 | 1653 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 5 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1652 | 16541660 |  | Matthew Breeding
7017 | 1654 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Functional Teams | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1653 | 1656 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
7018 | 1655 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Update & Publish Conversion Catalog | 26 hrs | 27 days | Fri 2/16/24 | Mon 3/25/24
7019 | 1656 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Conversion Catalog | 10 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1654 | 1657 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7020 | 1657 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Conversion Catalog | 1 hr | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1656 | 1658 |  | Jimmy Cox
7021 | 1658 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Coordinate Knowledge Base Update | 2 hrs | 5 days | Fri 3/8/24 | Thu 3/14/24 | 1657 | 1659 |  | Matthew Breeding,Daylin Reyes
7022 | 1659 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Publish - Conversion Catalog | 4 hrs | 5 days | Fri 3/15/24 | Thu 3/21/24 | 1658 | 1663 |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
7023 | 1660 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create Communication for Conversion Catalog | 2 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1653 | 1661 |  | Matthew Breeding,Dusti Kincl
7024 | 1661 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review for Communication for Conversion Catalog | 5 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1660 | 1662 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7025 | 1662 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Communication | 1 hr | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1661 |  |  | Jimmy Cox | Successor - UID 7026 | TW
7026 | 1663 | Future Task |  | RW-Communication | I-WP107 | Matt Breeding | Create | I-WP107 Share Communication | 1 hr | 2 days | Fri 3/22/24 | Mon 3/25/24 | 1659 |  |  | Dusti Kincl | Successor - UID 7028 | TW
7027 | 1664 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 4 - Conversions | 15 hrs | 25 days | Mon 4/29/24 | Mon 6/3/24
7028 | 1665 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create & Maintain - Conversion Catalog | 10 hrs | 15 days | Mon 4/29/24 | Fri 5/17/24 | 159SS+5 days | 1666 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7029 | 1666 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 1 hr | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1665 | 16671672 |  | Matthew Breeding
7030 | 1667 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Functional Teams | 4 hrs | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1666 | 1669 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
7031 | 1668 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Update & Publish Conversions Catalog | 32 hrs | 17 days | Tue 5/28/24 | Wed 6/19/24
7032 | 1669 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Conversion Catalog | 10 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1667 | 1670 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7033 | 1670 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Conversion Catalog | 1 hr | 5 days | Tue 6/11/24 | Mon 6/17/24 | 1669 | 1671 |  | Jimmy Cox
7034 | 1671 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Publish - Conversion Catalog | 4 hrs | 2 days | Tue 6/18/24 | Wed 6/19/24 | 1670 |  |  | Daylin Reyes,Richard Saltford,Pradeep Koul,Dusti Kincl | Successor - D651 – Execute Mock 1 – Conversion | TW
7035 | 1672 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create Communication for Conversions Catalog | 3 hrs | 2 days | Tue 5/28/24 | Wed 5/29/24 | 1666 | 1673 |  | Dusti Kincl,Pradeep Koul,Richard Barnes
7036 | 1673 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review for Communication for Conversions Catalog | 10 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1672 | 1674 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Nikki Klein,Daylin Reyes,Jennifer Grant
7037 | 1674 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Communication | 3 hrs | 5 days | Thu 6/6/24 | Wed 6/12/24 | 1673 | 16381675 |  | Dusti Kincl,Angie Robertson,Matthew Breeding
7038 | 1675 | Future Task |  | RW-Communication | I-WP107 | Matt Breeding | Create | I-WP107 Share Communication for Conversions Catalog | 1 hr | 5 days | Thu 6/13/24 | Wed 6/19/24 | 1674 |  |  | Jimmy Cox | Successor - D651 – Execute Mock 1 – Conversion | TW
2973 | 1676 | On Schedule |  |  | I-WP108 | Kimberly Kemp |  | I-WP108 - Training Curriculum | 53 hrs | 360 days | Thu 6/1/23 | Thu 10/31/24
2974 | 1677 | On Schedule |  |  | I-WP108 | Carolyn Hicks | Create | WPED I-WP108 - Training Curriculum - Create | 10 hrs | 10 days | Thu 6/1/23 | Wed 6/14/23 | 1 | 1678 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
2975 | 1678 | Future Task |  |  | I-WP108 | Carolyn Hicks | Submit | WPED I-WP108 - Training Curriculum - Submit | 0 hrs | 0 days | Wed 6/14/23 | Wed 6/14/23 | 1677 | 1679 |  | Carolyn Hicks
2976 | 1679 | Future Task |  |  | I-WP108 | Carolyn Hicks | Review | WPED I-WP108 - Training Curriculum - Collaborative Review & Update | 10 hrs | 10 days | Thu 6/15/23 | Wed 6/28/23 | 1678 | 1680 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
2977 | 1680 | Future Task |  |  | I-WP108 | Carolyn Hicks | Approve | WPED I-WP108 - Training Curriculum - Approve | 0 hrs | 0 days | Wed 6/28/23 | Wed 6/28/23 | 1679 | 1681 |  | Angie Robertson,Jimmy Cox
5689 | 1681 | Future Task |  |  | I-WP108 | Kimberly Kemp | Create | I-WP108 Training Curriculum <Activities per WPED> | 10 hrs | 287 days | Mon 8/21/23 | Tue 10/8/24 | 1680,48 | 1682,1693SS+30 days |  | Kimberly Kemp
2978 | 1682 | Future Task |  |  | I-WP108 | Kimberly Kemp | Submit | WP I-WP108 - Training Curriculum - Submit | 0 hrs | 0 days | Tue 10/8/24 | Tue 10/8/24 | 1681 | 1683 |  | Kimberly Kemp
2979 | 1683 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | WP I-WP108 - Training Curriculum - Department QC | 1 hr | 1 day | Wed 10/9/24 | Wed 10/9/24 | 1682 | 1684 |  | Tommy Werner
2980 | 1684 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | WP I-WP108 - Training Curriculum - Collaborative Review & Update | 10 hrs | 10 days | Thu 10/10/24 | Wed 10/23/24 | 1683 | 1685 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
2981 | 1685 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | WP I-WP108 - Training Curriculum - Style Guide Review | 2 hrs | 1 day | Thu 10/24/24 | Thu 10/24/24 | 1684 | 1686 |  | Dusti Kincl
2982 | 1686 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | WP I-WP108 - Training Curriculum - Final Review & Update | 10 hrs | 5 days | Fri 10/25/24 | Thu 10/31/24 | 1685 | 1687 |  | Angie Robertson,Jimmy Cox
2983 | 1687 | Future Task |  |  | I-WP108 | Kimberly Kemp | Approve | WP I-WP108 - Training Curriculum - Approve | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 1686 |  |  | Jimmy Cox | RW? Will this be shared with agencies, so they can begin planning for agency-specific training? Successor Training Design 109 | NK
2984 | 1688 | Future Task |  |  | I-WP109 | Kimberly Kemp |  | I-WP109 - Training Designs | 66 hrs | 315 days | Mon 7/3/23 | Mon 9/30/24
2985 | 1689 | Future Task |  |  | I-WP109 | Carolyn Hicks | Create | WPED I-WP109 - Training Designs - Create | 10 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 1 | 1690 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila
2986 | 1690 | Future Task |  |  | I-WP109 | Carolyn Hicks | Submit | WPED I-WP109 - Training Designs - Submit | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 1689 | 1691 |  | Carolyn Hicks
2987 | 1691 | Future Task |  |  | I-WP109 | Carolyn Hicks | Review | WPED I-WP109 - Training Designs - Collaborative Review & Update | 10 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 1690 | 1692 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
2988 | 1692 | Future Task |  |  | I-WP109 | Carolyn Hicks | Approve | WPED I-WP109 - Training Designs - Approve | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 1691 | 1693 |  | Angie Robertson,Jimmy Cox
5690 | 1693 | Future Task |  |  | I-WP109 | Kimberly Kemp | Create | I-WP109 Training Designs <Activities per WPED> | 10 hrs | 234 days | Tue 10/3/23 | Thu 9/5/24 | 1692,1681SS+30 days | 1694,1705SS |  | Kimberly Kemp
2989 | 1694 | Future Task |  |  | I-WP109 | Kimberly Kemp | Submit | WP I-WP109 - Training Designs - Submit | 0 hrs | 0 days | Thu 9/5/24 | Thu 9/5/24 | 1693 | 1695 |  | Kimberly Kemp
2990 | 1695 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | WP I-WP109 - Training Designs - Department QC | 8 hrs | 1 day | Fri 9/6/24 | Fri 9/6/24 | 1694 | 1696 |  | Gabriela Gibson
2991 | 1696 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | WP I-WP109 - Training Designs - Collaborative Review & Update | 10 hrs | 10 days | Mon 9/9/24 | Fri 9/20/24 | 1695 | 1697 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
2992 | 1697 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | WP I-WP109 - Training Designs - Style Guide Review | 8 hrs | 1 day | Mon 9/23/24 | Mon 9/23/24 | 1696 | 1698 |  | Tatiana Eubanks
2993 | 1698 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | WP I-WP109 - Training Designs - Final Review & Update | 10 hrs | 5 days | Tue 9/24/24 | Mon 9/30/24 | 1697 | 1699 |  | Angie Robertson,Jimmy Cox
2994 | 1699 | Future Task |  |  | I-WP109 | Kimberly Kemp | Approve | WP I-WP109 - Training Designs - Approve | 0 hrs | 0 days | Mon 9/30/24 | Mon 9/30/24 | 1698 | 1767 |  | Jimmy Cox
2995 | 1700 | Future Task |  |  | I-WP110 | Kimberly Kemp |  | I-WP110 - Training Build | 136 hrs | 401 days | Fri 3/1/24 | Tue 9/30/25
2996 | 1701 | Future Task |  |  | I-WP110 | Carolyn Hicks | Create | WPED I-WP110 - Training Build - Create | 10 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 1 | 1702 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
2997 | 1702 | Future Task |  |  | I-WP110 | Carolyn Hicks | Submit | WPED I-WP110 - Training Build - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 1701 | 1703 |  | Carolyn Hicks
2998 | 1703 | Future Task |  |  | I-WP110 | Carolyn Hicks | Review | WPED I-WP110 - Training Build - Collaborative Review & Update | 10 hrs | 10 days | Fri 3/15/24 | Thu 3/28/24 | 1702 | 1704 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
2999 | 1704 | Future Task |  |  | I-WP110 | Carolyn Hicks | Approve | WPED I-WP110 - Training Build - Approve | 0 hrs | 0 days | Thu 3/28/24 | Thu 3/28/24 | 1703 | 1705 |  | Angie Robertson,Jimmy Cox
5691 | 1705 | Future Task |  |  | I-WP110 | Kimberly Kemp | Create | I-WP110 Training Build <Activities per WPED> | 80 hrs | 364 days | Fri 3/29/24 | Fri 9/5/25 | 1704,1693SS | 1706 |  | Kimberly Kemp
3000 | 1706 | Future Task |  |  | I-WP110 | Kimberly Kemp | Submit | WP I-WP110 - Training Build - Submit | 0 hrs | 0 days | Fri 9/5/25 | Fri 9/5/25 | 1705 | 1707 |  | Kimberly Kemp | Why is this task a Milestone? | Angie
3001 | 1707 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | WP I-WP110 - Training Build - Department QC | 8 hrs | 1 day | Mon 9/8/25 | Mon 9/8/25 | 1706 | 1708 |  | Gabriela Gibson
3002 | 1708 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | WP I-WP110 - Training Build - Collaborative Review & Update | 10 hrs | 10 days | Tue 9/9/25 | Mon 9/22/25 | 1707 | 1709 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3003 | 1709 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | WP I-WP110 - Training Build - Style Guide Review | 8 hrs | 1 day | Tue 9/23/25 | Tue 9/23/25 | 1708 | 1710 |  | Tatiana Eubanks
3004 | 1710 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | WP I-WP110 - Training Build - Final Review & Update | 10 hrs | 5 days | Wed 9/24/25 | Tue 9/30/25 | 1709 | 1711 |  | Angie Robertson,Jimmy Cox
3005 | 1711 | Future Task |  |  | I-WP110 | Kimberly Kemp | Approve | WP I-WP110 - Training Build - Approve | 0 hrs | 0 days | Tue 9/30/25 | Tue 9/30/25 | 1710 |  |  | Jimmy Cox | Successor Training Measurement Report 114 | TW
3006 | 1712 | Future Task |  |  | I-WP111 | Kimberly Kemp |  | I-WP111 - UAT Training Materials | 129 hrs | 154 days | Thu 8/1/24 | Thu 3/13/25
3007 | 1713 | Future Task |  |  | I-WP111 | Carolyn Hicks | Create | WPED I-WP111 - UAT Training Materials - Create | 10 hrs | 10 days | Thu 8/1/24 | Wed 8/14/24 | 1 | 1714 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila
3008 | 1714 | Future Task |  |  | I-WP111 | Carolyn Hicks | Submit | WPEP I-WP111 - UAT Training Materials - Submit | 0 hrs | 0 days | Wed 8/14/24 | Wed 8/14/24 | 1713 | 1715 |  | Carolyn Hicks
3009 | 1715 | Future Task |  |  | I-WP111 | Carolyn Hicks | Review | WPED I-WP111 - UAT Training Materials - Collaborative Review & Update | 10 hrs | 10 days | Thu 8/15/24 | Wed 8/28/24 | 1714 | 1716 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
3010 | 1716 | Future Task |  |  | I-WP111 | Carolyn Hicks | Approve | WPED I-WP111 - UAT Training Materials - Approve | 0 hrs | 0 days | Wed 8/28/24 | Wed 8/28/24 | 1715 | 1717 |  | Angie Robertson,Jimmy Cox
5692 | 1717 | Future Task |  |  | I-WP111 | Kimberly Kemp | Create | I-WP111 UAT Training Materials <Activities per WPED> | 80 hrs | 117 days | Thu 8/29/24 | Tue 2/18/25 | 1716 | 1718 |  | Kimberly Kemp
3011 | 1718 | Future Task |  |  | I-WP111 | Kimberly Kemp | Submit | WP I-WP111 - UAT Training Materials - Submit | 0 hrs | 0 days | Tue 2/18/25 | Tue 2/18/25 | 1717 | 1719 |  | Kimberly Kemp
3012 | 1719 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | WP I-WP111 - UAT Training Materials - Department QC | 1 hr | 1 day | Wed 2/19/25 | Wed 2/19/25 | 1718 | 1720 |  | Tommy Werner
3013 | 1720 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | WP I-WP111 - UAT Training Materials - Collaborative Review & Update | 10 hrs | 10 days | Thu 2/20/25 | Wed 3/5/25 | 1719 | 1721 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3014 | 1721 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | WP I-WP111 - UAT Training Materials - Style Guide Review | 8 hrs | 1 day | Thu 3/6/25 | Thu 3/6/25 | 1720 | 1722 |  | Tatiana Eubanks
3015 | 1722 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | WP I-WP111 - UAT Training Materials - Final Review & Update | 10 hrs | 5 days | Fri 3/7/25 | Thu 3/13/25 | 1721 | 1723 |  | Angie Robertson,Jimmy Cox
3016 | 1723 | Future Task |  |  | I-WP111 | Kimberly Kemp | Approve | WP I-WP111 - UAT Training Materials - Approve | 0 hrs | 0 days | Thu 3/13/25 | Thu 3/13/25 | 1722 | 1724 |  | Jimmy Cox
3017 | 1724 | Future Task |  |  | I-WP111 | Kimberly Kemp | Milestone | WP I-WP111 - UAT Training Materials - Complete | 0 hrs | 0 days | Thu 3/13/25 | Thu 3/13/25 | 1723 | 1252 |  | Kimberly Kemp | Why is this task a Milestone? | Angie
3018 | 1725 | Future Task |  |  | I-WP112 | Kimberly Kemp |  | I-WP112 - End User Manual | 143 hrs | 210 days | Fri 1/31/25 | Wed 11/26/25 |  |  |  |  | RW/Comms - share with agencies - | NK
3019 | 1726 | Future Task |  |  | I-WP112 | Carolyn Hicks | Create | WPED I-WP112 - End User Manual - Create | 10 hrs | 10 days | Fri 1/31/25 | Thu 2/13/25 | 1 | 1727 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3020 | 1727 | Future Task |  |  | I-WP112 | Carolyn Hicks | Submit | WPED I-WP112 - End User Manual - Submit | 0 hrs | 0 days | Thu 2/13/25 | Thu 2/13/25 | 1726 | 1728 |  | Carolyn Hicks
3021 | 1728 | Future Task |  |  | I-WP112 | Carolyn Hicks | Review | WPED I-WP112 - End User Manual - Collaborative Review & Update | 10 hrs | 10 days | Fri 2/14/25 | Thu 2/27/25 | 1727 | 1729 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3022 | 1729 | Future Task |  |  | I-WP112 | Carolyn Hicks | Approve | WPED I-WP112 - End User Manual - Approve | 0 hrs | 0 days | Thu 2/27/25 | Thu 2/27/25 | 1728 | 1730 |  | Angie Robertson,Jimmy Cox
5693 | 1730 | Future Task |  |  | I-WP112 | Kimberly Kemp | Create | I-WP112 End User Manual <Activities per WPED> | 100 hrs | 173 days | Fri 2/28/25 | Fri 10/31/25 | 1729651 | 1731 |  | Kimberly Kemp
3023 | 1731 | Future Task |  |  | I-WP112 | Kimberly Kemp | Submit | WP I-WP112 - End User Manual - Submit | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 1730 | 1732 |  | Kimberly Kemp
3024 | 1732 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | WP I-WP112 - End User Manual - Department QC | 1 hr | 1 day | Mon 11/3/25 | Mon 11/3/25 | 1731 | 1733 |  | Tommy Werner
3025 | 1733 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | WP I-WP112 - End User Manual - Collaborative Review & Update | 10 hrs | 10 days | Tue 11/4/25 | Tue 11/18/25 | 1732 | 1734 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3026 | 1734 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | WP I-WP112 - End User Manual - Style Guide Review | 2 hrs | 1 day | Wed 11/19/25 | Wed 11/19/25 | 1733 | 1735 |  | Tatiana Eubanks
3027 | 1735 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | WP I-WP112 - End User Manual - Final Review & Update | 10 hrs | 5 days | Thu 11/20/25 | Wed 11/26/25 | 1734 | 1736 |  | Angie Robertson,Jimmy Cox
3028 | 1736 | Future Task |  |  | I-WP112 | Kimberly Kemp | Approve | WP I-WP112 - End User Manual - Approve | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 1735 | 1737 |  | Jimmy Cox
3029 | 1737 | Future Task |  |  | I-WP112 | Kimberly Kemp | Milestone | WP I-WP112 - End User Manual - Complete | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 1736 |  |  | Kimberly Kemp | Why is this task a Milestone? Successor - User Support Labs 116 | TW
3030 | 1738 | Future Task |  |  | I-WP113 | Kimberly Kemp |  | I-WP113 - ILT Training Delivery Plan | 156 hrs | 85 days | Thu 5/1/25 | Fri 8/29/25
3031 | 1739 | Future Task |  |  | I-WP113 | Carolyn Hicks | Create | WPED I-WP113 - ILT Training Delivery Plan - Create | 10 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 1 | 1740 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
3032 | 1740 | Future Task |  |  | I-WP113 | Carolyn Hicks | Submit | WPED I-WP113 - ILT Training Delivery Plan - Submit | 0 hrs | 0 days | Wed 5/14/25 | Wed 5/14/25 | 1739 | 1741 |  | Carolyn Hicks
3033 | 1741 | Future Task |  |  | I-WP113 | Carolyn Hicks | Review | WPED I-WP113 - ILT Training Delivery Plan - Collaborative Review & Update | 10 hrs | 10 days | Thu 5/15/25 | Thu 5/29/25 | 1740 | 1742 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
3034 | 1742 | Future Task |  |  | I-WP113 | Carolyn Hicks | Approve | WPED I-WP113- ILT Training Delivery Plan - Approve | 0 hrs | 0 days | Thu 5/29/25 | Thu 5/29/25 | 1741 | 1743 |  | Angie Robertson,Jimmy Cox
5694 | 1743 | Future Task |  |  | I-WP113 | Kimberly Kemp | Create | I-WP113 ILT Training Delivery Plan <Activities per WPED> | 100 hrs | 48 days | Fri 5/30/25 | Wed 8/6/25 | 1742 | 1744 |  | Kimberly Kemp
3035 | 1744 | Future Task |  |  | I-WP113 | Kimberly Kemp | Submit | WP I-WP113 - ILT Training Delivery Plan - Submit | 0 hrs | 0 days | Wed 8/6/25 | Wed 8/6/25 | 1743 | 1745 |  | Kimberly Kemp
3036 | 1745 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | WP I-WP113 - ILT Training Delivery Plan - Department QC | 8 hrs | 1 day | Thu 8/7/25 | Thu 8/7/25 | 1744 | 1746 |  | Gabriela Gibson
3037 | 1746 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | WP I-WP113 - ILT Training Delivery Plan - Collaborative Review & Update | 10 hrs | 10 days | Fri 8/8/25 | Thu 8/21/25 | 1745 | 1747 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3038 | 1747 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | WP I-WP113 - ILT Training Delivery Plan - Style Guide Review | 8 hrs | 1 day | Fri 8/22/25 | Fri 8/22/25 | 1746 | 1748 |  | Tatiana Eubanks
3039 | 1748 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | WP I-WP113 - ILT Training Delivery Plan - Final Review & Update | 10 hrs | 5 days | Mon 8/25/25 | Fri 8/29/25 | 1747 | 1749 |  | Angie Robertson,Jimmy Cox
3040 | 1749 | Future Task |  |  | I-WP113 | Kimberly Kemp | Approve | WP I-WP113 - ILT Training Delivery Plan - Approve | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 1748 |  |  | Jimmy Cox | Successor Training Measurement Report 114 | TW
3041 | 1750 | Future Task |  |  | I-WP114 | Kimberly Kemp |  | I-WP114 - Training Measurement Report | 143 hrs | 104 days | Wed 10/29/25 | Tue 3/31/26
3042 | 1751 | Future Task |  |  | I-WP114 | Carolyn Hicks | Create | WPED I-WP114 - Training Measurement Report - Create | 10 hrs | 10 days | Wed 10/29/25 | Wed 11/12/25 | 1 | 1752 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
3043 | 1752 | Future Task |  |  | I-WP114 | Kimberly Kemp | Submit | WPED I-WP114 - Training Measurement Report - Submit | 0 hrs | 0 days | Wed 11/12/25 | Wed 11/12/25 | 1751 | 1753 |  | Carolyn Hicks
3044 | 1753 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WPED I-WP114 - Training Measurement Report - Collaborative Review & Update | 10 hrs | 10 days | Thu 11/13/25 | Wed 11/26/25 | 1752 | 1754 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
3045 | 1754 | Future Task |  |  | I-WP114 | Kimberly Kemp | Approve | WPED I-WP114 - Training Measurement Report - Approve | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 1753 | 1755 |  | Angie Robertson,Jimmy Cox
5695 | 1755 | Future Task |  |  | I-WP114 | Kimberly Kemp | Create | I-WP114 Training Measurement Report <Activities per WPED> | 100 hrs | 67 days | Mon 12/1/25 | Fri 3/6/26 | 17541252 | 1756 |  | Kimberly Kemp
3046 | 1756 | Future Task |  |  | I-WP114 | Kimberly Kemp | Submit | WP I-WP114 - Training Measurement Report - Submit | 0 hrs | 0 days | Fri 3/6/26 | Fri 3/6/26 | 1755 | 1757 |  | Kimberly Kemp
3047 | 1757 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WP I-WP114 - Training Measurement Report - Department QC | 1 hr | 1 day | Mon 3/9/26 | Mon 3/9/26 | 1756 | 1758 |  | Tommy Werner
3048 | 1758 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WP I-WP114 - Training Measurement Report - Collaborative Review & Update | 10 hrs | 10 days | Tue 3/10/26 | Mon 3/23/26 | 1757 | 1759 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3049 | 1759 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WP I-WP114 - Training Measurement Report - Style Guide Review | 2 hrs | 1 day | Tue 3/24/26 | Tue 3/24/26 | 1758 | 1760 |  | Dusti Kincl
3050 | 1760 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WP I-WP114 - Training Measurement Report - Final Review & Update | 10 hrs | 5 days | Wed 3/25/26 | Tue 3/31/26 | 1759 | 1761 |  | Angie Robertson,Jimmy Cox
3051 | 1761 | Future Task |  |  | I-WP114 | Kimberly Kemp | Approve | WP I-WP114 - Training Measurement Report - Approve | 0 hrs | 0 days | Tue 3/31/26 | Tue 3/31/26 | 1760 |  |  | Jimmy Cox | Post Implementation Support Del Per talk on 6/8 we opted not to add a successor here. | TW
3052 | 1762 | Future Task |  |  | I-WP115 | Kimberly Kemp |  | I-WP115 - Train the Trainer | 156 hrs | 372 days | Fri 8/1/25 | Tue 1/26/27 |  |  |  |  | RW | NK
3053 | 1763 | Future Task |  |  | I-WP115 | Carolyn Hicks | Create | WPED I-WP115 - Train the Trainer - Create | 10 hrs | 10 days | Fri 8/1/25 | Thu 8/14/25 | 1 | 1764 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila | start should be 10/1/2024 | carolyn
3054 | 1764 | Future Task |  |  | I-WP115 | Carolyn Hicks | Submit | WPED I-WP115 - Train the Trainer - Submit | 0 hrs | 0 days | Thu 8/14/25 | Thu 8/14/25 | 1763 | 1765 |  | Carolyn Hicks | adjust as needed based on above | carolyn
3055 | 1765 | Future Task |  |  | I-WP115 | Carolyn Hicks | Review | WPED I-WP115 - Train the Trainer - Collaborative Review & Update | 10 hrs | 10 days | Fri 8/15/25 | Thu 8/28/25 | 1764 | 1766 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
3056 | 1766 | Future Task |  |  | I-WP115 | Carolyn Hicks | Approve | WPED I-WP115 - Train the Trainer - Approve | 0 hrs | 0 days | Thu 8/28/25 | Thu 8/28/25 | 1765 | 1767 |  | Angie Robertson,Jimmy Cox
5696 | 1767 | Future Task |  |  | I-WP115 | Kimberly Kemp | Create | I-WP115 Train the Trainer <Activities per WPED> | 100 hrs | 324 days | Fri 8/29/25 | Mon 12/14/26 | 17661699 | 1768FS+11 days |  | Kimberly Kemp | date range should be 2/1/2025 - 5/1/2025 | carolyn
3057 | 1768 | Future Task |  |  | I-WP115 | Kimberly Kemp | Submit | WP I-WP115 - Train the Trainer - Submit | 0 hrs | 0 days | Wed 12/30/26 | Wed 12/30/26 | 1767FS+11 days | 1769 |  | Kimberly Kemp | adjust as needed based on approve | carolyn
3058 | 1769 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | WP I-WP115 - Train the Trainer - Department QC | 8 hrs | 1 day | Thu 12/31/26 | Thu 12/31/26 | 1768 | 1770 |  | Gabriela Gibson
3059 | 1770 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | WP I-WP115 - Train the Trainer - Collaborative Review & Update | 10 hrs | 10 days | Mon 1/4/27 | Fri 1/15/27 | 1769 | 1771 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3060 | 1771 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | WP I-WP115 - Train the Trainer - Style Guide Review | 8 hrs | 1 day | Tue 1/19/27 | Tue 1/19/27 | 1770 | 1772 |  | Tatiana Eubanks
3061 | 1772 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | WP I-WP115 - Train the Trainer - Final Review & Update | 10 hrs | 5 days | Wed 1/20/27 | Tue 1/26/27 | 1771 | 1773 |  | Angie Robertson,Jimmy Cox
3062 | 1773 | Future Task |  |  | I-WP115 | Kimberly Kemp | Approve | WP I-WP115 - Train the Trainer - Approve | 0 hrs | 0 days | Tue 1/26/27 | Tue 1/26/27 | 1772 | 1774 |  | Jimmy Cox | this date should be 5/30/2025 | carolyn
3063 | 1774 | Future Task |  |  | I-WP115 | Kimberly Kemp | Milestone | WP I-WP115 - Train the Trainer - Complete | 0 hrs | 0 days | Tue 1/26/27 | Tue 1/26/27 | 1773 |  |  | Kimberly Kemp | Why is this task a Milestone? Move to 2025 | Angie
3064 | 1775 | Future Task |  |  | I-WP122 | Carolyn Hicks |  | I-WP122 - Update D33 Training Strategy | 143 hrs | 81 days | Wed 11/1/23 | Thu 2/29/24 |  |  |  |  | RW - update Traning approach to share with agencies? | NK
3065 | 1776 | Future Task |  |  | I-WP122 | Carolyn Hicks | Create | WPED I-WP122 - Update D33 Training Strategy - Create | 10 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23 | 1 | 1777 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3066 | 1777 | Future Task |  |  | I-WP122 | Carolyn Hicks | Submit | WPED I-WP122 - Update D33 Training Strategy - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 1776 | 1778 |  | Carolyn Hicks
3067 | 1778 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WPED I-WP122 - Update D33 Training Strategy - Collaborative Review & Update | 10 hrs | 10 days | Thu 11/16/23 | Fri 12/1/23 | 1777 | 1779 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3068 | 1779 | Future Task |  |  | I-WP122 | Carolyn Hicks | Approve | WPED I-WP122 - Update D33 Training Strategy - Approve | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 1778 | 1780 |  | Angie Robertson,Jimmy Cox
5697 | 1780 | Future Task |  |  | I-WP122 | Carolyn Hicks | Create | I-WP122 Update D33 Training Strategy <Activities per WPED> | 100 hrs | 44 days | Mon 12/4/23 | Tue 2/6/24 | 1779 | 1781 |  | Kimberly Kemp
3069 | 1781 | Future Task |  |  | I-WP122 | Carolyn Hicks | Submit | WP I-WP122 - Update D33 Training Strategy - Submit | 0 hrs | 0 days | Tue 2/6/24 | Tue 2/6/24 | 1780 | 1782 |  | Kimberly Kemp
3070 | 1782 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WP I-WP122 - Update D33 Training Strategy - Department QC | 1 hr | 1 day | Wed 2/7/24 | Wed 2/7/24 | 1781 | 1783 |  | Tommy Werner
3071 | 1783 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WP I-WP122 - Update D33 Training Strategy - Collaborative Review & Update | 10 hrs | 10 days | Thu 2/8/24 | Wed 2/21/24 | 1782 | 1784 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3072 | 1784 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WP I-WP122 - Update D33 Training Strategy - Style Guide Review | 2 hrs | 1 day | Thu 2/22/24 | Thu 2/22/24 | 1783 | 1785 |  | Dusti Kincl
3073 | 1785 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WP I-WP122 - Update D33 Training Strategy - Final Review & Update | 10 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1784 | 1786 |  | Angie Robertson,Jimmy Cox
3074 | 1786 | Future Task |  |  | I-WP122 | Carolyn Hicks | Approve | WP I-WP122 - Update D33 Training Strategy - Approve | 0 hrs | 0 days | Thu 2/29/24 | Thu 2/29/24 | 1785 |  |  | Jimmy Cox | Successor Training Curriculum 108 | TW
3075 | 1787 | Future Task |  |  | I-WP123 | Carolyn Hicks |  | I-WP123 - Update D112 Training Deployment and Measurement Plan | 149 hrs | 81 days | Wed 11/1/23 | Thu 2/29/24
3076 | 1788 | Future Task |  |  | I-WP123 | Carolyn Hicks | Create | WPED I-WP123 - Update D112 Training Deployment and Measurement Plan - Create | 10 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23 | 1 | 1789 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3077 | 1789 | Future Task |  |  | I-WP123 | Carolyn Hicks | Submit | WPED I-WP123 - Update D112 Training Deployment and Measurement Plan - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 1788 | 1790 |  | Carolyn Hicks
3078 | 1790 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WPED I-WP123 - Update D112 Training Deployment and Measurement Plan - Collaborative Review and Update | 10 hrs | 10 days | Thu 11/16/23 | Fri 12/1/23 | 1789 | 1791 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3079 | 1791 | Future Task |  |  | I-WP123 | Carolyn Hicks | Approve | WPED I-WP123 - Update D112 Training Deployment and Measurement Plan - Approve | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 1790 | 1792 |  | Angie Robertson,Jimmy Cox
5698 | 1792 | Future Task |  |  | I-WP123 | Carolyn Hicks | Create | I-WP123 Update D112 Training Deployment and Measurement Plan <Activities per WPED> | 100 hrs | 44 days | Mon 12/4/23 | Tue 2/6/24 | 1791 | 1793 |  | Kimberly Kemp
3080 | 1793 | Future Task |  |  | I-WP123 | Carolyn Hicks | Submit | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Submit | 0 hrs | 0 days | Tue 2/6/24 | Tue 2/6/24 | 1792 | 1794 |  | Kimberly Kemp
3081 | 1794 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Department QC | 1 hr | 1 day | Wed 2/7/24 | Wed 2/7/24 | 1793 | 1795 |  | Tommy Werner
3082 | 1795 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Collaborative Review & Update | 10 hrs | 10 days | Thu 2/8/24 | Wed 2/21/24 | 1794 | 1796 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3083 | 1796 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Style Guide Review | 8 hrs | 1 day | Thu 2/22/24 | Thu 2/22/24 | 1795 | 1797 |  | Tatiana Eubanks
3084 | 1797 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Final Review & Update | 10 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1796 | 1798 |  | Angie Robertson,Jimmy Cox
3085 | 1798 | Future Task |  |  | I-WP123 | Carolyn Hicks | Approve | WP I-WP123 - Update D112 Training Deployment and Measurement Plan - Approve | 0 hrs | 0 days | Thu 2/29/24 | Thu 2/29/24 | 1797 |  |  | Jimmy Cox | Successor Training Curriculum 108 | TW
6812 | 1799 | Future Task | [5 empty] | Training | 1 hr | 104 days | Tue 7/1/25 | Wed 11/26/25
6813 | 1800 | Future Task |  |  |  | Carolyn Hicks | Create | Conduct Training | 1 hr | 104 days | Tue 7/1/25 | Wed 11/26/25 | 1 |  | July - Nov 2025 | Carolyn Hicks | RW - Participate in Training | NK
3086 | 1801 | Late | [5 empty] | Readiness | 1,652 hrs | 730 days | Mon 5/8/23 | Tue 3/31/26
7183 | 1802 | Future Task |  |  | SG4 | Jimmy Cox |  | Stage Gate 4: Prepare Stage Gate Checklist | 6 hrs | 5 days | Thu 6/5/25 | Wed 6/11/25 |  | 1803 |  | Julian Gotreaux,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
7184 | 1803 | Future Task |  |  | SG4 | Jimmy Cox |  | Stage Gate 4: Collaborative Review and Update of Stage Gate Checklist | 10 hrs | 10 days | Thu 6/12/25 | Wed 6/25/25 | 1802 | 1804FS+77 days |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks
7185 | 1804 | Future Task |  |  | SG4 | Jimmy Cox |  | Stage Gate 4: Prepare information package for ESC | 11 hrs | 10 days | Wed 10/15/25 | Tue 10/28/25 | 1803FS+77 days | 1805 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7186 | 1805 | Future Task |  |  | SG4 | Jimmy Cox |  | Stage Gate 4: Collaborative Review and Update of information package | 11 hrs | 5 days | Wed 10/29/25 | Tue 11/4/25 | 1804 | 1806 |  | Jimmy Cox,Angie Robertson,Matt Cole,Sean Buchanan,Deana Metcalf,Stacey Terry,Matthew Breeding,Manojkumar Gurjar,Jennifer Reeves,Carolyn Hicks,Steven Fielder
7187 | 1806 | Future Task |  |  | SG4 | Jimmy Cox |  | Stage Gate 4: Provide Checklist and information package to the ESC | 1 hr | 1 day | Wed 11/5/25 | Wed 11/5/25 | 1805 |  |  | Dusti Kincl
7159 | 1807 | Future Task |  |  | SG4 | Jimmy Cox | Milestone | Stage Gate 4: Agency Readiness | 0 hrs | 0 days | Mon 11/3/25 | Mon 11/3/25 | 1 |  | November 2025 - ESC | Jimmy Cox,Angie Robertson,Matt Cole | This Milestone (Stage Gate) is to be approved by the ESC. We should show ESC as the Resource Name, instead of Jimmy, me, and Matt. | Angie
3087 | 1808 | Future Task |  |  | I-WP116 | Kimberly Kemp |  | I-WP116 - User Support Sessions | 156 hrs | 209 days | Mon 6/2/25 | Tue 3/31/26 |  |  |  |  | RW - agencies participate | NK
3088 | 1809 | Future Task |  |  | I-WP116 | Carolyn Hicks | Create | WPED I-WP116 - User Support Sessions - Create | 10 hrs | 10 days | Mon 6/2/25 | Fri 6/13/25 | 1 | 1810 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3089 | 1810 | Future Task |  |  | I-WP116 | Carolyn Hicks | Submit | WPED I-WP116 - User Support Sessions - Submit | 0 hrs | 0 days | Fri 6/13/25 | Fri 6/13/25 | 1809 | 1811 |  | Carolyn Hicks
3090 | 1811 | Future Task |  |  | I-WP116 | Carolyn Hicks | Review | WPED I-WP116 - User Support Sessions - Collaborative Review & Update | 10 hrs | 10 days | Mon 6/16/25 | Fri 6/27/25 | 1810 | 1812 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3091 | 1812 | Future Task |  |  | I-WP116 | Carolyn Hicks | Approve | WPED I-WP116 - User Support Sessions - Approve | 0 hrs | 0 days | Fri 6/27/25 | Fri 6/27/25 | 1811 | 1813 |  | Angie Robertson,Jimmy Cox
5699 | 1813 | Future Task |  |  | I-WP116 | Kimberly Kemp | Create | I-WP116 User Support Sessions <Activities per WPED> | 100 hrs | 172 days | Mon 6/30/25 | Fri 3/6/26 | 1812,1252SS+30 days | 1814 |  | Kimberly Kemp
3092 | 1814 | Future Task |  |  | I-WP116 | Kimberly Kemp | Submit | WP I-WP116 - User Support Sessions - Submit | 0 hrs | 0 days | Fri 3/6/26 | Fri 3/6/26 | 1813 | 1815 |  | Kimberly Kemp
3093 | 1815 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | WP I-WP116 - User Support Sessions - Department QC | 8 hrs | 1 day | Mon 3/9/26 | Mon 3/9/26 | 1814 | 1816 |  | Gabriela Gibson
3094 | 1816 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | WP I-WP116 - User Support Sessions - Collaborative Review & Update | 10 hrs | 10 days | Tue 3/10/26 | Mon 3/23/26 | 1815 | 1817 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3095 | 1817 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | WP I-WP116 - User Support Sessions - Style Guide Review | 8 hrs | 1 day | Tue 3/24/26 | Tue 3/24/26 | 1816 | 1818 |  | Tatiana Eubanks
3096 | 1818 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | WP I-WP116 - User Support Sessions - Final Review & Update | 10 hrs | 5 days | Wed 3/25/26 | Tue 3/31/26 | 1817 | 1819 |  | Angie Robertson,Jimmy Cox
3097 | 1819 | Future Task |  |  | I-WP116 | Kimberly Kemp | Approve | WP I-WP116 - User Support Sessions - Approve | 0 hrs | 0 days | Tue 3/31/26 | Tue 3/31/26 | 1818 |  |  | Jimmy Cox
3098 | 1820 | Future Task |  |  | I-WP117 | Nikki Klein |  | I-WP117 - Role Mapping Handbook | 149 hrs | 193 days | Thu 2/1/24 | Thu 10/31/24 |  |  |  |  | RW - Role Mapping | NK
3099 | 1821 | Future Task |  |  | I-WP117 | Carolyn Hicks | Create | WPED I-WP117- Role Mapping Handbook - Create | 10 hrs | 10 days | Thu 2/1/24 | Wed 2/14/24 | 1 | 1822 |  | Carolyn Hicks,Nikki Klein,Felicia Hall
3100 | 1822 | Future Task |  |  | I-WP117 | Carolyn Hicks | Submit | WPED I-WP117 - Role Mapping Handbook - Submit | 0 hrs | 0 days | Wed 2/14/24 | Wed 2/14/24 | 1821 | 1823 |  | Carolyn Hicks
3101 | 1823 | Future Task |  |  | I-WP117 | Carolyn Hicks | Review | WPED I-WP117 - Role Mapping Handbook - Collaborative Review & Update | 10 hrs | 10 days | Thu 2/15/24 | Wed 2/28/24 | 1822 | 1824 |  | Carolyn Hicks,Nikki Klein,Felicia Hall,Angie Robertson
3102 | 1824 | Future Task |  |  | I-WP117 | Carolyn Hicks | Approve | WPED I-WP117 - Role Mapping Handbook - Approve | 0 hrs | 0 days | Wed 2/28/24 | Wed 2/28/24 | 1823 | 1825 |  | Angie Robertson,Jimmy Cox
5700 | 1825 | Future Task |  |  | I-WP117 | Nikki Klein | Create | I-WP117 Role Mapping Handbook <Activities per WPED> | 100 hrs | 156 days | Thu 2/29/24 | Tue 10/8/24 | 1824109 | 1826,1837SS+40 days |  | Nikki Klein
3103 | 1826 | Future Task |  |  | I-WP117 | Nikki Klein | Submit | WP I-WP117 - Role Mapping Handbook - Submit | 0 hrs | 0 days | Tue 10/8/24 | Tue 10/8/24 | 1825 | 1827 |  | Nikki Klein
3104 | 1827 | Future Task |  |  | I-WP117 | Nikki Klein | Review | WP I-WP117 - Role Mapping Handbook - Department QC | 1 hr | 1 day | Wed 10/9/24 | Wed 10/9/24 | 1826 | 1828 |  | Gabriela Gibson
3105 | 1828 | Future Task |  |  | I-WP117 | Nikki Klein | Review | WP I-WP117 - Role Mapping Handbook - Collaborative Review & Update | 10 hrs | 10 days | Thu 10/10/24 | Wed 10/23/24 | 1827 | 1829 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3106 | 1829 | Future Task |  |  | I-WP117 | Nikki Klein | Review | WP I-WP117 - Role Mapping Handbook - Style Guide Review | 8 hrs | 1 day | Thu 10/24/24 | Thu 10/24/24 | 1828 | 1830 |  | Tatiana Eubanks
3107 | 1830 | Future Task |  |  | I-WP117 | Nikki Klein | Review | WP I-WP117 - Role Mapping Handbook - Final Review & Update | 10 hrs | 5 days | Fri 10/25/24 | Thu 10/31/24 | 1829 | 1831 |  | Angie Robertson,Jimmy Cox
3108 | 1831 | Future Task |  |  | I-WP117 | Nikki Klein | Approve | WP I-WP117 - Role Mapping Handbook - Approve | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 1830 |  |  | Jimmy Cox | Successor - Role Mapping Worksheet 118 | TW (open item)
3109 | 1832 | Future Task |  |  | I-WP118 | Nikki Klein |  | I-WP118 - Role Mapping Worksheet | 592 hrs | 135 days | Mon 6/3/24 | Fri 12/13/24 |  |  |  |  | RW - Role Mapping | NK
3110 | 1833 | Future Task |  |  | I-WP118 | Carolyn Hicks | Create | WPED I-WP118 - Role Mapping Worksheet - Create | 10 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 1 | 1834 |  | Carolyn Hicks,Nikki Klein,Felicia Hall
3111 | 1834 | Future Task |  |  | I-WP118 | Carolyn Hicks | Submit | WPED I-WP118 - Role Mapping Worksheet - Submit | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 1833 | 1835 |  | Carolyn Hicks
3112 | 1835 | Future Task |  |  | I-WP118 | Carolyn Hicks | Review | WPED I-WP118 - Role Mapping Worksheet - Collaborative Review & Update | 10 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 1834 | 1836 |  | Carolyn Hicks,Nikki Klein,Felicia Hall,Angie Robertson
3113 | 1836 | Future Task |  |  | I-WP118 | Carolyn Hicks | Approve | WPED I-WP118 - Role Mapping Worksheet - Approve | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 1835 | 1837 |  | Angie Robertson,Jimmy Cox
5701 | 1837 | Future Task |  |  | I-WP118 | Nikki Klein | Create | I-WP118 Role Mapping Worksheet <Activities per WPED> | 536 hrs | 67 days | Wed 8/14/24 | Mon 11/18/24 | 1836,1825SS+40 days,571,1892SS+40 days | 1838 |  | Nikki Klein
3114 | 1838 | Future Task |  |  | I-WP118 | Nikki Klein | Submit | WP I-WP118 - Role Mapping Worksheet - Submit | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 1837 | 1839 |  | Nikki Klein
3115 | 1839 | Future Task |  |  | I-WP118 | Nikki Klein | Review | WP I-WP118 - Role Mapping Worksheet - Department QC | 8 hrs | 1 day | Tue 11/19/24 | Tue 11/19/24 | 1838 | 1840 |  | Gabriela Gibson
3116 | 1840 | Future Task |  |  | I-WP118 | Nikki Klein | Review | WP I-WP118 - Role Mapping Worksheet - Collaborative Review & Update | 10 hrs | 10 days | Wed 11/20/24 | Thu 12/5/24 | 1839 | 1841 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3117 | 1841 | Future Task |  |  | I-WP118 | Nikki Klein | Review | WP I-WP118 - Role Mapping Worksheet - Style Guide Review | 8 hrs | 1 day | Fri 12/6/24 | Fri 12/6/24 | 1840 | 1842 |  | Tatiana Eubanks
3118 | 1842 | Future Task |  |  | I-WP118 | Nikki Klein | Review | WP I-WP118 - Role Mapping Worksheet - Final Review & Update | 10 hrs | 5 days | Mon 12/9/24 | Fri 12/13/24 | 1841 | 1843 |  | Angie Robertson,Jimmy Cox
3119 | 1843 | Future Task |  |  | I-WP118 | Nikki Klein | Approve | WP I-WP118 - Role Mapping Worksheet - Approve | 0 hrs | 0 days | Fri 12/13/24 | Fri 12/13/24 | 1842 | 560 |  | Jimmy Cox | Role Mapping Worksheet needs to be approved by 12/15/2024, so agencies can role map before UAT I updated the duration of the work tasks (which needs to be defined) to 67 days instead of 125. This has the WP accept on Friday December 13, 2024. | NK
3120 | 1844 | Future Task |  |  | I-WP119 | Nikki Klein |  | I-WP119 - Change Analysis | 66 hrs | 188 days | Wed 11/1/23 | Wed 7/31/24 |  |  |  |  | Change WP name to "Change Analysis Tool" throughout these schedule tasks, please. Nikki asked for this to be changed to this name, see cell R1824 of the Prior to 6.5 tab. Please confirm which we are using. | Angie
3121 | 1845 | Future Task |  |  | I-WP119 | Carolyn Hicks | Create | WPED I-WP119 - Change Analysis - Create | 10 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23 | 1 | 1846 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas | RW - Agencies complete Change Analysis | NK
3122 | 1846 | Future Task |  |  | I-WP119 | Carolyn Hicks | Submit | WPED I-WP119 - Change Analysis - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 1845 | 1847 |  | Carolyn Hicks
3123 | 1847 | Future Task |  |  | I-WP119 | Carolyn Hicks | Review | WPED I-WP119 - Change Analysis - Collaborative Review & Update | 10 hrs | 10 days | Thu 11/16/23 | Fri 12/1/23 | 1846 | 1848 |  | Carolyn Hicks,Nikki Klein,Kim York,Angie Robertson,Dora Thomas
3124 | 1848 | Future Task |  |  | I-WP119 | Carolyn Hicks | Approve | WPED I-WP119 - Change Analysis - Approve | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 1847 | 1849 |  | Angie Robertson,Jimmy Cox
6814 | 1849 | Future Task |  |  | I-WP119 | Nikki Klein | Submit | I-WP119 Change Analysis <Activities per WPED> | 10 hrs | 151 days | Mon 12/4/23 | Mon 7/8/24 | 1848 | 1850 |  | Nikki Klein
3125 | 1850 | Future Task |  |  | I-WP119 | Nikki Klein | Submit | WP I-WP119 - Change Analysis - Submit | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1849 | 1851 |  | Nikki Klein
3126 | 1851 | Future Task |  |  | I-WP119 | Nikki Klein | Review | WP I-WP119 - Change Analysis - Department QC | 8 hrs | 1 day | Tue 7/9/24 | Tue 7/9/24 | 1850 | 1852 |  | Gabriela Gibson
3127 | 1852 | Future Task |  |  | I-WP119 | Nikki Klein | Review | WP I-WP119 - Change Analysis - Collaborative Review & Update | 10 hrs | 10 days | Wed 7/10/24 | Tue 7/23/24 | 1851 | 1853 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3128 | 1853 | Future Task |  |  | I-WP119 | Nikki Klein | Review | WP I-WP119 - Change Analysis - Style Guide Review | 8 hrs | 1 day | Wed 7/24/24 | Wed 7/24/24 | 1852 | 1854 |  | Tatiana Eubanks
3129 | 1854 | Future Task |  |  | I-WP119 | Nikki Klein | Review | WP I-WP119 - Change Analysis - Final Review & Update | 10 hrs | 5 days | Thu 7/25/24 | Wed 7/31/24 | 1853 | 1855 |  | Angie Robertson,Jimmy Cox
3130 | 1855 | Future Task |  |  | I-WP119 | Nikki Klein | Approve | WP I-WP119 - Change Analysis - Approve | 0 hrs | 0 days | Wed 7/31/24 | Wed 7/31/24 | 1854 |  |  | Jimmy Cox | Successor - Role Mapping Handbook 117 | TW (open item)
3131 | 1856 | Future Task |  |  | I-WP121 | Carolyn Hicks |  | I-WP121 - Update D27 Readiness Plan | 143 hrs | 82 days | Mon 10/2/23 | Wed 1/31/24
3132 | 1857 | Future Task |  |  | I-WP121 | Carolyn Hicks | Create | WPED I-WP121 - Update D27 Readiness Plan - Create | 10 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 1 | 1858 |  | Carolyn Hicks,Nikki Klein
3133 | 1858 | Future Task |  |  | I-WP121 | Carolyn Hicks | Submit | WPED I-WP121 - Update D27 Readiness Plan - Submit | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 1857 | 1859 |  | Carolyn Hicks
3134 | 1859 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WPED I-WP121 - Update D27 Readiness Plan - Collaborative Review & Update | 10 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 1858 | 1860 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas,Angie Robertson
3135 | 1860 | Future Task |  |  | I-WP121 | Carolyn Hicks | Approve | WPED I-WP121 - Update D27 Readiness Plan - Approve | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 1859 | 1861 |  | Angie Robertson,Jimmy Cox
5702 | 1861 | Future Task |  |  | I-WP121 | Carolyn Hicks | Create | I-WP121 Update D27 Readiness Plan <Activities per WPED> | 100 hrs | 45 days | Mon 10/30/23 | Fri 1/5/24 | 1860 | 1862 |  | Nikki Klein
3136 | 1862 | Future Task |  |  | I-WP121 | Carolyn Hicks | Submit | WP I-WP121 - Update D27 Readiness Plan - Submit | 0 hrs | 0 days | Fri 1/5/24 | Fri 1/5/24 | 1861 | 1863 |  | Nikki Klein
3137 | 1863 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WP I-WP121 - Update D27 Readiness Plan - Department QC | 1 hr | 1 day | Mon 1/8/24 | Mon 1/8/24 | 1862 | 1864 |  | Gabriela Gibson
3138 | 1864 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WP I-WP121 - Update D27 Readiness Plan - Collaborative Review & Update | 10 hrs | 10 days | Tue 1/9/24 | Tue 1/23/24 | 1863 | 1865 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3139 | 1865 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WP I-WP121 - Update D27 Readiness Plan - Style Guide Review | 2 hrs | 1 day | Wed 1/24/24 | Wed 1/24/24 | 1864 | 1866 |  | Dusti Kincl
3140 | 1866 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WP I-WP121 - Update D27 Readiness Plan - Final Review & Update | 10 hrs | 5 days | Thu 1/25/24 | Wed 1/31/24 | 1865 | 1867 |  | Angie Robertson,Jimmy Cox
3141 | 1867 | Future Task |  |  | I-WP121 | Carolyn Hicks | Approve | WP I-WP121 - Update D27 Readiness Plan - Approve | 0 hrs | 0 days | Wed 1/31/24 | Wed 1/31/24 | 1866 |  |  | Jimmy Cox | Successor - Change Impact Analysis 119 | TW (open item)
3142 | 1868 | Future Task |  |  | I-WP124 | Carolyn Hicks |  | I-WP124 - Update D62 Workforce Transition Plan | 149 hrs | 82 days | Mon 10/2/23 | Wed 1/31/24
3143 | 1869 | Future Task |  |  | I-WP124 | Carolyn Hicks | Create | WPED I-WP124 - Update D62 Workforce Transition Plan - Create | 10 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 1 | 1870 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas
3144 | 1870 | Future Task |  |  | I-WP124 | Carolyn Hicks | Submit | WPED I-WP124 - Update D62 Workforce Transition Plan - Submit | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 1869 | 1871 |  | Carolyn Hicks
3145 | 1871 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WPED I-WP124 - Update D62 Workforce Transition Plan - Collaborative Review & Update | 10 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 1870 | 1872 |  | Carolyn Hicks,Nikki Klein,Kim York,Angie Robertson,Dora Thomas
3146 | 1872 | Future Task |  |  | I-WP124 | Carolyn Hicks | Approve | WPED I-WP124 - Update D62 Workforce Transition Plan - Approve | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 1871 | 1873 |  | Angie Robertson,Jimmy Cox
5703 | 1873 | Future Task |  |  | I-WP124 | Carolyn Hicks | Create | I-WP124 Update D62 Workforce Transition Plan <Activities per WPED> | 100 hrs | 45 days | Mon 10/30/23 | Fri 1/5/24 | 1872 | 1874 |  | Nikki Klein
3147 | 1874 | Future Task |  |  | I-WP124 | Carolyn Hicks | Submit | WP I-WP124 - Update D62 Workforce Transition Plan - Submit | 0 hrs | 0 days | Fri 1/5/24 | Fri 1/5/24 | 1873 | 1875 |  | Nikki Klein
3148 | 1875 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WP I-WP124 - Update D62 Workforce Transition Plan - Department QC | 1 hr | 1 day | Mon 1/8/24 | Mon 1/8/24 | 1874 | 1876 |  | Gabriela Gibson
3149 | 1876 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WP I-WP124 - Update D62 Workforce Transition Plan - Collaborative Review & Update | 10 hrs | 10 days | Tue 1/9/24 | Tue 1/23/24 | 1875 | 1877 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3150 | 1877 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WP I-WP124 - Update D62 Workforce Transition Plan - Style Guide Review | 8 hrs | 1 day | Wed 1/24/24 | Wed 1/24/24 | 1876 | 1878 |  | Tatiana Eubanks
3151 | 1878 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WP I-WP124 - Update D62 Workforce Transition Plan - Final Review & Update | 10 hrs | 5 days | Thu 1/25/24 | Wed 1/31/24 | 1877 | 1879 |  | Angie Robertson,Jimmy Cox
3152 | 1879 | Future Task |  |  | I-WP124 | Carolyn Hicks | Approve | WP I-WP124 - Update D62 Workforce Transition Plan - Approve | 0 hrs | 0 days | Wed 1/31/24 | Wed 1/31/24 | 1878 |  |  | Jimmy Cox | Successor - Change Impact Analysis 119 | TW (open item)
6777 | 1880 | Late |  |  | I-WP126 | Nikki Klein |  | I-WP126 - Readiness Workplan | 358 hrs | 88 days | Mon 5/8/23 | Mon 9/11/23
6778 | 1881 | Complete |  |  | I-WP126 | Carolyn Hicks | Create | WPED I-WP126 - Readiness Workplan - Create | 10 hrs | 10 days | Mon 5/8/23 | Fri 5/19/23 | 1 | 1882 |  | Carolyn Hicks,Nikki Klein,Jordan Nobles
6779 | 1882 | Complete |  |  | I-WP126 | Carolyn Hicks | Submit | WPED I-WP126 - Readiness Workplan - Submit | 0 hrs | 0 days | Fri 5/19/23 | Fri 5/19/23 | 1881 | 1883 |  | Carolyn Hicks
6780 | 1883 | Complete |  |  | I-WP126 | Carolyn Hicks | Review | WPED I-WP126 - Readiness Workplan - Collaborative Review & Update | 7 hrs | 7 days | Mon 5/22/23 | Wed 5/31/23 | 1882 | 1884 |  | Carolyn Hicks,Nikki Klein,Jordan Nobles,Angie Robertson
6781 | 1884 | Complete |  |  | I-WP126 | Carolyn Hicks | Approve | WPED I-WP126 - Readiness Workplan - Approve | 0 hrs | 0 days | Wed 5/31/23 | Wed 5/31/23 | 1883 | 1885FS+2 days |  | Angie Robertson,Jimmy Cox
7164 | 1885 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Create draft RW and roadmap | 72 hrs | 20 days | Mon 6/5/23 | Fri 6/30/23 | 1884FS+2 days | 1886 |  | Nikki Klein,Jordan Nobles,Vincent Cicco
7165 | 1886 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Gather input | 48 hrs | 14 days | Mon 7/3/23 | Fri 7/21/23 | 1885 | 1887SS |  | Carolyn Hicks,Jordan Nobles,Nikki Klein,Kimberly Kemp,Angie Robertson,Jimmy Cox
7166 | 1887 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Review Project Schedule | 24 hrs | 9 days | Mon 7/3/23 | Fri 7/14/23 | 1886SS | 1888 |  | Nikki Klein,Jordan Nobles,Vincent Cicco
7167 | 1888 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Update RW | 60 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 | 1887 | 1889SS |  | Nikki Klein,Jordan Nobles,Vincent Cicco
7162 | 1889 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Update Roadmap | 12 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 | 1888SS | 1890 |  | Jordan Nobles,Vincent Cicco
7163 | 1890 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Confirm RW tasks with Architects | 32 hrs | 13 days | Mon 7/31/23 | Wed 8/16/23 | 1889 | 1891 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Jordan Nobles,Nikki Klein,Kimberly Kemp,Angie Robertson
7161 | 1891 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Finalize RW | 38 hrs | 4 days | Thu 8/17/23 | Tue 8/22/23 | 1890 | 1892SS |  | Nikki Klein,Jordan Nobles,Vincent Cicco
7160 | 1892 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 - Finalize Roadmap | 4 hrs | 4 days | Thu 8/17/23 | Tue 8/22/23 | 1891SS | 1893,1837SS+40 days |  | Jordan Nobles,Vincent Cicco
6783 | 1893 | Future Task |  |  | I-WP126 | Nikki Klein | Submit | WP I-WP126 - Readiness Workplan - Submit | 0 hrs | 0 days | Tue 8/22/23 | Tue 8/22/23 | 1892 | 1894 |  | Nikki Klein
6784 | 1894 | Future Task |  |  | I-WP126 | Nikki Klein | Review | WP I-WP126 - Readiness Workplan - Department QC | 3 hrs | 1 day | Wed 8/23/23 | Wed 8/23/23 | 1893 | 1895 |  | Gabriela Gibson
6785 | 1895 | Future Task |  |  | I-WP126 | Nikki Klein | Review | WP I-WP126 - Readiness Workplan - Collaborative Review & Update | 18 hrs | 5 days | Thu 8/24/23 | Wed 8/30/23 | 1894 | 1896 |  | Nikki Klein,Carolyn Hicks,Angie Robertson
6786 | 1896 | Future Task |  |  | I-WP126 | Nikki Klein | Review | WP I-WP126 - Readiness Workplan - Style Guide Review | 4 hrs | 1 day | Thu 8/31/23 | Thu 8/31/23 | 1895 | 1897 |  | Dusti Kincl
6787 | 1897 | Future Task |  |  | I-WP126 | Nikki Klein | Review | WP I-WP126 - Readiness Workplan - Final Review & Update | 18 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 1896 | 1898 |  | Nikki Klein,Jordan Nobles,Vincent Cicco
6788 | 1898 | Future Task |  |  | I-WP126 | Nikki Klein | Approve | WP I-WP126 - Readiness Workplan - Approve | 8 hrs | 1 day | Mon 9/11/23 | Mon 9/11/23 | 1897 |  |  | Jimmy Cox,Angie Robertson | Successor - Change Impact Analysis 119 | TW
3 | 1899 | Future Task | [5 empty] | Production Support | 1,863 hrs | 638 days | Mon 1/6/25 | Thu 7/15/27
5850 | 1900 | Future Task | [5 empty] | Hypercare | 517 hrs | 355 days | Mon 1/6/25 | Mon 6/1/26
5852 | 1901 | Future Task | Maybe |  | D664 | Bryan Sohayda |  | D664 - Development of the Hypercare Support Plan | 205 hrs | 106 days | Mon 1/6/25 | Wed 6/4/25
5853 | 1902 | Future Task |  |  | D664 | Bryan Sohayda | Create | DED D664 - Development of the Hypercare Support Plan - Create | 8 hrs | 10 days | Mon 1/6/25 | Fri 1/17/25 | 1 | 1903,1972SS+5 days | 2025-02-03 | Bryan Sohayda
5854 | 1903 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DED D664 - Development of the Hypercare Support Plan - Submit | 0 hrs | 0 days | Fri 1/17/25 | Fri 1/17/25 | 1902 | 1904 |  | Bryan Sohayda,Joy Schneider
5855 | 1904 | Future Task |  |  | D664 | Bryan Sohayda | Review | DED D664 - Development of the Hypercare Support Plan - Collaborative Review | 16 hrs | 10 days | Tue 1/21/25 | Mon 2/3/25 | 1903 | 1905 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5856 | 1905 | Future Task |  |  | D664 | Bryan Sohayda | Approve | DED D664 - Development of the Hypercare Support Plan - Approve | 0 hrs | 0 days | Mon 2/3/25 | Mon 2/3/25 | 1904 | 1906FS+19 days |  | Jimmy Cox
5857 | 1906 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Development of the Hypercare Support Plan | 20 hrs | 50 days | Mon 3/3/25 | Fri 5/9/25 | 1905FS+19 days | 1907SS,1913 |  | Bryan Sohayda,Chetna Dewan
5858 | 1907 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Define and document hypercare support processes and procedures | 20 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1906SS | 1908 |  | Bryan Sohayda,Chetna Dewan
5859 | 1908 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Review hypercare support processes and procedures draft | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1907 | 1909 |  | Bryan Sohayda,Chetna Dewan
5860 | 1909 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Define and document tools used for hypercare support activities | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 1908 | 1910 |  | Bryan Sohayda,Chetna Dewan
5861 | 1910 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Review tools used for hypercare activities draft | 20 hrs | 5 days | Mon 3/31/25 | Fri 4/4/25 | 1909 | 1911 |  | Bryan Sohayda,Chetna Dewan
5862 | 1911 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Determine and document resource capacity and skills needed | 20 hrs | 5 days | Mon 4/7/25 | Fri 4/11/25 | 1910 | 1912 |  | Bryan Sohayda,Chetna Dewan
5863 | 1912 | Future Task |  |  | D664 | Bryan Sohayda | Create | D664 - Review resource capacity and skills needed draft | 20 hrs | 5 days | Mon 4/14/25 | Fri 4/18/25 | 1911 | 1913 |  | Bryan Sohayda,Chetna Dewan
5864 | 1913 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DEL D664 - Development of the Hypercare Support Plan - Draft Submission | 0 hrs | 0 days | Fri 5/9/25 | Fri 5/9/25 | 19061912 | 1914 |  | Bryan Sohayda,Joy Schneider
5865 | 1914 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Pre-Submission Collaborative Review | 12 hrs | 5 days | Mon 5/12/25 | Fri 5/16/25 | 1913 | 1915 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5866 | 1915 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Style Guide Review | 1 hr | 1 day | Mon 5/19/25 | Mon 5/19/25 | 1914 | 1916 |  | Dusti Kincl
5867 | 1916 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Final Collaborative Review | 12 hrs | 5 days | Tue 5/20/25 | Tue 5/27/25 | 1915 | 1917 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5868 | 1917 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Accenture QC | 4 hrs | 2 days | Wed 5/28/25 | Thu 5/29/25 | 1916 | 1918 |  | Joy Schneider
5869 | 1918 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DEL D664 - Development of the Hypercare Support Plan - Submit | 0 hrs | 0 days | Thu 5/29/25 | Thu 5/29/25 | 1917 | 1919 |  | Joy Schneider
5870 | 1919 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Department QC | 4 hrs | 1 day | Fri 5/30/25 | Fri 5/30/25 | 1918 | 1920 |  | Tommy Werner,Gabriela Gibson
5871 | 1920 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Contract Manager Review | 8 hrs | 3 days | Mon 6/2/25 | Wed 6/4/25 | 1919 | 1921 |  | Sean Buchanan
5872 | 1921 | Future Task |  |  | D664 | Bryan Sohayda | Accept | DEL D664 - Development of the Hypercare Support Plan - Accept | 0 hrs | 0 days | Wed 6/4/25 | Wed 6/4/25 | 1920 | 1923 | 2025-06-01 | Sean Buchanan
5873 | 1922 | Future Task |  |  | D680 | Bryan Sohayda |  | D680 - Hypercare Monthly Deliverable – January 2026 | 153 hrs | 80 days | Mon 11/3/25 | Mon 3/2/26
5874 | 1923 | Future Task |  |  | D680-D683 | Bryan Sohayda | Create | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Create | 80 hrs | 10 days | Mon 11/3/25 | Mon 11/17/25 | 1921 | 1924 |  | Bryan Sohayda
5875 | 1924 | Future Task |  |  | D680-D683 | Bryan Sohayda | Submit | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Submit | 0 hrs | 0 days | Mon 11/17/25 | Mon 11/17/25 | 1923 | 1925 |  | Bryan Sohayda,Joy Schneider
5876 | 1925 | Future Task |  |  | D680-D683 | Bryan Sohayda | Review | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Collaborative Review | 20 hrs | 10 days | Tue 11/18/25 | Wed 12/3/25 | 1924 | 1926 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
7150 | 1926 | Future Task |  |  | D680-D683 | Bryan Sohayda | Approve | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Approve | 0 hrs | 0 days | Tue 11/25/25 | Tue 11/25/25 | 1925 | 1927FS+44 days |  | Jimmy Cox
5877 | 1927 | Future Task |  |  | D680 | Bryan Sohayda | Create | Create D680 - Hypercare Monthly Deliverable – January 2026 | 4 hrs | 4 days | Mon 2/2/26 | Thu 2/5/26 | 1926FS+44 days | 1928 |  | Bryan Sohayda
5878 | 1928 | Future Task |  |  | D680 | Bryan Sohayda | Submit | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Draft Submission | 0 hrs | 0 days | Thu 2/5/26 | Thu 2/5/26 | 1927 | 1929 |  | Joy Schneider,Bryan Sohayda
5879 | 1929 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 2/6/26 | Thu 2/12/26 | 1928 | 1930 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5880 | 1930 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Style Guide Review | 1 hr | 1 day | Fri 2/13/26 | Fri 2/13/26 | 1929 | 1931 |  | Dusti Kincl
5881 | 1931 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Final Collaborative Review | 16 hrs | 5 days | Mon 2/16/26 | Fri 2/20/26 | 1930 | 1932 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5882 | 1932 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Accenture QC | 4 hrs | 2 days | Mon 2/23/26 | Tue 2/24/26 | 1931 | 1933 |  | Joy Schneider
5883 | 1933 | Future Task |  |  | D680 | Bryan Sohayda | Submit | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Submit | 0 hrs | 0 days | Tue 2/24/26 | Tue 2/24/26 | 1932 | 1934 |  | Joy Schneider
5884 | 1934 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Department QC | 4 hrs | 1 day | Wed 2/25/26 | Wed 2/25/26 | 1933 | 1935 |  | Tommy Werner
5885 | 1935 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 2/26/26 | Mon 3/2/26 | 1934 | 1936 |  | Sean Buchanan
5886 | 1936 | Future Task |  |  | D680 | Bryan Sohayda | Accept | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Accept | 0 hrs | 0 days | Mon 3/2/26 | Mon 3/2/26 | 1935 | 1938FS-1 day |  | Sean Buchanan
5887 | 1937 | Future Task |  |  | D681 | Bryan Sohayda |  | D681 - Hypercare Monthly Deliverable – February 2026 | 53 hrs | 21 days | Mon 3/2/26 | Mon 3/30/26
5888 | 1938 | Future Task |  |  | D681 | Bryan Sohayda | Create | Create D681 - Hypercare Monthly Deliverable – February 2026 | 4 hrs | 4 days | Mon 3/2/26 | Thu 3/5/26 | 1936FS-1 day | 1939 |  | Bryan Sohayda
5889 | 1939 | Future Task |  |  | D681 | Bryan Sohayda | Submit | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Draft Submission | 0 hrs | 0 days | Thu 3/5/26 | Thu 3/5/26 | 1938 | 1940 |  | Joy Schneider,Bryan Sohayda
5890 | 1940 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 3/6/26 | Thu 3/12/26 | 1939 | 1941 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5891 | 1941 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Style Guide Review | 1 hr | 1 day | Fri 3/13/26 | Fri 3/13/26 | 1940 | 1942 |  | Dusti Kincl
5892 | 1942 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Final Collaborative Review | 16 hrs | 5 days | Mon 3/16/26 | Fri 3/20/26 | 1941 | 1943 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5893 | 1943 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Accenture QC | 4 hrs | 2 days | Mon 3/23/26 | Tue 3/24/26 | 1942 | 1944 |  | Joy Schneider
5894 | 1944 | Future Task |  |  | D681 | Bryan Sohayda | Submit | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Submit | 0 hrs | 0 days | Tue 3/24/26 | Tue 3/24/26 | 1943 | 1945 |  | Joy Schneider
5895 | 1945 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Department QC | 4 hrs | 1 day | Wed 3/25/26 | Wed 3/25/26 | 1944 | 1946 |  | Tommy Werner
5896 | 1946 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 3/26/26 | Mon 3/30/26 | 1945 | 1947 |  | Sean Buchanan
5897 | 1947 | Future Task |  |  | D681 | Bryan Sohayda | Accept | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Accept | 0 hrs | 0 days | Mon 3/30/26 | Mon 3/30/26 | 1946 | 1949 |  | Sean Buchanan
5898 | 1948 | Future Task |  |  | D682 | Bryan Sohayda |  | D682 - Hypercare Monthly Deliverable – March 2026 | 53 hrs | 21 days | Wed 4/1/26 | Wed 4/29/26
5899 | 1949 | Future Task |  |  | D682 | Bryan Sohayda | Create | Create D682 - Hypercare Monthly Deliverable – March 2026 | 4 hrs | 4 days | Wed 4/1/26 | Mon 4/6/26 | 1947 | 1950 |  | Bryan Sohayda
5900 | 1950 | Future Task |  |  | D682 | Bryan Sohayda | Submit | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Draft Submission | 0 hrs | 0 days | Mon 4/6/26 | Mon 4/6/26 | 1949 | 1951 |  | Joy Schneider,Bryan Sohayda
5901 | 1951 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Tue 4/7/26 | Mon 4/13/26 | 1950 | 1952 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5902 | 1952 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Style Guide Review | 1 hr | 1 day | Tue 4/14/26 | Tue 4/14/26 | 1951 | 1953 |  | Dusti Kincl
5903 | 1953 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Final Collaborative Review | 16 hrs | 5 days | Wed 4/15/26 | Tue 4/21/26 | 1952 | 1954 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5904 | 1954 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Accenture QC | 4 hrs | 2 days | Wed 4/22/26 | Thu 4/23/26 | 1953 | 1955 |  | Joy Schneider
5905 | 1955 | Future Task |  |  | D682 | Bryan Sohayda | Submit | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Submit | 0 hrs | 0 days | Thu 4/23/26 | Thu 4/23/26 | 1954 | 1956 |  | Joy Schneider
5906 | 1956 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Department QC | 4 hrs | 1 day | Fri 4/24/26 | Fri 4/24/26 | 1955 | 1957 |  | Tommy Werner
5907 | 1957 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Contract Manager Review | 8 hrs | 3 days | Mon 4/27/26 | Wed 4/29/26 | 1956 | 1958 |  | Sean Buchanan
5908 | 1958 | Future Task |  |  | D682 | Bryan Sohayda | Accept | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Accept | 0 hrs | 0 days | Wed 4/29/26 | Wed 4/29/26 | 1957 | 1960 |  | Sean Buchanan
5909 | 1959 | Future Task |  |  | D683 | Bryan Sohayda |  | D683 - Hypercare Monthly Deliverable – April 2026 | 53 hrs | 21 days | Fri 5/1/26 | Mon 6/1/26
5910 | 1960 | Future Task |  |  | D683 | Bryan Sohayda | Create | Create D683 - Hypercare Monthly Deliverable – April 2026 | 4 hrs | 4 days | Fri 5/1/26 | Wed 5/6/26 | 1958 | 1961 |  | Bryan Sohayda
5911 | 1961 | Future Task |  |  | D683 | Bryan Sohayda | Submit | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Draft Submission | 0 hrs | 0 days | Wed 5/6/26 | Wed 5/6/26 | 1960 | 1962 |  | Joy Schneider,Bryan Sohayda
5912 | 1962 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Thu 5/7/26 | Wed 5/13/26 | 1961 | 1963 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5913 | 1963 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Style Guide Review | 1 hr | 1 day | Thu 5/14/26 | Thu 5/14/26 | 1962 | 1964 |  | Dusti Kincl
5914 | 1964 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Final Collaborative Review | 16 hrs | 5 days | Fri 5/15/26 | Thu 5/21/26 | 1963 | 1965 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5915 | 1965 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Accenture QC | 4 hrs | 2 days | Fri 5/22/26 | Tue 5/26/26 | 1964 | 1966 |  | Joy Schneider
5916 | 1966 | Future Task |  |  | D683 | Bryan Sohayda | Submit | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Submit | 0 hrs | 0 days | Tue 5/26/26 | Tue 5/26/26 | 1965 | 1967 |  | Joy Schneider
5917 | 1967 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Department QC | 4 hrs | 1 day | Wed 5/27/26 | Wed 5/27/26 | 1966 | 1968 |  | Tommy Werner
5918 | 1968 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 5/28/26 | Mon 6/1/26 | 1967 | 1969 |  | Sean Buchanan
5919 | 1969 | Future Task |  |  | D683 | Bryan Sohayda | Accept | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Accept | 0 hrs | 0 days | Mon 6/1/26 | Mon 6/1/26 | 1968 |  |  | Sean Buchanan
5851 | 1970 | Future Task | [5 empty] | Post-Implementation Support | 1,346 hrs | 633 days | Mon 1/13/25 | Thu 7/15/27
5488 | 1971 | Future Task |  |  | D665 | Bryan Sohayda |  | D665 - Updated Post-Implementation Support Plan | 154 hrs | 106 days | Mon 1/13/25 | Wed 6/11/25
5489 | 1972 | Future Task |  |  | D665 | Bryan Sohayda | Create | DED D665 - Updated Post-Implementation Support Plan - Create | 8 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 1902SS+5 days | 1973 |  | Bryan Sohayda
5490 | 1973 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DED D665 - Updated Post-Implementation Support Plan - Submit | 0 hrs | 0 days | Mon 1/27/25 | Mon 1/27/25 | 1972 | 1974 |  | Bryan Sohayda,Joy Schneider
5491 | 1974 | Future Task |  |  | D665 | Bryan Sohayda | Review | DED D665 - Updated Post-Implementation Support Plan - Collaborative Review | 16 hrs | 10 days | Tue 1/28/25 | Mon 2/10/25 | 1973 | 1975 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5492 | 1975 | Future Task |  |  | D665 | Bryan Sohayda | Approve | DED D665 - Updated Post-Implementation Support Plan - Approve | 0 hrs | 0 days | Mon 2/10/25 | Mon 2/10/25 | 1974 | 1976FS+14 days |  | Jimmy Cox
5493 | 1976 | Future Task |  |  | D665 | Bryan Sohayda | Create | Create Post Implementation Support Processes and Procedures | 20 hrs | 15 days | Mon 3/3/25 | Fri 3/21/25 | 1975FS+14 days | 1977 |  | Bryan Sohayda,Chetna Dewan
5494 | 1977 | Future Task |  |  | D665 | Bryan Sohayda | Create | Document Post Implementation Support Tools | 20 hrs | 10 days | Mon 3/24/25 | Fri 4/4/25 | 1976 | 1978 |  | Bryan Sohayda,Chetna Dewan
5495 | 1978 | Future Task |  |  | D665 | Bryan Sohayda | Create | Post-Implementation Support Resource Capacity and Skills | 20 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 1977 | 1979 |  | Bryan Sohayda,Chetna Dewan
5496 | 1979 | Future Task |  |  | D665 | Bryan Sohayda | Create | Full draft review pre-submission | 20 hrs | 20 days | Mon 4/21/25 | Fri 5/16/25 | 1978 | 1980 |  | Bryan Sohayda,Chetna Dewan
5497 | 1980 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DEL D665 - Updated Post-Implementation Support Plan - Draft Submission | 0 hrs | 0 days | Fri 5/16/25 | Fri 5/16/25 | 1979 | 1981 |  | Bryan Sohayda,Joy Schneider
5498 | 1981 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Pre-Submission Collaborative Review | 12 hrs | 5 days | Mon 5/19/25 | Fri 5/23/25 | 1980 | 1982 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5499 | 1982 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Style Guide Review | 1 hr | 1 day | Tue 5/27/25 | Tue 5/27/25 | 1981 | 1983 |  | Dusti Kincl
5500 | 1983 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Final Collaborative Review | 21 hrs | 5 days | Wed 5/28/25 | Tue 6/3/25 | 1982 | 1984 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5501 | 1984 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Accenture QC | 4 hrs | 2 days | Wed 6/4/25 | Thu 6/5/25 | 1983 | 1985 |  | Joy Schneider
5502 | 1985 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DEL D665 - Updated Post-Implementation Support Plan - Submit | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 1984 | 1986 |  | Joy Schneider
5503 | 1986 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Department QC | 4 hrs | 1 day | Fri 6/6/25 | Fri 6/6/25 | 1985 | 1987 |  | Tommy Werner,Gabriela Gibson
5504 | 1987 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Contract Manager Review | 8 hrs | 3 days | Mon 6/9/25 | Wed 6/11/25 | 1986 | 1988 |  | Sean Buchanan
5505 | 1988 | Future Task |  |  | D665 | Bryan Sohayda | Accept | DEL D665 - Updated Post-Implementation Support Plan - Accept | 0 hrs | 0 days | Wed 6/11/25 | Wed 6/11/25 | 1987 |  | 2025-06-01 | Sean Buchanan
5759 | 1989 | Future Task |  |  | D684 | Bryan Sohayda |  | D684 - Post-Implementation Support Monthly Deliverable – May 2026 | 122 hrs | 85 days | Mon 3/2/26 | Mon 6/29/26
5760 | 1990 | Future Task |  |  | D684-D691 | Bryan Sohayda | Create | DED Create - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 8 hrs | 5 days | Mon 3/2/26 | Fri 3/6/26 | 1 | 1991 |  | Bryan Sohayda
5761 | 1991 | Future Task |  |  | D684-D691 | Bryan Sohayda | Submit | DED Submit - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 0 hrs | 0 days | Fri 3/6/26 | Fri 3/6/26 | 1990 | 1992 |  | Bryan Sohayda,Joy Schneider
5762 | 1992 | Future Task |  |  | D684-D691 | Bryan Sohayda | Review | DED Collaborative Review & Accept - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 20 hrs | 10 days | Mon 3/9/26 | Fri 3/20/26 | 1991 | 1993 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5763 | 1993 | Future Task |  |  | D684 | Bryan Sohayda | Create | Create D684 - Post-Implementation Support Monthly Deliverable – May 2026 | 4 hrs | 4 days | Mon 6/1/26 | Thu 6/4/26 | 1992 | 1994 |  | Bryan Sohayda
5764 | 1994 | Future Task |  |  | D684 | Bryan Sohayda | Submit | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Draft Submission | 0 hrs | 0 days | Thu 6/4/26 | Thu 6/4/26 | 1993 | 1995 |  | Joy Schneider,Bryan Sohayda
5765 | 1995 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 6/5/26 | Thu 6/11/26 | 1994 | 1996 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5766 | 1996 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Style Guide Review | 8 hrs | 1 day | Fri 6/12/26 | Fri 6/12/26 | 1995 | 1997 |  | Dusti Kincl
5767 | 1997 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Final Collaborative Review | 20 hrs | 5 days | Mon 6/15/26 | Fri 6/19/26 | 1996 | 1998 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5768 | 1998 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Accenture QC | 16 hrs | 2 days | Mon 6/22/26 | Tue 6/23/26 | 1997 | 1999 |  | Joy Schneider
5769 | 1999 | Future Task |  |  | D684 | Bryan Sohayda | Submit | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Submit | 0 hrs | 0 days | Tue 6/23/26 | Tue 6/23/26 | 1998 | 2000 |  | Joy Schneider
5770 | 2000 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Department QC | 2 hrs | 1 day | Wed 6/24/26 | Wed 6/24/26 | 1999 | 2001 |  | Tommy Werner
5771 | 2001 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Contract Manager Review | 24 hrs | 3 days | Thu 6/25/26 | Mon 6/29/26 | 2000 | 2002 |  | Sean Buchanan
5772 | 2002 | Future Task |  |  | D684 | Bryan Sohayda | Accept | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Accept | 0 hrs | 0 days | Mon 6/29/26 | Mon 6/29/26 | 2001 | 2004 |  | Sean Buchanan
5773 | 2003 | Future Task |  |  | D685 | Bryan Sohayda |  | D685 - Post-Implementation Support Monthly Deliverable – June 2026 | 53 hrs | 21 days | Wed 7/1/26 | Thu 7/30/26
5774 | 2004 | Future Task |  |  | D685 | Bryan Sohayda | Create | Create D685 - Post-Implementation Support Monthly Deliverable – June 2026 | 4 hrs | 4 days | Wed 7/1/26 | Tue 7/7/26 | 2002 | 2005 |  | Bryan Sohayda
5775 | 2005 | Future Task |  |  | D685 | Bryan Sohayda | Submit | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Draft Submission | 0 hrs | 0 days | Tue 7/7/26 | Tue 7/7/26 | 2004 | 2006 |  | Joy Schneider,Bryan Sohayda
5776 | 2006 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Wed 7/8/26 | Tue 7/14/26 | 2005 | 2007 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5777 | 2007 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Style Guide Review | 1 hr | 1 day | Wed 7/15/26 | Wed 7/15/26 | 2006 | 2008 |  | Dusti Kincl
5778 | 2008 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Final Collaborative Review | 16 hrs | 5 days | Thu 7/16/26 | Wed 7/22/26 | 2007 | 2009 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5779 | 2009 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Accenture QC | 4 hrs | 2 days | Thu 7/23/26 | Fri 7/24/26 | 2008 | 2010 |  | Joy Schneider
5780 | 2010 | Future Task |  |  | D685 | Bryan Sohayda | Submit | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Submit | 0 hrs | 0 days | Fri 7/24/26 | Fri 7/24/26 | 2009 | 2011 |  | Joy Schneider
5781 | 2011 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Department QC | 4 hrs | 1 day | Mon 7/27/26 | Mon 7/27/26 | 2010 | 2012 |  | Tommy Werner
5782 | 2012 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 7/28/26 | Thu 7/30/26 | 2011 | 2013 |  | Sean Buchanan
5783 | 2013 | Future Task |  |  | D685 | Bryan Sohayda | Accept | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Accept | 0 hrs | 0 days | Thu 7/30/26 | Thu 7/30/26 | 2012 | 2015 |  | Sean Buchanan
5784 | 2014 | Future Task |  |  | D686 | Bryan Sohayda |  | D686 - Post-Implementation Support Monthly Deliverable – July 2026 | 53 hrs | 21 days | Mon 8/3/26 | Mon 8/31/26
5785 | 2015 | Future Task |  |  | D686 | Bryan Sohayda | Create | Create D686 - Post-Implementation Support Monthly Deliverable – July 2026 | 4 hrs | 4 days | Mon 8/3/26 | Thu 8/6/26 | 2013 | 2016 |  | Bryan Sohayda
5786 | 2016 | Future Task |  |  | D686 | Bryan Sohayda | Submit | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Draft Submission | 0 hrs | 0 days | Thu 8/6/26 | Thu 8/6/26 | 2015 | 2017 |  | Joy Schneider,Bryan Sohayda
5787 | 2017 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 8/7/26 | Thu 8/13/26 | 2016 | 2018 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5788 | 2018 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Style Guide Review | 1 hr | 1 day | Fri 8/14/26 | Fri 8/14/26 | 2017 | 2019 |  | Dusti Kincl
5789 | 2019 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Final Collaborative Review | 16 hrs | 5 days | Mon 8/17/26 | Fri 8/21/26 | 2018 | 2020 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5790 | 2020 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Accenture QC | 4 hrs | 2 days | Mon 8/24/26 | Tue 8/25/26 | 2019 | 2021 |  | Joy Schneider
5791 | 2021 | Future Task |  |  | D686 | Bryan Sohayda | Submit | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Submit | 0 hrs | 0 days | Tue 8/25/26 | Tue 8/25/26 | 2020 | 2022 |  | Joy Schneider
5792 | 2022 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Department QC | 4 hrs | 1 day | Wed 8/26/26 | Wed 8/26/26 | 2021 | 2023 |  | Tommy Werner
5793 | 2023 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 8/27/26 | Mon 8/31/26 | 2022 | 2024 |  | Sean Buchanan
5794 | 2024 | Future Task |  |  | D686 | Bryan Sohayda | Accept | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Accept | 0 hrs | 0 days | Mon 8/31/26 | Mon 8/31/26 | 2023 | 2026 |  | Sean Buchanan
5795 | 2025 | Future Task |  |  | D687 | Bryan Sohayda |  | D687 - Post-Implementation Support Monthly Deliverable – August 2026 | 53 hrs | 21 days | Tue 9/1/26 | Wed 9/30/26
5796 | 2026 | Future Task |  |  | D687 | Bryan Sohayda | Create | Create D687 - Post-Implementation Support Monthly Deliverable – August 2026 | 4 hrs | 4 days | Tue 9/1/26 | Fri 9/4/26 | 2024 | 2027 |  | Bryan Sohayda
5797 | 2027 | Future Task |  |  | D687 | Bryan Sohayda | Submit | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Draft Submission | 0 hrs | 0 days | Fri 9/4/26 | Fri 9/4/26 | 2026 | 2028 |  | Joy Schneider,Bryan Sohayda
5798 | 2028 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Tue 9/8/26 | Mon 9/14/26 | 2027 | 2029 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5799 | 2029 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Style Guide Review | 1 hr | 1 day | Tue 9/15/26 | Tue 9/15/26 | 2028 | 2030 |  | Dusti Kincl
5800 | 2030 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Final Collaborative Review | 16 hrs | 5 days | Wed 9/16/26 | Tue 9/22/26 | 2029 | 2031 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5801 | 2031 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Accenture QC | 4 hrs | 2 days | Wed 9/23/26 | Thu 9/24/26 | 2030 | 2032 |  | Joy Schneider
5802 | 2032 | Future Task |  |  | D687 | Bryan Sohayda | Submit | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Submit | 0 hrs | 0 days | Thu 9/24/26 | Thu 9/24/26 | 2031 | 2033 |  | Joy Schneider
5803 | 2033 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Department QC | 4 hrs | 1 day | Fri 9/25/26 | Fri 9/25/26 | 2032 | 2034 |  | Tommy Werner
5804 | 2034 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Contract Manager Review | 8 hrs | 3 days | Mon 9/28/26 | Wed 9/30/26 | 2033 | 2035 |  | Sean Buchanan
5805 | 2035 | Future Task |  |  | D687 | Bryan Sohayda | Accept | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Accept | 0 hrs | 0 days | Wed 9/30/26 | Wed 9/30/26 | 2034 | 2037 |  | Sean Buchanan
5806 | 2036 | Future Task |  |  | D688 | Bryan Sohayda |  | D688 - Post-Implementation Support Monthly Deliverable – September 2026 | 53 hrs | 21 days | Thu 10/1/26 | Thu 10/29/26
5807 | 2037 | Future Task |  |  | D688 | Bryan Sohayda | Create | Create D688 - Post-Implementation Support Monthly Deliverable – September 2026 | 4 hrs | 4 days | Thu 10/1/26 | Tue 10/6/26 | 2035 | 2038 |  | Bryan Sohayda
5808 | 2038 | Future Task |  |  | D688 | Bryan Sohayda | Submit | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Draft Submission | 0 hrs | 0 days | Tue 10/6/26 | Tue 10/6/26 | 2037 | 2039 |  | Joy Schneider,Bryan Sohayda
5809 | 2039 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Wed 10/7/26 | Tue 10/13/26 | 2038 | 2040 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5810 | 2040 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Style Guide Review | 1 hr | 1 day | Wed 10/14/26 | Wed 10/14/26 | 2039 | 2041 |  | Dusti Kincl
5811 | 2041 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Final Collaborative Review | 16 hrs | 5 days | Thu 10/15/26 | Wed 10/21/26 | 2040 | 2042 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5812 | 2042 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Accenture QC | 4 hrs | 2 days | Thu 10/22/26 | Fri 10/23/26 | 2041 | 2043 |  | Joy Schneider
5813 | 2043 | Future Task |  |  | D688 | Bryan Sohayda | Submit | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Submit | 0 hrs | 0 days | Fri 10/23/26 | Fri 10/23/26 | 2042 | 2044 |  | Joy Schneider
5814 | 2044 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Department QC | 4 hrs | 1 day | Mon 10/26/26 | Mon 10/26/26 | 2043 | 2045 |  | Tommy Werner
5815 | 2045 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 10/27/26 | Thu 10/29/26 | 2044 | 2046 |  | Sean Buchanan
5816 | 2046 | Future Task |  |  | D688 | Bryan Sohayda | Accept | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Accept | 0 hrs | 0 days | Thu 10/29/26 | Thu 10/29/26 | 2045 | 2048 |  | Sean Buchanan
5817 | 2047 | Future Task |  |  | D689 | Bryan Sohayda |  | D689 - Post-Implementation Support Monthly Deliverable – October 2026 | 53 hrs | 18 days | Mon 11/2/26 | Mon 11/30/26
5818 | 2048 | Future Task |  |  | D689 | Bryan Sohayda | Create | Create D689 - Post-Implementation Support Monthly Deliverable – October 2026 | 4 hrs | 4 days | Mon 11/2/26 | Thu 11/5/26 | 2046 | 2049 |  | Bryan Sohayda
5819 | 2049 | Future Task |  |  | D689 | Bryan Sohayda | Submit | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Draft Submission | 0 hrs | 0 days | Thu 11/5/26 | Thu 11/5/26 | 2048 | 2050 |  | Joy Schneider,Bryan Sohayda
5820 | 2050 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Pre-Submission Collaborative Review | 16 hrs | 4 days | Fri 11/6/26 | Thu 11/12/26 | 2049 | 2051 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5821 | 2051 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Style Guide Review | 1 hr | 1 day | Fri 11/13/26 | Fri 11/13/26 | 2050 | 2052 |  | Dusti Kincl
5822 | 2052 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Final Collaborative Review | 16 hrs | 3 days | Mon 11/16/26 | Wed 11/18/26 | 2051 | 2053 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5823 | 2053 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Accenture QC | 4 hrs | 2 days | Thu 11/19/26 | Fri 11/20/26 | 2052 | 2054 |  | Joy Schneider
5824 | 2054 | Future Task |  |  | D689 | Bryan Sohayda | Submit | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Submit | 0 hrs | 0 days | Fri 11/20/26 | Fri 11/20/26 | 2053 | 2055 |  | Joy Schneider
5825 | 2055 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Department QC | 4 hrs | 1 day | Mon 11/23/26 | Mon 11/23/26 | 2054 | 2056 |  | Tommy Werner
5826 | 2056 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 11/24/26 | Mon 11/30/26 | 2055 | 2057 |  | Sean Buchanan
5827 | 2057 | Future Task |  |  | D689 | Bryan Sohayda | Accept | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Accept | 0 hrs | 0 days | Mon 11/30/26 | Mon 11/30/26 | 2056 | 2059 |  | Sean Buchanan
5828 | 2058 | Future Task |  |  | D690 | Bryan Sohayda |  | D690 - Post-Implementation Support Monthly Deliverable – November 2026 | 53 hrs | 21 days | Tue 12/1/26 | Wed 12/30/26
5829 | 2059 | Future Task |  |  | D690 | Bryan Sohayda | Create | Create D690 - Post-Implementation Support Monthly Deliverable – November 2026 | 4 hrs | 4 days | Tue 12/1/26 | Fri 12/4/26 | 2057 | 2060 |  | Bryan Sohayda
5830 | 2060 | Future Task |  |  | D690 | Bryan Sohayda | Submit | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Draft Submission | 0 hrs | 0 days | Fri 12/4/26 | Fri 12/4/26 | 2059 | 2061 |  | Joy Schneider,Bryan Sohayda
5831 | 2061 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 12/7/26 | Fri 12/11/26 | 2060 | 2062 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5832 | 2062 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Style Guide Review | 1 hr | 1 day | Mon 12/14/26 | Mon 12/14/26 | 2061 | 2063 |  | Dusti Kincl
5833 | 2063 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Final Collaborative Review | 16 hrs | 5 days | Tue 12/15/26 | Mon 12/21/26 | 2062 | 2064 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5834 | 2064 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Accenture QC | 4 hrs | 2 days | Tue 12/22/26 | Wed 12/23/26 | 2063 | 2065 |  | Joy Schneider
5835 | 2065 | Future Task |  |  | D690 | Bryan Sohayda | Submit | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Submit | 0 hrs | 0 days | Wed 12/23/26 | Wed 12/23/26 | 2064 | 2066 |  | Joy Schneider
5836 | 2066 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Department QC | 4 hrs | 1 day | Thu 12/24/26 | Thu 12/24/26 | 2065 | 2067 |  | Tommy Werner
5837 | 2067 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Contract Manager Review | 8 hrs | 3 days | Mon 12/28/26 | Wed 12/30/26 | 2066 | 2068 |  | Sean Buchanan
5838 | 2068 | Future Task |  |  | D690 | Bryan Sohayda | Accept | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Accept | 0 hrs | 0 days | Wed 12/30/26 | Wed 12/30/26 | 2067 | 2070 |  | Sean Buchanan
5839 | 2069 | Future Task |  |  | D691 | Bryan Sohayda |  | D691 - Post-Implementation Support Monthly Deliverable – December 2026 | 53 hrs | 21 days | Mon 1/4/27 | Tue 2/2/27
5840 | 2070 | Future Task |  |  | D691 | Bryan Sohayda | Create | Create D691 - Post-Implementation Support Monthly Deliverable – December 2026 | 4 hrs | 4 days | Mon 1/4/27 | Thu 1/7/27 | 2068 | 2071 |  | Bryan Sohayda
5841 | 2071 | Future Task |  |  | D691 | Bryan Sohayda | Submit | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Draft Submission | 0 hrs | 0 days | Thu 1/7/27 | Thu 1/7/27 | 2070 | 2072 |  | Joy Schneider,Bryan Sohayda
5842 | 2072 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 1/8/27 | Thu 1/14/27 | 2071 | 2073 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5843 | 2073 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Style Guide Review | 1 hr | 1 day | Fri 1/15/27 | Fri 1/15/27 | 2072 | 2074 |  | Dusti Kincl
5844 | 2074 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Final Collaborative Review | 16 hrs | 5 days | Tue 1/19/27 | Mon 1/25/27 | 2073 | 2075 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5845 | 2075 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Accenture QC | 4 hrs | 2 days | Tue 1/26/27 | Wed 1/27/27 | 2074 | 2076 |  | Joy Schneider
5846 | 2076 | Future Task |  |  | D691 | Bryan Sohayda | Submit | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Submit | 0 hrs | 0 days | Wed 1/27/27 | Wed 1/27/27 | 2075 | 2077 |  | Joy Schneider
5847 | 2077 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Department QC | 4 hrs | 1 day | Thu 1/28/27 | Thu 1/28/27 | 2076 | 2078 |  | Tommy Werner
5848 | 2078 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Contract Manager Review | 8 hrs | 3 days | Fri 1/29/27 | Tue 2/2/27 | 2077 | 2079 |  | Sean Buchanan
5849 | 2079 | Future Task |  |  | D691 | Bryan Sohayda | Accept | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Accept | 0 hrs | 0 days | Tue 2/2/27 | Tue 2/2/27 | 2078 |  |  | Sean Buchanan
6704 | 2080 | Future Task |  |  | D692 | Stacey Terry |  | D692 - Tax Reporting Support CY 2026 (January 2027) | 179 hrs | 91 days | Mon 10/12/26 | Tue 2/23/27
6705 | 2081 | Future Task |  |  | D692 | Stacey Terry | Create | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Create | 8 hrs | 10 days | Mon 10/12/26 | Fri 10/23/26 | 1 | 2082 | 2026-11-12 | Stacey Terry
6706 | 2082 | Future Task |  |  | D692 | Stacey Terry | Submit | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Submit | 0 hrs | 0 days | Fri 10/23/26 | Fri 10/23/26 | 2081 | 2083 |  | Stacey Terry,Joy Schneider
6707 | 2083 | Future Task |  |  | D692 | Stacey Terry | Review | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Collaborative Review | 20 hrs | 10 days | Mon 10/26/26 | Fri 11/6/26 | 2082 | 2084 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
6708 | 2084 | Future Task |  |  | D692 | Stacey Terry | Approve | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Approve | 0 hrs | 0 days | Fri 11/6/26 | Fri 11/6/26 | 2083 | 2085FS+22 days |  | Jimmy Cox
6709 | 2085 | Future Task |  |  | D692 | Stacey Terry | Create | D692 - Create Tax Reporting Checklist (2026) | 36 hrs | 18 days | Mon 12/14/26 | Fri 1/8/27 | 2084FS+22 days | 2086FS-5 days,2087 |  | Stacey Terry,Yogesh Deshmukh
6710 | 2086 | Future Task |  |  | D692 | Stacey Terry | Create | D692 - Manage Year-end Checklist (2026) | 38 hrs | 19 days | Mon 1/4/27 | Fri 1/29/27 | 2085FS-5 days |  |  | Stacey Terry,Yogesh Deshmukh
6711 | 2087 | Future Task |  |  | D692 | Stacey Terry | Create | D692 - Create initial Year-end Checklist (2027) | 28 hrs | 14 days | Mon 1/11/27 | Fri 1/29/27 | 2085 | 2088 |  | Stacey Terry,Yogesh Deshmukh
6712 | 2088 | Future Task |  |  | D692 | Stacey Terry | Submit | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Draft Submission | 0 hrs | 0 days | Fri 1/29/27 | Fri 1/29/27 | 2087 | 2089 |  | Stacey Terry,Joy Schneider
6713 | 2089 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 2/1/27 | Fri 2/5/27 | 2088 | 2090 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson
6714 | 2090 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Style Guide Review | 1 hr | 1 day | Mon 2/8/27 | Mon 2/8/27 | 2089 | 2091 |  | Dusti Kincl
6715 | 2091 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Final Collaborative Review | 16 hrs | 5 days | Tue 2/9/27 | Mon 2/15/27 | 2090 | 2092 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson
6716 | 2092 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Accenture QC | 4 hrs | 2 days | Tue 2/16/27 | Wed 2/17/27 | 2091 | 2093 |  | Joy Schneider
6717 | 2093 | Future Task |  |  | D692 | Stacey Terry | Submit | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Submit | 0 hrs | 0 days | Wed 2/17/27 | Wed 2/17/27 | 2092 | 2094 |  | Joy Schneider
6718 | 2094 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Department QC | 4 hrs | 1 day | Thu 2/18/27 | Thu 2/18/27 | 2093 | 2095 |  | Tommy Werner,Gabriela Gibson
6719 | 2095 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Contract Manager Review | 8 hrs | 3 days | Fri 2/19/27 | Tue 2/23/27 | 2094 | 2096 |  | Sean Buchanan
6720 | 2096 | Future Task |  |  | D692 | Stacey Terry | Accept | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Accept | 0 hrs | 0 days | Tue 2/23/27 | Tue 2/23/27 | 2095 |  | 2027-02-01 | Sean Buchanan
6721 | 2097 | Future Task |  |  | D693 | Joy Schneider |  | D693 - Exit Transition Completion | 122 hrs | 136 days | Mon 1/4/27 | Thu 7/15/27
6722 | 2098 | Future Task |  |  | D693 | Joy Schneider | Create | DED D693 - Exit Transition Completion - Create | 6 hrs | 10 days | Mon 1/4/27 | Fri 1/15/27 | 2124 | 2099 |  | Joy Schneider,Matt Cole,Mary Punty
6723 | 2099 | Future Task |  |  | D693 | Joy Schneider | Submit | DED D693 - Exit Transition Completion - Submit | 0 hrs | 0 days | Fri 1/15/27 | Fri 1/15/27 | 2098 | 2100 |  | Joy Schneider
6724 | 2100 | Future Task |  |  | D693 | Joy Schneider | Review | DED D693 - Exit Transition Completion - Collaborative Review | 12 hrs | 10 days | Tue 1/19/27 | Mon 2/1/27 | 2099 | 2101 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6725 | 2101 | Future Task |  |  | D693 | Joy Schneider | Approve | DED D693 - Exit Transition Completion - Approve | 0 hrs | 0 days | Mon 2/1/27 | Mon 2/1/27 | 2100 | 2102FS+69 days |  | Jimmy Cox
6726 | 2102 | Future Task |  |  | D693 | Joy Schneider | Create | D693 - Review Status of Exit Transition Work Plan | 45 hrs | 15 days | Mon 5/10/27 | Fri 5/28/27 | 2101FS+69 days | 2103 |  | Joy Schneider,Matt Cole,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
6727 | 2103 | Future Task |  |  | D693 | Joy Schneider | Create | D693 - Obtain Department Sign Off | 30 hrs | 15 days | Tue 6/1/27 | Mon 6/21/27 | 2102 | 2104 |  | Sean Buchanan,Matt Cole
6728 | 2104 | Future Task |  |  | D693 | Joy Schneider | Submit | DEL D693 - Exit Transition Completion - Draft Submission | 0 hrs | 0 days | Mon 6/21/27 | Mon 6/21/27 | 2103 | 2105 |  | Joy Schneider
6729 | 2105 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Pre-Submission Collaborative Review | 6 hrs | 5 days | Tue 6/22/27 | Mon 6/28/27 | 2104 | 2106 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6730 | 2106 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Style Guide Review | 1 hr | 1 day | Tue 6/29/27 | Tue 6/29/27 | 2105 | 2107 |  | Dusti Kincl
6731 | 2107 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Final Collaborative Review | 6 hrs | 5 days | Wed 6/30/27 | Wed 7/7/27 | 2106 | 2108 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6732 | 2108 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Accenture QC | 4 hrs | 2 days | Thu 7/8/27 | Fri 7/9/27 | 2107 | 2109 |  | Joy Schneider
6733 | 2109 | Future Task |  |  | D693 | Joy Schneider | Submit | DEL D693 - Exit Transition Completion - Submit | 0 hrs | 0 days | Fri 7/9/27 | Fri 7/9/27 | 2108 | 2110 |  | Joy Schneider
6734 | 2110 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Department QC | 4 hrs | 1 day | Mon 7/12/27 | Mon 7/12/27 | 2109 | 2111 |  | Tommy Werner
6735 | 2111 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Contract Manager Review | 8 hrs | 3 days | Tue 7/13/27 | Thu 7/15/27 | 2110 | 2112 |  | Sean Buchanan
6736 | 2112 | Future Task |  |  | D693 | Joy Schneider | Accept | DEL D693 - Exit Transition Completion - Accept | 0 hrs | 0 days | Thu 7/15/27 | Thu 7/15/27 | 2111 |  | 2027-07-01 | Sean Buchanan
5655 | 2113 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 - Exit Transition Work Plan | 398 hrs | 121 days | Mon 7/6/26 | Mon 12/28/26
5656 | 2114 | Future Task |  |  | WP428 | Joy Schneider | Create | WPED WP428 - Exit Transition Work Plan - Create | 8 hrs | 10 days | Mon 7/6/26 | Fri 7/17/26 | 1 | 2115 |  | Joy Schneider
5657 | 2115 | Future Task |  |  | WP428 | Joy Schneider | Submit | WPED WP428 - Exit Transition Work Plan - Submit | 0 hrs | 0 days | Fri 7/17/26 | Fri 7/17/26 | 2114 | 2116 |  | Joy Schneider
5658 | 2116 | Future Task |  |  | WP428 | Joy Schneider | Review | WPED WP428 - Exit Transition Work Plan - Review | 16 hrs | 10 days | Mon 7/20/26 | Fri 7/31/26 | 2115 | 2117 |  | Joy Schneider,Jimmy Cox,Angie Robertson,Sean Buchanan
5659 | 2117 | Future Task |  |  | WP428 | Joy Schneider | Approve | WPED WP428 - Exit Transition Work Plan - Approve | 0 hrs | 0 days | Fri 7/31/26 | Fri 7/31/26 | 2116 | 2118FS+41 days |  | Jimmy Cox
5660 | 2118 | Future Task |  |  | WP428 | Joy Schneider | Create | WP428 - Develop Exit Transition Work Plan | 210 hrs | 15 days | Wed 9/30/26 | Tue 10/20/26 | 2117FS+41 days | 2119 |  | Joy Schneider,Stacey Terry,Manojkumar Gurjar,Matt Cole,Angie Robertson,Jimmy Cox,Francisca Li
5661 | 2119 | Future Task |  |  | WP428 | Joy Schneider | Create | WP428 - Determine Entry and Exit Criteria | 120 hrs | 15 days | Wed 10/21/26 | Tue 11/10/26 | 2118 | 2120 |  | Joy Schneider,Matt Cole,Angie Robertson,Jimmy Cox | Predecessor UID 2093 Note from Joy on 6/6: that would be "Submit approved LBR to DFS Budget Office" - what is the connection here? | TW
5662 | 2120 | Future Task |  |  | WP428 | Joy Schneider | Create | WP428 - Review and Confirm Exit Transition Plan | 20 hrs | 15 days | Thu 11/12/26 | Fri 12/4/26 | 2119 | 2121 |  | Jimmy Cox,Angie Robertson,Joy Schneider
5663 | 2121 | Future Task |  |  | WP428 | Joy Schneider | Submit | WP WP428 - Exit Transition Work Plan - Submit | 0 hrs | 0 days | Fri 12/4/26 | Fri 12/4/26 | 2120 | 2122 |  | Joy Schneider
5664 | 2122 | Future Task |  |  | WP428 | Joy Schneider | Review | WP WP428 - Exit Transition Work Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 12/7/26 | Fri 12/18/26 | 2121 | 2123 |  | Joy Schneider,Jimmy Cox,Angie Robertson
5665 | 2123 | Future Task |  |  | WP428 | Joy Schneider | Review | WP WP428 - Exit Transition Work Plan - Final Review & Edits | 12 hrs | 5 days | Mon 12/21/26 | Mon 12/28/26 | 2122 | 2124 |  | Joy Schneider,Jimmy Cox,Angie Robertson
5666 | 2124 | Future Task |  |  | WP428 | Joy Schneider | Approve | WP WP428 - Exit Transition Work Plan - Approve | 0 hrs | 0 days | Mon 12/28/26 | Mon 12/28/26 | 2123 | 2098 |  | Jimmy Cox
4 | 2125 | Late | [5 empty] | Administrative Tasks | 2,164.33 hrs | 1174 days | Mon 5/1/23 | Tue 12/28/27
10 | 2126 | Late | [5 empty] | Administrative Activities | 1,320 hrs | 1152 days | Thu 6/1/23 | Tue 12/28/27
2063 | 2127 | Late |  |  |  | Tommy Werner |  | Budget | 308 hrs | 933 days | Thu 6/1/23 | Mon 2/15/27
2064 | 2128 | Late |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q1 | 14 hrs | 30 days | Thu 6/1/23 | Thu 7/13/23
2065 | 2129 | Late |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Thu 6/1/23 | Wed 6/14/23 |  | 2130 |  | Tommy Werner,Gabriela Gibson
2066 | 2130 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Thu 6/15/23 | Wed 6/28/23 | 2129 | 2131 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2067 | 2131 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Thu 6/29/23 | Thu 7/13/23 | 2130 | 2132 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2068 | 2132 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Thu 7/13/23 | Thu 7/13/23 | 2131 | 2134SS-8 days |  | Tommy Werner | Add sccessor UID 2101 | TW
2069 | 2133 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q2 | 14 hrs | 30 days | Mon 7/3/23 | Mon 8/14/23
2070 | 2134 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 2132SS-8 days | 2135 |  | Tommy Werner,Gabriela Gibson | Change predecessor to Q1 draft (timing is funny on Q1, but this shouldn't be a true lag) | TW
2071 | 2135 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 2134 | 2136 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2072 | 2136 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 2135 | 2137 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2073 | 2137 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 2136 | 2139 |  | Tommy Werner
2074 | 2138 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q3 | 14 hrs | 30 days | Mon 10/2/23 | Mon 11/13/23
2075 | 2139 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 2137 | 2140 |  | Tommy Werner,Gabriela Gibson
2076 | 2140 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 2139 | 2141 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2077 | 2141 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 10/30/23 | Mon 11/13/23 | 2140 | 2142 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2078 | 2142 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 11/13/23 | Mon 11/13/23 | 2141 | 2144 |  | Tommy Werner
2079 | 2143 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q4 | 14 hrs | 30 days | Tue 1/2/24 | Tue 2/13/24
2080 | 2144 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Tue 1/2/24 | Tue 1/16/24 | 2142 | 2145 |  | Tommy Werner,Gabriela Gibson
2081 | 2145 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Wed 1/17/24 | Tue 1/30/24 | 2144 | 2146 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2082 | 2146 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Wed 1/31/24 | Tue 2/13/24 | 2145 | 2147 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2083 | 2147 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Tue 2/13/24 | Tue 2/13/24 | 2146 | 2159 |  | Tommy Werner
2084 | 2148 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 24-25 | 14 hrs | 30 days | Wed 5/1/24 | Wed 6/12/24
2085 | 2149 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 24-25 - Create | 4 hrs | 10 days | Wed 5/1/24 | Tue 5/14/24 |  | 2150 |  | Tommy Werner,Gabriela Gibson | Predecessor UID 2093 | TW
2086 | 2150 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 24-25 - Collaborative Review & Update | 4 hrs | 10 days | Wed 5/15/24 | Wed 5/29/24 | 2149 | 2151 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2087 | 2151 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 24-25 - Final Review & Edit | 6 hrs | 10 days | Thu 5/30/24 | Wed 6/12/24 | 2150 | 2152 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2088 | 2152 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 2151 | 2179 |  | Tommy Werner | Add successor UID 2097 | TW
2089 | 2153 | Late |  |  |  | Tommy Werner |  | Legislative Budget Request FY 24-25 | 14 hrs | 40 days | Thu 6/1/23 | Thu 7/27/23
2090 | 2154 | Late |  |  |  | Tommy Werner | Create | LBR FY 24-25 - Create | 4 hrs | 20 days | Thu 6/1/23 | Wed 6/28/23 |  | 2155 |  | Tommy Werner,Gabriela Gibson
2091 | 2155 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 24-25 - Collaborative Review & Update | 4 hrs | 10 days | Thu 6/29/23 | Thu 7/13/23 | 2154 | 2156 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2092 | 2156 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 24-25 - Final Review & Edit | 6 hrs | 10 days | Fri 7/14/23 | Thu 7/27/23 | 2155 | 2157 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2093 | 2157 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | Thu 7/27/23 | Thu 7/27/23 | 2156 | 2184 |  | Tommy Werner
2094 | 2158 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q1 | 14 hrs | 30 days | Mon 6/3/24 | Mon 7/15/24
2095 | 2159 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 2147 | 2160 |  | Tommy Werner,Gabriela Gibson
2096 | 2160 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 2159 | 2161 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2097 | 2161 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 2160 | 2162 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2098 | 2162 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 7/15/24 | Mon 7/15/24 | 2161 | 2164SS-10 days |  | Tommy Werner | Add sccessor UID 2101 | TW
2099 | 2163 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q2 | 14 hrs | 30 days | Mon 7/1/24 | Mon 8/12/24
2100 | 2164 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 2162SS-10 days | 2165 |  | Tommy Werner,Gabriela Gibson | Change predecessor to Q1 draft (timing is funny on Q1, but this shouldn't be a true lag) | TW
2101 | 2165 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Tue 7/16/24 | Mon 7/29/24 | 2164 | 2166 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2102 | 2166 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Tue 7/30/24 | Mon 8/12/24 | 2165 | 2167 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2103 | 2167 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 8/12/24 | Mon 8/12/24 | 2166 | 2169 |  | Tommy Werner
2104 | 2168 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q3 | 14 hrs | 30 days | Tue 10/1/24 | Tue 11/12/24
2105 | 2169 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Tue 10/1/24 | Mon 10/14/24 | 2167 | 2170 |  | Tommy Werner,Gabriela Gibson
2106 | 2170 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Tue 10/15/24 | Mon 10/28/24 | 2169 | 2171 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2107 | 2171 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Tue 10/29/24 | Tue 11/12/24 | 2170 | 2172 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2108 | 2172 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Tue 11/12/24 | Tue 11/12/24 | 2171 | 2174 |  | Tommy Werner
2109 | 2173 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q4 | 14 hrs | 30 days | Thu 1/2/25 | Thu 2/13/25
2110 | 2174 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Thu 1/2/25 | Wed 1/15/25 | 2172 | 2175 |  | Tommy Werner,Gabriela Gibson
2111 | 2175 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Thu 1/16/25 | Thu 1/30/25 | 2174 | 2176 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2112 | 2176 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Fri 1/31/25 | Thu 2/13/25 | 2175 | 2177 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2113 | 2177 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Thu 2/13/25 | Thu 2/13/25 | 2176 | 2189 |  | Tommy Werner
2114 | 2178 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 25-26 | 14 hrs | 30 days | Thu 5/1/25 | Thu 6/12/25
2115 | 2179 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 25-26 - Create | 4 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 2152 | 2180 |  | Tommy Werner,Gabriela Gibson | Add predecessor UID 2123 | TW
2116 | 2180 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 25-26 - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/15/25 | Thu 5/29/25 | 2179 | 2181 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2117 | 2181 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 25-26 - Final Review & Edit | 6 hrs | 10 days | Fri 5/30/25 | Thu 6/12/25 | 2180 | 2182 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2118 | 2182 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | Thu 6/12/25 | Thu 6/12/25 | 2181 | 2209 |  | Tommy Werner
2119 | 2183 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 25-26 | 14 hrs | 40 days | Mon 6/3/24 | Mon 7/29/24
2120 | 2184 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 25-26 - Create | 4 hrs | 20 days | Mon 6/3/24 | Fri 6/28/24 | 2157 | 2185 |  | Tommy Werner,Gabriela Gibson
2121 | 2185 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 25-26 - Collaborative Review & Update | 4 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 2184 | 2186 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2122 | 2186 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 25-26 - Final Review & Edit | 6 hrs | 10 days | Tue 7/16/24 | Mon 7/29/24 | 2185 | 2187 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2123 | 2187 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | Mon 7/29/24 | Mon 7/29/24 | 2186 | 2214 |  | Tommy Werner
2124 | 2188 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q1 | 14 hrs | 30 days | Mon 6/2/25 | Mon 7/14/25
2125 | 2189 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Mon 6/2/25 | Fri 6/13/25 | 2177 | 2190 |  | Tommy Werner,Gabriela Gibson
2126 | 2190 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Mon 6/16/25 | Fri 6/27/25 | 2189 | 2191 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2127 | 2191 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 6/30/25 | Mon 7/14/25 | 2190 | 2192 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2128 | 2192 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 7/14/25 | Mon 7/14/25 | 2191 | 2194FS-9 days |  | Tommy Werner | Add sccessor UID 2166 | TW
2129 | 2193 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q2 | 14 hrs | 30 days | Tue 7/1/25 | Tue 8/12/25
2130 | 2194 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Tue 7/1/25 | Tue 7/15/25 | 2192FS-9 days | 2195 |  | Tommy Werner,Gabriela Gibson | Change predecessor to Q1 draft (timing is funny on Q1, but this shouldn't be a true lag) | TW
2131 | 2195 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Wed 7/16/25 | Tue 7/29/25 | 2194 | 2196 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2132 | 2196 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Wed 7/30/25 | Tue 8/12/25 | 2195 | 2197 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2133 | 2197 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Tue 8/12/25 | Tue 8/12/25 | 2196 | 2199 |  | Tommy Werner
2134 | 2198 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q3 | 14 hrs | 30 days | Wed 10/1/25 | Wed 11/12/25
2135 | 2199 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Wed 10/1/25 | Tue 10/14/25 | 2197 | 2200 |  | Tommy Werner,Gabriela Gibson
2136 | 2200 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Wed 10/15/25 | Tue 10/28/25 | 2199 | 2201 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2137 | 2201 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Wed 10/29/25 | Wed 11/12/25 | 2200 | 2202 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2138 | 2202 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Wed 11/12/25 | Wed 11/12/25 | 2201 | 2204 |  | Tommy Werner
2139 | 2203 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q4 | 14 hrs | 30 days | Fri 1/2/26 | Fri 2/13/26
2140 | 2204 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Fri 1/2/26 | Thu 1/15/26 | 2202 | 2205 |  | Tommy Werner,Gabriela Gibson
2141 | 2205 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Fri 1/16/26 | Fri 1/30/26 | 2204 | 2206 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2142 | 2206 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 2/2/26 | Fri 2/13/26 | 2205 | 2207 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2143 | 2207 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Fri 2/13/26 | Fri 2/13/26 | 2206 | 2219 |  | Tommy Werner
2144 | 2208 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 26-27 | 14 hrs | 30 days | Fri 5/1/26 | Fri 6/12/26
2145 | 2209 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 26-27 - Create | 4 hrs | 10 days | Fri 5/1/26 | Thu 5/14/26 | 2182 | 2210 |  | Tommy Werner,Gabriela Gibson | Add predecessor UID 2153 | TW
2146 | 2210 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 26-27 - Collaborative Review & Update | 4 hrs | 10 days | Fri 5/15/26 | Fri 5/29/26 | 2209 | 2211 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2147 | 2211 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 26-27 - Final Review & Edit | 6 hrs | 10 days | Mon 6/1/26 | Fri 6/12/26 | 2210 | 2212 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2148 | 2212 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | Fri 6/12/26 | Fri 6/12/26 | 2211 |  |  | Tommy Werner
2149 | 2213 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 26-27 | 14 hrs | 40 days | Mon 6/2/25 | Mon 7/28/25
2150 | 2214 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 26-27 - Create | 4 hrs | 20 days | Mon 6/2/25 | Fri 6/27/25 | 2187 | 2215 |  | Tommy Werner,Gabriela Gibson
2151 | 2215 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 26-27 - Collaborative Review & Update | 4 hrs | 10 days | Mon 6/30/25 | Mon 7/14/25 | 2214 | 2216 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2152 | 2216 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 26-27 - Final Review & Edit | 6 hrs | 10 days | Tue 7/15/25 | Mon 7/28/25 | 2215 | 2217 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2153 | 2217 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | Mon 7/28/25 | Mon 7/28/25 | 2216 |  |  | Tommy Werner
2154 | 2218 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q1 | 14 hrs | 30 days | Mon 6/1/26 | Mon 7/13/26
2155 | 2219 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Mon 6/1/26 | Fri 6/12/26 | 2207 | 2220 |  | Tommy Werner,Gabriela Gibson
2156 | 2220 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Mon 6/15/26 | Fri 6/26/26 | 2219 | 2221 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2157 | 2221 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Mon 6/29/26 | Mon 7/13/26 | 2220 | 2222 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2158 | 2222 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 7/13/26 | Mon 7/13/26 | 2221 | 2224FS-8 days |  | Tommy Werner | Add sccessor UID 2161 | TW
2159 | 2223 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q2 | 14 hrs | 30 days | Wed 7/1/26 | Wed 8/12/26
2160 | 2224 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Wed 7/1/26 | Wed 7/15/26 | 2222FS-8 days | 2225 |  | Tommy Werner,Gabriela Gibson | Change predecessor to Q1 draft (timing is funny on Q1, but this shouldn't be a true lag) | TW
2161 | 2225 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Thu 7/16/26 | Wed 7/29/26 | 2224 | 2226 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2162 | 2226 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Thu 7/30/26 | Wed 8/12/26 | 2225 | 2227 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2163 | 2227 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Wed 8/12/26 | Wed 8/12/26 | 2226 | 2229 |  | Tommy Werner
2164 | 2228 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q3 | 14 hrs | 30 days | Thu 10/1/26 | Thu 11/12/26
2165 | 2229 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Thu 10/1/26 | Wed 10/14/26 | 2227 | 2230 |  | Tommy Werner,Gabriela Gibson
2166 | 2230 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Thu 10/15/26 | Wed 10/28/26 | 2229 | 2231 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2167 | 2231 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Thu 10/29/26 | Thu 11/12/26 | 2230 | 2232 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2168 | 2232 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Thu 11/12/26 | Thu 11/12/26 | 2231 | 2234 |  | Tommy Werner
2169 | 2233 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q4 | 14 hrs | 30 days | Mon 1/4/27 | Mon 2/15/27
2170 | 2234 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Mon 1/4/27 | Fri 1/15/27 | 2232 | 2235 |  | Tommy Werner,Gabriela Gibson
2171 | 2235 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review & Update | 4 hrs | 10 days | Tue 1/19/27 | Mon 2/1/27 | 2234 | 2236 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2172 | 2236 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review & Edits | 6 hrs | 10 days | Tue 2/2/27 | Mon 2/15/27 | 2235 | 2237 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2173 | 2237 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 2/15/27 | Mon 2/15/27 | 2236 |  |  | Tommy Werner
2174 | 2238 | Future Task | [5 empty] | Project Resources | 1,012 hrs | 1131 days | Fri 6/30/23 | Tue 12/28/27
2175 | 2239 | Future Task |  |  |  | Tommy Werner |  | Project Management Plan | 462 hrs | 1045 days | Wed 11/1/23 | Tue 12/28/27
2176 | 2240 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2023 | 54 hrs | 38 days | Wed 11/1/23 | Thu 12/28/23
2177 | 2241 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Wed 11/1/23 | Fri 12/1/23 |  | 2242 |  | Joy Schneider,Tommy Werner,Francisca Li,Jenifer Hartsfield,Gabriela Gibson
2178 | 2242 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Mon 12/4/23 | Fri 12/15/23 | 2241 | 2243 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2179 | 2243 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Mon 12/18/23 | Fri 12/22/23 | 2242 | 2244 |  | Jimmy Cox
2180 | 2244 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 4 hrs | 3 days | Tue 12/26/23 | Thu 12/28/23 | 2243 | 2246 |  | Tatiana Eubanks
2181 | 2245 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2024 | 51 hrs | 38 days | Fri 5/3/24 | Wed 6/26/24
2182 | 2246 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Fri 5/3/24 | Fri 5/31/24 | 2244 | 2247 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2183 | 2247 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 2246 | 2248 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2184 | 2248 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Mon 6/17/24 | Fri 6/21/24 | 2247 | 2249 |  | Jimmy Cox
2185 | 2249 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Mon 6/24/24 | Wed 6/26/24 | 2248 | 2251 |  | Tatiana Eubanks
2186 | 2250 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2024 | 51 hrs | 38 days | Mon 11/4/24 | Tue 12/31/24
2187 | 2251 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/4/24 | Wed 12/4/24 | 2249 | 2252 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2188 | 2252 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Thu 12/5/24 | Wed 12/18/24 | 2251 | 2253 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2189 | 2253 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Thu 12/19/24 | Thu 12/26/24 | 2252 | 2254 |  | Jimmy Cox
2190 | 2254 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Fri 12/27/24 | Tue 12/31/24 | 2253 | 2256 |  | Tatiana Eubanks
2191 | 2255 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2025 | 51 hrs | 38 days | Fri 5/2/25 | Wed 6/25/25
2192 | 2256 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Fri 5/2/25 | Fri 5/30/25 | 2254 | 2257 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2193 | 2257 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Mon 6/2/25 | Fri 6/13/25 | 2256 | 2258 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2194 | 2258 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Mon 6/16/25 | Fri 6/20/25 | 2257 | 2259 |  | Jimmy Cox
2195 | 2259 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Mon 6/23/25 | Wed 6/25/25 | 2258 | 2261 |  | Tatiana Eubanks
2196 | 2260 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2025 | 51 hrs | 38 days | Mon 11/3/25 | Tue 12/30/25
2197 | 2261 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/3/25 | Wed 12/3/25 | 2259 | 2262 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2198 | 2262 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Thu 12/4/25 | Wed 12/17/25 | 2261 | 2263 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2199 | 2263 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Thu 12/18/25 | Wed 12/24/25 | 2262 | 2264 |  | Jimmy Cox
2200 | 2264 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Fri 12/26/25 | Tue 12/30/25 | 2263 | 2266 |  | Tatiana Eubanks
2201 | 2265 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2026 | 51 hrs | 38 days | Fri 5/1/26 | Wed 6/24/26
2202 | 2266 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Fri 5/1/26 | Fri 5/29/26 | 2264 | 2267 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2203 | 2267 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Mon 6/1/26 | Fri 6/12/26 | 2266 | 2268 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2204 | 2268 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Mon 6/15/26 | Fri 6/19/26 | 2267 | 2269 |  | Jimmy Cox
2205 | 2269 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Mon 6/22/26 | Wed 6/24/26 | 2268 | 2271 |  | Tatiana Eubanks
2206 | 2270 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2026 | 51 hrs | 38 days | Mon 11/2/26 | Tue 12/29/26
2207 | 2271 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/2/26 | Wed 12/2/26 | 2269 | 2272 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2208 | 2272 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Thu 12/3/26 | Wed 12/16/26 | 2271 | 2273 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2209 | 2273 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Thu 12/17/26 | Wed 12/23/26 | 2272 | 2274 |  | Jimmy Cox
2210 | 2274 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Thu 12/24/26 | Tue 12/29/26 | 2273 | 2276 |  | Tatiana Eubanks
2211 | 2275 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2027 | 51 hrs | 38 days | Mon 5/3/27 | Thu 6/24/27
2212 | 2276 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 5/3/27 | Fri 5/28/27 | 2274 | 2277 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2213 | 2277 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Tue 6/1/27 | Mon 6/14/27 | 2276 | 2278 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2214 | 2278 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Tue 6/15/27 | Mon 6/21/27 | 2277 | 2279 |  | Jimmy Cox
2215 | 2279 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Tue 6/22/27 | Thu 6/24/27 | 2278 | 2281 |  | Tatiana Eubanks
2216 | 2280 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2027 | 51 hrs | 38 days | Mon 11/1/27 | Tue 12/28/27
2217 | 2281 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/1/27 | Wed 12/1/27 | 2279 | 2282 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2218 | 2282 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Collaborative Review & Update | 20 hrs | 10 days | Thu 12/2/27 | Wed 12/15/27 | 2281 | 2283 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2219 | 2283 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan - Final Review & Edit | 10 hrs | 5 days | Thu 12/16/27 | Wed 12/22/27 | 2282 | 2284 |  | Jimmy Cox
2220 | 2284 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Thu 12/23/27 | Tue 12/28/27 | 2283 |  |  | Tatiana Eubanks
2221 | 2285 | Future Task |  |  |  | Dusti Kincl |  | Florida PALM Style Guide | 104 hrs | 910 days | Wed 11/1/23 | Mon 6/14/27
2222 | 2286 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 23-24 | 13 hrs | 30 days | Wed 11/1/23 | Fri 12/15/23
2223 | 2287 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Wed 11/1/23 | Wed 11/22/23 |  | 2288 |  | Tatiana Eubanks,Elizabeth Gabert
2224 | 2288 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Mon 11/27/23 | Fri 12/8/23 | 2287 | 2289 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2225 | 2289 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Mon 12/11/23 | Fri 12/15/23 | 2288 | 2291 |  | Jimmy Cox
2226 | 2290 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 23-24 | 13 hrs | 30 days | Wed 5/1/24 | Wed 6/12/24
2227 | 2291 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Wed 5/1/24 | Tue 5/21/24 | 2289 | 2292 |  | Tatiana Eubanks,Elizabeth Gabert
2228 | 2292 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Wed 5/22/24 | Wed 6/5/24 | 2291 | 2293 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2229 | 2293 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Thu 6/6/24 | Wed 6/12/24 | 2292 | 2295 |  | Jimmy Cox
2230 | 2294 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 24-25 | 13 hrs | 30 days | Mon 11/4/24 | Wed 12/18/24
2231 | 2295 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 11/4/24 | Mon 11/25/24 | 2293 | 2296 |  | Tatiana Eubanks,Elizabeth Gabert
2232 | 2296 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Tue 11/26/24 | Wed 12/11/24 | 2295 | 2297 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2233 | 2297 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Thu 12/12/24 | Wed 12/18/24 | 2296 | 2299 |  | Jimmy Cox
2234 | 2298 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 24-25 | 13 hrs | 30 days | Thu 5/1/25 | Thu 6/12/25
2235 | 2299 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Thu 5/1/25 | Wed 5/21/25 | 2297 | 2300 |  | Tatiana Eubanks,Elizabeth Gabert
2236 | 2300 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/22/25 | Thu 6/5/25 | 2299 | 2301 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2237 | 2301 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Fri 6/6/25 | Thu 6/12/25 | 2300 | 2303 |  | Jimmy Cox
2238 | 2302 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 25-26 | 13 hrs | 30 days | Mon 11/3/25 | Wed 12/17/25
2239 | 2303 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 11/3/25 | Mon 11/24/25 | 2301 | 2304 |  | Tatiana Eubanks,Elizabeth Gabert
2240 | 2304 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Tue 11/25/25 | Wed 12/10/25 | 2303 | 2305 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2241 | 2305 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Thu 12/11/25 | Wed 12/17/25 | 2304 | 2307 |  | Jimmy Cox
2242 | 2306 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 25-26 | 13 hrs | 30 days | Mon 4/6/26 | Fri 5/15/26
2243 | 2307 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 4/6/26 | Fri 4/24/26 | 2305 | 2308 |  | Tatiana Eubanks,Elizabeth Gabert
2244 | 2308 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Mon 4/27/26 | Fri 5/8/26 | 2307 | 2309 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2245 | 2309 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Mon 5/11/26 | Fri 5/15/26 | 2308 | 2311 |  | Jimmy Cox
2246 | 2310 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 26-27 | 13 hrs | 30 days | Mon 11/2/26 | Wed 12/16/26
2247 | 2311 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 11/2/26 | Mon 11/23/26 | 2309 | 2312 |  | Tatiana Eubanks,Elizabeth Gabert
2248 | 2312 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Tue 11/24/26 | Wed 12/9/26 | 2311 | 2313 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2249 | 2313 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Thu 12/10/26 | Wed 12/16/26 | 2312 | 2315 |  | Jimmy Cox
2250 | 2314 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 26-27 | 13 hrs | 30 days | Mon 5/3/27 | Mon 6/14/27
2251 | 2315 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 5/3/27 | Fri 5/21/27 | 2313 | 2316 |  | Tatiana Eubanks,Elizabeth Gabert
2252 | 2316 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Collaborative Review & Update | 4 hrs | 10 days | Mon 5/24/27 | Mon 6/7/27 | 2315 | 2317 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2253 | 2317 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide - Final Review & Edit | 1 hr | 5 days | Tue 6/8/27 | Mon 6/14/27 | 2316 |  |  | Jimmy Cox
2254 | 2318 | Future Task | [5 empty] | Project Team Orientation Guide | 238 hrs | 252 days | Fri 6/30/23 | Fri 6/28/24
6683 | 2319 | Future Task |  |  | WP401 | Joy Schneider |  | WP401 - Project Orientation Guide | 88 hrs | 61 days | Fri 6/30/23 | Tue 9/26/23
6684 | 2320 | Future Task |  |  | WP401 | Joy Schneider | Create | WPED WP401 - Project Orientation Guide - Create | 8 hrs | 10 days | Fri 6/30/23 | Fri 7/14/23 | 32 | 2321 |  | Joy Schneider
6685 | 2321 | Future Task |  |  | WP401 | Joy Schneider | Submit | WPED WP401 - Project Orientation Guide - Submit | 0 hrs | 0 days | Fri 7/14/23 | Fri 7/14/23 | 2320 | 2322 |  | Joy Schneider
6686 | 2322 | Future Task |  |  | WP401 | Joy Schneider | Review | WPED WP401 - Project Orientation Guide - Review | 16 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 | 2321 | 2323 |  | Joy Schneider,Jimmy Cox,Angie Robertson,Sean Buchanan
6687 | 2323 | Future Task |  |  | WP401 | Joy Schneider | Approve | WPED WP401 - Project Orientation Guide - Approve | 0 hrs | 0 days | Fri 7/28/23 | Fri 7/28/23 | 2322 | 2324FS+11 days |  | Jimmy Cox
6688 | 2324 | Future Task |  |  | WP401 | Joy Schneider | Create | WP401 - Update Project Team Orientation Guide | 10 hrs | 5 days | Tue 8/15/23 | Mon 8/21/23 | 2323FS+11 days | 2325 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
6689 | 2325 | Future Task |  |  | WP401 | Joy Schneider | Create | WP401 - Project Team Orientation Guide - Collaborative Review & Update | 10 hrs | 5 days | Tue 8/22/23 | Mon 8/28/23 | 2324 | 2326 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
6690 | 2326 | Future Task |  |  | WP401 | Joy Schneider | Create | WP401 - Project Team Orientation Guide - Final Review & Update | 20 hrs | 5 days | Tue 8/29/23 | Tue 9/5/23 | 2325 | 2327 |  | Angie Robertson[25%],Jimmy Cox[25%]
6691 | 2327 | Future Task |  |  | WP401 | Joy Schneider | Submit | WP WP401 - Project Orientation Guide - Submit | 0 hrs | 0 days | Tue 9/5/23 | Tue 9/5/23 | 2326 | 2328 |  | Joy Schneider
6692 | 2328 | Future Task |  |  | WP401 | Joy Schneider | Review | WP WP401 - Project Orientation Guide - Collaborative Review & Update | 12 hrs | 10 days | Wed 9/6/23 | Tue 9/19/23 | 2327 | 2329 |  | Joy Schneider,Jimmy Cox,Angie Robertson
6693 | 2329 | Future Task |  |  | WP401 | Joy Schneider | Review | WP WP401 - Project Orientation Guide - Final Review & Edits | 12 hrs | 5 days | Wed 9/20/23 | Tue 9/26/23 | 2328 | 2330 |  | Joy Schneider,Jimmy Cox,Angie Robertson
6694 | 2330 | Future Task |  |  | WP401 | Joy Schneider | Approve | WP WP401 - Project Orientation Guide - Approve | 0 hrs | 0 days | Tue 9/26/23 | Tue 9/26/23 | 2329 | 2332FS-6 days | 2023-10-01 | Jimmy Cox
2255 | 2331 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q1 | 30 hrs | 15 days | Tue 9/19/23 | Mon 10/9/23
2257 | 2332 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Tue 9/19/23 | Mon 9/25/23 | 2330FS-6 days | 2333 |  | Jenifer Hartsfield,Gabriela Gibson
2258 | 2333 | Future Task |  |  |  | Julian Gotreaux | Review | FPO - Collaborative Review & Update | 10 hrs | 5 days | Tue 9/26/23 | Mon 10/2/23 | 2332 | 2334 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2259 | 2334 | Future Task |  |  |  | Julian Gotreaux | Review | FPO - Final Review & Update | 10 hrs | 5 days | Tue 10/3/23 | Mon 10/9/23 | 2333 | 23362436 |  | Angie Robertson,Jimmy Cox
2260 | 2335 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q2 | 40 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23
2261 | 2336 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | Fri 12/1/23 | Thu 12/7/23 | 2334 | 2337 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2262 | 2337 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Fri 12/8/23 | Thu 12/14/23 | 2336 | 2338 |  | Jenifer Hartsfield,Gabriela Gibson
2263 | 2338 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review & Update | 10 hrs | 5 days | Fri 12/15/23 | Thu 12/21/23 | 2337 | 2339 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2264 | 2339 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review & Update | 10 hrs | 5 days | Fri 12/22/23 | Fri 12/29/23 | 2338 | 2341 |  | Angie Robertson,Jimmy Cox
2265 | 2340 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q3 | 40 hrs | 20 days | Fri 3/1/24 | Thu 3/28/24
2266 | 2341 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 2339 | 2342 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2267 | 2342 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Fri 3/8/24 | Thu 3/14/24 | 2341 | 2343 |  | Jenifer Hartsfield,Gabriela Gibson
2268 | 2343 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review & Update | 10 hrs | 5 days | Fri 3/15/24 | Thu 3/21/24 | 2342 | 2344 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2269 | 2344 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review & Update | 10 hrs | 5 days | Fri 3/22/24 | Thu 3/28/24 | 2343 | 2346 |  | Angie Robertson,Jimmy Cox
2270 | 2345 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q4 | 40 hrs | 20 days | Mon 6/3/24 | Fri 6/28/24
2271 | 2346 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | Mon 6/3/24 | Fri 6/7/24 | 2344 | 2347 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2272 | 2347 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Mon 6/10/24 | Fri 6/14/24 | 2346 | 2348 |  | Jenifer Hartsfield,Gabriela Gibson
2273 | 2348 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review & Update | 10 hrs | 5 days | Mon 6/17/24 | Fri 6/21/24 | 2347 | 2349 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2274 | 2349 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review & Update | 10 hrs | 5 days | Mon 6/24/24 | Fri 6/28/24 | 2348 |  |  | Angie Robertson,Jimmy Cox
2275 | 2350 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 23-24 | 28 hrs | 134 days | Mon 7/17/23 | Mon 1/29/24
2276 | 2351 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 23-24 Q1 | 4 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 |  | 23522353 |  | Gabriela Gibson[5%]
2277 | 2352 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 23-24 Q3 | 4 hrs | 10 days | Tue 1/16/24 | Mon 1/29/24 | 2351 | 2359 |  | Gabriela Gibson
2278 | 2353 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 23-24 | 4 hrs | 10 days | Tue 8/15/23 | Mon 8/28/23 | 2351 | 2354 |  | Jenifer Hartsfield
2279 | 2354 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 23-24 | 4 hrs | 10 days | Fri 9/15/23 | Thu 9/28/23 | 2353 | 2355 |  | Tommy Werner
2280 | 2355 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 23-24 | 4 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 2354 | 2356 |  | Gabriela Gibson
2281 | 2356 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 23-24 | 4 hrs | 10 days | Wed 11/15/23 | Thu 11/30/23 | 2355 | 2357 |  | Tommy Werner
2282 | 2357 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 23-24 | 4 hrs | 10 days | Fri 12/15/23 | Fri 12/29/23 | 2356 | 2361 |  | Tommy Werner
2283 | 2358 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 24-25 | 28 hrs | 136 days | Mon 7/15/24 | Wed 1/29/25
2284 | 2359 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 24-25 Q1 | 4 hrs | 10 days | Mon 7/15/24 | Fri 7/26/24 | 2352 | 2360 |  | Gabriela Gibson
2285 | 2360 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 24-25 Q3 | 4 hrs | 10 days | Wed 1/15/25 | Wed 1/29/25 | 2359 | 2367 |  | Gabriela Gibson
2286 | 2361 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 24-25 | 4 hrs | 10 days | Thu 8/15/24 | Wed 8/28/24 | 2357 | 2362 |  | Jenifer Hartsfield
2287 | 2362 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 24-25 | 4 hrs | 10 days | Mon 9/16/24 | Fri 9/27/24 | 2361 | 2363 |  | Tommy Werner
2288 | 2363 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 24-25 | 4 hrs | 10 days | Tue 10/15/24 | Mon 10/28/24 | 2362 | 2364 |  | Gabriela Gibson
2289 | 2364 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 24-25 | 4 hrs | 10 days | Fri 11/15/24 | Mon 12/2/24 | 2363 | 2365 |  | Tommy Werner
2290 | 2365 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 24-25 | 4 hrs | 10 days | Mon 12/16/24 | Mon 12/30/24 | 2364 | 2369 |  | Tommy Werner
2291 | 2366 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 25-26 | 28 hrs | 136 days | Tue 7/15/25 | Thu 1/29/26
2292 | 2367 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 25-26 Q1 | 4 hrs | 10 days | Tue 7/15/25 | Mon 7/28/25 | 2360 | 2368 |  | Gabriela Gibson
2293 | 2368 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 25-26 Q3 | 4 hrs | 10 days | Thu 1/15/26 | Thu 1/29/26 | 2367 | 2375 |  | Gabriela Gibson
2294 | 2369 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 25-26 | 4 hrs | 10 days | Fri 8/15/25 | Thu 8/28/25 | 2365 | 2370 |  | Jenifer Hartsfield
2295 | 2370 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 25-26 | 4 hrs | 10 days | Mon 9/15/25 | Fri 9/26/25 | 2369 | 2371 |  | Tommy Werner
2296 | 2371 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 25-26 | 4 hrs | 10 days | Wed 10/15/25 | Tue 10/28/25 | 2370 | 2372 |  | Gabriela Gibson
2297 | 2372 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 25-26 | 4 hrs | 10 days | Mon 11/17/25 | Tue 12/2/25 | 2371 | 2373 |  | Tommy Werner
2298 | 2373 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 25-26 | 4 hrs | 10 days | Mon 12/15/25 | Mon 12/29/25 | 2372 | 2377 |  | Tommy Werner
2299 | 2374 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 26-27 | 28 hrs | 136 days | Wed 7/15/26 | Fri 1/29/27
2300 | 2375 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 26-27 Q1 | 4 hrs | 10 days | Wed 7/15/26 | Tue 7/28/26 | 2368 | 2376 |  | Gabriela Gibson
2301 | 2376 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 26-27 Q3 | 4 hrs | 10 days | Fri 1/15/27 | Fri 1/29/27 | 2375 |  |  | Gabriela Gibson
2302 | 2377 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 26-27 | 4 hrs | 10 days | Mon 8/17/26 | Fri 8/28/26 | 2373 | 2378 |  | Jenifer Hartsfield
2303 | 2378 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 26-27 | 4 hrs | 10 days | Tue 9/15/26 | Mon 9/28/26 | 2377 | 2379 |  | Tommy Werner
2304 | 2379 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 26-27 | 4 hrs | 10 days | Thu 10/15/26 | Wed 10/28/26 | 2378 | 2380 |  | Gabriela Gibson
2305 | 2380 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 26-27 | 4 hrs | 10 days | Mon 11/16/26 | Tue 12/1/26 | 2379 | 2381 |  | Tommy Werner
2306 | 2381 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 26-27 | 4 hrs | 10 days | Tue 12/15/26 | Tue 12/29/26 | 2380 |  |  | Tommy Werner
2307 | 2382 | Future Task |  |  |  | Julian Gotreaux |  | Access Control | 96 hrs | 965 days | Tue 8/15/23 | Mon 6/14/27
2308 | 2383 | Future Task |  |  |  | Julian Gotreaux |  | SharePoint Access Control | 32 hrs | 965 days | Tue 8/15/23 | Mon 6/14/27
2309 | 2384 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q1 | 2 hrs | 10 days | Tue 8/15/23 | Mon 8/28/23 |  | 2385 |  | Jenifer Hartsfield,Gabriela Gibson
2310 | 2385 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q2 | 2 hrs | 10 days | Wed 11/15/23 | Thu 11/30/23 | 2384 | 2386 |  | Jenifer Hartsfield,Gabriela Gibson
2311 | 2386 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q3 | 2 hrs | 10 days | Thu 2/15/24 | Wed 2/28/24 | 2385 | 2387 |  | Jenifer Hartsfield,Gabriela Gibson
2312 | 2387 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q4 | 2 hrs | 10 days | Wed 5/15/24 | Wed 5/29/24 | 2386 | 2388 |  | Jenifer Hartsfield,Gabriela Gibson
2313 | 2388 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q1 | 2 hrs | 10 days | Thu 8/15/24 | Wed 8/28/24 | 2387 | 2389 |  | Jenifer Hartsfield,Gabriela Gibson
2314 | 2389 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q2 | 2 hrs | 10 days | Fri 11/15/24 | Mon 12/2/24 | 2388 | 2390 |  | Jenifer Hartsfield,Gabriela Gibson
2315 | 2390 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q3 | 2 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 2389 | 2391 |  | Jenifer Hartsfield,Gabriela Gibson
2316 | 2391 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q4 | 2 hrs | 10 days | Thu 5/15/25 | Thu 5/29/25 | 2390 | 2392 |  | Jenifer Hartsfield,Gabriela Gibson
2317 | 2392 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q1 | 2 hrs | 10 days | Fri 8/15/25 | Thu 8/28/25 | 2391 | 2393 |  | Jenifer Hartsfield,Gabriela Gibson
2318 | 2393 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q2 | 2 hrs | 10 days | Mon 11/17/25 | Tue 12/2/25 | 2392 | 2394 |  | Jenifer Hartsfield,Gabriela Gibson
2319 | 2394 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q3 | 2 hrs | 10 days | Mon 2/16/26 | Fri 2/27/26 | 2393 | 2395 |  | Jenifer Hartsfield,Gabriela Gibson
2320 | 2395 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q4 | 2 hrs | 10 days | Fri 5/15/26 | Fri 5/29/26 | 2394 | 2396 |  | Jenifer Hartsfield,Gabriela Gibson
2321 | 2396 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q1 | 2 hrs | 10 days | Mon 8/17/26 | Fri 8/28/26 | 2395 | 2397 |  | Jenifer Hartsfield,Gabriela Gibson
2322 | 2397 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q2 | 2 hrs | 10 days | Mon 11/16/26 | Tue 12/1/26 | 2396 | 2398 |  | Jenifer Hartsfield,Gabriela Gibson
2323 | 2398 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q3 | 2 hrs | 10 days | Mon 2/15/27 | Fri 2/26/27 | 2397 | 2399 |  | Jenifer Hartsfield,Gabriela Gibson
2324 | 2399 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q4 | 2 hrs | 20 days | Mon 5/17/27 | Mon 6/14/27 | 2398 |  |  | Jenifer Hartsfield,Gabriela Gibson
2325 | 2400 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2023 | 8 hrs | 35 days | Mon 8/28/23 | Mon 10/16/23 |  |  |  |  | Remove all Smartsheet Tasks - these were for agency smartsheet access audits. This is now a recurring RW task. I suggest there be internal Project Smartsheet user reviews as part of other access audits | NK
2326 | 2401 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Mon 8/28/23 | Fri 9/1/23 |  | 2402 |  | Daylin Reyes,Richard Saltford
2327 | 2402 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Tue 9/5/23 | Mon 9/18/23 | 2401 | 2403 |  | Nikki Klein
2328 | 2403 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Tue 9/19/23 | Mon 10/9/23 | 2402 | 2404 |  | Richard Saltford
2329 | 2404 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Tue 10/10/23 | Mon 10/16/23 | 2403 |  |  | Daylin Reyes
2330 | 2405 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2024 | 8 hrs | 35 days | Tue 2/27/24 | Mon 4/15/24 |  |  |  |  | Remove all Smartsheet Tasks - these were for agency smartsheet access audits. This is now a recurring RW task. I suggest there be internal Project Smartsheet user reviews as part of other access audits | NK
2331 | 2406 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 2/27/24 | Mon 3/4/24 |  | 2407 |  | Daylin Reyes,Richard Saltford
2332 | 2407 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Tue 3/5/24 | Mon 3/18/24 | 2406 | 2408 |  | Nikki Klein
2333 | 2408 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Tue 3/19/24 | Mon 4/8/24 | 2407 | 2409 |  | Richard Saltford
2334 | 2409 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Tue 4/9/24 | Mon 4/15/24 | 2408 | 2411 |  | Daylin Reyes
2335 | 2410 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2024 | 8 hrs | 35 days | Tue 8/27/24 | Tue 10/15/24 |  |  |  |  | Remove all Smartsheet Tasks - these were for agency smartsheet access audits. This is now a recurring RW task. I suggest there be internal Project Smartsheet user reviews as part of other access audits | NK
2336 | 2411 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 8/27/24 | Tue 9/3/24 | 2409 | 2412 |  | Daylin Reyes,Richard Saltford
2337 | 2412 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Wed 9/4/24 | Tue 9/17/24 | 2411 | 2413 |  | Nikki Klein
2338 | 2413 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Wed 9/18/24 | Tue 10/8/24 | 2412 | 2414 |  | Richard Saltford
2339 | 2414 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Wed 10/9/24 | Tue 10/15/24 | 2413 | 2416 |  | Daylin Reyes
2340 | 2415 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2025 | 8 hrs | 35 days | Tue 2/25/25 | Mon 4/14/25 |  |  |  |  | Remove all Smartsheet Tasks - these were for agency smartsheet access audits. This is now a recurring RW task. I suggest there be internal Project Smartsheet user reviews as part of other access audits | NK
2341 | 2416 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 2/25/25 | Mon 3/3/25 | 2414 | 2417 |  | Daylin Reyes,Richard Saltford
2342 | 2417 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Tue 3/4/25 | Mon 3/17/25 | 2416 | 2418 |  | Nikki Klein
2343 | 2418 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Tue 3/18/25 | Mon 4/7/25 | 2417 | 2419 |  | Richard Saltford
2344 | 2419 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Tue 4/8/25 | Mon 4/14/25 | 2418 | 2421 |  | Daylin Reyes
2345 | 2420 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2025 | 8 hrs | 35 days | Tue 8/26/25 | Tue 10/14/25 |  |  |  |  | Remove all Smartsheet Tasks - these were for agency smartsheet access audits. This is now a recurring RW task. I suggest there be internal Project Smartsheet user reviews as part of other access audits | NK
2346 | 2421 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 8/26/25 | Tue 9/2/25 | 2419 | 2422 |  | Daylin Reyes,Richard Saltford
2347 | 2422 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Wed 9/3/25 | Tue 9/16/25 | 2421 | 2423 |  | Nikki Klein
2348 | 2423 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Wed 9/17/25 | Tue 10/7/25 | 2422 | 2424 |  | Richard Saltford
2349 | 2424 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Wed 10/8/25 | Tue 10/14/25 | 2423 | 2426 |  | Daylin Reyes
2350 | 2425 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2026 | 8 hrs | 35 days | Tue 2/24/26 | Mon 4/13/26 |  |  |  |  | Remove all Smartsheet Tasks - these were for agency smartsheet access audits. This is now a recurring RW task. I suggest there be internal Project Smartsheet user reviews as part of other access audits | NK
2351 | 2426 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 2/24/26 | Mon 3/2/26 | 2424 | 2427 |  | Daylin Reyes,Richard Saltford
2352 | 2427 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Tue 3/3/26 | Mon 3/16/26 | 2426 | 2428 |  | Nikki Klein
2353 | 2428 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Tue 3/17/26 | Mon 4/6/26 | 2427 | 2429 |  | Richard Saltford
2354 | 2429 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Tue 4/7/26 | Mon 4/13/26 | 2428 | 2431 |  | Daylin Reyes
2355 | 2430 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2026 | 8 hrs | 35 days | Tue 8/25/26 | Tue 10/13/26 |  |  |  |  | Remove all Smartsheet Tasks - these were for agency smartsheet access audits. This is now a recurring RW task. I suggest there be internal Project Smartsheet user reviews as part of other access audits | NK
2356 | 2431 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 8/25/26 | Mon 8/31/26 | 2429 | 2432 |  | Daylin Reyes,Richard Saltford
2357 | 2432 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Tue 9/1/26 | Tue 9/15/26 | 2431 | 2433 |  | Nikki Klein
2358 | 2433 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Wed 9/16/26 | Tue 10/6/26 | 2432 | 2434 |  | Richard Saltford
2359 | 2434 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Wed 10/7/26 | Tue 10/13/26 | 2433 |  |  | Daylin Reyes
2360 | 2435 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2027 | 8 hrs | 35 days | Tue 2/23/27 | Mon 4/12/27 |  |  |  |  | Remove all Smartsheet Tasks - these were for agency smartsheet access audits. This is now a recurring RW task. I suggest there be internal Project Smartsheet user reviews as part of other access audits | NK
2361 | 2436 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 2/23/27 | Mon 3/1/27 | 2334 | 2437 |  | Daylin Reyes,Richard Saltford
2362 | 2437 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Tue 3/2/27 | Mon 3/15/27 | 2436 | 2438 |  | Nikki Klein
2363 | 2438 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Tue 3/16/27 | Mon 4/5/27 | 2437 | 2439 |  | Richard Saltford
2364 | 2439 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Tue 4/6/27 | Mon 4/12/27 | 2438 |  |  | Daylin Reyes
2365 | 2440 | Late | [5 empty] | Proviso Requirements | 844.33 hrs | 1091 days | Mon 5/1/23 | Thu 8/26/27
2366 | 2441 | Future Task |  |  |  | Tommy Werner |  | Monthly Status Reporting | 192 hrs | 241 days | Tue 8/1/23 | Mon 7/15/24
2367 | 2442 | Future Task |  |  |  | Tommy Werner |  | July 2023 Monthly Status Reporting | 16 hrs | 11 days | Tue 8/1/23 | Tue 8/15/23
2368 | 2443 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | Tue 8/1/23 | Thu 8/10/23 |  | 2444SS,2445SS,2446SS |  | Tommy Werner,Gabriela Gibson
2369 | 2444 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 2443SS | 2447 |  | Tommy Werner,Joy Schneider,Francisca Li,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2370 | 2445 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | Tue 8/1/23 | Thu 8/10/23 | 2443SS | 2447 |  | Tommy Werner,Jenifer Hartsfield
2371 | 2446 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 2443SS | 2447 |  | Dusti Kincl,Nikki Klein | These are bimonthly reports starting in FY 2023. Please adjust to show bimonthly tasks starting September 2023. | Angie
2372 | 2447 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Tue 8/15/23 | Tue 8/15/23 | 244624442445 | 2449 |  | Dusti Kincl,Jimmy Cox
2373 | 2448 | Future Task |  |  |  | Tommy Werner |  | August 2023 Monthly Status Reporting | 16 hrs | 10 days | Fri 9/1/23 | Fri 9/15/23
2374 | 2449 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 2447 | 2450SS,2451SS,2452SS,2453 |  | Tommy Werner,Gabriela Gibson
2375 | 2450 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Fri 9/1/23 | Thu 9/14/23 | 2449SS | 2453 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2376 | 2451 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 2449SS | 2453 |  | Tommy Werner,Jenifer Hartsfield
2377 | 2452 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Fri 9/1/23 | Thu 9/14/23 | 2449SS | 2453 |  | Dusti Kincl,Nikki Klein | These are bimonthly reports starting in FY 2023. Please adjust to show bimonthly tasks starting September 2023. | Angie
2378 | 2453 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 9/15/23 | Fri 9/15/23 | 2449245024512450 | 2455 |  | Dusti Kincl,Jimmy Cox
2379 | 2454 | Future Task |  |  |  | Tommy Werner |  | September 2023 Monthly Status Reporting | 16 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23
2380 | 2455 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | Mon 10/2/23 | Tue 10/10/23 | 2453 | 2456SS,2457SS,2458SS,2459 |  | Tommy Werner,Gabriela Gibson
2381 | 2456 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Mon 10/2/23 | Thu 10/12/23 | 2455SS | 2459 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2382 | 2457 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | Mon 10/2/23 | Tue 10/10/23 | 2455SS | 2459 |  | Tommy Werner,Jenifer Hartsfield
2383 | 2458 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Mon 10/2/23 | Thu 10/12/23 | 2455SS | 2459 |  | Dusti Kincl,Nikki Klein | These are bimonthly reports starting in FY 2023. Please adjust to show bimonthly tasks starting September 2023. | Angie
2384 | 2459 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 10/13/23 | Fri 10/13/23 | 2455245624572450 | 2461 |  | Dusti Kincl,Jimmy Cox
2385 | 2460 | Future Task |  |  |  | Tommy Werner |  | October 2023 Monthly Status Reporting | 16 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23
2386 | 2461 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | Wed 11/1/23 | Thu 11/9/23 | 2459 | 2462SS,2463SS,2464SS,2465 |  | Tommy Werner,Gabriela Gibson
2387 | 2462 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Wed 11/1/23 | Tue 11/14/23 | 2461SS | 2465 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2388 | 2463 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | Wed 11/1/23 | Thu 11/9/23 | 2461SS | 2465 |  | Tommy Werner,Jenifer Hartsfield
2389 | 2464 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Wed 11/1/23 | Tue 11/14/23 | 2461SS | 2465 |  | Dusti Kincl,Nikki Klein | These are bimonthly reports starting in FY 2023. Please adjust to show bimonthly tasks starting September 2023. | Angie
2390 | 2465 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Wed 11/15/23 | Wed 11/15/23 | 2461246224632460 | 2467 |  | Dusti Kincl,Jimmy Cox
2391 | 2466 | Future Task |  |  |  | Tommy Werner |  | November 2023 Monthly Status Reporting | 16 hrs | 11 days | Fri 12/1/23 | Fri 12/15/23
2392 | 2467 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | Fri 12/1/23 | Fri 12/8/23 | 2465 | 2468SS,2469SS,2470SS,2471 |  | Tommy Werner,Gabriela Gibson
2393 | 2468 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Fri 12/1/23 | Thu 12/14/23 | 2467SS | 2471 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2394 | 2469 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | Fri 12/1/23 | Fri 12/8/23 | 2467SS |  |  | Tommy Werner,Jenifer Hartsfield
2395 | 2470 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Fri 12/1/23 | Thu 12/14/23 | 2467SS | 2471 |  | Dusti Kincl,Nikki Klein | These are bimonthly reports starting in FY 2023. Please adjust to show bimonthly tasks starting September 2023. | Angie
2396 | 2471 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 12/15/23 | Fri 12/15/23 | 246724682470 | 2473 |  | Dusti Kincl,Jimmy Cox
2397 | 2472 | Future Task |  |  |  | Tommy Werner |  | December 2023 Monthly Status Reporting | 16 hrs | 9 days | Tue 1/2/24 | Fri 1/12/24
2398 | 2473 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | Tue 1/2/24 | Tue 1/9/24 | 2471 | 2474SS,2477,2475SS,2476SS |  | Tommy Werner,Gabriela Gibson
2399 | 2474 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 8 days | Tue 1/2/24 | Thu 1/11/24 | 2473SS | 2477 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2400 | 2475 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | Tue 1/2/24 | Tue 1/9/24 | 2473SS | 2477 |  | Tommy Werner,Jenifer Hartsfield
2401 | 2476 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 8 days | Tue 1/2/24 | Thu 1/11/24 | 2473SS | 2477 |  | Dusti Kincl,Nikki Klein | These are bimonthly reports starting in FY 2023. Please adjust to show bimonthly tasks starting September 2023. | Angie
2402 | 2477 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 1/12/24 | Fri 1/12/24 | 2473247424752470 | 2479 |  | Dusti Kincl,Jimmy Cox
2403 | 2478 | Future Task |  |  |  | Tommy Werner |  | January 2023 Monthly Status Reporting | 16 hrs | 11 days | Thu 2/1/24 | Thu 2/15/24
2404 | 2479 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | Thu 2/1/24 | Fri 2/9/24 | 2477 | 2480SS,2481SS,2482SS,2483 |  | Tommy Werner,Gabriela Gibson
2405 | 2480 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Thu 2/1/24 | Wed 2/14/24 | 2479SS | 2483 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2406 | 2481 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | Thu 2/1/24 | Fri 2/9/24 | 2479SS | 2483 |  | Tommy Werner,Jenifer Hartsfield
2407 | 2482 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Thu 2/1/24 | Wed 2/14/24 | 2479SS | 2483 |  | Dusti Kincl,Nikki Klein | These are bimonthly reports starting in FY 2023. Please adjust to show bimonthly tasks starting September 2023. | Angie
2408 | 2483 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Thu 2/15/24 | Thu 2/15/24 | 2479248024812480 | 2485 |  | Dusti Kincl,Jimmy Cox
2409 | 2484 | Future Task |  |  |  | Tommy Werner |  | February 2024 Monthly Status Reporting | 16 hrs | 11 days | Fri 3/1/24 | Fri 3/15/24
2410 | 2485 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | Fri 3/1/24 | Fri 3/8/24 | 2483 | 2486SS,2487SS,2488SS,2489 |  | Tommy Werner,Gabriela Gibson
2411 | 2486 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 2485SS | 2489 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2412 | 2487 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | Fri 3/1/24 | Fri 3/8/24 | 2485SS | 2489 |  | Tommy Werner,Jenifer Hartsfield
2413 | 2488 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 2485SS | 2489 |  | Dusti Kincl,Nikki Klein | These are bimonthly reports starting in FY 2023. Please adjust to show bimonthly tasks starting September 2023. | Angie
2414 | 2489 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 3/15/24 | Fri 3/15/24 | 2485248624872480 | 2491 |  | Dusti Kincl,Jimmy Cox
2415 | 2490 | Future Task |  |  |  | Tommy Werner |  | March 2024 Monthly Status Reporting | 16 hrs | 11 days | Mon 4/1/24 | Mon 4/15/24
2416 | 2491 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | Mon 4/1/24 | Wed 4/10/24 | 2489 | 2492SS,2493SS,2494SS,2495 |  | Tommy Werner,Gabriela Gibson
2417 | 2492 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Mon 4/1/24 | Fri 4/12/24 | 2491SS | 2495 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2418 | 2493 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | Mon 4/1/24 | Wed 4/10/24 | 2491SS | 2495 |  | Tommy Werner,Jenifer Hartsfield
2419 | 2494 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Mon 4/1/24 | Fri 4/12/24 | 2491SS | 2495 |  | Dusti Kincl,Nikki Klein | These are bimonthly reports starting in FY 2023. Please adjust to show bimonthly tasks starting September 2023. | Angie
2420 | 2495 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Mon 4/15/24 | Mon 4/15/24 | 2491249224932490 | 2497 |  | Dusti Kincl,Jimmy Cox
2421 | 2496 | Future Task |  |  |  | Tommy Werner |  | April 2024 Monthly Status Reporting | 16 hrs | 11 days | Wed 5/1/24 | Wed 5/15/24
2422 | 2497 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | Wed 5/1/24 | Fri 5/10/24 | 2495 | 2498SS,2499SS,2500SS,2501 |  | Tommy Werner,Gabriela Gibson
2423 | 2498 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Wed 5/1/24 | Tue 5/14/24 | 2497SS | 2501 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2424 | 2499 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | Wed 5/1/24 | Fri 5/10/24 | 2497SS | 2501 |  | Tommy Werner,Jenifer Hartsfield
2425 | 2500 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Wed 5/1/24 | Tue 5/14/24 | 2497SS | 2501 |  | Dusti Kincl,Nikki Klein | These are bimonthly reports starting in FY 2023. Please adjust to show bimonthly tasks starting September 2023. | Angie
2426 | 2501 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Wed 5/15/24 | Wed 5/15/24 | 2497249824992500 | 2503 |  | Dusti Kincl,Jimmy Cox
2427 | 2502 | Future Task |  |  |  | Tommy Werner |  | May 2024 Monthly Status Reporting | 16 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24
2428 | 2503 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | Mon 6/3/24 | Mon 6/10/24 | 2501 | 2504SS,2505SS,2506SS,2507 |  | Tommy Werner,Gabriela Gibson
2429 | 2504 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Mon 6/3/24 | Thu 6/13/24 | 2503SS |  |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2430 | 2505 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | Mon 6/3/24 | Mon 6/10/24 | 2503SS | 2507 |  | Tommy Werner,Jenifer Hartsfield
2431 | 2506 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Mon 6/3/24 | Thu 6/13/24 | 2503SS | 2507 |  | Dusti Kincl,Nikki Klein | These are bimonthly reports starting in FY 2023. Please adjust to show bimonthly tasks starting September 2023. | Angie
2432 | 2507 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 6/14/24 | Fri 6/14/24 | 250325052506 | 2509 |  | Dusti Kincl,Jimmy Cox
2433 | 2508 | Future Task |  |  |  | Tommy Werner |  | June 2024 Monthly Status Reporting | 16 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24
2434 | 2509 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | Mon 7/1/24 | Wed 7/10/24 | 2507 | 2510SS,2511SS,2512SS |  | Tommy Werner,Gabriela Gibson
2435 | 2510 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 2509SS | 2513 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2436 | 2511 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | Mon 7/1/24 | Wed 7/10/24 | 2509SS | 2513 |  | Tommy Werner,Jenifer Hartsfield
2437 | 2512 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 2509SS | 2513 |  | Dusti Kincl,Nikki Klein | These are bimonthly reports starting in FY 2023. Please adjust to show bimonthly tasks starting September 2023. | Angie
2438 | 2513 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Mon 7/15/24 | Mon 7/15/24 | 251025112512 |  |  | Dusti Kincl,Jimmy Cox
9 | 2514 | Late | [5 empty] | Monthly Performance Reporting | 520.33 hrs | 1091 days | Mon 5/1/23 | Thu 8/26/27
6232 | 2515 | Complete |  |  | D219 | Joy Schneider |  | D219 - Monthly Performance Report (April 2023) | 10.33 hrs | 24 days | Mon 5/1/23 | Fri 6/2/23
6364 | 2516 | Complete |  |  | D219 | Joy Schneider | Create | D219 - Create April 2023 Monthly Performance Report | 2.33 hrs | 7 days | Mon 5/1/23 | Tue 5/9/23 | 1 | 2517 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6233 | 2517 | Complete |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 5/10/23 | Wed 5/10/23 | 2516 | 2518 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6234 | 2518 | Complete |  |  | D219 | Joy Schneider | Submit | DEL D219 - Monthly Performance Report (April 2023) - Submit | 0 hrs | 0 days | Wed 5/10/23 | Wed 5/10/23 | 2517 | 2519 |  | Joy Schneider
6235 | 2519 | Complete |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Department QC | 2 hrs | 14 days | Thu 5/11/23 | Wed 5/31/23 | 2518 | 2520 |  | Gabriela Gibson
6236 | 2520 | Complete |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Contract Manager Review | 2 hrs | 2 days | Thu 6/1/23 | Fri 6/2/23 | 2519 | 2521 |  | Sean Buchanan
6237 | 2521 | Complete |  |  | D219 | Joy Schneider | Accept | DEL D219 - Monthly Performance Report (April 2023) - Accept | 0 hrs | 0 days | Fri 6/2/23 | Fri 6/2/23 | 2520 | 2523FS-2 days |  | Sean Buchanan
6238 | 2522 | Late |  |  | D225 | Joy Schneider |  | D225 - Monthly Performance Report (May 2023) | 10 hrs | 19 days | Thu 6/1/23 | Tue 6/27/23
6365 | 2523 | Late |  |  | D225 | Joy Schneider | Create | D225 - Create May 2023 Monthly Performance Report | 3 hrs | 9 days | Thu 6/1/23 | Tue 6/13/23 | 2521FS-2 days | 2524 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6239 | 2524 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 6/14/23 | Wed 6/14/23 | 2523 | 2525 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6240 | 2525 | Future Task |  |  | D225 | Joy Schneider | Submit | DEL D225 - Monthly Performance Report (May 2023) - Submit | 0 hrs | 0 days | Wed 6/14/23 | Wed 6/14/23 | 2524 | 2526 |  | Joy Schneider
6241 | 2526 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Department QC | 1 hr | 7 days | Thu 6/15/23 | Fri 6/23/23 | 2525 | 2527 |  | Gabriela Gibson
6242 | 2527 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Contract Manager Review | 2 hrs | 2 days | Mon 6/26/23 | Tue 6/27/23 | 2526 | 2528 |  | Sean Buchanan
6243 | 2528 | Future Task |  |  | D225 | Joy Schneider | Accept | DEL D225 - Monthly Performance Report (May 2023) - Accept | 0 hrs | 0 days | Tue 6/27/23 | Tue 6/27/23 | 2527 | 2530 |  | Sean Buchanan
6244 | 2529 | Future Task |  |  | D232 | Joy Schneider |  | D232 - Monthly Performance Report (June 2023) | 10 hrs | 19 days | Mon 7/3/23 | Fri 7/28/23
6366 | 2530 | Future Task |  |  | D232 | Joy Schneider | Create | D232 - Create June 2023 Monthly Performance Report | 3 hrs | 9 days | Mon 7/3/23 | Fri 7/14/23 | 2528 | 2531 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6245 | 2531 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 7/17/23 | Mon 7/17/23 | 2530 | 2532 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6246 | 2532 | Future Task |  |  | D232 | Joy Schneider | Submit | DEL D232 - Monthly Performance Report (June 2023) - Submit | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 2531 | 2533 |  | Joy Schneider
6247 | 2533 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Department QC | 1 hr | 7 days | Tue 7/18/23 | Wed 7/26/23 | 2532 | 2534 |  | Gabriela Gibson
6248 | 2534 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Contract Manager Review | 2 hrs | 2 days | Thu 7/27/23 | Fri 7/28/23 | 2533 | 2535 |  | Sean Buchanan
6249 | 2535 | Future Task |  |  | D232 | Joy Schneider | Accept | DEL D232 - Monthly Performance Report (June 2023) - Accept | 0 hrs | 0 days | Fri 7/28/23 | Fri 7/28/23 | 2534 | 2537 |  | Sean Buchanan
6250 | 2536 | Future Task |  |  | D239 | Joy Schneider |  | D239 - Monthly Performance Report (July 2023) | 10 hrs | 19 days | Tue 8/1/23 | Fri 8/25/23
6367 | 2537 | Future Task |  |  | D239 | Joy Schneider | Create | D239 - Create July 2023 Monthly Performance Report | 3 hrs | 9 days | Tue 8/1/23 | Fri 8/11/23 | 2535 | 2538 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6251 | 2538 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 8/14/23 | Mon 8/14/23 | 2537 | 2539 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6252 | 2539 | Future Task |  |  | D239 | Joy Schneider | Submit | DEL D239 - Monthly Performance Report (July 2023) - Submit | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 2538 | 2540 |  | Joy Schneider
6253 | 2540 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Department QC | 1 hr | 7 days | Tue 8/15/23 | Wed 8/23/23 | 2539 | 2541 |  | Gabriela Gibson
6254 | 2541 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Contract Manager Review | 2 hrs | 2 days | Thu 8/24/23 | Fri 8/25/23 | 2540 | 2542 |  | Sean Buchanan
6255 | 2542 | Future Task |  |  | D239 | Joy Schneider | Accept | DEL D239 - Monthly Performance Report (July 2023) - Accept | 0 hrs | 0 days | Fri 8/25/23 | Fri 8/25/23 | 2541 | 2544 |  | Sean Buchanan
6256 | 2543 | Future Task |  |  | D249 | Joy Schneider |  | D249 - Monthly Performance Report (August 2023) | 10 hrs | 19 days | Fri 9/1/23 | Thu 9/28/23
6368 | 2544 | Future Task |  |  | D249 | Joy Schneider | Create | D249 - Create August 2023 Monthly Performance Report | 3 hrs | 9 days | Fri 9/1/23 | Thu 9/14/23 | 2542 | 2545 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6257 | 2545 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 9/15/23 | Fri 9/15/23 | 2544 | 2546 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6258 | 2546 | Future Task |  |  | D249 | Joy Schneider | Submit | DEL D249 - Monthly Performance Report (August 2023) - Submit | 0 hrs | 0 days | Fri 9/15/23 | Fri 9/15/23 | 2545 | 2547 |  | Joy Schneider
6259 | 2547 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Department QC | 1 hr | 7 days | Mon 9/18/23 | Tue 9/26/23 | 2546 | 2548 |  | Gabriela Gibson
6260 | 2548 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 9/27/23 | Thu 9/28/23 | 2547 | 2549 |  | Sean Buchanan
6261 | 2549 | Future Task |  |  | D249 | Joy Schneider | Accept | DEL D249 - Monthly Performance Report (August 2023) - Accept | 0 hrs | 0 days | Thu 9/28/23 | Thu 9/28/23 | 2548 | 2551 |  | Sean Buchanan
6262 | 2550 | Future Task |  |  | D253 | Joy Schneider |  | D253 - Monthly Performance Report (September 2023) | 10 hrs | 19 days | Mon 10/2/23 | Thu 10/26/23
6369 | 2551 | Future Task |  |  | D253 | Joy Schneider | Create | D253 - Create September 2023 Monthly Performance Report | 3 hrs | 9 days | Mon 10/2/23 | Thu 10/12/23 | 2549 | 2552 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6263 | 2552 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 10/13/23 | Fri 10/13/23 | 2551 | 2553 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6264 | 2553 | Future Task |  |  | D253 | Joy Schneider | Submit | DEL D253 - Monthly Performance Report (September 2023) - Submit | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 2552 | 2554 |  | Joy Schneider
6265 | 2554 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Department QC | 1 hr | 7 days | Mon 10/16/23 | Tue 10/24/23 | 2553 | 2555 |  | Gabriela Gibson
6266 | 2555 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 10/25/23 | Thu 10/26/23 | 2554 | 2556 |  | Sean Buchanan
6267 | 2556 | Future Task |  |  | D253 | Joy Schneider | Accept | DEL D253 - Monthly Performance Report (September 2023) - Accept | 0 hrs | 0 days | Thu 10/26/23 | Thu 10/26/23 | 2555 | 2558 |  | Sean Buchanan
6268 | 2557 | Future Task |  |  | D257 | Joy Schneider |  | D257 - Monthly Performance Report (October 2023) | 10 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23
6370 | 2558 | Future Task |  |  | D257 | Joy Schneider | Create | D257 - Create October 2023 Monthly Performance Report | 3 hrs | 9 days | Wed 11/1/23 | Tue 11/14/23 | 2556 | 2559 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6269 | 2559 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 11/15/23 | Wed 11/15/23 | 2558 | 2560 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6270 | 2560 | Future Task |  |  | D257 | Joy Schneider | Submit | DEL D257 - Monthly Performance Report (October 2023) - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 2559 | 2561 |  | Joy Schneider
6271 | 2561 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Department QC | 1 hr | 7 days | Thu 11/16/23 | Tue 11/28/23 | 2560 | 2562 |  | Gabriela Gibson
6272 | 2562 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 11/29/23 | Thu 11/30/23 | 2561 | 2563 |  | Sean Buchanan
6273 | 2563 | Future Task |  |  | D257 | Joy Schneider | Accept | DEL D257 - Monthly Performance Report (October 2023) - Accept | 0 hrs | 0 days | Thu 11/30/23 | Thu 11/30/23 | 2562 | 2565 |  | Sean Buchanan
6274 | 2564 | Future Task |  |  | D261 | Joy Schneider |  | D261 - Monthly Performance Report (November 2023) | 10 hrs | 19 days | Fri 12/1/23 | Thu 12/28/23
6385 | 2565 | Future Task |  |  | D261 | Joy Schneider | Create | D261 - Create November 2023 Monthly Performance Report | 3 hrs | 9 days | Fri 12/1/23 | Wed 12/13/23 | 2563 | 2566 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6275 | 2566 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 12/14/23 | Thu 12/14/23 | 2565 | 2567 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6276 | 2567 | Future Task |  |  | D261 | Joy Schneider | Submit | DEL D261 - Monthly Performance Report (November 2023) - Submit | 0 hrs | 0 days | Thu 12/14/23 | Thu 12/14/23 | 2566 | 2568 |  | Joy Schneider
6277 | 2568 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Department QC | 1 hr | 7 days | Fri 12/15/23 | Tue 12/26/23 | 2567 | 2569 |  | Gabriela Gibson
6278 | 2569 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 12/27/23 | Thu 12/28/23 | 2568 | 2570 |  | Sean Buchanan
6279 | 2570 | Future Task |  |  | D261 | Joy Schneider | Accept | DEL D261 - Monthly Performance Report (November 2023) - Accept | 0 hrs | 0 days | Thu 12/28/23 | Thu 12/28/23 | 2569 | 2572 |  | Sean Buchanan
6280 | 2571 | Future Task |  |  | D267 | Joy Schneider |  | D267 - Monthly Performance Report (December 2023) | 10 hrs | 19 days | Tue 1/2/24 | Mon 1/29/24
6384 | 2572 | Future Task |  |  | D267 | Joy Schneider | Create | D267 - Create December 2023 Monthly Performance Report | 3 hrs | 9 days | Tue 1/2/24 | Fri 1/12/24 | 2570 | 2573 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6281 | 2573 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 1/16/24 | Tue 1/16/24 | 2572 | 2574 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6282 | 2574 | Future Task |  |  | D267 | Joy Schneider | Submit | DEL D267 - Monthly Performance Report (December 2023) - Submit | 0 hrs | 0 days | Tue 1/16/24 | Tue 1/16/24 | 2573 | 2575 |  | Joy Schneider
6283 | 2575 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Department QC | 1 hr | 7 days | Wed 1/17/24 | Thu 1/25/24 | 2574 | 2576 |  | Gabriela Gibson
6284 | 2576 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Contract Manager Review | 2 hrs | 2 days | Fri 1/26/24 | Mon 1/29/24 | 2575 | 2577 |  | Sean Buchanan
6285 | 2577 | Future Task |  |  | D267 | Joy Schneider | Accept | DEL D267 - Monthly Performance Report (December 2023) - Accept | 0 hrs | 0 days | Mon 1/29/24 | Mon 1/29/24 | 2576 | 2579 |  | Sean Buchanan
6286 | 2578 | Future Task |  |  | D277 | Joy Schneider |  | D277 - Monthly Performance Report (January 2024) | 10 hrs | 19 days | Thu 2/1/24 | Tue 2/27/24
6383 | 2579 | Future Task |  |  | D277 | Joy Schneider | Create | D277 - Create January 2024 Monthly Performance Report | 3 hrs | 9 days | Thu 2/1/24 | Tue 2/13/24 | 2577 | 2580 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6287 | 2580 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 2/14/24 | Wed 2/14/24 | 2579 | 2581 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6288 | 2581 | Future Task |  |  | D277 | Joy Schneider | Submit | DEL D277 - Monthly Performance Report (January 2024) - Submit | 0 hrs | 0 days | Wed 2/14/24 | Wed 2/14/24 | 2580 | 2582 |  | Joy Schneider
6289 | 2582 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Department QC | 1 hr | 7 days | Thu 2/15/24 | Fri 2/23/24 | 2581 | 2583 |  | Gabriela Gibson
6290 | 2583 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Contract Manager Review | 2 hrs | 2 days | Mon 2/26/24 | Tue 2/27/24 | 2582 | 2584 |  | Sean Buchanan
6291 | 2584 | Future Task |  |  | D277 | Joy Schneider | Accept | DEL D277 - Monthly Performance Report (January 2024) - Accept | 0 hrs | 0 days | Tue 2/27/24 | Tue 2/27/24 | 2583 | 2586 |  | Sean Buchanan
6292 | 2585 | Future Task |  |  | D284 | Joy Schneider |  | D284 - Monthly Performance Report (February 2024) | 10 hrs | 19 days | Fri 3/1/24 | Wed 3/27/24
6382 | 2586 | Future Task |  |  | D284 | Joy Schneider | Create | D284 - Create February 2024 Monthly Performance Report | 3 hrs | 9 days | Fri 3/1/24 | Wed 3/13/24 | 2584 | 2587 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6293 | 2587 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 3/14/24 | Thu 3/14/24 | 2586 | 2588 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6294 | 2588 | Future Task |  |  | D284 | Joy Schneider | Submit | DEL D284 - Monthly Performance Report (February 2024) - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 2587 | 2589 |  | Joy Schneider
6295 | 2589 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Department QC | 1 hr | 7 days | Fri 3/15/24 | Mon 3/25/24 | 2588 | 2590 |  | Gabriela Gibson
6296 | 2590 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Contract Manager Review | 2 hrs | 2 days | Tue 3/26/24 | Wed 3/27/24 | 2589 | 2591 |  | Sean Buchanan
6297 | 2591 | Future Task |  |  | D284 | Joy Schneider | Accept | DEL D284 - Monthly Performance Report (February 2024) - Accept | 0 hrs | 0 days | Wed 3/27/24 | Wed 3/27/24 | 2590 | 2593 |  | Sean Buchanan
6298 | 2592 | Future Task |  |  | D288 | Joy Schneider |  | D288 - Monthly Performance Report (March 2024) | 10 hrs | 19 days | Mon 4/1/24 | Thu 4/25/24
6381 | 2593 | Future Task |  |  | D288 | Joy Schneider | Create | D288 - Create March 2024 Monthly Performance Report | 3 hrs | 9 days | Mon 4/1/24 | Thu 4/11/24 | 2591 | 2594 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6299 | 2594 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 4/12/24 | Fri 4/12/24 | 2593 | 2595 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6300 | 2595 | Future Task |  |  | D288 | Joy Schneider | Submit | DEL D288 - Monthly Performance Report (March 2024) - Submit | 0 hrs | 0 days | Fri 4/12/24 | Fri 4/12/24 | 2594 | 2596 |  | Joy Schneider
6301 | 2596 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Department QC | 1 hr | 7 days | Mon 4/15/24 | Tue 4/23/24 | 2595 | 2597 |  | Gabriela Gibson
6302 | 2597 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Contract Manager Review | 2 hrs | 2 days | Wed 4/24/24 | Thu 4/25/24 | 2596 | 2598 |  | Sean Buchanan
6303 | 2598 | Future Task |  |  | D288 | Joy Schneider | Accept | DEL D288 - Monthly Performance Report (March 2024) - Accept | 0 hrs | 0 days | Thu 4/25/24 | Thu 4/25/24 | 2597 | 2600 |  | Sean Buchanan
6304 | 2599 | Future Task |  |  | D296 | Joy Schneider |  | D296 - Monthly Performance Report (April 2024) | 10 hrs | 19 days | Wed 5/1/24 | Tue 5/28/24
6380 | 2600 | Future Task |  |  | D296 | Joy Schneider | Create | D296 - Create April 2024 Monthly Performance Report | 3 hrs | 9 days | Wed 5/1/24 | Mon 5/13/24 | 2598 | 2601 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6305 | 2601 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 5/14/24 | Tue 5/14/24 | 2600 | 2602 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6306 | 2602 | Future Task |  |  | D296 | Joy Schneider | Submit | DEL D296 - Monthly Performance Report (April 2024) - Submit | 0 hrs | 0 days | Tue 5/14/24 | Tue 5/14/24 | 2601 | 2603 |  | Joy Schneider
6307 | 2603 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Department QC | 1 hr | 7 days | Wed 5/15/24 | Thu 5/23/24 | 2602 | 2604 |  | Gabriela Gibson
6308 | 2604 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Contract Manager Review | 2 hrs | 2 days | Fri 5/24/24 | Tue 5/28/24 | 2603 | 2605 |  | Sean Buchanan
6309 | 2605 | Future Task |  |  | D296 | Joy Schneider | Accept | DEL D296 - Monthly Performance Report (April 2024) - Accept | 0 hrs | 0 days | Tue 5/28/24 | Tue 5/28/24 | 2604 | 2607 |  | Sean Buchanan
6310 | 2606 | Future Task |  |  | D302 | Joy Schneider |  | D302 - Monthly Performance Report (May 2024) | 10 hrs | 19 days | Mon 6/3/24 | Thu 6/27/24
6379 | 2607 | Future Task |  |  | D302 | Joy Schneider | Create | D302 - Create May 2024 Monthly Performance Report | 3 hrs | 9 days | Mon 6/3/24 | Thu 6/13/24 | 2605 | 2608 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6311 | 2608 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 6/14/24 | Fri 6/14/24 | 2607 | 2609 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6312 | 2609 | Future Task |  |  | D302 | Joy Schneider | Submit | DEL D302 - Monthly Performance Report (May 2024) - Submit | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 2608 | 2610 |  | Joy Schneider
6313 | 2610 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Department QC | 1 hr | 7 days | Mon 6/17/24 | Tue 6/25/24 | 2609 | 2611 |  | Gabriela Gibson
6314 | 2611 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Contract Manager Review | 2 hrs | 2 days | Wed 6/26/24 | Thu 6/27/24 | 2610 | 2612 |  | Sean Buchanan
6315 | 2612 | Future Task |  |  | D302 | Joy Schneider | Accept | DEL D302 - Monthly Performance Report (May 2024) - Accept | 0 hrs | 0 days | Thu 6/27/24 | Thu 6/27/24 | 2611 | 2614 |  | Sean Buchanan
6316 | 2613 | Future Task |  |  | D311 | Joy Schneider |  | D311 - Monthly Performance Report (June 2024) | 10 hrs | 19 days | Mon 7/1/24 | Fri 7/26/24
6378 | 2614 | Future Task |  |  | D311 | Joy Schneider | Create | D311 - Create June 2024 Monthly Performance Report | 3 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 2612 | 2615 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6317 | 2615 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 7/15/24 | Mon 7/15/24 | 2614 | 2616 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6318 | 2616 | Future Task |  |  | D311 | Joy Schneider | Submit | DEL D311 - Monthly Performance Report (June 2024) - Submit | 0 hrs | 0 days | Mon 7/15/24 | Mon 7/15/24 | 2615 | 2617 |  | Joy Schneider
6319 | 2617 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Department QC | 1 hr | 7 days | Tue 7/16/24 | Wed 7/24/24 | 2616 | 2618 |  | Gabriela Gibson
6320 | 2618 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Contract Manager Review | 2 hrs | 2 days | Thu 7/25/24 | Fri 7/26/24 | 2617 | 2619 |  | Sean Buchanan
6321 | 2619 | Future Task |  |  | D311 | Joy Schneider | Accept | DEL D311 - Monthly Performance Report (June 2024) - Accept | 0 hrs | 0 days | Fri 7/26/24 | Fri 7/26/24 | 2618 | 2621 |  | Sean Buchanan
6322 | 2620 | Future Task |  |  | D319 | Joy Schneider |  | D319 - Monthly Performance Report (July 2024) | 10 hrs | 19 days | Thu 8/1/24 | Tue 8/27/24
6377 | 2621 | Future Task |  |  | D319 | Joy Schneider | Create | D319 - Create July 2024 Monthly Performance Report | 3 hrs | 9 days | Thu 8/1/24 | Tue 8/13/24 | 2619 | 2622 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6323 | 2622 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 8/14/24 | Wed 8/14/24 | 2621 | 2623 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6324 | 2623 | Future Task |  |  | D319 | Joy Schneider | Submit | DEL D319 - Monthly Performance Report (July 2024) - Submit | 0 hrs | 0 days | Wed 8/14/24 | Wed 8/14/24 | 2622 | 2624 |  | Joy Schneider
6325 | 2624 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Department QC | 1 hr | 7 days | Thu 8/15/24 | Fri 8/23/24 | 2623 | 2625 |  | Gabriela Gibson
6326 | 2625 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Contract Manager Review | 2 hrs | 2 days | Mon 8/26/24 | Tue 8/27/24 | 2624 | 2626 |  | Sean Buchanan
6327 | 2626 | Future Task |  |  | D319 | Joy Schneider | Accept | DEL D319 - Monthly Performance Report (July 2024) - Accept | 0 hrs | 0 days | Tue 8/27/24 | Tue 8/27/24 | 2625 | 2628 |  | Sean Buchanan
6328 | 2627 | Future Task |  |  | D328 | Joy Schneider |  | D328 - Monthly Performance Report (August 2024) | 10 hrs | 19 days | Tue 9/3/24 | Fri 9/27/24
6376 | 2628 | Future Task |  |  | D328 | Joy Schneider | Create | D328 - Create August 2024 Monthly Performance Report | 3 hrs | 9 days | Tue 9/3/24 | Fri 9/13/24 | 2626 | 2629 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6329 | 2629 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 9/16/24 | Mon 9/16/24 | 2628 | 2630 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6330 | 2630 | Future Task |  |  | D328 | Joy Schneider | Submit | DEL D328 - Monthly Performance Report (August 2024) - Submit | 0 hrs | 0 days | Mon 9/16/24 | Mon 9/16/24 | 2629 | 2631 |  | Joy Schneider
6331 | 2631 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Department QC | 1 hr | 7 days | Tue 9/17/24 | Wed 9/25/24 | 2630 | 2632 |  | Gabriela Gibson
6332 | 2632 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Contract Manager Review | 2 hrs | 2 days | Thu 9/26/24 | Fri 9/27/24 | 2631 | 2633 |  | Sean Buchanan
6333 | 2633 | Future Task |  |  | D328 | Joy Schneider | Accept | DEL D328 - Monthly Performance Report (August 2024) - Accept | 0 hrs | 0 days | Fri 9/27/24 | Fri 9/27/24 | 2632 | 2635 |  | Sean Buchanan
6334 | 2634 | Future Task |  |  | D334 | Joy Schneider |  | D334 - Monthly Performance Report (September 2024) | 10 hrs | 19 days | Tue 10/1/24 | Fri 10/25/24
6375 | 2635 | Future Task |  |  | D334 | Joy Schneider | Create | D334 - Create September 2024 Monthly Performance Report | 3 hrs | 9 days | Tue 10/1/24 | Fri 10/11/24 | 2633 | 2636 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6335 | 2636 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 10/14/24 | Mon 10/14/24 | 2635 | 2637 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6336 | 2637 | Future Task |  |  | D334 | Joy Schneider | Submit | DEL D334 - Monthly Performance Report (September 2024) - Submit | 0 hrs | 0 days | Mon 10/14/24 | Mon 10/14/24 | 2636 | 2638 |  | Joy Schneider
6337 | 2638 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Department QC | 1 hr | 7 days | Tue 10/15/24 | Wed 10/23/24 | 2637 | 2639 |  | Gabriela Gibson
6338 | 2639 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Contract Manager Review | 2 hrs | 2 days | Thu 10/24/24 | Fri 10/25/24 | 2638 | 2640 |  | Sean Buchanan
6339 | 2640 | Future Task |  |  | D334 | Joy Schneider | Accept | DEL D334 - Monthly Performance Report (September 2024) - Accept | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 2639 | 2642 |  | Sean Buchanan
6340 | 2641 | Future Task |  |  | D342 | Joy Schneider |  | D342 - Monthly Performance Report (October 2024) | 10 hrs | 19 days | Fri 11/1/24 | Mon 12/2/24
6374 | 2642 | Future Task |  |  | D342 | Joy Schneider | Create | D342 - Create October 2024 Monthly Performance Report | 3 hrs | 9 days | Fri 11/1/24 | Thu 11/14/24 | 2640 | 2643 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6341 | 2643 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 11/15/24 | Fri 11/15/24 | 2642 | 2644 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6342 | 2644 | Future Task |  |  | D342 | Joy Schneider | Submit | DEL D342 - Monthly Performance Report (October 2024) - Submit | 0 hrs | 0 days | Fri 11/15/24 | Fri 11/15/24 | 2643 | 2645 |  | Joy Schneider
6343 | 2645 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Department QC | 1 hr | 7 days | Mon 11/18/24 | Tue 11/26/24 | 2644 | 2646 |  | Gabriela Gibson
6344 | 2646 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Contract Manager Review | 2 hrs | 2 days | Wed 11/27/24 | Mon 12/2/24 | 2645 | 2647 |  | Sean Buchanan
6345 | 2647 | Future Task |  |  | D342 | Joy Schneider | Accept | DEL D342 - Monthly Performance Report (October 2024) - Accept | 0 hrs | 0 days | Mon 12/2/24 | Mon 12/2/24 | 2646 | 2649 |  | Sean Buchanan
6346 | 2648 | Future Task |  |  | D347 | Joy Schneider |  | D347 - Monthly Performance Report (November 2024) | 10 hrs | 19 days | Tue 12/3/24 | Mon 12/30/24
6373 | 2649 | Future Task |  |  | D347 | Joy Schneider | Create | D347 - Create November 2024 Monthly Performance Report | 3 hrs | 9 days | Tue 12/3/24 | Fri 12/13/24 | 2647 | 2650 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6347 | 2650 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 12/16/24 | Mon 12/16/24 | 2649 | 2651 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6348 | 2651 | Future Task |  |  | D347 | Joy Schneider | Submit | DEL D347 - Monthly Performance Report (November 2024) - Submit | 0 hrs | 0 days | Mon 12/16/24 | Mon 12/16/24 | 2650 | 2652 |  | Joy Schneider
6349 | 2652 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Department QC | 1 hr | 7 days | Tue 12/17/24 | Thu 12/26/24 | 2651 | 2653 |  | Gabriela Gibson
6350 | 2653 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Contract Manager Review | 2 hrs | 2 days | Fri 12/27/24 | Mon 12/30/24 | 2652 | 2654 |  | Sean Buchanan
6351 | 2654 | Future Task |  |  | D347 | Joy Schneider | Accept | DEL D347 - Monthly Performance Report (November 2024) - Accept | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 2653 | 2656 |  | Sean Buchanan
6352 | 2655 | Future Task |  |  | D353 | Joy Schneider |  | D353 - Monthly Performance Report (December 2024) | 10 hrs | 19 days | Thu 1/2/25 | Wed 1/29/25
6372 | 2656 | Future Task |  |  | D353 | Joy Schneider | Create | D353 - Create December 2024 Monthly Performance Report | 3 hrs | 9 days | Thu 1/2/25 | Tue 1/14/25 | 2654 | 2657 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6353 | 2657 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 1/15/25 | Wed 1/15/25 | 2656 | 2658 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6354 | 2658 | Future Task |  |  | D353 | Joy Schneider | Submit | DEL D353 - Monthly Performance Report (December 2024) - Submit | 0 hrs | 0 days | Wed 1/15/25 | Wed 1/15/25 | 2657 | 2659 |  | Joy Schneider
6355 | 2659 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Department QC | 1 hr | 7 days | Thu 1/16/25 | Mon 1/27/25 | 2658 | 2660 |  | Gabriela Gibson
6356 | 2660 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Contract Manager Review | 2 hrs | 2 days | Tue 1/28/25 | Wed 1/29/25 | 2659 | 2661 |  | Sean Buchanan
6357 | 2661 | Future Task |  |  | D353 | Joy Schneider | Accept | DEL D353 - Monthly Performance Report (December 2024) - Accept | 0 hrs | 0 days | Wed 1/29/25 | Wed 1/29/25 | 2660 | 2663 |  | Sean Buchanan
6358 | 2662 | Future Task |  |  | D359 | Joy Schneider |  | D359 - Monthly Performance Report (January 2025) | 10 hrs | 19 days | Mon 2/3/25 | Thu 2/27/25
6371 | 2663 | Future Task |  |  | D359 | Joy Schneider | Create | D359 - Create January 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 2/3/25 | Thu 2/13/25 | 2661 | 2664 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6359 | 2664 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 2/14/25 | Fri 2/14/25 | 2663 | 2665 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6360 | 2665 | Future Task |  |  | D359 | Joy Schneider | Submit | DEL D359 - Monthly Performance Report (January 2025) - Submit | 0 hrs | 0 days | Fri 2/14/25 | Fri 2/14/25 | 2664 | 2666 |  | Joy Schneider
6361 | 2666 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Department QC | 1 hr | 7 days | Mon 2/17/25 | Tue 2/25/25 | 2665 | 2667 |  | Gabriela Gibson
6362 | 2667 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 2/26/25 | Thu 2/27/25 | 2666 | 2668 |  | Sean Buchanan
6363 | 2668 | Future Task |  |  | D359 | Joy Schneider | Accept | DEL D359 - Monthly Performance Report (January 2025) - Accept | 0 hrs | 0 days | Thu 2/27/25 | Thu 2/27/25 | 2667 | 2670 |  | Sean Buchanan
6386 | 2669 | Future Task |  |  | D362 | Joy Schneider |  | D362 - Monthly Performance Report (February 2025) | 10 hrs | 19 days | Mon 3/3/25 | Thu 3/27/25
6490 | 2670 | Future Task |  |  | D362 | Joy Schneider | Create | D362 - Create February 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 3/3/25 | Thu 3/13/25 | 2668 | 2671 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6387 | 2671 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 3/14/25 | Fri 3/14/25 | 2670 | 2672 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6388 | 2672 | Future Task |  |  | D362 | Joy Schneider | Submit | DEL D362 - Monthly Performance Report (February 2025) - Submit | 0 hrs | 0 days | Fri 3/14/25 | Fri 3/14/25 | 2671 | 2673 |  | Joy Schneider
6389 | 2673 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Department QC | 1 hr | 7 days | Mon 3/17/25 | Tue 3/25/25 | 2672 | 2674 |  | Gabriela Gibson
6390 | 2674 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 3/26/25 | Thu 3/27/25 | 2673 | 2675 |  | Sean Buchanan
6391 | 2675 | Future Task |  |  | D362 | Joy Schneider | Accept | DEL D362 - Monthly Performance Report (February 2025) - Accept | 0 hrs | 0 days | Thu 3/27/25 | Thu 3/27/25 | 2674 | 2677 |  | Sean Buchanan
6392 | 2676 | Future Task |  |  | D364 | Joy Schneider |  | D364 - Monthly Performance Report (March 2025) | 10 hrs | 19 days | Tue 4/1/25 | Fri 4/25/25
6489 | 2677 | Future Task |  |  | D364 | Joy Schneider | Create | D364 - Create March 2025 Monthly Performance Report | 3 hrs | 9 days | Tue 4/1/25 | Fri 4/11/25 | 2675 | 2678 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6393 | 2678 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 4/14/25 | Mon 4/14/25 | 2677 | 2679 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6394 | 2679 | Future Task |  |  | D364 | Joy Schneider | Submit | DEL D364 - Monthly Performance Report (March 2025) - Submit | 0 hrs | 0 days | Mon 4/14/25 | Mon 4/14/25 | 2678 | 2680 |  | Joy Schneider
6395 | 2680 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Department QC | 1 hr | 7 days | Tue 4/15/25 | Wed 4/23/25 | 2679 | 2681 |  | Gabriela Gibson
6396 | 2681 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Contract Manager Review | 2 hrs | 2 days | Thu 4/24/25 | Fri 4/25/25 | 2680 | 2682 |  | Sean Buchanan
6397 | 2682 | Future Task |  |  | D364 | Joy Schneider | Accept | DEL D364 - Monthly Performance Report (March 2025) - Accept | 0 hrs | 0 days | Fri 4/25/25 | Fri 4/25/25 | 2681 | 2684 |  | Sean Buchanan
6398 | 2683 | Future Task |  |  | D366 | Joy Schneider |  | D366 - Monthly Performance Report (April 2025) | 10 hrs | 19 days | Thu 5/1/25 | Wed 5/28/25
6488 | 2684 | Future Task |  |  | D366 | Joy Schneider | Create | D366 - Create April 2025 Monthly Performance Report | 3 hrs | 9 days | Thu 5/1/25 | Tue 5/13/25 | 2682 | 2685 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6399 | 2685 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 5/14/25 | Wed 5/14/25 | 2684 | 2686 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6400 | 2686 | Future Task |  |  | D366 | Joy Schneider | Submit | DEL D366 - Monthly Performance Report (April 2025) - Submit | 0 hrs | 0 days | Wed 5/14/25 | Wed 5/14/25 | 2685 | 2687 |  | Joy Schneider
6401 | 2687 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Department QC | 1 hr | 7 days | Thu 5/15/25 | Fri 5/23/25 | 2686 | 2688 |  | Gabriela Gibson
6402 | 2688 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Contract Manager Review | 2 hrs | 2 days | Tue 5/27/25 | Wed 5/28/25 | 2687 | 2689 |  | Sean Buchanan
6403 | 2689 | Future Task |  |  | D366 | Joy Schneider | Accept | DEL D366 - Monthly Performance Report (April 2025) - Accept | 0 hrs | 0 days | Wed 5/28/25 | Wed 5/28/25 | 2688 | 2691 |  | Sean Buchanan
6404 | 2690 | Future Task |  |  | D367 | Joy Schneider |  | D367 - Monthly Performance Report (May 2025) | 10 hrs | 19 days | Mon 6/2/25 | Thu 6/26/25
6487 | 2691 | Future Task |  |  | D367 | Joy Schneider | Create | D367 - Create May 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 6/2/25 | Thu 6/12/25 | 2689 | 2692 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6405 | 2692 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 6/13/25 | Fri 6/13/25 | 2691 | 2693 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6406 | 2693 | Future Task |  |  | D367 | Joy Schneider | Submit | DEL D367 - Monthly Performance Report (May 2025) - Submit | 0 hrs | 0 days | Fri 6/13/25 | Fri 6/13/25 | 2692 | 2694 |  | Joy Schneider
6407 | 2694 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Department QC | 1 hr | 7 days | Mon 6/16/25 | Tue 6/24/25 | 2693 | 2695 |  | Gabriela Gibson
6408 | 2695 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 6/25/25 | Thu 6/26/25 | 2694 | 2696 |  | Sean Buchanan
6409 | 2696 | Future Task |  |  | D367 | Joy Schneider | Accept | DEL D367 - Monthly Performance Report (May 2025) - Accept | 0 hrs | 0 days | Thu 6/26/25 | Thu 6/26/25 | 2695 | 2698 |  | Sean Buchanan
6410 | 2697 | Future Task |  |  | D368 | Joy Schneider |  | D368 - Monthly Performance Report (June 2025) | 10 hrs | 19 days | Tue 7/1/25 | Mon 7/28/25
6486 | 2698 | Future Task |  |  | D368 | Joy Schneider | Create | D368 - Create June 2025 Monthly Performance Report | 3 hrs | 9 days | Tue 7/1/25 | Mon 7/14/25 | 2696 | 2699 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6411 | 2699 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 7/15/25 | Tue 7/15/25 | 2698 | 2700 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6412 | 2700 | Future Task |  |  | D368 | Joy Schneider | Submit | DEL D368 - Monthly Performance Report (June 2025) - Submit | 0 hrs | 0 days | Tue 7/15/25 | Tue 7/15/25 | 2699 | 2701 |  | Joy Schneider
6413 | 2701 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Department QC | 1 hr | 7 days | Wed 7/16/25 | Thu 7/24/25 | 2700 | 2702 |  | Gabriela Gibson
6414 | 2702 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Contract Manager Review | 2 hrs | 2 days | Fri 7/25/25 | Mon 7/28/25 | 2701 | 2703 |  | Sean Buchanan
6415 | 2703 | Future Task |  |  | D368 | Joy Schneider | Accept | DEL D368 - Monthly Performance Report (June 2025) - Accept | 0 hrs | 0 days | Mon 7/28/25 | Mon 7/28/25 | 2702 | 2705 |  | Sean Buchanan
6416 | 2704 | Future Task |  |  | D369 | Joy Schneider |  | D369 - Monthly Performance Report (July 2025) | 10 hrs | 19 days | Fri 8/1/25 | Wed 8/27/25
6485 | 2705 | Future Task |  |  | D369 | Joy Schneider | Create | D369 - Create July 2025 Monthly Performance Report | 3 hrs | 9 days | Fri 8/1/25 | Wed 8/13/25 | 2703 | 2706 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6417 | 2706 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 8/14/25 | Thu 8/14/25 | 2705 | 2707 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6418 | 2707 | Future Task |  |  | D369 | Joy Schneider | Submit | DEL D369 - Monthly Performance Report (July 2025) - Submit | 0 hrs | 0 days | Thu 8/14/25 | Thu 8/14/25 | 2706 | 2708 |  | Joy Schneider
6419 | 2708 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Department QC | 1 hr | 7 days | Fri 8/15/25 | Mon 8/25/25 | 2707 | 2709 |  | Gabriela Gibson
6420 | 2709 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Contract Manager Review | 2 hrs | 2 days | Tue 8/26/25 | Wed 8/27/25 | 2708 | 2710 |  | Sean Buchanan
6421 | 2710 | Future Task |  |  | D369 | Joy Schneider | Accept | DEL D369 - Monthly Performance Report (July 2025) - Accept | 0 hrs | 0 days | Wed 8/27/25 | Wed 8/27/25 | 2709 | 2712 |  | Sean Buchanan
6422 | 2711 | Future Task |  |  | D370 | Joy Schneider |  | D370 - Monthly Performance Report (August 2025) | 10 hrs | 19 days | Tue 9/2/25 | Fri 9/26/25
6484 | 2712 | Future Task |  |  | D370 | Joy Schneider | Create | D370 - Create August 2025 Monthly Performance Report | 3 hrs | 9 days | Tue 9/2/25 | Fri 9/12/25 | 2710 | 2713 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6423 | 2713 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 9/15/25 | Mon 9/15/25 | 2712 | 2714 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6424 | 2714 | Future Task |  |  | D370 | Joy Schneider | Submit | DEL D370 - Monthly Performance Report (August 2025) - Submit | 0 hrs | 0 days | Mon 9/15/25 | Mon 9/15/25 | 2713 | 2715 |  | Joy Schneider
6425 | 2715 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Department QC | 1 hr | 7 days | Tue 9/16/25 | Wed 9/24/25 | 2714 | 2716 |  | Gabriela Gibson
6426 | 2716 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Contract Manager Review | 2 hrs | 2 days | Thu 9/25/25 | Fri 9/26/25 | 2715 | 2717 |  | Sean Buchanan
6427 | 2717 | Future Task |  |  | D370 | Joy Schneider | Accept | DEL D370 - Monthly Performance Report (August 2025) - Accept | 0 hrs | 0 days | Fri 9/26/25 | Fri 9/26/25 | 2716 | 2719 |  | Sean Buchanan
6428 | 2718 | Future Task |  |  | D371 | Joy Schneider |  | D371 - Monthly Performance Report (September 2025) | 10 hrs | 19 days | Wed 10/1/25 | Mon 10/27/25
6483 | 2719 | Future Task |  |  | D371 | Joy Schneider | Create | D371 - Create September 2025 Monthly Performance Report | 3 hrs | 9 days | Wed 10/1/25 | Mon 10/13/25 | 2717 | 2720 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6429 | 2720 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 10/14/25 | Tue 10/14/25 | 2719 | 2721 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6430 | 2721 | Future Task |  |  | D371 | Joy Schneider | Submit | DEL D371 - Monthly Performance Report (September 2025) - Submit | 0 hrs | 0 days | Tue 10/14/25 | Tue 10/14/25 | 2720 | 2722 |  | Joy Schneider
6431 | 2722 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Department QC | 1 hr | 7 days | Wed 10/15/25 | Thu 10/23/25 | 2721 | 2723 |  | Gabriela Gibson
6432 | 2723 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Contract Manager Review | 2 hrs | 2 days | Fri 10/24/25 | Mon 10/27/25 | 2722 | 2724 |  | Sean Buchanan
6433 | 2724 | Future Task |  |  | D371 | Joy Schneider | Accept | DEL D371 - Monthly Performance Report (September 2025) - Accept | 0 hrs | 0 days | Mon 10/27/25 | Mon 10/27/25 | 2723 | 2726 |  | Sean Buchanan
6434 | 2725 | Future Task |  |  | D373 | Joy Schneider |  | D373 - Monthly Performance Report (October 2025) | 10 hrs | 19 days | Mon 11/3/25 | Tue 12/2/25
6482 | 2726 | Future Task |  |  | D373 | Joy Schneider | Create | D373 - Create October 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 11/3/25 | Fri 11/14/25 | 2724 | 2727 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6435 | 2727 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 11/17/25 | Mon 11/17/25 | 2726 | 2728 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6436 | 2728 | Future Task |  |  | D373 | Joy Schneider | Submit | DEL D373 - Monthly Performance Report (October 2025) - Submit | 0 hrs | 0 days | Mon 11/17/25 | Mon 11/17/25 | 2727 | 2729 |  | Joy Schneider
6437 | 2729 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Department QC | 1 hr | 7 days | Tue 11/18/25 | Wed 11/26/25 | 2728 | 2730 |  | Gabriela Gibson
6438 | 2730 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Contract Manager Review | 2 hrs | 2 days | Mon 12/1/25 | Tue 12/2/25 | 2729 | 2731 |  | Sean Buchanan
6439 | 2731 | Future Task |  |  | D373 | Joy Schneider | Accept | DEL D373 - Monthly Performance Report (October 2025) - Accept | 0 hrs | 0 days | Tue 12/2/25 | Tue 12/2/25 | 2730 | 2733FS-2 days |  | Sean Buchanan
6440 | 2732 | Future Task |  |  | D374 | Joy Schneider |  | D374 - Monthly Performance Report (November 2025) | 10 hrs | 19 days | Mon 12/1/25 | Fri 12/26/25
6481 | 2733 | Future Task |  |  | D374 | Joy Schneider | Create | D374 - Create November 2025 Monthly Performance Report | 3 hrs | 9 days | Mon 12/1/25 | Thu 12/11/25 | 2731FS-2 days | 2734 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6441 | 2734 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 12/12/25 | Fri 12/12/25 | 2733 | 2735 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6442 | 2735 | Future Task |  |  | D374 | Joy Schneider | Submit | DEL D374 - Monthly Performance Report (November 2025) - Submit | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 2734 | 2736 |  | Joy Schneider
6443 | 2736 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Department QC | 1 hr | 7 days | Mon 12/15/25 | Tue 12/23/25 | 2735 | 2737 |  | Gabriela Gibson
6444 | 2737 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 12/24/25 | Fri 12/26/25 | 2736 | 2738 |  | Sean Buchanan
6445 | 2738 | Future Task |  |  | D374 | Joy Schneider | Accept | DEL D374 - Monthly Performance Report (November 2025) - Accept | 0 hrs | 0 days | Fri 12/26/25 | Fri 12/26/25 | 2737 | 2740 |  | Sean Buchanan
6446 | 2739 | Future Task |  |  | D375 | Joy Schneider |  | D375 - Monthly Performance Report (December 2025) | 10 hrs | 19 days | Fri 1/2/26 | Thu 1/29/26
6480 | 2740 | Future Task |  |  | D375 | Joy Schneider | Create | D375 - Create December 2025 Monthly Performance Report | 3 hrs | 9 days | Fri 1/2/26 | Wed 1/14/26 | 2738 | 2741 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6447 | 2741 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 1/15/26 | Thu 1/15/26 | 2740 | 2742 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6448 | 2742 | Future Task |  |  | D375 | Joy Schneider | Submit | DEL D375 - Monthly Performance Report (December 2025) - Submit | 0 hrs | 0 days | Thu 1/15/26 | Thu 1/15/26 | 2741 | 2743 |  | Joy Schneider
6449 | 2743 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Department QC | 1 hr | 7 days | Fri 1/16/26 | Tue 1/27/26 | 2742 | 2744 |  | Gabriela Gibson
6450 | 2744 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 1/28/26 | Thu 1/29/26 | 2743 | 2745 |  | Sean Buchanan
6451 | 2745 | Future Task |  |  | D375 | Joy Schneider | Accept | DEL D375 - Monthly Performance Report (December 2025) - Accept | 0 hrs | 0 days | Thu 1/29/26 | Thu 1/29/26 | 2744 | 2747 |  | Sean Buchanan
6452 | 2746 | Future Task |  |  | D432 | Joy Schneider |  | D432 - Monthly Performance Report (January 2026) | 10 hrs | 19 days | Mon 2/2/26 | Thu 2/26/26
6479 | 2747 | Future Task |  |  | D432 | Joy Schneider | Create | D432 - Create January 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 2/2/26 | Thu 2/12/26 | 2745 | 2748 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6453 | 2748 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 2/13/26 | Fri 2/13/26 | 2747 | 2749 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6454 | 2749 | Future Task |  |  | D432 | Joy Schneider | Submit | DEL D432 - Monthly Performance Report (January 2026) - Submit | 0 hrs | 0 days | Fri 2/13/26 | Fri 2/13/26 | 2748 | 2750 |  | Joy Schneider
6455 | 2750 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Department QC | 1 hr | 7 days | Mon 2/16/26 | Tue 2/24/26 | 2749 | 2751 |  | Gabriela Gibson
6456 | 2751 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 2/25/26 | Thu 2/26/26 | 2750 | 2752 |  | Sean Buchanan
6457 | 2752 | Future Task |  |  | D432 | Joy Schneider | Accept | DEL D432 - Monthly Performance Report (January 2026) - Accept | 0 hrs | 0 days | Thu 2/26/26 | Thu 2/26/26 | 2751 | 2754 |  | Sean Buchanan
6458 | 2753 | Future Task |  |  | D434 | Joy Schneider |  | D434 - Monthly Performance Report (February 2026) | 10 hrs | 19 days | Mon 3/2/26 | Thu 3/26/26
6478 | 2754 | Future Task |  |  | D434 | Joy Schneider | Create | D434 - Create February 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 3/2/26 | Thu 3/12/26 | 2752 | 2755 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6459 | 2755 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 3/13/26 | Fri 3/13/26 | 2754 | 2756 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6460 | 2756 | Future Task |  |  | D434 | Joy Schneider | Submit | DEL D434 - Monthly Performance Report (February 2026) - Submit | 0 hrs | 0 days | Fri 3/13/26 | Fri 3/13/26 | 2755 | 2757 |  | Joy Schneider
6461 | 2757 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Department QC | 1 hr | 7 days | Mon 3/16/26 | Tue 3/24/26 | 2756 | 2758 |  | Gabriela Gibson
6462 | 2758 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 3/25/26 | Thu 3/26/26 | 2757 | 2759 |  | Sean Buchanan
6463 | 2759 | Future Task |  |  | D434 | Joy Schneider | Accept | DEL D434 - Monthly Performance Report (February 2026) - Accept | 0 hrs | 0 days | Thu 3/26/26 | Thu 3/26/26 | 2758 | 2761 |  | Sean Buchanan
6464 | 2760 | Future Task |  |  | D435 | Joy Schneider |  | D435 - Monthly Performance Report (March 2026) | 10 hrs | 19 days | Wed 4/1/26 | Mon 4/27/26
6477 | 2761 | Future Task |  |  | D435 | Joy Schneider | Create | D435 - Create March 2026 Monthly Performance Report | 3 hrs | 9 days | Wed 4/1/26 | Mon 4/13/26 | 2759 | 2762 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6465 | 2762 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 4/14/26 | Tue 4/14/26 | 2761 | 2763 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6466 | 2763 | Future Task |  |  | D435 | Joy Schneider | Submit | DEL D435 - Monthly Performance Report (March 2026) - Submit | 0 hrs | 0 days | Tue 4/14/26 | Tue 4/14/26 | 2762 | 2764 |  | Joy Schneider
6467 | 2764 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Department QC | 1 hr | 7 days | Wed 4/15/26 | Thu 4/23/26 | 2763 | 2765 |  | Gabriela Gibson
6468 | 2765 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Contract Manager Review | 2 hrs | 2 days | Fri 4/24/26 | Mon 4/27/26 | 2764 | 2766 |  | Sean Buchanan
6469 | 2766 | Future Task |  |  | D435 | Joy Schneider | Accept | DEL D435 - Monthly Performance Report (March 2026) - Accept | 0 hrs | 0 days | Mon 4/27/26 | Mon 4/27/26 | 2765 | 2768 |  | Sean Buchanan
6470 | 2767 | Future Task |  |  | D437 | Joy Schneider |  | D437 - Monthly Performance Report (April 2026) | 10 hrs | 19 days | Fri 5/1/26 | Thu 5/28/26
6476 | 2768 | Future Task |  |  | D437 | Joy Schneider | Create | D437 - Create April 2026 Monthly Performance Report | 3 hrs | 9 days | Fri 5/1/26 | Wed 5/13/26 | 2766 | 2769 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6471 | 2769 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 5/14/26 | Thu 5/14/26 | 2768 | 2770 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6472 | 2770 | Future Task |  |  | D437 | Joy Schneider | Submit | DEL D437 - Monthly Performance Report (April 2026) - Submit | 0 hrs | 0 days | Thu 5/14/26 | Thu 5/14/26 | 2769 | 2771 |  | Joy Schneider
6473 | 2771 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Department QC | 1 hr | 7 days | Fri 5/15/26 | Tue 5/26/26 | 2770 | 2772 |  | Gabriela Gibson
6474 | 2772 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 5/27/26 | Thu 5/28/26 | 2771 | 2773 |  | Sean Buchanan
6475 | 2773 | Future Task |  |  | D437 | Joy Schneider | Accept | DEL D437 - Monthly Performance Report (April 2026) - Accept | 0 hrs | 0 days | Thu 5/28/26 | Thu 5/28/26 | 2772 | 2775 |  | Sean Buchanan
6491 | 2774 | Future Task |  |  | D438 | Joy Schneider |  | D438 - Monthly Performance Report (May 2026) | 10 hrs | 19 days | Mon 6/1/26 | Thu 6/25/26
6595 | 2775 | Future Task |  |  | D438 | Joy Schneider | Create | D438 - Create May 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 6/1/26 | Thu 6/11/26 | 2773 | 2776 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6492 | 2776 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 6/12/26 | Fri 6/12/26 | 2775 | 2777 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6493 | 2777 | Future Task |  |  | D438 | Joy Schneider | Submit | DEL D438 - Monthly Performance Report (May 2026) - Submit | 0 hrs | 0 days | Fri 6/12/26 | Fri 6/12/26 | 2776 | 2778 |  | Joy Schneider
6494 | 2778 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Department QC | 1 hr | 7 days | Mon 6/15/26 | Tue 6/23/26 | 2777 | 2779 |  | Gabriela Gibson
6495 | 2779 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 6/24/26 | Thu 6/25/26 | 2778 | 2780 |  | Sean Buchanan
6496 | 2780 | Future Task |  |  | D438 | Joy Schneider | Accept | DEL D438 - Monthly Performance Report (May 2026) - Accept | 0 hrs | 0 days | Thu 6/25/26 | Thu 6/25/26 | 2779 | 2782 |  | Sean Buchanan
6497 | 2781 | Future Task |  |  | D439 | Joy Schneider |  | D439 - Monthly Performance Report (June 2026) | 10 hrs | 19 days | Wed 7/1/26 | Tue 7/28/26
6594 | 2782 | Future Task |  |  | D439 | Joy Schneider | Create | D439 - Create June 2026 Monthly Performance Report | 3 hrs | 9 days | Wed 7/1/26 | Tue 7/14/26 | 2780 | 2783 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6498 | 2783 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 7/15/26 | Wed 7/15/26 | 2782 | 2784 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6499 | 2784 | Future Task |  |  | D439 | Joy Schneider | Submit | DEL D439 - Monthly Performance Report (June 2026) - Submit | 0 hrs | 0 days | Wed 7/15/26 | Wed 7/15/26 | 2783 | 2785 |  | Joy Schneider
6500 | 2785 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Department QC | 1 hr | 7 days | Thu 7/16/26 | Fri 7/24/26 | 2784 | 2786 |  | Gabriela Gibson
6501 | 2786 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 7/27/26 | Tue 7/28/26 | 2785 | 2787 |  | Sean Buchanan
6502 | 2787 | Future Task |  |  | D439 | Joy Schneider | Accept | DEL D439 - Monthly Performance Report (June 2026) - Accept | 0 hrs | 0 days | Tue 7/28/26 | Tue 7/28/26 | 2786 | 2789 |  | Sean Buchanan
6503 | 2788 | Future Task |  |  | D441 | Joy Schneider |  | D441 - Monthly Performance Report (July 2026) | 10 hrs | 19 days | Mon 8/3/26 | Thu 8/27/26
6593 | 2789 | Future Task |  |  | D441 | Joy Schneider | Create | D441 - Create July 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 8/3/26 | Thu 8/13/26 | 2787 | 2790 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6504 | 2790 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 8/14/26 | Fri 8/14/26 | 2789 | 2791 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6505 | 2791 | Future Task |  |  | D441 | Joy Schneider | Submit | DEL D441 - Monthly Performance Report (July 2026) - Submit | 0 hrs | 0 days | Fri 8/14/26 | Fri 8/14/26 | 2790 | 2792 |  | Joy Schneider
6506 | 2792 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Department QC | 1 hr | 7 days | Mon 8/17/26 | Tue 8/25/26 | 2791 | 2793 |  | Gabriela Gibson
6507 | 2793 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 8/26/26 | Thu 8/27/26 | 2792 | 2794 |  | Sean Buchanan
6508 | 2794 | Future Task |  |  | D441 | Joy Schneider | Accept | DEL D441 - Monthly Performance Report (July 2026) - Accept | 0 hrs | 0 days | Thu 8/27/26 | Thu 8/27/26 | 2793 | 2796 |  | Sean Buchanan
6509 | 2795 | Future Task |  |  | D442 | Joy Schneider |  | D442 - Monthly Performance Report (August 2026) | 10 hrs | 19 days | Tue 9/1/26 | Mon 9/28/26
6592 | 2796 | Future Task |  |  | D442 | Joy Schneider | Create | D442 - Create August 2026 Monthly Performance Report | 3 hrs | 9 days | Tue 9/1/26 | Mon 9/14/26 | 2794 | 2797 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6510 | 2797 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 9/15/26 | Tue 9/15/26 | 2796 | 2798 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6511 | 2798 | Future Task |  |  | D442 | Joy Schneider | Submit | DEL D442 - Monthly Performance Report (August 2026) - Submit | 0 hrs | 0 days | Tue 9/15/26 | Tue 9/15/26 | 2797 | 2799 |  | Joy Schneider
6512 | 2799 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Department QC | 1 hr | 7 days | Wed 9/16/26 | Thu 9/24/26 | 2798 | 2800 |  | Gabriela Gibson
6513 | 2800 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Contract Manager Review | 2 hrs | 2 days | Fri 9/25/26 | Mon 9/28/26 | 2799 | 2801 |  | Sean Buchanan
6514 | 2801 | Future Task |  |  | D442 | Joy Schneider | Accept | DEL D442 - Monthly Performance Report (August 2026) - Accept | 0 hrs | 0 days | Mon 9/28/26 | Mon 9/28/26 | 2800 | 2803 |  | Sean Buchanan
6515 | 2802 | Future Task |  |  | D443 | Joy Schneider |  | D443 - Monthly Performance Report (September 2026) | 10 hrs | 19 days | Thu 10/1/26 | Tue 10/27/26
6591 | 2803 | Future Task |  |  | D443 | Joy Schneider | Create | D443 - Create September 2026 Monthly Performance Report | 3 hrs | 9 days | Thu 10/1/26 | Tue 10/13/26 | 2801 | 2804 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6516 | 2804 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 10/14/26 | Wed 10/14/26 | 2803 | 2805 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6517 | 2805 | Future Task |  |  | D443 | Joy Schneider | Submit | DEL D443 - Monthly Performance Report (September 2026) - Submit | 0 hrs | 0 days | Wed 10/14/26 | Wed 10/14/26 | 2804 | 2806 |  | Joy Schneider
6518 | 2806 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Department QC | 1 hr | 7 days | Thu 10/15/26 | Fri 10/23/26 | 2805 | 2807 |  | Gabriela Gibson
6519 | 2807 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 10/26/26 | Tue 10/27/26 | 2806 | 2808 |  | Sean Buchanan
6520 | 2808 | Future Task |  |  | D443 | Joy Schneider | Accept | DEL D443 - Monthly Performance Report (September 2026) - Accept | 0 hrs | 0 days | Tue 10/27/26 | Tue 10/27/26 | 2807 | 2810 |  | Sean Buchanan
6521 | 2809 | Future Task |  |  | D444 | Joy Schneider |  | D444 - Monthly Performance Report (October 2026) | 10 hrs | 19 days | Mon 11/2/26 | Tue 12/1/26
6590 | 2810 | Future Task |  |  | D444 | Joy Schneider | Create | D444 - Create October 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 11/2/26 | Fri 11/13/26 | 2808 | 2811 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6522 | 2811 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 11/16/26 | Mon 11/16/26 | 2810 | 2812 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6523 | 2812 | Future Task |  |  | D444 | Joy Schneider | Submit | DEL D444 - Monthly Performance Report (October 2026) - Submit | 0 hrs | 0 days | Mon 11/16/26 | Mon 11/16/26 | 2811 | 2813 |  | Joy Schneider
6524 | 2813 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Department QC | 1 hr | 7 days | Tue 11/17/26 | Wed 11/25/26 | 2812 | 2814 |  | Gabriela Gibson
6525 | 2814 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 11/30/26 | Tue 12/1/26 | 2813 | 2815 |  | Sean Buchanan
6526 | 2815 | Future Task |  |  | D444 | Joy Schneider | Accept | DEL D444 - Monthly Performance Report (October 2026) - Accept | 0 hrs | 0 days | Tue 12/1/26 | Tue 12/1/26 | 2814 | 2817FS-1 day |  | Sean Buchanan
6527 | 2816 | Future Task |  |  | D445 | Joy Schneider |  | D445 - Monthly Performance Report (November 2026) | 10 hrs | 19 days | Tue 12/1/26 | Mon 12/28/26
6589 | 2817 | Future Task |  |  | D445 | Joy Schneider | Create | D445 - Create November 2026 Monthly Performance Report | 3 hrs | 9 days | Tue 12/1/26 | Fri 12/11/26 | 2815FS-1 day | 2818 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6528 | 2818 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 12/14/26 | Mon 12/14/26 | 2817 | 2819 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6529 | 2819 | Future Task |  |  | D445 | Joy Schneider | Submit | DEL D445 - Monthly Performance Report (November 2026) - Submit | 0 hrs | 0 days | Mon 12/14/26 | Mon 12/14/26 | 2818 | 2820 |  | Joy Schneider
6530 | 2820 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Department QC | 1 hr | 7 days | Tue 12/15/26 | Wed 12/23/26 | 2819 | 2821 |  | Gabriela Gibson
6531 | 2821 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Contract Manager Review | 2 hrs | 2 days | Thu 12/24/26 | Mon 12/28/26 | 2820 | 2822 |  | Sean Buchanan
6532 | 2822 | Future Task |  |  | D445 | Joy Schneider | Accept | DEL D445 - Monthly Performance Report (November 2026) - Accept | 0 hrs | 0 days | Mon 12/28/26 | Mon 12/28/26 | 2821 | 2824 |  | Sean Buchanan
6533 | 2823 | Future Task |  |  | D446 | Joy Schneider |  | D446 - Monthly Performance Report (December 2026) | 10 hrs | 19 days | Mon 1/4/27 | Fri 1/29/27
6588 | 2824 | Future Task |  |  | D446 | Joy Schneider | Create | D446 - Create December 2026 Monthly Performance Report | 3 hrs | 9 days | Mon 1/4/27 | Thu 1/14/27 | 2822 | 2825 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6534 | 2825 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 1/15/27 | Fri 1/15/27 | 2824 | 2826 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6535 | 2826 | Future Task |  |  | D446 | Joy Schneider | Submit | DEL D446 - Monthly Performance Report (December 2026) - Submit | 0 hrs | 0 days | Fri 1/15/27 | Fri 1/15/27 | 2825 | 2827 |  | Joy Schneider
6536 | 2827 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Department QC | 1 hr | 7 days | Tue 1/19/27 | Wed 1/27/27 | 2826 | 2828 |  | Gabriela Gibson
6537 | 2828 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Contract Manager Review | 2 hrs | 2 days | Thu 1/28/27 | Fri 1/29/27 | 2827 | 2829 |  | Sean Buchanan
6538 | 2829 | Future Task |  |  | D446 | Joy Schneider | Accept | DEL D446 - Monthly Performance Report (December 2026) - Accept | 0 hrs | 0 days | Fri 1/29/27 | Fri 1/29/27 | 2828 | 2831 |  | Sean Buchanan
6539 | 2830 | Future Task |  |  | D447 | Joy Schneider |  | D447 - Monthly Performance Report (January 2027) | 10 hrs | 19 days | Mon 2/1/27 | Thu 2/25/27
6587 | 2831 | Future Task |  |  | D447 | Joy Schneider | Create | D447 - Create January 2027 Monthly Performance Report | 3 hrs | 9 days | Mon 2/1/27 | Thu 2/11/27 | 2829 | 2832 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6540 | 2832 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 2/12/27 | Fri 2/12/27 | 2831 | 2833 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6541 | 2833 | Future Task |  |  | D447 | Joy Schneider | Submit | DEL D447 - Monthly Performance Report (January 2027) - Submit | 0 hrs | 0 days | Fri 2/12/27 | Fri 2/12/27 | 2832 | 2834 |  | Joy Schneider
6542 | 2834 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Department QC | 1 hr | 7 days | Mon 2/15/27 | Tue 2/23/27 | 2833 | 2835 |  | Gabriela Gibson
6543 | 2835 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 2/24/27 | Thu 2/25/27 | 2834 | 2836 |  | Sean Buchanan
6544 | 2836 | Future Task |  |  | D447 | Joy Schneider | Accept | DEL D447 - Monthly Performance Report (January 2027) - Accept | 0 hrs | 0 days | Thu 2/25/27 | Thu 2/25/27 | 2835 | 2838 |  | Sean Buchanan
6545 | 2837 | Future Task |  |  | D448 | Joy Schneider |  | D448 - Monthly Performance Report (February 2027) | 10 hrs | 19 days | Mon 3/1/27 | Thu 3/25/27
6586 | 2838 | Future Task |  |  | D448 | Joy Schneider | Create | D448 - Create February 2027 Monthly Performance Report | 3 hrs | 9 days | Mon 3/1/27 | Thu 3/11/27 | 2836 | 2839 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6546 | 2839 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 3/12/27 | Fri 3/12/27 | 2838 | 2840 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6547 | 2840 | Future Task |  |  | D448 | Joy Schneider | Submit | DEL D448 - Monthly Performance Report (February 2027) - Submit | 0 hrs | 0 days | Fri 3/12/27 | Fri 3/12/27 | 2839 | 2841 |  | Joy Schneider
6548 | 2841 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Department QC | 1 hr | 7 days | Mon 3/15/27 | Tue 3/23/27 | 2840 | 2842 |  | Gabriela Gibson
6549 | 2842 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 3/24/27 | Thu 3/25/27 | 2841 | 2843 |  | Sean Buchanan
6550 | 2843 | Future Task |  |  | D448 | Joy Schneider | Accept | DEL D448 - Monthly Performance Report (February 2027) - Accept | 0 hrs | 0 days | Thu 3/25/27 | Thu 3/25/27 | 2842 | 2845 |  | Sean Buchanan
6551 | 2844 | Future Task |  |  | D449 | Joy Schneider |  | D449 - Monthly Performance Report (March 2027) | 10 hrs | 19 days | Thu 4/1/27 | Tue 4/27/27
6585 | 2845 | Future Task |  |  | D449 | Joy Schneider | Create | D449 - Create March 2027 Monthly Performance Report | 3 hrs | 9 days | Thu 4/1/27 | Tue 4/13/27 | 2843 | 2846 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6552 | 2846 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 4/14/27 | Wed 4/14/27 | 2845 | 2847 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6553 | 2847 | Future Task |  |  | D449 | Joy Schneider | Submit | DEL D449 - Monthly Performance Report (March 2027) - Submit | 0 hrs | 0 days | Wed 4/14/27 | Wed 4/14/27 | 2846 | 2848 |  | Joy Schneider
6554 | 2848 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Department QC | 1 hr | 7 days | Thu 4/15/27 | Fri 4/23/27 | 2847 | 2849 |  | Gabriela Gibson
6555 | 2849 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Contract Manager Review | 2 hrs | 2 days | Mon 4/26/27 | Tue 4/27/27 | 2848 | 2850 |  | Sean Buchanan
6556 | 2850 | Future Task |  |  | D449 | Joy Schneider | Accept | DEL D449 - Monthly Performance Report (March 2027) - Accept | 0 hrs | 0 days | Tue 4/27/27 | Tue 4/27/27 | 2849 | 2852 |  | Sean Buchanan
6557 | 2851 | Future Task |  |  | D450 | Joy Schneider |  | D450 - Monthly Performance Report (April 2027) | 10 hrs | 19 days | Mon 5/3/27 | Thu 5/27/27
6584 | 2852 | Future Task |  |  | D450 | Joy Schneider | Create | D450 - Create April 2027 Monthly Performance Report | 3 hrs | 9 days | Mon 5/3/27 | Thu 5/13/27 | 2850 | 2853 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6558 | 2853 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 5/14/27 | Fri 5/14/27 | 2852 | 2854 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6559 | 2854 | Future Task |  |  | D450 | Joy Schneider | Submit | DEL D450 - Monthly Performance Report (April 2027) - Submit | 0 hrs | 0 days | Fri 5/14/27 | Fri 5/14/27 | 2853 | 2855 |  | Joy Schneider
6560 | 2855 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Department QC | 1 hr | 7 days | Mon 5/17/27 | Tue 5/25/27 | 2854 | 2856 |  | Gabriela Gibson
6561 | 2856 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 5/26/27 | Thu 5/27/27 | 2855 | 2857 |  | Sean Buchanan
6562 | 2857 | Future Task |  |  | D450 | Joy Schneider | Accept | DEL D450 - Monthly Performance Report (April 2027) - Accept | 0 hrs | 0 days | Thu 5/27/27 | Thu 5/27/27 | 2856 | 2859 |  | Sean Buchanan
6563 | 2858 | Future Task |  |  | D451 | Joy Schneider |  | D451 - Monthly Performance Report (May 2027) | 10 hrs | 19 days | Tue 6/1/27 | Fri 6/25/27
6583 | 2859 | Future Task |  |  | D451 | Joy Schneider | Create | D451 - Create May 2027 Monthly Performance Report | 3 hrs | 9 days | Tue 6/1/27 | Fri 6/11/27 | 2857 | 2860 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6564 | 2860 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 6/14/27 | Mon 6/14/27 | 2859 | 2861 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6565 | 2861 | Future Task |  |  | D451 | Joy Schneider | Submit | DEL D451 - Monthly Performance Report (May 2027) - Submit | 0 hrs | 0 days | Mon 6/14/27 | Mon 6/14/27 | 2860 | 2862 |  | Joy Schneider
6566 | 2862 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Department QC | 1 hr | 7 days | Tue 6/15/27 | Wed 6/23/27 | 2861 | 2863 |  | Gabriela Gibson
6567 | 2863 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Contract Manager Review | 2 hrs | 2 days | Thu 6/24/27 | Fri 6/25/27 | 2862 | 2864 |  | Sean Buchanan
6568 | 2864 | Future Task |  |  | D451 | Joy Schneider | Accept | DEL D451 - Monthly Performance Report (May 2027) - Accept | 0 hrs | 0 days | Fri 6/25/27 | Fri 6/25/27 | 2863 | 2866 |  | Sean Buchanan
6569 | 2865 | Future Task |  |  | D694 | Joy Schneider |  | D694 - Monthly Performance Report (June 2027) | 10 hrs | 19 days | Thu 7/1/27 | Wed 7/28/27
6582 | 2866 | Future Task |  |  | D694 | Joy Schneider | Create | D694 - Create June 2027 Monthly Performance Report | 3 hrs | 9 days | Thu 7/1/27 | Wed 7/14/27 | 2864 | 2867 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6570 | 2867 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 7/15/27 | Thu 7/15/27 | 2866 | 2868 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6571 | 2868 | Future Task |  |  | D694 | Joy Schneider | Submit | DEL D694 - Monthly Performance Report (June 2027) - Submit | 0 hrs | 0 days | Thu 7/15/27 | Thu 7/15/27 | 2867 | 2869 |  | Joy Schneider
6572 | 2869 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Department QC | 1 hr | 7 days | Fri 7/16/27 | Mon 7/26/27 | 2868 | 2870 |  | Gabriela Gibson
6573 | 2870 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Contract Manager Review | 2 hrs | 2 days | Tue 7/27/27 | Wed 7/28/27 | 2869 | 2871 |  | Sean Buchanan
6574 | 2871 | Future Task |  |  | D694 | Joy Schneider | Accept | DEL D694 - Monthly Performance Report (June 2027) - Accept | 0 hrs | 0 days | Wed 7/28/27 | Wed 7/28/27 | 2870 | 2873 |  | Sean Buchanan
6575 | 2872 | Future Task |  |  | D695 | Joy Schneider |  | D695 - Monthly Performance Report (July 2027) | 10 hrs | 19 days | Mon 8/2/27 | Thu 8/26/27
6581 | 2873 | Future Task |  |  | D695 | Joy Schneider | Create | D695 - Create July 2027 Monthly Performance Report | 3 hrs | 9 days | Mon 8/2/27 | Thu 8/12/27 | 2871 | 2874 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6576 | 2874 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 8/13/27 | Fri 8/13/27 | 2873 | 2875 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6577 | 2875 | Future Task |  |  | D695 | Joy Schneider | Submit | DEL D695 - Monthly Performance Report (July 2027) - Submit | 0 hrs | 0 days | Fri 8/13/27 | Fri 8/13/27 | 2874 | 2876 |  | Joy Schneider
6578 | 2876 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Department QC | 1 hr | 7 days | Mon 8/16/27 | Tue 8/24/27 | 2875 | 2877 |  | Gabriela Gibson
6579 | 2877 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 8/25/27 | Thu 8/26/27 | 2876 | 2878 |  | Sean Buchanan
6580 | 2878 | Future Task |  |  | D695 | Joy Schneider | Accept | DEL D695 - Monthly Performance Report (July 2027) - Accept | 0 hrs | 0 days | Thu 8/26/27 | Thu 8/26/27 | 2877 |  |  | Sean Buchanan
4047 | 2879 | Future Task | [5 empty] | Quarterly Newsletter for DDI of Reporting Functionality | 132 hrs | 658 days | Wed 6/21/23 | Mon 2/2/26
4048 | 2880 | Future Task | [5 empty] | Quarterly Newsletter | 132 hrs | 658 days | Wed 6/21/23 | Mon 2/2/26
4049 | 2881 | Future Task | [5 empty] | Quarterly Newsletter FY 22-23 Q4 | 12 hrs | 17 days | Wed 6/21/23 | Fri 7/14/23
4050 | 2882 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Wed 6/21/23 | Tue 6/27/23 |  | 2883 |  | Jennifer Grant,Jennifer Reeves
4051 | 2883 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Wed 6/28/23 | Wed 7/5/23 | 2882 | 2884 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4052 | 2884 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Thu 7/6/23 | Wed 7/12/23 | 2883 | 2885 |  | Jimmy Cox,Steven Fielder
4053 | 2885 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Thu 7/13/23 | Fri 7/14/23 | 2884 | 2887 |  | Dusti Kincl
4054 | 2886 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q1 | 12 hrs | 17 days | Fri 9/22/23 | Mon 10/16/23
4055 | 2887 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 9/22/23 | Thu 9/28/23 | 2885 | 2888 |  | Jennifer Grant,Jennifer Reeves
4056 | 2888 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 9/29/23 | Thu 10/5/23 | 2887 | 2889 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4057 | 2889 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 10/6/23 | Thu 10/12/23 | 2888 | 2890 |  | Jimmy Cox,Steven Fielder
4058 | 2890 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 10/13/23 | Mon 10/16/23 | 2889 | 2892 |  | Dusti Kincl
4059 | 2891 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q2 | 12 hrs | 17 days | Mon 12/18/23 | Thu 1/11/24
4060 | 2892 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 12/18/23 | Fri 12/22/23 | 2890 | 2893 |  | Jennifer Grant,Jennifer Reeves
4061 | 2893 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Tue 12/26/23 | Tue 1/2/24 | 2892 | 2894 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4062 | 2894 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Wed 1/3/24 | Tue 1/9/24 | 2893 | 2895 |  | Jimmy Cox,Steven Fielder
4063 | 2895 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Wed 1/10/24 | Thu 1/11/24 | 2894 | 2897 |  | Dusti Kincl
4064 | 2896 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q3 | 12 hrs | 17 days | Fri 3/22/24 | Mon 4/15/24
4065 | 2897 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 3/22/24 | Thu 3/28/24 | 2895 | 2898 |  | Jennifer Grant,Jennifer Reeves
4066 | 2898 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 3/29/24 | Thu 4/4/24 | 2897 | 2899 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4067 | 2899 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 4/5/24 | Thu 4/11/24 | 2898 | 2900 |  | Jimmy Cox,Steven Fielder
4068 | 2900 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 4/12/24 | Mon 4/15/24 | 2899 | 2902 |  | Dusti Kincl
4069 | 2901 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q4 | 12 hrs | 17 days | Thu 6/20/24 | Mon 7/15/24
4070 | 2902 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Thu 6/20/24 | Wed 6/26/24 | 2900 | 2903 |  | Jennifer Grant,Jennifer Reeves
4071 | 2903 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Thu 6/27/24 | Wed 7/3/24 | 2902 | 2904 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4072 | 2904 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 7/5/24 | Thu 7/11/24 | 2903 | 2905 |  | Jimmy Cox,Steven Fielder
4073 | 2905 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 7/12/24 | Mon 7/15/24 | 2904 | 2907 |  | Dusti Kincl
4074 | 2906 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q1 | 12 hrs | 17 days | Mon 9/23/24 | Tue 10/15/24
4075 | 2907 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 2905 | 2908 |  | Jennifer Grant,Jennifer Reeves
4076 | 2908 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Mon 9/30/24 | Fri 10/4/24 | 2907 | 2909 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4077 | 2909 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 | 2908 | 2910 |  | Jimmy Cox,Steven Fielder
4078 | 2910 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Mon 10/14/24 | Tue 10/15/24 | 2909 | 2912 |  | Dusti Kincl
4079 | 2911 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q2 | 12 hrs | 17 days | Mon 12/16/24 | Thu 1/9/25
4080 | 2912 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 12/16/24 | Fri 12/20/24 | 2910 | 2913 |  | Jennifer Grant,Jennifer Reeves
4081 | 2913 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Mon 12/23/24 | Mon 12/30/24 | 2912 | 2914 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4082 | 2914 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Tue 12/31/24 | Tue 1/7/25 | 2913 | 2915 |  | Jimmy Cox,Steven Fielder
4083 | 2915 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Wed 1/8/25 | Thu 1/9/25 | 2914 | 2917 |  | Dusti Kincl
4084 | 2916 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q3 | 12 hrs | 17 days | Mon 3/24/25 | Tue 4/15/25
4085 | 2917 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 2915 | 2918 |  | Jennifer Grant,Jennifer Reeves
4086 | 2918 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Mon 3/31/25 | Fri 4/4/25 | 2917 | 2919 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4087 | 2919 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Mon 4/7/25 | Fri 4/11/25 | 2918 | 2920 |  | Jimmy Cox,Steven Fielder
4088 | 2920 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Mon 4/14/25 | Tue 4/15/25 | 2919 | 2922 |  | Dusti Kincl
4089 | 2921 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q4 | 12 hrs | 17 days | Fri 6/20/25 | Tue 7/15/25
4090 | 2922 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 6/20/25 | Thu 6/26/25 | 2920 | 2923 |  | Jennifer Grant,Jennifer Reeves
4091 | 2923 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 6/27/25 | Thu 7/3/25 | 2922 | 2924 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4092 | 2924 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Mon 7/7/25 | Fri 7/11/25 | 2923 | 2925 |  | Jimmy Cox,Steven Fielder
4093 | 2925 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Mon 7/14/25 | Tue 7/15/25 | 2924 | 2927 |  | Dusti Kincl
4094 | 2926 | Future Task | [5 empty] | Quarterly Newsletter FY 25-26 Q1 | 12 hrs | 17 days | Fri 9/26/25 | Mon 10/20/25
4095 | 2927 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 9/26/25 | Thu 10/2/25 | 2925 | 2928 |  | Jennifer Grant,Jennifer Reeves
4096 | 2928 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 10/3/25 | Thu 10/9/25 | 2927 | 2929 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4097 | 2929 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 10/10/25 | Thu 10/16/25 | 2928 | 2930 |  | Jimmy Cox,Steven Fielder
4098 | 2930 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 10/17/25 | Mon 10/20/25 | 2929 | 2932 |  | Dusti Kincl
4099 | 2931 | Future Task | [5 empty] | Quarterly Newsletter FY 25-26 Q2 | 12 hrs | 17 days | Thu 1/8/26 | Mon 2/2/26
4100 | 2932 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Thu 1/8/26 | Wed 1/14/26 | 2930 | 2933 |  | Jennifer Grant,Jennifer Reeves
4101 | 2933 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review & Update - Quarterly Newsletter | 7 hrs | 5 days | Thu 1/15/26 | Thu 1/22/26 | 2932 | 2934 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4102 | 2934 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 1/23/26 | Thu 1/29/26 | 2933 | 2935 |  | Jimmy Cox,Steven Fielder
4103 | 2935 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish & Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 1/30/26 | Mon 2/2/26 | 2934 |  |  | Dusti Kincl

## Sheet1 (2) (hidden)
Unique ID | ID | Status | Critical Path | RW | DEL, WP, SG # | Task Coordinator | Task Type | Task Name | Work | Duration | Start | Finish | Predecessors | Successors | Notes | Resource Names | Requested Updates | Requested By
0 | 0 | Late | [5 empty] | Project Schedule (Financials, Payroll, Data Warehouse and Business Intelligence) | 23,243.58 hrs | 1177 days | Wed 4/26/23 | Tue 12/28/27
7152 | 1 | Complete |  |  |  | Jimmy Cox |  | Amendment 8 Executed | 0 hrs | 0 days | Wed 4/26/23 | Wed 4/26/23 |  | 6,30FS+3 days,49FS+47 days,86FS+27 days,107FS+27 days,212FS+90 days,355FS+112 days,185FS+27 days,199FS+27 days,587FS+47 days,68FS+27 days,147,166,225,239,253,330,342,395,451,473,493,513,533,546,640,682,741,781,806,825,843,885,910,929,1001,1019,1044,1058... |  | Jimmy Cox |  | Testing by Joy GOT IT!, thanks! Did you get this one?
2 | 2 | Late | [5 empty] | Implementation | 16,003.58 hrs | 699 days | Wed 4/26/23 | Wed 2/4/26
3769 | 3 | Late | [5 empty] | Design | 5,188 hrs | 475 days | Wed 4/26/23 | Fri 3/14/25
7155 | 4 | Future Task | Yes |  | SG1 | Jimmy Cox | Milestone | Stage Gate 1: Ready to Start Build | 0 hrs | 0 days | Mon 10/23/23 | Mon 10/23/23 | 47,57 |  | Nov/Dec 2023 | Jimmy Cox,Angie Robertson,Matt Cole
3793 | 5 | Late | Yes |  | D635 | Joy Schneider |  | D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) | 450 hrs | 38 days | Mon 5/8/23 | Thu 6/29/23
7130 | 6 | Complete |  |  | D635 | Joy Schneider |  | Develop Outline of Project Schedule | 2 hrs | 1 day | Mon 5/8/23 | Mon 5/8/23 | 1 | 7SS |  | Joy Schneider,Francisca Li
7131 | 7 | Complete |  |  | D635 | Joy Schneider |  | Create New Schedule Tasks Workbook | 4 hrs | 1 day | Mon 5/8/23 | Mon 5/8/23 | 6SS | 8,9,10FS+1 day |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner
7132 | 8 | Complete |  |  | D635 | Joy Schneider |  | Gather Tasks from State Architects | 60 hrs | 4 days | Tue 5/9/23 | Fri 5/12/23 | 7 | 19 |  | Julian Gotreaux,Gabriela Gibson,Tommy Werner,Angie Robertson,Deana Metcalf,Carolyn Hicks,Jennifer Reeves,Matthew Breeding
7133 | 9 | Complete |  |  | D635 | Joy Schneider |  | Load Amendment 8 Deliverables and Work Products to Project Schedule | 4 hrs | 2 days | Tue 5/9/23 | Wed 5/10/23 | 7 | 19 |  | Joy Schneider,Francisca Li
7134 | 10 | Complete |  |  | D635 | Joy Schneider |  | Load Resources into Project Schedule | 8 hrs | 1 day | Wed 5/10/23 | Wed 5/10/23 | 7FS+1 day | 11 |  | Joy Schneider,Francisca Li
7135 | 11 | Complete |  |  | D635 | Joy Schneider |  | Add and Refine Work Activities for Amendment 8 Deliverables | 17 hrs | 2 days | Thu 5/11/23 | Fri 5/12/23 | 10 | 12SS+1 day |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole
7136 | 12 | Complete |  |  | D635 | Joy Schneider |  | Add Tasks from State Architects | 10 hrs | 1 day | Fri 5/12/23 | Fri 5/12/23 | 11SS+1 day | 13 |  | Joy Schneider,Francisca Li
7137 | 13 | Late |  |  | D635 | Joy Schneider |  | Provide Project Schedule Export Reports | 2 hrs | 1 day | Mon 5/15/23 | Mon 5/15/23 | 12 | 14SS,15SS |  | Joy Schneider,Francisca Li
7138 | 14 | Late |  |  | D635 | Joy Schneider |  | Add and Refine Work Activities for Amendment 8 Work Products | 60 hrs | 5 days | Mon 5/15/23 | Fri 5/19/23 | 13SS | 19 |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole
7139 | 15 | Complete |  |  | D635 | Joy Schneider |  | Project Schedule Working Sessions | 85 hrs | 5 days | Mon 5/15/23 | Fri 5/19/23 | 13SS | 16 |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Manojkumar Gurjar,Yogesh Deshmukh,Matt Cole,Angie Robertson,Deana Metcalf,Matthew Breeding,Carolyn Hicks,Jimmy Cox,Jennifer Reeves
7140 | 16 | Late |  |  | D635 | Joy Schneider |  | Refine Work Activities for Non-SSI Deliverables and Work Products | 26 hrs | 5 days | Mon 5/22/23 | Fri 5/26/23 | 15 | 17SS+2 days |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Gabriela Gibson
7141 | 17 | Late |  |  | D635 | Joy Schneider |  | Define Tasks to Assign to Critical Path Column | 25 hrs | 3 days | Wed 5/24/23 | Fri 5/26/23 | 16SS+2 days | 18 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Jimmy Cox,Matt Cole
7142 | 18 | Future Task |  |  | D635 | Joy Schneider |  | Provide Project Schedule Export Reports and Refine Based on Input | 70 hrs | 9 days | Tue 5/30/23 | Fri 6/9/23 | 17 | 19 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Deana Metcalf,Matthew Breeding,Carlos Luis,Jimmy Cox,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Manojkumar Gurjar,Yogesh Deshmukh,Matt Cole,Jennifer Reeves
7143 | 19 | Future Task |  |  | D635 | Joy Schneider |  | Conduct Project Schedule Baseline Prep Meeting | 36 hrs | 1 day | Mon 6/12/23 | Mon 6/12/23 | 18,8,9,14 | 20 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Deana Metcalf,Matthew Breeding,Carolyn Hicks,Jimmy Cox,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole,Gabriela Gibson,Jennifer Reeves
4271 | 20 | Future Task |  |  | D635 | Joy Schneider | Submit | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Draft Submission | 0 hrs | 0 days | Mon 6/12/23 | Mon 6/12/23 | 19 | 21 |  | Joy Schneider
4272 | 21 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Pre-Submission Collaborative Review | 14 hrs | 3 days | Tue 6/13/23 | Thu 6/15/23 | 20 | 22 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Gabriela Gibson,Jenifer Hartsfield,Angie Robertson
4273 | 22 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Style Guide Review | 1 hr | 1 day | Fri 6/16/23 | Fri 6/16/23 | 21 | 23 |  | Dusti Kincl
4274 | 23 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Final Collaborative Review | 10 hrs | 3 days | Mon 6/19/23 | Wed 6/21/23 | 22 | 24 |  | Joy Schneider,Francisca Li,Angie Robertson,Jimmy Cox,Jennifer Reeves,Deana Metcalf,Matthew Breeding,Carolyn Hicks
4275 | 24 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Accenture QC | 4 hrs | 2 days | Thu 6/22/23 | Fri 6/23/23 | 23 | 25 |  | Joy Schneider
4276 | 25 | Future Task |  |  | D635 | Joy Schneider | Submit | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Submit | 0 hrs | 0 days | Fri 6/23/23 | Fri 6/23/23 | 24 | 26 |  | Joy Schneider
4277 | 26 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Department QC | 4 hrs | 1 day | Mon 6/26/23 | Mon 6/26/23 | 25 | 27 |  | Tommy Werner,Gabriela Gibson
4278 | 27 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Contract Manager Review | 8 hrs | 3 days | Tue 6/27/23 | Thu 6/29/23 | 26 | 28 |  | Sean Buchanan
4279 | 28 | Future Task |  |  | D635 | Joy Schneider | Accept | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Accept | 0 hrs | 0 days | Thu 6/29/23 | Thu 6/29/23 | 27 | 2291 | 2023-06-01 | Sean Buchanan
4280 | 29 | Late | Yes |  | D636 | Stacey Terry |  | D636 - Completion of Solution Design (Requirements) Segment I | 309 hrs | 82 days | Mon 5/1/23 | Thu 8/24/23
4308 | 30 | Late |  |  | D636 | Stacey Terry |  | Identify Functional Designs (Segment I) | 50 hrs | 10 days | Mon 5/1/23 | Fri 5/12/23 | 1FS+3 days | 31 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4281 | 31 | Late |  |  | D636 | Stacey Terry | Create | DED D636 - Completion of Solution Design (Requirements) Segment I - Create | 8 hrs | 10 days | Mon 5/15/23 | Fri 5/26/23 | 30 | 32 |  | Stacey Terry,Mary Punty
4282 | 32 | Future Task |  |  | D636 | Stacey Terry | Submit | DED D636 - Completion of Solution Design (Requirements) Segment I - Submit | 0 hrs | 0 days | Fri 5/26/23 | Fri 5/26/23 | 31 | 33 |  | Stacey Terry,Joy Schneider
4283 | 33 | Future Task |  |  | D636 | Stacey Terry | Review | DED D636 - Completion of Solution Design (Requirements) Segment I - Collaborative Review | 24 hrs | 4 days | Tue 5/30/23 | Fri 6/2/23 | 32 | 34 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4284 | 34 | Future Task |  |  | D636 | Stacey Terry | Approve | DED D636 - Completion of Solution Design (Requirements) Segment I - Approve | 0 hrs | 0 days | Fri 6/2/23 | Fri 6/2/23 | 33 | 35 |  | Jimmy Cox
4309 | 35 | Future Task |  |  | D636 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs (Segment I) | 50 hrs | 5 days | Mon 6/5/23 | Fri 6/9/23 | 34 | 36 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4310 | 36 | Future Task |  |  | D636 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment I) | 50 hrs | 4 days | Mon 6/12/23 | Thu 6/15/23 | 35 | 37 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4311 | 37 | Future Task |  |  | D636 | Stacey Terry |  | Create, Review and Approve Functional Design Documents (Segment I) | 50 hrs | 32 days | Fri 6/16/23 | Tue 8/1/23 | 36 | 38FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4312 | 38 | Future Task |  |  | D636 | Stacey Terry |  | Create Summary Document | 20 hrs | 11 days | Tue 7/18/23 | Tue 8/1/23 | 37FS-11 days | 39,1542SS,1586SS,1629SS,1454,1499 |  | Deana Metcalf,Stacey Terry,Mary Punty
4285 | 39 | Future Task |  |  | D636 | Stacey Terry | Submit | DEL D636 - Completion of Solution Design (Requirements) Segment I - Draft Submission | 0 hrs | 0 days | Tue 8/1/23 | Tue 8/1/23 | 38 | 40 |  | Stacey Terry,Joy Schneider
4286 | 40 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Wed 8/2/23 | Tue 8/8/23 | 39 | 41 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4287 | 41 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Style Guide Review | 1 hr | 1 day | Wed 8/9/23 | Wed 8/9/23 | 40 | 42 |  | Dusti Kincl
4288 | 42 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Final Collaborative Review | 20 hrs | 5 days | Thu 8/10/23 | Wed 8/16/23 | 41 | 43 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4289 | 43 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Accenture QC | 4 hrs | 2 days | Thu 8/17/23 | Fri 8/18/23 | 42 | 44 |  | Joy Schneider
4290 | 44 | Future Task |  |  | D636 | Stacey Terry | Submit | DEL D636 - Completion of Solution Design (Requirements) Segment I - Submit | 0 hrs | 0 days | Fri 8/18/23 | Fri 8/18/23 | 43 | 451664 |  | Joy Schneider
4291 | 45 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Department QC | 4 hrs | 1 day | Mon 8/21/23 | Mon 8/21/23 | 44 | 46 |  | Tommy Werner,Gabriela Gibson
4292 | 46 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Contract Manager Review | 8 hrs | 3 days | Tue 8/22/23 | Thu 8/24/23 | 45 | 47 |  | Sean Buchanan
4293 | 47 | Future Task |  |  | D636 | Stacey Terry | Accept | DEL D636 - Completion of Solution Design (Requirements) Segment I - Accept | 0 hrs | 0 days | Thu 8/24/23 | Thu 8/24/23 | 46 | 216,580,584,585,4 | July 2023 (Aug 2023) | Sean Buchanan
4294 | 48 | Future Task | Yes |  | D637 | Stacey Terry |  | D637 - Completion of Solution Design (Requirements) Segment II | 342 hrs | 96 days | Mon 7/3/23 | Thu 11/16/23
4313 | 49 | Future Task |  |  | D637 | Stacey Terry |  | Identify Functional Designs (Segment II) | 50 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 1FS+47 days | 50 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4295 | 50 | Future Task |  |  | D637 | Stacey Terry | Create | DED D637 - Completion of Solution Design (Requirements) Segment II - Create | 16 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 49 | 51 |  | Stacey Terry,Mary Punty
4296 | 51 | Future Task |  |  | D637 | Stacey Terry | Submit | DED D637 - Completion of Solution Design (Requirements) Segment II - Submit | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 50 | 52 |  | Stacey Terry,Joy Schneider
4297 | 52 | Future Task |  |  | D637 | Stacey Terry | Review | DED D637 - Completion of Solution Design (Requirements) Segment II - Collaborative Review | 24 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 51 | 53 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4298 | 53 | Future Task |  |  | D637 | Stacey Terry | Approve | DED D637 - Completion of Solution Design (Requirements) Segment II - Approve | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 52 | 54 |  | Jimmy Cox
4314 | 54 | Future Task |  |  | D637 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs (Segment II) | 50 hrs | 4 days | Tue 8/15/23 | Fri 8/18/23 | 53 | 55 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4315 | 55 | Future Task |  |  | D637 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment II) | 50 hrs | 5 days | Mon 8/21/23 | Fri 8/25/23 | 54 | 56 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4316 | 56 | Future Task |  |  | D637 | Stacey Terry |  | Create, Review and Approve Functional Design Documents (Segment II) | 50 hrs | 40 days | Mon 8/28/23 | Mon 10/23/23 | 55 | 57FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4317 | 57 | Future Task |  |  | D637 | Stacey Terry |  | Create Summary Document | 50 hrs | 11 days | Mon 10/9/23 | Mon 10/23/23 | 56FS-11 days | 58,1545SS,1411SS,1589SS+2 days,1632SS+5 days,1457,1502,4 |  | Deana Metcalf,Stacey Terry,Mary Punty
4299 | 58 | Future Task |  |  | D637 | Stacey Terry | Submit | DEL D637 - Completion of Solution Design (Requirements) Segment II - Draft Submission | 0 hrs | 0 days | Mon 10/23/23 | Mon 10/23/23 | 57 | 59 |  | Stacey Terry,Joy Schneider
4300 | 59 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 10/24/23 | Mon 10/30/23 | 58 | 60 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4301 | 60 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Style Guide Review | 1 hr | 1 day | Tue 10/31/23 | Tue 10/31/23 | 59 | 61 |  | Dusti Kincl
4302 | 61 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Final Collaborative Review | 20 hrs | 5 days | Wed 11/1/23 | Tue 11/7/23 | 60 | 62 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4303 | 62 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Accenture QC | 1 hr | 2 days | Wed 11/8/23 | Thu 11/9/23 | 61 | 63 |  | Francisca Li
4304 | 63 | Future Task |  |  | D637 | Stacey Terry | Submit | DEL D637 - Completion of Solution Design (Requirements) Segment II - Submit | 0 hrs | 0 days | Thu 11/9/23 | Thu 11/9/23 | 62 | 64 |  | Joy Schneider
4305 | 64 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Department QC | 2 hrs | 1 day | Mon 11/13/23 | Mon 11/13/23 | 63 | 65 |  | Tommy Werner,Gabriela Gibson
4306 | 65 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Contract Manager Review | 8 hrs | 3 days | Tue 11/14/23 | Thu 11/16/23 | 64 | 66 |  | Sean Buchanan
4307 | 66 | Future Task |  |  | D637 | Stacey Terry | Accept | DEL D637 - Completion of Solution Design (Requirements) Segment II - Accept | 0 hrs | 0 days | Thu 11/16/23 | Thu 11/16/23 | 65 | 580584585 | October 2023 (Nov 2023) | Sean Buchanan
5585 | 67 | Future Task |  |  | D638 | Manojkumar Gurjar |  | D638 - Updated Data Conversion and Migration Strategy | 213 hrs | 80 days | Mon 6/5/23 | Tue 9/26/23
5586 | 68 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | DED D638 - Updated Data Conversion and Migration Strategy - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 69 |  | Manojkumar Gurjar,Kurt Meisner
5587 | 69 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DED D638 - Updated Data Conversion and Migration Strategy - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 68 | 70 |  | Manojkumar Gurjar,Joy Schneider
5588 | 70 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DED D638 - Updated Data Conversion and Migration Strategy - Collaborative Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 69 | 71 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5589 | 71 | Future Task |  |  | D638 | Manojkumar Gurjar | Approve | DED D638 - Updated Data Conversion and Migration Strategy - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 70 | 72 |  | Jimmy Cox
5590 | 72 | Future Task |  |  | D638 | Manojkumar Gurjar |  | Define the approach for Data Cleansing | 8 hrs | 14 days | Mon 7/3/23 | Fri 7/21/23 | 71 | 73SS+4 days |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5591 | 73 | Future Task |  |  | D638 | Manojkumar Gurjar |  | Define Communication/Collaboration for Data Conversion approach | 8 hrs | 10 days | Mon 7/10/23 | Fri 7/21/23 | 72SS+4 days | 74 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5592 | 74 | Future Task |  |  | D638 | Manojkumar Gurjar |  | Identify Data Conversion Resources | 50 hrs | 10 days | Mon 7/24/23 | Fri 8/4/23 | 73 | 75 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer,Jeevan Mahajan,Janmejay Khare
5593 | 75 | Future Task |  |  | D638 | Manojkumar Gurjar |  | Updated Data Conversion and Migration Strategy Document | 50 hrs | 19 days | Mon 8/7/23 | Thu 8/31/23 | 74 | 76 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5594 | 76 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DEL D638 - Updated Data Conversion and Migration Strategy - Draft Submission | 0 hrs | 0 days | Thu 8/31/23 | Thu 8/31/23 | 75 | 77 |  | Manojkumar Gurjar,Joy Schneider
5595 | 77 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 76 | 78 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5596 | 78 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Style Guide Review | 1 hr | 1 day | Mon 9/11/23 | Mon 9/11/23 | 77 | 79 |  | Dusti Kincl
5597 | 79 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Final Collaborative Review | 20 hrs | 5 days | Tue 9/12/23 | Mon 9/18/23 | 78 | 80 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5598 | 80 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Accenture QC | 4 hrs | 2 days | Tue 9/19/23 | Wed 9/20/23 | 79 | 81 |  | Joy Schneider
5599 | 81 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DEL D638 - Updated Data Conversion and Migration Strategy - Submit | 0 hrs | 0 days | Wed 9/20/23 | Wed 9/20/23 | 80 | 82 |  | Joy Schneider
5600 | 82 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Department QC | 4 hrs | 1 day | Thu 9/21/23 | Thu 9/21/23 | 81 | 83 |  | Tommy Werner,Gabriela Gibson
5601 | 83 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Contract Manager Review | 8 hrs | 3 days | Fri 9/22/23 | Tue 9/26/23 | 82 | 84 |  | Sean Buchanan
5602 | 84 | Future Task |  |  | D638 | Manojkumar Gurjar | Accept | DEL D638 - Updated Data Conversion and Migration Strategy - Accept | 0 hrs | 0 days | Tue 9/26/23 | Tue 9/26/23 | 83 |  | 2023-10-01 | Sean Buchanan
4375 | 85 | Future Task | Yes |  | D639 | Stacey Terry |  | D639 - Development of Standardized Business Process Models – Payroll | 241 hrs | 94 days | Mon 6/5/23 | Mon 10/16/23
4376 | 86 | Future Task |  |  | D639 | Stacey Terry | Create | DED D639 - Development of Standardized Business Process Models – Payroll - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 87 |  | Stacey Terry,Mary Punty
4377 | 87 | Future Task |  |  | D639 | Stacey Terry | Submit | DED D639 - Development of Standardized Business Process Models – Payroll - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 86 | 88 |  | Stacey Terry,Joy Schneider
4378 | 88 | Future Task |  |  | D639 | Stacey Terry | Review | DED D639 - Development of Standardized Business Process Models – Payroll - Collaborative Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 87 | 89 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4379 | 89 | Future Task |  |  | D639 | Stacey Terry | Approve | DED D639 - Development of Standardized Business Process Models – Payroll - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 88 | 90 |  | Jimmy Cox
4417 | 90 | Future Task |  |  | D639 | Stacey Terry |  | Identify Payroll Wave Business Processes and Subprocesses | 25 hrs | 5 days | Mon 7/3/23 | Mon 7/10/23 | 89 | 91SS+2 days |  | Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari
4418 | 91 | Future Task |  |  | D639 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Payroll Wave Business Processes and Subprocesses | 4 hrs | 5 days | Thu 7/6/23 | Wed 7/12/23 | 90SS+2 days | 92 |  | Stacey Terry,Yogesh Deshmukh
4419 | 92 | Future Task |  |  | D639 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Payroll Wave Business Processes and Subprocesses | 20 hrs | 5 days | Thu 7/13/23 | Wed 7/19/23 | 91 | 93SS |  | Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4420 | 93 | Future Task |  |  | D639 | Stacey Terry |  | Create Payroll Wave Business Process Models | 30 hrs | 30 days | Thu 7/13/23 | Wed 8/23/23 | 92SS | 94 |  | Jimmy Cox,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari,Heather Cleary,Joanne Lane,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Donnie Doctor,Ryan R...
4421 | 94 | Future Task |  |  | D639 | Stacey Terry |  | Prepare Materials / Conduct Office Hours | 25 hrs | 10 days | Thu 8/24/23 | Thu 9/7/23 | 93 | 95 |  | Jimmy Cox,Angie Robertson,Carolyn Hicks,Dusti Kincl,Kimberly Kemp,Deana Metcalf,Stacey Terry,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Janice Jackson,LaVondria Norton,Robert Hic...
4422 | 95 | Future Task |  |  | D639 | Stacey Terry |  | Refine Payroll Wave Business Process Models | 20 hrs | 5 days | Fri 9/8/23 | Thu 9/14/23 | 94 | 96 |  | Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari
4423 | 96 | Future Task |  |  | D639 | Stacey Terry |  | Create Summary Document | 20 hrs | 5 days | Fri 9/15/23 | Thu 9/21/23 | 95 | 97 |  | Deana Metcalf,Stacey Terry,Mary Punty
4380 | 97 | Future Task |  |  | D639 | Stacey Terry | Submit | DEL D639 - Development of Standardized Business Process Models – Payroll - Draft Submission | 0 hrs | 0 days | Thu 9/21/23 | Thu 9/21/23 | 96 | 98 |  | Stacey Terry,Joy Schneider
4381 | 98 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 9/22/23 | Thu 9/28/23 | 97 | 99 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4382 | 99 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Style Guide Review | 1 hr | 1 day | Fri 9/29/23 | Fri 9/29/23 | 98 | 100 |  | Dusti Kincl
4383 | 100 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Final Collaborative Review | 20 hrs | 5 days | Mon 10/2/23 | Fri 10/6/23 | 99 | 101 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4384 | 101 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Accenture QC | 4 hrs | 2 days | Mon 10/9/23 | Tue 10/10/23 | 100 | 102 |  | Joy Schneider
4385 | 102 | Future Task |  |  | D639 | Stacey Terry | Submit | DEL D639 - Development of Standardized Business Process Models – Payroll - Submit | 0 hrs | 0 days | Tue 10/10/23 | Tue 10/10/23 | 101 | 103 |  | Joy Schneider
4386 | 103 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Department QC | 4 hrs | 1 day | Wed 10/11/23 | Wed 10/11/23 | 102 | 104 |  | Tommy Werner,Gabriela Gibson
4387 | 104 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Contract Manager Review | 8 hrs | 3 days | Thu 10/12/23 | Mon 10/16/23 | 103 | 105 |  | Sean Buchanan
4388 | 105 | Future Task |  |  | D639 | Stacey Terry | Accept | DEL D639 - Development of Standardized Business Process Models – Payroll - Accept | 0 hrs | 0 days | Mon 10/16/23 | Mon 10/16/23 | 104 | 1803580 | 2023-10-01 | Sean Buchanan
4389 | 106 | Future Task | Yes |  | D640 | Stacey Terry |  | D640 - Development of the Master Data Configuration Workbooks | 311 hrs | 142 days | Mon 6/5/23 | Wed 12/27/23
4390 | 107 | Future Task |  |  | D640 | Stacey Terry | Create | DED D640 - Development of the Master Data Configuration Workbooks - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 108,111SS+9 days |  | Stacey Terry,Mary Punty
4391 | 108 | Future Task |  |  | D640 | Stacey Terry | Submit | DED D640 - Development of the Master Data Configuration Workbooks - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 107 | 109 |  | Stacey Terry,Joy Schneider
4392 | 109 | Future Task |  |  | D640 | Stacey Terry | Review | DED D640 - Development of the Master Data Configuration Workbooks - Collaborative Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 108 | 110 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4393 | 110 | Future Task |  |  | D640 | Stacey Terry | Approve | DED D640 - Development of the Master Data Configuration Workbooks - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 109 |  |  | Jimmy Cox
4424 | 111 | Future Task |  |  | D640 | Stacey Terry |  | Identify Configuration Inventory | 20 hrs | 10 days | Fri 6/16/23 | Thu 6/29/23 | 107SS+9 days | 112 |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Donnie Doctor,Ryan Raagas,Pooj... | This first task is set to begin before the DED approves. This should begin after. | Angie
4425 | 112 | Future Task |  |  | D640 | Stacey Terry |  | Update Design Work Unit Tracker for Configuration | 4 hrs | 5 days | Fri 6/30/23 | Fri 7/7/23 | 111 | 113 |  | Stacey Terry,Yogesh Deshmukh
4426 | 113 | Future Task |  |  | D640 | Stacey Terry |  | Review and Confirm Design Work Unit Tracker for Configuration | 50 hrs | 4 days | Mon 7/10/23 | Thu 7/13/23 | 112 | 114 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4427 | 114 | Future Task |  |  | D640 | Stacey Terry |  | Create, Review, and Confirm Configuration Workbooks and Agency Configuration Workbook Templates (this is a WU) | 40 hrs | 80 days | Fri 7/14/23 | Fri 11/3/23 | 113 | 115SS+20 days |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Donnie Doctor,Ryan Raagas,Pooj...
4428 | 115 | Future Task |  |  | D640 | Stacey Terry |  | Configure Application | 40 hrs | 70 days | Fri 8/11/23 | Mon 11/20/23 | 114SS+20 days | 116 |  | Apoorva Panchanadikar,Divya Gupta,Supriya Vaddi,Suyesh Shingare,Purushottam Karambelkar,Ankita Sarang,Yash Jamkhedkar,Sajal Saurabh,Timtim Goel
4429 | 116 | Future Task |  |  | D640 | Stacey Terry |  | Finalize Configuration Workbooks | 30 hrs | 10 days | Tue 11/21/23 | Wed 12/6/23 | 115 | 117FS-10 days |  | Apoorva Panchanadikar,Divya Gupta,Supriya Vasudevan,Suyesh Shingare,Purushottam Karambelkar,Ankita Sarang,Yash Jamkhedkar,Sajal Saurabh,Timtim Goel,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Jack Je...
4430 | 117 | Future Task |  |  | D640 | Stacey Terry |  | Create Summary Document | 30 hrs | 7 days | Tue 11/21/23 | Fri 12/1/23 | 116FS-10 days | 118 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Mary Punty
4394 | 118 | Future Task |  |  | D640 | Stacey Terry | Submit | DEL D640 - Development of the Master Data Configuration Workbooks - Draft Submission | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 117 | 119 |  | Stacey Terry,Joy Schneider
4395 | 119 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 12/4/23 | Fri 12/8/23 | 118 | 120 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4396 | 120 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Style Guide Review | 1 hr | 1 day | Mon 12/11/23 | Mon 12/11/23 | 119 | 121 |  | Dusti Kincl
4397 | 121 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Final Collaborative Review | 20 hrs | 5 days | Tue 12/12/23 | Mon 12/18/23 | 120 | 122 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4398 | 122 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Accenture QC | 4 hrs | 2 days | Tue 12/19/23 | Wed 12/20/23 | 121 | 123 |  | Joy Schneider
4399 | 123 | Future Task |  |  | D640 | Stacey Terry | Submit | DEL D640 - Development of the Master Data Configuration Workbooks - Submit | 0 hrs | 0 days | Wed 12/20/23 | Wed 12/20/23 | 122 | 124 |  | Joy Schneider
4400 | 124 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Department QC | 4 hrs | 1 day | Thu 12/21/23 | Thu 12/21/23 | 123 | 125 |  | Tommy Werner,Gabriela Gibson
4401 | 125 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Contract Manager Review | 8 hrs | 3 days | Fri 12/22/23 | Wed 12/27/23 | 124 | 126 |  | Sean Buchanan
4402 | 126 | Future Task |  |  | D640 | Stacey Terry | Accept | DEL D640 - Development of the Master Data Configuration Workbooks - Accept | 0 hrs | 0 days | Wed 12/27/23 | Wed 12/27/23 | 125 | 577FS+6 days | 2023-12-01 | Sean Buchanan
4318 | 127 | Future Task | Yes |  | D641 | Stacey Terry |  | D641 - Completion of Solution Design (Requirements) Segment III | 327 hrs | 96 days | Mon 10/2/23 | Tue 2/20/24
4332 | 128 | Future Task |  |  | D641 | Stacey Terry |  | Identify Functional Designs (Segment III) | 50 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 1 | 129 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4319 | 129 | Future Task |  |  | D641 | Stacey Terry | Create | DED D641 - Completion of Solution Design (Requirements) Segment III - Create | 16 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 128 | 130 |  | Stacey Terry,Mary Punty
4320 | 130 | Future Task |  |  | D641 | Stacey Terry | Submit | DED D641 - Completion of Solution Design (Requirements) Segment III - Submit | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 129 | 131 |  | Stacey Terry,Joy Schneider
4321 | 131 | Future Task |  |  | D641 | Stacey Terry | Review | DED D641 - Completion of Solution Design (Requirements) Segment III - Collaborative Review | 24 hrs | 10 days | Mon 10/30/23 | Mon 11/13/23 | 130 | 132 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4322 | 132 | Future Task |  |  | D641 | Stacey Terry | Approve | DED D641 - Completion of Solution Design (Requirements) Segment III - Approve | 0 hrs | 0 days | Mon 11/13/23 | Mon 11/13/23 | 131 | 133 |  | Jimmy Cox
4333 | 133 | Future Task |  |  | D641 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs (Segment III) | 40 hrs | 4 days | Tue 11/14/23 | Fri 11/17/23 | 132 | 134 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4334 | 134 | Future Task |  |  | D641 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment III) | 40 hrs | 5 days | Mon 11/20/23 | Tue 11/28/23 | 133 | 135 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4335 | 135 | Future Task |  |  | D641 | Stacey Terry |  | Create, Review and Approve Functional Design Documents (Segment III) | 50 hrs | 40 days | Wed 11/29/23 | Fri 1/26/24 | 134 | 136FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4336 | 136 | Future Task |  |  | D641 | Stacey Terry |  | Create Summary Document | 50 hrs | 11 days | Thu 1/11/24 | Fri 1/26/24 | 135FS-11 days | 137,1548SS,1592SS,1635SS+5 days,1460SS,1505 |  | Deana Metcalf,Stacey Terry,Mary Punty
4323 | 137 | Future Task |  |  | D641 | Stacey Terry | Submit | DEL D641 - Completion of Solution Design (Requirements) Segment III - Draft Submission | 0 hrs | 0 days | Fri 1/26/24 | Fri 1/26/24 | 136 | 138 |  | Stacey Terry,Joy Schneider
4324 | 138 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 1/29/24 | Fri 2/2/24 | 137 | 139 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4325 | 139 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Style Guide Review | 1 hr | 1 day | Mon 2/5/24 | Mon 2/5/24 | 138 | 140 |  | Dusti Kincl
4326 | 140 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Final Collaborative Review | 20 hrs | 5 days | Tue 2/6/24 | Mon 2/12/24 | 139 | 141 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4327 | 141 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Accenture QC | 4 hrs | 2 days | Tue 2/13/24 | Wed 2/14/24 | 140 | 142 |  | Joy Schneider
4328 | 142 | Future Task |  |  | D641 | Stacey Terry | Submit | DEL D641 - Completion of Solution Design (Requirements) Segment III - Submit | 0 hrs | 0 days | Wed 2/14/24 | Wed 2/14/24 | 141 | 143 |  | Joy Schneider
4329 | 143 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Department QC | 4 hrs | 1 day | Thu 2/15/24 | Thu 2/15/24 | 142 | 144 |  | Tommy Werner,Gabriela Gibson
4330 | 144 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Contract Manager Review | 8 hrs | 3 days | Fri 2/16/24 | Tue 2/20/24 | 143 | 145 |  | Sean Buchanan
4331 | 145 | Future Task |  |  | D641 | Stacey Terry | Accept | DEL D641 - Completion of Solution Design (Requirements) Segment III - Accept | 0 hrs | 0 days | Tue 2/20/24 | Tue 2/20/24 | 144 | 580584585 | January 2024 (Feb 2024) | Sean Buchanan
4337 | 146 | Future Task | Yes |  | D644 | Stacey Terry |  | D644 - Completion of Solution Design (Requirements) Segment IV | 337 hrs | 85 days | Mon 1/29/24 | Fri 5/24/24
4351 | 147 | Future Task |  |  | D644 | Stacey Terry |  | Identify Functional Designs (Segment IV) | 50 hrs | 10 days | Mon 1/29/24 | Fri 2/9/24 | 1 | 148 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4338 | 148 | Future Task |  |  | D644 | Stacey Terry | Create | DED D644 - Completion of Solution Design (Requirements) Segment IV - Create | 16 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 147 | 149 |  | Stacey Terry,Mary Punty
4339 | 149 | Future Task |  |  | D644 | Stacey Terry | Submit | DED D644 - Completion of Solution Design (Requirements) Segment IV - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 148 | 150 |  | Stacey Terry,Joy Schneider
4340 | 150 | Future Task |  |  | D644 | Stacey Terry | Review | DED D644 - Completion of Solution Design (Requirements) Segment IV - Collaborative Review | 24 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 149 | 151 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4341 | 151 | Future Task |  |  | D644 | Stacey Terry | Approve | DED D644 - Completion of Solution Design (Requirements) Segment IV - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 150 | 152 |  | Jimmy Cox
4352 | 152 | Future Task |  |  | D644 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs (Segment IV) | 50 hrs | 4 days | Mon 3/11/24 | Thu 3/14/24 | 151 | 153 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4353 | 153 | Future Task |  |  | D644 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment IV) | 50 hrs | 4 days | Fri 3/15/24 | Wed 3/20/24 | 152 | 154 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4354 | 154 | Future Task |  |  | D644 | Stacey Terry |  | Create, Review and Approve Functional Design Documents (Segment IV) | 50 hrs | 30 days | Thu 3/21/24 | Wed 5/1/24 | 153 | 155FS-8 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4355 | 155 | Future Task |  |  | D644 | Stacey Terry |  | Create Summary Document | 40 hrs | 8 days | Mon 4/22/24 | Wed 5/1/24 | 154FS-8 days | 156,1561SS,1605SS,1648SS+5 days,1473SS,1518SS |  | Deana Metcalf,Stacey Terry,Mary Punty
4342 | 156 | Future Task |  |  | D644 | Stacey Terry | Submit | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Draft Submission | 0 hrs | 0 days | Wed 5/1/24 | Wed 5/1/24 | 155 | 157 |  | Stacey Terry,Joy Schneider
4343 | 157 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Pre-Submission Collaborative Review | 20 hrs | 5 days | Thu 5/2/24 | Wed 5/8/24 | 156 | 158584 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4344 | 158 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Style Guide Review | 1 hr | 1 day | Thu 5/9/24 | Thu 5/9/24 | 157 | 159 |  | Dusti Kincl
4345 | 159 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Final Collaborative Review | 20 hrs | 5 days | Fri 5/10/24 | Thu 5/16/24 | 158 | 160 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4346 | 160 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Accenture QC | 4 hrs | 2 days | Fri 5/17/24 | Mon 5/20/24 | 159 | 161 |  | Joy Schneider
4347 | 161 | Future Task |  |  | D644 | Stacey Terry | Submit | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Submit | 0 hrs | 0 days | Mon 5/20/24 | Mon 5/20/24 | 160 | 162 |  | Joy Schneider
4348 | 162 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Department QC | 4 hrs | 1 day | Tue 5/21/24 | Tue 5/21/24 | 161 | 163 |  | Tommy Werner,Gabriela Gibson
4349 | 163 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Contract Manager Review | 8 hrs | 3 days | Wed 5/22/24 | Fri 5/24/24 | 162 | 164 |  | Sean Buchanan
4350 | 164 | Future Task |  |  | D644 | Stacey Terry | Accept | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Accept | 0 hrs | 0 days | Fri 5/24/24 | Fri 5/24/24 | 163 | 580FS+24 days,585 | April 2024 (May 2024) | Sean Buchanan
4356 | 165 | Future Task | Yes |  | D650 | Stacey Terry |  | D650 - Completion of Solution Design (Requirements) DW/BI | 347 hrs | 160 days | Fri 3/1/24 | Tue 10/15/24
4357 | 166 | Future Task |  |  | D650 | Stacey Terry | Create | DED D650 - Completion of Solution Design (Requirements) DW/BI - Create | 16 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 1 | 167 |  | Stacey Terry,Mary Punty
4358 | 167 | Future Task |  |  | D650 | Stacey Terry | Submit | DED D650 - Completion of Solution Design (Requirements) DW/BI - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 166 | 168 |  | Stacey Terry,Joy Schneider
4359 | 168 | Future Task |  |  | D650 | Stacey Terry | Review | DED D650 - Completion of Solution Design (Requirements) DW/BI - Collaborative Review | 24 hrs | 10 days | Fri 3/15/24 | Thu 3/28/24 | 167 | 169 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4360 | 169 | Future Task |  |  | D650 | Stacey Terry | Approve | DED D650 - Completion of Solution Design (Requirements) DW/BI - Approve | 0 hrs | 0 days | Thu 3/28/24 | Thu 3/28/24 | 168 | 170 |  | Jimmy Cox
4370 | 170 | Future Task |  |  | D650 | Stacey Terry |  | Identify Functional Designs DW/BI | 50 hrs | 10 days | Fri 3/29/24 | Thu 4/11/24 | 169 | 171 |  | Stacey Terry,Yogesh Deshmukh
4371 | 171 | Future Task |  |  | D650 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs DW/BI | 50 hrs | 10 days | Fri 4/12/24 | Thu 4/25/24 | 170 | 172 |  | Stacey Terry,Yogesh Deshmukh
4372 | 172 | Future Task |  |  | D650 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs DW/BI | 50 hrs | 10 days | Fri 4/26/24 | Thu 5/9/24 | 171 | 173 |  | Stacey Terry,Yogesh Deshmukh
4373 | 173 | Future Task |  |  | D650 | Stacey Terry |  | Create, Review and Approve Functional Design Documents DW/BI | 50 hrs | 82 days | Fri 5/10/24 | Thu 9/5/24 | 172 | 174 |  | Stacey Terry,Yogesh Deshmukh
4374 | 174 | Future Task |  |  | D650 | Stacey Terry |  | Create Summary Document | 50 hrs | 11 days | Fri 9/6/24 | Fri 9/20/24 | 173 | 175 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4361 | 175 | Future Task |  |  | D650 | Stacey Terry | Submit | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Draft Submission | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 174 | 176 |  | Stacey Terry,Joy Schneider
4362 | 176 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 175 | 177 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4363 | 177 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Style Guide Review | 1 hr | 1 day | Mon 9/30/24 | Mon 9/30/24 | 176 | 178 |  | Dusti Kincl
4364 | 178 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Final Collaborative Review | 20 hrs | 5 days | Tue 10/1/24 | Mon 10/7/24 | 177 | 179 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4365 | 179 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Accenture QC | 4 hrs | 2 days | Tue 10/8/24 | Wed 10/9/24 | 178 | 180 |  | Joy Schneider
4366 | 180 | Future Task |  |  | D650 | Stacey Terry | Submit | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Submit | 0 hrs | 0 days | Wed 10/9/24 | Wed 10/9/24 | 179 | 181 |  | Joy Schneider
4367 | 181 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Department QC | 4 hrs | 1 day | Thu 10/10/24 | Thu 10/10/24 | 180 | 182 |  | Tommy Werner,Gabriela Gibson
4368 | 182 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Contract Manager Review | 8 hrs | 3 days | Fri 10/11/24 | Tue 10/15/24 | 181 | 183 |  | Sean Buchanan
4369 | 183 | Future Task |  |  | D650 | Stacey Terry | Accept | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Accept | 0 hrs | 0 days | Tue 10/15/24 | Tue 10/15/24 | 182 |  | 2024-10-01 | Sean Buchanan
4431 | 184 | Future Task |  |  | WP402 | Stacey Terry |  | WP402 - Requirements Traceability Matrix | 98 hrs | 55 days | Mon 6/5/23 | Mon 8/21/23
4432 | 185 | Future Task |  |  | WP402 | Stacey Terry | Create | WPED WP402 - Requirements Traceability Matrix - Create | 8 hrs | 5 days | Mon 6/5/23 | Fri 6/9/23 | 1FS+27 days | 186 |  | Stacey Terry,Mary Punty
4433 | 186 | Future Task |  |  | WP402 | Stacey Terry | Submit | WPED WP402 - Requirements Traceability Matrix - Submit | 0 hrs | 0 days | Fri 6/9/23 | Fri 6/9/23 | 185 | 187 |  | Joy Schneider,Stacey Terry
4434 | 187 | Future Task |  |  | WP402 | Stacey Terry | Review | WPED WP402 - Requirements Traceability Matrix - Review | 12 hrs | 5 days | Mon 6/12/23 | Fri 6/16/23 | 186 | 188 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4435 | 188 | Future Task |  |  | WP402 | Stacey Terry | Approve | WPED WP402 - Requirements Traceability Matrix - Approve | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 187 | 189 |  | Jimmy Cox
4449 | 189 | Future Task |  |  | WP402 | Stacey Terry |  | Create Requirements Traceability Matrix Template | 2 hrs | 3 days | Mon 6/19/23 | Wed 6/21/23 | 188 | 190 |  | Stacey Terry,Yogesh Deshmukh
4450 | 190 | Future Task |  |  | WP402 | Stacey Terry |  | Populate Requirements Traceability Matrix Template | 10 hrs | 5 days | Thu 6/22/23 | Wed 6/28/23 | 189 | 191 |  | Stacey Terry,Yogesh Deshmukh
4451 | 191 | Future Task |  |  | WP402 | Stacey Terry |  | Create Summary Document | 6 hrs | 2 days | Thu 6/29/23 | Fri 6/30/23 | 190 | 192 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4436 | 192 | Future Task |  |  | WP402 | Stacey Terry | Submit | WP WP402 - Requirements Traceability Matrix - Submit | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 191 | 193 |  | Joy Schneider,Stacey Terry
4437 | 193 | Future Task |  |  | WP402 | Stacey Terry | Review | WP WP402 - Requirements Traceability Matrix - Collaborative Review & Update | 20 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 192 | 194 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4438 | 194 | Future Task |  |  | WP402 | Stacey Terry | Review | WP WP402 - Requirements Traceability Matrix - Final Review & Edits | 20 hrs | 5 days | Tue 7/18/23 | Mon 7/24/23 | 193 | 195 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4439 | 195 | Future Task |  |  | WP402 | Stacey Terry | Approve | WP WP402 - Requirements Traceability Matrix - Approve | 0 hrs | 0 days | Mon 7/24/23 | Mon 7/24/23 | 194 | 373,412,431,722,196FS+5 days | 2023-06-01 | Jimmy Cox
7147 | 196 | Future Task |  |  | WP402 | Stacey Terry |  | Load Requirements in Requirements Traceability Tool | 10 hrs | 5 days | Tue 8/1/23 | Mon 8/7/23 | 195FS+5 days | 197 |  | Mary Punty,Joy Schneider
7148 | 197 | Future Task |  |  | WP402 | Stacey Terry |  | Validate Requirements in Requirements Traceability Tool | 10 hrs | 10 days | Tue 8/8/23 | Mon 8/21/23 | 196 |  |  | Deana Metcalf,Stacey Terry
4440 | 198 | Future Task |  |  | WP403 | Stacey Terry |  | WP403 - RICEFW Inventory | 200 hrs | 64 days | Mon 6/5/23 | Fri 9/1/23
4441 | 199 | Future Task |  |  | WP403 | Stacey Terry | Create | WPED WP403 - RICEFW Inventory - Create | 16 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1FS+27 days | 200 |  | Stacey Terry,Mary Punty
4442 | 200 | Future Task |  |  | WP403 | Stacey Terry | Submit | WPED WP403 - RICEFW Inventory - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 199 | 201 |  | Joy Schneider,Stacey Terry
4443 | 201 | Future Task |  |  | WP403 | Stacey Terry | Review | WPED WP403 - RICEFW Inventory - Review | 24 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 200 | 202 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4444 | 202 | Future Task |  |  | WP403 | Stacey Terry | Approve | WPED WP403 - RICEFW Inventory - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 201 | 203 |  | Jimmy Cox
4454 | 203 | Future Task |  |  | WP403 | Stacey Terry |  | Create RICEFW Inventory Template | 20 hrs | 5 days | Mon 7/3/23 | Mon 7/10/23 | 202 | 204 |  | Deana Metcalf,Stacey Terry
4455 | 204 | Future Task |  |  | WP403 | Stacey Terry |  | Define and document RICEFW Inventory | 50 hrs | 14 days | Tue 7/11/23 | Fri 7/28/23 | 203 | 205 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4456 | 205 | Future Task |  |  | WP403 | Stacey Terry |  | Populate RICEFW Inventory Template | 20 hrs | 5 days | Mon 7/31/23 | Fri 8/4/23 | 204 | 206 |  | Deana Metcalf,Stacey Terry
4457 | 206 | Future Task |  |  | WP403 | Stacey Terry |  | Create Summary Document | 30 hrs | 5 days | Mon 8/7/23 | Fri 8/11/23 | 205 | 207 |  | Deana Metcalf,Stacey Terry,Mary Punty
4445 | 207 | Future Task |  |  | WP403 | Stacey Terry | Submit | WP WP403 - RICEFW Inventory - Submit | 0 hrs | 0 days | Fri 8/11/23 | Fri 8/11/23 | 206 | 208 |  | Joy Schneider,Stacey Terry
4446 | 208 | Future Task |  |  | WP403 | Stacey Terry | Review | WP WP403 - RICEFW Inventory - Collaborative Review & Update | 20 hrs | 10 days | Mon 8/14/23 | Fri 8/25/23 | 207 | 209 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4447 | 209 | Future Task |  |  | WP403 | Stacey Terry | Review | WP WP403 - RICEFW Inventory - Final Review & Edits | 20 hrs | 5 days | Mon 8/28/23 | Fri 9/1/23 | 208 | 210 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4448 | 210 | Future Task |  |  | WP403 | Stacey Terry | Approve | WP WP403 - RICEFW Inventory - Approve | 0 hrs | 0 days | Fri 9/1/23 | Fri 9/1/23 | 209 |  | 2024-04-01 | Jimmy Cox
5667 | 211 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | WP404 - Data Conversion Inventory | 250 hrs | 108 days | Fri 9/1/23 | Thu 2/8/24
5668 | 212 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WPED WP404 - Data Conversion Inventory - Create | 16 hrs | 10 days | Fri 9/1/23 | Fri 9/15/23 | 1FS+90 days | 213 |  | Manojkumar Gurjar,Kurt Meisner
5669 | 213 | Future Task |  |  | WP404 | Manojkumar Gurjar | Submit | WPED WP404 - Data Conversion Inventory - Submit | 0 hrs | 0 days | Fri 9/15/23 | Fri 9/15/23 | 212 | 214 |  | Manojkumar Gurjar,Joy Schneider
5670 | 214 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WPED WP404 - Data Conversion Inventory - Review | 24 hrs | 10 days | Mon 9/18/23 | Fri 9/29/23 | 213 | 215 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5671 | 215 | Future Task |  |  | WP404 | Manojkumar Gurjar | Approve | WPED WP404 - Data Conversion Inventory - Approve | 0 hrs | 0 days | Fri 9/29/23 | Fri 9/29/23 | 214 | 216 |  | Jimmy Cox
5672 | 216 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | Create Data Conversion Inventory Template | 50 hrs | 32 days | Mon 10/2/23 | Wed 11/15/23 | 215,47 | 217 |  | Manojkumar Gurjar,Kurt Meisner
5673 | 217 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | Populate Data Conversion Inventory with RICEFW Inventory conversion items | 50 hrs | 16 days | Thu 11/16/23 | Mon 12/11/23 | 216 | 218 |  | Manojkumar Gurjar,Kurt Meisner
5674 | 218 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | Identify/confirm Anticipated Source Systems and Legacy Tables | 50 hrs | 20 days | Tue 12/12/23 | Wed 1/10/24 | 217 | 219 |  | Kurt Meisner,Manojkumar Gurjar
5675 | 219 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | Create Data Conversion Inventory Summary Document | 20 hrs | 5 days | Thu 1/11/24 | Thu 1/18/24 | 218 | 220 |  | Manojkumar Gurjar,Kurt Meisner
5676 | 220 | Future Task |  |  | WP404 | Manojkumar Gurjar | Submit | WP WP404 - Data Conversion Inventory - Submit | 0 hrs | 0 days | Thu 1/18/24 | Thu 1/18/24 | 219 | 221 |  | Manojkumar Gurjar,Joy Schneider
5677 | 221 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WP WP404 - Data Conversion Inventory - Collaborative Review & Update | 20 hrs | 10 days | Fri 1/19/24 | Thu 2/1/24 | 220 | 222 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5678 | 222 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WP WP404 - Data Conversion Inventory - Final Review & Edits | 20 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 221 | 223 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5679 | 223 | Future Task |  |  | WP404 | Manojkumar Gurjar | Approve | WP WP404 - Data Conversion Inventory - Approve | 0 hrs | 0 days | Thu 2/8/24 | Thu 2/8/24 | 222 |  | 2024-01-01 | Jimmy Cox
4458 | 224 | Future Task | Yes |  | WP405 | Stacey Terry |  | WP405 - Security Roles Matrix | 280 hrs | 85 days | Mon 4/1/24 | Tue 7/30/24
4459 | 225 | Future Task |  |  | WP405 | Stacey Terry | Create | WPED WP405 - Security Roles Matrix - Create | 16 hrs | 10 days | Mon 4/1/24 | Fri 4/12/24 | 1 | 226 |  | Stacey Terry,Mary Punty | Can we begin/create this (the DED) earlier? | Angie
4460 | 226 | Future Task |  |  | WP405 | Stacey Terry | Submit | WPED WP405 - Security Roles Matrix - Submit | 0 hrs | 0 days | Fri 4/12/24 | Fri 4/12/24 | 225 | 227 |  | Joy Schneider,Stacey Terry
4461 | 227 | Future Task |  |  | WP405 | Stacey Terry | Review | WPED WP405 - Security Roles Matrix - Review | 24 hrs | 10 days | Mon 4/15/24 | Fri 4/26/24 | 226 | 228 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4462 | 228 | Future Task |  |  | WP405 | Stacey Terry | Approve | WPED WP405 - Security Roles Matrix - Approve | 0 hrs | 0 days | Fri 4/26/24 | Fri 4/26/24 | 227 | 229 |  | Jimmy Cox
4467 | 229 | Future Task |  |  | WP405 | Stacey Terry |  | Create Security Roles Matrix Template | 20 hrs | 5 days | Mon 4/29/24 | Fri 5/3/24 | 228 | 230 |  | Stacey Terry,Yogesh Deshmukh
4468 | 230 | Future Task |  |  | WP405 | Stacey Terry |  | Design, Review, and Confirm Security Roles Matrix | 50 hrs | 20 days | Mon 5/6/24 | Mon 6/3/24 | 229 | 231 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4469 | 231 | Future Task |  |  | WP405 | Stacey Terry |  | Finalize Security Roles Matrix Design | 50 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 230 | 232 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4470 | 232 | Future Task |  |  | WP405 | Stacey Terry |  | Configure Security Roles and Permission Lists | 50 hrs | 15 days | Tue 6/11/24 | Mon 7/1/24 | 231 | 233 |  | Manojkumar Gurjar,Paul Jureidini
4471 | 233 | Future Task |  |  | WP405 | Stacey Terry |  | Create Security Roles Matrix Summary Document | 30 hrs | 5 days | Tue 7/2/24 | Tue 7/9/24 | 232 | 234 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4463 | 234 | Future Task |  |  | WP405 | Stacey Terry | Submit | WP WP405 - Security Roles Matrix - Submit | 0 hrs | 0 days | Tue 7/9/24 | Tue 7/9/24 | 233 | 235 |  | Joy Schneider,Stacey Terry
4464 | 235 | Future Task |  |  | WP405 | Stacey Terry | Review | WP WP405 - Security Roles Matrix - Collaborative Review & Update | 20 hrs | 10 days | Wed 7/10/24 | Tue 7/23/24 | 234 | 236 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4465 | 236 | Future Task |  |  | WP405 | Stacey Terry | Review | WP WP405 - Security Roles Matrix - Final Review & Edits | 20 hrs | 5 days | Wed 7/24/24 | Tue 7/30/24 | 235 | 237 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4466 | 237 | Future Task |  |  | WP405 | Stacey Terry | Approve | WP WP405 - Security Roles Matrix - Approve | 0 hrs | 0 days | Tue 7/30/24 | Tue 7/30/24 | 236 | 579 | 2024-07-01 | Jimmy Cox
5680 | 238 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | WP411 - Batch and Interface Procedures | 109 hrs | 92 days | Wed 10/30/24 | Fri 3/14/25
5681 | 239 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WPED WP411 - Batch and Interface Procedures - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1 | 240 |  | Manojkumar Gurjar,Kurt Meisner
5682 | 240 | Future Task |  |  | WP411 | Manojkumar Gurjar | Submit | WPED WP411 - Batch and Interface Procedures - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 239 | 241 |  | Manojkumar Gurjar,Joy Schneider
5683 | 241 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WPED WP411 - Batch and Interface Procedures - Review | 24 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 240 | 242 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5684 | 242 | Future Task |  |  | WP411 | Manojkumar Gurjar | Approve | WPED WP411 - Batch and Interface Procedures - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 241 | 243 |  | Jimmy Cox
6701 | 243 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | Define Interface Procedures | 3 hrs | 28 days | Mon 12/2/24 | Fri 1/10/25 | 242 | 244 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
6702 | 244 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | Create Batch Flow Diagram | 6 hrs | 9 days | Mon 1/13/25 | Fri 1/24/25 | 243 | 245 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
6703 | 245 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | Create Batch and Interface Procedures Document | 20 hrs | 20 days | Mon 1/27/25 | Fri 2/21/25 | 244 | 246 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
5685 | 246 | Future Task |  |  | WP411 | Manojkumar Gurjar | Submit | WP WP411 - Batch and Interface Procedures - Submit | 0 hrs | 0 days | Fri 2/21/25 | Fri 2/21/25 | 245 | 247 |  | Manojkumar Gurjar,Joy Schneider
5686 | 247 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WP WP411 - Batch and Interface Procedures - Collaborative Review & Update | 20 hrs | 10 days | Mon 2/24/25 | Fri 3/7/25 | 246 | 248 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5687 | 248 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WP WP411 - Batch and Interface Procedures - Final Review & Edits | 20 hrs | 5 days | Mon 3/10/25 | Fri 3/14/25 | 247 | 249 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5688 | 249 | Future Task |  |  | WP411 | Manojkumar Gurjar | Approve | WP WP411 - Batch and Interface Procedures - Approve | 0 hrs | 0 days | Fri 3/14/25 | Fri 3/14/25 | 248 |  |  | Jimmy Cox
6596 | 250 | Late | Yes |  | I-WP101 | Deana Metcalf |  | I-WP101 Update Financials BPMs | 1,336 hrs | 294 days | Wed 4/26/23 | Mon 6/24/24
6597 | 251 | Late |  |  | I-WP101 | Deana Metcalf | Create | Identify BPMs by module | 6 hrs | 3 days | Wed 4/26/23 | Fri 4/28/23 | 1 | 258259 |  | Deana Metcalf,Stacey Terry,Tiffany Porter,Janice Jackson,Brendan Jones
6598 | 252 | Late |  |  | I-WP101 | Deana Metcalf |  | WPED - I-WP101 Update Financials BPMs | 1,072 hrs | 274 days | Mon 5/1/23 | Thu 5/30/24
6599 | 253 | On Schedule |  |  | I-WP101 | Deana Metcalf | Create | WPED - I-WP101 Update Financials BPMs - Create | 8 hrs | 2 days | Fri 5/26/23 | Tue 5/30/23 | 1 | 254 |  | Deana Metcalf
6600 | 254 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | WPED - I-WP101 Update Financials BPMs - Submit | 0 hrs | 0 days | Tue 5/30/23 | Tue 5/30/23 | 253 | 255 |  | Deana Metcalf
6601 | 255 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WPED - I-WP101 Update Financials BPMs - Collaborative Review and Update | 10 hrs | 8 days | Wed 5/31/23 | Fri 6/9/23 | 254 | 256 |  | Tiffany Porter,Janice Jackson,Brendan Jones,Angie Robertson,Jimmy Cox,Tommy Werner
6602 | 256 | Future Task |  |  | I-WP101 | Deana Metcalf | Approve | WPED - I-WP101 Update Financials BPMs - Approve | 0 hrs | 0 days | Fri 6/9/23 | Fri 6/9/23 | 255 |  |  | Jimmy Cox
6603 | 257 | Late |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 1 - Financials Wave Business Process Models | 176 hrs | 86 days | Mon 5/1/23 | Wed 8/30/23
6604 | 258 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - May | 20 hrs | 22 days | Mon 5/1/23 | Wed 5/31/23 | 251 | 260 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6605 | 259 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - May | 20 hrs | 22 days | Mon 5/1/23 | Wed 5/31/23 | 251 | 261 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6606 | 260 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - June | 20 hrs | 22 days | Thu 6/1/23 | Fri 6/30/23 | 258 | 262 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6607 | 261 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - June | 20 hrs | 22 days | Thu 6/1/23 | Fri 6/30/23 | 259 | 263 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6608 | 262 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - July | 20 hrs | 20 days | Mon 7/3/23 | Mon 7/31/23 | 260 | 264 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6609 | 263 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - July | 20 hrs | 20 days | Mon 7/3/23 | Mon 7/31/23 | 261 | 264 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6610 | 264 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 1 - Submit | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 262263 | 265270271272 |  | Deana Metcalf
6611 | 265 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Financials Wave Business Process Models - Segment 1 - Collaborative Review and Update | 20 hrs | 4 days | Tue 8/1/23 | Fri 8/4/23 | 264 | 266 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6789 | 266 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Financials Wave Business Process Models - Segment 1 - Advisory Council Review and Updates | 14 hrs | 12 days | Mon 8/7/23 | Tue 8/22/23 | 265 | 267 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson,Dusti Kincl
6612 | 267 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Financials Wave Business Process Models - Segment 1 - Style Guide Updates | 2 hrs | 1 day | Wed 8/23/23 | Wed 8/23/23 | 266 | 268 |  | Dusti Kincl
6613 | 268 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Financials Wave Business Process Models - Segment 1 - Final Review and Update | 20 hrs | 5 days | Thu 8/24/23 | Wed 8/30/23 | 267 | 323 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6614 | 269 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 2 - Financials Wave Business Process Models | 274 hrs | 210 days | Tue 8/1/23 | Thu 5/30/24
6615 | 270 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - August | 20 hrs | 23 days | Tue 8/1/23 | Thu 8/31/23 | 264 | 273 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6616 | 271 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - August | 20 hrs | 23 days | Tue 8/1/23 | Thu 8/31/23 | 264 | 274 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6617 | 272 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - August | 20 hrs | 23 days | Tue 8/1/23 | Thu 8/31/23 | 264 | 275 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6618 | 273 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - September | 20 hrs | 20 days | Fri 9/1/23 | Fri 9/29/23 | 270 | 276279280 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6619 | 274 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - September | 20 hrs | 20 days | Fri 9/1/23 | Fri 9/29/23 | 271 | 277 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6620 | 275 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - September | 20 hrs | 20 days | Fri 9/1/23 | Fri 9/29/23 | 272 | 278 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6621 | 276 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - October | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 273 | 281 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6622 | 277 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - October | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 274 | 281 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6623 | 278 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - October | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 275 | 281 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6624 | 279 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment LMC models Impacted by Segment 2 | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 273 | 281 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6625 | 280 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment PPA models Impacted by Segment 2 | 20 hrs | 20 days | Mon 10/2/23 | Fri 10/27/23 | 273 | 281 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6626 | 281 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 2 - Submit | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 276277278279280 | 282,287FS+2 days,288FS+2 days,289FS+2 days |  | Deana Metcalf
6627 | 282 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Collaborative Review and Update | 20 hrs | 5 days | Mon 10/30/23 | Fri 11/3/23 | 281 | 283 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6790 | 283 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Advisory Council Review and Updates | 20 hrs | 11 days | Mon 11/6/23 | Tue 11/21/23 | 282 | 284 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6628 | 284 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 1 - Style Guide Updates | 2 hrs | 1 day | Wed 5/22/24 | Wed 5/22/24 | 283301319 | 285 |  | Dusti Kincl | This date seems off. It should be November 21st or 22nd of 2023. Also, the title says "Segment I" instead of "Segment II". | Angie
6629 | 285 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Final Review and Update | 12 hrs | 5 days | Thu 5/23/24 | Thu 5/30/24 | 284 | 323 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6630 | 286 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 3 - Financials Wave Business Process Models | 302 hrs | 145 days | Wed 11/1/23 | Thu 5/30/24
6631 | 287 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - November | 20 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23 | 281FS+2 days | 290 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6632 | 288 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - November | 20 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23 | 281FS+2 days | 291 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6633 | 289 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - November | 20 hrs | 19 days | Wed 11/1/23 | Thu 11/30/23 | 281FS+2 days | 292 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6634 | 290 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - December | 20 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23 | 287 | 293296 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6635 | 291 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - December | 20 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23 | 288 | 294297 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6636 | 292 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - December | 20 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23 | 289 | 295298 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6637 | 293 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - January | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 290 | 299 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6638 | 294 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - January | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 291 | 299 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6639 | 295 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - January | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 292 | 299 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6640 | 296 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 3 | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 290 | 299 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6641 | 297 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 3 | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 291 | 299 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6642 | 298 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 3 | 20 hrs | 18 days | Tue 1/2/24 | Fri 1/26/24 | 292 | 299 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6643 | 299 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 3 - Submit | 0 hrs | 0 days | Fri 1/26/24 | Fri 1/26/24 | 2.9329e+17 | 300,305FS+3 days,306FS+3 days,307FS+3 days |  | Deana Metcalf
6644 | 300 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Collaborative Review and Update | 20 hrs | 5 days | Mon 1/29/24 | Fri 2/2/24 | 299 | 301 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6792 | 301 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Advisory Council Review and Updates | 20 hrs | 17 days | Mon 2/5/24 | Tue 2/27/24 | 300 | 284302 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6645 | 302 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Style Guide Updates | 2 hrs | 1 day | Wed 5/22/24 | Wed 5/22/24 | 301319 | 303 |  | Dusti Kincl | This date seems off. It should be March 2024. | Angie
6646 | 303 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Final Review and Update | 20 hrs | 5 days | Thu 5/23/24 | Thu 5/30/24 | 302 | 323 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6647 | 304 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 4 - Financials Wave Business Process Models | 302 hrs | 85 days | Thu 2/1/24 | Thu 5/30/24
6648 | 305 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - February | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 299FS+3 days | 308 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6649 | 306 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - February | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 299FS+3 days | 309 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6650 | 307 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - February | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 299FS+3 days | 310 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6651 | 308 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - March | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 305 | 311314 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6652 | 309 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - March | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 306 | 312315 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6653 | 310 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - March | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 307 | 313316 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6654 | 311 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - April | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 308 | 317 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6655 | 312 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - April | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 309 | 317 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6656 | 313 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - April | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 310 | 317 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6657 | 314 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 4 | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 308 | 317 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6658 | 315 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 4 | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 309 | 317 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6659 | 316 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 4 | 20 hrs | 20 days | Mon 4/1/24 | Fri 4/26/24 | 310 | 317 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6660 | 317 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 4 - Submit | 0 hrs | 0 days | Fri 4/26/24 | Fri 4/26/24 | 3.1131e+17 | 318 |  | Deana Metcalf
6661 | 318 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Collaborative Review and Update | 20 hrs | 5 days | Mon 4/29/24 | Fri 5/3/24 | 317 | 319 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6793 | 319 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Advisory Council Review and Updates | 20 hrs | 12 days | Mon 5/6/24 | Tue 5/21/24 | 318 | 284302320 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6662 | 320 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Style Guide Updates | 2 hrs | 1 day | Wed 5/22/24 | Wed 5/22/24 | 319 | 321 |  | Dusti Kincl
6663 | 321 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Final Review and Update | 20 hrs | 5 days | Thu 5/23/24 | Thu 5/30/24 | 320 | 323 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6664 | 322 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Update Financials BPMs Review Tasks | 44 hrs | 17 days | Thu 5/30/24 | Mon 6/24/24
6665 | 323 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | DEL - I-WP101 Update Financials BPMs - Submit | 0 hrs | 0 days | Thu 5/30/24 | Thu 5/30/24 | 268285303321 | 324 |  | Deana Metcalf | These should say "WP" as the first word in the title, not "DEL" | Angie
6666 | 324 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | DEL - I-WP101 Update Financials BPMs - Dept QC | 2 hrs | 1 day | Fri 5/31/24 | Fri 5/31/24 | 323 | 325 |  | Gabriela Gibson | These should say "WP" as the first word in the title, not "DEL" | Angie
6667 | 325 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | DEL - I-WP101 Update Financials BPMs - Collaborative Review and Update | 20 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 324 | 326 |  | Deana Metcalf,Stacey Terry,Tiffany Porter,Janice Jackson,Brendan Jones | These should say "WP" as the first word in the title, not "DEL" | Angie
6668 | 326 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | DEL - I-WP101 Update Financials BPMs - Style Guide Review | 2 hrs | 1 day | Mon 6/17/24 | Mon 6/17/24 | 325 | 327 |  | Dusti Kincl | These should say "WP" as the first word in the title, not "DEL" | Angie
6669 | 327 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | DEL - I-WP101 Update Financials BPMs - Final Review and Update | 20 hrs | 5 days | Tue 6/18/24 | Mon 6/24/24 | 326 | 328 |  | Jimmy Cox,Angie Robertson | These should say "WP" as the first word in the title, not "DEL" | Angie
6670 | 328 | Future Task |  |  | I-WP101 | Deana Metcalf | Approve | DEL - I-WP101 Update Financials BPMs - Approve | 0 hrs | 0 days | Mon 6/24/24 | Mon 6/24/24 | 327 |  |  | Jimmy Cox | These should say "WP" as the first word in the title, not "DEL" | Angie
6671 | 329 | Future Task | Yes |  | I-WP125 | Deana Metcalf |  | I-WP125 - Updated D66 Chart of Accounts Design | 214 hrs | 63 days | Mon 6/5/23 | Thu 8/31/23
6672 | 330 | Future Task |  |  | I-WP125 | Deana Metcalf | Create | WPED - I-WP125 - Update D66 Chart of Accounts Design - Create | 2 hrs | 10 days | Mon 6/5/23 | Fri 6/16/23 | 1 | 331 |  | Deana Metcalf
6673 | 331 | Future Task |  |  | I-WP125 | Deana Metcalf | Submit | WPED - I-WP125 - Update D66 Chart of Accounts Design - Submit | 0 hrs | 0 days | Fri 6/16/23 | Fri 6/16/23 | 330 | 332 |  | Deana Metcalf
6674 | 332 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WPED - I-WP125 - Update D66 Chart of Accounts Design - Collaborative Review and Update | 8 hrs | 10 days | Mon 6/19/23 | Fri 6/30/23 | 331 | 333 |  | Janice Jackson,LaWanda Warren,Robert Hicks,Tommy Werner
6675 | 333 | Future Task |  |  | I-WP125 | Deana Metcalf | Approve | WPED - I-WP125 - Update D66 Chart of Accounts Design - Approve | 0 hrs | 0 days | Fri 6/30/23 | Fri 6/30/23 | 332 | 334 |  | Angie Robertson,Jimmy Cox
6676 | 334 | Future Task |  |  | I-WP125 | Deana Metcalf | Create | I-WP125 Update D66 Chart of Accounts Design <Activities per WPED> | 100 hrs | 26 days | Mon 7/3/23 | Tue 8/8/23 | 333 | 335 |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp
6677 | 335 | Future Task |  |  | I-WP125 | Deana Metcalf | Submit | I-WP125 Update D66 Chart of Accounts Design - Submit | 0 hrs | 0 days | Tue 8/8/23 | Tue 8/8/23 | 334 | 336 |  | Janice Jackson
6678 | 336 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | I-WP125 Update D66 Chart of Accounts Design - Dept QC | 1 hr | 1 day | Wed 8/9/23 | Wed 8/9/23 | 335 | 337 |  | Gabriela Gibson
6679 | 337 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | I-WP125Update D66 Chart of Accounts Design - Collaborative Review and Update | 100 hrs | 10 days | Thu 8/10/23 | Wed 8/23/23 | 336 | 338 |  | Deana Metcalf,Janice Jackson,Jennifer Reeves,Angie Robertson
6680 | 338 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | I-WP125 Update D66 Chart of Accounts Design - Style Guide Review | 1 hr | 1 day | Thu 8/24/23 | Thu 8/24/23 | 337 | 339 |  | Tatiana Eubanks
6681 | 339 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | I-WP125 Update D66 Chart of Accounts Design - Final Review and Update | 2 hrs | 5 days | Fri 8/25/23 | Thu 8/31/23 | 338 | 340 |  | Angie Robertson,Jimmy Cox
6682 | 340 | Future Task |  |  | I-WP125 | Deana Metcalf | Approve | I-WP125 Update D66 Chart of Accounts Design - Approve | 0 hrs | 0 days | Thu 8/31/23 | Thu 8/31/23 | 339 |  |  | Jimmy Cox
6795 | 341 | Future Task |  |  | I-WP120 | Deana Metcalf |  | I-WP120 - Knowledge Base Plan | 38 hrs | 49 days | Tue 5/30/23 | Mon 8/7/23
6796 | 342 | Future Task |  |  | I-WP120 | Deana Metcalf | Create | WPED- I-WP120 - Knowledge Base Plan - Create | 2 hrs | 9 days | Tue 5/30/23 | Fri 6/9/23 | 1 | 343 |  | Daylin Reyes,Matthew Breeding,Jennifer Reeves,Nikki Klein,Carolyn Hicks,Kimberly Kemp
6797 | 343 | Future Task |  |  | I-WP120 | Deana Metcalf | Submit | WPED- I-WP120 - Knowledge Base Plan - Submit | 0 hrs | 0 days | Fri 6/9/23 | Fri 6/9/23 | 342 | 344 |  | Daylin Reyes
6798 | 344 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WPED- I-WP120 - Knowledge Base Plan - Review | 8 hrs | 9 days | Mon 6/12/23 | Thu 6/22/23 | 343 | 345 |  | Tommy Werner,Angie Robertson,Jimmy Cox,Deana Metcalf,Matthew Breeding,Jennifer Reeves
6799 | 345 | Future Task |  |  | I-WP120 | Deana Metcalf | Approve | WPED- I-WP120 - Knowledge Base Plan - Approve | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 344 | 346 |  | Jimmy Cox
6800 | 346 | Future Task |  |  | I-WP120 | Deana Metcalf | Create | WP- I-WP120 - Knowledge Base Plan - Create | 20 hrs | 15 days | Fri 6/23/23 | Fri 7/14/23 | 345 | 347 |  | Daylin Reyes,Matthew Breeding,Jennifer Reeves,Nikki Klein,Carolyn Hicks,Kimberly Kemp
6801 | 347 | Future Task |  |  | I-WP120 | Deana Metcalf | Submit | WP- I-WP120 - Knowledge Base Plan - Submit | 0 hrs | 0 days | Fri 7/14/23 | Fri 7/14/23 | 346 | 348 |  | Daylin Reyes
6802 | 348 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WP- I-WP120 - Knowledge Base Plan - Department QC | 1 hr | 1 day | Mon 7/17/23 | Mon 7/17/23 | 347 | 349 |  | Tommy Werner
6803 | 349 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WP- I-WP120 - Knowledge Base Plan - Collaborative Review & Update | 4 hrs | 9 days | Tue 7/18/23 | Fri 7/28/23 | 348 | 350 |  | Deana Metcalf,Angie Robertson,Jimmy Cox,Matthew Breeding,Jennifer Reeves
6804 | 350 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WP- I-WP120 - Knowledge Base Plan - Style Guide Review | 1 hr | 1 day | Mon 7/31/23 | Mon 7/31/23 | 349 | 351 |  | Dusti Kincl
6805 | 351 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WP- I-WP120 - Knowledge Base Plan - Final Review & Edits | 2 hrs | 5 days | Tue 8/1/23 | Mon 8/7/23 | 350 | 352 |  | Angie Robertson,Jimmy Cox
6806 | 352 | Future Task |  |  | I-WP120 | Deana Metcalf | Approve | WP- I-WP120 - Knowledge Base Plan - Approve | 0 hrs | 0 days | Mon 8/7/23 | Mon 8/7/23 | 351 |  |  | Jimmy Cox
3770 | 353 | Future Task | [5 empty] | Build | 2,496 hrs | 598 days | Mon 8/7/23 | Fri 12/19/25
5534 | 354 | Future Task | Yes |  | D642 | Jarad Hermann |  | D642 - Updated Technical Architecture Design | 169 hrs | 77 days | Wed 10/4/23 | Fri 1/26/24
5535 | 355 | Future Task |  |  | D642 | Jarad Hermann | Create | DED D642 - Updated Technical Architecture Design - Create | 8 hrs | 10 days | Wed 10/4/23 | Tue 10/17/23 | 1FS+112 days | 356 |  | Jarad Hermann,Manojkumar Gurjar | Can we begin/create this (the DED) earlier? | Angie
5536 | 356 | Future Task |  |  | D642 | Jarad Hermann | Submit | DED D642 - Updated Technical Architecture Design - Submit | 0 hrs | 0 days | Tue 10/17/23 | Tue 10/17/23 | 355 | 357 |  | Jarad Hermann,Joy Schneider
5537 | 357 | Future Task |  |  | D642 | Jarad Hermann | Review | DED D642 - Updated Technical Architecture Design - Collaborative Review | 24 hrs | 10 days | Wed 10/18/23 | Tue 10/31/23 | 356 | 358 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5538 | 358 | Future Task |  |  | D642 | Jarad Hermann | Approve | DED D642 - Updated Technical Architecture Design - Approve | 0 hrs | 0 days | Tue 10/31/23 | Tue 10/31/23 | 357 | 359 |  | Jimmy Cox
5539 | 359 | Future Task |  |  | D642 | Jarad Hermann |  | Confirm content to be migrated from D80 | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 358 | 360SS,361SS,362SS |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5540 | 360 | Future Task |  |  | D642 | Jarad Hermann |  | Review, update, and document run time architecture design | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 359SS | 363 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5541 | 361 | Future Task |  |  | D642 | Jarad Hermann |  | Review, update, and document development and operational architecture design | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 359SS | 363 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5542 | 362 | Future Task |  |  | D642 | Jarad Hermann |  | Review, update, and document architecture blueprint diagrams | 20 hrs | 40 days | Wed 11/1/23 | Tue 1/2/24 | 359SS | 363 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5543 | 363 | Future Task |  |  | D642 | Jarad Hermann | Submit | DEL D642 - Updated Technical Architecture Design - Draft Submission | 0 hrs | 0 days | Tue 1/2/24 | Tue 1/2/24 | 362360361 | 364 |  | Jarad Hermann,Joy Schneider
5544 | 364 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Pre-Submission Collaborative Review | 20 hrs | 5 days | Wed 1/3/24 | Tue 1/9/24 | 363 | 365 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
5545 | 365 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Style Guide Review | 1 hr | 1 day | Wed 1/10/24 | Wed 1/10/24 | 364 | 366 |  | Dusti Kincl
5546 | 366 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Final Collaborative Review | 20 hrs | 5 days | Thu 1/11/24 | Thu 1/18/24 | 365 | 367 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
5547 | 367 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Accenture QC | 4 hrs | 2 days | Fri 1/19/24 | Mon 1/22/24 | 366 | 368 |  | Joy Schneider
5548 | 368 | Future Task |  |  | D642 | Jarad Hermann | Submit | DEL D642 - Updated Technical Architecture Design - Submit | 0 hrs | 0 days | Mon 1/22/24 | Mon 1/22/24 | 367 | 369 |  | Joy Schneider
5549 | 369 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Department QC | 4 hrs | 1 day | Tue 1/23/24 | Tue 1/23/24 | 368 | 370 |  | Tommy Werner,Gabriela Gibson
5550 | 370 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Contract Manager Review | 8 hrs | 3 days | Wed 1/24/24 | Fri 1/26/24 | 369 | 371 |  | Sean Buchanan
5551 | 371 | Future Task |  |  | D642 | Jarad Hermann | Accept | DEL D642 - Updated Technical Architecture Design - Accept | 0 hrs | 0 days | Fri 1/26/24 | Fri 1/26/24 | 370 |  | 2024-03-01 | Sean Buchanan
4486 | 372 | Future Task | Yes |  | D646 | Manojkumar Gurjar |  | D646 - Completion of Build Segment I | 257 hrs | 137 days | Fri 10/13/23 | Tue 4/30/24
4487 | 373 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | DED D646 - Completion of Build Segment I - Create | 16 hrs | 10 days | Fri 10/13/23 | Thu 10/26/23 | 195 | 374 |  | Manojkumar Gurjar,Kurt Meisner | Can we begin/create this (the DED) earlier? | Angie
4488 | 374 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DED D646 - Completion of Build Segment I - Submit | 0 hrs | 0 days | Thu 10/26/23 | Thu 10/26/23 | 373 | 375 |  | Manojkumar Gurjar,Joy Schneider
4489 | 375 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DED D646 - Completion of Build Segment I - Collaborative Review | 24 hrs | 10 days | Fri 10/27/23 | Thu 11/9/23 | 374 | 376 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4490 | 376 | Future Task |  |  | D646 | Manojkumar Gurjar | Approve | DED D646 - Completion of Build Segment I - Approve | 0 hrs | 0 days | Thu 11/9/23 | Thu 11/9/23 | 375 | 377 |  | Jimmy Cox
4500 | 377 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment I | 20 hrs | 8 days | Mon 11/13/23 | Wed 11/22/23 | 376 | 378 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4501 | 378 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment I | 20 hrs | 5 days | Mon 11/27/23 | Fri 12/1/23 | 377 | 379 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4502 | 379 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment I | 20 hrs | 10 days | Mon 12/4/23 | Fri 12/15/23 | 378 | 380 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4503 | 380 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Conduct Kick-Off meeting for Build Segment I | 20 hrs | 9 days | Mon 12/18/23 | Fri 12/29/23 | 379 | 381 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4504 | 381 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I - Group 1 | 20 hrs | 21 days | Tue 1/2/24 | Wed 1/31/24 | 380 | 382 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4505 | 382 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I - Group 2 | 20 hrs | 21 days | Thu 2/1/24 | Thu 2/29/24 | 381 | 383 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4506 | 383 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I - Group 3 | 20 hrs | 21 days | Fri 3/1/24 | Fri 3/29/24 | 382 | 384FS-5 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4507 | 384 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Create Summary Document for Build Segment I | 20 hrs | 10 days | Mon 3/25/24 | Fri 4/5/24 | 383FS-5 days | 385 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4491 | 385 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DEL D646 - Completion of Build Segment I - Draft Submission | 0 hrs | 0 days | Fri 4/5/24 | Fri 4/5/24 | 384 | 386 |  | Manojkumar Gurjar,Joy Schneider
4492 | 386 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 4/8/24 | Fri 4/12/24 | 385 | 387 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4493 | 387 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Style Guide Review | 1 hr | 1 day | Mon 4/15/24 | Mon 4/15/24 | 386 | 388 |  | Dusti Kincl
4494 | 388 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Final Collaborative Review | 20 hrs | 5 days | Tue 4/16/24 | Mon 4/22/24 | 387 | 389 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4495 | 389 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Accenture QC | 4 hrs | 2 days | Tue 4/23/24 | Wed 4/24/24 | 388 | 390 |  | Joy Schneider
4496 | 390 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DEL D646 - Completion of Build Segment I - Submit | 0 hrs | 0 days | Wed 4/24/24 | Wed 4/24/24 | 389 | 391 |  | Joy Schneider
4497 | 391 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Department QC | 4 hrs | 1 day | Thu 4/25/24 | Thu 4/25/24 | 390 | 392 |  | Tommy Werner,Gabriela Gibson
4498 | 392 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Contract Manager Review | 8 hrs | 3 days | Fri 4/26/24 | Tue 4/30/24 | 391 | 393 |  | Sean Buchanan
4499 | 393 | Future Task |  |  | D646 | Manojkumar Gurjar | Accept | DEL D646 - Completion of Build Segment I - Accept | 0 hrs | 0 days | Tue 4/30/24 | Tue 4/30/24 | 392 | 584585 | 2024-04-01 | Sean Buchanan
4629 | 394 | Future Task | Yes |  | D647 | Manojkumar Gurjar |  | D647 - Establish DW/BI Environments | 149 hrs | 96 days | Thu 12/7/23 | Tue 4/23/24
4630 | 395 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | DED D647 - Establish DW/BI Environments - Create | 8 hrs | 10 days | Thu 12/7/23 | Wed 12/20/23 | 1 | 396 |  | Jarad Hermann,Manojkumar Gurjar
4631 | 396 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DED D647 - Establish DW/BI Environments - Submit | 0 hrs | 0 days | Wed 12/20/23 | Wed 12/20/23 | 395 | 397 |  | Manojkumar Gurjar,Joy Schneider
4632 | 397 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DED D647 - Establish DW/BI Environments - Collaborative Review | 24 hrs | 10 days | Thu 12/21/23 | Fri 1/5/24 | 396 | 398 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4633 | 398 | Future Task |  |  | D647 | Manojkumar Gurjar | Approve | DED D647 - Establish DW/BI Environments - Approve | 0 hrs | 0 days | Fri 1/5/24 | Fri 1/5/24 | 397 | 399 |  | Jimmy Cox
4643 | 399 | Future Task |  |  | D647 | Manojkumar Gurjar |  | Establish DW/BI Environment Connections | 20 hrs | 19 days | Mon 1/8/24 | Fri 2/2/24 | 398 | 400 |  | Jarad Hermann,Manojkumar Gurjar
4644 | 400 | Future Task |  |  | D647 | Manojkumar Gurjar |  | Environment build and stand up | 20 hrs | 20 days | Mon 2/5/24 | Fri 3/1/24 | 399 | 401 |  | Jarad Hermann,Manojkumar Gurjar
4645 | 401 | Future Task |  |  | D647 | Manojkumar Gurjar |  | Verify access to DW/BI Environments | 20 hrs | 20 days | Mon 3/4/24 | Fri 3/29/24 | 400 | 402 |  | Jarad Hermann,Manojkumar Gurjar
4634 | 402 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DEL D647 - Establish DW/BI Environments - Draft Submission | 0 hrs | 0 days | Fri 3/29/24 | Fri 3/29/24 | 401 | 403 |  | Manojkumar Gurjar,Joy Schneider
4635 | 403 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 4/1/24 | Fri 4/5/24 | 402 | 404 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
4636 | 404 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Style Guide Review | 1 hr | 1 day | Mon 4/8/24 | Mon 4/8/24 | 403 | 405 |  | Dusti Kincl
4637 | 405 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Final Collaborative Review | 20 hrs | 5 days | Tue 4/9/24 | Mon 4/15/24 | 404 | 406 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
4638 | 406 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Accenture QC | 4 hrs | 2 days | Tue 4/16/24 | Wed 4/17/24 | 405 | 407 |  | Joy Schneider
4639 | 407 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DEL D647 - Establish DW/BI Environments - Submit | 0 hrs | 0 days | Wed 4/17/24 | Wed 4/17/24 | 406 | 408 |  | Joy Schneider
4640 | 408 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Department QC | 4 hrs | 1 day | Thu 4/18/24 | Thu 4/18/24 | 407 | 409 |  | Tommy Werner,Gabriela Gibson
4641 | 409 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Contract Manager Review | 8 hrs | 3 days | Fri 4/19/24 | Tue 4/23/24 | 408 | 410 |  | Sean Buchanan
4642 | 410 | Future Task |  |  | D647 | Manojkumar Gurjar | Accept | DEL D647 - Establish DW/BI Environments - Accept | 0 hrs | 0 days | Tue 4/23/24 | Tue 4/23/24 | 409 |  | 2024-05-01 | Sean Buchanan
4508 | 411 | Future Task | Yes |  | D648 | Manojkumar Gurjar |  | D648 - Completion of Build Segment II | 197 hrs | 90 days | Mon 3/11/24 | Tue 7/16/24
4509 | 412 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | DED D648 - Completion of Build Segment II - Create | 16 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 195 | 413 |  | Manojkumar Gurjar,Kurt Meisner
4510 | 413 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DED D648 - Completion of Build Segment II - Submit | 0 hrs | 0 days | Fri 3/22/24 | Fri 3/22/24 | 412 | 414 |  | Manojkumar Gurjar,Joy Schneider
4511 | 414 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DED D648 - Completion of Build Segment II - Collaborative Review | 24 hrs | 10 days | Mon 3/25/24 | Fri 4/5/24 | 413 | 415 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4512 | 415 | Future Task |  |  | D648 | Manojkumar Gurjar | Approve | DED D648 - Completion of Build Segment II - Approve | 0 hrs | 0 days | Fri 4/5/24 | Fri 4/5/24 | 414 | 416 |  | Jimmy Cox
4536 | 416 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment II | 20 hrs | 7 days | Mon 4/8/24 | Tue 4/16/24 | 415 | 417 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4537 | 417 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment II | 20 hrs | 8 days | Wed 4/17/24 | Fri 4/26/24 | 416 | 418 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4538 | 418 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment II - Group 1 | 20 hrs | 19 days | Mon 4/29/24 | Thu 5/23/24 | 417 | 419 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4539 | 419 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment II - Group 2 | 20 hrs | 19 days | Fri 5/24/24 | Thu 6/20/24 | 418 | 420FS-9 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4540 | 420 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Create Summary Document for Build Segment II | 20 hrs | 9 days | Mon 6/10/24 | Thu 6/20/24 | 419FS-9 days | 421 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4513 | 421 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DEL D648 - Completion of Build Segment II - Draft Submission | 0 hrs | 0 days | Thu 6/20/24 | Thu 6/20/24 | 420 | 422 |  | Manojkumar Gurjar,Joy Schneider
4514 | 422 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 6/21/24 | Thu 6/27/24 | 421 | 423 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4515 | 423 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Style Guide Review | 1 hr | 1 day | Fri 6/28/24 | Fri 6/28/24 | 422 | 424 |  | Dusti Kincl
4516 | 424 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Final Collaborative Review | 20 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 423 | 425 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4517 | 425 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Accenture QC | 4 hrs | 2 days | Tue 7/9/24 | Wed 7/10/24 | 424 | 426 |  | Joy Schneider
4518 | 426 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DEL D648 - Completion of Build Segment II - Submit | 0 hrs | 0 days | Wed 7/10/24 | Wed 7/10/24 | 425 | 427 |  | Joy Schneider
4519 | 427 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Department QC | 4 hrs | 1 day | Thu 7/11/24 | Thu 7/11/24 | 426 | 428 |  | Tommy Werner,Gabriela Gibson
4520 | 428 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Contract Manager Review | 8 hrs | 3 days | Fri 7/12/24 | Tue 7/16/24 | 427 | 429 |  | Sean Buchanan
4521 | 429 | Future Task |  |  | D648 | Manojkumar Gurjar | Accept | DEL D648 - Completion of Build Segment II - Accept | 0 hrs | 0 days | Tue 7/16/24 | Tue 7/16/24 | 428 | 585 | 2024-07-01 | Sean Buchanan
4522 | 430 | Future Task | Yes |  | D649 | Manojkumar Gurjar |  | D649 - Completion of Build Segment III | 217 hrs | 101 days | Fri 6/7/24 | Tue 10/29/24
4523 | 431 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | DED D649 - Completion of Build Segment III - Create | 16 hrs | 10 days | Fri 6/7/24 | Thu 6/20/24 | 195 | 432 |  | Manojkumar Gurjar,Kurt Meisner
4524 | 432 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DED D649 - Completion of Build Segment III - Submit | 0 hrs | 0 days | Thu 6/20/24 | Thu 6/20/24 | 431 | 433 |  | Manojkumar Gurjar,Joy Schneider
4525 | 433 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DED D649 - Completion of Build Segment III - Collaborative Review | 24 hrs | 10 days | Fri 6/21/24 | Fri 7/5/24 | 432 | 434 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4526 | 434 | Future Task |  |  | D649 | Manojkumar Gurjar | Approve | DED D649 - Completion of Build Segment III - Approve | 0 hrs | 0 days | Fri 7/5/24 | Fri 7/5/24 | 433 | 435 |  | Jimmy Cox
4541 | 435 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment III | 20 hrs | 10 days | Mon 7/8/24 | Fri 7/19/24 | 434 | 436 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4542 | 436 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment III | 20 hrs | 5 days | Mon 7/22/24 | Fri 7/26/24 | 435 | 437 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4543 | 437 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment III | 20 hrs | 10 days | Mon 7/29/24 | Fri 8/9/24 | 436 | 438 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4544 | 438 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment III - Group 1 | 20 hrs | 19 days | Mon 8/12/24 | Fri 9/6/24 | 437 | 439 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4545 | 439 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment III - Group 2 | 20 hrs | 20 days | Mon 9/9/24 | Fri 10/4/24 | 438 | 440FS-10 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4546 | 440 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Create Summary Document for Build Segment III | 20 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 439FS-10 days | 441 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4527 | 441 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DEL D649 - Completion of Build Segment III - Draft Submission | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 440 | 442 |  | Manojkumar Gurjar,Joy Schneider
4528 | 442 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 | 441 | 443 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4529 | 443 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Style Guide Review | 1 hr | 1 day | Mon 10/14/24 | Mon 10/14/24 | 442 | 444 |  | Dusti Kincl
4530 | 444 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Final Collaborative Review | 20 hrs | 5 days | Tue 10/15/24 | Mon 10/21/24 | 443 | 445 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4531 | 445 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Accenture QC | 4 hrs | 2 days | Tue 10/22/24 | Wed 10/23/24 | 444 | 446 |  | Joy Schneider
4532 | 446 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DEL D649 - Completion of Build Segment III - Submit | 0 hrs | 0 days | Wed 10/23/24 | Wed 10/23/24 | 445 | 447 |  | Joy Schneider
4533 | 447 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Department QC | 4 hrs | 1 day | Thu 10/24/24 | Thu 10/24/24 | 446 | 448 |  | Tommy Werner,Gabriela Gibson
4534 | 448 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Contract Manager Review | 8 hrs | 3 days | Fri 10/25/24 | Tue 10/29/24 | 447 | 449 |  | Sean Buchanan
4535 | 449 | Future Task |  |  | D649 | Manojkumar Gurjar | Accept | DEL D649 - Completion of Build Segment III - Accept | 0 hrs | 0 days | Tue 10/29/24 | Tue 10/29/24 | 448 | 585 | 2024-10-01 | Sean Buchanan
4547 | 450 | Future Task | Yes |  | D653 | Manojkumar Gurjar |  | D653 - Completion of Build Segment I DW/BI | 297 hrs | 147 days | Mon 6/3/24 | Thu 1/2/25
4548 | 451 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | DED D653 - Completion of Build Segment I DW/BI - Create | 16 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 1 | 452 |  | Manojkumar Gurjar,Kurt Meisner
4549 | 452 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DED D653 - Completion of Build Segment I DW/BI - Submit | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 451 | 453 |  | Manojkumar Gurjar,Joy Schneider
4550 | 453 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DED D653 - Completion of Build Segment I DW/BI - Collaborative Review | 24 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 452 | 454 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4551 | 454 | Future Task |  |  | D653 | Manojkumar Gurjar | Approve | DED D653 - Completion of Build Segment I DW/BI - Approve | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 453 | 455 |  | Jimmy Cox
4575 | 455 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment I DW/BI | 36 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 454 | 456 |  | Manojkumar Gurjar,Kurt Meisner
4576 | 456 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment I DW/BI | 20 hrs | 5 days | Mon 7/15/24 | Fri 7/19/24 | 455 | 457 |  | Manojkumar Gurjar,Kurt Meisner
4577 | 457 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment I DW/BI | 40 hrs | 10 days | Mon 7/22/24 | Fri 8/2/24 | 456 | 458 |  | Manojkumar Gurjar,Kurt Meisner
4578 | 458 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Conduct Kick-Off meeting for Build Segment I DW/BI | 40 hrs | 5 days | Mon 8/5/24 | Fri 8/9/24 | 457 | 459 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4579 | 459 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I DW/BI - Group 1 | 20 hrs | 19 days | Mon 8/12/24 | Fri 9/6/24 | 458 | 460 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4580 | 460 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I DW/BI - Group 2 | 20 hrs | 20 days | Mon 9/9/24 | Fri 10/4/24 | 459 | 461 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4581 | 461 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I DW/BI - Group 3 | 20 hrs | 20 days | Mon 10/7/24 | Fri 11/1/24 | 460 | 462 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4582 | 462 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Create Summary Document for Build Segment I DW/BI | 4 hrs | 22 days | Mon 11/4/24 | Fri 12/6/24 | 461 | 463 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4552 | 463 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DEL D653 - Completion of Build Segment I DW/BI - Draft Submission | 0 hrs | 0 days | Fri 12/6/24 | Fri 12/6/24 | 462 | 464 |  | Manojkumar Gurjar,Joy Schneider
4553 | 464 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 12/9/24 | Fri 12/13/24 | 463 | 465 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4554 | 465 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Style Guide Review | 1 hr | 1 day | Mon 12/16/24 | Mon 12/16/24 | 464 | 466 |  | Dusti Kincl
4555 | 466 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Final Collaborative Review | 20 hrs | 5 days | Tue 12/17/24 | Mon 12/23/24 | 465 | 467 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4556 | 467 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Accenture QC | 4 hrs | 2 days | Tue 12/24/24 | Thu 12/26/24 | 466 | 468 |  | Joy Schneider
4557 | 468 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DEL D653 - Completion of Build Segment I DW/BI - Submit | 0 hrs | 0 days | Thu 12/26/24 | Thu 12/26/24 | 467 | 469 |  | Joy Schneider
4558 | 469 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Department QC | 4 hrs | 1 day | Fri 12/27/24 | Fri 12/27/24 | 468 | 470 |  | Tommy Werner,Gabriela Gibson
4559 | 470 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Contract Manager Review | 8 hrs | 3 days | Mon 12/30/24 | Thu 1/2/25 | 469 | 471 |  | Sean Buchanan
4560 | 471 | Future Task |  |  | D653 | Manojkumar Gurjar | Accept | DEL D653 - Completion of Build Segment I DW/BI - Accept | 0 hrs | 0 days | Thu 1/2/25 | Thu 1/2/25 | 470 | 585 | 2025-01-01 | Sean Buchanan
4561 | 472 | Future Task | Yes |  | D654 | Manojkumar Gurjar |  | D654 - Completion of Build Segment IV | 217 hrs | 98 days | Mon 9/9/24 | Thu 1/30/25
4562 | 473 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | DED D654 - Completion of Build Segment IV - Create | 16 hrs | 10 days | Mon 9/9/24 | Fri 9/20/24 | 1 | 474 |  | Manojkumar Gurjar,Kurt Meisner
4563 | 474 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DED D654 - Completion of Build Segment IV - Submit | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 473 | 475 |  | Manojkumar Gurjar,Joy Schneider
4564 | 475 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DED D654 - Completion of Build Segment IV - Collaborative Review | 24 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 474 | 476 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4565 | 476 | Future Task |  |  | D654 | Manojkumar Gurjar | Approve | DED D654 - Completion of Build Segment IV - Approve | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 475 | 477 |  | Jimmy Cox
4583 | 477 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment IV | 20 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 476 | 478 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4584 | 478 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment IV | 20 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 477 | 479 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4585 | 479 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment IV | 20 hrs | 10 days | Mon 10/28/24 | Fri 11/8/24 | 478 | 480 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4586 | 480 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment IV - Group 1 | 20 hrs | 17 days | Tue 11/12/24 | Fri 12/6/24 | 479 | 481 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4587 | 481 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment IV - Group 2 | 20 hrs | 19 days | Mon 12/9/24 | Mon 1/6/25 | 480 | 482FS-14 days,483 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4588 | 482 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Create Summary Document for Build Segment IV | 20 hrs | 13 days | Mon 12/16/24 | Fri 1/3/25 | 481FS-14 days | 483 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4566 | 483 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DEL D654 - Completion of Build Segment IV - Draft Submission | 0 hrs | 0 days | Mon 1/6/25 | Mon 1/6/25 | 481482 | 484 |  | Manojkumar Gurjar,Joy Schneider
4567 | 484 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 1/7/25 | Mon 1/13/25 | 483 | 485 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4568 | 485 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Style Guide Review | 1 hr | 1 day | Tue 1/14/25 | Tue 1/14/25 | 484 | 486 |  | Dusti Kincl
4569 | 486 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Final Collaborative Review | 20 hrs | 5 days | Wed 1/15/25 | Wed 1/22/25 | 485 | 487 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4570 | 487 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Accenture QC | 4 hrs | 2 days | Thu 1/23/25 | Fri 1/24/25 | 486 | 488 |  | Joy Schneider
4571 | 488 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DEL D654 - Completion of Build Segment IV - Submit | 0 hrs | 0 days | Fri 1/24/25 | Fri 1/24/25 | 487 | 489 |  | Joy Schneider
4572 | 489 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Department QC | 4 hrs | 1 day | Mon 1/27/25 | Mon 1/27/25 | 488 | 490 |  | Tommy Werner,Gabriela Gibson
4573 | 490 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Contract Manager Review | 8 hrs | 3 days | Tue 1/28/25 | Thu 1/30/25 | 489 | 491 |  | Sean Buchanan
4574 | 491 | Future Task |  |  | D654 | Manojkumar Gurjar | Accept | DEL D654 - Completion of Build Segment IV - Accept | 0 hrs | 0 days | Thu 1/30/25 | Thu 1/30/25 | 490 | 585 | 2025-01-01 | Sean Buchanan
4589 | 492 | Future Task | Yes |  | D659 | Manojkumar Gurjar |  | D659 - Completion of Build Segment II DW/BI | 219 hrs | 116 days | Mon 9/9/24 | Tue 2/25/25
4590 | 493 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | DED D659 - Completion of Build Segment II DW/BI - Create | 16 hrs | 10 days | Mon 9/9/24 | Fri 9/20/24 | 1 | 494 |  | Manojkumar Gurjar,Kurt Meisner
4591 | 494 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DED D659 - Completion of Build Segment II DW/BI - Submit | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 493 | 495 |  | Manojkumar Gurjar,Joy Schneider
4592 | 495 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DED D659 - Completion of Build Segment II DW/BI - Collaborative Review | 24 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 494 | 496 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4593 | 496 | Future Task |  |  | D659 | Manojkumar Gurjar | Approve | DED D659 - Completion of Build Segment II DW/BI - Approve | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 495 | 497 |  | Jimmy Cox
4603 | 497 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment II DW/BI | 40 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 496 | 498 |  | Manojkumar Gurjar,Kurt Meisner
4604 | 498 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment II DW/BI | 20 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 497 | 499 |  | Manojkumar Gurjar,Kurt Meisner
4605 | 499 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment II DW/BI | 20 hrs | 5 days | Mon 10/28/24 | Fri 11/1/24 | 498 | 500 |  | Manojkumar Gurjar,Kurt Meisner
4606 | 500 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment II DW/BI - Group 1 | 20 hrs | 17 days | Mon 11/4/24 | Wed 11/27/24 | 499 | 501 |  | Manojkumar Gurjar,Kurt Meisner
4607 | 501 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment II DW/BI - Group 2 | 2 hrs | 23 days | Mon 12/2/24 | Fri 1/3/25 | 500 | 502 |  | Manojkumar Gurjar,Kurt Meisner
4608 | 502 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Create Summary Document for Build Segment II DW/BI | 20 hrs | 19 days | Mon 1/6/25 | Fri 1/31/25 | 501 | 503 |  | Manojkumar Gurjar,Kurt Meisner
4594 | 503 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DEL D659 - Completion of Build Segment II DW/BI - Draft Submission | 0 hrs | 0 days | Fri 1/31/25 | Fri 1/31/25 | 502 | 504 |  | Manojkumar Gurjar,Joy Schneider
4595 | 504 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 2/3/25 | Fri 2/7/25 | 503 | 505 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4596 | 505 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Style Guide Review | 1 hr | 1 day | Mon 2/10/25 | Mon 2/10/25 | 504 | 506 |  | Dusti Kincl
4597 | 506 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Final Collaborative Review | 20 hrs | 5 days | Tue 2/11/25 | Mon 2/17/25 | 505 | 507 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4598 | 507 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Accenture QC | 4 hrs | 2 days | Tue 2/18/25 | Wed 2/19/25 | 506 | 508 |  | Joy Schneider
4599 | 508 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DEL D659 - Completion of Build Segment II DW/BI - Submit | 0 hrs | 0 days | Wed 2/19/25 | Wed 2/19/25 | 507 | 509 |  | Joy Schneider
4600 | 509 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Department QC | 4 hrs | 1 day | Thu 2/20/25 | Thu 2/20/25 | 508 | 510 |  | Tommy Werner,Gabriela Gibson
4601 | 510 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Contract Manager Review | 8 hrs | 3 days | Fri 2/21/25 | Tue 2/25/25 | 509 | 511 |  | Sean Buchanan
4602 | 511 | Future Task |  |  | D659 | Manojkumar Gurjar | Accept | DEL D659 - Completion of Build Segment II DW/BI - Accept | 0 hrs | 0 days | Tue 2/25/25 | Tue 2/25/25 | 510 | 585 | 2025-04-01 | Sean Buchanan
4609 | 512 | Future Task | Yes |  | D668 | Manojkumar Gurjar |  | D668 - Completion of Build Segment III DW/BI | 281 hrs | 93 days | Wed 10/30/24 | Mon 3/17/25
4610 | 513 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | DED D668 - Completion of Build Segment III DW/BI - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1 | 514 |  | Manojkumar Gurjar,Kurt Meisner
4611 | 514 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DED D668 - Completion of Build Segment III DW/BI - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 513 | 515 |  | Manojkumar Gurjar,Joy Schneider
4612 | 515 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DED D668 - Completion of Build Segment III DW/BI - Collaborative Review | 24 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 514 | 516 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4613 | 516 | Future Task |  |  | D668 | Manojkumar Gurjar | Approve | DED D668 - Completion of Build Segment III DW/BI - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 515 | 517 |  | Jimmy Cox
4623 | 517 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment III DW/BI | 40 hrs | 5 days | Mon 12/2/24 | Fri 12/6/24 | 516 | 518SS+2 days |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4624 | 518 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment III DW/BI | 40 hrs | 5 days | Wed 12/4/24 | Tue 12/10/24 | 517SS+2 days | 519 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4625 | 519 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment III DW/BI | 24 hrs | 3 days | Wed 12/11/24 | Fri 12/13/24 | 518 | 520 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4626 | 520 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment III DW/BI - Group 1 | 20 hrs | 18 days | Mon 12/16/24 | Fri 1/10/25 | 519 | 521 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4627 | 521 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment III DW/BI - Group 2 | 20 hrs | 18 days | Mon 1/13/25 | Thu 2/6/25 | 520 | 522 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4628 | 522 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Create Summary Document for Build Segment III DW/BI | 40 hrs | 10 days | Fri 2/7/25 | Thu 2/20/25 | 521 | 523 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4614 | 523 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DEL D668 - Completion of Build Segment III DW/BI - Draft Submission | 0 hrs | 0 days | Thu 2/20/25 | Thu 2/20/25 | 522 | 524 |  | Manojkumar Gurjar,Joy Schneider
4615 | 524 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 2/21/25 | Thu 2/27/25 | 523 | 525 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4616 | 525 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Style Guide Review | 1 hr | 1 day | Fri 2/28/25 | Fri 2/28/25 | 524 | 526 |  | Dusti Kincl
4617 | 526 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Final Collaborative Review | 20 hrs | 5 days | Mon 3/3/25 | Fri 3/7/25 | 525 | 527 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4618 | 527 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Accenture QC | 4 hrs | 2 days | Mon 3/10/25 | Tue 3/11/25 | 526 | 528 |  | Joy Schneider
4619 | 528 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DEL D668 - Completion of Build Segment III DW/BI - Submit | 0 hrs | 0 days | Tue 3/11/25 | Tue 3/11/25 | 527 | 529 |  | Joy Schneider
4620 | 529 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Department QC | 4 hrs | 1 day | Wed 3/12/25 | Wed 3/12/25 | 528 | 530 |  | Tommy Werner,Gabriela Gibson
4621 | 530 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Contract Manager Review | 8 hrs | 3 days | Thu 3/13/25 | Mon 3/17/25 | 529 | 531 |  | Sean Buchanan
4622 | 531 | Future Task |  |  | D668 | Manojkumar Gurjar | Accept | DEL D668 - Completion of Build Segment III DW/BI - Accept | 0 hrs | 0 days | Mon 3/17/25 | Mon 3/17/25 | 530 | 585 | 2025-08-01 | Sean Buchanan
4646 | 532 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | WP410 - Integration and Interface Strategy | 160 hrs | 95 days | Mon 8/7/23 | Thu 12/21/23
4647 | 533 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WPED WP410 - Integration and Interface Strategy - Create | 16 hrs | 10 days | Mon 8/7/23 | Fri 8/18/23 | 1 | 534 |  | Manojkumar Gurjar,Kurt Meisner
4648 | 534 | Future Task |  |  | WP410 | Manojkumar Gurjar | Submit | WPED WP410 - Integration and Interface Strategy - Submit | 0 hrs | 0 days | Fri 8/18/23 | Fri 8/18/23 | 533 | 535 |  | Manojkumar Gurjar,Joy Schneider
4649 | 535 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WPED WP410 - Integration and Interface Strategy - Review | 24 hrs | 10 days | Mon 8/21/23 | Fri 9/1/23 | 534 | 536 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4650 | 536 | Future Task |  |  | WP410 | Manojkumar Gurjar | Approve | WPED WP410 - Integration and Interface Strategy - Approve | 0 hrs | 0 days | Fri 9/1/23 | Fri 9/1/23 | 535 | 537 |  | Jimmy Cox
4655 | 537 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | Define Interface and Integration Approach | 20 hrs | 19 days | Tue 9/5/23 | Fri 9/29/23 | 536 | 538 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4656 | 538 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | Create Interface and Integration Architecture Diagram | 20 hrs | 15 days | Mon 10/2/23 | Fri 10/20/23 | 537 | 539540 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4657 | 539 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | Review and update Interface and Integration Operations | 20 hrs | 19 days | Mon 10/23/23 | Fri 11/17/23 | 538 | 540 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4658 | 540 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | Finalize the Interface and Integration Strategy Document | 20 hrs | 7 days | Mon 11/20/23 | Thu 11/30/23 | 538539 | 541 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4651 | 541 | Future Task |  |  | WP410 | Manojkumar Gurjar | Submit | WP WP410 - Integration and Interface Strategy - Submit | 0 hrs | 0 days | Thu 11/30/23 | Thu 11/30/23 | 540 | 542 |  | Manojkumar Gurjar,Joy Schneider
4652 | 542 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WP WP410 - Integration and Interface Strategy - Collaborative Review & Update | 20 hrs | 10 days | Fri 12/1/23 | Thu 12/14/23 | 541 | 543 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4653 | 543 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WP WP410 - Integration and Interface Strategy - Final Review & Edits | 20 hrs | 5 days | Fri 12/15/23 | Thu 12/21/23 | 542 | 544 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4654 | 544 | Future Task |  |  | WP410 | Manojkumar Gurjar | Approve | WP WP410 - Integration and Interface Strategy - Approve | 0 hrs | 0 days | Thu 12/21/23 | Thu 12/21/23 | 543 | 1070FS+92 days | 2023-11-01 | Jimmy Cox
5603 | 545 | Future Task |  |  | WP426 | Jarad Hermann |  | WP426 - System Infrastructure Capacity Plan | 148 hrs | 52 days | Mon 10/6/25 | Fri 12/19/25
5604 | 546 | Future Task |  |  | WP426 | Jarad Hermann | Create | WPED WP426 - System Infrastructure Capacity Plan - Create | 8 hrs | 10 days | Mon 10/6/25 | Fri 10/17/25 | 1 | 547 |  | Jarad Hermann
5605 | 547 | Future Task |  |  | WP426 | Jarad Hermann | Submit | WPED WP426 - System Infrastructure Capacity Plan - Submit | 0 hrs | 0 days | Fri 10/17/25 | Fri 10/17/25 | 546 | 548 |  | Joy Schneider,Jarad Hermann
5606 | 548 | Future Task |  |  | WP426 | Jarad Hermann | Review | WPED WP426 - System Infrastructure Capacity Plan - Review | 16 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 547 | 549 |  | Jarad Hermann,Jimmy Cox,Angie Robertson,Sean Buchanan
5607 | 549 | Future Task |  |  | WP426 | Jarad Hermann | Approve | WPED WP426 - System Infrastructure Capacity Plan - Approve | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 548 | 550 |  | Jimmy Cox
5608 | 550 | Future Task |  |  | WP426 | Jarad Hermann |  | Review and refine the excel doc | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 549 | 551SS,552SS,553SS,554SS |  | Jarad Hermann,Bryan Sohayda
5609 | 551 | Future Task |  |  | WP426 | Jarad Hermann |  | Review and refine the FL PALM Capacity Plan | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 550SS | 555 |  | Jarad Hermann,Bryan Sohayda
5610 | 552 | Future Task |  |  | WP426 | Jarad Hermann |  | Define and document current infrastructure demand | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 550SS | 555 |  | Jarad Hermann,Bryan Sohayda
5611 | 553 | Future Task |  |  | WP426 | Jarad Hermann |  | Define and document current infrastructure capacity | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 550SS | 555 |  | Jarad Hermann,Bryan Sohayda
5612 | 554 | Future Task |  |  | WP426 | Jarad Hermann |  | Define and document projected infrastructure demand | 20 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25 | 550SS | 555 |  | Jarad Hermann,Bryan Sohayda
5613 | 555 | Future Task |  |  | WP426 | Jarad Hermann | Submit | WP WP426 - System Infrastructure Capacity Plan - Submit | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 554551552553 | 556 |  | Joy Schneider,Jarad Hermann
5614 | 556 | Future Task |  |  | WP426 | Jarad Hermann | Review | WP WP426 - System Infrastructure Capacity Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 12/1/25 | Fri 12/12/25 | 555 | 557 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5615 | 557 | Future Task |  |  | WP426 | Jarad Hermann | Review | WP WP426 - System Infrastructure Capacity Plan - Final Review & Edits | 12 hrs | 5 days | Mon 12/15/25 | Fri 12/19/25 | 556 | 558 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5616 | 558 | Future Task |  |  | WP426 | Jarad Hermann | Approve | WP WP426 - System Infrastructure Capacity Plan - Approve | 0 hrs | 0 days | Fri 12/19/25 | Fri 12/19/25 | 557 |  |  | Jimmy Cox
3868 | 559 | Future Task | Yes |  |  |  |  | Environment Builds | 137 hrs | 207 days | Mon 8/5/24 | Fri 5/30/25 |  |  |  |  | Is this related to a WP? | Tommy
4203 | 560 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure System Test Environment | 10 hrs | 15 days | Mon 8/5/24 | Fri 8/23/24 | 605 | 561 |  | Manojkumar Gurjar,Jarad Hermann | Is this the correct naming convention? | Tommy
4204 | 561 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate System Test Environment | 8 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 560 | 648 |  | Manojkumar Gurjar,Jarad Hermann
4195 | 562 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Interface Test Environment | 10 hrs | 14 days | Tue 9/3/24 | Fri 9/20/24 | 1083FS-10 days | 563 |  | Manojkumar Gurjar,Jarad Hermann
4196 | 563 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Interface Test Environment | 8 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 562 | 789 |  | Manojkumar Gurjar,Jarad Hermann
4197 | 564 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Mock Conversion Test Environment | 10 hrs | 15 days | Mon 8/5/24 | Fri 8/23/24 | 1030 | 565 |  | Manojkumar Gurjar,Jarad Hermann
4198 | 565 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Mock Conversion Test Environment | 8 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 564 | 627 |  | Manojkumar Gurjar,Jarad Hermann
4199 | 566 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure UAT Test Environment | 10 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1248FS+46 days | 567 |  | Manojkumar Gurjar,Jarad Hermann
4200 | 567 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate UAT Test Environment | 10 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 566 | 568 |  | Manojkumar Gurjar,Jarad Hermann
4201 | 568 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Load Security Roles to ForgeRock for UAT | 4 hrs | 4 days | Tue 3/11/25 | Fri 3/14/25 | 5671821 | 569 |  | Jarad Hermann
4202 | 569 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Security Roles in ForgeRock for UAT | 5 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 568 | 1250585 |  | Jarad Hermann
4191 | 570 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Dry Run Test Environment | 10 hrs | 14 days | Mon 5/5/25 | Thu 5/22/25 |  | 571 |  | Manojkumar Gurjar,Jarad Hermann
4192 | 571 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Dry Run Test Environment | 8 hrs | 5 days | Fri 5/23/25 | Fri 5/30/25 | 570 | 829 |  | Manojkumar Gurjar,Jarad Hermann
4193 | 572 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Performance Test Environment | 10 hrs | 15 days | Mon 5/5/25 | Fri 5/23/25 | 1186 | 573 |  | Manojkumar Gurjar,Jarad Hermann
4194 | 573 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Performance Test Environment | 8 hrs | 4 days | Tue 5/27/25 | Fri 5/30/25 | 572 | 969 |  | Manojkumar Gurjar,Jarad Hermann
4189 | 574 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Disaster Recovery Test Environment | 10 hrs | 15 days | Mon 3/3/25 | Fri 3/21/25 | 1172 | 575 |  | Manojkumar Gurjar,Jarad Hermann
4190 | 575 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Disaster Recovery Test Environment | 8 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 574 | 987 |  | Manojkumar Gurjar,Jarad Hermann
6809 | 576 | Future Task | [5 empty] | Other | 48 hrs | 187 days | Mon 1/8/24 | Mon 9/30/24 |  |  |  |  | Discuss
7144 | 577 | Future Task |  |  |  | Stacey Terry |  | Support Agency Configuration Workbook | 20 hrs | 103 days | Mon 1/8/24 | Fri 5/31/24 | 126FS+6 days | 578 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
7145 | 578 | Future Task |  |  |  | Stacey Terry |  | Load Agency Configuration Workbook | 20 hrs | 64 days | Mon 6/3/24 | Fri 8/30/24 | 577 |  |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
6808 | 579 | Future Task |  |  |  | Stacey Terry |  | Define User Preferences | 2 hrs | 10 days | Wed 7/31/24 | Tue 8/13/24 | 237 | 1815 |  | Stacey Terry
6810 | 580 | Future Task |  |  |  | Stacey Terry |  | Create Batch Design/Online | 2 hrs | 22 days | Mon 7/1/24 | Wed 7/31/24 | 47,66,105,145,164FS+24 days | 581 |  | Stacey Terry,Manojkumar Gurjar
6807 | 581 | Future Task |  |  |  | Stacey Terry |  | Create Batch Design/Interface | 2 hrs | 22 days | Thu 8/1/24 | Fri 8/30/24 | 580 | 582 |  | Stacey Terry,Manojkumar Gurjar
6811 | 582 | Future Task |  |  |  | Stacey Terry |  | Review and Confirm Batch Design | 2 hrs | 20 days | Tue 9/3/24 | Mon 9/30/24 | 581 |  |  | Stacey Terry,Manojkumar Gurjar
3771 | 583 | Future Task | [5 empty] | Test | 6,513.58 hrs | 617 days | Mon 7/3/23 | Fri 12/12/25
7153 | 584 | Future Task | Yes |  | SG2 | Jimmy Cox | Milestone | Stage Gate 2: Ready to Begin System Testing | 0 hrs | 0 days | Wed 5/8/24 | Wed 5/8/24 | 47,66,145,157,393 |  | July/August 2024 | Jimmy Cox,Angie Robertson,Matt Cole | This should be July / August 2024, per the SOW | Angie
7154 | 585 | Future Task | Yes |  | SG3 | Jimmy Cox | Milestone | Stage Gate 3: Ready to Begin UAT | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 47,66,145,164,393,429,449,471,491,511,531,1248,747,688,648,569 |  | March 2025 - ESC | Jimmy Cox,Angie Robertson,Matt Cole | This should be March 2025 per the SOW. The Resource Names include the ESC and we need tasks / dates for ESC review prior to milestone date. | Angie
4662 | 586 | Future Task |  |  | D643 | Stacey Terry |  | D643 - Updated System Testing Plan | 343 hrs | 361 days | Mon 7/3/23 | Fri 12/6/24
4663 | 587 | Future Task |  |  | D643 | Stacey Terry | Create | DED D643 - Updated System Testing Plan - Create | 16 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 1FS+47 days | 588 |  | Stacey Terry,Mary Punty
4664 | 588 | Future Task |  |  | D643 | Stacey Terry | Submit | DED D643 - Updated System Testing Plan - Submit | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 587 | 589 |  | Stacey Terry,Joy Schneider
4665 | 589 | Future Task |  |  | D643 | Stacey Terry | Review | DED D643 - Updated System Testing Plan - Collaborative Review | 24 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 588 | 590 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4666 | 590 | Future Task |  |  | D643 | Stacey Terry | Approve | DED D643 - Updated System Testing Plan - Approve | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 589 | 591FS+80 days |  | Jimmy Cox
4685 | 591 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test approach for Financials and Payroll | 20 hrs | 15 days | Mon 11/27/23 | Fri 12/15/23 | 590FS+80 days | 592 |  | Yogesh Deshmukh,Stacey Terry,Mary Punty,Manojkumar Gurjar,Kurt Meisner,Matt Cole
4686 | 592 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test Cycles for Financials and Payroll | 20 hrs | 9 days | Mon 12/18/23 | Fri 12/29/23 | 591 | 593FS-4 days |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Mary Punty
4687 | 593 | Future Task |  |  | D643 | Stacey Terry |  | Identify System Test Resources for Financials and Payroll | 20 hrs | 11 days | Tue 12/26/23 | Wed 1/10/24 | 592FS-4 days | 594SS+4 days |  | Stacey Terry,Manojkumar Gurjar,Janice Jackson,Tiffany Porter,Brendan Jones,Jennifer Reeves,Deana Metcalf,Matthew Breeding,Carolyn Hicks
4688 | 594 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test Tools and Test Management processes | 20 hrs | 11 days | Tue 1/2/24 | Wed 1/17/24 | 593SS+4 days | 595FS-2 days |  | Yogesh Deshmukh,Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jennifer Reeves
4689 | 595 | Future Task |  |  | D643 | Stacey Terry |  | Create Initial List of System Test Scenarios for Financials and Payroll | 20 hrs | 24 days | Tue 1/16/24 | Fri 2/16/24 | 594FS-2 days | 596FS-5 days |  | Yogesh Deshmukh,Stacey Terry,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4690 | 596 | Future Task |  |  | D643 | Stacey Terry |  | Define requirements traceability approach for system testing | 20 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 595FS-5 days | 597 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Mary Punty,Jennifer Reeves
4667 | 597 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 - Updated System Testing Plan - Draft Submission | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 596 | 598 |  | Stacey Terry,Joy Schneider
4668 | 598 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 2/26/24 | Fri 3/1/24 | 597 | 599 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4669 | 599 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Style Guide Review | 1 hr | 1 day | Mon 3/4/24 | Mon 3/4/24 | 598 | 600 |  | Dusti Kincl
4670 | 600 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Final Collaborative Review | 20 hrs | 5 days | Tue 3/5/24 | Mon 3/11/24 | 599 | 601 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4671 | 601 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Accenture QC | 4 hrs | 2 days | Tue 3/12/24 | Wed 3/13/24 | 600 | 602 |  | Joy Schneider
4672 | 602 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 - Updated System Testing Plan - Submit | 0 hrs | 0 days | Wed 3/13/24 | Wed 3/13/24 | 601 | 603 |  | Joy Schneider
4673 | 603 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Department QC | 4 hrs | 1 day | Thu 3/14/24 | Thu 3/14/24 | 602 | 604 |  | Tommy Werner,Gabriela Gibson
4674 | 604 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Contract Manager Review | 8 hrs | 3 days | Fri 3/15/24 | Tue 3/19/24 | 603 | 605 |  | Sean Buchanan
4675 | 605 | Future Task |  |  | D643 | Stacey Terry | Accept | DEL D643 - Updated System Testing Plan - Accept | 0 hrs | 0 days | Tue 3/19/24 | Tue 3/19/24 | 604 | 606FS+101 days,560 | 2024-03-01 | Sean Buchanan
4691 | 606 | Future Task |  |  | D643 | Stacey Terry |  | Update DED D643 to include the system testing plan for DW and BI | 20 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 605FS+101 days | 607FS+9 days |  | Mary Punty,Stacey Terry
4692 | 607 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test approach for DW & BI | 20 hrs | 20 days | Mon 9/9/24 | Fri 10/4/24 | 606FS+9 days | 608SS+10 days |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
4693 | 608 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test Cycles for DW & BI | 20 hrs | 15 days | Mon 9/23/24 | Fri 10/11/24 | 607SS+10 days | 609SS+5 days |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
4694 | 609 | Future Task |  |  | D643 | Stacey Terry |  | Identify System Test Resources for DW & BI | 20 hrs | 10 days | Mon 9/30/24 | Fri 10/11/24 | 608SS+5 days | 610 |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
4695 | 610 | Future Task |  |  | D643 | Stacey Terry |  | Create Initial List of DW & BI System Test Scenarios | 4 hrs | 20 days | Mon 10/14/24 | Fri 11/8/24 | 609 | 611 |  | Jennifer Reeves,Manojkumar Gurjar
4676 | 611 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 2.0 - Updated System Testing Plan - Draft Submission | 0 hrs | 0 days | Fri 11/8/24 | Fri 11/8/24 | 610 | 612 |  | Stacey Terry,Joy Schneider
4677 | 612 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Pre-Submission Collaborative Review | 5 hrs | 5 days | Tue 11/12/24 | Mon 11/18/24 | 611 | 613 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4678 | 613 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Style Guide Review | 1 hr | 1 day | Tue 11/19/24 | Tue 11/19/24 | 612 | 614 |  | Dusti Kincl
4679 | 614 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Final Collaborative Review | 20 hrs | 5 days | Wed 11/20/24 | Tue 11/26/24 | 613 | 615 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4680 | 615 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Accenture QC | 4 hrs | 2 days | Wed 11/27/24 | Mon 12/2/24 | 614 | 616 |  | Joy Schneider
4681 | 616 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 2.0 - Updated System Testing Plan - Submit | 0 hrs | 0 days | Mon 12/2/24 | Mon 12/2/24 | 615 | 617 |  | Joy Schneider
4682 | 617 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Department QC | 4 hrs | 1 day | Tue 12/3/24 | Tue 12/3/24 | 616 | 618 |  | Tommy Werner,Gabriela Gibson
4683 | 618 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Contract Manager Review | 8 hrs | 3 days | Wed 12/4/24 | Fri 12/6/24 | 617 | 619 |  | Sean Buchanan
4684 | 619 | Future Task |  |  | D643 | Stacey Terry | Accept | DEL D643 2.0 - Updated System Testing Plan - Accept | 0 hrs | 0 days | Fri 12/6/24 | Fri 12/6/24 | 618 |  |  | Sean Buchanan
5004 | 620 | Future Task | Yes |  | D651 | Manojkumar Gurjar |  | D651 - Completion of Mock Conversion I | 197 hrs | 71 days | Mon 7/15/24 | Tue 10/22/24
5005 | 621 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | DED D651 - Completion of Mock Conversion I - Create | 16 hrs | 10 days | Mon 7/15/24 | Fri 7/26/24 | 1042FS-28 days | 622 |  | Manojkumar Gurjar,Kurt Meisner
5006 | 622 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DED D651 - Completion of Mock Conversion I - Submit | 0 hrs | 0 days | Fri 7/26/24 | Fri 7/26/24 | 621 | 623 |  | Manojkumar Gurjar,Joy Schneider
5007 | 623 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DED D651 - Completion of Mock Conversion I - Collaborative Review | 24 hrs | 10 days | Mon 7/29/24 | Fri 8/9/24 | 622 | 624 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5008 | 624 | Future Task |  |  | D651 | Manojkumar Gurjar | Approve | DED D651 - Completion of Mock Conversion I - Approve | 0 hrs | 0 days | Fri 8/9/24 | Fri 8/9/24 | 623 | 625 |  | Jimmy Cox
5018 | 625 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Confirm Mock 1 Conversion Test Environment Readiness | 20 hrs | 5 days | Mon 8/12/24 | Fri 8/16/24 | 624 | 626 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5019 | 626 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Create Mock 1 Conversion Checklist | 20 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 625 | 627 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5020 | 627 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Execute Mock 1 – Conversion | 20 hrs | 9 days | Tue 9/3/24 | Fri 9/13/24 | 626565 | 628 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5021 | 628 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Validate Mock 1 – Conversion | 20 hrs | 5 days | Mon 9/16/24 | Fri 9/20/24 | 627 | 629 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5022 | 629 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Conduct Mock 1 - Conversion Test Exit Criteria Review Meeting | 20 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 628 | 630 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5009 | 630 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DEL D651 - Completion of Mock Conversion I - Draft Submission | 0 hrs | 0 days | Fri 9/27/24 | Fri 9/27/24 | 629 | 631 |  | Manojkumar Gurjar,Joy Schneider
5010 | 631 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 9/30/24 | Fri 10/4/24 | 630 | 632 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5011 | 632 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Style Guide Review | 1 hr | 1 day | Mon 10/7/24 | Mon 10/7/24 | 631 | 633 |  | Dusti Kincl
5012 | 633 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Final Collaborative Review | 20 hrs | 5 days | Tue 10/8/24 | Mon 10/14/24 | 632 | 634 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5013 | 634 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Accenture QC | 4 hrs | 2 days | Tue 10/15/24 | Wed 10/16/24 | 633 | 635 |  | Joy Schneider
5014 | 635 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DEL D651 - Completion of Mock Conversion I - Submit | 0 hrs | 0 days | Wed 10/16/24 | Wed 10/16/24 | 634 | 636 |  | Joy Schneider
5015 | 636 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Department QC | 4 hrs | 1 day | Thu 10/17/24 | Thu 10/17/24 | 635 | 637 |  | Tommy Werner,Gabriela Gibson
5016 | 637 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Contract Manager Review | 8 hrs | 3 days | Fri 10/18/24 | Tue 10/22/24 | 636 | 638 |  | Sean Buchanan
5017 | 638 | Future Task |  |  | D651 | Manojkumar Gurjar | Accept | DEL D651 - Completion of Mock Conversion I - Accept | 0 hrs | 0 days | Tue 10/22/24 | Tue 10/22/24 | 637 | 663FS-3 days | 2024-11-01 | Sean Buchanan
4696 | 639 | Future Task | Yes |  | D652 | Stacey Terry |  | D652 - Completion of System Test Segment I | 206 hrs | 123 days | Mon 7/8/24 | Thu 1/2/25
4697 | 640 | Future Task |  |  | D652 | Stacey Terry | Create | DED D652 - Completion of System Test Segment I - Create | 16 hrs | 10 days | Mon 7/8/24 | Fri 7/19/24 | 1 | 641 |  | Stacey Terry,Mary Punty
4698 | 641 | Future Task |  |  | D652 | Stacey Terry | Submit | DED D652 - Completion of System Test Segment I - Submit | 0 hrs | 0 days | Fri 7/19/24 | Fri 7/19/24 | 640 | 642 |  | Stacey Terry,Joy Schneider
4699 | 642 | Future Task |  |  | D652 | Stacey Terry | Review | DED D652 - Completion of System Test Segment I - Collaborative Review | 24 hrs | 10 days | Mon 7/22/24 | Fri 8/2/24 | 641 | 643 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4700 | 643 | Future Task |  |  | D652 | Stacey Terry | Approve | DED D652 - Completion of System Test Segment I - Approve | 0 hrs | 0 days | Fri 8/2/24 | Fri 8/2/24 | 642 | 644 |  | Jimmy Cox
4752 | 644 | Future Task |  |  | D652 | Stacey Terry |  | Create Work Unit Tracker for System Test Segment 1 Execution | 20 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 643 | 645 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4753 | 645 | Future Task |  |  | D652 | Stacey Terry |  | Review, Update and confirm Work Unit Tracker for System Test Segment 1 Execution | 20 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 644 | 646SS+5 days |  | Mary Punty,Stacey Terry,Deana Metcalf,Janice Jackson,Tiffany Porter,Brendan Jones
4754 | 646 | Future Task |  |  | D652 | Stacey Terry |  | Confirm System Test Environment Readiness | 20 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 645SS+5 days | 647SS |  | Manojkumar Gurjar,Jarad Hermann
4755 | 647 | Future Task |  |  | D652 | Stacey Terry |  | Conduct System Test Kick Off Meeting | 30 hrs | 5 days | Mon 8/26/24 | Fri 8/30/24 | 646SS | 648 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4756 | 648 | Future Task |  |  | D652 | Stacey Terry |  | Execute System Test Segment 1 - this is a WU | 10 hrs | 51 days | Tue 9/17/24 | Wed 11/27/24 | 6471056561 | 649,650FS-3 days,585 |  | Yogesh Deshmukh,Stacey Terry,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4757 | 649 | Future Task |  |  | D652 | Stacey Terry | Milestone | Milestone: System Test Segment 1 Execution Complete | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 648 | 1713 |  | Stacey Terry
4758 | 650 | Future Task |  |  | D652 | Stacey Terry |  | Create Completion of System Testing Segment 1 Summary Document | 3 hrs | 8 days | Mon 11/25/24 | Fri 12/6/24 | 648FS-3 days | 651SS+3 days,652SS+3 days,653 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4759 | 651 | Future Task |  |  | D652 | Stacey Terry |  | Conduct System Test Segment 1 Exit Criteria Review Meeting | 3 hrs | 5 days | Mon 12/2/24 | Fri 12/6/24 | 650SS+3 days | 653 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4760 | 652 | Future Task |  |  | D652 | Stacey Terry |  | Confirm requirements traceability for System Test Segment 1 | 3 hrs | 5 days | Mon 12/2/24 | Fri 12/6/24 | 650SS+3 days | 653 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4701 | 653 | Future Task |  |  | D652 | Stacey Terry | Submit | DEL D652 - Completion of System Test Segment I - Draft Submission | 0 hrs | 0 days | Fri 12/6/24 | Fri 12/6/24 | 650651652 | 654 |  | Stacey Terry,Joy Schneider
4702 | 654 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 12/9/24 | Fri 12/13/24 | 653 | 655 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4703 | 655 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Style Guide Review | 1 hr | 1 day | Mon 12/16/24 | Mon 12/16/24 | 654 | 656 |  | Dusti Kincl
4704 | 656 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Final Collaborative Review | 20 hrs | 5 days | Tue 12/17/24 | Mon 12/23/24 | 655 | 657 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4705 | 657 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Accenture QC | 4 hrs | 2 days | Tue 12/24/24 | Thu 12/26/24 | 656 | 658 |  | Joy Schneider
4706 | 658 | Future Task |  |  | D652 | Stacey Terry | Submit | DEL D652 - Completion of System Test Segment I - Submit | 0 hrs | 0 days | Thu 12/26/24 | Thu 12/26/24 | 657 | 659 |  | Joy Schneider
4707 | 659 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Department QC | 4 hrs | 1 day | Fri 12/27/24 | Fri 12/27/24 | 658 | 660 |  | Tommy Werner,Gabriela Gibson
4708 | 660 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Contract Manager Review | 8 hrs | 3 days | Mon 12/30/24 | Thu 1/2/25 | 659 | 661 |  | Sean Buchanan
4709 | 661 | Future Task |  |  | D652 | Stacey Terry | Accept | DEL D652 - Completion of System Test Segment I - Accept | 0 hrs | 0 days | Thu 1/2/25 | Thu 1/2/25 | 660 |  | 2024-12-01 | Sean Buchanan
4710 | 662 | Future Task | Yes |  | D655 | Manojkumar Gurjar |  | D655 - Completion of Mock Conversion II (System Test Environment) | 197 hrs | 65 days | Fri 10/18/24 | Fri 1/24/25
4711 | 663 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | DED D655 - Completion of Mock Conversion II (System Test Environment) - Create | 16 hrs | 10 days | Fri 10/18/24 | Thu 10/31/24 | 638FS-3 days | 664 |  | Manojkumar Gurjar,Kurt Meisner
4712 | 664 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DED D655 - Completion of Mock Conversion II (System Test Environment) - Submit | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 663 | 665 |  | Manojkumar Gurjar,Joy Schneider
4713 | 665 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DED D655 - Completion of Mock Conversion II (System Test Environment) - Collaborative Review | 24 hrs | 10 days | Fri 11/1/24 | Fri 11/15/24 | 664 | 666 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4714 | 666 | Future Task |  |  | D655 | Manojkumar Gurjar | Approve | DED D655 - Completion of Mock Conversion II (System Test Environment) - Approve | 0 hrs | 0 days | Fri 11/15/24 | Fri 11/15/24 | 665 | 667 |  | Jimmy Cox
4761 | 667 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Confirm Mock 2 Conversion - System Test Environment Readiness | 20 hrs | 4 days | Mon 11/18/24 | Thu 11/21/24 | 666 | 668 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4762 | 668 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Create Mock 2 Conversion Checklist (System Test Environment) | 20 hrs | 5 days | Fri 11/22/24 | Mon 12/2/24 | 667 | 669 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4763 | 669 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Execute Mock 2 – Conversion (System Test Environment) | 20 hrs | 10 days | Tue 12/3/24 | Mon 12/16/24 | 668 | 670 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4764 | 670 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Validate Mock 2 – Conversion (System Test Environment) | 20 hrs | 4 days | Tue 12/17/24 | Fri 12/20/24 | 669 | 671 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4765 | 671 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Conduct Mock 2 - Conversion (System Test Environment) Test Exit Criteria Review Meeting | 20 hrs | 5 days | Mon 12/23/24 | Mon 12/30/24 | 670 | 672 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4715 | 672 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Draft Submission | 0 hrs | 0 days | Mon 12/30/24 | Mon 12/30/24 | 671 | 673 |  | Manojkumar Gurjar,Joy Schneider
4716 | 673 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Pre-Submission Collaborative Review | 20 hrs | 5 days | Tue 12/31/24 | Tue 1/7/25 | 672 | 674 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4717 | 674 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Style Guide Review | 1 hr | 1 day | Wed 1/8/25 | Wed 1/8/25 | 673 | 675 |  | Dusti Kincl
4718 | 675 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Final Collaborative Review | 20 hrs | 5 days | Thu 1/9/25 | Wed 1/15/25 | 674 | 676 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4719 | 676 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Accenture QC | 4 hrs | 2 days | Thu 1/16/25 | Fri 1/17/25 | 675 | 677 |  | Joy Schneider
4720 | 677 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Submit | 0 hrs | 0 days | Fri 1/17/25 | Fri 1/17/25 | 676 | 678 |  | Joy Schneider
4721 | 678 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Department QC | 4 hrs | 1 day | Tue 1/21/25 | Tue 1/21/25 | 677 | 679 |  | Tommy Werner,Gabriela Gibson
4722 | 679 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Contract Manager Review | 8 hrs | 3 days | Wed 1/22/25 | Fri 1/24/25 | 678 | 680 |  | Sean Buchanan
4723 | 680 | Future Task |  |  | D655 | Manojkumar Gurjar | Accept | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Accept | 0 hrs | 0 days | Fri 1/24/25 | Fri 1/24/25 | 679 | 703FS-40 days | 2025-01-01 | Sean Buchanan
4724 | 681 | Future Task | Yes |  | D656 | Stacey Terry |  | D656 - Completion of System Test Segment II | 154 hrs | 99 days | Mon 10/7/24 | Fri 2/28/25
4725 | 682 | Future Task |  |  | D656 | Stacey Terry | Create | DED D656 - Completion of System Test Segment II - Create | 16 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1 | 683 |  | Stacey Terry,Mary Punty
4726 | 683 | Future Task |  |  | D656 | Stacey Terry | Submit | DED D656 - Completion of System Test Segment II - Submit | 0 hrs | 0 days | Fri 10/18/24 | Fri 10/18/24 | 682 | 684 |  | Stacey Terry,Joy Schneider
4727 | 684 | Future Task |  |  | D656 | Stacey Terry | Review | DED D656 - Completion of System Test Segment II - Collaborative Review | 20 hrs | 10 days | Mon 10/21/24 | Fri 11/1/24 | 683 | 685 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4728 | 685 | Future Task |  |  | D656 | Stacey Terry | Approve | DED D656 - Completion of System Test Segment II - Approve | 0 hrs | 0 days | Fri 11/1/24 | Fri 11/1/24 | 684 | 686 |  | Jimmy Cox
4766 | 686 | Future Task |  |  | D656 | Stacey Terry |  | Create Work Unit Tracker for System Test Segment 2 Execution | 6 hrs | 9 days | Mon 11/4/24 | Fri 11/15/24 | 685 | 687 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4767 | 687 | Future Task |  |  | D656 | Stacey Terry |  | Review, Update and confirm Work Unit Tracker for System Test Segment 2 Execution | 20 hrs | 8 days | Mon 11/18/24 | Wed 11/27/24 | 686 | 688 |  | Mary Punty,Stacey Terry,Deana Metcalf,Janice Jackson,Tiffany Porter,Brendan Jones
4768 | 688 | Future Task |  |  | D656 | Stacey Terry |  | Execute System Test Segment 2 - this is a WU | 20 hrs | 40 days | Mon 12/2/24 | Wed 1/29/25 | 687 | 689,690FS-5 days,585 |  | Yogesh Deshmukh,Stacey Terry,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4769 | 689 | Future Task |  |  | D656 | Stacey Terry | Milestone | Milestone: System Test Segment 2 Execution Complete | 0 hrs | 0 days | Wed 1/29/25 | Wed 1/29/25 | 688 |  |  | Stacey Terry
4770 | 690 | Future Task |  |  | D656 | Stacey Terry |  | Create Completion of System Testing Segment 2 Summary Document | 6 hrs | 10 days | Thu 1/23/25 | Wed 2/5/25 | 688FS-5 days | 691SS+5 days,692SS+5 days,693 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4771 | 691 | Future Task |  |  | D656 | Stacey Terry |  | Conduct System Test Segment 2 Exit Criteria Review Meeting | 3 hrs | 5 days | Thu 1/30/25 | Wed 2/5/25 | 690SS+5 days | 693 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4772 | 692 | Future Task |  |  | D656 | Stacey Terry |  | Confirm requirements traceability for System Test Segment 2 | 6 hrs | 5 days | Thu 1/30/25 | Wed 2/5/25 | 690SS+5 days | 693 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4729 | 693 | Future Task |  |  | D656 | Stacey Terry | Submit | DEL D656 - Completion of System Test Segment II - Draft Submission | 0 hrs | 0 days | Wed 2/5/25 | Wed 2/5/25 | 690691692 | 694 |  | Stacey Terry,Joy Schneider
4730 | 694 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Thu 2/6/25 | Wed 2/12/25 | 693 | 695 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4731 | 695 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Style Guide Review | 1 hr | 1 day | Thu 2/13/25 | Thu 2/13/25 | 694 | 696 |  | Dusti Kincl
4732 | 696 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Final Collaborative Review | 20 hrs | 5 days | Fri 2/14/25 | Thu 2/20/25 | 695 | 697 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4733 | 697 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Accenture QC | 4 hrs | 2 days | Fri 2/21/25 | Mon 2/24/25 | 696 | 698 |  | Joy Schneider
4734 | 698 | Future Task |  |  | D656 | Stacey Terry | Submit | DEL D656 - Completion of System Test Segment II - Submit | 0 hrs | 0 days | Mon 2/24/25 | Mon 2/24/25 | 697 | 699 |  | Joy Schneider
4735 | 699 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Department QC | 4 hrs | 1 day | Tue 2/25/25 | Tue 2/25/25 | 698 | 700 |  | Tommy Werner,Gabriela Gibson
4736 | 700 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Contract Manager Review | 8 hrs | 3 days | Wed 2/26/25 | Fri 2/28/25 | 699 | 701 |  | Sean Buchanan
4737 | 701 | Future Task |  |  | D656 | Stacey Terry | Accept | DEL D656 - Completion of System Test Segment II - Accept | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 700 |  | 2025-02-01 | Sean Buchanan
4738 | 702 | Future Task | Yes |  | D657 | Manojkumar Gurjar |  | D657 - Completion of Mock Conversion III (UAT) | 151 hrs | 77 days | Mon 11/25/24 | Tue 3/18/25
4739 | 703 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | DED D657 - Completion of Mock Conversion III (UAT) - Create | 16 hrs | 10 days | Mon 11/25/24 | Tue 12/10/24 | 680FS-40 days | 704 |  | Manojkumar Gurjar,Kurt Meisner
4740 | 704 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DED D657 - Completion of Mock Conversion III (UAT) - Submit | 0 hrs | 0 days | Tue 12/10/24 | Tue 12/10/24 | 703 | 705 |  | Manojkumar Gurjar,Joy Schneider
4741 | 705 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DED D657 - Completion of Mock Conversion III (UAT) - Collaborative Review | 24 hrs | 10 days | Wed 12/11/24 | Tue 12/24/24 | 704 | 706 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4742 | 706 | Future Task |  |  | D657 | Manojkumar Gurjar | Approve | DED D657 - Completion of Mock Conversion III (UAT) - Approve | 0 hrs | 0 days | Tue 12/24/24 | Tue 12/24/24 | 705 | 707 |  | Jimmy Cox
4773 | 707 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Confirm Mock 3 Conversion - UAT Environment Readiness | 2 hrs | 5 days | Thu 12/26/24 | Thu 1/2/25 | 706 | 708 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4774 | 708 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Create Mock 3 Conversion Checklist (UAT) | 2 hrs | 6 days | Fri 1/3/25 | Fri 1/10/25 | 707 | 709 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4775 | 709 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Execute Mock 3 – Conversion (UAT) | 10 hrs | 21 days | Mon 1/13/25 | Tue 2/11/25 | 708 | 710 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4776 | 710 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Validate Mock 3 – Conversion (UAT) | 20 hrs | 4 days | Wed 2/12/25 | Mon 2/17/25 | 709 | 711 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4777 | 711 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Conduct Mock 3 - Conversion UAT Exit Criteria Review Meeting | 20 hrs | 4 days | Tue 2/18/25 | Fri 2/21/25 | 710 | 712 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4743 | 712 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DEL D657 - Completion of Mock Conversion III (UAT) - Draft Submission | 0 hrs | 0 days | Fri 2/21/25 | Fri 2/21/25 | 711 | 713 |  | Manojkumar Gurjar,Joy Schneider
4744 | 713 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 712 | 714 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4745 | 714 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Style Guide Review | 1 hr | 1 day | Mon 3/3/25 | Mon 3/3/25 | 713 | 715 |  | Dusti Kincl
4746 | 715 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Final Collaborative Review | 20 hrs | 5 days | Tue 3/4/25 | Mon 3/10/25 | 714 | 716 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4747 | 716 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Accenture QC | 4 hrs | 2 days | Tue 3/11/25 | Wed 3/12/25 | 715 | 717 |  | Joy Schneider
4748 | 717 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DEL D657 - Completion of Mock Conversion III (UAT) - Submit | 0 hrs | 0 days | Wed 3/12/25 | Wed 3/12/25 | 716 | 718 |  | Joy Schneider
4749 | 718 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Department QC | 4 hrs | 1 day | Thu 3/13/25 | Thu 3/13/25 | 717 | 719 |  | Tommy Werner,Gabriela Gibson
4750 | 719 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Contract Manager Review | 8 hrs | 3 days | Fri 3/14/25 | Tue 3/18/25 | 718 | 720 |  | Sean Buchanan
4751 | 720 | Future Task |  |  | D657 | Manojkumar Gurjar | Accept | DEL D657 - Completion of Mock Conversion III (UAT) - Accept | 0 hrs | 0 days | Tue 3/18/25 | Tue 3/18/25 | 719 | 762FS-22 days,1252 | 2025-02-01 | Sean Buchanan
5023 | 721 | Future Task |  |  | D660 | Stacey Terry |  | D660 - Payroll Parallel Testing Plan | 182 hrs | 72 days | Fri 1/3/25 | Tue 4/15/25
5024 | 722 | Future Task |  |  | D660 | Stacey Terry | Create | DED D660 - Payroll Parallel Testing Plan - Create | 16 hrs | 10 days | Fri 1/3/25 | Thu 1/16/25 | 195 | 723 |  | Stacey Terry,Mary Punty
5025 | 723 | Future Task |  |  | D660 | Stacey Terry | Submit | DED D660 - Payroll Parallel Testing Plan - Submit | 0 hrs | 0 days | Thu 1/16/25 | Thu 1/16/25 | 722 | 724,1099SS-4 days |  | Stacey Terry,Joy Schneider
5026 | 724 | Future Task |  |  | D660 | Stacey Terry | Review | DED D660 - Payroll Parallel Testing Plan - Collaborative Review | 24 hrs | 10 days | Fri 1/17/25 | Fri 1/31/25 | 723 | 725 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5027 | 725 | Future Task |  |  | D660 | Stacey Terry | Approve | DED D660 - Payroll Parallel Testing Plan - Approve | 0 hrs | 0 days | Fri 1/31/25 | Fri 1/31/25 | 724 | 726 |  | Jimmy Cox
5037 | 726 | Future Task |  |  | D660 | Stacey Terry |  | Define Payroll Parallel Test approach | 20 hrs | 20 days | Mon 2/3/25 | Fri 2/28/25 | 725 | 727FS-5 days |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5038 | 727 | Future Task |  |  | D660 | Stacey Terry |  | Define Payroll Parallel Test Cycles | 15 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 726FS-5 days | 728 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5039 | 728 | Future Task |  |  | D660 | Stacey Terry |  | Identify Test Resources for Payroll Parallel Test | 20 hrs | 5 days | Mon 3/3/25 | Fri 3/7/25 | 727 | 729 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5040 | 729 | Future Task |  |  | D660 | Stacey Terry |  | Define Payroll Parallel Test Tools and Test Management processes | 20 hrs | 5 days | Mon 3/10/25 | Fri 3/14/25 | 728 | 730FS-5 days |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5041 | 730 | Future Task |  |  | D660 | Stacey Terry |  | Create Initial List of Payroll Parallel Test Scenarios | 20 hrs | 10 days | Mon 3/10/25 | Fri 3/21/25 | 729FS-5 days | 731 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5028 | 731 | Future Task |  |  | D660 | Stacey Terry | Submit | DEL D660 - Payroll Parallel Testing Plan - Draft Submission | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 730 | 732 |  | Stacey Terry,Joy Schneider
5029 | 732 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 731 | 733 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5030 | 733 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Style Guide Review | 1 hr | 1 day | Mon 3/31/25 | Mon 3/31/25 | 732 | 734 |  | Dusti Kincl
5031 | 734 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Final Collaborative Review | 10 hrs | 5 days | Tue 4/1/25 | Mon 4/7/25 | 733 | 735 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5032 | 735 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Accenture QC | 4 hrs | 2 days | Tue 4/8/25 | Wed 4/9/25 | 734 | 736 |  | Joy Schneider
5033 | 736 | Future Task |  |  | D660 | Stacey Terry | Submit | DEL D660 - Payroll Parallel Testing Plan - Submit | 0 hrs | 0 days | Wed 4/9/25 | Wed 4/9/25 | 735 | 737 |  | Joy Schneider
5034 | 737 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Department QC | 4 hrs | 1 day | Thu 4/10/25 | Thu 4/10/25 | 736 | 738 |  | Tommy Werner,Gabriela Gibson
5035 | 738 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Contract Manager Review | 8 hrs | 3 days | Fri 4/11/25 | Tue 4/15/25 | 737 | 739 |  | Sean Buchanan
5036 | 739 | Future Task |  |  | D660 | Stacey Terry | Accept | DEL D660 - Payroll Parallel Testing Plan - Accept | 0 hrs | 0 days | Tue 4/15/25 | Tue 4/15/25 | 738 | 862FS-37 days | 2025-04-01 | Sean Buchanan
4778 | 740 | Future Task | Yes |  | D661 | Stacey Terry |  | D661 - Completion of System Test DW/BI | 207 hrs | 120 days | Mon 11/4/24 | Mon 4/28/25
4779 | 741 | Future Task |  |  | D661 | Stacey Terry | Create | DED D661 - Completion of System Test DW/BI - Create | 16 hrs | 10 days | Mon 11/4/24 | Mon 11/18/24 | 1 | 742 |  | Stacey Terry,Mary Punty | This should be earlier than immediately before work begins. | Angie
4780 | 742 | Future Task |  |  | D661 | Stacey Terry | Submit | DED D661 - Completion of System Test DW/BI - Submit | 0 hrs | 0 days | Mon 11/18/24 | Mon 11/18/24 | 741 | 743 |  | Stacey Terry,Joy Schneider
4781 | 743 | Future Task |  |  | D661 | Stacey Terry | Review | DED D661 - Completion of System Test DW/BI - Collaborative Review | 24 hrs | 10 days | Tue 11/19/24 | Wed 12/4/24 | 742 | 744 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4782 | 744 | Future Task |  |  | D661 | Stacey Terry | Approve | DED D661 - Completion of System Test DW/BI - Approve | 0 hrs | 0 days | Wed 12/4/24 | Wed 12/4/24 | 743 | 745 |  | Jimmy Cox
4820 | 745 | Future Task |  |  | D661 | Stacey Terry |  | Create Work Unit Tracker for System Test DW/BI Execution | 36 hrs | 9 days | Thu 12/5/24 | Tue 12/17/24 | 744 | 746 |  | Manojkumar Gurjar,Mary Punty
4821 | 746 | Future Task |  |  | D661 | Stacey Terry |  | Review, Update and confirm Work Unit Tracker for System Test DW/BI Execution | 20 hrs | 10 days | Wed 12/18/24 | Thu 1/2/25 | 745 | 747 |  | Manojkumar Gurjar,Mary Punty
4822 | 747 | Future Task |  |  | D661 | Stacey Terry |  | Execute System Test DW/BI - This is a WU | 20 hrs | 60 days | Fri 1/3/25 | Fri 3/28/25 | 746 | 748,749FS-6 days,585 |  | Manojkumar Gurjar,Mary Punty
4823 | 748 | Future Task |  |  | D661 | Stacey Terry | Milestone | Milestone: System Test DW/BI Execution Complete | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 747 |  |  | Stacey Terry
4824 | 749 | Future Task |  |  | D661 | Stacey Terry |  | Create Completion of System Testing DW/BI Summary Document | 4 hrs | 10 days | Fri 3/21/25 | Thu 4/3/25 | 747FS-6 days | 750SS+5 days,752 |  | Manojkumar Gurjar,Mary Punty
4825 | 750 | Future Task |  |  | D661 | Stacey Terry |  | Conduct System Test DW/BI Exit Criteria Review Meeting | 10 hrs | 5 days | Fri 3/28/25 | Thu 4/3/25 | 749SS+5 days | 751SS,752 |  | Manojkumar Gurjar,Mary Punty
4826 | 751 | Future Task |  |  | D661 | Stacey Terry |  | Confirm requirements traceability for System Test DW/BI | 20 hrs | 5 days | Fri 3/28/25 | Thu 4/3/25 | 750SS | 752 |  | Manojkumar Gurjar,Mary Punty
4783 | 752 | Future Task |  |  | D661 | Stacey Terry | Submit | DEL D661 - Completion of System Test DW/BI - Draft Submission | 0 hrs | 0 days | Thu 4/3/25 | Thu 4/3/25 | 749750751 | 753 |  | Stacey Terry,Joy Schneider
4784 | 753 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 4/4/25 | Thu 4/10/25 | 752 | 754 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4785 | 754 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Style Guide Review | 1 hr | 1 day | Fri 4/11/25 | Fri 4/11/25 | 753 | 755 |  | Dusti Kincl
4786 | 755 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Final Collaborative Review | 20 hrs | 5 days | Mon 4/14/25 | Fri 4/18/25 | 754 | 756 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4787 | 756 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Accenture QC | 4 hrs | 2 days | Mon 4/21/25 | Tue 4/22/25 | 755 | 757 |  | Joy Schneider
4788 | 757 | Future Task |  |  | D661 | Stacey Terry | Submit | DEL D661 - Completion of System Test DW/BI - Submit | 0 hrs | 0 days | Tue 4/22/25 | Tue 4/22/25 | 756 | 758 |  | Joy Schneider
4789 | 758 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Department QC | 4 hrs | 1 day | Wed 4/23/25 | Wed 4/23/25 | 757 | 759 |  | Tommy Werner,Gabriela Gibson
4790 | 759 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Contract Manager Review | 8 hrs | 3 days | Thu 4/24/25 | Mon 4/28/25 | 758 | 760 |  | Sean Buchanan
4791 | 760 | Future Task |  |  | D661 | Stacey Terry | Accept | DEL D661 - Completion of System Test DW/BI - Accept | 0 hrs | 0 days | Mon 4/28/25 | Mon 4/28/25 | 759 |  | 2025-05-01 | Sean Buchanan
4792 | 761 | Future Task | Yes |  | D662 | Manojkumar Gurjar |  | D662 - Completion of Dress Rehearsal (Mock Conversion IV) | 197 hrs | 72 days | Mon 2/17/25 | Wed 5/28/25
4793 | 762 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Create | 16 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 720FS-22 days | 763 |  | Manojkumar Gurjar,Kurt Meisner
4794 | 763 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 762 | 764 |  | Manojkumar Gurjar,Joy Schneider
4795 | 764 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Collaborative Review | 24 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 763 | 765 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4796 | 765 | Future Task |  |  | D662 | Manojkumar Gurjar | Approve | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Approve | 0 hrs | 0 days | Fri 3/14/25 | Fri 3/14/25 | 764 | 766 |  | Jimmy Cox
4827 | 766 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Confirm Mock 4 Conversion - (Dress Rehearsal) Environment Readiness | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 765 | 767 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4828 | 767 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Create Mock 4 Conversion Checklist (Dress Rehearsal) | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 766 | 768 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4829 | 768 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Execute Mock 4 – Conversion (Dress Rehearsal) | 20 hrs | 10 days | Mon 3/31/25 | Fri 4/11/25 | 767 | 769 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4830 | 769 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Validate Mock 4 – Conversion (Dress Rehearsal) | 20 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 768 | 770 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4831 | 770 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Conduct Mock 4 - Conversion (Dress Rehearsal) Exit Criteria Review Meeting | 20 hrs | 5 days | Mon 4/28/25 | Fri 5/2/25 | 769 | 771 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4797 | 771 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Draft Submission | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 770 | 772 |  | Manojkumar Gurjar,Joy Schneider
4798 | 772 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 5/5/25 | Fri 5/9/25 | 771 | 773 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4799 | 773 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Style Guide Review | 1 hr | 1 day | Mon 5/12/25 | Mon 5/12/25 | 772 | 774 |  | Dusti Kincl
4800 | 774 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Final Collaborative Review | 20 hrs | 5 days | Tue 5/13/25 | Mon 5/19/25 | 773 | 775 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4801 | 775 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Accenture QC | 4 hrs | 2 days | Tue 5/20/25 | Wed 5/21/25 | 774 | 776 |  | Joy Schneider
4802 | 776 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Submit | 0 hrs | 0 days | Wed 5/21/25 | Wed 5/21/25 | 775 | 777 |  | Joy Schneider
4803 | 777 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Department QC | 4 hrs | 1 day | Thu 5/22/25 | Thu 5/22/25 | 776 | 778 |  | Tommy Werner,Gabriela Gibson
4804 | 778 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Contract Manager Review | 8 hrs | 3 days | Fri 5/23/25 | Wed 5/28/25 | 777 | 779 |  | Sean Buchanan
4805 | 779 | Future Task |  |  | D662 | Manojkumar Gurjar | Accept | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Accept | 0 hrs | 0 days | Wed 5/28/25 | Wed 5/28/25 | 778 | 1252 | 2025-05-01 | Sean Buchanan
4806 | 780 | Future Task | Yes |  | D663 | Manojkumar Gurjar |  | D663 - Completion of Interface Testing Segment I | 236.58 hrs | 204 days | Mon 9/9/24 | Mon 6/30/25
4807 | 781 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | DED D663 - Completion of Interface Testing Segment I - Create | 24 hrs | 10 days | Mon 9/9/24 | Fri 9/20/24 | 1 | 782 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4808 | 782 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DED D663 - Completion of Interface Testing Segment I - Submit | 0 hrs | 0 days | Fri 9/20/24 | Fri 9/20/24 | 781 | 783 |  | Manojkumar Gurjar,Joy Schneider
4809 | 783 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DED D663 - Completion of Interface Testing Segment I - Collaborative Review | 28 hrs | 10 days | Mon 9/23/24 | Fri 10/4/24 | 782 | 784 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4810 | 784 | Future Task |  |  | D663 | Manojkumar Gurjar | Approve | DED D663 - Completion of Interface Testing Segment I - Approve | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 783 | 785 |  | Jimmy Cox
4832 | 785 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Create Interface Testing Segment 1 Execution Work Unit Tracker | 30 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 784 | 786,790SS |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4833 | 786 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Review/Confirm Interface Testing Segment 1 Execution Work Unit Tracker | 15 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 785 | 787 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4834 | 787 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Conduct Interface Testing Segment 1 Readiness Review Meeting | 15 hrs | 5 days | Mon 10/28/24 | Fri 11/1/24 | 786 | 788 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4835 | 788 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Conduct Interface Test Kickoff Meeting with Integration Partners | 3 hrs | 9 days | Mon 11/4/24 | Fri 11/15/24 | 787 | 789 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4836 | 789 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Confirm Interface Test Environment Readiness | 15 hrs | 5 days | Mon 11/18/24 | Fri 11/22/24 | 788563 | 791 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4837 | 790 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Establish Interface Connectivity Segment 1 | 20 hrs | 20 days | Mon 10/7/24 | Fri 11/1/24 | 785SS | 791FS+17 days |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4838 | 791 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Execute Interface Testing Segment 1 - This is WU | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 790FS+17 days,789 | 792793 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4839 | 792 | Future Task |  |  | D663 | Manojkumar Gurjar | Milestone | Milestone: Interface Testing Segment 1 Complete | 0 hrs | 0 days | Wed 4/30/25 | Wed 4/30/25 | 791 | 795 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4840 | 793 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Conduct Test Exit Criteria Review Meeting | 15 hrs | 5 days | Thu 5/1/25 | Wed 5/7/25 | 791 | 794 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4841 | 794 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Confirm requirements traceability for Interface Testing Segment 1 | 15 hrs | 10 days | Thu 5/8/25 | Wed 5/21/25 | 793 | 795 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4842 | 795 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Create Completion of Interface Testing Segment 1 Summary Document | 1.58 hrs | 10 days | Thu 5/22/25 | Thu 6/5/25 | 794792 | 796 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4811 | 796 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DEL D663 - Completion of Interface Testing Segment I - Draft Submission | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 795 | 797 |  | Manojkumar Gurjar,Joy Schneider
4812 | 797 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Pre-Submission Collaborative Review | 6 hrs | 5 days | Fri 6/6/25 | Thu 6/12/25 | 796 | 798 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4813 | 798 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Style Guide Review | 1 hr | 1 day | Fri 6/13/25 | Fri 6/13/25 | 797 | 799 |  | Dusti Kincl
4814 | 799 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Final Collaborative Review | 12 hrs | 5 days | Mon 6/16/25 | Fri 6/20/25 | 798 | 800 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4815 | 800 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Accenture QC | 4 hrs | 2 days | Mon 6/23/25 | Tue 6/24/25 | 799 | 801 |  | Joy Schneider
4816 | 801 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DEL D663 - Completion of Interface Testing Segment I - Submit | 0 hrs | 0 days | Tue 6/24/25 | Tue 6/24/25 | 800 | 802 |  | Joy Schneider
4817 | 802 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Department QC | 4 hrs | 1 day | Wed 6/25/25 | Wed 6/25/25 | 801 | 803 |  | Tommy Werner,Gabriela Gibson
4818 | 803 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Contract Manager Review | 8 hrs | 3 days | Thu 6/26/25 | Mon 6/30/25 | 802 | 804 |  | Sean Buchanan
4819 | 804 | Future Task |  |  | D663 | Manojkumar Gurjar | Accept | DEL D663 - Completion of Interface Testing Segment I - Accept | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 803 |  | 2025-06-01 | Sean Buchanan
5042 | 805 | Future Task | Yes |  | D666 | Stacey Terry |  | D666 - Support of UAT Segment I | 111 hrs | 95 days | Mon 2/17/25 | Mon 6/30/25
5043 | 806 | Future Task |  |  | D666 | Stacey Terry | Create | DED D666 - Support of UAT Segment I - Create | 16 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 1 | 807 |  | Stacey Terry,Mary Punty
5044 | 807 | Future Task |  |  | D666 | Stacey Terry | Submit | DED D666 - Support of UAT Segment I - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 806 | 808 |  | Stacey Terry,Joy Schneider
5045 | 808 | Future Task |  |  | D666 | Stacey Terry | Review | DED D666 - Support of UAT Segment I - Collaborative Review | 24 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 807 | 809 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5046 | 809 | Future Task |  |  | D666 | Stacey Terry | Approve | DED D666 - Support of UAT Segment I - Approve | 0 hrs | 0 days | Fri 3/14/25 | Fri 3/14/25 | 808 | 810 |  | Jimmy Cox
5056 | 810 | Future Task |  |  | D666 | Stacey Terry |  | Identify UAT support resources for UAT Segment 1 | 20 hrs | 11 days | Mon 3/17/25 | Mon 3/31/25 | 809 | 811 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5057 | 811 | Future Task |  |  | D666 | Stacey Terry |  | Participate in UAT sessions for UAT Segment 1 | 6 hrs | 43 days | Tue 4/1/25 | Fri 5/30/25 | 810 | 812SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp
5058 | 812 | Future Task |  |  | D666 | Stacey Terry |  | Support resolution of UAT issues for UAT Segment 1 | 7 hrs | 42 days | Tue 4/1/25 | Thu 5/29/25 | 811SS | 813FS-4 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
5059 | 813 | Future Task |  |  | D666 | Stacey Terry |  | Confirm requirements traceability for UAT Segment 1 | 3 hrs | 4 days | Fri 5/23/25 | Thu 5/29/25 | 812FS-4 days | 814SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5060 | 814 | Future Task |  |  | D666 | Stacey Terry |  | Create UAT Segment 1 Summary Document | 3 hrs | 9 days | Fri 5/23/25 | Thu 6/5/25 | 813SS | 815 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5047 | 815 | Future Task |  |  | D666 | Stacey Terry | Submit | DEL D666 - Support of UAT Segment I - Draft Submission | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 814 | 816 |  | Stacey Terry,Joy Schneider
5048 | 816 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Pre-Submission Collaborative Review | 5 hrs | 5 days | Fri 6/6/25 | Thu 6/12/25 | 815 | 817 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5049 | 817 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Style Guide Review | 1 hr | 1 day | Fri 6/13/25 | Fri 6/13/25 | 816 | 818 |  | Dusti Kincl
5050 | 818 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Final Collaborative Review | 10 hrs | 5 days | Mon 6/16/25 | Fri 6/20/25 | 817 | 819 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5051 | 819 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Accenture QC | 4 hrs | 2 days | Mon 6/23/25 | Tue 6/24/25 | 818 | 820 |  | Joy Schneider
5052 | 820 | Future Task |  |  | D666 | Stacey Terry | Submit | DEL D666 - Support of UAT Segment I - Submit | 0 hrs | 0 days | Tue 6/24/25 | Tue 6/24/25 | 819 | 821 |  | Joy Schneider
5053 | 821 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Department QC | 4 hrs | 1 day | Wed 6/25/25 | Wed 6/25/25 | 820 | 822 |  | Tommy Werner,Gabriela Gibson
5054 | 822 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Contract Manager Review | 8 hrs | 3 days | Thu 6/26/25 | Mon 6/30/25 | 821 | 823 |  | Sean Buchanan
5055 | 823 | Future Task |  |  | D666 | Stacey Terry | Accept | DEL D666 - Support of UAT Segment I - Accept | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 822 |  | 2025-06-01 | Sean Buchanan
5520 | 824 | Future Task | Yes |  | D667 | Stacey Terry |  | D667 - Completion of Mock Go-Lives (Dry Run #1) | 108 hrs | 62 days | Fri 5/2/25 | Wed 7/30/25
5521 | 825 | Future Task |  |  | D667 | Stacey Terry | Create | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Create | 6 hrs | 10 days | Fri 5/2/25 | Thu 5/15/25 | 1 | 826 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5522 | 826 | Future Task |  |  | D667 | Stacey Terry | Submit | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Submit | 0 hrs | 0 days | Thu 5/15/25 | Thu 5/15/25 | 825 | 827 |  | Stacey Terry,Joy Schneider
5523 | 827 | Future Task |  |  | D667 | Stacey Terry | Review | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Collaborative Review | 8 hrs | 10 days | Fri 5/16/25 | Fri 5/30/25 | 826 | 828 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5524 | 828 | Future Task |  |  | D667 | Stacey Terry | Approve | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Approve | 0 hrs | 0 days | Fri 5/30/25 | Fri 5/30/25 | 827 | 829 |  | Jimmy Cox
6697 | 829 | Future Task |  |  | D667 | Stacey Terry |  | Confirm Mock Go-Live Dry Run #1 Execution Readiness | 3 hrs | 5 days | Mon 6/2/25 | Fri 6/6/25 | 828571 | 830 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6698 | 830 | Future Task |  |  | D667 | Stacey Terry |  | Execute Mock Go-Live Dry Run #1 | 6 hrs | 10 days | Mon 6/9/25 | Fri 6/20/25 | 829 | 831 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6699 | 831 | Future Task |  |  | D667 | Stacey Terry |  | Document Mock Go-Live Dry Run Results #1 | 6 hrs | 5 days | Mon 6/23/25 | Fri 6/27/25 | 830 | 832 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6700 | 832 | Future Task |  |  | D667 | Stacey Terry |  | Create Mock Go-Live Dry Run #1 Summary Document | 6 hrs | 5 days | Mon 6/30/25 | Mon 7/7/25 | 831 | 833 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5525 | 833 | Future Task |  |  | D667 | Stacey Terry | Submit | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Draft Submission | 0 hrs | 0 days | Mon 7/7/25 | Mon 7/7/25 | 832 | 834 |  | Stacey Terry,Joy Schneider
5526 | 834 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Pre-Submission Collaborative Review | 28 hrs | 5 days | Tue 7/8/25 | Mon 7/14/25 | 833 | 835 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5527 | 835 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Style Guide Review | 1 hr | 1 day | Tue 7/15/25 | Tue 7/15/25 | 834 | 836 |  | Dusti Kincl
5528 | 836 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Final Collaborative Review | 28 hrs | 5 days | Wed 7/16/25 | Tue 7/22/25 | 835 | 837 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5529 | 837 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Accenture QC | 4 hrs | 2 days | Wed 7/23/25 | Thu 7/24/25 | 836 | 838 |  | Joy Schneider
5530 | 838 | Future Task |  |  | D667 | Stacey Terry | Submit | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Submit | 0 hrs | 0 days | Thu 7/24/25 | Thu 7/24/25 | 837 | 839 |  | Joy Schneider
5531 | 839 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Department QC | 4 hrs | 1 day | Fri 7/25/25 | Fri 7/25/25 | 838 | 840 |  | Tommy Werner,Gabriela Gibson
5532 | 840 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Contract Manager Review | 8 hrs | 3 days | Mon 7/28/25 | Wed 7/30/25 | 839 | 841 |  | Sean Buchanan
5533 | 841 | Future Task |  |  | D667 | Stacey Terry | Accept | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Accept | 0 hrs | 0 days | Wed 7/30/25 | Wed 7/30/25 | 840 | 1252 | 2025-07-01 | Sean Buchanan
5061 | 842 | Future Task | Yes |  | D669 | Stacey Terry |  | D669 - Support of UAT Segment II | 132 hrs | 72 days | Mon 5/19/25 | Thu 8/28/25
5062 | 843 | Future Task |  |  | D669 | Stacey Terry | Create | DED D669 - Support of UAT Segment II - Create | 2 hrs | 10 days | Mon 5/19/25 | Mon 6/2/25 | 1 | 844 |  | Stacey Terry,Mary Punty
5063 | 844 | Future Task |  |  | D669 | Stacey Terry | Submit | DED D669 - Support of UAT Segment II - Submit | 0 hrs | 0 days | Mon 6/2/25 | Mon 6/2/25 | 843 | 845 |  | Stacey Terry,Joy Schneider
5064 | 845 | Future Task |  |  | D669 | Stacey Terry | Review | DED D669 - Support of UAT Segment II - Collaborative Review | 12 hrs | 10 days | Tue 6/3/25 | Mon 6/16/25 | 844 | 846 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5065 | 846 | Future Task |  |  | D669 | Stacey Terry | Approve | DED D669 - Support of UAT Segment II - Approve | 0 hrs | 0 days | Mon 6/16/25 | Mon 6/16/25 | 845 | 847FS+4 days |  | Jimmy Cox
5075 | 847 | Future Task |  |  | D669 | Stacey Terry |  | Identify UAT support resources for UAT Segment 2 | 6 hrs | 5 days | Mon 6/23/25 | Fri 6/27/25 | 846FS+4 days | 848 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5076 | 848 | Future Task |  |  | D669 | Stacey Terry |  | Participate in UAT sessions for UAT Segment 2 | 6 hrs | 23 days | Mon 6/30/25 | Thu 7/31/25 | 847 | 849SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp
5077 | 849 | Future Task |  |  | D669 | Stacey Terry |  | Support resolution of UAT issues for UAT Segment 2 | 7 hrs | 23 days | Mon 6/30/25 | Thu 7/31/25 | 848SS | 850FS-4 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
5078 | 850 | Future Task |  |  | D669 | Stacey Terry |  | Confirm requirements traceability for UAT Segment 2 | 21 hrs | 7 days | Mon 7/28/25 | Tue 8/5/25 | 849FS-4 days | 851SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5079 | 851 | Future Task |  |  | D669 | Stacey Terry |  | Create UAT Segment 2 Summary Document | 21 hrs | 7 days | Mon 7/28/25 | Tue 8/5/25 | 850SS | 852 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5066 | 852 | Future Task |  |  | D669 | Stacey Terry | Submit | DEL D669 - Support of UAT Segment II - Draft Submission | 0 hrs | 0 days | Tue 8/5/25 | Tue 8/5/25 | 851 | 853 |  | Stacey Terry,Joy Schneider
5067 | 853 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | Wed 8/6/25 | Tue 8/12/25 | 852 | 854 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5068 | 854 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Style Guide Review | 1 hr | 1 day | Wed 8/13/25 | Wed 8/13/25 | 853 | 855 |  | Dusti Kincl
5069 | 855 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Final Collaborative Review | 20 hrs | 5 days | Thu 8/14/25 | Wed 8/20/25 | 854 | 856 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5070 | 856 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Accenture QC | 4 hrs | 2 days | Thu 8/21/25 | Fri 8/22/25 | 855 | 857 |  | Joy Schneider
5071 | 857 | Future Task |  |  | D669 | Stacey Terry | Submit | DEL D669 - Support of UAT Segment II - Submit | 0 hrs | 0 days | Fri 8/22/25 | Fri 8/22/25 | 856 | 858 |  | Joy Schneider
5072 | 858 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Department QC | 4 hrs | 1 day | Mon 8/25/25 | Mon 8/25/25 | 857 | 859 |  | Tommy Werner,Gabriela Gibson
5073 | 859 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Contract Manager Review | 8 hrs | 3 days | Tue 8/26/25 | Thu 8/28/25 | 858 | 860 |  | Sean Buchanan
5074 | 860 | Future Task |  |  | D669 | Stacey Terry | Accept | DEL D669 - Support of UAT Segment II - Accept | 0 hrs | 0 days | Thu 8/28/25 | Thu 8/28/25 | 859 |  | 2025-08-01 | Sean Buchanan
4843 | 861 | Future Task | Yes |  | D670 | Stacey Terry |  | D670 - Completion of Payroll Parallel Testing | 254 hrs | 133 days | Mon 2/24/25 | Fri 8/29/25
4844 | 862 | Future Task |  |  | D670 | Stacey Terry | Create | DED D670 - Completion of Payroll Parallel Testing - Create | 16 hrs | 10 days | Mon 2/24/25 | Fri 3/7/25 | 739FS-37 days | 863 |  | Stacey Terry,Mary Punty
4845 | 863 | Future Task |  |  | D670 | Stacey Terry | Submit | DED D670 - Completion of Payroll Parallel Testing - Submit | 0 hrs | 0 days | Fri 3/7/25 | Fri 3/7/25 | 862 | 864 |  | Stacey Terry,Joy Schneider
4846 | 864 | Future Task |  |  | D670 | Stacey Terry | Review | DED D670 - Completion of Payroll Parallel Testing - Collaborative Review | 24 hrs | 10 days | Mon 3/10/25 | Fri 3/21/25 | 863 | 865 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4847 | 865 | Future Task |  |  | D670 | Stacey Terry | Approve | DED D670 - Completion of Payroll Parallel Testing - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 864 | 866 |  | Jimmy Cox
4955 | 866 | Future Task |  |  | D670 | Stacey Terry |  | Create Work Unit Tracker for Payroll Parallel Test Execution | 40 hrs | 10 days | Mon 3/24/25 | Fri 4/4/25 | 865 | 867 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty
4956 | 867 | Future Task |  |  | D670 | Stacey Terry |  | Review, Update and confirm Work Unit Tracker for Payroll Parallel Test Execution | 20 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 866 | 868 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Jennifer Peddicord
4957 | 868 | Future Task |  |  | D670 | Stacey Terry |  | Confirm Payroll Parallel Test Environment Readiness | 20 hrs | 5 days | Mon 4/21/25 | Fri 4/25/25 | 867 | 869 |  | Manojkumar Gurjar,Jarad Hermann
4958 | 869 | Future Task |  |  | D670 | Stacey Terry |  | Conduct Parallel Payroll Test Kick Off Meeting | 12 hrs | 5 days | Mon 4/28/25 | Fri 5/2/25 | 868 | 870 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Jennifer Peddicord
4959 | 870 | Future Task |  |  | D670 | Stacey Terry |  | Execute Parallel Payroll Testing - this is a WU | 5 hrs | 60 days | Mon 5/5/25 | Tue 7/29/25 | 869 | 871,872FS-4 days |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
4960 | 871 | Future Task |  |  | D670 | Stacey Terry | Milestone | Milestone: Payroll Parallel Test Execution Complete | 0 hrs | 0 days | Tue 7/29/25 | Tue 7/29/25 | 870 | 875 |  | Stacey Terry
4961 | 872 | Future Task |  |  | D670 | Stacey Terry |  | Conduct Payroll Parallel Test Exit Criteria Review Meeting | 10 hrs | 10 days | Thu 7/24/25 | Wed 8/6/25 | 870FS-4 days | 873SS,874SS,875 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
4962 | 873 | Future Task |  |  | D670 | Stacey Terry |  | Confirm requirements traceability for Payroll Parallel test | 20 hrs | 10 days | Thu 7/24/25 | Wed 8/6/25 | 872SS | 875 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty
4963 | 874 | Future Task |  |  | D670 | Stacey Terry |  | Create Completion of Payroll Parallel Test Summary Document | 30 hrs | 10 days | Thu 7/24/25 | Wed 8/6/25 | 872SS | 875 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4848 | 875 | Future Task |  |  | D670 | Stacey Terry | Submit | DEL D670 - Completion of Payroll Parallel Testing - Draft Submission | 0 hrs | 0 days | Wed 8/6/25 | Wed 8/6/25 | 871872874873 | 876 |  | Stacey Terry,Joy Schneider
4849 | 876 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Pre-Submission Collaborative Review | 20 hrs | 5 days | Thu 8/7/25 | Wed 8/13/25 | 875 | 877 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4850 | 877 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Style Guide Review | 1 hr | 1 day | Thu 8/14/25 | Thu 8/14/25 | 876 | 878 |  | Dusti Kincl
4851 | 878 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Final Collaborative Review | 20 hrs | 5 days | Fri 8/15/25 | Thu 8/21/25 | 877 | 879 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4852 | 879 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Accenture QC | 4 hrs | 2 days | Fri 8/22/25 | Mon 8/25/25 | 878 | 880 |  | Joy Schneider
4853 | 880 | Future Task |  |  | D670 | Stacey Terry | Submit | DEL D670 - Completion of Payroll Parallel Testing - Submit | 0 hrs | 0 days | Mon 8/25/25 | Mon 8/25/25 | 879 | 881 |  | Joy Schneider
4854 | 881 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Department QC | 4 hrs | 1 day | Tue 8/26/25 | Tue 8/26/25 | 880 | 882 |  | Tommy Werner,Gabriela Gibson
4855 | 882 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Contract Manager Review | 8 hrs | 3 days | Wed 8/27/25 | Fri 8/29/25 | 881 | 883 |  | Sean Buchanan
4856 | 883 | Future Task |  |  | D670 | Stacey Terry | Accept | DEL D670 - Completion of Payroll Parallel Testing - Accept | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 882 |  | 2025-08-01 | Sean Buchanan
4857 | 884 | Future Task | Yes |  | D671 | Manojkumar Gurjar |  | D671 - Completion of Interface Testing Segment II | 291 hrs | 160 days | Mon 3/3/25 | Wed 10/15/25
4858 | 885 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | DED D671 - Completion of Interface Testing Segment II - Create | 6 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1 | 886 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4859 | 886 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DED D671 - Completion of Interface Testing Segment II - Submit | 0 hrs | 0 days | Fri 3/14/25 | Fri 3/14/25 | 885 | 887 |  | Manojkumar Gurjar,Joy Schneider
4860 | 887 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DED D671 - Completion of Interface Testing Segment II - Collaborative Review | 8 hrs | 10 days | Mon 3/17/25 | Fri 3/28/25 | 886 | 888 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4861 | 888 | Future Task |  |  | D671 | Manojkumar Gurjar | Approve | DED D671 - Completion of Interface Testing Segment II - Approve | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 887 | 889 |  | Jimmy Cox
4964 | 889 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Create Interface Testing Segment 2 Execution Work Unit Tracker | 6 hrs | 4 days | Mon 3/31/25 | Thu 4/3/25 | 888 | 890 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4965 | 890 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Review/Confirm Interface Testing Segment 2 Execution Work Unit Tracker | 6 hrs | 4 days | Fri 4/4/25 | Wed 4/9/25 | 889 | 891 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4966 | 891 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Conduct Interface Testing Segment 2 Readiness Review Meeting | 15 hrs | 5 days | Thu 4/10/25 | Wed 4/16/25 | 890 | 892 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4967 | 892 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Conduct Interface Test Kickoff Meeting with Integration Partners | 30 hrs | 5 days | Thu 4/17/25 | Wed 4/23/25 | 891 | 893 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4968 | 893 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Confirm Interface Test Environment Readiness | 15 hrs | 5 days | Thu 4/24/25 | Wed 4/30/25 | 892 | 894 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4969 | 894 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Establish Interface Connectivity Segment 2 | 20 hrs | 7 days | Thu 5/1/25 | Fri 5/9/25 | 893 | 895 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4970 | 895 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Execute Interface Testing Segment 2 - This is WU | 10 hrs | 78 days | Mon 5/12/25 | Fri 8/29/25 | 894 | 896 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4971 | 896 | Future Task |  |  | D671 | Manojkumar Gurjar | Milestone | Milestone: Interface Testing Segment 2 Complete | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 895 | 897 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4972 | 897 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Conduct Test Exit Criteria Review Meeting | 30 hrs | 5 days | Tue 9/2/25 | Mon 9/8/25 | 896 | 898 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4973 | 898 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Confirm requirements traceability for Interface Testing Segment 2 | 40 hrs | 5 days | Tue 9/9/25 | Mon 9/15/25 | 897 | 899 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4974 | 899 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Create Completion of Interface Testing Segment 2 deliverable (D671) | 40 hrs | 5 days | Tue 9/16/25 | Mon 9/22/25 | 898 | 900 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4862 | 900 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DEL D671 - Completion of Interface Testing Segment II - Draft Submission | 0 hrs | 0 days | Mon 9/22/25 | Mon 9/22/25 | 899 | 901 |  | Manojkumar Gurjar,Joy Schneider
4863 | 901 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Pre-Submission Collaborative Review | 24 hrs | 5 days | Tue 9/23/25 | Mon 9/29/25 | 900 | 902 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4864 | 902 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Style Guide Review | 1 hr | 1 day | Tue 9/30/25 | Tue 9/30/25 | 901 | 903 |  | Dusti Kincl
4865 | 903 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Final Collaborative Review | 24 hrs | 5 days | Wed 10/1/25 | Tue 10/7/25 | 902 | 904 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4866 | 904 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Accenture QC | 4 hrs | 2 days | Wed 10/8/25 | Thu 10/9/25 | 903 | 905 |  | Joy Schneider
4867 | 905 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DEL D671 - Completion of Interface Testing Segment II - Submit | 0 hrs | 0 days | Thu 10/9/25 | Thu 10/9/25 | 904 | 906 |  | Joy Schneider
4868 | 906 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Department QC | 4 hrs | 1 day | Fri 10/10/25 | Fri 10/10/25 | 905 | 907 |  | Tommy Werner,Gabriela Gibson
4869 | 907 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Contract Manager Review | 8 hrs | 3 days | Mon 10/13/25 | Wed 10/15/25 | 906 | 908 |  | Sean Buchanan
4870 | 908 | Future Task |  |  | D671 | Manojkumar Gurjar | Accept | DEL D671 - Completion of Interface Testing Segment II - Accept | 0 hrs | 0 days | Wed 10/15/25 | Wed 10/15/25 | 907 |  | 2025-10-01 | Sean Buchanan
4871 | 909 | Future Task | Yes |  | D672 | Stacey Terry |  | D672 - Support of UAT Segment III | 122 hrs | 67 days | Fri 8/22/25 | Wed 11/26/25
4872 | 910 | Future Task |  |  | D672 | Stacey Terry | Create | DED D672 - Support of UAT Segment III - Create | 16 hrs | 10 days | Fri 8/22/25 | Fri 9/5/25 | 1 | 911 |  | Stacey Terry,Mary Punty
4873 | 911 | Future Task |  |  | D672 | Stacey Terry | Submit | DED D672 - Support of UAT Segment III - Submit | 0 hrs | 0 days | Fri 9/5/25 | Fri 9/5/25 | 910 | 912 |  | Stacey Terry,Joy Schneider
4874 | 912 | Future Task |  |  | D672 | Stacey Terry | Review | DED D672 - Support of UAT Segment III - Collaborative Review | 24 hrs | 10 days | Mon 9/8/25 | Fri 9/19/25 | 911 | 913 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4875 | 913 | Future Task |  |  | D672 | Stacey Terry | Approve | DED D672 - Support of UAT Segment III - Approve | 0 hrs | 0 days | Fri 9/19/25 | Fri 9/19/25 | 912 | 914 |  | Jimmy Cox
4975 | 914 | Future Task |  |  | D672 | Stacey Terry |  | Identify UAT support resources for UAT Segment 3 | 12 hrs | 7 days | Mon 9/22/25 | Tue 9/30/25 | 913 | 915 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4976 | 915 | Future Task |  |  | D672 | Stacey Terry |  | Participate in UAT sessions for UAT Segment 3 | 6 hrs | 21 days | Wed 10/1/25 | Wed 10/29/25 | 914 | 916SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp
4977 | 916 | Future Task |  |  | D672 | Stacey Terry |  | Support resolution of UAT issues for UAT Segment 3 | 7 hrs | 21 days | Wed 10/1/25 | Wed 10/29/25 | 915SS | 917FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
4978 | 917 | Future Task |  |  | D672 | Stacey Terry |  | Confirm requirements traceability for UAT Segment 3 | 3 hrs | 7 days | Thu 10/23/25 | Fri 10/31/25 | 916FS-5 days | 918SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4979 | 918 | Future Task |  |  | D672 | Stacey Terry |  | Create UAT Segment 3 Summary Document | 3 hrs | 7 days | Thu 10/23/25 | Fri 10/31/25 | 917SS | 919 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4876 | 919 | Future Task |  |  | D672 | Stacey Terry | Submit | DEL D672 - Support of UAT Segment III - Draft Submission | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 918 | 920 |  | Stacey Terry,Joy Schneider
4877 | 920 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | Mon 11/3/25 | Fri 11/7/25 | 919 | 921 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4878 | 921 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Style Guide Review | 1 hr | 1 day | Mon 11/10/25 | Mon 11/10/25 | 920 | 922 |  | Dusti Kincl
4879 | 922 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Final Collaborative Review | 20 hrs | 5 days | Wed 11/12/25 | Tue 11/18/25 | 921 | 923 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4880 | 923 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Accenture QC | 4 hrs | 2 days | Wed 11/19/25 | Thu 11/20/25 | 922 | 924 |  | Francisca Li
4881 | 924 | Future Task |  |  | D672 | Stacey Terry | Submit | DEL D672 - Support of UAT Segment III - Submit | 0 hrs | 0 days | Thu 11/20/25 | Thu 11/20/25 | 923 | 925 |  | Joy Schneider
4882 | 925 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Department QC | 4 hrs | 1 day | Fri 11/21/25 | Fri 11/21/25 | 924 | 926 |  | Tommy Werner,Gabriela Gibson
4883 | 926 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Contract Manager Review | 2 hrs | 3 days | Mon 11/24/25 | Wed 11/26/25 | 925 | 927 |  | Sean Buchanan
4884 | 927 | Future Task |  |  | D672 | Stacey Terry | Accept | DEL D672 - Support of UAT Segment III - Accept | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 926 |  | 2025-11-01 | Sean Buchanan
4885 | 928 | Future Task | Yes |  | D673 | Stacey Terry |  | D673 - Completion of Mock Go-Lives (Dry Run #2) | 223 hrs | 66 days | Mon 8/4/25 | Tue 11/4/25
4886 | 929 | Future Task |  |  | D673 | Stacey Terry | Create | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Create | 24 hrs | 10 days | Mon 8/4/25 | Fri 8/15/25 | 1 | 930 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4887 | 930 | Future Task |  |  | D673 | Stacey Terry | Submit | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Submit | 0 hrs | 0 days | Fri 8/15/25 | Fri 8/15/25 | 929 | 931 |  | Stacey Terry,Joy Schneider
4888 | 931 | Future Task |  |  | D673 | Stacey Terry | Review | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Collaborative Review | 32 hrs | 10 days | Mon 8/18/25 | Fri 8/29/25 | 930 | 932 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4889 | 932 | Future Task |  |  | D673 | Stacey Terry | Approve | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Approve | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 931 | 933 |  | Jimmy Cox
4980 | 933 | Future Task |  |  | D673 | Stacey Terry |  | Confirm Mock Go-Live Dry Run #2 Execution Readiness | 24 hrs | 4 days | Tue 9/2/25 | Fri 9/5/25 | 932 | 934 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4981 | 934 | Future Task |  |  | D673 | Stacey Terry |  | Execute Mock Go-Live Dry Run #2 | 20 hrs | 10 days | Mon 9/8/25 | Fri 9/19/25 | 933 | 935 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4982 | 935 | Future Task |  |  | D673 | Stacey Terry |  | Document Mock Go-Live Dry Run Results #2 | 30 hrs | 5 days | Mon 9/22/25 | Fri 9/26/25 | 934 | 936 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4983 | 936 | Future Task |  |  | D673 | Stacey Terry |  | Create Mock Go-Live Dry Run #2 Summary Document | 20 hrs | 10 days | Mon 9/29/25 | Fri 10/10/25 | 935 | 937 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4890 | 937 | Future Task |  |  | D673 | Stacey Terry | Submit | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Draft Submission | 0 hrs | 0 days | Fri 10/10/25 | Fri 10/10/25 | 936 | 938 |  | Stacey Terry,Joy Schneider
4891 | 938 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Pre-Submission Collaborative Review | 28 hrs | 5 days | Mon 10/13/25 | Fri 10/17/25 | 937 | 939 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4892 | 939 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Style Guide Review | 1 hr | 1 day | Mon 10/20/25 | Mon 10/20/25 | 938 | 940 |  | Dusti Kincl
4893 | 940 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Final Collaborative Review | 28 hrs | 5 days | Tue 10/21/25 | Mon 10/27/25 | 939 | 941 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4894 | 941 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Accenture QC | 4 hrs | 2 days | Tue 10/28/25 | Wed 10/29/25 | 940 | 942 |  | Joy Schneider
4895 | 942 | Future Task |  |  | D673 | Stacey Terry | Submit | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Submit | 0 hrs | 0 days | Wed 10/29/25 | Wed 10/29/25 | 941 | 943 |  | Joy Schneider
4896 | 943 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Department QC | 4 hrs | 1 day | Thu 10/30/25 | Thu 10/30/25 | 942 | 944 |  | Tommy Werner,Gabriela Gibson
4897 | 944 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Contract Manager Review | 8 hrs | 3 days | Fri 10/31/25 | Tue 11/4/25 | 943 | 945 |  | Sean Buchanan
4898 | 945 | Future Task |  |  | D673 | Stacey Terry | Accept | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Accept | 0 hrs | 0 days | Tue 11/4/25 | Tue 11/4/25 | 944 | 1252 | 2025-11-01 | Sean Buchanan
4899 | 946 | Future Task | Yes |  | D674 | Jarad Hermann |  | D674 - Completion of Penetration Testing | 100 hrs | 145 days | Fri 5/2/25 | Wed 11/26/25
4900 | 947 | Future Task |  |  | D674 | Jarad Hermann | Create | DED D674 - Completion of Penetration Testing - Create | 2 hrs | 10 days | Fri 5/2/25 | Thu 5/15/25 | 1201FS+29 days,1236FS+29 days | 948 | Note: should be in version we go live with | Jarad Hermann,Mary Punty
4901 | 948 | Future Task |  |  | D674 | Jarad Hermann | Submit | DED D674 - Completion of Penetration Testing - Submit | 0 hrs | 0 days | Thu 5/15/25 | Thu 5/15/25 | 947 | 949 |  | Jarad Hermann,Joy Schneider
4902 | 949 | Future Task |  |  | D674 | Jarad Hermann | Review | DED D674 - Completion of Penetration Testing - Collaborative Review | 5 hrs | 10 days | Fri 5/16/25 | Fri 5/30/25 | 948 | 950 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4903 | 950 | Future Task |  |  | D674 | Jarad Hermann | Approve | DED D674 - Completion of Penetration Testing - Approve | 0 hrs | 0 days | Fri 5/30/25 | Fri 5/30/25 | 949 | 951 |  | Jimmy Cox
4984 | 951 | Future Task |  |  | D674 | Jarad Hermann |  | Execute/Complete Penetration Test | 10 hrs | 64 days | Mon 6/2/25 | Fri 8/29/25 | 950 | 952 |  | Jarad Hermann,Bryan Sohayda
4985 | 952 | Future Task |  |  | D674 | Jarad Hermann |  | Review Penetration Test Outcome | 10 hrs | 20 days | Tue 9/2/25 | Mon 9/29/25 | 951 | 953SS |  | Jarad Hermann,Bryan Sohayda
4986 | 953 | Future Task |  |  | D674 | Jarad Hermann |  | Remediate Penetration Test | 10 hrs | 44 days | Tue 9/2/25 | Fri 10/31/25 | 952SS | 954SS |  | Jarad Hermann,Bryan Sohayda
4987 | 954 | Future Task |  |  | D674 | Jarad Hermann |  | Create Final Pen Testing Results/Remediation Summary Report | 20 hrs | 44 days | Tue 9/2/25 | Fri 10/31/25 | 953SS | 955 |  | Jarad Hermann,Bryan Sohayda
4904 | 955 | Future Task |  |  | D674 | Jarad Hermann | Submit | DEL D674 - Completion of Penetration Testing - Draft Submission | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 954 | 956 |  | Jarad Hermann,Joy Schneider
4905 | 956 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 11/3/25 | Fri 11/7/25 | 955 | 957 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4906 | 957 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Style Guide Review | 1 hr | 1 day | Mon 11/10/25 | Mon 11/10/25 | 956 | 958 |  | Dusti Kincl
4907 | 958 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Final Collaborative Review | 16 hrs | 5 days | Wed 11/12/25 | Tue 11/18/25 | 957 | 959 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4908 | 959 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Accenture QC | 4 hrs | 2 days | Wed 11/19/25 | Thu 11/20/25 | 958 | 960 |  | Joy Schneider
4909 | 960 | Future Task |  |  | D674 | Jarad Hermann | Submit | DEL D674 - Completion of Penetration Testing - Submit | 0 hrs | 0 days | Thu 11/20/25 | Thu 11/20/25 | 959 | 961 |  | Joy Schneider
4910 | 961 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Department QC | 4 hrs | 1 day | Fri 11/21/25 | Fri 11/21/25 | 960 | 962 |  | Tommy Werner,Gabriela Gibson
4911 | 962 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Contract Manager Review | 2 hrs | 3 days | Mon 11/24/25 | Wed 11/26/25 | 961 | 963 |  | Sean Buchanan
4912 | 963 | Future Task |  |  | D674 | Jarad Hermann | Accept | DEL D674 - Completion of Penetration Testing - Accept | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 962 | 1252 | 2025-11-01 | Sean Buchanan
4913 | 964 | Future Task | Yes |  | D675 | Jarad Hermann |  | D675 - Completion of Performance Testing | 180 hrs | 145 days | Fri 5/2/25 | Wed 11/26/25
4914 | 965 | Future Task |  |  | D675 | Jarad Hermann | Create | DED D675 - Completion of Performance Testing - Create | 2 hrs | 10 days | Fri 5/2/25 | Thu 5/15/25 | 1189FS-14 days,1225FS-14 days | 966 |  | Jarad Hermann,Mary Punty
4915 | 966 | Future Task |  |  | D675 | Jarad Hermann | Submit | DED D675 - Completion of Performance Testing - Submit | 0 hrs | 0 days | Thu 5/15/25 | Thu 5/15/25 | 965 | 967 |  | Jarad Hermann,Joy Schneider
4916 | 967 | Future Task |  |  | D675 | Jarad Hermann | Review | DED D675 - Completion of Performance Testing - Collaborative Review | 5 hrs | 10 days | Fri 5/16/25 | Fri 5/30/25 | 966 | 968 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4917 | 968 | Future Task |  |  | D675 | Jarad Hermann | Approve | DED D675 - Completion of Performance Testing - Approve | 0 hrs | 0 days | Fri 5/30/25 | Fri 5/30/25 | 967 | 969 |  | Jimmy Cox
4988 | 969 | Future Task |  |  | D675 | Jarad Hermann |  | Execute Performance Testing | 4 hrs | 108 days | Mon 6/2/25 | Fri 10/31/25 | 968573 | 970FS-10 days,973 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4989 | 970 | Future Task |  |  | D675 | Jarad Hermann |  | Create Completion of Performance Testing Summary Document | 40 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 969FS-10 days | 971SS,972SS,973 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4990 | 971 | Future Task |  |  | D675 | Jarad Hermann |  | Conduct Performance Testing Exit Criteria Review Meeting | 40 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 970SS | 973 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4991 | 972 | Future Task |  |  | D675 | Jarad Hermann |  | Confirm requirements traceability for Performance Testing | 40 hrs | 10 days | Mon 10/20/25 | Fri 10/31/25 | 970SS | 973 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4918 | 973 | Future Task |  |  | D675 | Jarad Hermann | Submit | DEL D675 - Completion of Performance Testing - Draft Submission | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 972969970971 | 974 |  | Jarad Hermann,Joy Schneider
4919 | 974 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 11/3/25 | Fri 11/7/25 | 973 | 975 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4920 | 975 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Style Guide Review | 1 hr | 1 day | Mon 11/10/25 | Mon 11/10/25 | 974 | 976 |  | Dusti Kincl
4921 | 976 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Final Collaborative Review | 16 hrs | 5 days | Wed 11/12/25 | Tue 11/18/25 | 975 | 977 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4922 | 977 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Accenture QC | 4 hrs | 2 days | Wed 11/19/25 | Thu 11/20/25 | 976 | 978 |  | Joy Schneider
4923 | 978 | Future Task |  |  | D675 | Jarad Hermann | Submit | DEL D675 - Completion of Performance Testing - Submit | 0 hrs | 0 days | Thu 11/20/25 | Thu 11/20/25 | 977 | 979 |  | Joy Schneider
4924 | 979 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Department QC | 4 hrs | 1 day | Fri 11/21/25 | Fri 11/21/25 | 978 | 980 |  | Tommy Werner,Gabriela Gibson
4925 | 980 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Contract Manager Review | 8 hrs | 3 days | Mon 11/24/25 | Wed 11/26/25 | 979 | 981 |  | Sean Buchanan
4926 | 981 | Future Task |  |  | D675 | Jarad Hermann | Accept | DEL D675 - Completion of Performance Testing - Accept | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 980 | 1252 | 2025-11-01 | Sean Buchanan
4927 | 982 | Future Task | Yes |  | D676 | Jarad Hermann |  | D676 - Completion of Disaster Recovery Testing | 158 hrs | 114 days | Tue 3/4/25 | Tue 8/12/25
4928 | 983 | Future Task |  |  | D676 | Jarad Hermann | Create | DED D676 - Completion of Disaster Recovery Testing - Create | 8 hrs | 10 days | Tue 3/4/25 | Mon 3/17/25 | 1213FS-14 days,1175FS-14 days,1162 | 984 |  | Jarad Hermann,Mary Punty
4929 | 984 | Future Task |  |  | D676 | Jarad Hermann | Submit | DED D676 - Completion of Disaster Recovery Testing - Submit | 0 hrs | 0 days | Mon 3/17/25 | Mon 3/17/25 | 983 | 985 |  | Jarad Hermann,Joy Schneider
4930 | 985 | Future Task |  |  | D676 | Jarad Hermann | Review | DED D676 - Completion of Disaster Recovery Testing - Collaborative Review | 20 hrs | 10 days | Tue 3/18/25 | Mon 3/31/25 | 984 | 986 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4931 | 986 | Future Task |  |  | D676 | Jarad Hermann | Approve | DED D676 - Completion of Disaster Recovery Testing - Approve | 0 hrs | 0 days | Mon 3/31/25 | Mon 3/31/25 | 985 | 987 |  | Jimmy Cox
4992 | 987 | Future Task |  |  | D676 | Jarad Hermann |  | Execute Disaster Recovery Testing | 3 hrs | 64 days | Tue 4/1/25 | Mon 6/30/25 | 986575 | 988 |  | Jarad Hermann,Vivek Sharma,Stacey Terry
4993 | 988 | Future Task |  |  | D676 | Jarad Hermann |  | Create Completion of Disaster Recovery Testing Summary Document | 26 hrs | 13 days | Tue 7/1/25 | Fri 7/18/25 | 987 | 989SS,990SS,991 |  | Jarad Hermann,Vivek Sharma
4994 | 989 | Future Task |  |  | D676 | Jarad Hermann |  | Conduct Disaster Recovery Testing Exit Criteria Review Meeting | 26 hrs | 13 days | Tue 7/1/25 | Fri 7/18/25 | 988SS | 991 |  | Jarad Hermann,Vivek Sharma
4995 | 990 | Future Task |  |  | D676 | Jarad Hermann |  | Confirm requirements traceability for Disaster Recovery Testing | 26 hrs | 13 days | Tue 7/1/25 | Fri 7/18/25 | 988SS | 991 |  | Jarad Hermann,Vivek Sharma
4932 | 991 | Future Task |  |  | D676 | Jarad Hermann | Submit | DEL D676 - Completion of Disaster Recovery Testing - Draft Submission | 0 hrs | 0 days | Fri 7/18/25 | Fri 7/18/25 | 990988989 | 992 |  | Jarad Hermann,Joy Schneider
4933 | 992 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 7/21/25 | Fri 7/25/25 | 991 | 993 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4934 | 993 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Style Guide Review | 1 hr | 1 day | Mon 7/28/25 | Mon 7/28/25 | 992 | 994 |  | Dusti Kincl
4935 | 994 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Final Collaborative Review | 16 hrs | 5 days | Tue 7/29/25 | Mon 8/4/25 | 993 | 995 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4936 | 995 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Accenture QC | 4 hrs | 2 days | Tue 8/5/25 | Wed 8/6/25 | 994 | 996 |  | Joy Schneider
4937 | 996 | Future Task |  |  | D676 | Jarad Hermann | Submit | DEL D676 - Completion of Disaster Recovery Testing - Submit | 0 hrs | 0 days | Wed 8/6/25 | Wed 8/6/25 | 995 | 997 |  | Joy Schneider
4938 | 997 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Department QC | 4 hrs | 1 day | Thu 8/7/25 | Thu 8/7/25 | 996 | 998 |  | Tommy Werner,Jenifer Hartsfield
4939 | 998 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Contract Manager Review | 8 hrs | 3 days | Fri 8/8/25 | Tue 8/12/25 | 997 | 999 |  | Sean Buchanan
4940 | 999 | Future Task |  |  | D676 | Jarad Hermann | Accept | DEL D676 - Completion of Disaster Recovery Testing - Accept | 0 hrs | 0 days | Tue 8/12/25 | Tue 8/12/25 | 998 | 1252 | 2025-11-01 | Sean Buchanan
4941 | 1000 | Future Task | Yes |  | D677 | Stacey Terry |  | D677 - Completion of Mock Go-Lives (Dry Run #3) | 229 hrs | 52 days | Mon 9/29/25 | Fri 12/12/25
4942 | 1001 | Future Task |  |  | D677 | Stacey Terry | Create | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Create | 24 hrs | 10 days | Mon 9/29/25 | Fri 10/10/25 | 1 | 1002 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4943 | 1002 | Future Task |  |  | D677 | Stacey Terry | Submit | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Submit | 0 hrs | 0 days | Fri 10/10/25 | Fri 10/10/25 | 1001 | 1003 |  | Stacey Terry,Joy Schneider
4944 | 1003 | Future Task |  |  | D677 | Stacey Terry | Review | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Collaborative Review | 32 hrs | 10 days | Mon 10/13/25 | Fri 10/24/25 | 1002 | 1004 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4945 | 1004 | Future Task |  |  | D677 | Stacey Terry | Approve | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Approve | 0 hrs | 0 days | Fri 10/24/25 | Fri 10/24/25 | 1003 | 1005 |  | Jimmy Cox
5000 | 1005 | Future Task |  |  | D677 | Stacey Terry |  | Confirm Mock Go-Live Dry Run #3 Readiness | 40 hrs | 4 days | Mon 10/27/25 | Thu 10/30/25 | 1004 | 1006FS+1 day |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5001 | 1006 | Future Task |  |  | D677 | Stacey Terry |  | Execute Mock Go-Live Dry Run #3 | 10 hrs | 10 days | Mon 11/3/25 | Mon 11/17/25 | 1005FS+1 day | 1007 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5002 | 1007 | Future Task |  |  | D677 | Stacey Terry |  | Document Mock Go-Live Dry Run Results #3 | 30 hrs | 3 days | Tue 11/18/25 | Thu 11/20/25 | 1006 | 1008 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5003 | 1008 | Future Task |  |  | D677 | Stacey Terry |  | Create Mock Go-Live Dry Run #3 Summary Document | 20 hrs | 2 days | Fri 11/21/25 | Mon 11/24/25 | 1007 | 1009 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
4946 | 1009 | Future Task |  |  | D677 | Stacey Terry | Submit | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Draft Submission | 0 hrs | 0 days | Mon 11/24/25 | Mon 11/24/25 | 1008 | 1010 |  | Stacey Terry,Joy Schneider
4947 | 1010 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Pre-Submission Collaborative Review | 28 hrs | 3 days | Tue 11/25/25 | Mon 12/1/25 | 1009 | 1011 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4948 | 1011 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Style Guide Review | 1 hr | 1 day | Tue 12/2/25 | Tue 12/2/25 | 1010 | 1012 |  | Dusti Kincl
4949 | 1012 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Final Collaborative Review | 28 hrs | 3 days | Wed 12/3/25 | Fri 12/5/25 | 1011 | 1013 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4950 | 1013 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Accenture QC | 4 hrs | 1 day | Mon 12/8/25 | Mon 12/8/25 | 1012 | 1014 |  | Joy Schneider
4951 | 1014 | Future Task |  |  | D677 | Stacey Terry | Submit | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Submit | 0 hrs | 0 days | Mon 12/8/25 | Mon 12/8/25 | 1013 | 1015 |  | Joy Schneider
4952 | 1015 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Department QC | 4 hrs | 1 day | Tue 12/9/25 | Tue 12/9/25 | 1014 | 1016 |  | Tommy Werner,Gabriela Gibson
4953 | 1016 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Contract Manager Review | 8 hrs | 3 days | Wed 12/10/25 | Fri 12/12/25 | 1015 | 1017 |  | Sean Buchanan
4954 | 1017 | Future Task |  |  | D677 | Stacey Terry | Accept | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Accept | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 1016 | 1252 | 2025-12-01 | Sean Buchanan
5080 | 1018 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | WP406 - Mock Conversion Testing Plan | 180 hrs | 94 days | Mon 3/11/24 | Mon 7/22/24
5081 | 1019 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WPED WP406 - Mock Conversion Testing Plan - Create | 24 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 1 | 1020 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5082 | 1020 | Future Task |  |  | WP406 | Manojkumar Gurjar | Submit | WPED WP406 - Mock Conversion Testing Plan - Submit | 0 hrs | 0 days | Fri 3/22/24 | Fri 3/22/24 | 1019 | 1021 |  | Joy Schneider,Manojkumar Gurjar
5083 | 1021 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WPED WP406 - Mock Conversion Testing Plan - Review | 28 hrs | 10 days | Mon 3/25/24 | Fri 4/5/24 | 1020 | 1022 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5084 | 1022 | Future Task |  |  | WP406 | Manojkumar Gurjar | Approve | WPED WP406 - Mock Conversion Testing Plan - Approve | 0 hrs | 0 days | Fri 4/5/24 | Fri 4/5/24 | 1021 | 1023 |  | Jimmy Cox
5116 | 1023 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | Define Mock Conversion Testing Approach | 20 hrs | 10 days | Mon 4/8/24 | Fri 4/19/24 | 1022 | 1024 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5117 | 1024 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | Identify Resources for Mock Conversion Testing | 20 hrs | 10 days | Mon 4/22/24 | Fri 5/3/24 | 1023 | 1025 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5118 | 1025 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | Define Test Cycles and Scenarios | 20 hrs | 24 days | Mon 5/6/24 | Fri 6/7/24 | 1024 | 1026 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5119 | 1026 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | Define and review Entry/Exit Criteria for Mock Conversion Testing | 20 hrs | 15 days | Mon 6/10/24 | Fri 6/28/24 | 1025 | 1027 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5085 | 1027 | Future Task |  |  | WP406 | Manojkumar Gurjar | Submit | WP WP406 - Mock Conversion Testing Plan - Submit | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 1026 | 1028 |  | Joy Schneider,Manojkumar Gurjar
5086 | 1028 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WP WP406 - Mock Conversion Testing Plan - Collaborative Review & Update | 24 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 1027 | 1029 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5087 | 1029 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WP WP406 - Mock Conversion Testing Plan - Final Review & Edits | 24 hrs | 5 days | Tue 7/16/24 | Mon 7/22/24 | 1028 | 1030 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5088 | 1030 | Future Task |  |  | WP406 | Manojkumar Gurjar | Approve | WP WP406 - Mock Conversion Testing Plan - Approve | 0 hrs | 0 days | Mon 7/22/24 | Mon 7/22/24 | 1029 | 1032FS-45 days,564 | 2024-05-01 | Jimmy Cox
5089 | 1031 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | WP407 - Mock Conversion Scripts | 160 hrs | 67 days | Fri 5/17/24 | Wed 8/21/24
5090 | 1032 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WPED WP407 - Mock Conversion Scripts - Create | 24 hrs | 10 days | Fri 5/17/24 | Fri 5/31/24 | 1030FS-45 days | 1033 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5091 | 1033 | Future Task |  |  | WP407 | Manojkumar Gurjar | Submit | WPED WP407 - Mock Conversion Scripts - Submit | 0 hrs | 0 days | Fri 5/31/24 | Fri 5/31/24 | 1032 | 1034 |  | Joy Schneider,Manojkumar Gurjar
5092 | 1034 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WPED WP407 - Mock Conversion Scripts - Review | 28 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 1033 | 1035 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5093 | 1035 | Future Task |  |  | WP407 | Manojkumar Gurjar | Approve | WPED WP407 - Mock Conversion Scripts - Approve | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 1034 | 1036 |  | Jimmy Cox
5120 | 1036 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | Create Test Scripts | 20 hrs | 19 days | Mon 6/17/24 | Fri 7/12/24 | 1035 | 1037 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5121 | 1037 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | Identify System Test Scripts for Mock Conversion Testing | 20 hrs | 8 days | Mon 7/15/24 | Wed 7/24/24 | 1036 | 1038 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5122 | 1038 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | Review System Test Scripts for Mock Conversion Testing | 20 hrs | 5 days | Thu 7/25/24 | Wed 7/31/24 | 1037 | 1039 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5094 | 1039 | Future Task |  |  | WP407 | Manojkumar Gurjar | Submit | WP WP407 - Mock Conversion Scripts - Submit | 0 hrs | 0 days | Wed 7/31/24 | Wed 7/31/24 | 1038 | 1040 |  | Joy Schneider,Manojkumar Gurjar
5095 | 1040 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WP WP407 - Mock Conversion Scripts - Collaborative Review & Update | 24 hrs | 10 days | Thu 8/1/24 | Wed 8/14/24 | 1039 | 1041 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5096 | 1041 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WP WP407 - Mock Conversion Scripts - Final Review & Edits | 24 hrs | 5 days | Thu 8/15/24 | Wed 8/21/24 | 1040 | 1042 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5097 | 1042 | Future Task |  |  | WP407 | Manojkumar Gurjar | Approve | WP WP407 - Mock Conversion Scripts - Approve | 0 hrs | 0 days | Wed 8/21/24 | Wed 8/21/24 | 1041 | 621FS-28 days | 2024-07-01 | Jimmy Cox
5098 | 1043 | Future Task |  |  | WP408 | Stacey Terry |  | WP408 - System Test Scripts | 188 hrs | 153 days | Mon 2/12/24 | Mon 9/16/24
5099 | 1044 | Future Task |  |  | WP408 | Stacey Terry | Create | WPED WP408 - System Test Scripts - Create | 16 hrs | 10 days | Mon 2/12/24 | Fri 2/23/24 | 1 | 1045 |  | Stacey Terry,Mary Punty
5100 | 1045 | Future Task |  |  | WP408 | Stacey Terry | Submit | WPED WP408 - System Test Scripts - Submit | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 1044 | 1046 |  | Joy Schneider,Stacey Terry
5101 | 1046 | Future Task |  |  | WP408 | Stacey Terry | Review | WPED WP408 - System Test Scripts - Review | 12 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 1045 | 1047 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5102 | 1047 | Future Task |  |  | WP408 | Stacey Terry | Approve | WPED WP408 - System Test Scripts - Approve | 0 hrs | 0 days | Fri 3/8/24 | Fri 3/8/24 | 1046 | 1048 |  | Jimmy Cox
5123 | 1048 | Future Task |  |  | WP408 | Stacey Terry |  | Create Work Unit Tracker for System Test Preparation | 20 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 1047 | 1049 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5124 | 1049 | Future Task |  |  | WP408 | Stacey Terry |  | Review, update, & confirm Work Unit Tracker for System Test Preparation | 20 hrs | 10 days | Mon 3/25/24 | Fri 4/5/24 | 1048 | 1050FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter
5125 | 1050 | Future Task |  |  | WP408 | Stacey Terry |  | Create System Test Script Template | 30 hrs | 5 days | Mon 4/1/24 | Fri 4/5/24 | 1049FS-5 days | 1051 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5126 | 1051 | Future Task |  |  | WP408 | Stacey Terry |  | Create, Review and Confirm System Test Scripts and Data (this is a WU) | 20 hrs | 93 days | Mon 4/8/24 | Fri 8/16/24 | 1050 | 1052 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
5127 | 1052 | Future Task |  |  | WP408 | Stacey Terry |  | Create System Test Script Summary Document | 30 hrs | 5 days | Mon 8/19/24 | Fri 8/23/24 | 1051 | 1053 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5103 | 1053 | Future Task |  |  | WP408 | Stacey Terry | Submit | WP WP408 - System Test Scripts - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 1052 | 1054 |  | Joy Schneider,Stacey Terry
5104 | 1054 | Future Task |  |  | WP408 | Stacey Terry | Review | WP WP408 - System Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1053 | 1055 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5105 | 1055 | Future Task |  |  | WP408 | Stacey Terry | Review | WP WP408 - System Test Scripts - Final Review & Edits | 20 hrs | 5 days | Tue 9/10/24 | Mon 9/16/24 | 1054 | 1056 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5106 | 1056 | Future Task |  |  | WP408 | Stacey Terry | Approve | WP WP408 - System Test Scripts - Approve | 0 hrs | 0 days | Mon 9/16/24 | Mon 9/16/24 | 1055 | 648 | 2024-09-01 | Jimmy Cox
5107 | 1057 | Future Task |  |  | WP409 | Stacey Terry |  | WP409 - Regression Testing Plan | 116 hrs | 58 days | Tue 9/3/24 | Fri 11/22/24
5108 | 1058 | Future Task |  |  | WP409 | Stacey Terry | Create | WPED WP409 - Regression Testing Plan - Create | 2 hrs | 9 days | Tue 9/3/24 | Fri 9/13/24 | 1 | 1059 |  | Stacey Terry,Mary Punty
5109 | 1059 | Future Task |  |  | WP409 | Stacey Terry | Submit | WPED WP409 - Regression Testing Plan - Submit | 0 hrs | 0 days | Fri 9/13/24 | Fri 9/13/24 | 1058 | 1060 |  | Joy Schneider,Stacey Terry
5110 | 1060 | Future Task |  |  | WP409 | Stacey Terry | Review | WPED WP409 - Regression Testing Plan - Review | 24 hrs | 10 days | Mon 9/16/24 | Fri 9/27/24 | 1059 | 1061 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5111 | 1061 | Future Task |  |  | WP409 | Stacey Terry | Approve | WPED WP409 - Regression Testing Plan - Approve | 0 hrs | 0 days | Fri 9/27/24 | Fri 9/27/24 | 1060 | 1062 |  | Jimmy Cox
5128 | 1062 | Future Task |  |  | WP409 | Stacey Terry |  | Create Regression Testing Approach/Plan | 20 hrs | 24 days | Mon 9/30/24 | Thu 10/31/24 | 1061 | 1063SS+10 days,1065 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5129 | 1063 | Future Task |  |  | WP409 | Stacey Terry |  | Define the scope of the Regression Test suite | 20 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 1062SS+10 days | 1064SS+5 days,1065 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5130 | 1064 | Future Task |  |  | WP409 | Stacey Terry |  | Identify testing resources for Regression Testing | 20 hrs | 5 days | Mon 10/21/24 | Fri 10/25/24 | 1063SS+5 days | 1065 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5112 | 1065 | Future Task |  |  | WP409 | Stacey Terry | Submit | WP WP409 - Regression Testing Plan - Submit | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 106210631064 | 1066 |  | Joy Schneider,Stacey Terry
5113 | 1066 | Future Task |  |  | WP409 | Stacey Terry | Review | WP WP409 - Regression Testing Plan - Collaborative Review & Update | 10 hrs | 10 days | Fri 11/1/24 | Fri 11/15/24 | 1065 | 1067 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5114 | 1067 | Future Task |  |  | WP409 | Stacey Terry | Review | WP WP409 - Regression Testing Plan - Final Review & Edits | 20 hrs | 5 days | Mon 11/18/24 | Fri 11/22/24 | 1066 | 1068 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5115 | 1068 | Future Task |  |  | WP409 | Stacey Terry | Approve | WP WP409 - Regression Testing Plan - Approve | 0 hrs | 0 days | Fri 11/22/24 | Fri 11/22/24 | 1067 | 1112FS-17 days,1124FS+5 days | 2024-12-01 | Jimmy Cox
5257 | 1069 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | WP412 - Interface Testing Plan | 220 hrs | 94 days | Fri 5/3/24 | Mon 9/16/24
5258 | 1070 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WPED WP412 - Interface Testing Plan - Create | 24 hrs | 10 days | Fri 5/3/24 | Thu 5/16/24 | 544FS+92 days | 1071,1085SS+29 days |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5259 | 1071 | Future Task |  |  | WP412 | Manojkumar Gurjar | Submit | WPED WP412 - Interface Testing Plan - Submit | 0 hrs | 0 days | Thu 5/16/24 | Thu 5/16/24 | 1070 | 1072 |  | Joy Schneider,Manojkumar Gurjar
5260 | 1072 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WPED WP412 - Interface Testing Plan - Review | 28 hrs | 10 days | Fri 5/17/24 | Fri 5/31/24 | 1071 | 1073 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5261 | 1073 | Future Task |  |  | WP412 | Manojkumar Gurjar | Approve | WPED WP412 - Interface Testing Plan - Approve | 0 hrs | 0 days | Fri 5/31/24 | Fri 5/31/24 | 1072 | 1074 |  | Jimmy Cox
5284 | 1074 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Define Interface Test approach | 20 hrs | 15 days | Mon 6/3/24 | Fri 6/21/24 | 1073 | 1075 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5285 | 1075 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Define Interface Test Cycles | 20 hrs | 14 days | Mon 6/24/24 | Fri 7/12/24 | 1074 | 1076 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5286 | 1076 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Identify Test Resources for Interface Testing | 20 hrs | 5 days | Mon 7/15/24 | Fri 7/19/24 | 1075 | 1077 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5287 | 1077 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Define Test Tools and Test Management processes for Interface Testing | 20 hrs | 5 days | Mon 7/22/24 | Fri 7/26/24 | 1076 | 1078 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5288 | 1078 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Create Initial List of Interface Test Scenarios | 20 hrs | 10 days | Mon 7/29/24 | Fri 8/9/24 | 1077 | 1079 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5289 | 1079 | Future Task |  | RW | WP412 | Manojkumar Gurjar |  | Prepare High-level Interface Test Approach for Integration Partners | 20 hrs | 10 days | Mon 8/12/24 | Fri 8/23/24 | 1078 | 1080 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5262 | 1080 | Future Task |  |  | WP412 | Manojkumar Gurjar | Submit | WP WP412 - Interface Testing Plan - Submit | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 1079 | 1081 |  | Joy Schneider,Manojkumar Gurjar
5263 | 1081 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WP WP412 - Interface Testing Plan - Collaborative Review & Update | 24 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1080 | 1082 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5264 | 1082 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WP WP412 - Interface Testing Plan - Final Review & Edits | 24 hrs | 5 days | Tue 9/10/24 | Mon 9/16/24 | 1081 | 1083 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5265 | 1083 | Future Task |  |  | WP412 | Manojkumar Gurjar | Approve | WP WP412 - Interface Testing Plan - Approve | 0 hrs | 0 days | Mon 9/16/24 | Mon 9/16/24 | 1082 | 562FS-10 days | 2024-08-01 | Jimmy Cox
5266 | 1084 | Future Task |  |  | WP413 | Stacey Terry |  | WP413 - Interface Test Scripts | 180 hrs | 89 days | Fri 6/14/24 | Fri 10/18/24
5267 | 1085 | Future Task |  |  | WP413 | Stacey Terry | Create | WPED WP413 - Interface Test Scripts - Create | 16 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1070SS+29 days | 1086 |  | Stacey Terry,Mary Punty
5268 | 1086 | Future Task |  |  | WP413 | Stacey Terry | Submit | WPED WP413 - Interface Test Scripts - Submit | 0 hrs | 0 days | Thu 6/27/24 | Thu 6/27/24 | 1085 | 1087 |  | Joy Schneider,Stacey Terry
5269 | 1087 | Future Task |  |  | WP413 | Stacey Terry | Review | WPED WP413 - Interface Test Scripts - Review | 24 hrs | 10 days | Fri 6/28/24 | Fri 7/12/24 | 1086 | 1088 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5270 | 1088 | Future Task |  |  | WP413 | Stacey Terry | Approve | WPED WP413 - Interface Test Scripts - Approve | 0 hrs | 0 days | Fri 7/12/24 | Fri 7/12/24 | 1087 | 1089 |  | Jimmy Cox
5290 | 1089 | Future Task |  |  | WP413 | Stacey Terry |  | Create Work Unit Tracker for Interface Test Preparation | 20 hrs | 10 days | Mon 7/15/24 | Fri 7/26/24 | 1088 | 1090 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5291 | 1090 | Future Task |  |  | WP413 | Stacey Terry |  | Review, update, & confirm Work Unit Tracker for Interface Test Preparation | 20 hrs | 5 days | Mon 7/29/24 | Fri 8/2/24 | 1089 | 1091 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5292 | 1091 | Future Task |  |  | WP413 | Stacey Terry |  | Create, Review and Confirm Interface Test Scenarios/Scripts and Data (this is a WU) | 20 hrs | 24 days | Mon 8/5/24 | Fri 9/6/24 | 1090 | 1092 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5293 | 1092 | Future Task |  |  | WP413 | Stacey Terry |  | Create Interface Test Scripts Summary Document | 20 hrs | 5 days | Mon 9/9/24 | Fri 9/13/24 | 1091 | 1093 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5271 | 1093 | Future Task |  |  | WP413 | Stacey Terry | Submit | WP WP413 - Interface Test Scripts - Submit | 0 hrs | 0 days | Fri 9/13/24 | Fri 9/13/24 | 1092 | 1094 |  | Joy Schneider,Stacey Terry
5272 | 1094 | Future Task |  |  | WP413 | Stacey Terry | Review | WP WP413 - Interface Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Mon 9/16/24 | Fri 9/27/24 | 1093 | 1095 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5273 | 1095 | Future Task |  |  | WP413 | Stacey Terry | Review | WP WP413 - Interface Test Scripts - Final Review & Edits | 20 hrs | 5 days | Mon 9/30/24 | Fri 10/4/24 | 1094 | 1096 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5274 | 1096 | Future Task |  |  | WP413 | Stacey Terry | Approve | WP WP413 - Interface Test Scripts - Approve | 0 hrs | 0 days | Fri 10/4/24 | Fri 10/4/24 | 1095 | 1097 | 2024-08-01 | Jimmy Cox
7149 | 1097 | Future Task |  | RW | WP413 | Stacey Terry |  | Prepare and share Test Scenarios and Scripts with Integration partners | 20 hrs | 10 days | Mon 10/7/24 | Fri 10/18/24 | 1096 |  |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5275 | 1098 | Future Task |  |  | WP414 | Stacey Terry |  | WP414 - Payroll Parallel Test Scripts | 160 hrs | 80 days | Mon 1/13/25 | Mon 5/5/25
5276 | 1099 | Future Task |  |  | WP414 | Stacey Terry | Create | WPED WP414 - Payroll Parallel Test Scripts - Create | 16 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 723SS-4 days | 1100 |  | Stacey Terry,Mary Punty
5277 | 1100 | Future Task |  |  | WP414 | Stacey Terry | Submit | WPED WP414 - Payroll Parallel Test Scripts - Submit | 0 hrs | 0 days | Mon 1/27/25 | Mon 1/27/25 | 1099 | 1101 |  | Joy Schneider,Stacey Terry
5278 | 1101 | Future Task |  |  | WP414 | Stacey Terry | Review | WPED WP414 - Payroll Parallel Test Scripts - Review | 24 hrs | 10 days | Tue 1/28/25 | Mon 2/10/25 | 1100 | 1102 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5279 | 1102 | Future Task |  |  | WP414 | Stacey Terry | Approve | WPED WP414 - Payroll Parallel Test Scripts - Approve | 0 hrs | 0 days | Mon 2/10/25 | Mon 2/10/25 | 1101 | 1103 |  | Jimmy Cox
5295 | 1103 | Future Task |  |  | WP414 | Stacey Terry |  | Create Work Unit Tracker for Payroll Parallel Test Preparation | 20 hrs | 5 days | Tue 2/11/25 | Mon 2/17/25 | 1102 | 1104 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh
5296 | 1104 | Future Task |  |  | WP414 | Stacey Terry |  | Review, update, & confirm Work Unit Tracker for Payroll Parallel Test Preparation | 20 hrs | 10 days | Tue 2/18/25 | Mon 3/3/25 | 1103 | 1105FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
5297 | 1105 | Future Task |  |  | WP414 | Stacey Terry |  | Create, Review and Confirm Payroll Parallel Test Scenarios/Scripts and Data - this is a WU | 20 hrs | 30 days | Tue 2/25/25 | Mon 4/7/25 | 1104FS-5 days | 1106FS-5 days |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Jennifer Peddicord
5298 | 1106 | Future Task |  |  | WP414 | Stacey Terry |  | Create Payroll Parallel Test Script Summary Document | 20 hrs | 10 days | Tue 4/1/25 | Mon 4/14/25 | 1105FS-5 days | 1107 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5280 | 1107 | Future Task |  |  | WP414 | Stacey Terry | Submit | WP WP414 - Payroll Parallel Test Scripts - Submit | 0 hrs | 0 days | Mon 4/14/25 | Mon 4/14/25 | 1106 | 1108 |  | Joy Schneider,Stacey Terry
5281 | 1108 | Future Task |  |  | WP414 | Stacey Terry | Review | WP WP414 - Payroll Parallel Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Tue 4/15/25 | Mon 4/28/25 | 1107 | 1109 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5282 | 1109 | Future Task |  |  | WP414 | Stacey Terry | Review | WP WP414 - Payroll Parallel Test Scripts - Final Review & Edits | 20 hrs | 5 days | Tue 4/29/25 | Mon 5/5/25 | 1108 | 1110 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5283 | 1110 | Future Task |  |  | WP414 | Stacey Terry | Approve | WP WP414 - Payroll Parallel Test Scripts - Approve | 0 hrs | 0 days | Mon 5/5/25 | Mon 5/5/25 | 1109 |  | 2025-03-01 | Jimmy Cox
5131 | 1111 | Future Task |  |  | WP415 | Stacey Terry |  | WP415 - Regression Test Scripts | 140 hrs | 63 days | Wed 10/30/24 | Mon 2/3/25
5132 | 1112 | Future Task |  |  | WP415 | Stacey Terry | Create | WPED WP415 - Regression Test Scripts - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1068FS-17 days | 1113 |  | Stacey Terry,Mary Punty
5133 | 1113 | Future Task |  |  | WP415 | Stacey Terry | Submit | WPED WP415 - Regression Test Scripts - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 1112 | 1114 |  | Joy Schneider,Stacey Terry
5134 | 1114 | Future Task |  |  | WP415 | Stacey Terry | Review | WPED WP415 - Regression Test Scripts - Review | 24 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 1113 | 1115 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5135 | 1115 | Future Task |  |  | WP415 | Stacey Terry | Approve | WPED WP415 - Regression Test Scripts - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1114 | 1116 |  | Jimmy Cox
5221 | 1116 | Future Task |  |  | WP415 | Stacey Terry |  | Create Regression Test Suite | 20 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 1115 | 1117 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5222 | 1117 | Future Task |  |  | WP415 | Stacey Terry |  | Review, update & confirm Regression Test Suite | 20 hrs | 9 days | Mon 12/16/24 | Fri 12/27/24 | 1116 | 1118 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter
5223 | 1118 | Future Task |  |  | WP415 | Stacey Terry |  | Create Regression Test Scripts Summary Document | 20 hrs | 9 days | Mon 12/30/24 | Fri 1/10/25 | 1117 | 1119 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5136 | 1119 | Future Task |  |  | WP415 | Stacey Terry | Submit | WP WP415 - Regression Test Scripts - Submit | 0 hrs | 0 days | Fri 1/10/25 | Fri 1/10/25 | 1118 | 1120 |  | Joy Schneider,Stacey Terry
5137 | 1120 | Future Task |  |  | WP415 | Stacey Terry | Review | WP WP415 - Regression Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | Mon 1/13/25 | Mon 1/27/25 | 1119 | 1121 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5138 | 1121 | Future Task |  |  | WP415 | Stacey Terry | Review | WP WP415 - Regression Test Scripts - Final Review & Edits | 20 hrs | 5 days | Tue 1/28/25 | Mon 2/3/25 | 1120 | 1122 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5139 | 1122 | Future Task |  |  | WP415 | Stacey Terry | Approve | WP WP415 - Regression Test Scripts - Approve | 0 hrs | 0 days | Mon 2/3/25 | Mon 2/3/25 | 1121 |  | 2024-12-01 | Jimmy Cox
5140 | 1123 | Future Task | Yes |  | WP416 | Stacey Terry |  | WP416 - Completion of Regression Testing | 123 hrs | 160 days | Wed 12/4/24 | Tue 7/22/25
5141 | 1124 | Future Task |  |  | WP416 | Stacey Terry | Create | WPED WP416 - Completion of Regression Testing - Create | 16 hrs | 10 days | Wed 12/4/24 | Tue 12/17/24 | 1068FS+5 days | 1125 |  | Stacey Terry,Mary Punty
5142 | 1125 | Future Task |  |  | WP416 | Stacey Terry | Submit | WPED WP416 - Completion of Regression Testing - Submit | 0 hrs | 0 days | Tue 12/17/24 | Tue 12/17/24 | 1124 | 1126 |  | Joy Schneider,Stacey Terry
5143 | 1126 | Future Task |  |  | WP416 | Stacey Terry | Review | WPED WP416 - Completion of Regression Testing - Review | 24 hrs | 10 days | Wed 12/18/24 | Thu 1/2/25 | 1125 | 1127 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5144 | 1127 | Future Task |  |  | WP416 | Stacey Terry | Approve | WPED WP416 - Completion of Regression Testing - Approve | 0 hrs | 0 days | Thu 1/2/25 | Thu 1/2/25 | 1126 | 1128 |  | Jimmy Cox
5224 | 1128 | Future Task |  |  | WP416 | Stacey Terry |  | Create Work Unit Tracker for Regression Test Execution | 20 hrs | 10 days | Fri 1/3/25 | Thu 1/16/25 | 1127 | 1129 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5225 | 1129 | Future Task |  |  | WP416 | Stacey Terry |  | Review, update, and confirm Work Unit Tracker for Regression Test Execution | 20 hrs | 10 days | Fri 1/17/25 | Fri 1/31/25 | 1128 | 1130 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5226 | 1130 | Future Task |  |  | WP416 | Stacey Terry |  | Conduct Regression Test Execution Kickoff Meeting | 20 hrs | 5 days | Mon 2/3/25 | Fri 2/7/25 | 1129 | 1131 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5227 | 1131 | Future Task |  |  | WP416 | Stacey Terry |  | Execute Regression Test - this is a WU | 10 hrs | 90 days | Mon 2/10/25 | Mon 6/16/25 | 1130 | 1132 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Matthew Culp,Abdel El Bacha,Donnie Doctor
5228 | 1132 | Future Task |  |  | WP416 | Stacey Terry |  | Create Completion of Regression Test Execution Summary Document | 3 hrs | 10 days | Tue 6/17/25 | Mon 6/30/25 | 1131 | 1133 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5145 | 1133 | Future Task |  |  | WP416 | Stacey Terry | Submit | WP WP416 - Completion of Regression Testing - Submit | 0 hrs | 0 days | Mon 6/30/25 | Mon 6/30/25 | 1132 | 1134 |  | Joy Schneider,Stacey Terry
5146 | 1134 | Future Task |  |  | WP416 | Stacey Terry | Review | WP WP416 - Completion of Regression Testing - Collaborative Review & Update | 5 hrs | 10 days | Tue 7/1/25 | Tue 7/15/25 | 1133 | 1135 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5147 | 1135 | Future Task |  |  | WP416 | Stacey Terry | Review | WP WP416 - Completion of Regression Testing - Final Review & Edits | 5 hrs | 5 days | Wed 7/16/25 | Tue 7/22/25 | 1134 | 1136 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5148 | 1136 | Future Task |  |  | WP416 | Stacey Terry | Approve | WP WP416 - Completion of Regression Testing - Approve | 0 hrs | 0 days | Tue 7/22/25 | Tue 7/22/25 | 1135 |  | 2025-06-01 | Jimmy Cox
5149 | 1137 | Future Task |  |  | WP417 | Stacey Terry |  | WP417 - Data Dictionary | 192 hrs | 112 days | Wed 10/30/24 | Fri 4/11/25
5150 | 1138 | Future Task |  |  | WP417 | Stacey Terry | Create | WPED WP417 - Data Dictionary - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1 | 1139 |  | Stacey Terry,Manojkumar Gurjar
5151 | 1139 | Future Task |  |  | WP417 | Stacey Terry | Submit | WPED WP417 - Data Dictionary - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 1138 | 1140 |  | Joy Schneider,Stacey Terry
5152 | 1140 | Future Task |  |  | WP417 | Stacey Terry | Review | WPED WP417 - Data Dictionary - Review | 28 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 1139 | 1141 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5153 | 1141 | Future Task |  |  | WP417 | Stacey Terry | Approve | WPED WP417 - Data Dictionary - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1140 | 1142 |  | Jimmy Cox
5229 | 1142 | Future Task |  |  | WP417 | Stacey Terry |  | Update data dictionary with latest tables and data elements as needed - Financials | 20 hrs | 21 days | Mon 12/2/24 | Tue 12/31/24 | 1141 | 1143 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5230 | 1143 | Future Task |  |  | WP417 | Stacey Terry |  | Update data dictionary with latest tables and data elements as needed - Payroll | 20 hrs | 21 days | Thu 1/2/25 | Fri 1/31/25 | 1142 | 1144 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5231 | 1144 | Future Task |  |  | WP417 | Stacey Terry |  | Update data dictionary with latest tables and data elements as needed - DW Related | 20 hrs | 20 days | Mon 2/3/25 | Fri 2/28/25 | 1143 | 1145 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5232 | 1145 | Future Task |  |  | WP417 | Stacey Terry |  | Review and confirm data dictionary | 20 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1144 | 1146 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5233 | 1146 | Future Task |  |  | WP417 | Stacey Terry |  | Share Data Dictionary | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1145 | 1147 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5154 | 1147 | Future Task |  |  | WP417 | Stacey Terry | Submit | WP WP417 - Data Dictionary - Submit | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1146 | 1148 |  | Joy Schneider,Stacey Terry
5155 | 1148 | Future Task |  |  | WP417 | Stacey Terry | Review | WP WP417 - Data Dictionary - Collaborative Review & Update | 24 hrs | 10 days | Mon 3/24/25 | Fri 4/4/25 | 1147 | 1149 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5156 | 1149 | Future Task |  |  | WP417 | Stacey Terry | Review | WP WP417 - Data Dictionary - Final Review & Edits | 24 hrs | 5 days | Mon 4/7/25 | Fri 4/11/25 | 1148 | 1150 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5157 | 1150 | Future Task |  |  | WP417 | Stacey Terry | Approve | WP WP417 - Data Dictionary - Approve | 0 hrs | 0 days | Fri 4/11/25 | Fri 4/11/25 | 1149 |  | 2025-02-01 | Jimmy Cox
5158 | 1151 | Future Task |  |  | WP418 | Jarad Hermann |  | WP418 - Disaster Recovery Plan | 102 hrs | 81 days | Mon 8/26/24 | Fri 12/20/24
5159 | 1152 | Future Task |  |  | WP418 | Jarad Hermann | Create | WPED WP418 - Disaster Recovery Plan - Create | 2 hrs | 10 days | Mon 8/26/24 | Mon 9/9/24 | 1 | 1153,1164SS+5 days |  | Jarad Hermann
5160 | 1153 | Future Task |  |  | WP418 | Jarad Hermann | Submit | WPED WP418 - Disaster Recovery Plan - Submit | 0 hrs | 0 days | Mon 9/9/24 | Mon 9/9/24 | 1152 | 1154 |  | Joy Schneider,Jarad Hermann
5161 | 1154 | Future Task |  |  | WP418 | Jarad Hermann | Review | WPED WP418 - Disaster Recovery Plan - Review | 16 hrs | 10 days | Tue 9/10/24 | Mon 9/23/24 | 1153 | 1155 |  | Jarad Hermann,Jimmy Cox,Angie Robertson,Sean Buchanan
5162 | 1155 | Future Task |  |  | WP418 | Jarad Hermann | Approve | WPED WP418 - Disaster Recovery Plan - Approve | 0 hrs | 0 days | Mon 9/23/24 | Mon 9/23/24 | 1154 | 1156FS+4 days |  | Jimmy Cox
5234 | 1156 | Future Task |  |  | WP418 | Jarad Hermann |  | Design/Update Disaster Recovery (DR) Plan | 20 hrs | 15 days | Mon 9/30/24 | Fri 10/18/24 | 1155FS+4 days | 1157 |  | Jarad Hermann,Vivek Sharma
5235 | 1157 | Future Task |  |  | WP418 | Jarad Hermann |  | Review Financials Disaster Recovery Plan | 20 hrs | 15 days | Mon 10/21/24 | Fri 11/8/24 | 1156 | 1158 |  | Jarad Hermann,Vivek Sharma
5236 | 1158 | Future Task |  |  | WP418 | Jarad Hermann |  | Create Payroll Disaster Recovery Plan | 20 hrs | 12 days | Tue 11/12/24 | Wed 11/27/24 | 1157 | 1159 |  | Jarad Hermann,Vivek Sharma
5163 | 1159 | Future Task |  |  | WP418 | Jarad Hermann | Submit | WP WP418 - Disaster Recovery Plan - Submit | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1158 | 1160 |  | Joy Schneider,Jarad Hermann
5164 | 1160 | Future Task |  |  | WP418 | Jarad Hermann | Review | WP WP418 - Disaster Recovery Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 1159 | 1161 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5165 | 1161 | Future Task |  |  | WP418 | Jarad Hermann | Review | WP WP418 - Disaster Recovery Plan - Final Review & Edits | 12 hrs | 5 days | Mon 12/16/24 | Fri 12/20/24 | 1160 | 1162 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5166 | 1162 | Future Task |  |  | WP418 | Jarad Hermann | Approve | WP WP418 - Disaster Recovery Plan - Approve | 0 hrs | 0 days | Fri 12/20/24 | Fri 12/20/24 | 1161 | 983 | 2024-11-01 | Jimmy Cox
5167 | 1163 | Future Task |  |  | WP419 | Jarad Hermann |  | WP419 - Disaster Recovery Testing Plan | 116 hrs | 138 days | Tue 9/3/24 | Fri 3/21/25
5168 | 1164 | Future Task |  |  | WP419 | Jarad Hermann | Create | WPED WP419 - Disaster Recovery Testing Plan - Create | 16 hrs | 10 days | Tue 9/3/24 | Mon 9/16/24 | 1152SS+5 days | 1165 |  | Jarad Hermann,Mary Punty
5169 | 1165 | Future Task |  |  | WP419 | Jarad Hermann | Submit | WPED WP419 - Disaster Recovery Testing Plan - Submit | 0 hrs | 0 days | Mon 9/16/24 | Mon 9/16/24 | 1164 | 1166 |  | Joy Schneider,Jarad Hermann
5170 | 1166 | Future Task |  |  | WP419 | Jarad Hermann | Review | WPED WP419 - Disaster Recovery Testing Plan - Review | 20 hrs | 10 days | Tue 9/17/24 | Mon 9/30/24 | 1165 | 1167 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5171 | 1167 | Future Task |  |  | WP419 | Jarad Hermann | Approve | WPED WP419 - Disaster Recovery Testing Plan - Approve | 0 hrs | 0 days | Mon 9/30/24 | Mon 9/30/24 | 1166 | 1168 |  | Jimmy Cox
5237 | 1168 | Future Task |  |  | WP419 | Jarad Hermann |  | Define and Document Disaster Recovery Test Tasks including Test Planning, Preparation, Execution, and Closure | 20 hrs | 62 days | Tue 10/1/24 | Tue 12/31/24 | 1167 | 1169SS,1203SS+42 days |  | Jarad Hermann,Bryan Sohayda
5238 | 1169 | Future Task |  |  | WP419 | Jarad Hermann |  | Define Disaster Recovery Testing Tools | 20 hrs | 62 days | Tue 10/1/24 | Tue 12/31/24 | 1168SS | 1170 |  | Jarad Hermann,Bryan Sohayda
5239 | 1170 | Future Task |  |  | WP419 | Jarad Hermann |  | Define and Document Disaster Recovery Test Management | 4 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1169 | 1171SS |  | Jarad Hermann,Bryan Sohayda
5240 | 1171 | Future Task |  |  | WP419 | Jarad Hermann |  | Define and Document Disaster Recovery Test Resources and Responsibilities | 4 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1170SS | 1172 |  | Jarad Hermann,Bryan Sohayda
5172 | 1172 | Future Task |  |  | WP419 | Jarad Hermann | Submit | WP WP419 - Disaster Recovery Testing Plan - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 1171 | 1173574 |  | Joy Schneider,Jarad Hermann
5173 | 1173 | Future Task |  |  | WP419 | Jarad Hermann | Review | WP WP419 - Disaster Recovery Testing Plan - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1172 | 1174 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5174 | 1174 | Future Task |  |  | WP419 | Jarad Hermann | Review | WP WP419 - Disaster Recovery Testing Plan - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1173 | 1175 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5175 | 1175 | Future Task |  |  | WP419 | Jarad Hermann | Approve | WP WP419 - Disaster Recovery Testing Plan - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1174 | 983FS-14 days | 2025-02-01 | Jimmy Cox
5176 | 1176 | Future Task |  |  | WP420 | Jarad Hermann |  | WP420 - Performance Testing Plan | 128 hrs | 140 days | Wed 10/30/24 | Wed 5/21/25
5177 | 1177 | Future Task |  |  | WP420 | Jarad Hermann | Create | WPED WP420 - Performance Testing Plan - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1 | 1178,1215SS |  | Jarad Hermann,Mary Punty
5178 | 1178 | Future Task |  |  | WP420 | Jarad Hermann | Submit | WPED WP420 - Performance Testing Plan - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 1177 | 1179 |  | Joy Schneider,Jarad Hermann
5179 | 1179 | Future Task |  |  | WP420 | Jarad Hermann | Review | WPED WP420 - Performance Testing Plan - Review | 20 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 1178 | 1180 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5180 | 1180 | Future Task |  |  | WP420 | Jarad Hermann | Approve | WPED WP420 - Performance Testing Plan - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1179 | 1181,1182SS,1183SS,1184SS,1185SS |  | Jimmy Cox
5241 | 1181 | Future Task |  |  | WP420 | Jarad Hermann |  | Identify and establish the projected load of the system | 4 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1180 | 1186 |  | Jarad Hermann,Bryan Sohayda
5242 | 1182 | Future Task |  |  | WP420 | Jarad Hermann |  | Define test cycles to be included | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1180SS | 1186 |  | Jarad Hermann,Bryan Sohayda
5243 | 1183 | Future Task |  |  | WP420 | Jarad Hermann |  | Define Performance Testing objectives, scope, environments, and metrics | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1180SS | 1186 |  | Jarad Hermann,Bryan Sohayda
5244 | 1184 | Future Task |  |  | WP420 | Jarad Hermann |  | Identify performance testing project team members and responsibilities | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1180SS | 1186 |  | Jarad Hermann,Bryan Sohayda
5245 | 1185 | Future Task |  |  | WP420 | Jarad Hermann |  | Define and document Performance Testing entry and exit criteria | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1180SS | 1186 |  | Jarad Hermann,Bryan Sohayda
5181 | 1186 | Future Task |  |  | WP420 | Jarad Hermann | Submit | WP WP420 - Performance Testing Plan - Submit | 0 hrs | 0 days | Wed 4/30/25 | Wed 4/30/25 | 1.1851e+19 | 1187572 |  | Joy Schneider,Jarad Hermann
5182 | 1187 | Future Task |  |  | WP420 | Jarad Hermann | Review | WP WP420 - Performance Testing Plan - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 1186 | 1188 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5183 | 1188 | Future Task |  |  | WP420 | Jarad Hermann | Review | WP WP420 - Performance Testing Plan - Final Review & Edits | 4 hrs | 5 days | Thu 5/15/25 | Wed 5/21/25 | 1187 | 1189 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5184 | 1189 | Future Task |  |  | WP420 | Jarad Hermann | Approve | WP WP420 - Performance Testing Plan - Approve | 0 hrs | 0 days | Wed 5/21/25 | Wed 5/21/25 | 1188 | 965FS-14 days | 2025-04-01 | Jimmy Cox
5185 | 1190 | Future Task |  |  | WP421 | Jarad Hermann |  | WP421 - Penetration Testing Plan | 128 hrs | 97 days | Wed 10/30/24 | Fri 3/21/25
5186 | 1191 | Future Task |  |  | WP421 | Jarad Hermann | Create | WPED WP421 - Penetration Testing Plan - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1 | 1192,1227SS |  | Jarad Hermann,Mary Punty
5187 | 1192 | Future Task |  |  | WP421 | Jarad Hermann | Submit | WPED WP421 - Penetration Testing Plan - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 1191 | 1193 |  | Joy Schneider,Jarad Hermann
5188 | 1193 | Future Task |  |  | WP421 | Jarad Hermann | Review | WPED WP421 - Penetration Testing Plan - Review | 20 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 1192 | 1194 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5189 | 1194 | Future Task |  |  | WP421 | Jarad Hermann | Approve | WPED WP421 - Penetration Testing Plan - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1193 | 1195 |  | Jimmy Cox
5246 | 1195 | Future Task |  |  | WP421 | Jarad Hermann |  | Create Penetration Testing Plan/approach | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1194 | 1196SS,1197SS,1198 |  | Jarad Hermann,Bryan Sohayda
5247 | 1196 | Future Task |  |  | WP421 | Jarad Hermann |  | Identify resources for Penetration Testing | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1195SS | 1198 |  | Jarad Hermann,Bryan Sohayda
5248 | 1197 | Future Task |  |  | WP421 | Jarad Hermann |  | Define Penetration Testing entry and exit criteria | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1195SS | 1198 |  | Jarad Hermann,Bryan Sohayda
5190 | 1198 | Future Task |  |  | WP421 | Jarad Hermann | Submit | WP WP421 - Penetration Testing Plan - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 119711951196 | 1199 |  | Joy Schneider,Jarad Hermann
5191 | 1199 | Future Task |  |  | WP421 | Jarad Hermann | Review | WP WP421 - Penetration Testing Plan - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1198 | 1200 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5192 | 1200 | Future Task |  |  | WP421 | Jarad Hermann | Review | WP WP421 - Penetration Testing Plan - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1199 | 1201 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5193 | 1201 | Future Task |  |  | WP421 | Jarad Hermann | Approve | WP WP421 - Penetration Testing Plan - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1200 | 947FS+29 days | 2025-02-01 | Jimmy Cox
5194 | 1202 | Future Task |  |  | WP422 | Jarad Hermann |  | WP422 - Disaster Recovery Test Scripts | 128 hrs | 76 days | Tue 12/3/24 | Fri 3/21/25
5195 | 1203 | Future Task |  |  | WP422 | Jarad Hermann | Create | WPED WP422 - Disaster Recovery Test Scripts - Create | 16 hrs | 10 days | Tue 12/3/24 | Mon 12/16/24 | 1168SS+42 days | 1204 |  | Jarad Hermann,Mary Punty
5196 | 1204 | Future Task |  |  | WP422 | Jarad Hermann | Submit | WPED WP422 - Disaster Recovery Test Scripts - Submit | 0 hrs | 0 days | Mon 12/16/24 | Mon 12/16/24 | 1203 | 1205 |  | Joy Schneider,Jarad Hermann
5197 | 1205 | Future Task |  |  | WP422 | Jarad Hermann | Review | WPED WP422 - Disaster Recovery Test Scripts - Review | 20 hrs | 10 days | Tue 12/17/24 | Tue 12/31/24 | 1204 | 1206 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5198 | 1206 | Future Task |  |  | WP422 | Jarad Hermann | Approve | WPED WP422 - Disaster Recovery Test Scripts - Approve | 0 hrs | 0 days | Tue 12/31/24 | Tue 12/31/24 | 1205 | 1207 |  | Jimmy Cox
5249 | 1207 | Future Task |  |  | WP422 | Jarad Hermann |  | Finalize Disaster Recovery Test Scripts Inventory | 20 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1206 | 1208SS,1209SS,1210 |  | Jarad Hermann,Bryan Sohayda
5250 | 1208 | Future Task |  |  | WP422 | Jarad Hermann |  | Create, review, and confirm DR Test Script Work Unit Tracker | 20 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1207SS | 1210 |  | Jarad Hermann,Bryan Sohayda
5251 | 1209 | Future Task |  |  | WP422 | Jarad Hermann |  | Create, Review and Confirm Disaster Recovery Test Scripts | 20 hrs | 41 days | Thu 1/2/25 | Fri 2/28/25 | 1207SS | 1210 |  | Jarad Hermann,Bryan Sohayda
5199 | 1210 | Future Task |  |  | WP422 | Jarad Hermann | Submit | WP WP422 - Disaster Recovery Test Scripts - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 120912071208 | 1211 |  | Joy Schneider,Jarad Hermann
5200 | 1211 | Future Task |  |  | WP422 | Jarad Hermann | Review | WP WP422 - Disaster Recovery Test Scripts - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1210 | 1212 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5201 | 1212 | Future Task |  |  | WP422 | Jarad Hermann | Review | WP WP422 - Disaster Recovery Test Scripts - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1211 | 1213 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5202 | 1213 | Future Task |  |  | WP422 | Jarad Hermann | Approve | WP WP422 - Disaster Recovery Test Scripts - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1212 | 983FS-14 days |  | Jimmy Cox
5203 | 1214 | Future Task |  |  | WP423 | Jarad Hermann |  | WP423 - Performance Test Scripts | 104 hrs | 140 days | Wed 10/30/24 | Wed 5/21/25
5204 | 1215 | Future Task |  |  | WP423 | Jarad Hermann | Create | WPED WP423 - Performance Test Scripts - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1177SS | 1216 |  | Jarad Hermann,Mary Punty
5205 | 1216 | Future Task |  |  | WP423 | Jarad Hermann | Submit | WPED WP423 - Performance Test Scripts - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 1215 | 1217 |  | Joy Schneider,Jarad Hermann
5206 | 1217 | Future Task |  |  | WP423 | Jarad Hermann | Review | WPED WP423 - Performance Test Scripts - Review | 20 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 1216 | 1218 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5207 | 1218 | Future Task |  |  | WP423 | Jarad Hermann | Approve | WPED WP423 - Performance Test Scripts - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1217 | 1219 |  | Jimmy Cox
5252 | 1219 | Future Task |  |  | WP423 | Jarad Hermann |  | Finalize Performance Test Scripts Inventory | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1218 | 1220SS,1221SS,1222 |  | Jarad Hermann,Bryan Sohayda
5253 | 1220 | Future Task |  |  | WP423 | Jarad Hermann |  | Create, review, and confirm Performance Test Script Work Unit Tracker | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1219SS | 1222 |  | Jarad Hermann,Bryan Sohayda
5254 | 1221 | Future Task |  |  | WP423 | Jarad Hermann |  | Create, Review and Confirm Performance Test Scripts | 20 hrs | 105 days | Mon 12/2/24 | Wed 4/30/25 | 1219SS | 1222 |  | Jarad Hermann,Bryan Sohayda
5208 | 1222 | Future Task |  |  | WP423 | Jarad Hermann | Submit | WP WP423 - Performance Test Scripts - Submit | 0 hrs | 0 days | Wed 4/30/25 | Wed 4/30/25 | 122112191220 | 1223 |  | Joy Schneider,Jarad Hermann
5209 | 1223 | Future Task |  |  | WP423 | Jarad Hermann | Review | WP WP423 - Performance Test Scripts - Collaborative Review & Update | 4 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 1222 | 1224 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5210 | 1224 | Future Task |  |  | WP423 | Jarad Hermann | Review | WP WP423 - Performance Test Scripts - Final Review & Edits | 4 hrs | 5 days | Thu 5/15/25 | Wed 5/21/25 | 1223 | 1225 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5211 | 1225 | Future Task |  |  | WP423 | Jarad Hermann | Approve | WP WP423 - Performance Test Scripts - Approve | 0 hrs | 0 days | Wed 5/21/25 | Wed 5/21/25 | 1224 | 965FS-14 days |  | Jimmy Cox
5212 | 1226 | Future Task |  |  | WP424 | Jarad Hermann |  | WP424 - Penetration Test Scripts/Scenarios | 108 hrs | 97 days | Wed 10/30/24 | Fri 3/21/25
5213 | 1227 | Future Task |  |  | WP424 | Jarad Hermann | Create | WPED WP424 - Penetration Test Scripts/Scenarios - Create | 16 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1191SS | 1228 |  | Jarad Hermann,Mary Punty
5214 | 1228 | Future Task |  |  | WP424 | Jarad Hermann | Submit | WPED WP424 - Penetration Test Scripts/Scenarios - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 1227 | 1229 |  | Joy Schneider,Jarad Hermann
5215 | 1229 | Future Task |  |  | WP424 | Jarad Hermann | Review | WPED WP424 - Penetration Test Scripts/Scenarios - Review | 20 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 1228 | 1230 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5216 | 1230 | Future Task |  |  | WP424 | Jarad Hermann | Approve | WPED WP424 - Penetration Test Scripts/Scenarios - Approve | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1229 | 1231 |  | Jimmy Cox
5255 | 1231 | Future Task |  |  | WP424 | Jarad Hermann |  | Finalize Penetration Test Scripts Inventory | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1230 | 1232SS |  | Jarad Hermann,Bryan Sohayda
5256 | 1232 | Future Task |  |  | WP424 | Jarad Hermann |  | Create, review, and confirm Penetration Test Scripts/Scenarios | 20 hrs | 62 days | Mon 12/2/24 | Fri 2/28/25 | 1231SS | 1233 |  | Jarad Hermann,Bryan Sohayda
5217 | 1233 | Future Task |  |  | WP424 | Jarad Hermann | Submit | WP WP424 - Penetration Test Scripts/Scenarios - Submit | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 1232 | 1234 |  | Joy Schneider,Jarad Hermann
5218 | 1234 | Future Task |  |  | WP424 | Jarad Hermann | Review | WP WP424 - Penetration Test Scripts/Scenarios - Collaborative Review & Update | 16 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1233 | 1235 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5219 | 1235 | Future Task |  |  | WP424 | Jarad Hermann | Review | WP WP424 - Penetration Test Scripts/Scenarios - Final Review & Edits | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1234 | 1236 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5220 | 1236 | Future Task |  |  | WP424 | Jarad Hermann | Approve | WP WP424 - Penetration Test Scripts/Scenarios - Approve | 0 hrs | 0 days | Fri 3/21/25 | Fri 3/21/25 | 1235 | 947FS+29 days |  | Jimmy Cox
5299 | 1237 | Future Task |  |  | I-WP127 | Angie Robertson |  | I-WP127 - User Acceptance Testing Plan | 61 hrs | 77 days | Mon 8/5/24 | Thu 11/21/24
5300 | 1238 | Future Task |  |  | I-WP127 | Angie Robertson | Create | WPED - I-WP127 - User Acceptance Testing Plan - Create | 4 hrs | 10 days | Mon 8/5/24 | Fri 8/16/24 | 1 | 1239 |  | Angie Robertson,Jimmy Cox
5301 | 1239 | Future Task |  |  | I-WP127 | Angie Robertson | Submit | WPED - I-WP127 - User Acceptance Testing Plan - Submit | 0 hrs | 0 days | Fri 8/16/24 | Fri 8/16/24 | 1238 | 1240 |  | Angie Robertson
5302 | 1240 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WPED - I-WP127 - User Acceptance Testing Plan - Collaborative Review and Update | 17 hrs | 10 days | Mon 8/19/24 | Fri 8/30/24 | 1239 | 1241 |  | Carolyn Hicks,Angie Robertson,Matthew Breeding,Jennifer Reeves,Deana Metcalf,Julian Gotreaux,Tommy Werner,Matt Cole,Mary Punty,Stacey Terry
5303 | 1241 | Future Task |  |  | I-WP127 | Angie Robertson | Approve | WPED - I-WP127 - User Acceptance Testing Plan - Approve | 0 hrs | 0 days | Fri 8/30/24 | Fri 8/30/24 | 1240 | 1242 |  | Jimmy Cox
5310 | 1242 | Future Task |  |  | I-WP127 | Angie Robertson |  | Create User Acceptance Plan | 10 hrs | 40 days | Tue 9/3/24 | Mon 10/28/24 | 1241 | 1243 |  | Matthew Breeding,Jennifer Reeves,Carolyn Hicks,Deana Metcalf,Angie Robertson
5304 | 1243 | Future Task |  |  | I-WP127 | Angie Robertson | Submit | I-WP127 - User Acceptance Testing Plan - Submit | 0 hrs | 0 days | Mon 10/28/24 | Mon 10/28/24 | 1242 | 1244 |  | Matthew Breeding
5305 | 1244 | Future Task |  |  | I-WP127 | Angie Robertson | Review | I-WP127 - User Acceptance Testing Plan - Dept QC | 8 hrs | 1 day | Tue 10/29/24 | Tue 10/29/24 | 1243 | 1245 |  | Gabriela Gibson
5306 | 1245 | Future Task |  |  | I-WP127 | Angie Robertson | Review | I-WP127 - User Acceptance Testing Plan - Collaborative Review and Update | 10 hrs | 10 days | Wed 10/30/24 | Wed 11/13/24 | 1244 | 1246 |  | Matthew Breeding,Jennifer Reeves,Carolyn Hicks,Deana Metcalf,Angie Robertson
5307 | 1246 | Future Task |  |  | I-WP127 | Angie Robertson | Review | I-WP127 - User Acceptance Testing Plan - Style Guide Review | 2 hrs | 1 day | Thu 11/14/24 | Thu 11/14/24 | 1245 | 1247 |  | Tatiana Eubanks
5308 | 1247 | Future Task |  |  | I-WP127 | Angie Robertson | Review | I-WP127 - User Acceptance Testing Plan - Final Review and Update | 10 hrs | 5 days | Fri 11/15/24 | Thu 11/21/24 | 1246 | 1248 |  | Angie Robertson,Jimmy Cox
5309 | 1248 | Future Task |  |  | I-WP127 | Angie Robertson | Approve | I-WP127 - User Acceptance Testing Plan - Approve | 0 hrs | 0 days | Thu 11/21/24 | Thu 11/21/24 | 1247 | 1250,566FS+46 days,585 |  | Jimmy Cox
3967 | 1249 | Future Task | [5 empty] | UAT | 1 hr | 163 days | Tue 4/1/25 | Wed 11/19/25
4002 | 1250 | Future Task |  |  | UAT | Matt Breeding |  | UAT Testing | 1 hr | 163 days | Tue 4/1/25 | Wed 11/19/25 | 17075691248 | 1738,1791SS+30 days |  | Jimmy Cox,Angie Robertson
3772 | 1251 | Future Task | [5 empty] | Deploy | 1,806 hrs | 548 days | Fri 12/1/23 | Wed 2/4/26
7156 | 1252 | Future Task | Yes |  | SG5 | Jimmy Cox | Milestone | Stage Gate 5: Deployment Readiness | 0 hrs | 0 days | Fri 12/12/25 | Fri 12/12/25 | 7.2078e+32 |  | December 17, 2025 - ESC | Jimmy Cox,Angie Robertson,Matt Cole | This should be December 17, 2025 per the SOW. The Resource Names include the ESC and we need tasks / dates for ESC review prior to milestone date. | Angie
7157 | 1253 | Future Task | Yes |  | SG6 | Jimmy Cox | Milestone | Stage Gate 6: Confirm Deployment | 0 hrs | 0 days | Fri 12/19/25 | Fri 12/19/25 | 137313881339 | 1254 | 2025-12-30 | Jimmy Cox,Angie Robertson,Matt Cole | This should be December 30, 2025 per the SOW. | Angie
7158 | 1254 | Future Task | Yes |  | SG7 | Jimmy Cox | Milestone | Stage Gate 7: Go-Live | 0 hrs | 0 days | Fri 12/19/25 | Fri 12/19/25 | 1253 |  | Janaury 6, 2026 | Jimmy Cox,Angie Robertson,Matt Cole | This should be January 6, 2026 per the SOW. The Resource Names include the ESC and we need tasks / dates for ESC review prior to milestone date. | Angie
5311 | 1255 | Future Task |  |  | D645 | Mary Punty |  | D645 - Updated Deployment Strategy | 265 hrs | 105 days | Fri 12/1/23 | Tue 4/30/24
5312 | 1256 | Future Task |  |  | D645 | Mary Punty | Create | DED D645 - Updated Deployment Strategy - Create | 16 hrs | 10 days | Fri 12/1/23 | Thu 12/14/23 | 1 | 1257 |  | Mary Punty,Bryan Sohayda
5313 | 1257 | Future Task |  |  | D645 | Mary Punty | Submit | DED D645 - Updated Deployment Strategy - Submit | 0 hrs | 0 days | Thu 12/14/23 | Thu 12/14/23 | 1256 | 1258 |  | Mary Punty,Joy Schneider
5314 | 1258 | Future Task |  |  | D645 | Mary Punty | Review | DED D645 - Updated Deployment Strategy - Collaborative Review | 20 hrs | 10 days | Fri 12/15/23 | Fri 12/29/23 | 1257 | 1259 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5315 | 1259 | Future Task |  |  | D645 | Mary Punty | Approve | DED D645 - Updated Deployment Strategy - Approve | 0 hrs | 0 days | Fri 12/29/23 | Fri 12/29/23 | 1258 | 1260 |  | Jimmy Cox
5339 | 1260 | Future Task |  |  | D645 | Mary Punty |  | Document assumptions about deployment | 20 hrs | 9 days | Tue 1/2/24 | Fri 1/12/24 | 1259 | 1261 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5340 | 1261 | Future Task |  |  | D645 | Mary Punty |  | Create Deployment Kickoff Presentation | 20 hrs | 9 days | Tue 1/16/24 | Fri 1/26/24 | 1260 | 1262 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5341 | 1262 | Future Task |  |  | D645 | Mary Punty |  | Review Deployment Kickoff Presentation | 20 hrs | 5 days | Mon 1/29/24 | Fri 2/2/24 | 1261 | 1263 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5342 | 1263 | Future Task |  |  | D645 | Mary Punty |  | Describe Deployment Calendar | 20 hrs | 10 days | Mon 2/5/24 | Fri 2/16/24 | 1262 | 1264 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5343 | 1264 | Future Task |  |  | D645 | Mary Punty |  | Review Deployment Calendar | 20 hrs | 5 days | Mon 2/19/24 | Fri 2/23/24 | 1263 | 1265 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5344 | 1265 | Future Task |  |  | D645 | Mary Punty |  | Describe Cutover Checklist | 20 hrs | 10 days | Mon 2/26/24 | Fri 3/8/24 | 1264 | 1266 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5345 | 1266 | Future Task |  |  | D645 | Mary Punty |  | Review Cutover Checklist | 20 hrs | 10 days | Mon 3/11/24 | Fri 3/22/24 | 1265 | 1267 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5346 | 1267 | Future Task |  |  | D645 | Mary Punty |  | Finalize Draft - Deployment Strategy | 20 hrs | 5 days | Mon 3/25/24 | Fri 3/29/24 | 1266 | 1268 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5347 | 1268 | Future Task |  |  | D645 | Mary Punty |  | Review Draft - Deployment Strategy | 20 hrs | 5 days | Mon 4/1/24 | Fri 4/5/24 | 1267 | 1269 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5316 | 1269 | Future Task |  |  | D645 | Mary Punty | Submit | DEL D645 - Updated Deployment Strategy - Draft Submission | 0 hrs | 0 days | Fri 4/5/24 | Fri 4/5/24 | 1268 | 1270 |  | Mary Punty,Joy Schneider
5317 | 1270 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 4/8/24 | Fri 4/12/24 | 1269 | 1271 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5318 | 1271 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Style Guide Review | 1 hr | 1 day | Mon 4/15/24 | Mon 4/15/24 | 1270 | 1272 |  | Dusti Kincl
5319 | 1272 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Final Collaborative Review | 16 hrs | 5 days | Tue 4/16/24 | Mon 4/22/24 | 1271 | 1273 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5320 | 1273 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Accenture QC | 4 hrs | 2 days | Tue 4/23/24 | Wed 4/24/24 | 1272 | 1274 |  | Joy Schneider
5321 | 1274 | Future Task |  |  | D645 | Mary Punty | Submit | DEL D645 - Updated Deployment Strategy - Submit | 0 hrs | 0 days | Wed 4/24/24 | Wed 4/24/24 | 1273 | 1275 |  | Joy Schneider
5322 | 1275 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Department QC | 4 hrs | 1 day | Thu 4/25/24 | Thu 4/25/24 | 1274 | 1276 |  | Tommy Werner,Gabriela Gibson
5323 | 1276 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Contract Manager Review | 8 hrs | 3 days | Fri 4/26/24 | Tue 4/30/24 | 1275 | 12771279 |  | Sean Buchanan
5324 | 1277 | Future Task |  |  | D645 | Mary Punty | Accept | DEL D645 - Updated Deployment Strategy - Accept | 0 hrs | 0 days | Tue 4/30/24 | Tue 4/30/24 | 1276 |  | 2024-04-01 | Sean Buchanan
5325 | 1278 | Future Task | Yes |  | D658 | Mary Punty |  | D658 - Develop the Deployment and Contingency Plan | 498 hrs | 125 days | Mon 9/30/24 | Mon 3/31/25 |  |  |  |  | There are lots of "create" tasks already defined below. This seems very detailed considering the DED has not been created or approved. | Angie
5326 | 1279 | Future Task |  |  | D658 | Mary Punty | Create | DED D658 - Develop the Deployment and Contingency Plan - Create | 16 hrs | 10 days | Mon 9/30/24 | Fri 10/11/24 | 1276 | 1280 |  | Mary Punty,Bryan Sohayda
5327 | 1280 | Future Task |  |  | D658 | Mary Punty | Submit | DED D658 - Develop the Deployment and Contingency Plan - Submit | 0 hrs | 0 days | Fri 10/11/24 | Fri 10/11/24 | 1279 | 1281 |  | Mary Punty,Joy Schneider
5328 | 1281 | Future Task |  |  | D658 | Mary Punty | Review | DED D658 - Develop the Deployment and Contingency Plan - Collaborative Review | 20 hrs | 10 days | Mon 10/14/24 | Fri 10/25/24 | 1280 | 1282 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5329 | 1282 | Future Task |  |  | D658 | Mary Punty | Approve | DED D658 - Develop the Deployment and Contingency Plan - Approve | 0 hrs | 0 days | Fri 10/25/24 | Fri 10/25/24 | 1281 | 1283 |  | Jimmy Cox
5348 | 1283 | Future Task |  |  | D658 | Mary Punty |  | Create Deployment and Contingency Plan pitch deck | 18 hrs | 9 days | Mon 10/28/24 | Thu 11/7/24 | 1282 | 1284 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5349 | 1284 | Future Task |  |  | D658 | Mary Punty |  | Review Deployment and Contingency Plan pitch deck | 40 hrs | 4 days | Fri 11/8/24 | Thu 11/14/24 | 1283 | 1285FS+8 days,1289 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5350 | 1285 | Future Task |  |  | D658 | Mary Punty |  | Prepare materials for Dec Sponsor Meeting and Review | 25 hrs | 5 days | Wed 11/27/24 | Thu 12/5/24 | 1284FS+8 days | 1286 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5351 | 1286 | Future Task |  |  | D658 | Mary Punty |  | Plan for and hold December Sponsor Meeting | 25 hrs | 5 days | Fri 12/6/24 | Thu 12/12/24 | 1285 | 1287FS+11 days |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5352 | 1287 | Future Task |  |  | D658 | Mary Punty |  | Gather Deployment and Contingency Plan materials for January ESC Meeting | 35 hrs | 7 days | Tue 12/31/24 | Thu 1/9/25 | 1286FS+11 days | 1288,1293SS |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5353 | 1288 | Future Task |  |  | D658 | Mary Punty |  | Review Deployment and Contingency Plan materials for January ESC Meeting | 25 hrs | 5 days | Fri 1/10/25 | Thu 1/16/25 | 1287 | 1297 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5354 | 1289 | Future Task |  |  | D658 | Mary Punty |  | Identify and document deployment and post-implementation support activities | 20 hrs | 8 days | Fri 11/15/24 | Tue 11/26/24 | 1284 | 1290 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5355 | 1290 | Future Task |  |  | D658 | Mary Punty |  | Review and document deployment and post-implementation support activities | 25 hrs | 5 days | Wed 11/27/24 | Thu 12/5/24 | 1289 | 1291 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5356 | 1291 | Future Task |  |  | D658 | Mary Punty |  | Identify and document timing of cutover activities | 25 hrs | 5 days | Fri 12/6/24 | Thu 12/12/24 | 1290 | 1292 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5357 | 1292 | Future Task |  |  | D658 | Mary Punty |  | Review and document timing of cutover activities | 25 hrs | 5 days | Fri 12/13/24 | Thu 12/19/24 | 1291 | 1293 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5358 | 1293 | Future Task |  |  | D658 | Mary Punty |  | Identify and document contingency scenarios | 20 hrs | 7 days | Tue 12/31/24 | Thu 1/9/25 | 1287SS,1292 | 1294 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5359 | 1294 | Future Task |  |  | D658 | Mary Punty |  | Review contingency scenarios | 25 hrs | 5 days | Fri 1/10/25 | Thu 1/16/25 | 1293 | 1295 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5360 | 1295 | Future Task |  |  | D658 | Mary Punty |  | Define and document the approach to revert changes | 20 hrs | 4 days | Fri 1/17/25 | Thu 1/23/25 | 1294 | 1296 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5361 | 1296 | Future Task |  |  | D658 | Mary Punty |  | Review the approach to revert changes | 25 hrs | 5 days | Fri 1/24/25 | Thu 1/30/25 | 1295 | 1297 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5362 | 1297 | Future Task |  |  | D658 | Mary Punty |  | Gather Deployment and Contingency Plan materials for February ESC Meeting | 25 hrs | 5 days | Fri 1/31/25 | Thu 2/6/25 | 12961288 | 1298 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5363 | 1298 | Future Task |  |  | D658 | Mary Punty |  | Review Deployment and Contingency Plan materials for February ESC Meeting | 15 hrs | 3 days | Fri 2/7/25 | Tue 2/11/25 | 1297 | 1299FS+12 days |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5364 | 1299 | Future Task |  |  | D658 | Mary Punty |  | Confirm approach to Deployment and Contingency | 20 hrs | 5 days | Fri 2/28/25 | Thu 3/6/25 | 1298FS+12 days | 1300 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5330 | 1300 | Future Task |  |  | D658 | Mary Punty | Submit | DEL D658 - Develop the Deployment and Contingency Plan - Draft Submission | 0 hrs | 0 days | Thu 3/6/25 | Thu 3/6/25 | 1299 | 1301 |  | Mary Punty,Joy Schneider
5331 | 1301 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 3/7/25 | Thu 3/13/25 | 1300 | 1302 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5332 | 1302 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Style Guide Review | 1 hr | 1 day | Fri 3/14/25 | Fri 3/14/25 | 1301 | 1303 |  | Dusti Kincl
5333 | 1303 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Final Collaborative Review | 16 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1302 | 1304 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5334 | 1304 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Accenture QC | 4 hrs | 2 days | Mon 3/24/25 | Tue 3/25/25 | 1303 | 1305 |  | Joy Schneider
5335 | 1305 | Future Task |  |  | D658 | Mary Punty | Submit | DEL D658 - Develop the Deployment and Contingency Plan - Submit | 0 hrs | 0 days | Tue 3/25/25 | Tue 3/25/25 | 1304 | 1306 |  | Joy Schneider
5336 | 1306 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Department QC | 4 hrs | 1 day | Wed 3/26/25 | Wed 3/26/25 | 1305 | 1307 |  | Tommy Werner,Gabriela Gibson
5337 | 1307 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Contract Manager Review | 8 hrs | 3 days | Thu 3/27/25 | Mon 3/31/25 | 1306 | 1308 |  | Sean Buchanan
5338 | 1308 | Future Task |  |  | D658 | Mary Punty | Accept | DEL D658 - Develop the Deployment and Contingency Plan - Accept | 0 hrs | 0 days | Mon 3/31/25 | Mon 3/31/25 | 1307 | 1252 | 2025-03-01 | Sean Buchanan
5365 | 1309 | Future Task | Yes |  | D678 | Bryan Sohayda |  | D678 - Final Known Issues & Enhancements Lists | 350 hrs | 65 days | Wed 9/3/25 | Fri 12/5/25
5366 | 1310 | Future Task |  |  | D678 | Bryan Sohayda | Create | DED D678 - Final Known Issues & Enhancements Lists - Create | 16 hrs | 10 days | Wed 9/3/25 | Tue 9/16/25 | 1 | 1311 |  | Mary Punty,Bryan Sohayda
5367 | 1311 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DED D678 - Final Known Issues & Enhancements Lists - Submit | 0 hrs | 0 days | Tue 9/16/25 | Tue 9/16/25 | 1310 | 1312 |  | Bryan Sohayda,Joy Schneider
5368 | 1312 | Future Task |  |  | D678 | Bryan Sohayda | Review | DED D678 - Final Known Issues & Enhancements Lists - Collaborative Review | 20 hrs | 10 days | Wed 9/17/25 | Tue 9/30/25 | 1311 | 1313 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5369 | 1313 | Future Task |  |  | D678 | Bryan Sohayda | Approve | DED D678 - Final Known Issues & Enhancements Lists - Approve | 0 hrs | 0 days | Tue 9/30/25 | Tue 9/30/25 | 1312 | 1314 |  | Jimmy Cox
5393 | 1314 | Future Task |  |  | D678 | Bryan Sohayda |  | Initial Known Issues & Enhancements Lists | 20 hrs | 22 days | Wed 10/1/25 | Thu 10/30/25 | 1313 | 1315SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5394 | 1315 | Future Task |  |  | D678 | Bryan Sohayda |  | Review Open SIRs - Candidates for Known Issues List | 25 hrs | 5 days | Wed 10/1/25 | Tue 10/7/25 | 1314SS | 1316,1317SS |  | Bryan Sohayda,Mary Punty,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5395 | 1316 | Future Task |  |  | D678 | Bryan Sohayda |  | Finalize Open SIRs - Candidates for Known Issues List | 24 hrs | 4 days | Wed 10/8/25 | Mon 10/13/25 | 1315 | 1318SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5396 | 1317 | Future Task |  |  | D678 | Bryan Sohayda |  | Review Open SIRs - Candidates for Known Enhancements List | 30 hrs | 5 days | Wed 10/1/25 | Tue 10/7/25 | 1315SS | 1319 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5397 | 1318 | Future Task |  |  | D678 | Bryan Sohayda |  | Finalize Open SIRs - Candidates for Known Enhancements List | 20 hrs | 4 days | Wed 10/8/25 | Mon 10/13/25 | 1316SS | 1319 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5398 | 1319 | Future Task |  |  | D678 | Bryan Sohayda |  | Confirm Agreed Upon Known Issues | 30 hrs | 5 days | Tue 10/14/25 | Mon 10/20/25 | 13181317 | 1320SS,1321SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5399 | 1320 | Future Task |  |  | D678 | Bryan Sohayda |  | Confirm Agreed Upon Known Enhancements | 30 hrs | 5 days | Tue 10/14/25 | Mon 10/20/25 | 1319SS | 1323 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5400 | 1321 | Future Task |  |  | D678 | Bryan Sohayda |  | Create DEL Draft - Wrapper Document and Known Issues/Enhancements Lists | 20 hrs | 5 days | Tue 10/14/25 | Mon 10/20/25 | 1319SS | 1322 |  | Bryan Sohayda,Mary Punty
5401 | 1322 | Future Task |  |  | D678 | Bryan Sohayda |  | Review DEL Draft - Wrapper Document and Known Issues/Enhancements Lists | 48 hrs | 8 days | Tue 10/21/25 | Thu 10/30/25 | 1321 | 1323 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5370 | 1323 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DEL D678 - Final Known Issues & Enhancements Lists - Draft Submission | 0 hrs | 0 days | Thu 10/30/25 | Thu 10/30/25 | 13221320 | 1324 |  | Bryan Sohayda,Joy Schneider
5371 | 1324 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 10/31/25 | Thu 11/6/25 | 1323 | 1325 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5372 | 1325 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Style Guide Review | 1 hr | 1 day | Fri 11/7/25 | Fri 11/7/25 | 1324 | 1326 |  | Dusti Kincl
5373 | 1326 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Final Collaborative Review | 16 hrs | 5 days | Mon 11/10/25 | Mon 11/17/25 | 1325 | 1327 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5374 | 1327 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Accenture QC | 4 hrs | 2 days | Tue 11/18/25 | Wed 11/19/25 | 1326 | 1328 |  | Joy Schneider
5375 | 1328 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DEL D678 - Final Known Issues & Enhancements Lists - Submit | 0 hrs | 0 days | Wed 11/19/25 | Wed 11/19/25 | 1327 | 1329 |  | Joy Schneider
5376 | 1329 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Department QC | 4 hrs | 1 day | Thu 11/20/25 | Thu 11/20/25 | 1328 | 1330 |  | Tommy Werner,Gabriela Gibson
5377 | 1330 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Contract Manager Review | 8 hrs | 3 days | Fri 11/21/25 | Tue 11/25/25 | 1329 | 1331 |  | Sean Buchanan
5378 | 1331 | Future Task |  |  | D678 | Bryan Sohayda | Accept | DEL D678 - Final Known Issues & Enhancements Lists - Accept | 0 hrs | 0 days | Tue 11/25/25 | Tue 11/25/25 | 1330 | 1332FS+1 day,1252 | 2025-12-01 | Sean Buchanan
5407 | 1332 | Future Task |  |  | D678 | Bryan Sohayda |  | Refresh Known Issues/Enhancements List to Prep for Stage Gate 5 | 18 hrs | 5 days | Mon 12/1/25 | Fri 12/5/25 | 1331FS+1 day |  |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5379 | 1333 | Future Task | Maybe |  | D679 | Stacey Terry |  | D679 - Go-Live of Financials and Payroll Waves | 169 hrs | 60 days | Wed 11/5/25 | Wed 2/4/26
5380 | 1334 | Future Task |  |  | D679 | Stacey Terry | Create | DED D679 - Go-Live of Financials and Payroll Waves - Create | 16 hrs | 10 days | Wed 11/5/25 | Wed 11/19/25 | 1 | 1335 |  | Stacey Terry,Manojkumar Gurjar
5381 | 1335 | Future Task |  |  | D679 | Stacey Terry | Submit | DED D679 - Go-Live of Financials and Payroll Waves - Submit | 0 hrs | 0 days | Wed 11/19/25 | Wed 11/19/25 | 1334 | 1336 |  | Stacey Terry,Joy Schneider
5382 | 1336 | Future Task |  |  | D679 | Stacey Terry | Review | DED D679 - Go-Live of Financials and Payroll Waves - Collaborative Review | 28 hrs | 10 days | Thu 11/20/25 | Fri 12/5/25 | 1335 | 1337 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5383 | 1337 | Future Task |  |  | D679 | Stacey Terry | Approve | DED D679 - Go-Live of Financials and Payroll Waves - Approve | 0 hrs | 0 days | Fri 12/5/25 | Fri 12/5/25 | 1336 | 1338 |  | Jimmy Cox
5403 | 1338 | Future Task |  |  | D679 | Stacey Terry |  | Go-Live of Financials and Payroll Waves | 15 hrs | 5 days | Mon 12/8/25 | Fri 12/12/25 | 1337 | 1339 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5404 | 1339 | Future Task |  |  | D679 | Stacey Terry |  | Document Go-Live Applications Listing | 15 hrs | 5 days | Mon 12/15/25 | Fri 12/19/25 | 1338 | 1340FS+8 days,1253 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5405 | 1340 | Future Task |  |  | D679 | Stacey Terry |  | Document Go-Live Tasks completed | 15 hrs | 5 days | Mon 1/5/26 | Fri 1/9/26 | 1339FS+8 days | 1341SS |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5406 | 1341 | Future Task |  |  | D679 | Stacey Terry |  | Document Go-List of Agencies Participated | 15 hrs | 5 days | Mon 1/5/26 | Fri 1/9/26 | 1340SS | 1342 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5384 | 1342 | Future Task |  |  | D679 | Stacey Terry | Submit | DEL D679 - Go-Live of Financials and Payroll Waves - Draft Submission | 0 hrs | 0 days | Fri 1/9/26 | Fri 1/9/26 | 1341 | 1343 |  | Stacey Terry,Joy Schneider
5385 | 1343 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Pre-Submission Collaborative Review | 24 hrs | 5 days | Mon 1/12/26 | Fri 1/16/26 | 1342 | 1344 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5386 | 1344 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Style Guide Review | 1 hr | 1 day | Tue 1/20/26 | Tue 1/20/26 | 1343 | 1345 |  | Dusti Kincl
5387 | 1345 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Final Collaborative Review | 24 hrs | 5 days | Wed 1/21/26 | Tue 1/27/26 | 1344 | 1346 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5388 | 1346 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Accenture QC | 4 hrs | 2 days | Wed 1/28/26 | Thu 1/29/26 | 1345 | 1347 |  | Joy Schneider
5389 | 1347 | Future Task |  |  | D679 | Stacey Terry | Submit | DEL D679 - Go-Live of Financials and Payroll Waves - Submit | 0 hrs | 0 days | Thu 1/29/26 | Thu 1/29/26 | 1346 | 1348 |  | Joy Schneider
5390 | 1348 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Department QC | 4 hrs | 1 day | Fri 1/30/26 | Fri 1/30/26 | 1347 | 1349 |  | Tommy Werner,Gabriela Gibson
5391 | 1349 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Contract Manager Review | 8 hrs | 3 days | Mon 2/2/26 | Wed 2/4/26 | 1348 | 1350 |  | Sean Buchanan
5392 | 1350 | Future Task |  |  | D679 | Stacey Terry | Accept | DEL D679 - Go-Live of Financials and Payroll Waves - Accept | 0 hrs | 0 days | Wed 2/4/26 | Wed 2/4/26 | 1349 |  | 2026-01-01 | Sean Buchanan
6739 | 1351 | Future Task |  |  | WP425 | Bryan Sohayda |  | WP425 - Production Support Operations Plan | 356 hrs | 107 days | Thu 11/14/24 | Fri 4/18/25
6740 | 1352 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WPED WP425 - Production Support Operations Plan - Create | 8 hrs | 10 days | Thu 11/14/24 | Wed 11/27/24 | 1 | 1353 |  | Bryan Sohayda
6741 | 1353 | Future Task |  |  | WP425 | Bryan Sohayda | Submit | WPED WP425 - Production Support Operations Plan - Submit | 0 hrs | 0 days | Wed 11/27/24 | Wed 11/27/24 | 1352 | 1354 |  | Joy Schneider,Bryan Sohayda
6742 | 1354 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WPED WP425 - Production Support Operations Plan - Review | 16 hrs | 10 days | Mon 12/2/24 | Fri 12/13/24 | 1353 | 1355 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
6743 | 1355 | Future Task |  |  | WP425 | Bryan Sohayda | Approve | WPED WP425 - Production Support Operations Plan - Approve | 0 hrs | 0 days | Fri 12/13/24 | Fri 12/13/24 | 1354 | 1356 |  | Jimmy Cox
6744 | 1356 | Future Task |  |  | WP425 | Bryan Sohayda |  | Update Production Support Operations Plan | 20 hrs | 72 days | Mon 12/16/24 | Fri 3/28/25 | 1355 | 1357SS |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6745 | 1357 | Future Task |  |  | WP425 | Bryan Sohayda |  | Introduction, Overview, Collab taken with partners, team R&R | 20 hrs | 5 days | Mon 12/16/24 | Fri 12/20/24 | 1356SS | 1358FS+8 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6746 | 1358 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document Production Support services provided | 20 hrs | 5 days | Mon 1/6/25 | Fri 1/10/25 | 1357FS+8 days | 1359 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6747 | 1359 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review and provide feedback on Production Support Services Provided draft | 20 hrs | 5 days | Mon 1/13/25 | Fri 1/17/25 | 1358 | 1360 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6748 | 1360 | Future Task |  |  | WP425 | Bryan Sohayda |  | Create Maintenance Calendar template | 48 hrs | 4 days | Tue 1/21/25 | Fri 1/24/25 | 1359 | 1361 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6749 | 1361 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review Maintenance Calendar template | 20 hrs | 5 days | Mon 1/27/25 | Fri 1/31/25 | 1360 | 1362 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6750 | 1362 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document production support business processes and tools list | 20 hrs | 5 days | Mon 2/3/25 | Fri 2/7/25 | 1361 | 1363 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6751 | 1363 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review and provide feedback on Production Support business processes and tools list draft | 20 hrs | 5 days | Mon 2/10/25 | Fri 2/14/25 | 1362 | 1364 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6752 | 1364 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document production support schedule of activities | 20 hrs | 5 days | Mon 2/17/25 | Fri 2/21/25 | 1363 | 1365 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6753 | 1365 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review and provide feedback on Production Support schedule of activities draft | 20 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 1364 | 1366 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6754 | 1366 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document production support performance expectations | 20 hrs | 5 days | Mon 3/3/25 | Fri 3/7/25 | 1365 | 1367 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6755 | 1367 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review and provide feedback on Production Support performance expectations draft | 20 hrs | 5 days | Mon 3/10/25 | Fri 3/14/25 | 1366 | 1368 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6756 | 1368 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document production support team roles, responsibilities, and staffing | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1367 | 1369 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6757 | 1369 | Future Task |  |  | WP425 | Bryan Sohayda |  | Full walkthrough of Production Support Operations Plan through facilitated meetings | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 1368 | 1370 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6758 | 1370 | Future Task |  |  | WP425 | Bryan Sohayda | Submit | WP WP425 - Production Support Operations Plan - Submit | 0 hrs | 0 days | Fri 3/28/25 | Fri 3/28/25 | 1369 | 1371 |  | Joy Schneider,Bryan Sohayda
6759 | 1371 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WP WP425 - Production Support Operations Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 3/31/25 | Fri 4/11/25 | 1370 | 1372 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6760 | 1372 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WP WP425 - Production Support Operations Plan - Final Review & Edits | 12 hrs | 5 days | Mon 4/14/25 | Fri 4/18/25 | 1371 | 1373 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6761 | 1373 | Future Task |  |  | WP425 | Bryan Sohayda | Approve | WP WP425 - Production Support Operations Plan - Approve | 0 hrs | 0 days | Fri 4/18/25 | Fri 4/18/25 | 1372 | 1253 | 2025-04-01 | Jimmy Cox
6762 | 1374 | Future Task |  |  | WP427 | Bryan Sohayda |  | WP427 - Production Support Application Configuration Management Plan | 168 hrs | 85 days | Fri 1/3/25 | Fri 5/2/25
6763 | 1375 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WPED WP427 - Production Support Application Configuration Management Plan - Create | 8 hrs | 10 days | Fri 1/3/25 | Thu 1/16/25 | 1 | 1376 |  | Bryan Sohayda
6764 | 1376 | Future Task |  |  | WP427 | Bryan Sohayda | Submit | WPED WP427 - Production Support Application Configuration Management Plan - Submit | 0 hrs | 0 days | Thu 1/16/25 | Thu 1/16/25 | 1375 | 1377 |  | Joy Schneider,Bryan Sohayda
6765 | 1377 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WPED WP427 - Production Support Application Configuration Management Plan - Review | 16 hrs | 10 days | Fri 1/17/25 | Fri 1/31/25 | 1376 | 1378 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
6766 | 1378 | Future Task |  |  | WP427 | Bryan Sohayda | Approve | WPED WP427 - Production Support Application Configuration Management Plan - Approve | 0 hrs | 0 days | Fri 1/31/25 | Fri 1/31/25 | 1377 | 1379 |  | Jimmy Cox
6767 | 1379 | Future Task |  |  | WP427 | Bryan Sohayda |  | Updated Configuration Management Processes for Release and Maintenance | 20 hrs | 50 days | Mon 2/3/25 | Fri 4/11/25 | 1378 | 1380SS,1385,1381SS+10 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6768 | 1380 | Future Task |  |  | WP427 | Bryan Sohayda |  | Define and Document Application Configuration Management Processes for Release and Maintenance | 20 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1379SS | 1381 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6769 | 1381 | Future Task |  |  | WP427 | Bryan Sohayda |  | Review and confirm Application and Infrastructure Configuration Management Processes for Release and Maintenance | 20 hrs | 5 days | Mon 2/17/25 | Fri 2/21/25 | 1379SS+10 days,1380 | 1382 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6770 | 1382 | Future Task |  |  | WP427 | Bryan Sohayda |  | Define and document System Configuration Control Process Steps and Diagram | 20 hrs | 5 days | Mon 2/24/25 | Fri 2/28/25 | 1381 | 1383 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6771 | 1383 | Future Task |  |  | WP427 | Bryan Sohayda |  | Review System Configuration Control Process Steps and Diagram | 20 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1382 | 1384FS+10 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6772 | 1384 | Future Task |  |  | WP427 | Bryan Sohayda |  | Full draft review pre-submission | 20 hrs | 10 days | Mon 3/31/25 | Fri 4/11/25 | 1383FS+10 days | 1385 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6773 | 1385 | Future Task |  |  | WP427 | Bryan Sohayda | Submit | WP WP427 - Production Support Application Configuration Management Plan - Submit | 0 hrs | 0 days | Fri 4/11/25 | Fri 4/11/25 | 13791384 | 1386 |  | Joy Schneider,Bryan Sohayda
6774 | 1386 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WP WP427 - Production Support Application Configuration Management Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 4/14/25 | Fri 4/25/25 | 1385 | 1387 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6775 | 1387 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WP WP427 - Production Support Application Configuration Management Plan - Final Review & Edits | 12 hrs | 5 days | Mon 4/28/25 | Fri 5/2/25 | 1386 | 1388 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6776 | 1388 | Future Task |  |  | WP427 | Bryan Sohayda | Approve | WP WP427 - Production Support Application Configuration Management Plan - Approve | 0 hrs | 0 days | Fri 5/2/25 | Fri 5/2/25 | 1387 | 1253 | 2025-04-01 | Jimmy Cox
2953 | 1389 | Late | [5 empty] | Stakeholder Engagement | 3,213 hrs | 936 days | Mon 5/8/23 | Tue 1/26/27
2972 | 1390 | Late | [5 empty] | Training | 2,336 hrs | 928 days | Thu 5/18/23 | Tue 1/26/27
6906 | 1391 | Late |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Data Inventory for Financials and Payroll Wave | 105 hrs | 277 days | Thu 5/18/23 | Fri 6/21/24
6907 | 1392 | Late |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Data Inventory for Financials and Payroll Wave | 22 hrs | 277 days | Thu 5/18/23 | Fri 6/21/24
6908 | 1393 | Late |  |  | I-WP102 | Jennifer Reeves | Create | WPED - I-WP102 Data Inventory for Financials and Payroll Wave - Create | 2 hrs | 10 days | Thu 5/18/23 | Thu 6/1/23 | 1 | 1394 |  | Jennifer Grant,Jennifer Reeves
6909 | 1394 | Future Task |  |  | I-WP102 | Jennifer Reeves | Submit | WPED - I-WP102 Data Inventory for Financials and Payroll Wave - Submit | 0 hrs | 0 days | Thu 6/1/23 | Thu 6/1/23 | 1393 | 1395 |  | Jennifer Grant,Jennifer Reeves
6910 | 1395 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WPED - I-WP102 Data Inventory for Financials and Payroll Wave - Collaborative Review and Update | 8 hrs | 10 days | Fri 6/2/23 | Thu 6/15/23 | 1394 | 1396 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Reeves,Jennifer Grant
6911 | 1396 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | WPED - I-WP102 Data Inventory for Financials and Payroll Wave - Approve | 0 hrs | 0 days | Thu 6/15/23 | Thu 6/15/23 | 1395 | 1405 |  | Jimmy Cox
6912 | 1397 | Future Task |  |  | I-WP102 | Jennifer Reeves | Milestone | WP - IWP102 Data Inventory for Financials and Payroll Wave - Submit | 0 hrs | 0 days | Wed 5/29/24 | Wed 5/29/24 | 1436 | 1398 |  | Jennifer Grant,Jennifer Reeves | Why is this task a Milestone? | Angie
6913 | 1398 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP - IWP102 Data Inventory for Financials and Payroll Wave - Dept QC | 2 hrs | 1 day | Thu 5/30/24 | Thu 5/30/24 | 1397 | 1399 |  | Gabriela Gibson
6914 | 1399 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP - IWP102 Data Inventory for Financials and Payroll Wave - Collaborative Review and Update | 7 hrs | 10 days | Fri 5/31/24 | Thu 6/13/24 | 1398 | 1400 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Nikki Klein,Daylin Reyes,Angie Robertson
6915 | 1400 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP - IWP102 Data Inventory for Financials and Payroll Wave - Style Guide Review | 1 hr | 1 day | Fri 6/14/24 | Fri 6/14/24 | 1399 | 1401 |  | Tatiana Eubanks
6916 | 1401 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP - IWP102 Data Inventory for Financials and Payroll Wave - Final Review and Update | 2 hrs | 5 days | Mon 6/17/24 | Fri 6/21/24 | 1400 | 1402 |  | Angie Robertson,Jimmy Cox
6917 | 1402 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | WP - IWP102 Data Inventory for Financials and Payroll Wave - Approve | 0 hrs | 0 days | Fri 6/21/24 | Fri 6/21/24 | 1401 |  |  | Jimmy Cox
6918 | 1403 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | Data Inventory for Financials and Payroll Wave | 83 hrs | 245 days | Fri 6/16/23 | Wed 6/5/24
6919 | 1404 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 1 - Data | 20 hrs | 45 days | Fri 6/16/23 | Fri 8/18/23
6920 | 1405 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create - Data Inventory Format | 7 hrs | 5 days | Fri 6/16/23 | Thu 6/22/23 | 1396 | 1406 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Nikki Klein,Daylin Reyes,Angie Robertson
6921 | 1406 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory Format | 5 hrs | 5 days | Fri 6/23/23 | Thu 6/29/23 | 1405 | 1407 |  | Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Daylin Reyes,Angie Robertson
6922 | 1407 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory Format | 1 hr | 5 days | Fri 6/30/23 | Fri 7/7/23 | 1406 | 1408 |  | Jimmy Cox
6923 | 1408 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | Mon 7/10/23 | Fri 7/28/23 | 1407 | 1409 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6924 | 1409 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 15 days | Mon 7/31/23 | Fri 8/18/23 | 1408 |  |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6925 | 1410 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 2 - Data | 7 hrs | 20 days | Mon 10/9/23 | Fri 11/3/23
6926 | 1411 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | Mon 10/9/23 | Fri 10/27/23 | 57SS | 1412 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6927 | 1412 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 5 days | Mon 10/30/23 | Fri 11/3/23 | 1411 |  |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6928 | 1413 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 3 - Data | 13 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
6929 | 1414 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 1 | 14151421 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6930 | 1415 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1414 | 14161422 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6931 | 1416 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Functional Teams | 6 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1415 | 1418 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6932 | 1417 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Update & Publish Data Inventory | 18 hrs | 25 days | Fri 2/2/24 | Thu 3/7/24
6933 | 1418 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 5 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1416 | 1419 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6934 | 1419 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1418 | 1420 |  | Jimmy Cox
6935 | 1420 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Coordinate Knowledge Base Update | 2 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1419 |  |  | Jennifer Reeves,Daylin Reyes
6936 | 1421 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create Communication for Data Inventory | 2 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1414 |  |  | Jennifer Grant,Jennifer Reeves
6937 | 1422 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review for Communication for Data Inventory | 2 hrs | 9 days | Fri 2/9/24 | Wed 2/21/24 | 1415 | 1423 |  | Dusti Kincl,Angie Robertson
6938 | 1423 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Communication | 1 hr | 5 days | Thu 2/22/24 | Wed 2/28/24 | 1422 | 1424 |  | Jimmy Cox
6939 | 1424 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Publish Data Inventory | 4 hrs | 2 days | Thu 2/29/24 | Fri 3/1/24 | 1423 | 1425 |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6940 | 1425 | Future Task |  | RW-Communication | I-WP102 | Jennifer Reeves | Create | I-WP102 Share - Communication for Data Inventory | 1 hr | 2 days | Mon 3/4/24 | Tue 3/5/24 | 1424 |  |  | Dusti Kincl
6941 | 1426 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 4 - Data | 11 hrs | 25 days | Wed 4/10/24 | Tue 5/14/24
6942 | 1427 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 3 hrs | 15 days | Wed 4/10/24 | Tue 4/30/24 | 1 | 14281434 |  | Jennifer Reeves,Pradeep Koul,Tanya McCarty
6943 | 1428 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 2 hrs | 5 days | Wed 5/1/24 | Tue 5/7/24 | 1427 | 1429 |  | Jennifer Reeves,Matthew Breeding
6944 | 1429 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 6 hrs | 5 days | Wed 5/8/24 | Tue 5/14/24 | 1428 | 1431 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6945 | 1430 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Update & Publish Data Inventory | 14 hrs | 25 days | Wed 5/1/24 | Wed 6/5/24
6946 | 1431 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 3 hrs | 5 days | Wed 5/15/24 | Tue 5/21/24 | 1429 | 1432 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves
6947 | 1432 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory | 2 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1431 | 1433 |  | Angie Robertson,Jimmy Cox
6948 | 1433 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Coordinate Knowledge Base Update | 2 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1432 |  |  | Jennifer Reeves,Daylin Reyes
6949 | 1434 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create Communication - Data Inventory | 2 hrs | 5 days | Wed 5/1/24 | Tue 5/7/24 | 1427 | 1435 |  | Jennifer Grant,Jennifer Reeves
6950 | 1435 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Communication for Data Inventory | 2 hrs | 10 days | Wed 5/8/24 | Tue 5/21/24 | 1434 | 1436 |  | Dusti Kincl,Angie Robertson
6951 | 1436 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Communication for Data Inventory | 2 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1435 | 13971437 |  | Jennifer Grant,Jennifer Reeves
6952 | 1437 | Future Task |  | RW-Communication | I-WP102 | Jennifer Reeves | Create | I-WP102 Share Communication for Data Inventory | 1 hr | 2 days | Thu 5/30/24 | Fri 5/31/24 | 1436 |  |  | Dusti Kincl
7039 | 1438 | Late |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Accounting Entry Inventory | 271 hrs | 285 days | Thu 5/18/23 | Wed 7/3/24
7040 | 1439 | Late |  |  | I-WP103 | Jennifer Reeves | Create | WPED - I-WP103 Accounting Entry Inventory - Create | 10 hrs | 10 days | Thu 5/18/23 | Thu 6/1/23 | 1 | 1440 |  | Jennifer Grant,Jennifer Reeves
7041 | 1440 | Future Task |  |  | I-WP103 | Jennifer Reeves | Submit | WPED - I-WP103 Accounting Entry Inventory - Submit | 0 hrs | 0 days | Thu 6/1/23 | Thu 6/1/23 | 1439 | 1441 |  | Jennifer Grant,Jennifer Reeves
7042 | 1441 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WPED - I-WP103 Accounting Entry Inventory - Collaborative Review and Update | 10 hrs | 10 days | Fri 6/2/23 | Thu 6/15/23 | 1440 | 1442 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7043 | 1442 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | WPED - I-WP103 Accounting Entry Inventory - Approve | 0 hrs | 0 days | Thu 6/15/23 | Thu 6/15/23 | 1441 | 1451FS+37 days |  | Jimmy Cox
7044 | 1443 | Future Task |  |  | I-WP103 | Jennifer Reeves | Submit | WP - IWP103 Accounting Entry Inventory - Submit | 0 hrs | 0 days | Mon 6/10/24 | Mon 6/10/24 | 1482 | 1444 |  | Jennifer Grant,Jennifer Reeves
7045 | 1444 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP - IWP103 Accounting Entry Inventory - Dept QC | 1 hr | 1 day | Tue 6/11/24 | Tue 6/11/24 | 1443 | 1445 |  | Gabriela Gibson
7046 | 1445 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP - IWP103 Accounting Entry Inventory - Collaborative Review and Update | 10 hrs | 10 days | Wed 6/12/24 | Tue 6/25/24 | 1444 | 1446 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7047 | 1446 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP - IWP103 Accounting Entry Inventory - Style Guide Review | 1 hr | 1 day | Wed 6/26/24 | Wed 6/26/24 | 1445 | 1447 |  | Tatiana Eubanks
7048 | 1447 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP - IWP103 Accounting Entry Inventory - Final Review and Update | 2 hrs | 5 days | Thu 6/27/24 | Wed 7/3/24 | 1446 | 1448 |  | Angie Robertson,Jimmy Cox
7049 | 1448 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | WP - IWP103 Accounting Entry Inventory - Approve | 0 hrs | 0 days | Wed 7/3/24 | Wed 7/3/24 | 1447 |  |  | Jimmy Cox
7050 | 1449 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | Accounting Entry Inventory | 237 hrs | 216 days | Wed 8/9/23 | Mon 6/17/24
7051 | 1450 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 1 | 48 hrs | 37 days | Wed 8/9/23 | Fri 9/29/23
7052 | 1451 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Accounting Entry Inventory Format | 10 hrs | 5 days | Wed 8/9/23 | Tue 8/15/23 | 1442FS+37 days | 1452 |  | Jennifer Reeves,Daylin Reyes
7053 | 1452 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory Format | 10 hrs | 6 days | Wed 8/16/23 | Wed 8/23/23 | 1451 | 1453 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7054 | 1453 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory Format | 10 hrs | 5 days | Thu 8/24/23 | Wed 8/30/23 | 1452 | 1454 |  | Jimmy Cox
7055 | 1454 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 16 days | Thu 8/31/23 | Fri 9/22/23 | 1453,38 | 1455 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7056 | 1455 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Mon 9/25/23 | Fri 9/29/23 | 1454 |  |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7057 | 1456 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 2 | 18 hrs | 20 days | Tue 10/24/23 | Tue 11/21/23
7058 | 1457 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | Tue 10/24/23 | Tue 11/14/23 | 57 | 1458 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7059 | 1458 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Wed 11/15/23 | Tue 11/21/23 | 1457 |  |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7060 | 1459 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 3 | 28 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
7061 | 1460 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 136SS | 14611467 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7062 | 1461 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1460 | 1462 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7063 | 1462 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Functional Teams | 10 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1461 | 1464 |  | Brendan Jones,Janice Jackson,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7064 | 1463 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Update & Publish Accounting Entry Inventory | 54 hrs | 25 days | Fri 2/2/24 | Thu 3/7/24
7065 | 1464 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1462 | 1465 |  | Jennifer Reeves,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson
7066 | 1465 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory | 2 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1464 | 1466 |  | Jimmy Cox
7067 | 1466 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Coordinate Knowledge Base Update | 10 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1465 |  |  | Jennifer Reeves,Daylin Reyes
7068 | 1467 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1460 | 1468 |  | Jennifer Grant,Jennifer Reeves
7069 | 1468 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review for Communication for Accounting Entry Inventory | 10 hrs | 9 days | Fri 2/9/24 | Wed 2/21/24 | 1467 | 1469 |  | Dusti Kincl,Angie Robertson
7070 | 1469 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Thu 2/22/24 | Wed 2/28/24 | 1468 | 1470 |  | Jimmy Cox
7071 | 1470 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Publish - Accounting Entry Inventory | 1 hr | 2 days | Thu 2/29/24 | Fri 3/1/24 | 1469 | 1471 |  | Pradeep Koul,Richard Saltford,Daylin Reyes,Dusti Kincl
7072 | 1471 | Future Task |  | RW-Communication | I-WP103 | Jennifer Reeves | Create | I-WP103 Share - Communication for Accounting Entry Inventory | 1 hr | 2 days | Mon 3/4/24 | Tue 3/5/24 | 1470 |  |  | Dusti Kincl
7073 | 1472 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 4 | 28 hrs | 25 days | Mon 4/22/24 | Fri 5/24/24
7074 | 1473 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | Mon 4/22/24 | Fri 5/10/24 | 155SS | 14741480 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7075 | 1474 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1473 | 1475 |  | Matthew Breeding,Jennifer Reeves
7076 | 1475 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Functional Teams | 10 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1474 | 1477 |  | Brendan Jones,Janice Jackson,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7077 | 1476 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Update & Publish Accounting Entry Inventory | 61 hrs | 25 days | Mon 5/13/24 | Mon 6/17/24
7078 | 1477 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review -Accounting Entry Inventory | 10 hrs | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1475 | 1478 |  | Jennifer Reeves,Matthew Breeding,Deana Metcalf
7079 | 1478 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory | 10 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1477 | 1479 |  | Jimmy Cox,Angie Robertson
7080 | 1479 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Coordinate Knowledge Base Update | 10 hrs | 5 days | Tue 6/11/24 | Mon 6/17/24 | 1478 |  |  | Jennifer Reeves,Daylin Reyes
7081 | 1480 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1473 | 1481 |  | Jennifer Grant,Jennifer Reeves
7082 | 1481 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Communication for Accounting Entry Inventory | 10 hrs | 10 days | Mon 5/20/24 | Mon 6/3/24 | 1480 | 1482 |  | Dusti Kincl,Angie Robertson
7083 | 1482 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Communication for Accounting Entry Inventory | 10 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1481 | 14431483 |  | Jennifer Grant,Jennifer Reeves
7084 | 1483 | Future Task |  | RW-Communication | I-WP103 | Jennifer Reeves | Create | I-WP103 Share Communication for Accounting Entry Inventory | 1 hr | 2 days | Tue 6/11/24 | Wed 6/12/24 | 1482 |  |  | Dusti Kincl
7085 | 1484 | Late |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Error Matrix | 113 hrs | 287 days | Thu 5/18/23 | Mon 7/8/24
7086 | 1485 | Late |  |  | I-WP104 | Jennifer Reeves | Create | WPED - I-WP104 Error Matrix - Create | 9 hrs | 9 days | Thu 5/18/23 | Wed 5/31/23 | 1 | 1486 |  | Jennifer Grant,Jennifer Reeves
7087 | 1486 | Future Task |  |  | I-WP104 | Jennifer Reeves | Submit | WPED - I-WP104 Error Matrix - Submit | 0 hrs | 0 days | Wed 5/31/23 | Wed 5/31/23 | 1485 | 1487 |  | Jennifer Grant,Jennifer Reeves
7088 | 1487 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WPED - I-WP104 Error Matrix - Collaborative Review and Update | 10 hrs | 10 days | Thu 6/1/23 | Wed 6/14/23 | 1486 | 14881496 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7089 | 1488 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | WPED - I-WP104 Error Matrix - Approve | 0 hrs | 0 days | Wed 6/14/23 | Wed 6/14/23 | 1487 |  |  | Jimmy Cox
7090 | 1489 | Future Task |  |  | I-WP104 | Jennifer Reeves | Submit | WP - IWP104 Error Matrix - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 15271528 | 1490 |  | Jennifer Grant,Jennifer Reeves
7091 | 1490 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP - IWP104 Error Matrix - Dept QC | 1 hr | 1 day | Thu 6/13/24 | Thu 6/13/24 | 1489 | 1491 |  | Gabriela Gibson
7092 | 1491 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP - IWP104 Error Matrix - Collaborative Review and Update | 10 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1490 | 1492 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7093 | 1492 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP - IWP104 Error Matrix - Style Guide Review | 1 hr | 1 day | Fri 6/28/24 | Fri 6/28/24 | 1491 | 1493 |  | Tatiana Eubanks
7094 | 1493 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP - IWP104 Error Matrix - Final Review and Update | 2 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 1492 | 1494 |  | Angie Robertson,Jimmy Cox
7095 | 1494 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | WP - IWP104 Error Matrix - Approve | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1493 |  |  | Jimmy Cox
7096 | 1495 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 1 | 15 hrs | 63 days | Thu 6/15/23 | Wed 9/13/23
7097 | 1496 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Error Matrix Format | 2 hrs | 5 days | Thu 6/15/23 | Wed 6/21/23 | 1487 | 1497 |  | Jennifer Reeves,Daylin Reyes
7098 | 1497 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 5 hrs | 5 days | Thu 6/22/23 | Wed 6/28/23 | 1496 | 1498 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7099 | 1498 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix Format | 1 hr | 5 days | Thu 6/29/23 | Thu 7/6/23 | 1497 | 1499 |  | Jimmy Cox
7100 | 1499 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Wed 8/2/23 | Tue 8/22/23 | 1498,38 | 1500 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7101 | 1500 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 15 days | Wed 8/23/23 | Wed 9/13/23 | 1499 |  |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7102 | 1501 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 2 | 7 hrs | 20 days | Tue 10/24/23 | Tue 11/21/23
7103 | 1502 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Tue 10/24/23 | Tue 11/14/23 | 57 | 1503 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7104 | 1503 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | Wed 11/15/23 | Tue 11/21/23 | 1502 |  |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7105 | 1504 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 3 | 13 hrs | 25 days | Mon 1/29/24 | Fri 3/1/24
7106 | 1505 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Mon 1/29/24 | Fri 2/16/24 | 136 | 15061512 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7107 | 1506 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | Mon 2/19/24 | Fri 2/23/24 | 1505 | 1507 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7108 | 1507 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Functional Teams | 6 hrs | 5 days | Mon 2/26/24 | Fri 3/1/24 | 1506 | 1509 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7109 | 1508 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Update & Publish Error Matrix | 18 hrs | 25 days | Mon 2/19/24 | Fri 3/22/24
7110 | 1509 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 5 hrs | 5 days | Mon 3/4/24 | Fri 3/8/24 | 1507 | 1510 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7111 | 1510 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix | 1 hr | 5 days | Mon 3/11/24 | Fri 3/15/24 | 1509 | 1511 |  | Jimmy Cox
7112 | 1511 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Coordinate Knowledge Base Update | 2 hrs | 5 days | Mon 3/18/24 | Fri 3/22/24 | 1510 |  |  | Jennifer Reeves,Daylin Reyes
7113 | 1512 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Communication for Error Matrix | 2 hrs | 5 days | Mon 2/19/24 | Fri 2/23/24 | 1505 | 1513 |  | Jennifer Grant,Jennifer Reeves
7114 | 1513 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review for Communication for Error Matrix | 2 hrs | 9 days | Mon 2/26/24 | Thu 3/7/24 | 1512 | 1514 |  | Dusti Kincl,Angie Robertson
7115 | 1514 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Communication for Error Matrix | 1 hr | 5 days | Fri 3/8/24 | Thu 3/14/24 | 1513 | 1515 |  | Jimmy Cox
7116 | 1515 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Publish - Error Matrix | 4 hrs | 2 days | Fri 3/15/24 | Mon 3/18/24 | 1514 | 1516 |  | Pradeep Koul,Richard Saltford,Daylin Reyes,Dusti Kincl
7117 | 1516 | Future Task |  | RW-Communication | I-WP104 | Jennifer Reeves | Create | I-WP104 Share - Communication for Error Matrix | 1 hr | 2 days | Tue 3/19/24 | Wed 3/20/24 | 1515 |  |  | Dusti Kincl
7118 | 1517 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 4 | 13 hrs | 25 days | Mon 4/22/24 | Fri 5/24/24
7119 | 1518 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | Mon 4/22/24 | Fri 5/10/24 | 155SS | 15191525 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7120 | 1519 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1518 | 1520 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7121 | 1520 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Functional Teams | 6 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1519 | 1522 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7122 | 1521 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Update & Publish Error Matrix | 14 hrs | 25 days | Mon 5/13/24 | Mon 6/17/24
7123 | 1522 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 3 hrs | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1520 | 1523 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves
7124 | 1523 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix | 2 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1522 | 1524 |  | Angie Robertson,Jimmy Cox
7125 | 1524 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Coordinate Knowledge Base Update | 2 hrs | 5 days | Tue 6/11/24 | Mon 6/17/24 | 1523 |  |  | Jennifer Reeves,Daylin Reyes
7126 | 1525 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Task Instructions & Communication for Error Matrix | 2 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1518 | 1526 |  | Jennifer Reeves,Nikki Klein
7127 | 1526 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Communication for Error Matrix | 2 hrs | 10 days | Mon 5/20/24 | Mon 6/3/24 | 1525 | 1527 |  | Dusti Kincl,Angie Robertson
7128 | 1527 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Task Instructions & Communication for Error Matrix | 2 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1526 | 14891528 |  | Jennifer Grant,Jennifer Reeves
7129 | 1528 | Future Task |  | RW-Communication | I-WP104 | Jennifer Reeves | Create | I-WP104 Share Communication for Error Matrix | 1 hr | 2 days | Tue 6/11/24 | Wed 6/12/24 | 1527 | 1489 |  | Dusti Kincl
6862 | 1529 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Maintain Catalogs | 239 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6863 | 1530 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Report Catalog | 51 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6864 | 1531 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | WPED - I-WP105 Report Catalog - Create | 2 hrs | 10 days | Fri 6/9/23 | Thu 6/22/23 | 1 | 1532 |  | Jennifer Grant,Jennifer Reeves
6865 | 1532 | Future Task |  |  | I-WP105 | Jennifer Reeves | Submit | WPED - I-WP105 Report Catalog - Submit | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 1531 | 1533 |  | Jennifer Grant,Jennifer Reeves
6866 | 1533 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WPED - I-WP105 Report Catalog - Collaborative Review and Update | 8 hrs | 10 days | Fri 6/23/23 | Fri 7/7/23 | 1532 | 1534 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Reeves,Jennifer Grant
6867 | 1534 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | WPED - I-WP105 Report Catalog - Approve | 0 hrs | 0 days | Fri 7/7/23 | Fri 7/7/23 | 1533 |  |  | Jimmy Cox
6868 | 1535 | Future Task |  |  | I-WP105 | Jennifer Reeves | Milestone | WP - IWP105 Report Catalog - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 15581571 | 1536 |  | Jennifer Grant,Jennifer Reeves | Why is this task a Milestone? | Angie
6869 | 1536 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP - IWP105 Report Catalog - Dept QC | 1 hr | 1 day | Thu 6/13/24 | Thu 6/13/24 | 1535 | 1537 |  | Jenifer Hartsfield
6870 | 1537 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP - IWP105 Report Catalog - Collaborative Review and Update | 2 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1536 | 1538 |  | Jennifer Grant,Jennifer Reeves
6871 | 1538 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP - IWP105 Report Catalog - Style Guide Review | 1 hr | 1 day | Fri 6/28/24 | Fri 6/28/24 | 1537 | 1539 |  | Tatiana Eubanks
6872 | 1539 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP - IWP105 Report Catalog - Final Review and Update | 2 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 1538 | 1540 |  | Angie Robertson,Jimmy Cox
6873 | 1540 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | WP - IWP105 Report Catalog - Approve | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1539 |  |  | Jimmy Cox
6874 | 1541 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 1 - Reports | 35 hrs | 20 days | Tue 7/18/23 | Mon 8/14/23
6875 | 1542 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | Tue 7/18/23 | Mon 8/7/23 | 38SS | 1543 |  | Pradeep Koul,Tanya McCarty,Stanton Beazley,Jennifer Reeves,Elizabeth Sargent
6876 | 1543 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | Tue 8/8/23 | Mon 8/14/23 | 1542 |  |  | Jennifer Grant,Jennifer Reeves
6877 | 1544 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 2 - Reports | 35 hrs | 20 days | Mon 10/9/23 | Fri 11/3/23
6878 | 1545 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | Mon 10/9/23 | Fri 10/27/23 | 57SS | 1546 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6879 | 1546 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | Mon 10/30/23 | Fri 11/3/23 | 1545 |  |  | Jennifer Grant,Jennifer Reeves
6880 | 1547 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 3 - Reports | 55 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
6881 | 1548 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 136SS | 1549 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6882 | 1549 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1548 | 15501556 |  | Jennifer Grant,Jennifer Reeves
6883 | 1550 | Future Task |  |  |  | Jennifer Reeves | Review | I-WP105 Collaborative Review - Functional Teams | 20 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1549 | 1552 |  | Jennifer Grant,Jennifer Reeves,Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
6884 | 1551 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Update & Publish Report Catalog | 41 hrs | 22 days | Fri 2/9/24 | Mon 3/11/24
6885 | 1552 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Report Catalog | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1550 | 1553 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6886 | 1553 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Report Catalog | 2 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1552 | 1554 |  | Jimmy Cox
6887 | 1554 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Coordinate Knowledge Base Update | 18 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1553 | 1555 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6888 | 1555 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Publish - Report Catalog | 4 hrs | 2 days | Fri 3/8/24 | Mon 3/11/24 | 1554 |  |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6889 | 1556 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Create Communication for Report Catalog | 2 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1549 | 1557 |  | Jennifer Grant,Jennifer Reeves
6890 | 1557 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review for Communication | 3 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1556 | 1558 |  | Dusti Kincl,Angie Robertson,Jennifer Reeves
6891 | 1558 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Communication for Report Catalog | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1557 | 15351559 |  | Jimmy Cox
6892 | 1559 | Future Task |  | RW-Communication | I-WP105 | Jennifer Reeves | Create | I-WP105 Share Communication for Report Catalog | 1 hr | 2 days | Fri 3/1/24 | Mon 3/4/24 | 1558 |  |  | Dusti Kincl
6893 | 1560 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 4 - Reports | 32 hrs | 27 days | Mon 4/22/24 | Wed 5/29/24
6894 | 1561 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 10 hrs | 16 days | Mon 4/22/24 | Mon 5/13/24 | 155SS | 1562 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
6895 | 1562 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 2 hrs | 6 days | Tue 5/14/24 | Tue 5/21/24 | 1561 | 15631569 |  | Jennifer Grant,Jennifer Reeves
6896 | 1563 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Functional Teams | 20 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1562 | 1565 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6897 | 1564 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Update & Publish Report Catalog | 25 hrs | 22 days | Wed 5/22/24 | Fri 6/21/24
6898 | 1565 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Report Catalog | 10 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1563 | 1566 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6899 | 1566 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Report Catalog | 1 hr | 5 days | Thu 6/6/24 | Wed 6/12/24 | 1565 | 1567 |  | Jimmy Cox
6900 | 1567 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Coordinate Knowledge Base Update | 3 hrs | 5 days | Thu 6/13/24 | Wed 6/19/24 | 1566 | 1568 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6901 | 1568 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Publish - Report Catalog | 4 hrs | 2 days | Thu 6/20/24 | Fri 6/21/24 | 1567 |  |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6902 | 1569 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Create Communication for Report Catalog | 2 hrs | 5 days | Wed 5/22/24 | Wed 5/29/24 | 1562 | 1570 |  | Jennifer Grant,Jennifer Reeves
6903 | 1570 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review for Communication | 3 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1569 | 1571 |  | Dusti Kincl,Angie Robertson,Jennifer Reeves
6904 | 1571 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Communication for Report Catalog | 1 hr | 5 days | Thu 6/6/24 | Wed 6/12/24 | 1570 | 15351572 |  | Jimmy Cox
6905 | 1572 | Future Task |  | RW-Communication | I-WP105 | Jennifer Reeves | Create | I-WP105 Share Communication for Report Catalog | 1 hr | 2 days | Thu 6/13/24 | Fri 6/14/24 | 1571 |  |  | Dusti Kincl
6953 | 1573 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Interface Catalog | 210 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6954 | 1574 | Future Task |  |  | I-WP106 | Matt Breeding | Create | WPED - I-WP106 Interface Catalog - Create | 10 hrs | 10 days | Fri 6/9/23 | Thu 6/22/23 | 1 | 1575 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding
6955 | 1575 | Future Task |  |  | I-WP106 | Matt Breeding | Submit | WPED - I-WP106 Interface Catalog - Submit | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 1574 | 1576 |  | Matthew Breeding
6956 | 1576 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WPED - I-WP106 Interface Catalog - Collaborative Review and Update | 10 hrs | 10 days | Fri 6/23/23 | Fri 7/7/23 | 1575 | 1577 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
6957 | 1577 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | WPED - I-WP106 Interface Catalog - Approve | 0 hrs | 0 days | Fri 7/7/23 | Fri 7/7/23 | 1576 |  |  | Jimmy Cox
6958 | 1578 | Future Task |  |  | I-WP106 | Matt Breeding | Submit | WP - IWP106 Interface Catalog - Submit | 0 hrs | 0 days | Mon 6/3/24 | Mon 6/3/24 | 1614 | 1579 |  | Matthew Breeding
6959 | 1579 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP - IWP106 Interface Catalog - Dept QC | 1 hr | 1 day | Tue 6/4/24 | Tue 6/4/24 | 1578 | 1580 |  | Gabriela Gibson
6960 | 1580 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP - IWP106 Interface Catalog - Collaborative Review and Update | 10 hrs | 10 days | Wed 6/5/24 | Tue 6/18/24 | 1579 | 1581 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
6961 | 1581 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP - IWP106 Interface Catalog - Style Guide Review | 2 hrs | 1 day | Wed 6/19/24 | Wed 6/19/24 | 1580 | 1582 |  | Tatiana Eubanks
6962 | 1582 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP - IWP106 Interface Catalog - Final Review and Update | 10 hrs | 5 days | Thu 6/20/24 | Wed 6/26/24 | 1581 | 1583 |  | Angie Robertson,Jimmy Cox
6963 | 1583 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | WP - IWP106 Interface Catalog - Approve | 0 hrs | 0 days | Wed 6/26/24 | Wed 6/26/24 | 1582 |  |  | Jimmy Cox
6964 | 1584 | Future Task |  |  | I-WP106 | Matt Breeding |  | Interface Catalog | 167 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6965 | 1585 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 1 - Interfaces | 12 hrs | 20 days | Tue 7/18/23 | Mon 8/14/23
6966 | 1586 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Tue 7/18/23 | Mon 8/7/23 | 38SS | 1587 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6967 | 1587 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Tue 8/8/23 | Mon 8/14/23 | 1586 |  |  | Matthew Breeding
6968 | 1588 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 2 - Interfaces | 12 hrs | 20 days | Wed 10/11/23 | Tue 11/7/23
6969 | 1589 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Wed 10/11/23 | Tue 10/31/23 | 57SS+2 days | 1590 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6970 | 1590 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Wed 11/1/23 | Tue 11/7/23 | 1589 |  |  | Matthew Breeding
6971 | 1591 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 3 - Interfaces | 22 hrs | 25 days | Thu 1/11/24 | Thu 2/15/24
6972 | 1592 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Thu 1/11/24 | Thu 2/1/24 | 136SS | 1593 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6973 | 1593 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Fri 2/2/24 | Thu 2/8/24 | 1592 | 15941600 |  | Matthew Breeding
6974 | 1594 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Functional Teams | 10 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1593 | 1596 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
6975 | 1595 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Update & Publish Interface Catalog | 45 hrs | 24 days | Fri 2/9/24 | Wed 3/13/24
6976 | 1596 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Interface Catalog | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1594 | 1597 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6977 | 1597 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Interface Catalog | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1596 | 1598 |  | Jimmy Cox
6978 | 1598 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Coordinate Knowledge Base Update | 10 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1597 | 1599 |  | Matthew Breeding,Daylin Reyes
6979 | 1599 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Publish - Interface Catalog | 10 hrs | 2 days | Fri 3/8/24 | Mon 3/11/24 | 1598 | 1603 |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
6980 | 1600 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Create Communication for Interface Catalog | 2 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1593 | 1601 |  | Matthew Breeding,Dusti Kincl
6981 | 1601 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review for Communication for Interface Catalog | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1600 | 1602 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6982 | 1602 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Communication for Interface Catalog | 1 hr | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1601 |  |  | Jimmy Cox
6983 | 1603 | Future Task |  | RW-Communication | I-WP106 | Matt Breeding | Create | I-WP106 Share Communication for Interface Catalog | 1 hr | 2 days | Tue 3/12/24 | Wed 3/13/24 | 1599 |  |  | Dusti Kincl
6984 | 1604 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 4 - Interfaces | 12 hrs | 20 days | Mon 4/22/24 | Fri 5/17/24
6985 | 1605 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | Mon 4/22/24 | Fri 5/10/24 | 155SS | 16061612 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6986 | 1606 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1605 | 1608 |  | Matthew Breeding
6987 | 1607 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Update & Publish Interface Catalog | 64 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6988 | 1608 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Interface Catalog | 10 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1606 | 1609 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6989 | 1609 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Interface Catalog | 1 hr | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1608 | 1610 |  | Jimmy Cox
6990 | 1610 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Coordinate Knowledge Base Update | 2 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1609 | 1611 |  | Matthew Breeding,Daylin Reyes
6991 | 1611 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Publish Interface Catalog | 1 hr | 2 days | Tue 6/11/24 | Wed 6/12/24 | 1610 |  |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
6992 | 1612 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Create Communication for Interface Catalog | 2 hrs | 5 days | Mon 5/13/24 | Fri 5/17/24 | 1605 | 1613 |  | Matthew Breeding,Dusti Kincl
6993 | 1613 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review for Communication for Interface Catalog | 3 hrs | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1612 | 1614 |  | Dusti Kincl,Angie Robertson,Matthew Breeding
6994 | 1614 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Communication for Interface Catalog | 1 hr | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1613 | 15781615 |  | Jimmy Cox
6995 | 1615 | Future Task |  | RW-Communication | I-WP106 | Matt Breeding | Create | I-WP106 Share Communication for Interface Catalog | 1 hr | 2 days | Tue 6/4/24 | Wed 6/5/24 | 1614 |  |  | Dusti Kincl
6996 | 1616 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Conversions Inventory | 43 hrs | 272 days | Fri 6/9/23 | Mon 7/8/24
6997 | 1617 | Future Task |  |  | I-WP107 | Matt Breeding | Create | WPED - I-WP107 Conversions Inventory - Create | 10 hrs | 10 days | Fri 6/9/23 | Thu 6/22/23 | 1 | 1618 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding
6998 | 1618 | Future Task |  |  | I-WP107 | Matt Breeding | Submit | WPED - I-WP107 Conversions Inventory - Submit | 0 hrs | 0 days | Thu 6/22/23 | Thu 6/22/23 | 1617 | 1619 |  | Matthew Breeding
6999 | 1619 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WPED - I-WP107 Conversions Inventory - Collaborative Review and Update | 10 hrs | 10 days | Fri 6/23/23 | Fri 7/7/23 | 1618 | 1620 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7000 | 1620 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | WPED - I-WP107 Conversions Inventory - Approve | 0 hrs | 0 days | Fri 7/7/23 | Fri 7/7/23 | 1619 |  |  | Jimmy Cox
7001 | 1621 | Future Task |  |  | I-WP107 | Matt Breeding | Submit | WP - IWP107 Conversions Inventory - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 1657 | 1622 |  | Matthew Breeding
7002 | 1622 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP - IWP107 Conversions Inventory - Dept QC | 1 hr | 1 day | Thu 6/13/24 | Thu 6/13/24 | 1621 | 1623 |  | Gabriela Gibson
7003 | 1623 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP - IWP107 Conversions Inventory - Collaborative Review and Update | 10 hrs | 10 days | Fri 6/14/24 | Thu 6/27/24 | 1622 | 1624 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7004 | 1624 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP - IWP107 Conversions Inventory - Style Guide Review | 2 hrs | 1 day | Fri 6/28/24 | Fri 6/28/24 | 1623 | 1625 |  | Tatiana Eubanks
7005 | 1625 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP - IWP107 Conversions Inventory - Final Review and Update | 10 hrs | 5 days | Mon 7/1/24 | Mon 7/8/24 | 1624 | 1626 |  | Angie Robertson,Jimmy Cox
7006 | 1626 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | WP - IWP107 Conversions Inventory - Approve | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1625 |  |  | Jimmy Cox
7007 | 1627 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Conversions Inventory | 124 hrs | 234 days | Tue 7/18/23 | Wed 6/19/24
7008 | 1628 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 1 - Conversions | 11 hrs | 20 days | Tue 7/18/23 | Mon 8/14/23
7009 | 1629 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | Tue 7/18/23 | Mon 8/7/23 | 38SS | 1630 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7010 | 1630 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 1 hr | 5 days | Tue 8/8/23 | Mon 8/14/23 | 1629 |  |  | Matthew Breeding
7011 | 1631 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 2 - Conversions | 15 hrs | 20 days | Mon 10/16/23 | Mon 11/13/23
7012 | 1632 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | Mon 10/16/23 | Fri 11/3/23 | 57SS+5 days | 1633 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7013 | 1633 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 5 hrs | 5 days | Mon 11/6/23 | Mon 11/13/23 | 1632 |  |  | Matthew Breeding
7014 | 1634 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 3 - Conversions | 25 hrs | 25 days | Fri 1/19/24 | Thu 2/22/24
7015 | 1635 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | Fri 1/19/24 | Thu 2/8/24 | 136SS+5 days | 1636 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7016 | 1636 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 5 hrs | 5 days | Fri 2/9/24 | Thu 2/15/24 | 1635 | 16371643 |  | Matthew Breeding
7017 | 1637 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Functional Teams | 10 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1636 | 1639 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
7018 | 1638 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Update & Publish Conversion Catalog | 26 hrs | 27 days | Fri 2/16/24 | Mon 3/25/24
7019 | 1639 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Conversion Catalog | 10 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1637 | 1640 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7020 | 1640 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Conversion Catalog | 1 hr | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1639 | 1641 |  | Jimmy Cox
7021 | 1641 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Coordinate Knowledge Base Update | 2 hrs | 5 days | Fri 3/8/24 | Thu 3/14/24 | 1640 | 1642 |  | Matthew Breeding,Daylin Reyes
7022 | 1642 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Publish - Conversion Catalog | 4 hrs | 5 days | Fri 3/15/24 | Thu 3/21/24 | 1641 | 1646 |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
7023 | 1643 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create Communication for Conversion Catalog | 2 hrs | 5 days | Fri 2/16/24 | Thu 2/22/24 | 1636 | 1644 |  | Matthew Breeding,Dusti Kincl
7024 | 1644 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review for Communication for Conversion Catalog | 5 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1643 | 1645 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7025 | 1645 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Communication | 1 hr | 5 days | Fri 3/1/24 | Thu 3/7/24 | 1644 |  |  | Jimmy Cox
7026 | 1646 | Future Task |  | RW-Communication | I-WP107 | Matt Breeding | Create | I-WP107 Share Communication | 1 hr | 2 days | Fri 3/22/24 | Mon 3/25/24 | 1642 |  |  | Dusti Kincl
7027 | 1647 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 4 - Conversions | 15 hrs | 25 days | Mon 4/29/24 | Mon 6/3/24
7028 | 1648 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create & Maintain - Conversion Catalog | 10 hrs | 15 days | Mon 4/29/24 | Fri 5/17/24 | 155SS+5 days | 1649 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7029 | 1649 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 1 hr | 5 days | Mon 5/20/24 | Fri 5/24/24 | 1648 | 16501655 |  | Matthew Breeding
7030 | 1650 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Functional Teams | 4 hrs | 5 days | Tue 5/28/24 | Mon 6/3/24 | 1649 | 1652 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
7031 | 1651 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Update & Publish Conversions Catalog | 32 hrs | 17 days | Tue 5/28/24 | Wed 6/19/24
7032 | 1652 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Conversion Catalog | 10 hrs | 5 days | Tue 6/4/24 | Mon 6/10/24 | 1650 | 1653 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7033 | 1653 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Conversion Catalog | 1 hr | 5 days | Tue 6/11/24 | Mon 6/17/24 | 1652 | 1654 |  | Jimmy Cox
7034 | 1654 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Publish - Conversion Catalog | 4 hrs | 2 days | Tue 6/18/24 | Wed 6/19/24 | 1653 |  |  | Daylin Reyes,Richard Saltford,Pradeep Koul,Dusti Kincl
7035 | 1655 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create Communication for Conversions Catalog | 3 hrs | 2 days | Tue 5/28/24 | Wed 5/29/24 | 1649 | 1656 |  | Dusti Kincl,Pradeep Koul,Richard Barnes
7036 | 1656 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review for Communication for Conversions Catalog | 10 hrs | 5 days | Thu 5/30/24 | Wed 6/5/24 | 1655 | 1657 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Nikki Klein,Daylin Reyes,Jennifer Grant
7037 | 1657 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Communication | 3 hrs | 5 days | Thu 6/6/24 | Wed 6/12/24 | 1656 | 16211658 |  | Dusti Kincl,Angie Robertson,Matthew Breeding
7038 | 1658 | Future Task |  | RW-Communication | I-WP107 | Matt Breeding | Create | I-WP107 Share Communication for Conversions Catalog | 1 hr | 5 days | Thu 6/13/24 | Wed 6/19/24 | 1657 |  |  | Jimmy Cox
2973 | 1659 | Future Task |  |  | I-WP108 | Kimberly Kemp |  | I-WP108 Training Curriculum | 53 hrs | 360 days | Thu 6/1/23 | Thu 10/31/24
2974 | 1660 | Future Task |  |  | I-WP108 | Carolyn Hicks | Create | WPED - I-WP108 - Training Curriculum - Create | 10 hrs | 10 days | Thu 6/1/23 | Wed 6/14/23 | 1 | 1661 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
2975 | 1661 | Future Task |  |  | I-WP108 | Carolyn Hicks | Submit | WPED - I-WP108 - Training Curriculum - Submit | 0 hrs | 0 days | Wed 6/14/23 | Wed 6/14/23 | 1660 | 1662 |  | Carolyn Hicks
2976 | 1662 | Future Task |  |  | I-WP108 | Carolyn Hicks | Review | WPED - I-WP108 - Training Curriculum - Collaborative Review and Update | 10 hrs | 10 days | Thu 6/15/23 | Wed 6/28/23 | 1661 | 1663 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
2977 | 1663 | Future Task |  |  | I-WP108 | Carolyn Hicks | Approve | WPED - I-WP108 - Training Curriculum - Approve | 0 hrs | 0 days | Wed 6/28/23 | Wed 6/28/23 | 1662 | 1664 |  | Angie Robertson,Jimmy Cox
5689 | 1664 | Future Task |  |  | I-WP108 | Kimberly Kemp | Create | I-WP108 Training Curriculum <Activities per WPED> | 10 hrs | 287 days | Mon 8/21/23 | Tue 10/8/24 | 1663,44 | 1665,1676SS+30 days |  | Kimberly Kemp
2978 | 1665 | Future Task |  |  | I-WP108 | Kimberly Kemp | Submit | I-WP108 Training Curriculum - Submit | 0 hrs | 0 days | Tue 10/8/24 | Tue 10/8/24 | 1664 | 1666 |  | Kimberly Kemp
2979 | 1666 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | I-WP108 Training Curriculum - Dept QC | 1 hr | 1 day | Wed 10/9/24 | Wed 10/9/24 | 1665 | 1667 |  | Tommy Werner
2980 | 1667 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | I-WP108 Training Curriculum - Collaborative Review and Update | 10 hrs | 10 days | Thu 10/10/24 | Wed 10/23/24 | 1666 | 1668 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
2981 | 1668 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | I-WP108 Training Curriculum - Style Guide Review | 2 hrs | 1 day | Thu 10/24/24 | Thu 10/24/24 | 1667 | 1669 |  | Dusti Kincl
2982 | 1669 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | I-WP108 Training Curriculum - Final Review and Update | 10 hrs | 5 days | Fri 10/25/24 | Thu 10/31/24 | 1668 | 1670 |  | Angie Robertson,Jimmy Cox
2983 | 1670 | Future Task |  |  | I-WP108 | Kimberly Kemp | Approve | I-WP108 Training Curriculum - Approve | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 1669 |  |  | Jimmy Cox
2984 | 1671 | Future Task |  |  | I-WP109 | Kimberly Kemp |  | I-WP109 Training Designs | 66 hrs | 315 days | Mon 7/3/23 | Mon 9/30/24
2985 | 1672 | Future Task |  |  | I-WP109 | Carolyn Hicks | Create | WPED - I-WP109 - Training Designs - Create | 10 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 1 | 1673 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila
2986 | 1673 | Future Task |  |  | I-WP109 | Carolyn Hicks | Submit | WPED - I-WP109 - Training Designs - Submit | 0 hrs | 0 days | Mon 7/17/23 | Mon 7/17/23 | 1672 | 1674 |  | Carolyn Hicks
2987 | 1674 | Future Task |  |  | I-WP109 | Carolyn Hicks | Review | WPED - I-WP109 - Training Designs - Collaborative Review and Update | 10 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 1673 | 1675 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
2988 | 1675 | Future Task |  |  | I-WP109 | Carolyn Hicks | Approve | WPED - I-WP109 - Training Designs - Approve | 0 hrs | 0 days | Mon 7/31/23 | Mon 7/31/23 | 1674 | 1676 |  | Angie Robertson,Jimmy Cox
5690 | 1676 | Future Task |  |  | I-WP109 | Kimberly Kemp | Create | I-WP109 Training Designs <Activities per WPED> | 10 hrs | 234 days | Tue 10/3/23 | Thu 9/5/24 | 1675,1664SS+30 days | 1677,1688SS |  | Kimberly Kemp
2989 | 1677 | Future Task |  |  | I-WP109 | Kimberly Kemp | Submit | I-WP109 Training Designs - Submit | 0 hrs | 0 days | Thu 9/5/24 | Thu 9/5/24 | 1676 | 1678 |  | Kimberly Kemp
2990 | 1678 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | I-WP109 Training Designs - Dept QC | 8 hrs | 1 day | Fri 9/6/24 | Fri 9/6/24 | 1677 | 1679 |  | Gabriela Gibson
2991 | 1679 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | I-WP109 Training Designs - Collaborative Review and Update | 10 hrs | 10 days | Mon 9/9/24 | Fri 9/20/24 | 1678 | 1680 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
2992 | 1680 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | I-WP109 Training Designs - Style Guide Review | 8 hrs | 1 day | Mon 9/23/24 | Mon 9/23/24 | 1679 | 1681 |  | Tatiana Eubanks
2993 | 1681 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | I-WP109 Training Designs - Final Review and Update | 10 hrs | 5 days | Tue 9/24/24 | Mon 9/30/24 | 1680 | 1682 |  | Angie Robertson,Jimmy Cox
2994 | 1682 | Future Task |  |  | I-WP109 | Kimberly Kemp | Approve | I-WP109 Training Designs - Approve | 0 hrs | 0 days | Mon 9/30/24 | Mon 9/30/24 | 1681 | 1750 |  | Jimmy Cox
2995 | 1683 | Future Task | Yes |  | I-WP110 | Kimberly Kemp |  | I-WP110 Training Build | 136 hrs | 401 days | Fri 3/1/24 | Tue 9/30/25
2996 | 1684 | Future Task |  |  | I-WP110 | Carolyn Hicks | Create | WPED - I-WP110 - Training Build - Create | 10 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 1 | 1685 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
2997 | 1685 | Future Task |  |  | I-WP110 | Carolyn Hicks | Submit | WPED - I-WP110 - Training Build - Submit | 0 hrs | 0 days | Thu 3/14/24 | Thu 3/14/24 | 1684 | 1686 |  | Carolyn Hicks
2998 | 1686 | Future Task |  |  | I-WP110 | Carolyn Hicks | Review | WPED - I-WP110 - Training Build - Collaborative Review and Update | 10 hrs | 10 days | Fri 3/15/24 | Thu 3/28/24 | 1685 | 1687 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
2999 | 1687 | Future Task |  |  | I-WP110 | Carolyn Hicks | Approve | WPED - I-WP110 - Training Build - Approve | 0 hrs | 0 days | Thu 3/28/24 | Thu 3/28/24 | 1686 | 1688 |  | Angie Robertson,Jimmy Cox
5691 | 1688 | Future Task |  |  | I-WP110 | Kimberly Kemp | Create | I-WP110 Training Build <Activities per WPED> | 80 hrs | 364 days | Fri 3/29/24 | Fri 9/5/25 | 1687,1676SS | 1689 |  | Kimberly Kemp
3000 | 1689 | Future Task |  |  | I-WP110 | Kimberly Kemp | Submit | I-WP110 Training Build - Submit | 0 hrs | 0 days | Fri 9/5/25 | Fri 9/5/25 | 1688 | 1690 |  | Kimberly Kemp
3001 | 1690 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | I-WP110 Training Build - Dept QC | 8 hrs | 1 day | Mon 9/8/25 | Mon 9/8/25 | 1689 | 1691 |  | Gabriela Gibson
3002 | 1691 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | I-WP110 Training Build - Collaborative Review and Update | 10 hrs | 10 days | Tue 9/9/25 | Mon 9/22/25 | 1690 | 1692 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3003 | 1692 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | I-WP110 Training Build - Style Guide Review | 8 hrs | 1 day | Tue 9/23/25 | Tue 9/23/25 | 1691 | 1693 |  | Tatiana Eubanks
3004 | 1693 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | I-WP110 Training Build - Final Review and Update | 10 hrs | 5 days | Wed 9/24/25 | Tue 9/30/25 | 1692 | 1694 |  | Angie Robertson,Jimmy Cox
3005 | 1694 | Future Task |  |  | I-WP110 | Kimberly Kemp | Approve | I-WP110 Training Build - Approve | 0 hrs | 0 days | Tue 9/30/25 | Tue 9/30/25 | 1693 |  |  | Jimmy Cox
3006 | 1695 | Future Task |  |  | I-WP111 | Kimberly Kemp |  | I-WP111 UAT Training Materials | 129 hrs | 154 days | Thu 8/1/24 | Thu 3/13/25
3007 | 1696 | Future Task |  |  | I-WP111 | Carolyn Hicks | Create | WPED - I-WP111 - UAT Training Materials - Create | 10 hrs | 10 days | Thu 8/1/24 | Wed 8/14/24 | 1 | 1697 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila
3008 | 1697 | Future Task |  |  | I-WP111 | Carolyn Hicks | Submit | WPED - I-WP111 - UAT Training Materials - Submit | 0 hrs | 0 days | Wed 8/14/24 | Wed 8/14/24 | 1696 | 1698 |  | Carolyn Hicks
3009 | 1698 | Future Task |  |  | I-WP111 | Carolyn Hicks | Review | WPED - I-WP111 - UAT Training Materials - Collaborative Review and Update | 10 hrs | 10 days | Thu 8/15/24 | Wed 8/28/24 | 1697 | 1699 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
3010 | 1699 | Future Task |  |  | I-WP111 | Carolyn Hicks | Approve | WPED - I-WP111 - UAT Training Materials - Approve | 0 hrs | 0 days | Wed 8/28/24 | Wed 8/28/24 | 1698 | 1700 |  | Angie Robertson,Jimmy Cox
5692 | 1700 | Future Task |  |  | I-WP111 | Kimberly Kemp | Create | I-WP111 UAT Training Materials <Activities per WPED> | 80 hrs | 117 days | Thu 8/29/24 | Tue 2/18/25 | 1699 | 1701 |  | Kimberly Kemp
3011 | 1701 | Future Task |  |  | I-WP111 | Kimberly Kemp | Submit | I-WP111 UAT Training Materials - Submit | 0 hrs | 0 days | Tue 2/18/25 | Tue 2/18/25 | 1700 | 1702 |  | Kimberly Kemp
3012 | 1702 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | I-WP111 UAT Training Materials - Dept QC | 1 hr | 1 day | Wed 2/19/25 | Wed 2/19/25 | 1701 | 1703 |  | Tommy Werner
3013 | 1703 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | I-WP111 UAT Training Materials - Collaborative Review and Update | 10 hrs | 10 days | Thu 2/20/25 | Wed 3/5/25 | 1702 | 1704 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3014 | 1704 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | I-WP111 UAT Training Materials - Style Guide Review | 8 hrs | 1 day | Thu 3/6/25 | Thu 3/6/25 | 1703 | 1705 |  | Tatiana Eubanks
3015 | 1705 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | I-WP111 UAT Training Materials - Final Review and Update | 10 hrs | 5 days | Fri 3/7/25 | Thu 3/13/25 | 1704 | 1706 |  | Angie Robertson,Jimmy Cox
3016 | 1706 | Future Task |  |  | I-WP111 | Kimberly Kemp | Approve | I-WP111 UAT Training Materials - Approve | 0 hrs | 0 days | Thu 3/13/25 | Thu 3/13/25 | 1705 | 1707 |  | Jimmy Cox
3017 | 1707 | Future Task |  |  | I-WP111 | Kimberly Kemp | Milestone | I-WP111 UAT Training Materials Complete | 0 hrs | 0 days | Thu 3/13/25 | Thu 3/13/25 | 1706 | 1250 |  | Kimberly Kemp | Why is this task a Milestone? | Angie
3018 | 1708 | Future Task |  |  | I-WP112 | Kimberly Kemp |  | I-WP112 End User Manual | 143 hrs | 210 days | Fri 1/31/25 | Wed 11/26/25
3019 | 1709 | Future Task |  |  | I-WP112 | Carolyn Hicks | Create | WPED - I-WP112 - End User Manual - Create | 10 hrs | 10 days | Fri 1/31/25 | Thu 2/13/25 | 1 | 1710 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3020 | 1710 | Future Task |  |  | I-WP112 | Carolyn Hicks | Submit | WPED - I-WP112 - End User Manual - Submit | 0 hrs | 0 days | Thu 2/13/25 | Thu 2/13/25 | 1709 | 1711 |  | Carolyn Hicks
3021 | 1711 | Future Task |  |  | I-WP112 | Carolyn Hicks | Review | WPED - I-WP112 - End User Manual - Collaborative Review and Update | 10 hrs | 10 days | Fri 2/14/25 | Thu 2/27/25 | 1710 | 1712 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3022 | 1712 | Future Task |  |  | I-WP112 | Carolyn Hicks | Approve | WPED - I-WP112 - End User Manual - Approve | 0 hrs | 0 days | Thu 2/27/25 | Thu 2/27/25 | 1711 | 1713 |  | Angie Robertson,Jimmy Cox
5693 | 1713 | Future Task |  |  | I-WP112 | Kimberly Kemp | Create | I-WP112 End User Manual <Activities per WPED> | 100 hrs | 173 days | Fri 2/28/25 | Fri 10/31/25 | 1712649 | 1714 |  | Kimberly Kemp
3023 | 1714 | Future Task |  |  | I-WP112 | Kimberly Kemp | Submit | I-WP112 End User Manual - Submit | 0 hrs | 0 days | Fri 10/31/25 | Fri 10/31/25 | 1713 | 1715 |  | Kimberly Kemp
3024 | 1715 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | I-WP112 End User Manual - Dept QC | 1 hr | 1 day | Mon 11/3/25 | Mon 11/3/25 | 1714 | 1716 |  | Tommy Werner
3025 | 1716 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | I-WP112 End User Manual - Collaborative Review and Update | 10 hrs | 10 days | Tue 11/4/25 | Tue 11/18/25 | 1715 | 1717 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3026 | 1717 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | I-WP112 End User Manual - Style Guide Review | 2 hrs | 1 day | Wed 11/19/25 | Wed 11/19/25 | 1716 | 1718 |  | Tatiana Eubanks
3027 | 1718 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | I-WP112 End User Manual - Final Review and Update | 10 hrs | 5 days | Thu 11/20/25 | Wed 11/26/25 | 1717 | 1719 |  | Angie Robertson,Jimmy Cox
3028 | 1719 | Future Task |  |  | I-WP112 | Kimberly Kemp | Approve | I-WP112 End User Manual - Approve | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 1718 | 1720 |  | Jimmy Cox
3029 | 1720 | Future Task |  |  | I-WP112 | Kimberly Kemp | Milestone | I-WP112 End User Manual Complete | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 1719 |  |  | Kimberly Kemp | Why is this task a Milestone? | Angie
3030 | 1721 | Future Task |  |  | I-WP113 | Kimberly Kemp |  | I-WP113 ILT Training Delivery Plan | 156 hrs | 85 days | Thu 5/1/25 | Fri 8/29/25
3031 | 1722 | Future Task |  |  | I-WP113 | Carolyn Hicks | Create | WPED - I-WP113 - ILT Training Delivery Plan - Create | 10 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 1 | 1723 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
3032 | 1723 | Future Task |  |  | I-WP113 | Carolyn Hicks | Submit | WPED - I-WP113 - ILT Training Delivery Plan - Submit | 0 hrs | 0 days | Wed 5/14/25 | Wed 5/14/25 | 1722 | 1724 |  | Carolyn Hicks
3033 | 1724 | Future Task |  |  | I-WP113 | Carolyn Hicks | Review | WPED - I-WP113 - ILT Training Delivery Plan - Collaborative Review and Update | 10 hrs | 10 days | Thu 5/15/25 | Thu 5/29/25 | 1723 | 1725 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
3034 | 1725 | Future Task |  |  | I-WP113 | Carolyn Hicks | Approve | WPED - I-WP113- ILT Training Delivery Plan - Approve | 0 hrs | 0 days | Thu 5/29/25 | Thu 5/29/25 | 1724 | 1726 |  | Angie Robertson,Jimmy Cox
5694 | 1726 | Future Task |  |  | I-WP113 | Kimberly Kemp | Create | I-WP113 ILT Training Delivery Plan <Activities per WPED> | 100 hrs | 48 days | Fri 5/30/25 | Wed 8/6/25 | 1725 | 1727 |  | Kimberly Kemp
3035 | 1727 | Future Task |  |  | I-WP113 | Kimberly Kemp | Submit | I-WP113 ILT Training Delivery Plan - Submit | 0 hrs | 0 days | Wed 8/6/25 | Wed 8/6/25 | 1726 | 1728 |  | Kimberly Kemp
3036 | 1728 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | I-WP113 ILT Training Delivery Plan - Dept QC | 8 hrs | 1 day | Thu 8/7/25 | Thu 8/7/25 | 1727 | 1729 |  | Gabriela Gibson
3037 | 1729 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | I-WP113 ILT Training Delivery Plan - Collaborative Review and Update | 10 hrs | 10 days | Fri 8/8/25 | Thu 8/21/25 | 1728 | 1730 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3038 | 1730 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | I-WP113 ILT Training Delivery Plan - Style Guide Review | 8 hrs | 1 day | Fri 8/22/25 | Fri 8/22/25 | 1729 | 1731 |  | Tatiana Eubanks
3039 | 1731 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | I-WP113 ILT Training Delivery Plan - Final Review and Update | 10 hrs | 5 days | Mon 8/25/25 | Fri 8/29/25 | 1730 | 1732 |  | Angie Robertson,Jimmy Cox
3040 | 1732 | Future Task |  |  | I-WP113 | Kimberly Kemp | Approve | I-WP113 ILT Training Delivery Plan - Approve | 0 hrs | 0 days | Fri 8/29/25 | Fri 8/29/25 | 1731 |  |  | Jimmy Cox
3041 | 1733 | Future Task |  |  | I-WP114 | Kimberly Kemp |  | I-WP114 Training Measurement Report | 143 hrs | 104 days | Wed 10/29/25 | Tue 3/31/26
3042 | 1734 | Future Task |  |  | I-WP114 | Carolyn Hicks | Create | WPED - I-WP114 - Training Measurement Report - Create | 10 hrs | 10 days | Wed 10/29/25 | Wed 11/12/25 | 1 | 1735 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
3043 | 1735 | Future Task |  |  | I-WP114 | Kimberly Kemp | Submit | WPED - I-WP114 - Training Measurement Report - Submit | 0 hrs | 0 days | Wed 11/12/25 | Wed 11/12/25 | 1734 | 1736 |  | Carolyn Hicks
3044 | 1736 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WPED - I-WP114 - Training Measurement Report - Collaborative Review and Update | 10 hrs | 10 days | Thu 11/13/25 | Wed 11/26/25 | 1735 | 1737 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
3045 | 1737 | Future Task |  |  | I-WP114 | Kimberly Kemp | Approve | WPED - I-WP114 - Training Measurement Report - Approve | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 1736 | 1738 |  | Angie Robertson,Jimmy Cox
5695 | 1738 | Future Task |  |  | I-WP114 | Kimberly Kemp | Create | I-WP114 Training Measurement Report <Activities per WPED> | 100 hrs | 67 days | Mon 12/1/25 | Fri 3/6/26 | 17371250 | 1739 |  | Kimberly Kemp
3046 | 1739 | Future Task |  |  | I-WP114 | Kimberly Kemp | Submit | I-WP114 Training Measurement Report - Submit | 0 hrs | 0 days | Fri 3/6/26 | Fri 3/6/26 | 1738 | 1740 |  | Kimberly Kemp
3047 | 1740 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | I-WP114 Training Measurement Report - Dept QC | 1 hr | 1 day | Mon 3/9/26 | Mon 3/9/26 | 1739 | 1741 |  | Tommy Werner
3048 | 1741 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | I-WP114 Training Measurement Report - Collaborative Review and Update | 10 hrs | 10 days | Tue 3/10/26 | Mon 3/23/26 | 1740 | 1742 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3049 | 1742 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | I-WP114 Training Measurement Report - Style Guide Review | 2 hrs | 1 day | Tue 3/24/26 | Tue 3/24/26 | 1741 | 1743 |  | Dusti Kincl
3050 | 1743 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | I-WP114 Training Measurement Report - Final Review and Update | 10 hrs | 5 days | Wed 3/25/26 | Tue 3/31/26 | 1742 | 1744 |  | Angie Robertson,Jimmy Cox
3051 | 1744 | Future Task |  |  | I-WP114 | Kimberly Kemp | Approve | Training Measurement Report - Approve | 0 hrs | 0 days | Tue 3/31/26 | Tue 3/31/26 | 1743 |  |  | Jimmy Cox
3052 | 1745 | Future Task |  |  | I-WP115 | Kimberly Kemp |  | I-WP115 Train the Trainer | 156 hrs | 372 days | Fri 8/1/25 | Tue 1/26/27
3053 | 1746 | Future Task |  |  | I-WP115 | Carolyn Hicks | Create | WPED - I-WP115 - Train the Trainer - Create | 10 hrs | 10 days | Fri 8/1/25 | Thu 8/14/25 | 1 | 1747 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila
3054 | 1747 | Future Task |  |  | I-WP115 | Carolyn Hicks | Submit | WPED - I-WP115 - Train the Trainer - Submit | 0 hrs | 0 days | Thu 8/14/25 | Thu 8/14/25 | 1746 | 1748 |  | Carolyn Hicks
3055 | 1748 | Future Task |  |  | I-WP115 | Carolyn Hicks | Review | WPED - I-WP115 - Train the Trainer - Collaborative Review and Update | 10 hrs | 10 days | Fri 8/15/25 | Thu 8/28/25 | 1747 | 1749 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
3056 | 1749 | Future Task |  |  | I-WP115 | Carolyn Hicks | Approve | WPED - I-WP115 - Train the Trainer - Approve | 0 hrs | 0 days | Thu 8/28/25 | Thu 8/28/25 | 1748 | 1750 |  | Angie Robertson,Jimmy Cox
5696 | 1750 | Future Task |  |  | I-WP115 | Kimberly Kemp | Create | I-WP115 Train the Trainer <Activities per WPED> | 100 hrs | 324 days | Fri 8/29/25 | Mon 12/14/26 | 17491682 | 1751FS+11 days |  | Kimberly Kemp
3057 | 1751 | Future Task |  |  | I-WP115 | Kimberly Kemp | Submit | I-WP115 Train the Trainer - Submit | 0 hrs | 0 days | Wed 12/30/26 | Wed 12/30/26 | 1750FS+11 days | 1752 |  | Kimberly Kemp
3058 | 1752 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | I-WP115 Train the Trainer - Dept QC | 8 hrs | 1 day | Thu 12/31/26 | Thu 12/31/26 | 1751 | 1753 |  | Gabriela Gibson
3059 | 1753 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | I-WP115 Train the Trainer - Collaborative Review and Update | 10 hrs | 10 days | Mon 1/4/27 | Fri 1/15/27 | 1752 | 1754 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3060 | 1754 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | I-WP115 Train the Trainer - Style Guide Review | 8 hrs | 1 day | Tue 1/19/27 | Tue 1/19/27 | 1753 | 1755 |  | Tatiana Eubanks
3061 | 1755 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | I-WP115 Train the Trainer - Final Review and Update | 10 hrs | 5 days | Wed 1/20/27 | Tue 1/26/27 | 1754 | 1756 |  | Angie Robertson,Jimmy Cox
3062 | 1756 | Future Task |  |  | I-WP115 | Kimberly Kemp | Approve | I-WP115 Train the Trainer - Approve | 0 hrs | 0 days | Tue 1/26/27 | Tue 1/26/27 | 1755 | 1757 |  | Jimmy Cox
3063 | 1757 | Future Task |  |  | I-WP115 | Kimberly Kemp | Milestone | Train the Trainer Complete | 0 hrs | 0 days | Tue 1/26/27 | Tue 1/26/27 | 1756 |  |  | Kimberly Kemp | Why is this task a Milestone? | Angie
3064 | 1758 | Future Task |  |  | I-WP122 | Carolyn Hicks |  | I-WP122 - Update D33 Training Strategy | 143 hrs | 81 days | Wed 11/1/23 | Thu 2/29/24
3065 | 1759 | Future Task |  |  | I-WP122 | Carolyn Hicks | Create | WPED - I-WP122 - Update D33 Training Strategy - Create | 10 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23 | 1 | 1760 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3066 | 1760 | Future Task |  |  | I-WP122 | Carolyn Hicks | Submit | WPED - I-WP122 - Update D33 Training Strategy - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 1759 | 1761 |  | Carolyn Hicks
3067 | 1761 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WPED - I-WP122 - Update D33 Training Strategy - Collaborative Review and Update | 10 hrs | 10 days | Thu 11/16/23 | Fri 12/1/23 | 1760 | 1762 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3068 | 1762 | Future Task |  |  | I-WP122 | Carolyn Hicks | Approve | WPED - I-WP122 - Update D33 Training Strategy - Approve | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 1761 | 1763 |  | Angie Robertson,Jimmy Cox
5697 | 1763 | Future Task |  |  | I-WP122 | Carolyn Hicks | Create | I-WP122 Update D33 Training Strategy <Activities per WPED> | 100 hrs | 44 days | Mon 12/4/23 | Tue 2/6/24 | 1762 | 1764 |  | Kimberly Kemp
3069 | 1764 | Future Task |  |  | I-WP122 | Carolyn Hicks | Submit | I-WP122 Update D33 Training Strategy - Submit | 0 hrs | 0 days | Tue 2/6/24 | Tue 2/6/24 | 1763 | 1765 |  | Kimberly Kemp
3070 | 1765 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | I-WP122 Update D33 Training Strategy - Dept QC | 1 hr | 1 day | Wed 2/7/24 | Wed 2/7/24 | 1764 | 1766 |  | Tommy Werner
3071 | 1766 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | I-WP122Update D33 Training Strategy - Collaborative Review and Update | 10 hrs | 10 days | Thu 2/8/24 | Wed 2/21/24 | 1765 | 1767 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3072 | 1767 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | I-WP122 Update D33 Training Strategy - Style Guide Review | 2 hrs | 1 day | Thu 2/22/24 | Thu 2/22/24 | 1766 | 1768 |  | Dusti Kincl
3073 | 1768 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | I-WP122 Update D33 Training Strategy - Final Review and Update | 10 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1767 | 1769 |  | Angie Robertson,Jimmy Cox
3074 | 1769 | Future Task |  |  | I-WP122 | Carolyn Hicks | Approve | I-WP122 Update D33 Training Strategy - Approve | 0 hrs | 0 days | Thu 2/29/24 | Thu 2/29/24 | 1768 |  |  | Jimmy Cox
3075 | 1770 | Future Task |  |  | I-WP123 | Carolyn Hicks |  | I-WP123 - Update D112 Training Deployment and Measurement Plan | 149 hrs | 81 days | Wed 11/1/23 | Thu 2/29/24
3076 | 1771 | Future Task |  |  | I-WP123 | Carolyn Hicks | Create | WPED - I-WP123 - Update D112 Training Deployment and Measurement Plan - Create | 10 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23 | 1 | 1772 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3077 | 1772 | Future Task |  |  | I-WP123 | Carolyn Hicks | Submit | WPED - I-WP123 - Update D112 Training Deployment and Measurement Plan - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 1771 | 1773 |  | Carolyn Hicks
3078 | 1773 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WPED - I-WP123 - Update D112 Training Deployment and Measurement Plan - Collaborative Review and Update | 10 hrs | 10 days | Thu 11/16/23 | Fri 12/1/23 | 1772 | 1774 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3079 | 1774 | Future Task |  |  | I-WP123 | Carolyn Hicks | Approve | WPED - I-WP123 - Update D112 Training Deployment and Measurement Plan - Approve | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 1773 | 1775 |  | Angie Robertson,Jimmy Cox
5698 | 1775 | Future Task |  |  | I-WP123 | Carolyn Hicks | Create | I-WP123 Update D112 Training Deployment and Measurement Plan <Activities per WPED> | 100 hrs | 44 days | Mon 12/4/23 | Tue 2/6/24 | 1774 | 1776 |  | Kimberly Kemp
3080 | 1776 | Future Task |  |  | I-WP123 | Carolyn Hicks | Submit | I-WP123 Update D112 Training Deployment and Measurement Plan - Submit | 0 hrs | 0 days | Tue 2/6/24 | Tue 2/6/24 | 1775 | 1777 |  | Kimberly Kemp
3081 | 1777 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | I-WP123 Update D112 Training Deployment and Measurement Plan - Dept QC | 1 hr | 1 day | Wed 2/7/24 | Wed 2/7/24 | 1776 | 1778 |  | Tommy Werner
3082 | 1778 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | I-WP123Update D112 Training Deployment and Measurement Plan - Collaborative Review and Update | 10 hrs | 10 days | Thu 2/8/24 | Wed 2/21/24 | 1777 | 1779 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3083 | 1779 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | I-WP123 Update D112 Training Deployment and Measurement Plan - Style Guide Review | 8 hrs | 1 day | Thu 2/22/24 | Thu 2/22/24 | 1778 | 1780 |  | Tatiana Eubanks
3084 | 1780 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | I-WP123 Update D112 Training Deployment and Measurement Plan - Final Review and Update | 10 hrs | 5 days | Fri 2/23/24 | Thu 2/29/24 | 1779 | 1781 |  | Angie Robertson,Jimmy Cox
3085 | 1781 | Future Task |  |  | I-WP123 | Carolyn Hicks | Approve | I-WP123 Update D112 Training Deployment and Measurement Plan - Approve | 0 hrs | 0 days | Thu 2/29/24 | Thu 2/29/24 | 1780 |  |  | Jimmy Cox
6812 | 1782 | Future Task | [5 empty] | Training | 1 hr | 104 days | Tue 7/1/25 | Wed 11/26/25
6813 | 1783 | Future Task |  |  |  | Carolyn Hicks |  | Conduct Training | 1 hr | 104 days | Tue 7/1/25 | Wed 11/26/25 | 1 |  | July - Nov 2025 | Carolyn Hicks
3086 | 1784 | Late | [5 empty] | Readiness | 876 hrs | 730 days | Mon 5/8/23 | Tue 3/31/26
7159 | 1785 | Future Task | Yes |  | SG4 | Jimmy Cox | Milestone | Stage Gate 4: Agency Readiness | 0 hrs | 0 days | Mon 11/3/25 | Mon 11/3/25 | 1 |  | November 2025 - ESC | Jimmy Cox,Angie Robertson,Matt Cole | The Resource Names include the ESC and we need tasks / dates for ESC review prior to milestone date. | Angie
3087 | 1786 | Future Task |  |  | I-WP116 | Kimberly Kemp |  | I-WP116 User Support Sessions | 156 hrs | 209 days | Mon 6/2/25 | Tue 3/31/26
3088 | 1787 | Future Task |  |  | I-WP116 | Carolyn Hicks | Create | WPED - I-WP116 - User Support Sessions - Create | 10 hrs | 10 days | Mon 6/2/25 | Fri 6/13/25 | 1 | 1788 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3089 | 1788 | Future Task |  |  | I-WP116 | Carolyn Hicks | Submit | WPED - I-WP116 - User Support Sessions - Submit | 0 hrs | 0 days | Fri 6/13/25 | Fri 6/13/25 | 1787 | 1789 |  | Carolyn Hicks
3090 | 1789 | Future Task |  |  | I-WP116 | Carolyn Hicks | Review | WPED - I-WP116 - User Support Sessions - Collaborative Review and Update | 10 hrs | 10 days | Mon 6/16/25 | Fri 6/27/25 | 1788 | 1790 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3091 | 1790 | Future Task |  |  | I-WP116 | Carolyn Hicks | Approve | WPED - I-WP116 - User Support Sessions - Approve | 0 hrs | 0 days | Fri 6/27/25 | Fri 6/27/25 | 1789 | 1791 |  | Angie Robertson,Jimmy Cox
5699 | 1791 | Future Task |  |  | I-WP116 | Kimberly Kemp | Create | I-WP116 User Support Sessions <Activities per WPED> | 100 hrs | 172 days | Mon 6/30/25 | Fri 3/6/26 | 1790,1250SS+30 days | 1792 |  | Kimberly Kemp
3092 | 1792 | Future Task |  |  | I-WP116 | Kimberly Kemp | Submit | I-WP116 User Support Sessions - Submit | 0 hrs | 0 days | Fri 3/6/26 | Fri 3/6/26 | 1791 | 1793 |  | Kimberly Kemp
3093 | 1793 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | I-WP116 User Support Sessions - Dept QC | 8 hrs | 1 day | Mon 3/9/26 | Mon 3/9/26 | 1792 | 1794 |  | Gabriela Gibson
3094 | 1794 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | I-WP116 User Support Sessions - Collaborative Review and Update | 10 hrs | 10 days | Tue 3/10/26 | Mon 3/23/26 | 1793 | 1795 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3095 | 1795 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | I-WP116 User Support Sessions - Style Guide Review | 8 hrs | 1 day | Tue 3/24/26 | Tue 3/24/26 | 1794 | 1796 |  | Tatiana Eubanks
3096 | 1796 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | I-WP116User Support Sessions - Final Review and Update | 10 hrs | 5 days | Wed 3/25/26 | Tue 3/31/26 | 1795 | 1797 |  | Angie Robertson,Jimmy Cox
3097 | 1797 | Future Task |  |  | I-WP116 | Kimberly Kemp | Approve | I-WP116 User Support Sessions - Approve | 0 hrs | 0 days | Tue 3/31/26 | Tue 3/31/26 | 1796 |  |  | Jimmy Cox
3098 | 1798 | Future Task |  |  | I-WP117 | Nikki Klein |  | I-WP117 Role Mapping Handbook | 149 hrs | 193 days | Thu 2/1/24 | Thu 10/31/24
3099 | 1799 | Future Task |  |  | I-WP117 | Carolyn Hicks | Create | WPED - I-WP117- Role Mapping Handbook - Create | 10 hrs | 10 days | Thu 2/1/24 | Wed 2/14/24 | 1 | 1800 |  | Carolyn Hicks,Nikki Klein,Felicia Hall
3100 | 1800 | Future Task |  |  | I-WP117 | Carolyn Hicks | Submit | WPED - I-WP117 - Role Mapping Handbook - Submit | 0 hrs | 0 days | Wed 2/14/24 | Wed 2/14/24 | 1799 | 1801 |  | Carolyn Hicks
3101 | 1801 | Future Task |  |  | I-WP117 | Carolyn Hicks | Review | WPED - I-WP117 - Role Mapping Handbook - Collaborative Review and Update | 10 hrs | 10 days | Thu 2/15/24 | Wed 2/28/24 | 1800 | 1802 |  | Carolyn Hicks,Nikki Klein,Felicia Hall,Angie Robertson
3102 | 1802 | Future Task |  |  | I-WP117 | Carolyn Hicks | Approve | WPED - I-WP117 - Role Mapping Handbook - Approve | 0 hrs | 0 days | Wed 2/28/24 | Wed 2/28/24 | 1801 | 1803 |  | Angie Robertson,Jimmy Cox
5700 | 1803 | Future Task |  |  | I-WP117 | Nikki Klein | Create | I-WP117 Role Mapping Handbook <Activities per WPED> | 100 hrs | 156 days | Thu 2/29/24 | Tue 10/8/24 | 1802105 | 1804,1815SS+40 days |  | Nikki Klein
3103 | 1804 | Future Task |  |  | I-WP117 | Nikki Klein | Submit | I-WP117 Role Mapping Handbook - Submit | 0 hrs | 0 days | Tue 10/8/24 | Tue 10/8/24 | 1803 | 1805 |  | Nikki Klein
3104 | 1805 | Future Task |  |  | I-WP117 | Nikki Klein | Review | I-WP117 Role Mapping Handbook - Dept QC | 1 hr | 1 day | Wed 10/9/24 | Wed 10/9/24 | 1804 | 1806 |  | Gabriela Gibson
3105 | 1806 | Future Task |  |  | I-WP117 | Nikki Klein | Review | I-WP117 Role Mapping Handbook - Collaborative Review and Update | 10 hrs | 10 days | Thu 10/10/24 | Wed 10/23/24 | 1805 | 1807 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3106 | 1807 | Future Task |  |  | I-WP117 | Nikki Klein | Review | I-WP117 Role Mapping Handbook - Style Guide Review | 8 hrs | 1 day | Thu 10/24/24 | Thu 10/24/24 | 1806 | 1808 |  | Tatiana Eubanks
3107 | 1808 | Future Task |  |  | I-WP117 | Nikki Klein | Review | I-WP117 Role Mapping Handbook - Final Review and Update | 10 hrs | 5 days | Fri 10/25/24 | Thu 10/31/24 | 1807 | 1809 |  | Angie Robertson,Jimmy Cox
3108 | 1809 | Future Task |  |  | I-WP117 | Nikki Klein | Approve | I-WP117 Role Mapping Handbook - Approve | 0 hrs | 0 days | Thu 10/31/24 | Thu 10/31/24 | 1808 |  |  | Jimmy Cox
3109 | 1810 | Future Task | Yes |  | I-WP118 | Nikki Klein |  | I-WP118 Role Mapping Worksheet | 156 hrs | 193 days | Mon 6/3/24 | Mon 3/10/25
3110 | 1811 | Future Task |  |  | I-WP118 | Carolyn Hicks | Create | WPED - I-WP118 - Role Mapping Worksheet - Create | 10 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 1 | 1812 |  | Carolyn Hicks,Nikki Klein,Felicia Hall
3111 | 1812 | Future Task |  |  | I-WP118 | Carolyn Hicks | Submit | WPED - I-WP118 - Role Mapping Worksheet - Submit | 0 hrs | 0 days | Fri 6/14/24 | Fri 6/14/24 | 1811 | 1813 |  | Carolyn Hicks
3112 | 1813 | Future Task |  |  | I-WP118 | Carolyn Hicks | Review | WPED - I-WP118 - Role Mapping Worksheet - Collaborative Review and Update | 10 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 1812 | 1814 |  | Carolyn Hicks,Nikki Klein,Felicia Hall,Angie Robertson
3113 | 1814 | Future Task |  |  | I-WP118 | Carolyn Hicks | Approve | WPED - I-WP118 - Role Mapping Worksheet - Approve | 0 hrs | 0 days | Fri 6/28/24 | Fri 6/28/24 | 1813 | 1815 |  | Angie Robertson,Jimmy Cox
5701 | 1815 | Future Task |  |  | I-WP118 | Nikki Klein | Create | I-WP118 Role Mapping Worksheet <Activities per WPED> | 100 hrs | 125 days | Wed 8/14/24 | Thu 2/13/25 | 1814,1803SS+40 days,1863SS+40 days,579 | 1816 |  | Nikki Klein
3114 | 1816 | Future Task |  |  | I-WP118 | Nikki Klein | Submit | I-WP118 Role Mapping Worksheet - Submit | 0 hrs | 0 days | Thu 2/13/25 | Thu 2/13/25 | 1815 | 1817 |  | Nikki Klein
3115 | 1817 | Future Task |  |  | I-WP118 | Nikki Klein | Review | I-WP118 Role Mapping Worksheet - Dept QC | 8 hrs | 1 day | Fri 2/14/25 | Fri 2/14/25 | 1816 | 1818 |  | Gabriela Gibson
3116 | 1818 | Future Task |  |  | I-WP118 | Nikki Klein | Review | I-WP118 Role Mapping Worksheet - Collaborative Review and Update | 10 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 1817 | 1819 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3117 | 1819 | Future Task |  |  | I-WP118 | Nikki Klein | Review | I-WP118 Role Mapping Worksheet - Style Guide Review | 8 hrs | 1 day | Mon 3/3/25 | Mon 3/3/25 | 1818 | 1820 |  | Tatiana Eubanks
3118 | 1820 | Future Task |  |  | I-WP118 | Nikki Klein | Review | I-WP118 Role Mapping Worksheet - Final Review and Update | 10 hrs | 5 days | Tue 3/4/25 | Mon 3/10/25 | 1819 | 1821 |  | Angie Robertson,Jimmy Cox
3119 | 1821 | Future Task |  |  | I-WP118 | Nikki Klein | Approve | I-WP118 Role Mapping Worksheet - Approve | 0 hrs | 0 days | Mon 3/10/25 | Mon 3/10/25 | 1820 | 568 |  | Jimmy Cox
3120 | 1822 | Future Task |  |  | I-WP119 | Nikki Klein |  | I-WP119 Change Impact Analysis | 66 hrs | 188 days | Wed 11/1/23 | Wed 7/31/24
3121 | 1823 | Future Task |  |  | I-WP119 | Carolyn Hicks | Create | WPED - I-WP119 - Change Impact Analysis - Create | 10 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23 | 1 | 1824 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas
3122 | 1824 | Future Task |  |  | I-WP119 | Carolyn Hicks | Submit | WPED - I-WP119 - Change Impact Analysis - Submit | 0 hrs | 0 days | Wed 11/15/23 | Wed 11/15/23 | 1823 | 1825 |  | Carolyn Hicks
3123 | 1825 | Future Task |  |  | I-WP119 | Carolyn Hicks | Review | WPED - I-WP119 - Change Impact Analysis - Collaborative Review and Update | 10 hrs | 10 days | Thu 11/16/23 | Fri 12/1/23 | 1824 | 1826 |  | Carolyn Hicks,Nikki Klein,Kim York,Angie Robertson,Dora Thomas
3124 | 1826 | Future Task |  |  | I-WP119 | Carolyn Hicks | Approve | WPED - I-WP119 - Change Impact Analysis | 0 hrs | 0 days | Fri 12/1/23 | Fri 12/1/23 | 1825 | 1827 |  | Angie Robertson,Jimmy Cox
6814 | 1827 | Future Task |  |  | I-WP119 | Nikki Klein | Submit | I-WP119 Change Impact Analysis <Activities per WPED> | 10 hrs | 151 days | Mon 12/4/23 | Mon 7/8/24 | 1826 | 1828 |  | Nikki Klein
3125 | 1828 | Future Task |  |  | I-WP119 | Nikki Klein | Submit | I-WP119 Change Impact Analysis - Submit | 0 hrs | 0 days | Mon 7/8/24 | Mon 7/8/24 | 1827 | 1829 |  | Nikki Klein
3126 | 1829 | Future Task |  |  | I-WP119 | Nikki Klein | Review | I-WP119 Change Impact Analysis - Dept QC | 8 hrs | 1 day | Tue 7/9/24 | Tue 7/9/24 | 1828 | 1830 |  | Gabriela Gibson
3127 | 1830 | Future Task |  |  | I-WP119 | Nikki Klein | Review | I-WP119 Change Impact Analysis - Collaborative Review and Update | 10 hrs | 10 days | Wed 7/10/24 | Tue 7/23/24 | 1829 | 1831 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3128 | 1831 | Future Task |  |  | I-WP119 | Nikki Klein | Review | I-WP119 Change Impact Analysis - Style Guide Review | 8 hrs | 1 day | Wed 7/24/24 | Wed 7/24/24 | 1830 | 1832 |  | Tatiana Eubanks
3129 | 1832 | Future Task |  |  | I-WP119 | Nikki Klein | Review | I-WP119 Change Impact Analysis - Final Review and Update | 10 hrs | 5 days | Thu 7/25/24 | Wed 7/31/24 | 1831 | 1833 |  | Angie Robertson,Jimmy Cox
3130 | 1833 | Future Task |  |  | I-WP119 | Nikki Klein | Approve | I-WP119 Change Impact Analysis - Approve | 0 hrs | 0 days | Wed 7/31/24 | Wed 7/31/24 | 1832 |  |  | Jimmy Cox
3131 | 1834 | Future Task |  |  | I-WP121 | Carolyn Hicks |  | I-WP121 Updated D27 Readiness Plan | 143 hrs | 82 days | Mon 10/2/23 | Wed 1/31/24
3132 | 1835 | Future Task |  |  | I-WP121 | Carolyn Hicks | Create | WPED - I-WP121 - Update D27 Readiness Plan - Create | 10 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 1 | 1836 |  | Carolyn Hicks,Nikki Klein
3133 | 1836 | Future Task |  |  | I-WP121 | Carolyn Hicks | Submit | WPED - I-WP121 - Update D27 Readiness Plan - Submit | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 1835 | 1837 |  | Carolyn Hicks
3134 | 1837 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WPED - I-WP121 - Update D27 Readiness Plan - Collaborative Review and Update | 10 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 1836 | 1838 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas,Angie Robertson
3135 | 1838 | Future Task |  |  | I-WP121 | Carolyn Hicks | Approve | WPED - I-WP121 - Update D27 Readiness Plan - Approve | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 1837 | 1839 |  | Angie Robertson,Jimmy Cox
5702 | 1839 | Future Task |  |  | I-WP121 | Carolyn Hicks | Create | I-WP121 Update D27 Readiness Plan <Activities per WPED> | 100 hrs | 45 days | Mon 10/30/23 | Fri 1/5/24 | 1838 | 1840 |  | Nikki Klein
3136 | 1840 | Future Task |  |  | I-WP121 | Carolyn Hicks | Submit | I-WP121 Update D27 Readiness Plan - Submit | 0 hrs | 0 days | Fri 1/5/24 | Fri 1/5/24 | 1839 | 1841 |  | Nikki Klein
3137 | 1841 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | I-WP121 Update D27 Readiness Plan - Dept QC | 1 hr | 1 day | Mon 1/8/24 | Mon 1/8/24 | 1840 | 1842 |  | Gabriela Gibson
3138 | 1842 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | I-WP121Update D27 Readiness Plan - Collaborative Review and Update | 10 hrs | 10 days | Tue 1/9/24 | Tue 1/23/24 | 1841 | 1843 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3139 | 1843 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | I-WP121 Update D27 Readiness Plan - Style Guide Review | 2 hrs | 1 day | Wed 1/24/24 | Wed 1/24/24 | 1842 | 1844 |  | Dusti Kincl
3140 | 1844 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | I-WP121 Update D27 Readiness Plan - Final Review and Update | 10 hrs | 5 days | Thu 1/25/24 | Wed 1/31/24 | 1843 | 1845 |  | Angie Robertson,Jimmy Cox
3141 | 1845 | Future Task |  |  | I-WP121 | Carolyn Hicks | Approve | I-WP121 Update D27 Readiness Plan - Approve | 0 hrs | 0 days | Wed 1/31/24 | Wed 1/31/24 | 1844 |  |  | Jimmy Cox
3142 | 1846 | Future Task |  |  | I-WP124 | Carolyn Hicks |  | I-WP124 Update D62 Workforce Transition Plan | 149 hrs | 82 days | Mon 10/2/23 | Wed 1/31/24
3143 | 1847 | Future Task |  |  | I-WP124 | Carolyn Hicks | Create | WPED - I-WP124 - Update D62 Workforce Transition Plan - Create | 10 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 1 | 1848 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas
3144 | 1848 | Future Task |  |  | I-WP124 | Carolyn Hicks | Submit | WPED - I-WP124 - Update D62 Workforce Transition Plan - Submit | 0 hrs | 0 days | Fri 10/13/23 | Fri 10/13/23 | 1847 | 1849 |  | Carolyn Hicks
3145 | 1849 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WPED - I-WP124 - Update D62 Workforce Transition Plan - Collaborative Review and Update | 10 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 1848 | 1850 |  | Carolyn Hicks,Nikki Klein,Kim York,Angie Robertson,Dora Thomas
3146 | 1850 | Future Task |  |  | I-WP124 | Carolyn Hicks | Approve | WPED - I-WP124 - Update D62 Workforce Transition Plan - Approve | 0 hrs | 0 days | Fri 10/27/23 | Fri 10/27/23 | 1849 | 1851 |  | Angie Robertson,Jimmy Cox
5703 | 1851 | Future Task |  |  | I-WP124 | Carolyn Hicks | Create | I-WP124 Update D62 Workforce Transition Plan <Activities per WPED> | 100 hrs | 45 days | Mon 10/30/23 | Fri 1/5/24 | 1850 | 1852 |  | Nikki Klein
3147 | 1852 | Future Task |  |  | I-WP124 | Carolyn Hicks | Submit | I-WP124 Update D62 Workforce Transition Plan - Submit | 0 hrs | 0 days | Fri 1/5/24 | Fri 1/5/24 | 1851 | 1853 |  | Nikki Klein
3148 | 1853 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | I-WP124 Update D62 Workforce Transition Plan - Dept QC | 1 hr | 1 day | Mon 1/8/24 | Mon 1/8/24 | 1852 | 1854 |  | Gabriela Gibson
3149 | 1854 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | I-WP124Update D62 Workforce Transition Plan - Collaborative Review and Update | 10 hrs | 10 days | Tue 1/9/24 | Tue 1/23/24 | 1853 | 1855 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3150 | 1855 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | I-WP124 Update D62 Workforce Transition Plan - Style Guide Review | 8 hrs | 1 day | Wed 1/24/24 | Wed 1/24/24 | 1854 | 1856 |  | Tatiana Eubanks
3151 | 1856 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | I-WP124 Update D62 Workforce Transition Plan - Final Review and Update | 10 hrs | 5 days | Thu 1/25/24 | Wed 1/31/24 | 1855 | 1857 |  | Angie Robertson,Jimmy Cox
3152 | 1857 | Future Task |  |  | I-WP124 | Carolyn Hicks | Approve | I-WP124 Update D62 Workforce Transition Plan - Approve | 0 hrs | 0 days | Wed 1/31/24 | Wed 1/31/24 | 1856 |  |  | Jimmy Cox
6777 | 1858 | Late | Yes |  | I-WP126 | Nikki Klein |  | I-WP126 Readiness Workplan | 57 hrs | 62 days | Mon 5/8/23 | Thu 8/3/23
6778 | 1859 | Late |  |  | I-WP126 | Carolyn Hicks | Create | WPED - I-WP126 - Readiness Workplan - Create | 10 hrs | 10 days | Mon 5/8/23 | Fri 5/19/23 | 1 | 1860 |  | Carolyn Hicks,Nikki Klein,Jordan Nobles
6779 | 1860 | Late |  |  | I-WP126 | Carolyn Hicks | Submit | WPED - I-WP126 - Readiness Workplan - Submit | 0 hrs | 0 days | Fri 5/19/23 | Fri 5/19/23 | 1859 | 1861 |  | Carolyn Hicks
6780 | 1861 | Late |  |  | I-WP126 | Carolyn Hicks | Review | WPED - I-WP126 - Readiness Workplan - Collaborative Review and Update | 10 hrs | 10 days | Mon 5/22/23 | Mon 6/5/23 | 1860 | 1862 |  | Carolyn Hicks,Nikki Klein,Jordan Nobles,Angie Robertson
6781 | 1862 | Future Task |  |  | I-WP126 | Carolyn Hicks | Approve | WPED - I-WP126 - Readiness Workplan - Approve | 0 hrs | 0 days | Mon 6/5/23 | Mon 6/5/23 | 1861 | 1863 |  | Angie Robertson,Jimmy Cox
6782 | 1863 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 Readiness Workplan <Activities per WPED> | 10 hrs | 25 days | Tue 6/6/23 | Tue 7/11/23 | 1862 | 1864,1815SS+40 days |  | Nikki Klein
6783 | 1864 | Future Task |  |  | I-WP126 | Nikki Klein | Submit | I-WP126 Readiness Workplan - Submit | 0 hrs | 0 days | Tue 7/11/23 | Tue 7/11/23 | 1863 | 1865 |  | Nikki Klein
6784 | 1865 | Future Task |  |  | I-WP126 | Nikki Klein | Review | I-WP126 Readiness Workplan - Dept QC | 1 hr | 1 day | Wed 7/12/23 | Wed 7/12/23 | 1864 | 1866 |  | Gabriela Gibson
6785 | 1866 | Future Task |  |  | I-WP126 | Nikki Klein | Review | I-WP126 Readiness Workplan - Collaborative Review and Update | 8 hrs | 10 days | Thu 7/13/23 | Wed 7/26/23 | 1865 | 1867 |  | Nikki Klein,Jordan Nobles,Carolyn Hicks,Angie Robertson
6786 | 1867 | Future Task |  |  | I-WP126 | Nikki Klein | Review | I-WP126 Readiness Workplan - Style Guide Review | 8 hrs | 1 day | Thu 7/27/23 | Thu 7/27/23 | 1866 | 1868 |  | Tatiana Eubanks
6787 | 1868 | Future Task |  |  | I-WP126 | Nikki Klein | Review | I-WP126 Readiness Workplan - Final Review and Update | 10 hrs | 5 days | Fri 7/28/23 | Thu 8/3/23 | 1867 | 1869 |  | Angie Robertson,Jimmy Cox
6788 | 1869 | Future Task |  |  | I-WP126 | Nikki Klein | Approve | I-WP126 Readiness Workplan - Approve | 0 hrs | 0 days | Thu 8/3/23 | Thu 8/3/23 | 1868 |  |  | Jimmy Cox
3 | 1870 | Future Task | [5 empty] | Production Support | 1,863 hrs | 619 days | Mon 2/3/25 | Thu 7/15/27
5850 | 1871 | Future Task | [5 empty] | Hypercare | 517 hrs | 336 days | Mon 2/3/25 | Mon 6/1/26
5852 | 1872 | Future Task |  |  | D664 | Bryan Sohayda |  | D664 - Development of the Hypercare Support Plan | 205 hrs | 87 days | Mon 2/3/25 | Wed 6/4/25
5853 | 1873 | Future Task |  |  | D664 | Bryan Sohayda | Create | DED D664 - Development of the Hypercare Support Plan - Create | 8 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1 | 1874,1943SS | 2025-02-03 | Bryan Sohayda
5854 | 1874 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DED D664 - Development of the Hypercare Support Plan - Submit | 0 hrs | 0 days | Fri 2/14/25 | Fri 2/14/25 | 1873 | 1875 |  | Bryan Sohayda,Joy Schneider
5855 | 1875 | Future Task |  |  | D664 | Bryan Sohayda | Review | DED D664 - Development of the Hypercare Support Plan - Collaborative Review | 16 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 1874 | 1876 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5856 | 1876 | Future Task |  |  | D664 | Bryan Sohayda | Approve | DED D664 - Development of the Hypercare Support Plan - Approve | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 1875 | 1877 |  | Jimmy Cox
5857 | 1877 | Future Task |  |  | D664 | Bryan Sohayda |  | Development of the Hypercare Support Plan | 20 hrs | 50 days | Mon 3/3/25 | Fri 5/9/25 | 1876 | 1878SS,1884 |  | Bryan Sohayda,Chetna Dewan
5858 | 1878 | Future Task |  |  | D664 | Bryan Sohayda |  | Define and document hypercare support processes and procedures | 20 hrs | 10 days | Mon 3/3/25 | Fri 3/14/25 | 1877SS | 1879 |  | Bryan Sohayda,Chetna Dewan
5859 | 1879 | Future Task |  |  | D664 | Bryan Sohayda |  | Review hypercare support processes and procedures draft | 20 hrs | 5 days | Mon 3/17/25 | Fri 3/21/25 | 1878 | 1880 |  | Bryan Sohayda,Chetna Dewan
5860 | 1880 | Future Task |  |  | D664 | Bryan Sohayda |  | Define and document tools used for hypercare support activities | 20 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 1879 | 1881 |  | Bryan Sohayda,Chetna Dewan
5861 | 1881 | Future Task |  |  | D664 | Bryan Sohayda |  | Review tools used for hypercare activities draft | 20 hrs | 5 days | Mon 3/31/25 | Fri 4/4/25 | 1880 | 1882 |  | Bryan Sohayda,Chetna Dewan
5862 | 1882 | Future Task |  |  | D664 | Bryan Sohayda |  | Determine and document resource capacity and skills needed | 20 hrs | 5 days | Mon 4/7/25 | Fri 4/11/25 | 1881 | 1883 |  | Bryan Sohayda,Chetna Dewan
5863 | 1883 | Future Task |  |  | D664 | Bryan Sohayda |  | Review resource capacity and skills needed draft | 20 hrs | 5 days | Mon 4/14/25 | Fri 4/18/25 | 1882 | 1884 |  | Bryan Sohayda,Chetna Dewan
5864 | 1884 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DEL D664 - Development of the Hypercare Support Plan - Draft Submission | 0 hrs | 0 days | Fri 5/9/25 | Fri 5/9/25 | 18771883 | 1885 |  | Bryan Sohayda,Joy Schneider
5865 | 1885 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Pre-Submission Collaborative Review | 12 hrs | 5 days | Mon 5/12/25 | Fri 5/16/25 | 1884 | 1886 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5866 | 1886 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Style Guide Review | 1 hr | 1 day | Mon 5/19/25 | Mon 5/19/25 | 1885 | 1887 |  | Dusti Kincl
5867 | 1887 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Final Collaborative Review | 12 hrs | 5 days | Tue 5/20/25 | Tue 5/27/25 | 1886 | 1888 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5868 | 1888 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Accenture QC | 4 hrs | 2 days | Wed 5/28/25 | Thu 5/29/25 | 1887 | 1889 |  | Joy Schneider
5869 | 1889 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DEL D664 - Development of the Hypercare Support Plan - Submit | 0 hrs | 0 days | Thu 5/29/25 | Thu 5/29/25 | 1888 | 1890 |  | Joy Schneider
5870 | 1890 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Department QC | 4 hrs | 1 day | Fri 5/30/25 | Fri 5/30/25 | 1889 | 1891 |  | Tommy Werner,Gabriela Gibson
5871 | 1891 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Contract Manager Review | 8 hrs | 3 days | Mon 6/2/25 | Wed 6/4/25 | 1890 | 1892 |  | Sean Buchanan
5872 | 1892 | Future Task |  |  | D664 | Bryan Sohayda | Accept | DEL D664 - Development of the Hypercare Support Plan - Accept | 0 hrs | 0 days | Wed 6/4/25 | Wed 6/4/25 | 1891 | 1894 | 2025-06-01 | Sean Buchanan
5873 | 1893 | Future Task |  |  | D680 | Bryan Sohayda |  | D680 - Hypercare Monthly Deliverable – January 2026 | 153 hrs | 80 days | Mon 11/3/25 | Mon 3/2/26
5874 | 1894 | Future Task |  |  | D680-D683 | Bryan Sohayda | Create | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Create | 80 hrs | 10 days | Mon 11/3/25 | Mon 11/17/25 | 1892 | 1895 |  | Bryan Sohayda
5875 | 1895 | Future Task |  |  | D680-D683 | Bryan Sohayda | Submit | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Submit | 0 hrs | 0 days | Mon 11/17/25 | Mon 11/17/25 | 1894 | 1896 |  | Bryan Sohayda,Joy Schneider
5876 | 1896 | Future Task |  |  | D680-D683 | Bryan Sohayda | Review | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Collaborative Review | 20 hrs | 10 days | Tue 11/18/25 | Wed 12/3/25 | 1895 | 1897 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
7150 | 1897 | Future Task |  |  | D680-D683 | Bryan Sohayda | Approve | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Approve | 0 hrs | 0 days | Tue 11/25/25 | Tue 11/25/25 | 1896 | 1898FS+44 days |  | Jimmy Cox
5877 | 1898 | Future Task |  |  | D680 | Bryan Sohayda |  | Create D680 - Hypercare Monthly Deliverable – January 2026 | 4 hrs | 4 days | Mon 2/2/26 | Thu 2/5/26 | 1897FS+44 days | 1899 |  | Bryan Sohayda
5878 | 1899 | Future Task |  |  | D680 | Bryan Sohayda | Submit | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Draft Submission | 0 hrs | 0 days | Thu 2/5/26 | Thu 2/5/26 | 1898 | 1900 |  | Joy Schneider,Bryan Sohayda
5879 | 1900 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 2/6/26 | Thu 2/12/26 | 1899 | 1901 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5880 | 1901 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Style Guide Review | 1 hr | 1 day | Fri 2/13/26 | Fri 2/13/26 | 1900 | 1902 |  | Dusti Kincl
5881 | 1902 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Final Collaborative Review | 16 hrs | 5 days | Mon 2/16/26 | Fri 2/20/26 | 1901 | 1903 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5882 | 1903 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Accenture QC | 4 hrs | 2 days | Mon 2/23/26 | Tue 2/24/26 | 1902 | 1904 |  | Joy Schneider
5883 | 1904 | Future Task |  |  | D680 | Bryan Sohayda | Submit | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Submit | 0 hrs | 0 days | Tue 2/24/26 | Tue 2/24/26 | 1903 | 1905 |  | Joy Schneider
5884 | 1905 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Department QC | 4 hrs | 1 day | Wed 2/25/26 | Wed 2/25/26 | 1904 | 1906 |  | Tommy Werner
5885 | 1906 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 2/26/26 | Mon 3/2/26 | 1905 | 1907 |  | Sean Buchanan
5886 | 1907 | Future Task |  |  | D680 | Bryan Sohayda | Accept | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Accept | 0 hrs | 0 days | Mon 3/2/26 | Mon 3/2/26 | 1906 | 1909FS-1 day |  | Sean Buchanan
5887 | 1908 | Future Task |  |  | D681 | Bryan Sohayda |  | D681 - Hypercare Monthly Deliverable – February 2026 | 53 hrs | 21 days | Mon 3/2/26 | Mon 3/30/26
5888 | 1909 | Future Task |  |  | D681 | Bryan Sohayda |  | Create D681 - Hypercare Monthly Deliverable – February 2026 | 4 hrs | 4 days | Mon 3/2/26 | Thu 3/5/26 | 1907FS-1 day | 1910 |  | Bryan Sohayda
5889 | 1910 | Future Task |  |  | D681 | Bryan Sohayda | Submit | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Draft Submission | 0 hrs | 0 days | Thu 3/5/26 | Thu 3/5/26 | 1909 | 1911 |  | Joy Schneider,Bryan Sohayda
5890 | 1911 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 3/6/26 | Thu 3/12/26 | 1910 | 1912 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5891 | 1912 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Style Guide Review | 1 hr | 1 day | Fri 3/13/26 | Fri 3/13/26 | 1911 | 1913 |  | Dusti Kincl
5892 | 1913 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Final Collaborative Review | 16 hrs | 5 days | Mon 3/16/26 | Fri 3/20/26 | 1912 | 1914 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5893 | 1914 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Accenture QC | 4 hrs | 2 days | Mon 3/23/26 | Tue 3/24/26 | 1913 | 1915 |  | Joy Schneider
5894 | 1915 | Future Task |  |  | D681 | Bryan Sohayda | Submit | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Submit | 0 hrs | 0 days | Tue 3/24/26 | Tue 3/24/26 | 1914 | 1916 |  | Joy Schneider
5895 | 1916 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Department QC | 4 hrs | 1 day | Wed 3/25/26 | Wed 3/25/26 | 1915 | 1917 |  | Tommy Werner
5896 | 1917 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 3/26/26 | Mon 3/30/26 | 1916 | 1918 |  | Sean Buchanan
5897 | 1918 | Future Task |  |  | D681 | Bryan Sohayda | Accept | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Accept | 0 hrs | 0 days | Mon 3/30/26 | Mon 3/30/26 | 1917 | 1920 |  | Sean Buchanan
5898 | 1919 | Future Task |  |  | D682 | Bryan Sohayda |  | D682 - Hypercare Monthly Deliverable – March 2026 | 53 hrs | 21 days | Wed 4/1/26 | Wed 4/29/26
5899 | 1920 | Future Task |  |  | D682 | Bryan Sohayda |  | Create D682 - Hypercare Monthly Deliverable – March 2026 | 4 hrs | 4 days | Wed 4/1/26 | Mon 4/6/26 | 1918 | 1921 |  | Bryan Sohayda
5900 | 1921 | Future Task |  |  | D682 | Bryan Sohayda | Submit | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Draft Submission | 0 hrs | 0 days | Mon 4/6/26 | Mon 4/6/26 | 1920 | 1922 |  | Joy Schneider,Bryan Sohayda
5901 | 1922 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Tue 4/7/26 | Mon 4/13/26 | 1921 | 1923 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5902 | 1923 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Style Guide Review | 1 hr | 1 day | Tue 4/14/26 | Tue 4/14/26 | 1922 | 1924 |  | Dusti Kincl
5903 | 1924 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Final Collaborative Review | 16 hrs | 5 days | Wed 4/15/26 | Tue 4/21/26 | 1923 | 1925 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5904 | 1925 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Accenture QC | 4 hrs | 2 days | Wed 4/22/26 | Thu 4/23/26 | 1924 | 1926 |  | Joy Schneider
5905 | 1926 | Future Task |  |  | D682 | Bryan Sohayda | Submit | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Submit | 0 hrs | 0 days | Thu 4/23/26 | Thu 4/23/26 | 1925 | 1927 |  | Joy Schneider
5906 | 1927 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Department QC | 4 hrs | 1 day | Fri 4/24/26 | Fri 4/24/26 | 1926 | 1928 |  | Tommy Werner
5907 | 1928 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Contract Manager Review | 8 hrs | 3 days | Mon 4/27/26 | Wed 4/29/26 | 1927 | 1929 |  | Sean Buchanan
5908 | 1929 | Future Task |  |  | D682 | Bryan Sohayda | Accept | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Accept | 0 hrs | 0 days | Wed 4/29/26 | Wed 4/29/26 | 1928 | 1931 |  | Sean Buchanan
5909 | 1930 | Future Task |  |  | D683 | Bryan Sohayda |  | D683 - Hypercare Monthly Deliverable – April 2026 | 53 hrs | 21 days | Fri 5/1/26 | Mon 6/1/26
5910 | 1931 | Future Task |  |  | D683 | Bryan Sohayda |  | Create D683 - Hypercare Monthly Deliverable – April 2026 | 4 hrs | 4 days | Fri 5/1/26 | Wed 5/6/26 | 1929 | 1932 |  | Bryan Sohayda
5911 | 1932 | Future Task |  |  | D683 | Bryan Sohayda | Submit | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Draft Submission | 0 hrs | 0 days | Wed 5/6/26 | Wed 5/6/26 | 1931 | 1933 |  | Joy Schneider,Bryan Sohayda
5912 | 1933 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Thu 5/7/26 | Wed 5/13/26 | 1932 | 1934 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5913 | 1934 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Style Guide Review | 1 hr | 1 day | Thu 5/14/26 | Thu 5/14/26 | 1933 | 1935 |  | Dusti Kincl
5914 | 1935 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Final Collaborative Review | 16 hrs | 5 days | Fri 5/15/26 | Thu 5/21/26 | 1934 | 1936 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5915 | 1936 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Accenture QC | 4 hrs | 2 days | Fri 5/22/26 | Tue 5/26/26 | 1935 | 1937 |  | Joy Schneider
5916 | 1937 | Future Task |  |  | D683 | Bryan Sohayda | Submit | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Submit | 0 hrs | 0 days | Tue 5/26/26 | Tue 5/26/26 | 1936 | 1938 |  | Joy Schneider
5917 | 1938 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Department QC | 4 hrs | 1 day | Wed 5/27/26 | Wed 5/27/26 | 1937 | 1939 |  | Tommy Werner
5918 | 1939 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 5/28/26 | Mon 6/1/26 | 1938 | 1940 |  | Sean Buchanan
5919 | 1940 | Future Task |  |  | D683 | Bryan Sohayda | Accept | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Accept | 0 hrs | 0 days | Mon 6/1/26 | Mon 6/1/26 | 1939 |  |  | Sean Buchanan
5851 | 1941 | Future Task | [5 empty] | Post-Implementation Support | 1,346 hrs | 619 days | Mon 2/3/25 | Thu 7/15/27
5488 | 1942 | Future Task |  |  | D665 | Bryan Sohayda |  | D665 - Updated Post-Implementation Support Plan | 154 hrs | 92 days | Mon 2/3/25 | Wed 6/11/25
5489 | 1943 | Future Task |  |  | D665 | Bryan Sohayda | Create | DED D665 - Updated Post-Implementation Support Plan - Create | 8 hrs | 10 days | Mon 2/3/25 | Fri 2/14/25 | 1873SS | 1944 |  | Bryan Sohayda
5490 | 1944 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DED D665 - Updated Post-Implementation Support Plan - Submit | 0 hrs | 0 days | Fri 2/14/25 | Fri 2/14/25 | 1943 | 1945 |  | Bryan Sohayda,Joy Schneider
5491 | 1945 | Future Task |  |  | D665 | Bryan Sohayda | Review | DED D665 - Updated Post-Implementation Support Plan - Collaborative Review | 16 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 1944 | 1946 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5492 | 1946 | Future Task |  |  | D665 | Bryan Sohayda | Approve | DED D665 - Updated Post-Implementation Support Plan - Approve | 0 hrs | 0 days | Fri 2/28/25 | Fri 2/28/25 | 1945 | 1947 |  | Jimmy Cox
5493 | 1947 | Future Task |  |  | D665 | Bryan Sohayda |  | Create Post Implementation Support Processes and Procedures | 20 hrs | 15 days | Mon 3/3/25 | Fri 3/21/25 | 1946 | 1948 |  | Bryan Sohayda,Chetna Dewan
5494 | 1948 | Future Task |  |  | D665 | Bryan Sohayda |  | Document Post Implementation Support Tools | 20 hrs | 10 days | Mon 3/24/25 | Fri 4/4/25 | 1947 | 1949 |  | Bryan Sohayda,Chetna Dewan
5495 | 1949 | Future Task |  |  | D665 | Bryan Sohayda |  | Post-Implementation Support Resource Capacity and Skills | 20 hrs | 10 days | Mon 4/7/25 | Fri 4/18/25 | 1948 | 1950 |  | Bryan Sohayda,Chetna Dewan
5496 | 1950 | Future Task |  |  | D665 | Bryan Sohayda |  | Full draft review pre-submission | 20 hrs | 20 days | Mon 4/21/25 | Fri 5/16/25 | 1949 | 1951 |  | Bryan Sohayda,Chetna Dewan
5497 | 1951 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DEL D665 - Updated Post-Implementation Support Plan - Draft Submission | 0 hrs | 0 days | Fri 5/16/25 | Fri 5/16/25 | 1950 | 1952 |  | Bryan Sohayda,Joy Schneider
5498 | 1952 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Pre-Submission Collaborative Review | 12 hrs | 5 days | Mon 5/19/25 | Fri 5/23/25 | 1951 | 1953 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5499 | 1953 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Style Guide Review | 1 hr | 1 day | Tue 5/27/25 | Tue 5/27/25 | 1952 | 1954 |  | Dusti Kincl
5500 | 1954 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Final Collaborative Review | 21 hrs | 5 days | Wed 5/28/25 | Tue 6/3/25 | 1953 | 1955 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5501 | 1955 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Accenture QC | 4 hrs | 2 days | Wed 6/4/25 | Thu 6/5/25 | 1954 | 1956 |  | Joy Schneider
5502 | 1956 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DEL D665 - Updated Post-Implementation Support Plan - Submit | 0 hrs | 0 days | Thu 6/5/25 | Thu 6/5/25 | 1955 | 1957 |  | Joy Schneider
5503 | 1957 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Department QC | 4 hrs | 1 day | Fri 6/6/25 | Fri 6/6/25 | 1956 | 1958 |  | Tommy Werner,Gabriela Gibson
5504 | 1958 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Contract Manager Review | 8 hrs | 3 days | Mon 6/9/25 | Wed 6/11/25 | 1957 | 1959 |  | Sean Buchanan
5505 | 1959 | Future Task |  |  | D665 | Bryan Sohayda | Accept | DEL D665 - Updated Post-Implementation Support Plan - Accept | 0 hrs | 0 days | Wed 6/11/25 | Wed 6/11/25 | 1958 |  | 2025-06-01 | Sean Buchanan
5759 | 1960 | Future Task |  |  | D684 | Bryan Sohayda |  | D684 - Post-Implementation Support Monthly Deliverable – May 2026 | 122 hrs | 85 days | Mon 3/2/26 | Mon 6/29/26
5760 | 1961 | Future Task |  |  | D684-D691 | Bryan Sohayda | Create | DED Create - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 8 hrs | 5 days | Mon 3/2/26 | Fri 3/6/26 | 1 | 1962 |  | Bryan Sohayda
5761 | 1962 | Future Task |  |  | D684-D691 | Bryan Sohayda | Submit | DED Submit - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 0 hrs | 0 days | Fri 3/6/26 | Fri 3/6/26 | 1961 | 1963 |  | Bryan Sohayda,Joy Schneider
5762 | 1963 | Future Task |  |  | D684-D691 | Bryan Sohayda | Review | DED Collaborative Review & Accept - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 20 hrs | 10 days | Mon 3/9/26 | Fri 3/20/26 | 1962 | 1964 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5763 | 1964 | Future Task |  |  | D684 | Bryan Sohayda |  | Create D684 - Post-Implementation Support Monthly Deliverable – May 2026 | 4 hrs | 4 days | Mon 6/1/26 | Thu 6/4/26 | 1963 | 1965 |  | Bryan Sohayda
5764 | 1965 | Future Task |  |  | D684 | Bryan Sohayda | Submit | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Draft Submission | 0 hrs | 0 days | Thu 6/4/26 | Thu 6/4/26 | 1964 | 1966 |  | Joy Schneider,Bryan Sohayda
5765 | 1966 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Pre-Submission Collaborative Review | 20 hrs | 5 days | Fri 6/5/26 | Thu 6/11/26 | 1965 | 1967 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5766 | 1967 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Style Guide Review | 8 hrs | 1 day | Fri 6/12/26 | Fri 6/12/26 | 1966 | 1968 |  | Dusti Kincl
5767 | 1968 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Final Collaborative Review | 20 hrs | 5 days | Mon 6/15/26 | Fri 6/19/26 | 1967 | 1969 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5768 | 1969 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Accenture QC | 16 hrs | 2 days | Mon 6/22/26 | Tue 6/23/26 | 1968 | 1970 |  | Joy Schneider
5769 | 1970 | Future Task |  |  | D684 | Bryan Sohayda | Submit | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Submit | 0 hrs | 0 days | Tue 6/23/26 | Tue 6/23/26 | 1969 | 1971 |  | Joy Schneider
5770 | 1971 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Department QC | 2 hrs | 1 day | Wed 6/24/26 | Wed 6/24/26 | 1970 | 1972 |  | Tommy Werner
5771 | 1972 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Contract Manager Review | 24 hrs | 3 days | Thu 6/25/26 | Mon 6/29/26 | 1971 | 1973 |  | Sean Buchanan
5772 | 1973 | Future Task |  |  | D684 | Bryan Sohayda | Accept | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Accept | 0 hrs | 0 days | Mon 6/29/26 | Mon 6/29/26 | 1972 | 1975 |  | Sean Buchanan
5773 | 1974 | Future Task |  |  | D685 | Bryan Sohayda |  | D685 - Post-Implementation Support Monthly Deliverable – June 2026 | 53 hrs | 21 days | Wed 7/1/26 | Thu 7/30/26
5774 | 1975 | Future Task |  |  | D685 | Bryan Sohayda |  | Create D685 - Post-Implementation Support Monthly Deliverable – June 2026 | 4 hrs | 4 days | Wed 7/1/26 | Tue 7/7/26 | 1973 | 1976 |  | Bryan Sohayda
5775 | 1976 | Future Task |  |  | D685 | Bryan Sohayda | Submit | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Draft Submission | 0 hrs | 0 days | Tue 7/7/26 | Tue 7/7/26 | 1975 | 1977 |  | Joy Schneider,Bryan Sohayda
5776 | 1977 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Wed 7/8/26 | Tue 7/14/26 | 1976 | 1978 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5777 | 1978 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Style Guide Review | 1 hr | 1 day | Wed 7/15/26 | Wed 7/15/26 | 1977 | 1979 |  | Dusti Kincl
5778 | 1979 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Final Collaborative Review | 16 hrs | 5 days | Thu 7/16/26 | Wed 7/22/26 | 1978 | 1980 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5779 | 1980 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Accenture QC | 4 hrs | 2 days | Thu 7/23/26 | Fri 7/24/26 | 1979 | 1981 |  | Joy Schneider
5780 | 1981 | Future Task |  |  | D685 | Bryan Sohayda | Submit | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Submit | 0 hrs | 0 days | Fri 7/24/26 | Fri 7/24/26 | 1980 | 1982 |  | Joy Schneider
5781 | 1982 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Department QC | 4 hrs | 1 day | Mon 7/27/26 | Mon 7/27/26 | 1981 | 1983 |  | Tommy Werner
5782 | 1983 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 7/28/26 | Thu 7/30/26 | 1982 | 1984 |  | Sean Buchanan
5783 | 1984 | Future Task |  |  | D685 | Bryan Sohayda | Accept | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Accept | 0 hrs | 0 days | Thu 7/30/26 | Thu 7/30/26 | 1983 | 1986 |  | Sean Buchanan
5784 | 1985 | Future Task |  |  | D686 | Bryan Sohayda |  | D686 - Post-Implementation Support Monthly Deliverable – July 2026 | 53 hrs | 21 days | Mon 8/3/26 | Mon 8/31/26
5785 | 1986 | Future Task |  |  | D686 | Bryan Sohayda |  | Create D686 - Post-Implementation Support Monthly Deliverable – July 2026 | 4 hrs | 4 days | Mon 8/3/26 | Thu 8/6/26 | 1984 | 1987 |  | Bryan Sohayda
5786 | 1987 | Future Task |  |  | D686 | Bryan Sohayda | Submit | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Draft Submission | 0 hrs | 0 days | Thu 8/6/26 | Thu 8/6/26 | 1986 | 1988 |  | Joy Schneider,Bryan Sohayda
5787 | 1988 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 8/7/26 | Thu 8/13/26 | 1987 | 1989 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5788 | 1989 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Style Guide Review | 1 hr | 1 day | Fri 8/14/26 | Fri 8/14/26 | 1988 | 1990 |  | Dusti Kincl
5789 | 1990 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Final Collaborative Review | 16 hrs | 5 days | Mon 8/17/26 | Fri 8/21/26 | 1989 | 1991 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5790 | 1991 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Accenture QC | 4 hrs | 2 days | Mon 8/24/26 | Tue 8/25/26 | 1990 | 1992 |  | Joy Schneider
5791 | 1992 | Future Task |  |  | D686 | Bryan Sohayda | Submit | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Submit | 0 hrs | 0 days | Tue 8/25/26 | Tue 8/25/26 | 1991 | 1993 |  | Joy Schneider
5792 | 1993 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Department QC | 4 hrs | 1 day | Wed 8/26/26 | Wed 8/26/26 | 1992 | 1994 |  | Tommy Werner
5793 | 1994 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Contract Manager Review | 8 hrs | 3 days | Thu 8/27/26 | Mon 8/31/26 | 1993 | 1995 |  | Sean Buchanan
5794 | 1995 | Future Task |  |  | D686 | Bryan Sohayda | Accept | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Accept | 0 hrs | 0 days | Mon 8/31/26 | Mon 8/31/26 | 1994 | 1997 |  | Sean Buchanan
5795 | 1996 | Future Task |  |  | D687 | Bryan Sohayda |  | D687 - Post-Implementation Support Monthly Deliverable – August 2026 | 53 hrs | 21 days | Tue 9/1/26 | Wed 9/30/26
5796 | 1997 | Future Task |  |  | D687 | Bryan Sohayda |  | Create D687 - Post-Implementation Support Monthly Deliverable – August 2026 | 4 hrs | 4 days | Tue 9/1/26 | Fri 9/4/26 | 1995 | 1998 |  | Bryan Sohayda
5797 | 1998 | Future Task |  |  | D687 | Bryan Sohayda | Submit | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Draft Submission | 0 hrs | 0 days | Fri 9/4/26 | Fri 9/4/26 | 1997 | 1999 |  | Joy Schneider,Bryan Sohayda
5798 | 1999 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Tue 9/8/26 | Mon 9/14/26 | 1998 | 2000 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5799 | 2000 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Style Guide Review | 1 hr | 1 day | Tue 9/15/26 | Tue 9/15/26 | 1999 | 2001 |  | Dusti Kincl
5800 | 2001 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Final Collaborative Review | 16 hrs | 5 days | Wed 9/16/26 | Tue 9/22/26 | 2000 | 2002 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5801 | 2002 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Accenture QC | 4 hrs | 2 days | Wed 9/23/26 | Thu 9/24/26 | 2001 | 2003 |  | Joy Schneider
5802 | 2003 | Future Task |  |  | D687 | Bryan Sohayda | Submit | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Submit | 0 hrs | 0 days | Thu 9/24/26 | Thu 9/24/26 | 2002 | 2004 |  | Joy Schneider
5803 | 2004 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Department QC | 4 hrs | 1 day | Fri 9/25/26 | Fri 9/25/26 | 2003 | 2005 |  | Tommy Werner
5804 | 2005 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Contract Manager Review | 8 hrs | 3 days | Mon 9/28/26 | Wed 9/30/26 | 2004 | 2006 |  | Sean Buchanan
5805 | 2006 | Future Task |  |  | D687 | Bryan Sohayda | Accept | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Accept | 0 hrs | 0 days | Wed 9/30/26 | Wed 9/30/26 | 2005 | 2008 |  | Sean Buchanan
5806 | 2007 | Future Task |  |  | D688 | Bryan Sohayda |  | D688 - Post-Implementation Support Monthly Deliverable – September 2026 | 53 hrs | 21 days | Thu 10/1/26 | Thu 10/29/26
5807 | 2008 | Future Task |  |  | D688 | Bryan Sohayda |  | Create D688 - Post-Implementation Support Monthly Deliverable – September 2026 | 4 hrs | 4 days | Thu 10/1/26 | Tue 10/6/26 | 2006 | 2009 |  | Bryan Sohayda
5808 | 2009 | Future Task |  |  | D688 | Bryan Sohayda | Submit | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Draft Submission | 0 hrs | 0 days | Tue 10/6/26 | Tue 10/6/26 | 2008 | 2010 |  | Joy Schneider,Bryan Sohayda
5809 | 2010 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Wed 10/7/26 | Tue 10/13/26 | 2009 | 2011 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5810 | 2011 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Style Guide Review | 1 hr | 1 day | Wed 10/14/26 | Wed 10/14/26 | 2010 | 2012 |  | Dusti Kincl
5811 | 2012 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Final Collaborative Review | 16 hrs | 5 days | Thu 10/15/26 | Wed 10/21/26 | 2011 | 2013 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5812 | 2013 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Accenture QC | 4 hrs | 2 days | Thu 10/22/26 | Fri 10/23/26 | 2012 | 2014 |  | Joy Schneider
5813 | 2014 | Future Task |  |  | D688 | Bryan Sohayda | Submit | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Submit | 0 hrs | 0 days | Fri 10/23/26 | Fri 10/23/26 | 2013 | 2015 |  | Joy Schneider
5814 | 2015 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Department QC | 4 hrs | 1 day | Mon 10/26/26 | Mon 10/26/26 | 2014 | 2016 |  | Tommy Werner
5815 | 2016 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 10/27/26 | Thu 10/29/26 | 2015 | 2017 |  | Sean Buchanan
5816 | 2017 | Future Task |  |  | D688 | Bryan Sohayda | Accept | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Accept | 0 hrs | 0 days | Thu 10/29/26 | Thu 10/29/26 | 2016 | 2019 |  | Sean Buchanan
5817 | 2018 | Future Task |  |  | D689 | Bryan Sohayda |  | D689 - Post-Implementation Support Monthly Deliverable – October 2026 | 53 hrs | 18 days | Mon 11/2/26 | Mon 11/30/26
5818 | 2019 | Future Task |  |  | D689 | Bryan Sohayda |  | Create D689 - Post-Implementation Support Monthly Deliverable – October 2026 | 4 hrs | 4 days | Mon 11/2/26 | Thu 11/5/26 | 2017 | 2020,2052SS |  | Bryan Sohayda
5819 | 2020 | Future Task |  |  | D689 | Bryan Sohayda | Submit | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Draft Submission | 0 hrs | 0 days | Thu 11/5/26 | Thu 11/5/26 | 2019 | 2021 |  | Joy Schneider,Bryan Sohayda
5820 | 2021 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Pre-Submission Collaborative Review | 16 hrs | 4 days | Fri 11/6/26 | Thu 11/12/26 | 2020 | 2022 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5821 | 2022 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Style Guide Review | 1 hr | 1 day | Fri 11/13/26 | Fri 11/13/26 | 2021 | 2023 |  | Dusti Kincl
5822 | 2023 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Final Collaborative Review | 16 hrs | 3 days | Mon 11/16/26 | Wed 11/18/26 | 2022 | 2024 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5823 | 2024 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Accenture QC | 4 hrs | 2 days | Thu 11/19/26 | Fri 11/20/26 | 2023 | 2025 |  | Joy Schneider
5824 | 2025 | Future Task |  |  | D689 | Bryan Sohayda | Submit | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Submit | 0 hrs | 0 days | Fri 11/20/26 | Fri 11/20/26 | 2024 | 2026 |  | Joy Schneider
5825 | 2026 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Department QC | 4 hrs | 1 day | Mon 11/23/26 | Mon 11/23/26 | 2025 | 2027 |  | Tommy Werner
5826 | 2027 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Contract Manager Review | 8 hrs | 3 days | Tue 11/24/26 | Mon 11/30/26 | 2026 | 2028 |  | Sean Buchanan
5827 | 2028 | Future Task |  |  | D689 | Bryan Sohayda | Accept | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Accept | 0 hrs | 0 days | Mon 11/30/26 | Mon 11/30/26 | 2027 | 2030 |  | Sean Buchanan
5828 | 2029 | Future Task |  |  | D690 | Bryan Sohayda |  | D690 - Post-Implementation Support Monthly Deliverable – November 2026 | 53 hrs | 21 days | Tue 12/1/26 | Wed 12/30/26
5829 | 2030 | Future Task |  |  | D690 | Bryan Sohayda |  | Create D690 - Post-Implementation Support Monthly Deliverable – November 2026 | 4 hrs | 4 days | Tue 12/1/26 | Fri 12/4/26 | 2028 | 2031 |  | Bryan Sohayda
5830 | 2031 | Future Task |  |  | D690 | Bryan Sohayda | Submit | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Draft Submission | 0 hrs | 0 days | Fri 12/4/26 | Fri 12/4/26 | 2030 | 2032 |  | Joy Schneider,Bryan Sohayda
5831 | 2032 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 12/7/26 | Fri 12/11/26 | 2031 | 2033 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5832 | 2033 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Style Guide Review | 1 hr | 1 day | Mon 12/14/26 | Mon 12/14/26 | 2032 | 2034 |  | Dusti Kincl
5833 | 2034 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Final Collaborative Review | 16 hrs | 5 days | Tue 12/15/26 | Mon 12/21/26 | 2033 | 2035 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5834 | 2035 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Accenture QC | 4 hrs | 2 days | Tue 12/22/26 | Wed 12/23/26 | 2034 | 2036 |  | Joy Schneider
5835 | 2036 | Future Task |  |  | D690 | Bryan Sohayda | Submit | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Submit | 0 hrs | 0 days | Wed 12/23/26 | Wed 12/23/26 | 2035 | 2037 |  | Joy Schneider
5836 | 2037 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Department QC | 4 hrs | 1 day | Thu 12/24/26 | Thu 12/24/26 | 2036 | 2038 |  | Tommy Werner
5837 | 2038 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Contract Manager Review | 8 hrs | 3 days | Mon 12/28/26 | Wed 12/30/26 | 2037 | 2039 |  | Sean Buchanan
5838 | 2039 | Future Task |  |  | D690 | Bryan Sohayda | Accept | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Accept | 0 hrs | 0 days | Wed 12/30/26 | Wed 12/30/26 | 2038 | 2041 |  | Sean Buchanan
5839 | 2040 | Future Task |  |  | D691 | Bryan Sohayda |  | D691 - Post-Implementation Support Monthly Deliverable – December 2026 | 53 hrs | 21 days | Mon 1/4/27 | Tue 2/2/27
5840 | 2041 | Future Task |  |  | D691 | Bryan Sohayda |  | Create D691 - Post-Implementation Support Monthly Deliverable – December 2026 | 4 hrs | 4 days | Mon 1/4/27 | Thu 1/7/27 | 2039 | 2042 |  | Bryan Sohayda
5841 | 2042 | Future Task |  |  | D691 | Bryan Sohayda | Submit | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Draft Submission | 0 hrs | 0 days | Thu 1/7/27 | Thu 1/7/27 | 2041 | 2043 |  | Joy Schneider,Bryan Sohayda
5842 | 2043 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | Fri 1/8/27 | Thu 1/14/27 | 2042 | 2044 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5843 | 2044 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Style Guide Review | 1 hr | 1 day | Fri 1/15/27 | Fri 1/15/27 | 2043 | 2045 |  | Dusti Kincl
5844 | 2045 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Final Collaborative Review | 16 hrs | 5 days | Tue 1/19/27 | Mon 1/25/27 | 2044 | 2046 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5845 | 2046 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Accenture QC | 4 hrs | 2 days | Tue 1/26/27 | Wed 1/27/27 | 2045 | 2047 |  | Joy Schneider
5846 | 2047 | Future Task |  |  | D691 | Bryan Sohayda | Submit | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Submit | 0 hrs | 0 days | Wed 1/27/27 | Wed 1/27/27 | 2046 | 2048 |  | Joy Schneider
5847 | 2048 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Department QC | 4 hrs | 1 day | Thu 1/28/27 | Thu 1/28/27 | 2047 | 2049 |  | Tommy Werner
5848 | 2049 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Contract Manager Review | 8 hrs | 3 days | Fri 1/29/27 | Tue 2/2/27 | 2048 | 2050 |  | Sean Buchanan
5849 | 2050 | Future Task |  |  | D691 | Bryan Sohayda | Accept | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Accept | 0 hrs | 0 days | Tue 2/2/27 | Tue 2/2/27 | 2049 |  |  | Sean Buchanan
6704 | 2051 | Future Task |  |  | D692 | Stacey Terry |  | D692 - Tax Reporting Support CY 2026 (January 2027) | 179 hrs | 69 days | Thu 11/12/26 | Tue 2/23/27
6705 | 2052 | Future Task |  |  | D692 | Stacey Terry | Create | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Create | 8 hrs | 10 days | Thu 11/12/26 | Wed 11/25/26 | 2019SS | 2053 | 2026-11-12 | Stacey Terry
6706 | 2053 | Future Task |  |  | D692 | Stacey Terry | Submit | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Submit | 0 hrs | 0 days | Wed 11/25/26 | Wed 11/25/26 | 2052 | 2054 |  | Stacey Terry,Joy Schneider
6707 | 2054 | Future Task |  |  | D692 | Stacey Terry | Review | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Collaborative Review | 20 hrs | 10 days | Mon 11/30/26 | Fri 12/11/26 | 2053 | 2055 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
6708 | 2055 | Future Task |  |  | D692 | Stacey Terry | Approve | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Approve | 0 hrs | 0 days | Fri 12/11/26 | Fri 12/11/26 | 2054 | 2056 |  | Jimmy Cox
6709 | 2056 | Future Task |  |  | D692 | Stacey Terry |  | Create Tax Reporting Checklist (2026) | 36 hrs | 18 days | Mon 12/14/26 | Fri 1/8/27 | 2055 | 2057FS-5 days,2058 |  | Stacey Terry,Yogesh Deshmukh
6710 | 2057 | Future Task |  |  | D692 | Stacey Terry |  | Manage Year-end Checklist (2026) | 38 hrs | 19 days | Mon 1/4/27 | Fri 1/29/27 | 2056FS-5 days |  |  | Stacey Terry,Yogesh Deshmukh
6711 | 2058 | Future Task |  |  | D692 | Stacey Terry |  | Create initial Year-end Checklist (2027) | 28 hrs | 14 days | Mon 1/11/27 | Fri 1/29/27 | 2056 | 2059 |  | Stacey Terry,Yogesh Deshmukh
6712 | 2059 | Future Task |  |  | D692 | Stacey Terry | Submit | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Draft Submission | 0 hrs | 0 days | Fri 1/29/27 | Fri 1/29/27 | 2058 | 2060 |  | Stacey Terry,Joy Schneider
6713 | 2060 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Pre-Submission Collaborative Review | 16 hrs | 5 days | Mon 2/1/27 | Fri 2/5/27 | 2059 | 2061 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson
6714 | 2061 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Style Guide Review | 1 hr | 1 day | Mon 2/8/27 | Mon 2/8/27 | 2060 | 2062 |  | Dusti Kincl
6715 | 2062 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Final Collaborative Review | 16 hrs | 5 days | Tue 2/9/27 | Mon 2/15/27 | 2061 | 2063 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson
6716 | 2063 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Accenture QC | 4 hrs | 2 days | Tue 2/16/27 | Wed 2/17/27 | 2062 | 2064 |  | Joy Schneider
6717 | 2064 | Future Task |  |  | D692 | Stacey Terry | Submit | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Submit | 0 hrs | 0 days | Wed 2/17/27 | Wed 2/17/27 | 2063 | 2065 |  | Joy Schneider
6718 | 2065 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Department QC | 4 hrs | 1 day | Thu 2/18/27 | Thu 2/18/27 | 2064 | 2066 |  | Tommy Werner,Gabriela Gibson
6719 | 2066 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Contract Manager Review | 8 hrs | 3 days | Fri 2/19/27 | Tue 2/23/27 | 2065 | 2067 |  | Sean Buchanan
6720 | 2067 | Future Task |  |  | D692 | Stacey Terry | Accept | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Accept | 0 hrs | 0 days | Tue 2/23/27 | Tue 2/23/27 | 2066 |  | 2027-02-01 | Sean Buchanan
6721 | 2068 | Future Task | Maybe |  | D693 | Joy Schneider |  | D693 - Exit Transition Completion | 122 hrs | 67 days | Mon 4/12/27 | Thu 7/15/27
6722 | 2069 | Future Task |  |  | D693 | Joy Schneider | Create | DED D693 - Exit Transition Completion - Create | 6 hrs | 10 days | Mon 4/12/27 | Fri 4/23/27 | 2095 | 2070 |  | Joy Schneider,Matt Cole,Mary Punty
6723 | 2070 | Future Task |  |  | D693 | Joy Schneider | Submit | DED D693 - Exit Transition Completion - Submit | 0 hrs | 0 days | Fri 4/23/27 | Fri 4/23/27 | 2069 | 2071 |  | Joy Schneider
6724 | 2071 | Future Task |  |  | D693 | Joy Schneider | Review | DED D693 - Exit Transition Completion - Collaborative Review | 12 hrs | 10 days | Mon 4/26/27 | Fri 5/7/27 | 2070 | 2072 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6725 | 2072 | Future Task |  |  | D693 | Joy Schneider | Approve | DED D693 - Exit Transition Completion - Approve | 0 hrs | 0 days | Fri 5/7/27 | Fri 5/7/27 | 2071 | 2073 |  | Jimmy Cox
6726 | 2073 | Future Task |  |  | D693 | Joy Schneider |  | D693 Review Status of Exit Transition Work Plan | 45 hrs | 15 days | Mon 5/10/27 | Fri 5/28/27 | 2072 | 2074 |  | Joy Schneider,Matt Cole,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
6727 | 2074 | Future Task |  |  | D693 | Joy Schneider |  | D693 Obtain Department Sign Off | 30 hrs | 15 days | Tue 6/1/27 | Mon 6/21/27 | 2073 | 2075 |  | Sean Buchanan,Matt Cole
6728 | 2075 | Future Task |  |  | D693 | Joy Schneider | Submit | DEL D693 - Exit Transition Completion - Draft Submission | 0 hrs | 0 days | Mon 6/21/27 | Mon 6/21/27 | 2074 | 2076 |  | Joy Schneider
6729 | 2076 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Pre-Submission Collaborative Review | 6 hrs | 5 days | Tue 6/22/27 | Mon 6/28/27 | 2075 | 2077 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6730 | 2077 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Style Guide Review | 1 hr | 1 day | Tue 6/29/27 | Tue 6/29/27 | 2076 | 2078 |  | Dusti Kincl
6731 | 2078 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Final Collaborative Review | 6 hrs | 5 days | Wed 6/30/27 | Wed 7/7/27 | 2077 | 2079 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6732 | 2079 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Accenture QC | 4 hrs | 2 days | Thu 7/8/27 | Fri 7/9/27 | 2078 | 2080 |  | Joy Schneider
6733 | 2080 | Future Task |  |  | D693 | Joy Schneider | Submit | DEL D693 - Exit Transition Completion - Submit | 0 hrs | 0 days | Fri 7/9/27 | Fri 7/9/27 | 2079 | 2081 |  | Joy Schneider
6734 | 2081 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Department QC | 4 hrs | 1 day | Mon 7/12/27 | Mon 7/12/27 | 2080 | 2082 |  | Tommy Werner
6735 | 2082 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Contract Manager Review | 8 hrs | 3 days | Tue 7/13/27 | Thu 7/15/27 | 2081 | 2083 |  | Sean Buchanan
6736 | 2083 | Future Task |  |  | D693 | Joy Schneider | Accept | DEL D693 - Exit Transition Completion - Accept | 0 hrs | 0 days | Thu 7/15/27 | Thu 7/15/27 | 2082 |  | 2027-07-01 | Sean Buchanan
5655 | 2084 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 - Exit Transition Work Plan | 398 hrs | 80 days | Tue 9/1/26 | Mon 12/28/26
5656 | 2085 | Future Task |  |  | WP428 | Joy Schneider | Create | WPED WP428 - Exit Transition Work Plan - Create | 8 hrs | 10 days | Tue 9/1/26 | Tue 9/15/26 | 1 | 2086 |  | Joy Schneider
5657 | 2086 | Future Task |  |  | WP428 | Joy Schneider | Submit | WPED WP428 - Exit Transition Work Plan - Submit | 0 hrs | 0 days | Tue 9/15/26 | Tue 9/15/26 | 2085 | 2087 |  | Joy Schneider
5658 | 2087 | Future Task |  |  | WP428 | Joy Schneider | Review | WPED WP428 - Exit Transition Work Plan - Review | 16 hrs | 10 days | Wed 9/16/26 | Tue 9/29/26 | 2086 | 2088 |  | Joy Schneider,Jimmy Cox,Angie Robertson,Sean Buchanan
5659 | 2088 | Future Task |  |  | WP428 | Joy Schneider | Approve | WPED WP428 - Exit Transition Work Plan - Approve | 0 hrs | 0 days | Tue 9/29/26 | Tue 9/29/26 | 2087 | 2089 |  | Jimmy Cox
5660 | 2089 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 Develop Exit Transition Work Plan | 210 hrs | 15 days | Wed 9/30/26 | Tue 10/20/26 | 2088 | 2090 |  | Joy Schneider,Stacey Terry,Manojkumar Gurjar,Matt Cole,Angie Robertson,Jimmy Cox,Francisca Li
5661 | 2090 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 Determine Entry and Exit Criteria | 120 hrs | 15 days | Wed 10/21/26 | Tue 11/10/26 | 2089 | 2091 |  | Joy Schneider,Matt Cole,Angie Robertson,Jimmy Cox
5662 | 2091 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 Review and Confirm Exit Transition Plan | 20 hrs | 15 days | Thu 11/12/26 | Fri 12/4/26 | 2090 | 2092 |  | Jimmy Cox,Angie Robertson,Joy Schneider
5663 | 2092 | Future Task |  |  | WP428 | Joy Schneider | Submit | WP WP428 - Exit Transition Work Plan - Submit | 0 hrs | 0 days | Fri 12/4/26 | Fri 12/4/26 | 2091 | 2093 |  | Joy Schneider
5664 | 2093 | Future Task |  |  | WP428 | Joy Schneider | Review | WP WP428 - Exit Transition Work Plan - Collaborative Review & Update | 12 hrs | 10 days | Mon 12/7/26 | Fri 12/18/26 | 2092 | 2094 |  | Joy Schneider,Jimmy Cox,Angie Robertson
5665 | 2094 | Future Task |  |  | WP428 | Joy Schneider | Review | WP WP428 - Exit Transition Work Plan - Final Review & Edits | 12 hrs | 5 days | Mon 12/21/26 | Mon 12/28/26 | 2093 | 2095 |  | Joy Schneider,Jimmy Cox,Angie Robertson
5666 | 2095 | Future Task |  |  | WP428 | Joy Schneider | Approve | WP WP428 - Exit Transition Work Plan - Approve | 0 hrs | 0 days | Mon 12/28/26 | Mon 12/28/26 | 2094 | 2069 |  | Jimmy Cox
4 | 2096 | Late | [5 empty] | Administrative Tasks | 2,164 hrs | 1174 days | Mon 5/1/23 | Tue 12/28/27
10 | 2097 | Future Task | [5 empty] | Administrative Activities | 1,320 hrs | 1152 days | Thu 6/1/23 | Tue 12/28/27
2063 | 2098 | Future Task |  |  |  | Tommy Werner |  | Budget | 308 hrs | 933 days | Thu 6/1/23 | Mon 2/15/27
2064 | 2099 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q1 | 14 hrs | 30 days | Thu 6/1/23 | Thu 7/13/23
2065 | 2100 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Thu 6/1/23 | Wed 6/14/23 |  | 2101 |  | Tommy Werner,Gabriela Gibson
2066 | 2101 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Thu 6/15/23 | Wed 6/28/23 | 2100 | 2102 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2067 | 2102 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Thu 6/29/23 | Thu 7/13/23 | 2101 | 2103 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2068 | 2103 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Thu 7/13/23 | Thu 7/13/23 | 2102 | 2105SS-8 days |  | Tommy Werner
2069 | 2104 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q2 | 14 hrs | 30 days | Mon 7/3/23 | Mon 8/14/23
2070 | 2105 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Mon 7/3/23 | Mon 7/17/23 | 2103SS-8 days | 2106 |  | Tommy Werner,Gabriela Gibson
2071 | 2106 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Tue 7/18/23 | Mon 7/31/23 | 2105 | 2107 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2072 | 2107 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 2106 | 2108 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2073 | 2108 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 8/14/23 | Mon 8/14/23 | 2107 | 2110 |  | Tommy Werner
2074 | 2109 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q3 | 14 hrs | 30 days | Mon 10/2/23 | Mon 11/13/23
2075 | 2110 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23 | 2108 | 2111 |  | Tommy Werner,Gabriela Gibson
2076 | 2111 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 2110 | 2112 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2077 | 2112 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Mon 10/30/23 | Mon 11/13/23 | 2111 | 2113 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2078 | 2113 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 11/13/23 | Mon 11/13/23 | 2112 | 2115 |  | Tommy Werner
2079 | 2114 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q4 | 14 hrs | 30 days | Tue 1/2/24 | Tue 2/13/24
2080 | 2115 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Tue 1/2/24 | Tue 1/16/24 | 2113 | 2116 |  | Tommy Werner,Gabriela Gibson
2081 | 2116 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Wed 1/17/24 | Tue 1/30/24 | 2115 | 2117 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2082 | 2117 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Wed 1/31/24 | Tue 2/13/24 | 2116 | 2118 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2083 | 2118 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Tue 2/13/24 | Tue 2/13/24 | 2117 | 2130 |  | Tommy Werner
2084 | 2119 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 24-25 | 14 hrs | 30 days | Wed 5/1/24 | Wed 6/12/24
2085 | 2120 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 24-25 - Create | 4 hrs | 10 days | Wed 5/1/24 | Tue 5/14/24 |  | 2121 |  | Tommy Werner,Gabriela Gibson
2086 | 2121 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 24-25 - Collaborative Review and Update | 4 hrs | 10 days | Wed 5/15/24 | Wed 5/29/24 | 2120 | 2122 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2087 | 2122 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 24-25 - Final Review and Edit | 6 hrs | 10 days | Thu 5/30/24 | Wed 6/12/24 | 2121 | 2123 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2088 | 2123 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 2122 | 2150 |  | Tommy Werner
2089 | 2124 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 24-25 | 14 hrs | 40 days | Thu 6/1/23 | Thu 7/27/23
2090 | 2125 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 24-25 - Create | 4 hrs | 20 days | Thu 6/1/23 | Wed 6/28/23 |  | 2126 |  | Tommy Werner,Gabriela Gibson
2091 | 2126 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 24-25 - Collaborative Review and Update | 4 hrs | 10 days | Thu 6/29/23 | Thu 7/13/23 | 2125 | 2127 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2092 | 2127 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 24-25 - Final Review and Edit | 6 hrs | 10 days | Fri 7/14/23 | Thu 7/27/23 | 2126 | 2128 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2093 | 2128 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | Thu 7/27/23 | Thu 7/27/23 | 2127 | 2155 |  | Tommy Werner
2094 | 2129 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q1 | 14 hrs | 30 days | Mon 6/3/24 | Mon 7/15/24
2095 | 2130 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 2118 | 2131 |  | Tommy Werner,Gabriela Gibson
2096 | 2131 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Mon 6/17/24 | Fri 6/28/24 | 2130 | 2132 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2097 | 2132 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 2131 | 2133 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2098 | 2133 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 7/15/24 | Mon 7/15/24 | 2132 | 2135SS-10 days |  | Tommy Werner
2099 | 2134 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q2 | 14 hrs | 30 days | Mon 7/1/24 | Mon 8/12/24
2100 | 2135 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 2133SS-10 days | 2136 |  | Tommy Werner,Gabriela Gibson
2101 | 2136 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Tue 7/16/24 | Mon 7/29/24 | 2135 | 2137 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2102 | 2137 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Tue 7/30/24 | Mon 8/12/24 | 2136 | 2138 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2103 | 2138 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 8/12/24 | Mon 8/12/24 | 2137 | 2140 |  | Tommy Werner
2104 | 2139 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q3 | 14 hrs | 30 days | Tue 10/1/24 | Tue 11/12/24
2105 | 2140 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Tue 10/1/24 | Mon 10/14/24 | 2138 | 2141 |  | Tommy Werner,Gabriela Gibson
2106 | 2141 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Tue 10/15/24 | Mon 10/28/24 | 2140 | 2142 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2107 | 2142 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Tue 10/29/24 | Tue 11/12/24 | 2141 | 2143 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2108 | 2143 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Tue 11/12/24 | Tue 11/12/24 | 2142 | 2145 |  | Tommy Werner
2109 | 2144 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q4 | 14 hrs | 30 days | Thu 1/2/25 | Thu 2/13/25
2110 | 2145 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Thu 1/2/25 | Wed 1/15/25 | 2143 | 2146 |  | Tommy Werner,Gabriela Gibson
2111 | 2146 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Thu 1/16/25 | Thu 1/30/25 | 2145 | 2147 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2112 | 2147 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Fri 1/31/25 | Thu 2/13/25 | 2146 | 2148 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2113 | 2148 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Thu 2/13/25 | Thu 2/13/25 | 2147 | 2160 |  | Tommy Werner
2114 | 2149 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 25-26 | 14 hrs | 30 days | Thu 5/1/25 | Thu 6/12/25
2115 | 2150 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 25-26 - Create | 4 hrs | 10 days | Thu 5/1/25 | Wed 5/14/25 | 2123 | 2151 |  | Tommy Werner,Gabriela Gibson
2116 | 2151 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 25-26 - Collaborative Review and Update | 4 hrs | 10 days | Thu 5/15/25 | Thu 5/29/25 | 2150 | 2152 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2117 | 2152 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 25-26 - Final Review and Edit | 6 hrs | 10 days | Fri 5/30/25 | Thu 6/12/25 | 2151 | 2153 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2118 | 2153 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | Thu 6/12/25 | Thu 6/12/25 | 2152 | 2180 |  | Tommy Werner
2119 | 2154 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 25-26 | 14 hrs | 40 days | Mon 6/3/24 | Mon 7/29/24
2120 | 2155 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 25-26 - Create | 4 hrs | 20 days | Mon 6/3/24 | Fri 6/28/24 | 2128 | 2156 |  | Tommy Werner,Gabriela Gibson
2121 | 2156 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 25-26 - Collaborative Review and Update | 4 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24 | 2155 | 2157 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2122 | 2157 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 25-26 - Final Review and Edit | 6 hrs | 10 days | Tue 7/16/24 | Mon 7/29/24 | 2156 | 2158 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2123 | 2158 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | Mon 7/29/24 | Mon 7/29/24 | 2157 | 2185 |  | Tommy Werner
2124 | 2159 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q1 | 14 hrs | 30 days | Mon 6/2/25 | Mon 7/14/25
2125 | 2160 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Mon 6/2/25 | Fri 6/13/25 | 2148 | 2161 |  | Tommy Werner,Gabriela Gibson
2126 | 2161 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Mon 6/16/25 | Fri 6/27/25 | 2160 | 2162 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2127 | 2162 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Mon 6/30/25 | Mon 7/14/25 | 2161 | 2163 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2128 | 2163 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 7/14/25 | Mon 7/14/25 | 2162 | 2165FS-9 days |  | Tommy Werner
2129 | 2164 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q2 | 14 hrs | 30 days | Tue 7/1/25 | Tue 8/12/25
2130 | 2165 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Tue 7/1/25 | Tue 7/15/25 | 2163FS-9 days | 2166 |  | Tommy Werner,Gabriela Gibson
2131 | 2166 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Wed 7/16/25 | Tue 7/29/25 | 2165 | 2167 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2132 | 2167 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Wed 7/30/25 | Tue 8/12/25 | 2166 | 2168 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2133 | 2168 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Tue 8/12/25 | Tue 8/12/25 | 2167 | 2170 |  | Tommy Werner
2134 | 2169 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q3 | 14 hrs | 30 days | Wed 10/1/25 | Wed 11/12/25
2135 | 2170 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Wed 10/1/25 | Tue 10/14/25 | 2168 | 2171 |  | Tommy Werner,Gabriela Gibson
2136 | 2171 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Wed 10/15/25 | Tue 10/28/25 | 2170 | 2172 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2137 | 2172 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Wed 10/29/25 | Wed 11/12/25 | 2171 | 2173 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2138 | 2173 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Wed 11/12/25 | Wed 11/12/25 | 2172 | 2175 |  | Tommy Werner
2139 | 2174 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q4 | 14 hrs | 30 days | Fri 1/2/26 | Fri 2/13/26
2140 | 2175 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Fri 1/2/26 | Thu 1/15/26 | 2173 | 2176 |  | Tommy Werner,Gabriela Gibson
2141 | 2176 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Fri 1/16/26 | Fri 1/30/26 | 2175 | 2177 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2142 | 2177 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Mon 2/2/26 | Fri 2/13/26 | 2176 | 2178 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2143 | 2178 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Fri 2/13/26 | Fri 2/13/26 | 2177 | 2190 |  | Tommy Werner
2144 | 2179 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 26-27 | 14 hrs | 30 days | Fri 5/1/26 | Fri 6/12/26
2145 | 2180 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 26-27 - Create | 4 hrs | 10 days | Fri 5/1/26 | Thu 5/14/26 | 2153 | 2181 |  | Tommy Werner,Gabriela Gibson
2146 | 2181 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 26-27 - Collaborative Review and Update | 4 hrs | 10 days | Fri 5/15/26 | Fri 5/29/26 | 2180 | 2182 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2147 | 2182 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 26-27 - Final Review and Edit | 6 hrs | 10 days | Mon 6/1/26 | Fri 6/12/26 | 2181 | 2183 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2148 | 2183 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | Fri 6/12/26 | Fri 6/12/26 | 2182 |  |  | Tommy Werner
2149 | 2184 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 26-27 | 14 hrs | 40 days | Mon 6/2/25 | Mon 7/28/25
2150 | 2185 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 26-27 - Create | 4 hrs | 20 days | Mon 6/2/25 | Fri 6/27/25 | 2158 | 2186 |  | Tommy Werner,Gabriela Gibson
2151 | 2186 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 26-27 - Collaborative Review and Update | 4 hrs | 10 days | Mon 6/30/25 | Mon 7/14/25 | 2185 | 2187 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2152 | 2187 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 26-27 - Final Review and Edit | 6 hrs | 10 days | Tue 7/15/25 | Mon 7/28/25 | 2186 | 2188 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2153 | 2188 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | Mon 7/28/25 | Mon 7/28/25 | 2187 |  |  | Tommy Werner
2154 | 2189 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q1 | 14 hrs | 30 days | Mon 6/1/26 | Mon 7/13/26
2155 | 2190 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | Mon 6/1/26 | Fri 6/12/26 | 2178 | 2191 |  | Tommy Werner,Gabriela Gibson
2156 | 2191 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Mon 6/15/26 | Fri 6/26/26 | 2190 | 2192 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2157 | 2192 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Mon 6/29/26 | Mon 7/13/26 | 2191 | 2193 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2158 | 2193 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 7/13/26 | Mon 7/13/26 | 2192 | 2195FS-8 days |  | Tommy Werner
2159 | 2194 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q2 | 14 hrs | 30 days | Wed 7/1/26 | Wed 8/12/26
2160 | 2195 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | Wed 7/1/26 | Wed 7/15/26 | 2193FS-8 days | 2196 |  | Tommy Werner,Gabriela Gibson
2161 | 2196 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Thu 7/16/26 | Wed 7/29/26 | 2195 | 2197 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2162 | 2197 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Thu 7/30/26 | Wed 8/12/26 | 2196 | 2198 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2163 | 2198 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Wed 8/12/26 | Wed 8/12/26 | 2197 | 2200 |  | Tommy Werner
2164 | 2199 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q3 | 14 hrs | 30 days | Thu 10/1/26 | Thu 11/12/26
2165 | 2200 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | Thu 10/1/26 | Wed 10/14/26 | 2198 | 2201 |  | Tommy Werner,Gabriela Gibson
2166 | 2201 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Thu 10/15/26 | Wed 10/28/26 | 2200 | 2202 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2167 | 2202 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Thu 10/29/26 | Thu 11/12/26 | 2201 | 2203 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2168 | 2203 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Thu 11/12/26 | Thu 11/12/26 | 2202 | 2205 |  | Tommy Werner
2169 | 2204 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q4 | 14 hrs | 30 days | Mon 1/4/27 | Mon 2/15/27
2170 | 2205 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | Mon 1/4/27 | Fri 1/15/27 | 2203 | 2206 |  | Tommy Werner,Gabriela Gibson
2171 | 2206 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | Tue 1/19/27 | Mon 2/1/27 | 2205 | 2207 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2172 | 2207 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | Tue 2/2/27 | Mon 2/15/27 | 2206 | 2208 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2173 | 2208 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | Mon 2/15/27 | Mon 2/15/27 | 2207 |  |  | Tommy Werner
2174 | 2209 | Future Task | [5 empty] | Project Resources | 1,012 hrs | 1131 days | Fri 6/30/23 | Tue 12/28/27
2175 | 2210 | Future Task |  |  |  | Tommy Werner |  | Project Management Plan | 462 hrs | 1045 days | Wed 11/1/23 | Tue 12/28/27
2176 | 2211 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2023 | 54 hrs | 38 days | Wed 11/1/23 | Thu 12/28/23
2177 | 2212 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Wed 11/1/23 | Fri 12/1/23 |  | 2213 |  | Joy Schneider,Tommy Werner,Francisca Li,Jenifer Hartsfield,Gabriela Gibson
2178 | 2213 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | Mon 12/4/23 | Fri 12/15/23 | 2212 | 2214 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2179 | 2214 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | Mon 12/18/23 | Fri 12/22/23 | 2213 | 2215 |  | Jimmy Cox
2180 | 2215 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 4 hrs | 3 days | Tue 12/26/23 | Thu 12/28/23 | 2214 | 2217 |  | Tatiana Eubanks
2181 | 2216 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2024 | 51 hrs | 38 days | Fri 5/3/24 | Wed 6/26/24
2182 | 2217 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Fri 5/3/24 | Fri 5/31/24 | 2215 | 2218 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2183 | 2218 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24 | 2217 | 2219 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2184 | 2219 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | Mon 6/17/24 | Fri 6/21/24 | 2218 | 2220 |  | Jimmy Cox
2185 | 2220 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Mon 6/24/24 | Wed 6/26/24 | 2219 | 2222 |  | Tatiana Eubanks
2186 | 2221 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2024 | 51 hrs | 38 days | Mon 11/4/24 | Tue 12/31/24
2187 | 2222 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/4/24 | Wed 12/4/24 | 2220 | 2223 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2188 | 2223 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | Thu 12/5/24 | Wed 12/18/24 | 2222 | 2224 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2189 | 2224 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | Thu 12/19/24 | Thu 12/26/24 | 2223 | 2225 |  | Jimmy Cox
2190 | 2225 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Fri 12/27/24 | Tue 12/31/24 | 2224 | 2227 |  | Tatiana Eubanks
2191 | 2226 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2025 | 51 hrs | 38 days | Fri 5/2/25 | Wed 6/25/25
2192 | 2227 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Fri 5/2/25 | Fri 5/30/25 | 2225 | 2228 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2193 | 2228 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | Mon 6/2/25 | Fri 6/13/25 | 2227 | 2229 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2194 | 2229 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | Mon 6/16/25 | Fri 6/20/25 | 2228 | 2230 |  | Jimmy Cox
2195 | 2230 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Mon 6/23/25 | Wed 6/25/25 | 2229 | 2232 |  | Tatiana Eubanks
2196 | 2231 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2025 | 51 hrs | 38 days | Mon 11/3/25 | Tue 12/30/25
2197 | 2232 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/3/25 | Wed 12/3/25 | 2230 | 2233 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2198 | 2233 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | Thu 12/4/25 | Wed 12/17/25 | 2232 | 2234 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2199 | 2234 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | Thu 12/18/25 | Wed 12/24/25 | 2233 | 2235 |  | Jimmy Cox
2200 | 2235 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Fri 12/26/25 | Tue 12/30/25 | 2234 | 2237 |  | Tatiana Eubanks
2201 | 2236 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2026 | 51 hrs | 38 days | Fri 5/1/26 | Wed 6/24/26
2202 | 2237 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Fri 5/1/26 | Fri 5/29/26 | 2235 | 2238 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2203 | 2238 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | Mon 6/1/26 | Fri 6/12/26 | 2237 | 2239 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2204 | 2239 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | Mon 6/15/26 | Fri 6/19/26 | 2238 | 2240 |  | Jimmy Cox
2205 | 2240 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Mon 6/22/26 | Wed 6/24/26 | 2239 | 2242 |  | Tatiana Eubanks
2206 | 2241 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2026 | 51 hrs | 38 days | Mon 11/2/26 | Tue 12/29/26
2207 | 2242 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/2/26 | Wed 12/2/26 | 2240 | 2243 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2208 | 2243 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | Thu 12/3/26 | Wed 12/16/26 | 2242 | 2244 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2209 | 2244 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | Thu 12/17/26 | Wed 12/23/26 | 2243 | 2245 |  | Jimmy Cox
2210 | 2245 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Thu 12/24/26 | Tue 12/29/26 | 2244 | 2247 |  | Tatiana Eubanks
2211 | 2246 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2027 | 51 hrs | 38 days | Mon 5/3/27 | Thu 6/24/27
2212 | 2247 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 5/3/27 | Fri 5/28/27 | 2245 | 2248 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2213 | 2248 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | Tue 6/1/27 | Mon 6/14/27 | 2247 | 2249 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2214 | 2249 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | Tue 6/15/27 | Mon 6/21/27 | 2248 | 2250 |  | Jimmy Cox
2215 | 2250 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Tue 6/22/27 | Thu 6/24/27 | 2249 | 2252 |  | Tatiana Eubanks
2216 | 2251 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2027 | 51 hrs | 38 days | Mon 11/1/27 | Tue 12/28/27
2217 | 2252 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | Mon 11/1/27 | Wed 12/1/27 | 2250 | 2253 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2218 | 2253 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | Thu 12/2/27 | Wed 12/15/27 | 2252 | 2254 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2219 | 2254 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | Thu 12/16/27 | Wed 12/22/27 | 2253 | 2255 |  | Jimmy Cox
2220 | 2255 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | Thu 12/23/27 | Tue 12/28/27 | 2254 |  |  | Tatiana Eubanks
2221 | 2256 | Future Task |  |  |  | Dusti Kincl |  | Florida PALM Style Guide | 104 hrs | 910 days | Wed 11/1/23 | Mon 6/14/27
2222 | 2257 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 23-24 | 13 hrs | 30 days | Wed 11/1/23 | Fri 12/15/23
2223 | 2258 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Wed 11/1/23 | Wed 11/22/23 |  | 2259 |  | Tatiana Eubanks,Elizabeth Gabert
2224 | 2259 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | Mon 11/27/23 | Fri 12/8/23 | 2258 | 2260 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2225 | 2260 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | Mon 12/11/23 | Fri 12/15/23 | 2259 | 2262 |  | Jimmy Cox
2226 | 2261 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 23-24 | 13 hrs | 30 days | Wed 5/1/24 | Wed 6/12/24
2227 | 2262 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Wed 5/1/24 | Tue 5/21/24 | 2260 | 2263 |  | Tatiana Eubanks,Elizabeth Gabert
2228 | 2263 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | Wed 5/22/24 | Wed 6/5/24 | 2262 | 2264 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2229 | 2264 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | Thu 6/6/24 | Wed 6/12/24 | 2263 | 2266 |  | Jimmy Cox
2230 | 2265 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 24-25 | 13 hrs | 30 days | Mon 11/4/24 | Wed 12/18/24
2231 | 2266 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 11/4/24 | Mon 11/25/24 | 2264 | 2267 |  | Tatiana Eubanks,Elizabeth Gabert
2232 | 2267 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | Tue 11/26/24 | Wed 12/11/24 | 2266 | 2268 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2233 | 2268 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | Thu 12/12/24 | Wed 12/18/24 | 2267 | 2270 |  | Jimmy Cox
2234 | 2269 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 24-25 | 13 hrs | 30 days | Thu 5/1/25 | Thu 6/12/25
2235 | 2270 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Thu 5/1/25 | Wed 5/21/25 | 2268 | 2271 |  | Tatiana Eubanks,Elizabeth Gabert
2236 | 2271 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | Thu 5/22/25 | Thu 6/5/25 | 2270 | 2272 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2237 | 2272 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | Fri 6/6/25 | Thu 6/12/25 | 2271 | 2274 |  | Jimmy Cox
2238 | 2273 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 25-26 | 13 hrs | 30 days | Mon 11/3/25 | Wed 12/17/25
2239 | 2274 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 11/3/25 | Mon 11/24/25 | 2272 | 2275 |  | Tatiana Eubanks,Elizabeth Gabert
2240 | 2275 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | Tue 11/25/25 | Wed 12/10/25 | 2274 | 2276 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2241 | 2276 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | Thu 12/11/25 | Wed 12/17/25 | 2275 | 2278 |  | Jimmy Cox
2242 | 2277 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 25-26 | 13 hrs | 30 days | Mon 4/6/26 | Fri 5/15/26
2243 | 2278 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 4/6/26 | Fri 4/24/26 | 2276 | 2279 |  | Tatiana Eubanks,Elizabeth Gabert
2244 | 2279 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | Mon 4/27/26 | Fri 5/8/26 | 2278 | 2280 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2245 | 2280 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | Mon 5/11/26 | Fri 5/15/26 | 2279 | 2282 |  | Jimmy Cox
2246 | 2281 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 26-27 | 13 hrs | 30 days | Mon 11/2/26 | Wed 12/16/26
2247 | 2282 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 11/2/26 | Mon 11/23/26 | 2280 | 2283 |  | Tatiana Eubanks,Elizabeth Gabert
2248 | 2283 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | Tue 11/24/26 | Wed 12/9/26 | 2282 | 2284 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2249 | 2284 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | Thu 12/10/26 | Wed 12/16/26 | 2283 | 2286 |  | Jimmy Cox
2250 | 2285 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 26-27 | 13 hrs | 30 days | Mon 5/3/27 | Mon 6/14/27
2251 | 2286 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | Mon 5/3/27 | Fri 5/21/27 | 2284 | 2287 |  | Tatiana Eubanks,Elizabeth Gabert
2252 | 2287 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | Mon 5/24/27 | Mon 6/7/27 | 2286 | 2288 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2253 | 2288 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | Tue 6/8/27 | Mon 6/14/27 | 2287 |  |  | Jimmy Cox
2254 | 2289 | Future Task | [5 empty] | Project Team Orientation Guide | 238 hrs | 252 days | Fri 6/30/23 | Fri 6/28/24
6683 | 2290 | Future Task |  |  | WP401 | Joy Schneider |  | WP401 - Project Orientation Guide | 88 hrs | 50 days | Fri 6/30/23 | Mon 9/11/23
6684 | 2291 | Future Task |  |  | WP401 | Joy Schneider | Create | WPED WP401 - Project Orientation Guide - Create | 8 hrs | 10 days | Fri 6/30/23 | Fri 7/14/23 | 28 | 2292 |  | Joy Schneider
6685 | 2292 | Future Task |  |  | WP401 | Joy Schneider | Submit | WPED WP401 - Project Orientation Guide - Submit | 0 hrs | 0 days | Fri 7/14/23 | Fri 7/14/23 | 2291 | 2293 |  | Joy Schneider
6686 | 2293 | Future Task |  |  | WP401 | Joy Schneider | Review | WPED WP401 - Project Orientation Guide - Review | 16 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 | 2292 | 2294 |  | Joy Schneider,Jimmy Cox,Angie Robertson,Sean Buchanan
6687 | 2294 | Future Task |  |  | WP401 | Joy Schneider | Approve | WPED WP401 - Project Orientation Guide - Approve | 0 hrs | 0 days | Fri 7/28/23 | Fri 7/28/23 | 2293 | 2295 |  | Jimmy Cox
6688 | 2295 | Future Task |  |  | WP401 | Joy Schneider |  | Update Project Team Orientation Guide | 10 hrs | 5 days | Mon 7/31/23 | Fri 8/4/23 | 2294 | 2296 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
6689 | 2296 | Future Task |  |  | WP401 | Joy Schneider |  | Project Team Orientation Guide - Collaborative Review and Update | 10 hrs | 5 days | Mon 8/7/23 | Fri 8/11/23 | 2295 | 2297 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
6690 | 2297 | Future Task |  |  | WP401 | Joy Schneider |  | Project Team Orientation Guide - Final Review and Update | 20 hrs | 5 days | Mon 8/14/23 | Fri 8/18/23 | 2296 | 2298 |  | Angie Robertson[25%],Jimmy Cox[25%]
6691 | 2298 | Future Task |  |  | WP401 | Joy Schneider | Submit | WP WP401 - Project Orientation Guide - Submit | 0 hrs | 0 days | Fri 8/18/23 | Fri 8/18/23 | 2297 | 2299 |  | Joy Schneider
6692 | 2299 | Future Task |  |  | WP401 | Joy Schneider | Review | WP WP401 - Project Orientation Guide - Collaborative Review & Update | 12 hrs | 10 days | Mon 8/21/23 | Fri 9/1/23 | 2298 | 2300 |  | Joy Schneider,Jimmy Cox,Angie Robertson
6693 | 2300 | Future Task |  |  | WP401 | Joy Schneider | Review | WP WP401 - Project Orientation Guide - Final Review & Edits | 12 hrs | 5 days | Tue 9/5/23 | Mon 9/11/23 | 2299 | 2301 |  | Joy Schneider,Jimmy Cox,Angie Robertson
6694 | 2301 | Future Task |  |  | WP401 | Joy Schneider | Approve | WP WP401 - Project Orientation Guide - Approve | 0 hrs | 0 days | Mon 9/11/23 | Mon 9/11/23 | 2300 | 2303FS-6 days | 2023-10-01 | Jimmy Cox
2255 | 2302 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q1 | 30 hrs | 15 days | Fri 9/1/23 | Fri 9/22/23
2257 | 2303 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 2301FS-6 days | 2304 |  | Jenifer Hartsfield,Gabriela Gibson
2258 | 2304 | Future Task |  |  |  | Julian Gotreaux | Review | FPO - Collaborative Review and Update | 10 hrs | 5 days | Mon 9/11/23 | Fri 9/15/23 | 2303 | 2305 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2259 | 2305 | Future Task |  |  |  | Julian Gotreaux | Review | FPO - Final Review and Update | 10 hrs | 5 days | Mon 9/18/23 | Fri 9/22/23 | 2304 | 23072407 |  | Angie Robertson,Jimmy Cox
2260 | 2306 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q2 | 40 hrs | 20 days | Fri 12/1/23 | Fri 12/29/23
2261 | 2307 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | Fri 12/1/23 | Thu 12/7/23 | 2305 | 2308 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2262 | 2308 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Fri 12/8/23 | Thu 12/14/23 | 2307 | 2309 |  | Jenifer Hartsfield,Gabriela Gibson
2263 | 2309 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review and Update | 10 hrs | 5 days | Fri 12/15/23 | Thu 12/21/23 | 2308 | 2310 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2264 | 2310 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review and Update | 10 hrs | 5 days | Fri 12/22/23 | Fri 12/29/23 | 2309 | 2312 |  | Angie Robertson,Jimmy Cox
2265 | 2311 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q3 | 40 hrs | 20 days | Fri 3/1/24 | Thu 3/28/24
2266 | 2312 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | Fri 3/1/24 | Thu 3/7/24 | 2310 | 2313 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2267 | 2313 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Fri 3/8/24 | Thu 3/14/24 | 2312 | 2314 |  | Jenifer Hartsfield,Gabriela Gibson
2268 | 2314 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review and Update | 10 hrs | 5 days | Fri 3/15/24 | Thu 3/21/24 | 2313 | 2315 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2269 | 2315 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review and Update | 10 hrs | 5 days | Fri 3/22/24 | Thu 3/28/24 | 2314 | 2317 |  | Angie Robertson,Jimmy Cox
2270 | 2316 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q4 | 40 hrs | 20 days | Mon 6/3/24 | Fri 6/28/24
2271 | 2317 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | Mon 6/3/24 | Fri 6/7/24 | 2315 | 2318 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2272 | 2318 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | Mon 6/10/24 | Fri 6/14/24 | 2317 | 2319 |  | Jenifer Hartsfield,Gabriela Gibson
2273 | 2319 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review and Update | 10 hrs | 5 days | Mon 6/17/24 | Fri 6/21/24 | 2318 | 2320 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2274 | 2320 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review and Update | 10 hrs | 5 days | Mon 6/24/24 | Fri 6/28/24 | 2319 |  |  | Angie Robertson,Jimmy Cox
2275 | 2321 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 23-24 | 28 hrs | 134 days | Mon 7/17/23 | Mon 1/29/24
2276 | 2322 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 23-24 Q1 | 4 hrs | 10 days | Mon 7/17/23 | Fri 7/28/23 |  | 23232324 |  | Gabriela Gibson[5%]
2277 | 2323 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 23-24 Q3 | 4 hrs | 10 days | Tue 1/16/24 | Mon 1/29/24 | 2322 | 2330 |  | Gabriela Gibson[5%]
2278 | 2324 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 23-24 | 4 hrs | 10 days | Tue 8/15/23 | Mon 8/28/23 | 2322 | 2325 |  | Jenifer Hartsfield[5%]
2279 | 2325 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 23-24 | 4 hrs | 10 days | Fri 9/15/23 | Thu 9/28/23 | 2324 | 2326 |  | Tommy Werner[5%]
2280 | 2326 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 23-24 | 4 hrs | 10 days | Mon 10/16/23 | Fri 10/27/23 | 2325 | 2327 |  | Gabriela Gibson[5%]
2281 | 2327 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 23-24 | 4 hrs | 10 days | Wed 11/15/23 | Thu 11/30/23 | 2326 | 2328 |  | Tommy Werner[5%]
2282 | 2328 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 23-24 | 4 hrs | 10 days | Fri 12/15/23 | Fri 12/29/23 | 2327 | 2332 |  | Tommy Werner[5%]
2283 | 2329 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 24-25 | 28 hrs | 136 days | Mon 7/15/24 | Wed 1/29/25
2284 | 2330 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 24-25 Q1 | 4 hrs | 10 days | Mon 7/15/24 | Fri 7/26/24 | 2323 | 2331 |  | Gabriela Gibson[5%]
2285 | 2331 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 24-25 Q3 | 4 hrs | 10 days | Wed 1/15/25 | Wed 1/29/25 | 2330 | 2338 |  | Gabriela Gibson[5%]
2286 | 2332 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 24-25 | 4 hrs | 10 days | Thu 8/15/24 | Wed 8/28/24 | 2328 | 2333 |  | Jenifer Hartsfield[5%]
2287 | 2333 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 24-25 | 4 hrs | 10 days | Mon 9/16/24 | Fri 9/27/24 | 2332 | 2334 |  | Tommy Werner[5%]
2288 | 2334 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 24-25 | 4 hrs | 10 days | Tue 10/15/24 | Mon 10/28/24 | 2333 | 2335 |  | Gabriela Gibson[5%]
2289 | 2335 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 24-25 | 4 hrs | 10 days | Fri 11/15/24 | Mon 12/2/24 | 2334 | 2336 |  | Tommy Werner[5%]
2290 | 2336 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 24-25 | 4 hrs | 10 days | Mon 12/16/24 | Mon 12/30/24 | 2335 | 2340 |  | Tommy Werner[5%]
2291 | 2337 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 25-26 | 28 hrs | 136 days | Tue 7/15/25 | Thu 1/29/26
2292 | 2338 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 25-26 Q1 | 4 hrs | 10 days | Tue 7/15/25 | Mon 7/28/25 | 2331 | 2339 |  | Gabriela Gibson[5%]
2293 | 2339 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 25-26 Q3 | 4 hrs | 10 days | Thu 1/15/26 | Thu 1/29/26 | 2338 | 2346 |  | Gabriela Gibson[5%]
2294 | 2340 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 25-26 | 4 hrs | 10 days | Fri 8/15/25 | Thu 8/28/25 | 2336 | 2341 |  | Jenifer Hartsfield[5%]
2295 | 2341 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 25-26 | 4 hrs | 10 days | Mon 9/15/25 | Fri 9/26/25 | 2340 | 2342 |  | Tommy Werner[5%]
2296 | 2342 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 25-26 | 4 hrs | 10 days | Wed 10/15/25 | Tue 10/28/25 | 2341 | 2343 |  | Gabriela Gibson[5%]
2297 | 2343 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 25-26 | 4 hrs | 10 days | Mon 11/17/25 | Tue 12/2/25 | 2342 | 2344 |  | Tommy Werner[5%]
2298 | 2344 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 25-26 | 4 hrs | 10 days | Mon 12/15/25 | Mon 12/29/25 | 2343 | 2348 |  | Tommy Werner[5%]
2299 | 2345 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 26-27 | 28 hrs | 136 days | Wed 7/15/26 | Fri 1/29/27
2300 | 2346 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 26-27 Q1 | 4 hrs | 10 days | Wed 7/15/26 | Tue 7/28/26 | 2339 | 2347 |  | Gabriela Gibson
2301 | 2347 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 26-27 Q3 | 4 hrs | 10 days | Fri 1/15/27 | Fri 1/29/27 | 2346 |  |  | Gabriela Gibson
2302 | 2348 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 26-27 | 4 hrs | 10 days | Mon 8/17/26 | Fri 8/28/26 | 2344 | 2349 |  | Jenifer Hartsfield
2303 | 2349 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 26-27 | 4 hrs | 10 days | Tue 9/15/26 | Mon 9/28/26 | 2348 | 2350 |  | Tommy Werner
2304 | 2350 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 26-27 | 4 hrs | 10 days | Thu 10/15/26 | Wed 10/28/26 | 2349 | 2351 |  | Gabriela Gibson
2305 | 2351 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 26-27 | 4 hrs | 10 days | Mon 11/16/26 | Tue 12/1/26 | 2350 | 2352 |  | Tommy Werner
2306 | 2352 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 26-27 | 4 hrs | 10 days | Tue 12/15/26 | Tue 12/29/26 | 2351 |  |  | Tommy Werner
2307 | 2353 | Future Task |  |  |  | Julian Gotreaux |  | Access Control | 96 hrs | 965 days | Tue 8/15/23 | Mon 6/14/27
2308 | 2354 | Future Task |  |  |  | Julian Gotreaux |  | SharePoint Access Control | 32 hrs | 965 days | Tue 8/15/23 | Mon 6/14/27
2309 | 2355 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q1 | 2 hrs | 10 days | Tue 8/15/23 | Mon 8/28/23 |  | 2356 |  | Jenifer Hartsfield,Gabriela Gibson
2310 | 2356 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q2 | 2 hrs | 10 days | Wed 11/15/23 | Thu 11/30/23 | 2355 | 2357 |  | Jenifer Hartsfield,Gabriela Gibson
2311 | 2357 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q3 | 2 hrs | 10 days | Thu 2/15/24 | Wed 2/28/24 | 2356 | 2358 |  | Jenifer Hartsfield,Gabriela Gibson
2312 | 2358 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q4 | 2 hrs | 10 days | Wed 5/15/24 | Wed 5/29/24 | 2357 | 2359 |  | Jenifer Hartsfield,Gabriela Gibson
2313 | 2359 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q1 | 2 hrs | 10 days | Thu 8/15/24 | Wed 8/28/24 | 2358 | 2360 |  | Jenifer Hartsfield,Gabriela Gibson
2314 | 2360 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q2 | 2 hrs | 10 days | Fri 11/15/24 | Mon 12/2/24 | 2359 | 2361 |  | Jenifer Hartsfield,Gabriela Gibson
2315 | 2361 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q3 | 2 hrs | 10 days | Mon 2/17/25 | Fri 2/28/25 | 2360 | 2362 |  | Jenifer Hartsfield,Gabriela Gibson
2316 | 2362 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q4 | 2 hrs | 10 days | Thu 5/15/25 | Thu 5/29/25 | 2361 | 2363 |  | Jenifer Hartsfield,Gabriela Gibson
2317 | 2363 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q1 | 2 hrs | 10 days | Fri 8/15/25 | Thu 8/28/25 | 2362 | 2364 |  | Jenifer Hartsfield,Gabriela Gibson
2318 | 2364 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q2 | 2 hrs | 10 days | Mon 11/17/25 | Tue 12/2/25 | 2363 | 2365 |  | Jenifer Hartsfield,Gabriela Gibson
2319 | 2365 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q3 | 2 hrs | 10 days | Mon 2/16/26 | Fri 2/27/26 | 2364 | 2366 |  | Jenifer Hartsfield,Gabriela Gibson
2320 | 2366 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q4 | 2 hrs | 10 days | Fri 5/15/26 | Fri 5/29/26 | 2365 | 2367 |  | Jenifer Hartsfield,Gabriela Gibson
2321 | 2367 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q1 | 2 hrs | 10 days | Mon 8/17/26 | Fri 8/28/26 | 2366 | 2368 |  | Jenifer Hartsfield,Gabriela Gibson
2322 | 2368 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q2 | 2 hrs | 10 days | Mon 11/16/26 | Tue 12/1/26 | 2367 | 2369 |  | Jenifer Hartsfield,Gabriela Gibson
2323 | 2369 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q3 | 2 hrs | 10 days | Mon 2/15/27 | Fri 2/26/27 | 2368 | 2370 |  | Jenifer Hartsfield,Gabriela Gibson
2324 | 2370 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q4 | 2 hrs | 20 days | Mon 5/17/27 | Mon 6/14/27 | 2369 |  |  | Jenifer Hartsfield,Gabriela Gibson
2325 | 2371 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2023 | 8 hrs | 35 days | Mon 8/28/23 | Mon 10/16/23
2326 | 2372 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Mon 8/28/23 | Fri 9/1/23 |  | 2373 |  | Daylin Reyes,Richard Saltford
2327 | 2373 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Tue 9/5/23 | Mon 9/18/23 | 2372 | 2374 |  | Nikki Klein
2328 | 2374 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Tue 9/19/23 | Mon 10/9/23 | 2373 | 2375 |  | Richard Saltford
2329 | 2375 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Tue 10/10/23 | Mon 10/16/23 | 2374 |  |  | Daylin Reyes
2330 | 2376 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2024 | 8 hrs | 35 days | Tue 2/27/24 | Mon 4/15/24
2331 | 2377 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 2/27/24 | Mon 3/4/24 |  | 2378 |  | Daylin Reyes,Richard Saltford
2332 | 2378 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Tue 3/5/24 | Mon 3/18/24 | 2377 | 2379 |  | Nikki Klein
2333 | 2379 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Tue 3/19/24 | Mon 4/8/24 | 2378 | 2380 |  | Richard Saltford
2334 | 2380 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Tue 4/9/24 | Mon 4/15/24 | 2379 | 2382 |  | Daylin Reyes
2335 | 2381 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2024 | 8 hrs | 35 days | Tue 8/27/24 | Tue 10/15/24
2336 | 2382 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 8/27/24 | Tue 9/3/24 | 2380 | 2383 |  | Daylin Reyes,Richard Saltford
2337 | 2383 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Wed 9/4/24 | Tue 9/17/24 | 2382 | 2384 |  | Nikki Klein
2338 | 2384 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Wed 9/18/24 | Tue 10/8/24 | 2383 | 2385 |  | Richard Saltford
2339 | 2385 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Wed 10/9/24 | Tue 10/15/24 | 2384 | 2387 |  | Daylin Reyes
2340 | 2386 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2025 | 8 hrs | 35 days | Tue 2/25/25 | Mon 4/14/25
2341 | 2387 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 2/25/25 | Mon 3/3/25 | 2385 | 2388 |  | Daylin Reyes,Richard Saltford
2342 | 2388 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Tue 3/4/25 | Mon 3/17/25 | 2387 | 2389 |  | Nikki Klein
2343 | 2389 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Tue 3/18/25 | Mon 4/7/25 | 2388 | 2390 |  | Richard Saltford
2344 | 2390 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Tue 4/8/25 | Mon 4/14/25 | 2389 | 2392 |  | Daylin Reyes
2345 | 2391 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2025 | 8 hrs | 35 days | Tue 8/26/25 | Tue 10/14/25
2346 | 2392 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 8/26/25 | Tue 9/2/25 | 2390 | 2393 |  | Daylin Reyes,Richard Saltford
2347 | 2393 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Wed 9/3/25 | Tue 9/16/25 | 2392 | 2394 |  | Nikki Klein
2348 | 2394 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Wed 9/17/25 | Tue 10/7/25 | 2393 | 2395 |  | Richard Saltford
2349 | 2395 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Wed 10/8/25 | Tue 10/14/25 | 2394 | 2397 |  | Daylin Reyes
2350 | 2396 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2026 | 8 hrs | 35 days | Tue 2/24/26 | Mon 4/13/26
2351 | 2397 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 2/24/26 | Mon 3/2/26 | 2395 | 2398 |  | Daylin Reyes,Richard Saltford
2352 | 2398 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Tue 3/3/26 | Mon 3/16/26 | 2397 | 2399 |  | Nikki Klein
2353 | 2399 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Tue 3/17/26 | Mon 4/6/26 | 2398 | 2400 |  | Richard Saltford
2354 | 2400 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Tue 4/7/26 | Mon 4/13/26 | 2399 | 2402 |  | Daylin Reyes
2355 | 2401 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2026 | 8 hrs | 35 days | Tue 8/25/26 | Tue 10/13/26
2356 | 2402 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 8/25/26 | Mon 8/31/26 | 2400 | 2403 |  | Daylin Reyes,Richard Saltford
2357 | 2403 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Tue 9/1/26 | Tue 9/15/26 | 2402 | 2404 |  | Nikki Klein
2358 | 2404 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Wed 9/16/26 | Tue 10/6/26 | 2403 | 2405 |  | Richard Saltford
2359 | 2405 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Wed 10/7/26 | Tue 10/13/26 | 2404 |  |  | Daylin Reyes
2360 | 2406 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2027 | 8 hrs | 35 days | Tue 2/23/27 | Mon 4/12/27
2361 | 2407 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | Tue 2/23/27 | Mon 3/1/27 | 2305 | 2408 |  | Daylin Reyes,Richard Saltford
2362 | 2408 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | Tue 3/2/27 | Mon 3/15/27 | 2407 | 2409 |  | Nikki Klein
2363 | 2409 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | Tue 3/16/27 | Mon 4/5/27 | 2408 | 2410 |  | Richard Saltford
2364 | 2410 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | Tue 4/6/27 | Mon 4/12/27 | 2409 |  |  | Daylin Reyes
2365 | 2411 | Late | [5 empty] | Proviso Requirements | 844 hrs | 1089 days | Mon 5/1/23 | Tue 8/24/27
2366 | 2412 | Future Task |  |  |  | Tommy Werner |  | Monthly Status Reporting | 192 hrs | 241 days | Tue 8/1/23 | Mon 7/15/24
2367 | 2413 | Future Task |  |  |  | Tommy Werner |  | July 2023 Monthly Status Reporting | 16 hrs | 11 days | Tue 8/1/23 | Tue 8/15/23
2368 | 2414 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | Tue 8/1/23 | Thu 8/10/23 |  | 2415SS,2416SS,2417SS |  | Tommy Werner,Gabriela Gibson
2369 | 2415 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 2414SS | 2418 |  | Tommy Werner,Joy Schneider,Francisca Li,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2370 | 2416 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | Tue 8/1/23 | Thu 8/10/23 | 2414SS | 2418 |  | Tommy Werner,Jenifer Hartsfield
2371 | 2417 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Tue 8/1/23 | Mon 8/14/23 | 2414SS | 2418 |  | Dusti Kincl,Nikki Klein
2372 | 2418 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Tue 8/15/23 | Tue 8/15/23 | 241724152416 | 2420 |  | Dusti Kincl,Jimmy Cox
2373 | 2419 | Future Task |  |  |  | Tommy Werner |  | August 2023 Monthly Status Reporting | 16 hrs | 10 days | Fri 9/1/23 | Fri 9/15/23
2374 | 2420 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 2418 | 2421SS,2422SS,2423SS,2424 |  | Tommy Werner,Gabriela Gibson
2375 | 2421 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Fri 9/1/23 | Thu 9/14/23 | 2420SS | 2424 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2376 | 2422 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 5 days | Fri 9/1/23 | Fri 9/8/23 | 2420SS | 2424 |  | Tommy Werner,Jenifer Hartsfield
2377 | 2423 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Fri 9/1/23 | Thu 9/14/23 | 2420SS | 2424 |  | Dusti Kincl,Nikki Klein
2378 | 2424 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 9/15/23 | Fri 9/15/23 | 2420242124222420 | 2426 |  | Dusti Kincl,Jimmy Cox
2379 | 2425 | Future Task |  |  |  | Tommy Werner |  | September 2023 Monthly Status Reporting | 16 hrs | 10 days | Mon 10/2/23 | Fri 10/13/23
2380 | 2426 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | Mon 10/2/23 | Tue 10/10/23 | 2424 | 2427SS,2428SS,2429SS,2430 |  | Tommy Werner,Gabriela Gibson
2381 | 2427 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Mon 10/2/23 | Thu 10/12/23 | 2426SS | 2430 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2382 | 2428 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | Mon 10/2/23 | Tue 10/10/23 | 2426SS | 2430 |  | Tommy Werner,Jenifer Hartsfield
2383 | 2429 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Mon 10/2/23 | Thu 10/12/23 | 2426SS | 2430 |  | Dusti Kincl,Nikki Klein
2384 | 2430 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 10/13/23 | Fri 10/13/23 | 2426242724282420 | 2432 |  | Dusti Kincl,Jimmy Cox
2385 | 2431 | Future Task |  |  |  | Tommy Werner |  | October 2023 Monthly Status Reporting | 16 hrs | 10 days | Wed 11/1/23 | Wed 11/15/23
2386 | 2432 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | Wed 11/1/23 | Thu 11/9/23 | 2430 | 2433SS,2434SS,2435SS,2436 |  | Tommy Werner,Gabriela Gibson
2387 | 2433 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Wed 11/1/23 | Tue 11/14/23 | 2432SS | 2436 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2388 | 2434 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | Wed 11/1/23 | Thu 11/9/23 | 2432SS | 2436 |  | Tommy Werner,Jenifer Hartsfield
2389 | 2435 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Wed 11/1/23 | Tue 11/14/23 | 2432SS | 2436 |  | Dusti Kincl,Nikki Klein
2390 | 2436 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Wed 11/15/23 | Wed 11/15/23 | 2432243324342430 | 2438 |  | Dusti Kincl,Jimmy Cox
2391 | 2437 | Future Task |  |  |  | Tommy Werner |  | November 2023 Monthly Status Reporting | 16 hrs | 11 days | Fri 12/1/23 | Fri 12/15/23
2392 | 2438 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | Fri 12/1/23 | Fri 12/8/23 | 2436 | 2439SS,2440SS,2441SS,2442 |  | Tommy Werner,Gabriela Gibson
2393 | 2439 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Fri 12/1/23 | Thu 12/14/23 | 2438SS | 2442 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2394 | 2440 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | Fri 12/1/23 | Fri 12/8/23 | 2438SS |  |  | Tommy Werner,Jenifer Hartsfield
2395 | 2441 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Fri 12/1/23 | Thu 12/14/23 | 2438SS | 2442 |  | Dusti Kincl,Nikki Klein
2396 | 2442 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 12/15/23 | Fri 12/15/23 | 243824392441 | 2444 |  | Dusti Kincl,Jimmy Cox
2397 | 2443 | Future Task |  |  |  | Tommy Werner |  | December 2023 Monthly Status Reporting | 16 hrs | 9 days | Tue 1/2/24 | Fri 1/12/24
2398 | 2444 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | Tue 1/2/24 | Tue 1/9/24 | 2442 | 2445SS,2448,2446SS,2447SS |  | Tommy Werner,Gabriela Gibson
2399 | 2445 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 8 days | Tue 1/2/24 | Thu 1/11/24 | 2444SS | 2448 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2400 | 2446 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | Tue 1/2/24 | Tue 1/9/24 | 2444SS | 2448 |  | Tommy Werner,Jenifer Hartsfield
2401 | 2447 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 8 days | Tue 1/2/24 | Thu 1/11/24 | 2444SS | 2448 |  | Dusti Kincl,Nikki Klein
2402 | 2448 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 1/12/24 | Fri 1/12/24 | 2444244524462440 | 2450 |  | Dusti Kincl,Jimmy Cox
2403 | 2449 | Future Task |  |  |  | Tommy Werner |  | January 2023 Monthly Status Reporting | 16 hrs | 11 days | Thu 2/1/24 | Thu 2/15/24
2404 | 2450 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | Thu 2/1/24 | Fri 2/9/24 | 2448 | 2451SS,2452SS,2453SS,2454 |  | Tommy Werner,Gabriela Gibson
2405 | 2451 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Thu 2/1/24 | Wed 2/14/24 | 2450SS | 2454 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2406 | 2452 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | Thu 2/1/24 | Fri 2/9/24 | 2450SS | 2454 |  | Tommy Werner,Jenifer Hartsfield
2407 | 2453 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Thu 2/1/24 | Wed 2/14/24 | 2450SS | 2454 |  | Dusti Kincl,Nikki Klein
2408 | 2454 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Thu 2/15/24 | Thu 2/15/24 | 2450245124522450 | 2456 |  | Dusti Kincl,Jimmy Cox
2409 | 2455 | Future Task |  |  |  | Tommy Werner |  | February 2024 Monthly Status Reporting | 16 hrs | 11 days | Fri 3/1/24 | Fri 3/15/24
2410 | 2456 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | Fri 3/1/24 | Fri 3/8/24 | 2454 | 2457SS,2458SS,2459SS,2460 |  | Tommy Werner,Gabriela Gibson
2411 | 2457 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 2456SS | 2460 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2412 | 2458 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | Fri 3/1/24 | Fri 3/8/24 | 2456SS | 2460 |  | Tommy Werner,Jenifer Hartsfield
2413 | 2459 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Fri 3/1/24 | Thu 3/14/24 | 2456SS | 2460 |  | Dusti Kincl,Nikki Klein
2414 | 2460 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 3/15/24 | Fri 3/15/24 | 2456245724582450 | 2462 |  | Dusti Kincl,Jimmy Cox
2415 | 2461 | Future Task |  |  |  | Tommy Werner |  | March 2024 Monthly Status Reporting | 16 hrs | 11 days | Mon 4/1/24 | Mon 4/15/24
2416 | 2462 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | Mon 4/1/24 | Wed 4/10/24 | 2460 | 2463SS,2464SS,2465SS,2466 |  | Tommy Werner,Gabriela Gibson
2417 | 2463 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Mon 4/1/24 | Fri 4/12/24 | 2462SS | 2466 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2418 | 2464 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | Mon 4/1/24 | Wed 4/10/24 | 2462SS | 2466 |  | Tommy Werner,Jenifer Hartsfield
2419 | 2465 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Mon 4/1/24 | Fri 4/12/24 | 2462SS | 2466 |  | Dusti Kincl,Nikki Klein
2420 | 2466 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Mon 4/15/24 | Mon 4/15/24 | 2462246324642460 | 2468 |  | Dusti Kincl,Jimmy Cox
2421 | 2467 | Future Task |  |  |  | Tommy Werner |  | April 2024 Monthly Status Reporting | 16 hrs | 11 days | Wed 5/1/24 | Wed 5/15/24
2422 | 2468 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | Wed 5/1/24 | Fri 5/10/24 | 2466 | 2469SS,2470SS,2471SS,2472 |  | Tommy Werner,Gabriela Gibson
2423 | 2469 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | Wed 5/1/24 | Tue 5/14/24 | 2468SS | 2472 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2424 | 2470 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | Wed 5/1/24 | Fri 5/10/24 | 2468SS | 2472 |  | Tommy Werner,Jenifer Hartsfield
2425 | 2471 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | Wed 5/1/24 | Tue 5/14/24 | 2468SS | 2472 |  | Dusti Kincl,Nikki Klein
2426 | 2472 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Wed 5/15/24 | Wed 5/15/24 | 2468246924702470 | 2474 |  | Dusti Kincl,Jimmy Cox
2427 | 2473 | Future Task |  |  |  | Tommy Werner |  | May 2024 Monthly Status Reporting | 16 hrs | 10 days | Mon 6/3/24 | Fri 6/14/24
2428 | 2474 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | Mon 6/3/24 | Mon 6/10/24 | 2472 | 2475SS,2476SS,2477SS,2478 |  | Tommy Werner,Gabriela Gibson
2429 | 2475 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Mon 6/3/24 | Thu 6/13/24 | 2474SS |  |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2430 | 2476 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | Mon 6/3/24 | Mon 6/10/24 | 2474SS | 2478 |  | Tommy Werner,Jenifer Hartsfield
2431 | 2477 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Mon 6/3/24 | Thu 6/13/24 | 2474SS | 2478 |  | Dusti Kincl,Nikki Klein
2432 | 2478 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Fri 6/14/24 | Fri 6/14/24 | 247424762477 | 2480 |  | Dusti Kincl,Jimmy Cox
2433 | 2479 | Future Task |  |  |  | Tommy Werner |  | June 2024 Monthly Status Reporting | 16 hrs | 10 days | Mon 7/1/24 | Mon 7/15/24
2434 | 2480 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | Mon 7/1/24 | Wed 7/10/24 | 2478 | 2481SS,2482SS,2483SS |  | Tommy Werner,Gabriela Gibson
2435 | 2481 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 2480SS | 2484 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2436 | 2482 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | Mon 7/1/24 | Wed 7/10/24 | 2480SS | 2484 |  | Tommy Werner,Jenifer Hartsfield
2437 | 2483 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | Mon 7/1/24 | Fri 7/12/24 | 2480SS | 2484 |  | Dusti Kincl,Nikki Klein
2438 | 2484 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | Mon 7/15/24 | Mon 7/15/24 | 248124822483 |  |  | Dusti Kincl,Jimmy Cox
9 | 2485 | Late | [5 empty] | Monthly Performance Reporting | 520 hrs | 1089 days | Mon 5/1/23 | Tue 8/24/27
6232 | 2486 | Late |  |  | D219 | Joy Schneider |  | D219 - Monthly Performance Report (April 2023) | 10 hrs | 17 days | Mon 5/1/23 | Tue 5/23/23
6364 | 2487 | Late |  |  | D219 | Joy Schneider | Create | Create April 2023 Monthly Performance Report | 3 hrs | 7 days | Mon 5/1/23 | Tue 5/9/23 | 1 | 2488 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6233 | 2488 | Late |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 5/10/23 | Wed 5/10/23 | 2487 | 2489 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6234 | 2489 | Late |  |  | D219 | Joy Schneider | Submit | DEL D219 - Monthly Performance Report (April 2023) - Submit | 0 hrs | 0 days | Wed 5/10/23 | Wed 5/10/23 | 2488 | 2490 |  | Joy Schneider
6235 | 2490 | Late |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Department QC | 1 hr | 7 days | Thu 5/11/23 | Fri 5/19/23 | 2489 | 2491 |  | Gabriela Gibson
6236 | 2491 | Late |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Contract Manager Review | 2 hrs | 2 days | Mon 5/22/23 | Tue 5/23/23 | 2490 | 2492 |  | Sean Buchanan
6237 | 2492 | Late |  |  | D219 | Joy Schneider | Accept | DEL D219 - Monthly Performance Report (April 2023) - Accept | 0 hrs | 0 days | Tue 5/23/23 | Tue 5/23/23 | 2491 | 2494 |  | Sean Buchanan
6238 | 2493 | Future Task |  |  | D225 | Joy Schneider |  | D225 - Monthly Performance Report (May 2023) | 10 hrs | 17 days | Thu 6/1/23 | Fri 6/23/23
6365 | 2494 | Future Task |  |  | D225 | Joy Schneider | Create | Create May 2023 Monthly Performance Report | 3 hrs | 7 days | Thu 6/1/23 | Fri 6/9/23 | 2492 | 2495 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6239 | 2495 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 6/12/23 | Mon 6/12/23 | 2494 | 2496 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6240 | 2496 | Future Task |  |  | D225 | Joy Schneider | Submit | DEL D225 - Monthly Performance Report (May 2023) - Submit | 0 hrs | 0 days | Mon 6/12/23 | Mon 6/12/23 | 2495 | 2497 |  | Joy Schneider
6241 | 2497 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Department QC | 1 hr | 7 days | Tue 6/13/23 | Wed 6/21/23 | 2496 | 2498 |  | Gabriela Gibson
6242 | 2498 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Contract Manager Review | 2 hrs | 2 days | Thu 6/22/23 | Fri 6/23/23 | 2497 | 2499 |  | Sean Buchanan
6243 | 2499 | Future Task |  |  | D225 | Joy Schneider | Accept | DEL D225 - Monthly Performance Report (May 2023) - Accept | 0 hrs | 0 days | Fri 6/23/23 | Fri 6/23/23 | 2498 | 2501 |  | Sean Buchanan
6244 | 2500 | Future Task |  |  | D232 | Joy Schneider |  | D232 - Monthly Performance Report (June 2023) | 10 hrs | 17 days | Mon 7/3/23 | Wed 7/26/23
6366 | 2501 | Future Task |  |  | D232 | Joy Schneider | Create | Create June 2023 Monthly Performance Report | 3 hrs | 7 days | Mon 7/3/23 | Wed 7/12/23 | 2499 | 2502 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6245 | 2502 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 7/13/23 | Thu 7/13/23 | 2501 | 2503 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6246 | 2503 | Future Task |  |  | D232 | Joy Schneider | Submit | DEL D232 - Monthly Performance Report (June 2023) - Submit | 0 hrs | 0 days | Thu 7/13/23 | Thu 7/13/23 | 2502 | 2504 |  | Joy Schneider
6247 | 2504 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Department QC | 1 hr | 7 days | Fri 7/14/23 | Mon 7/24/23 | 2503 | 2505 |  | Gabriela Gibson
6248 | 2505 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Contract Manager Review | 2 hrs | 2 days | Tue 7/25/23 | Wed 7/26/23 | 2504 | 2506 |  | Sean Buchanan
6249 | 2506 | Future Task |  |  | D232 | Joy Schneider | Accept | DEL D232 - Monthly Performance Report (June 2023) - Accept | 0 hrs | 0 days | Wed 7/26/23 | Wed 7/26/23 | 2505 | 2508 |  | Sean Buchanan
6250 | 2507 | Future Task |  |  | D239 | Joy Schneider |  | D239 - Monthly Performance Report (July 2023) | 10 hrs | 17 days | Tue 8/1/23 | Wed 8/23/23
6367 | 2508 | Future Task |  |  | D239 | Joy Schneider | Create | Create July 2023 Monthly Performance Report | 3 hrs | 7 days | Tue 8/1/23 | Wed 8/9/23 | 2506 | 2509 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6251 | 2509 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 8/10/23 | Thu 8/10/23 | 2508 | 2510 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6252 | 2510 | Future Task |  |  | D239 | Joy Schneider | Submit | DEL D239 - Monthly Performance Report (July 2023) - Submit | 0 hrs | 0 days | Thu 8/10/23 | Thu 8/10/23 | 2509 | 2511 |  | Joy Schneider
6253 | 2511 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Department QC | 1 hr | 7 days | Fri 8/11/23 | Mon 8/21/23 | 2510 | 2512 |  | Gabriela Gibson
6254 | 2512 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Contract Manager Review | 2 hrs | 2 days | Tue 8/22/23 | Wed 8/23/23 | 2511 | 2513 |  | Sean Buchanan
6255 | 2513 | Future Task |  |  | D239 | Joy Schneider | Accept | DEL D239 - Monthly Performance Report (July 2023) - Accept | 0 hrs | 0 days | Wed 8/23/23 | Wed 8/23/23 | 2512 | 2515 |  | Sean Buchanan
6256 | 2514 | Future Task |  |  | D249 | Joy Schneider |  | D249 - Monthly Performance Report (August 2023) | 10 hrs | 17 days | Fri 9/1/23 | Tue 9/26/23
6368 | 2515 | Future Task |  |  | D249 | Joy Schneider | Create | Create August 2023 Monthly Performance Report | 3 hrs | 7 days | Fri 9/1/23 | Tue 9/12/23 | 2513 | 2516 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6257 | 2516 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 9/13/23 | Wed 9/13/23 | 2515 | 2517 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6258 | 2517 | Future Task |  |  | D249 | Joy Schneider | Submit | DEL D249 - Monthly Performance Report (August 2023) - Submit | 0 hrs | 0 days | Wed 9/13/23 | Wed 9/13/23 | 2516 | 2518 |  | Joy Schneider
6259 | 2518 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Department QC | 1 hr | 7 days | Thu 9/14/23 | Fri 9/22/23 | 2517 | 2519 |  | Gabriela Gibson
6260 | 2519 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Contract Manager Review | 2 hrs | 2 days | Mon 9/25/23 | Tue 9/26/23 | 2518 | 2520 |  | Sean Buchanan
6261 | 2520 | Future Task |  |  | D249 | Joy Schneider | Accept | DEL D249 - Monthly Performance Report (August 2023) - Accept | 0 hrs | 0 days | Tue 9/26/23 | Tue 9/26/23 | 2519 | 2522 |  | Sean Buchanan
6262 | 2521 | Future Task |  |  | D253 | Joy Schneider |  | D253 - Monthly Performance Report (September 2023) | 10 hrs | 17 days | Mon 10/2/23 | Tue 10/24/23
6369 | 2522 | Future Task |  |  | D253 | Joy Schneider | Create | Create September 2023 Monthly Performance Report | 3 hrs | 7 days | Mon 10/2/23 | Tue 10/10/23 | 2520 | 2523 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6263 | 2523 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 10/11/23 | Wed 10/11/23 | 2522 | 2524 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6264 | 2524 | Future Task |  |  | D253 | Joy Schneider | Submit | DEL D253 - Monthly Performance Report (September 2023) - Submit | 0 hrs | 0 days | Wed 10/11/23 | Wed 10/11/23 | 2523 | 2525 |  | Joy Schneider
6265 | 2525 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Department QC | 1 hr | 7 days | Thu 10/12/23 | Fri 10/20/23 | 2524 | 2526 |  | Gabriela Gibson
6266 | 2526 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Contract Manager Review | 2 hrs | 2 days | Mon 10/23/23 | Tue 10/24/23 | 2525 | 2527 |  | Sean Buchanan
6267 | 2527 | Future Task |  |  | D253 | Joy Schneider | Accept | DEL D253 - Monthly Performance Report (September 2023) - Accept | 0 hrs | 0 days | Tue 10/24/23 | Tue 10/24/23 | 2526 | 2529 |  | Sean Buchanan
6268 | 2528 | Future Task |  |  | D257 | Joy Schneider |  | D257 - Monthly Performance Report (October 2023) | 10 hrs | 17 days | Wed 11/1/23 | Tue 11/28/23
6370 | 2529 | Future Task |  |  | D257 | Joy Schneider | Create | Create October 2023 Monthly Performance Report | 3 hrs | 7 days | Wed 11/1/23 | Thu 11/9/23 | 2527 | 2530 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6269 | 2530 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 11/13/23 | Mon 11/13/23 | 2529 | 2531 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6270 | 2531 | Future Task |  |  | D257 | Joy Schneider | Submit | DEL D257 - Monthly Performance Report (October 2023) - Submit | 0 hrs | 0 days | Mon 11/13/23 | Mon 11/13/23 | 2530 | 2532 |  | Joy Schneider
6271 | 2532 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Department QC | 1 hr | 7 days | Tue 11/14/23 | Wed 11/22/23 | 2531 | 2533 |  | Gabriela Gibson
6272 | 2533 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Contract Manager Review | 2 hrs | 2 days | Mon 11/27/23 | Tue 11/28/23 | 2532 | 2534 |  | Sean Buchanan
6273 | 2534 | Future Task |  |  | D257 | Joy Schneider | Accept | DEL D257 - Monthly Performance Report (October 2023) - Accept | 0 hrs | 0 days | Tue 11/28/23 | Tue 11/28/23 | 2533 | 2536 |  | Sean Buchanan
6274 | 2535 | Future Task |  |  | D261 | Joy Schneider |  | D261 - Monthly Performance Report (November 2023) | 10 hrs | 17 days | Fri 12/1/23 | Tue 12/26/23
6385 | 2536 | Future Task |  |  | D261 | Joy Schneider | Create | Create November 2023 Monthly Performance Report | 3 hrs | 7 days | Fri 12/1/23 | Mon 12/11/23 | 2534 | 2537 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6275 | 2537 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 12/12/23 | Tue 12/12/23 | 2536 | 2538 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6276 | 2538 | Future Task |  |  | D261 | Joy Schneider | Submit | DEL D261 - Monthly Performance Report (November 2023) - Submit | 0 hrs | 0 days | Tue 12/12/23 | Tue 12/12/23 | 2537 | 2539 |  | Joy Schneider
6277 | 2539 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Department QC | 1 hr | 7 days | Wed 12/13/23 | Thu 12/21/23 | 2538 | 2540 |  | Gabriela Gibson
6278 | 2540 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Contract Manager Review | 2 hrs | 2 days | Fri 12/22/23 | Tue 12/26/23 | 2539 | 2541 |  | Sean Buchanan
6279 | 2541 | Future Task |  |  | D261 | Joy Schneider | Accept | DEL D261 - Monthly Performance Report (November 2023) - Accept | 0 hrs | 0 days | Tue 12/26/23 | Tue 12/26/23 | 2540 | 2543 |  | Sean Buchanan
6280 | 2542 | Future Task |  |  | D267 | Joy Schneider |  | D267 - Monthly Performance Report (December 2023) | 10 hrs | 17 days | Tue 1/2/24 | Thu 1/25/24
6384 | 2543 | Future Task |  |  | D267 | Joy Schneider | Create | Create December 2023 Monthly Performance Report | 3 hrs | 7 days | Tue 1/2/24 | Wed 1/10/24 | 2541 | 2544 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6281 | 2544 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 1/11/24 | Thu 1/11/24 | 2543 | 2545 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6282 | 2545 | Future Task |  |  | D267 | Joy Schneider | Submit | DEL D267 - Monthly Performance Report (December 2023) - Submit | 0 hrs | 0 days | Thu 1/11/24 | Thu 1/11/24 | 2544 | 2546 |  | Joy Schneider
6283 | 2546 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Department QC | 1 hr | 7 days | Fri 1/12/24 | Tue 1/23/24 | 2545 | 2547 |  | Gabriela Gibson
6284 | 2547 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Contract Manager Review | 2 hrs | 2 days | Wed 1/24/24 | Thu 1/25/24 | 2546 | 2548 |  | Sean Buchanan
6285 | 2548 | Future Task |  |  | D267 | Joy Schneider | Accept | DEL D267 - Monthly Performance Report (December 2023) - Accept | 0 hrs | 0 days | Thu 1/25/24 | Thu 1/25/24 | 2547 | 2550 |  | Sean Buchanan
6286 | 2549 | Future Task |  |  | D277 | Joy Schneider |  | D277 - Monthly Performance Report (January 2024) | 10 hrs | 17 days | Thu 2/1/24 | Fri 2/23/24
6383 | 2550 | Future Task |  |  | D277 | Joy Schneider | Create | Create January 2024 Monthly Performance Report | 3 hrs | 7 days | Thu 2/1/24 | Fri 2/9/24 | 2548 | 2551 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6287 | 2551 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 2/12/24 | Mon 2/12/24 | 2550 | 2552 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6288 | 2552 | Future Task |  |  | D277 | Joy Schneider | Submit | DEL D277 - Monthly Performance Report (January 2024) - Submit | 0 hrs | 0 days | Mon 2/12/24 | Mon 2/12/24 | 2551 | 2553 |  | Joy Schneider
6289 | 2553 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Department QC | 1 hr | 7 days | Tue 2/13/24 | Wed 2/21/24 | 2552 | 2554 |  | Gabriela Gibson
6290 | 2554 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Contract Manager Review | 2 hrs | 2 days | Thu 2/22/24 | Fri 2/23/24 | 2553 | 2555 |  | Sean Buchanan
6291 | 2555 | Future Task |  |  | D277 | Joy Schneider | Accept | DEL D277 - Monthly Performance Report (January 2024) - Accept | 0 hrs | 0 days | Fri 2/23/24 | Fri 2/23/24 | 2554 | 2557 |  | Sean Buchanan
6292 | 2556 | Future Task |  |  | D284 | Joy Schneider |  | D284 - Monthly Performance Report (February 2024) | 10 hrs | 17 days | Fri 3/1/24 | Mon 3/25/24
6382 | 2557 | Future Task |  |  | D284 | Joy Schneider | Create | Create February 2024 Monthly Performance Report | 3 hrs | 7 days | Fri 3/1/24 | Mon 3/11/24 | 2555 | 2558 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6293 | 2558 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 3/12/24 | Tue 3/12/24 | 2557 | 2559 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6294 | 2559 | Future Task |  |  | D284 | Joy Schneider | Submit | DEL D284 - Monthly Performance Report (February 2024) - Submit | 0 hrs | 0 days | Tue 3/12/24 | Tue 3/12/24 | 2558 | 2560 |  | Joy Schneider
6295 | 2560 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Department QC | 1 hr | 7 days | Wed 3/13/24 | Thu 3/21/24 | 2559 | 2561 |  | Gabriela Gibson
6296 | 2561 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Contract Manager Review | 2 hrs | 2 days | Fri 3/22/24 | Mon 3/25/24 | 2560 | 2562 |  | Sean Buchanan
6297 | 2562 | Future Task |  |  | D284 | Joy Schneider | Accept | DEL D284 - Monthly Performance Report (February 2024) - Accept | 0 hrs | 0 days | Mon 3/25/24 | Mon 3/25/24 | 2561 | 2564 |  | Sean Buchanan
6298 | 2563 | Future Task |  |  | D288 | Joy Schneider |  | D288 - Monthly Performance Report (March 2024) | 10 hrs | 17 days | Mon 4/1/24 | Tue 4/23/24
6381 | 2564 | Future Task |  |  | D288 | Joy Schneider | Create | Create March 2024 Monthly Performance Report | 3 hrs | 7 days | Mon 4/1/24 | Tue 4/9/24 | 2562 | 2565 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6299 | 2565 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 4/10/24 | Wed 4/10/24 | 2564 | 2566 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6300 | 2566 | Future Task |  |  | D288 | Joy Schneider | Submit | DEL D288 - Monthly Performance Report (March 2024) - Submit | 0 hrs | 0 days | Wed 4/10/24 | Wed 4/10/24 | 2565 | 2567 |  | Joy Schneider
6301 | 2567 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Department QC | 1 hr | 7 days | Thu 4/11/24 | Fri 4/19/24 | 2566 | 2568 |  | Gabriela Gibson
6302 | 2568 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Contract Manager Review | 2 hrs | 2 days | Mon 4/22/24 | Tue 4/23/24 | 2567 | 2569 |  | Sean Buchanan
6303 | 2569 | Future Task |  |  | D288 | Joy Schneider | Accept | DEL D288 - Monthly Performance Report (March 2024) - Accept | 0 hrs | 0 days | Tue 4/23/24 | Tue 4/23/24 | 2568 | 2571 |  | Sean Buchanan
6304 | 2570 | Future Task |  |  | D296 | Joy Schneider |  | D296 - Monthly Performance Report (April 2024) | 10 hrs | 17 days | Wed 5/1/24 | Thu 5/23/24
6380 | 2571 | Future Task |  |  | D296 | Joy Schneider | Create | Create April 2024 Monthly Performance Report | 3 hrs | 7 days | Wed 5/1/24 | Thu 5/9/24 | 2569 | 2572 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6305 | 2572 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 5/10/24 | Fri 5/10/24 | 2571 | 2573 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6306 | 2573 | Future Task |  |  | D296 | Joy Schneider | Submit | DEL D296 - Monthly Performance Report (April 2024) - Submit | 0 hrs | 0 days | Fri 5/10/24 | Fri 5/10/24 | 2572 | 2574 |  | Joy Schneider
6307 | 2574 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Department QC | 1 hr | 7 days | Mon 5/13/24 | Tue 5/21/24 | 2573 | 2575 |  | Gabriela Gibson
6308 | 2575 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Contract Manager Review | 2 hrs | 2 days | Wed 5/22/24 | Thu 5/23/24 | 2574 | 2576 |  | Sean Buchanan
6309 | 2576 | Future Task |  |  | D296 | Joy Schneider | Accept | DEL D296 - Monthly Performance Report (April 2024) - Accept | 0 hrs | 0 days | Thu 5/23/24 | Thu 5/23/24 | 2575 | 2578 |  | Sean Buchanan
6310 | 2577 | Future Task |  |  | D302 | Joy Schneider |  | D302 - Monthly Performance Report (May 2024) | 10 hrs | 17 days | Mon 6/3/24 | Tue 6/25/24
6379 | 2578 | Future Task |  |  | D302 | Joy Schneider | Create | Create May 2024 Monthly Performance Report | 3 hrs | 7 days | Mon 6/3/24 | Tue 6/11/24 | 2576 | 2579 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6311 | 2579 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 6/12/24 | Wed 6/12/24 | 2578 | 2580 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6312 | 2580 | Future Task |  |  | D302 | Joy Schneider | Submit | DEL D302 - Monthly Performance Report (May 2024) - Submit | 0 hrs | 0 days | Wed 6/12/24 | Wed 6/12/24 | 2579 | 2581 |  | Joy Schneider
6313 | 2581 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Department QC | 1 hr | 7 days | Thu 6/13/24 | Fri 6/21/24 | 2580 | 2582 |  | Gabriela Gibson
6314 | 2582 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Contract Manager Review | 2 hrs | 2 days | Mon 6/24/24 | Tue 6/25/24 | 2581 | 2583 |  | Sean Buchanan
6315 | 2583 | Future Task |  |  | D302 | Joy Schneider | Accept | DEL D302 - Monthly Performance Report (May 2024) - Accept | 0 hrs | 0 days | Tue 6/25/24 | Tue 6/25/24 | 2582 | 2585 |  | Sean Buchanan
6316 | 2584 | Future Task |  |  | D311 | Joy Schneider |  | D311 - Monthly Performance Report (June 2024) | 10 hrs | 17 days | Mon 7/1/24 | Wed 7/24/24
6378 | 2585 | Future Task |  |  | D311 | Joy Schneider | Create | Create June 2024 Monthly Performance Report | 3 hrs | 7 days | Mon 7/1/24 | Wed 7/10/24 | 2583 | 2586 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6317 | 2586 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 7/11/24 | Thu 7/11/24 | 2585 | 2587 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6318 | 2587 | Future Task |  |  | D311 | Joy Schneider | Submit | DEL D311 - Monthly Performance Report (June 2024) - Submit | 0 hrs | 0 days | Thu 7/11/24 | Thu 7/11/24 | 2586 | 2588 |  | Joy Schneider
6319 | 2588 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Department QC | 1 hr | 7 days | Fri 7/12/24 | Mon 7/22/24 | 2587 | 2589 |  | Gabriela Gibson
6320 | 2589 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Contract Manager Review | 2 hrs | 2 days | Tue 7/23/24 | Wed 7/24/24 | 2588 | 2590 |  | Sean Buchanan
6321 | 2590 | Future Task |  |  | D311 | Joy Schneider | Accept | DEL D311 - Monthly Performance Report (June 2024) - Accept | 0 hrs | 0 days | Wed 7/24/24 | Wed 7/24/24 | 2589 | 2592 |  | Sean Buchanan
6322 | 2591 | Future Task |  |  | D319 | Joy Schneider |  | D319 - Monthly Performance Report (July 2024) | 10 hrs | 17 days | Thu 8/1/24 | Fri 8/23/24
6377 | 2592 | Future Task |  |  | D319 | Joy Schneider | Create | Create July 2024 Monthly Performance Report | 3 hrs | 7 days | Thu 8/1/24 | Fri 8/9/24 | 2590 | 2593 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6323 | 2593 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 8/12/24 | Mon 8/12/24 | 2592 | 2594 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6324 | 2594 | Future Task |  |  | D319 | Joy Schneider | Submit | DEL D319 - Monthly Performance Report (July 2024) - Submit | 0 hrs | 0 days | Mon 8/12/24 | Mon 8/12/24 | 2593 | 2595 |  | Joy Schneider
6325 | 2595 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Department QC | 1 hr | 7 days | Tue 8/13/24 | Wed 8/21/24 | 2594 | 2596 |  | Gabriela Gibson
6326 | 2596 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Contract Manager Review | 2 hrs | 2 days | Thu 8/22/24 | Fri 8/23/24 | 2595 | 2597 |  | Sean Buchanan
6327 | 2597 | Future Task |  |  | D319 | Joy Schneider | Accept | DEL D319 - Monthly Performance Report (July 2024) - Accept | 0 hrs | 0 days | Fri 8/23/24 | Fri 8/23/24 | 2596 | 2599 |  | Sean Buchanan
6328 | 2598 | Future Task |  |  | D328 | Joy Schneider |  | D328 - Monthly Performance Report (August 2024) | 10 hrs | 17 days | Tue 9/3/24 | Wed 9/25/24
6376 | 2599 | Future Task |  |  | D328 | Joy Schneider | Create | Create August 2024 Monthly Performance Report | 3 hrs | 7 days | Tue 9/3/24 | Wed 9/11/24 | 2597 | 2600 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6329 | 2600 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 9/12/24 | Thu 9/12/24 | 2599 | 2601 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6330 | 2601 | Future Task |  |  | D328 | Joy Schneider | Submit | DEL D328 - Monthly Performance Report (August 2024) - Submit | 0 hrs | 0 days | Thu 9/12/24 | Thu 9/12/24 | 2600 | 2602 |  | Joy Schneider
6331 | 2602 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Department QC | 1 hr | 7 days | Fri 9/13/24 | Mon 9/23/24 | 2601 | 2603 |  | Gabriela Gibson
6332 | 2603 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Contract Manager Review | 2 hrs | 2 days | Tue 9/24/24 | Wed 9/25/24 | 2602 | 2604 |  | Sean Buchanan
6333 | 2604 | Future Task |  |  | D328 | Joy Schneider | Accept | DEL D328 - Monthly Performance Report (August 2024) - Accept | 0 hrs | 0 days | Wed 9/25/24 | Wed 9/25/24 | 2603 | 2606 |  | Sean Buchanan
6334 | 2605 | Future Task |  |  | D334 | Joy Schneider |  | D334 - Monthly Performance Report (September 2024) | 10 hrs | 17 days | Tue 10/1/24 | Wed 10/23/24
6375 | 2606 | Future Task |  |  | D334 | Joy Schneider | Create | Create September 2024 Monthly Performance Report | 3 hrs | 7 days | Tue 10/1/24 | Wed 10/9/24 | 2604 | 2607 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6335 | 2607 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 10/10/24 | Thu 10/10/24 | 2606 | 2608 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6336 | 2608 | Future Task |  |  | D334 | Joy Schneider | Submit | DEL D334 - Monthly Performance Report (September 2024) - Submit | 0 hrs | 0 days | Thu 10/10/24 | Thu 10/10/24 | 2607 | 2609 |  | Joy Schneider
6337 | 2609 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Department QC | 1 hr | 7 days | Fri 10/11/24 | Mon 10/21/24 | 2608 | 2610 |  | Gabriela Gibson
6338 | 2610 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Contract Manager Review | 2 hrs | 2 days | Tue 10/22/24 | Wed 10/23/24 | 2609 | 2611 |  | Sean Buchanan
6339 | 2611 | Future Task |  |  | D334 | Joy Schneider | Accept | DEL D334 - Monthly Performance Report (September 2024) - Accept | 0 hrs | 0 days | Wed 10/23/24 | Wed 10/23/24 | 2610 | 2613 |  | Sean Buchanan
6340 | 2612 | Future Task |  |  | D342 | Joy Schneider |  | D342 - Monthly Performance Report (October 2024) | 10 hrs | 17 days | Fri 11/1/24 | Tue 11/26/24
6374 | 2613 | Future Task |  |  | D342 | Joy Schneider | Create | Create October 2024 Monthly Performance Report | 3 hrs | 7 days | Fri 11/1/24 | Tue 11/12/24 | 2611 | 2614 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6341 | 2614 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 11/13/24 | Wed 11/13/24 | 2613 | 2615 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6342 | 2615 | Future Task |  |  | D342 | Joy Schneider | Submit | DEL D342 - Monthly Performance Report (October 2024) - Submit | 0 hrs | 0 days | Wed 11/13/24 | Wed 11/13/24 | 2614 | 2616 |  | Joy Schneider
6343 | 2616 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Department QC | 1 hr | 7 days | Thu 11/14/24 | Fri 11/22/24 | 2615 | 2617 |  | Gabriela Gibson
6344 | 2617 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Contract Manager Review | 2 hrs | 2 days | Mon 11/25/24 | Tue 11/26/24 | 2616 | 2618 |  | Sean Buchanan
6345 | 2618 | Future Task |  |  | D342 | Joy Schneider | Accept | DEL D342 - Monthly Performance Report (October 2024) - Accept | 0 hrs | 0 days | Tue 11/26/24 | Tue 11/26/24 | 2617 | 2620 |  | Sean Buchanan
6346 | 2619 | Future Task |  |  | D347 | Joy Schneider |  | D347 - Monthly Performance Report (November 2024) | 10 hrs | 17 days | Mon 12/2/24 | Tue 12/24/24
6373 | 2620 | Future Task |  |  | D347 | Joy Schneider | Create | Create November 2024 Monthly Performance Report | 3 hrs | 7 days | Mon 12/2/24 | Tue 12/10/24 | 2618 | 2621 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6347 | 2621 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 12/11/24 | Wed 12/11/24 | 2620 | 2622 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6348 | 2622 | Future Task |  |  | D347 | Joy Schneider | Submit | DEL D347 - Monthly Performance Report (November 2024) - Submit | 0 hrs | 0 days | Wed 12/11/24 | Wed 12/11/24 | 2621 | 2623 |  | Joy Schneider
6349 | 2623 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Department QC | 1 hr | 7 days | Thu 12/12/24 | Fri 12/20/24 | 2622 | 2624 |  | Gabriela Gibson
6350 | 2624 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Contract Manager Review | 2 hrs | 2 days | Mon 12/23/24 | Tue 12/24/24 | 2623 | 2625 |  | Sean Buchanan
6351 | 2625 | Future Task |  |  | D347 | Joy Schneider | Accept | DEL D347 - Monthly Performance Report (November 2024) - Accept | 0 hrs | 0 days | Tue 12/24/24 | Tue 12/24/24 | 2624 | 2627 |  | Sean Buchanan
6352 | 2626 | Future Task |  |  | D353 | Joy Schneider |  | D353 - Monthly Performance Report (December 2024) | 10 hrs | 17 days | Thu 1/2/25 | Mon 1/27/25
6372 | 2627 | Future Task |  |  | D353 | Joy Schneider | Create | Create December 2024 Monthly Performance Report | 3 hrs | 7 days | Thu 1/2/25 | Fri 1/10/25 | 2625 | 2628 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6353 | 2628 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 1/13/25 | Mon 1/13/25 | 2627 | 2629 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6354 | 2629 | Future Task |  |  | D353 | Joy Schneider | Submit | DEL D353 - Monthly Performance Report (December 2024) - Submit | 0 hrs | 0 days | Mon 1/13/25 | Mon 1/13/25 | 2628 | 2630 |  | Joy Schneider
6355 | 2630 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Department QC | 1 hr | 7 days | Tue 1/14/25 | Thu 1/23/25 | 2629 | 2631 |  | Gabriela Gibson
6356 | 2631 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Contract Manager Review | 2 hrs | 2 days | Fri 1/24/25 | Mon 1/27/25 | 2630 | 2632 |  | Sean Buchanan
6357 | 2632 | Future Task |  |  | D353 | Joy Schneider | Accept | DEL D353 - Monthly Performance Report (December 2024) - Accept | 0 hrs | 0 days | Mon 1/27/25 | Mon 1/27/25 | 2631 | 2634 |  | Sean Buchanan
6358 | 2633 | Future Task |  |  | D359 | Joy Schneider |  | D359 - Monthly Performance Report (January 2025) | 10 hrs | 17 days | Mon 2/3/25 | Tue 2/25/25
6371 | 2634 | Future Task |  |  | D359 | Joy Schneider | Create | Create January 2025 Monthly Performance Report | 3 hrs | 7 days | Mon 2/3/25 | Tue 2/11/25 | 2632 | 2635 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6359 | 2635 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 2/12/25 | Wed 2/12/25 | 2634 | 2636 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6360 | 2636 | Future Task |  |  | D359 | Joy Schneider | Submit | DEL D359 - Monthly Performance Report (January 2025) - Submit | 0 hrs | 0 days | Wed 2/12/25 | Wed 2/12/25 | 2635 | 2637 |  | Joy Schneider
6361 | 2637 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Department QC | 1 hr | 7 days | Thu 2/13/25 | Fri 2/21/25 | 2636 | 2638 |  | Gabriela Gibson
6362 | 2638 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Contract Manager Review | 2 hrs | 2 days | Mon 2/24/25 | Tue 2/25/25 | 2637 | 2639 |  | Sean Buchanan
6363 | 2639 | Future Task |  |  | D359 | Joy Schneider | Accept | DEL D359 - Monthly Performance Report (January 2025) - Accept | 0 hrs | 0 days | Tue 2/25/25 | Tue 2/25/25 | 2638 | 2641 |  | Sean Buchanan
6386 | 2640 | Future Task |  |  | D362 | Joy Schneider |  | D362 - Monthly Performance Report (February 2025) | 10 hrs | 17 days | Mon 3/3/25 | Tue 3/25/25
6490 | 2641 | Future Task |  |  | D362 | Joy Schneider | Create | Create February 2025 Monthly Performance Report | 3 hrs | 7 days | Mon 3/3/25 | Tue 3/11/25 | 2639 | 2642 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6387 | 2642 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 3/12/25 | Wed 3/12/25 | 2641 | 2643 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6388 | 2643 | Future Task |  |  | D362 | Joy Schneider | Submit | DEL D362 - Monthly Performance Report (February 2025) - Submit | 0 hrs | 0 days | Wed 3/12/25 | Wed 3/12/25 | 2642 | 2644 |  | Joy Schneider
6389 | 2644 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Department QC | 1 hr | 7 days | Thu 3/13/25 | Fri 3/21/25 | 2643 | 2645 |  | Gabriela Gibson
6390 | 2645 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Contract Manager Review | 2 hrs | 2 days | Mon 3/24/25 | Tue 3/25/25 | 2644 | 2646 |  | Sean Buchanan
6391 | 2646 | Future Task |  |  | D362 | Joy Schneider | Accept | DEL D362 - Monthly Performance Report (February 2025) - Accept | 0 hrs | 0 days | Tue 3/25/25 | Tue 3/25/25 | 2645 | 2648 |  | Sean Buchanan
6392 | 2647 | Future Task |  |  | D364 | Joy Schneider |  | D364 - Monthly Performance Report (March 2025) | 10 hrs | 17 days | Tue 4/1/25 | Wed 4/23/25
6489 | 2648 | Future Task |  |  | D364 | Joy Schneider | Create | Create March 2025 Monthly Performance Report | 3 hrs | 7 days | Tue 4/1/25 | Wed 4/9/25 | 2646 | 2649 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6393 | 2649 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 4/10/25 | Thu 4/10/25 | 2648 | 2650 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6394 | 2650 | Future Task |  |  | D364 | Joy Schneider | Submit | DEL D364 - Monthly Performance Report (March 2025) - Submit | 0 hrs | 0 days | Thu 4/10/25 | Thu 4/10/25 | 2649 | 2651 |  | Joy Schneider
6395 | 2651 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Department QC | 1 hr | 7 days | Fri 4/11/25 | Mon 4/21/25 | 2650 | 2652 |  | Gabriela Gibson
6396 | 2652 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Contract Manager Review | 2 hrs | 2 days | Tue 4/22/25 | Wed 4/23/25 | 2651 | 2653 |  | Sean Buchanan
6397 | 2653 | Future Task |  |  | D364 | Joy Schneider | Accept | DEL D364 - Monthly Performance Report (March 2025) - Accept | 0 hrs | 0 days | Wed 4/23/25 | Wed 4/23/25 | 2652 | 2655 |  | Sean Buchanan
6398 | 2654 | Future Task |  |  | D366 | Joy Schneider |  | D366 - Monthly Performance Report (April 2025) | 10 hrs | 17 days | Thu 5/1/25 | Fri 5/23/25
6488 | 2655 | Future Task |  |  | D366 | Joy Schneider | Create | Create April 2025 Monthly Performance Report | 3 hrs | 7 days | Thu 5/1/25 | Fri 5/9/25 | 2653 | 2656 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6399 | 2656 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 5/12/25 | Mon 5/12/25 | 2655 | 2657 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6400 | 2657 | Future Task |  |  | D366 | Joy Schneider | Submit | DEL D366 - Monthly Performance Report (April 2025) - Submit | 0 hrs | 0 days | Mon 5/12/25 | Mon 5/12/25 | 2656 | 2658 |  | Joy Schneider
6401 | 2658 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Department QC | 1 hr | 7 days | Tue 5/13/25 | Wed 5/21/25 | 2657 | 2659 |  | Gabriela Gibson
6402 | 2659 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Contract Manager Review | 2 hrs | 2 days | Thu 5/22/25 | Fri 5/23/25 | 2658 | 2660 |  | Sean Buchanan
6403 | 2660 | Future Task |  |  | D366 | Joy Schneider | Accept | DEL D366 - Monthly Performance Report (April 2025) - Accept | 0 hrs | 0 days | Fri 5/23/25 | Fri 5/23/25 | 2659 | 2662 |  | Sean Buchanan
6404 | 2661 | Future Task |  |  | D367 | Joy Schneider |  | D367 - Monthly Performance Report (May 2025) | 10 hrs | 17 days | Mon 6/2/25 | Tue 6/24/25
6487 | 2662 | Future Task |  |  | D367 | Joy Schneider | Create | Create May 2025 Monthly Performance Report | 3 hrs | 7 days | Mon 6/2/25 | Tue 6/10/25 | 2660 | 2663 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6405 | 2663 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 6/11/25 | Wed 6/11/25 | 2662 | 2664 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6406 | 2664 | Future Task |  |  | D367 | Joy Schneider | Submit | DEL D367 - Monthly Performance Report (May 2025) - Submit | 0 hrs | 0 days | Wed 6/11/25 | Wed 6/11/25 | 2663 | 2665 |  | Joy Schneider
6407 | 2665 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Department QC | 1 hr | 7 days | Thu 6/12/25 | Fri 6/20/25 | 2664 | 2666 |  | Gabriela Gibson
6408 | 2666 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Contract Manager Review | 2 hrs | 2 days | Mon 6/23/25 | Tue 6/24/25 | 2665 | 2667 |  | Sean Buchanan
6409 | 2667 | Future Task |  |  | D367 | Joy Schneider | Accept | DEL D367 - Monthly Performance Report (May 2025) - Accept | 0 hrs | 0 days | Tue 6/24/25 | Tue 6/24/25 | 2666 | 2669 |  | Sean Buchanan
6410 | 2668 | Future Task |  |  | D368 | Joy Schneider |  | D368 - Monthly Performance Report (June 2025) | 10 hrs | 17 days | Tue 7/1/25 | Thu 7/24/25
6486 | 2669 | Future Task |  |  | D368 | Joy Schneider | Create | Create June 2025 Monthly Performance Report | 3 hrs | 7 days | Tue 7/1/25 | Thu 7/10/25 | 2667 | 2670 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6411 | 2670 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 7/11/25 | Fri 7/11/25 | 2669 | 2671 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6412 | 2671 | Future Task |  |  | D368 | Joy Schneider | Submit | DEL D368 - Monthly Performance Report (June 2025) - Submit | 0 hrs | 0 days | Fri 7/11/25 | Fri 7/11/25 | 2670 | 2672 |  | Joy Schneider
6413 | 2672 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Department QC | 1 hr | 7 days | Mon 7/14/25 | Tue 7/22/25 | 2671 | 2673 |  | Gabriela Gibson
6414 | 2673 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 7/23/25 | Thu 7/24/25 | 2672 | 2674 |  | Sean Buchanan
6415 | 2674 | Future Task |  |  | D368 | Joy Schneider | Accept | DEL D368 - Monthly Performance Report (June 2025) - Accept | 0 hrs | 0 days | Thu 7/24/25 | Thu 7/24/25 | 2673 | 2676 |  | Sean Buchanan
6416 | 2675 | Future Task |  |  | D369 | Joy Schneider |  | D369 - Monthly Performance Report (July 2025) | 10 hrs | 17 days | Fri 8/1/25 | Mon 8/25/25
6485 | 2676 | Future Task |  |  | D369 | Joy Schneider | Create | Create July 2025 Monthly Performance Report | 3 hrs | 7 days | Fri 8/1/25 | Mon 8/11/25 | 2674 | 2677 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6417 | 2677 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 8/12/25 | Tue 8/12/25 | 2676 | 2678 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6418 | 2678 | Future Task |  |  | D369 | Joy Schneider | Submit | DEL D369 - Monthly Performance Report (July 2025) - Submit | 0 hrs | 0 days | Tue 8/12/25 | Tue 8/12/25 | 2677 | 2679 |  | Joy Schneider
6419 | 2679 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Department QC | 1 hr | 7 days | Wed 8/13/25 | Thu 8/21/25 | 2678 | 2680 |  | Gabriela Gibson
6420 | 2680 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Contract Manager Review | 2 hrs | 2 days | Fri 8/22/25 | Mon 8/25/25 | 2679 | 2681 |  | Sean Buchanan
6421 | 2681 | Future Task |  |  | D369 | Joy Schneider | Accept | DEL D369 - Monthly Performance Report (July 2025) - Accept | 0 hrs | 0 days | Mon 8/25/25 | Mon 8/25/25 | 2680 | 2683 |  | Sean Buchanan
6422 | 2682 | Future Task |  |  | D370 | Joy Schneider |  | D370 - Monthly Performance Report (August 2025) | 10 hrs | 17 days | Tue 9/2/25 | Wed 9/24/25
6484 | 2683 | Future Task |  |  | D370 | Joy Schneider | Create | Create August 2025 Monthly Performance Report | 3 hrs | 7 days | Tue 9/2/25 | Wed 9/10/25 | 2681 | 2684 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6423 | 2684 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 9/11/25 | Thu 9/11/25 | 2683 | 2685 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6424 | 2685 | Future Task |  |  | D370 | Joy Schneider | Submit | DEL D370 - Monthly Performance Report (August 2025) - Submit | 0 hrs | 0 days | Thu 9/11/25 | Thu 9/11/25 | 2684 | 2686 |  | Joy Schneider
6425 | 2686 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Department QC | 1 hr | 7 days | Fri 9/12/25 | Mon 9/22/25 | 2685 | 2687 |  | Gabriela Gibson
6426 | 2687 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Contract Manager Review | 2 hrs | 2 days | Tue 9/23/25 | Wed 9/24/25 | 2686 | 2688 |  | Sean Buchanan
6427 | 2688 | Future Task |  |  | D370 | Joy Schneider | Accept | DEL D370 - Monthly Performance Report (August 2025) - Accept | 0 hrs | 0 days | Wed 9/24/25 | Wed 9/24/25 | 2687 | 2690 |  | Sean Buchanan
6428 | 2689 | Future Task |  |  | D371 | Joy Schneider |  | D371 - Monthly Performance Report (September 2025) | 10 hrs | 17 days | Wed 10/1/25 | Thu 10/23/25
6483 | 2690 | Future Task |  |  | D371 | Joy Schneider | Create | Create September 2025 Monthly Performance Report | 3 hrs | 7 days | Wed 10/1/25 | Thu 10/9/25 | 2688 | 2691 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6429 | 2691 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 10/10/25 | Fri 10/10/25 | 2690 | 2692 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6430 | 2692 | Future Task |  |  | D371 | Joy Schneider | Submit | DEL D371 - Monthly Performance Report (September 2025) - Submit | 0 hrs | 0 days | Fri 10/10/25 | Fri 10/10/25 | 2691 | 2693 |  | Joy Schneider
6431 | 2693 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Department QC | 1 hr | 7 days | Mon 10/13/25 | Tue 10/21/25 | 2692 | 2694 |  | Gabriela Gibson
6432 | 2694 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Contract Manager Review | 2 hrs | 2 days | Wed 10/22/25 | Thu 10/23/25 | 2693 | 2695 |  | Sean Buchanan
6433 | 2695 | Future Task |  |  | D371 | Joy Schneider | Accept | DEL D371 - Monthly Performance Report (September 2025) - Accept | 0 hrs | 0 days | Thu 10/23/25 | Thu 10/23/25 | 2694 | 2697 |  | Sean Buchanan
6434 | 2696 | Future Task |  |  | D373 | Joy Schneider |  | D373 - Monthly Performance Report (October 2025) | 10 hrs | 17 days | Mon 11/3/25 | Wed 11/26/25
6482 | 2697 | Future Task |  |  | D373 | Joy Schneider | Create | Create October 2025 Monthly Performance Report | 3 hrs | 7 days | Mon 11/3/25 | Wed 11/12/25 | 2695 | 2698 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6435 | 2698 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 11/13/25 | Thu 11/13/25 | 2697 | 2699 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6436 | 2699 | Future Task |  |  | D373 | Joy Schneider | Submit | DEL D373 - Monthly Performance Report (October 2025) - Submit | 0 hrs | 0 days | Thu 11/13/25 | Thu 11/13/25 | 2698 | 2700 |  | Joy Schneider
6437 | 2700 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Department QC | 1 hr | 7 days | Fri 11/14/25 | Mon 11/24/25 | 2699 | 2701 |  | Gabriela Gibson
6438 | 2701 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Contract Manager Review | 2 hrs | 2 days | Tue 11/25/25 | Wed 11/26/25 | 2700 | 2702 |  | Sean Buchanan
6439 | 2702 | Future Task |  |  | D373 | Joy Schneider | Accept | DEL D373 - Monthly Performance Report (October 2025) - Accept | 0 hrs | 0 days | Wed 11/26/25 | Wed 11/26/25 | 2701 | 2704 |  | Sean Buchanan
6440 | 2703 | Future Task |  |  | D374 | Joy Schneider |  | D374 - Monthly Performance Report (November 2025) | 10 hrs | 17 days | Mon 12/1/25 | Tue 12/23/25
6481 | 2704 | Future Task |  |  | D374 | Joy Schneider | Create | Create November 2025 Monthly Performance Report | 3 hrs | 7 days | Mon 12/1/25 | Tue 12/9/25 | 2702 | 2705 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6441 | 2705 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 12/10/25 | Wed 12/10/25 | 2704 | 2706 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6442 | 2706 | Future Task |  |  | D374 | Joy Schneider | Submit | DEL D374 - Monthly Performance Report (November 2025) - Submit | 0 hrs | 0 days | Wed 12/10/25 | Wed 12/10/25 | 2705 | 2707 |  | Joy Schneider
6443 | 2707 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Department QC | 1 hr | 7 days | Thu 12/11/25 | Fri 12/19/25 | 2706 | 2708 |  | Gabriela Gibson
6444 | 2708 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Contract Manager Review | 2 hrs | 2 days | Mon 12/22/25 | Tue 12/23/25 | 2707 | 2709 |  | Sean Buchanan
6445 | 2709 | Future Task |  |  | D374 | Joy Schneider | Accept | DEL D374 - Monthly Performance Report (November 2025) - Accept | 0 hrs | 0 days | Tue 12/23/25 | Tue 12/23/25 | 2708 | 2711 |  | Sean Buchanan
6446 | 2710 | Future Task |  |  | D375 | Joy Schneider |  | D375 - Monthly Performance Report (December 2025) | 10 hrs | 17 days | Fri 1/2/26 | Tue 1/27/26
6480 | 2711 | Future Task |  |  | D375 | Joy Schneider | Create | Create December 2025 Monthly Performance Report | 3 hrs | 7 days | Fri 1/2/26 | Mon 1/12/26 | 2709 | 2712 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6447 | 2712 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 1/13/26 | Tue 1/13/26 | 2711 | 2713 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6448 | 2713 | Future Task |  |  | D375 | Joy Schneider | Submit | DEL D375 - Monthly Performance Report (December 2025) - Submit | 0 hrs | 0 days | Tue 1/13/26 | Tue 1/13/26 | 2712 | 2714 |  | Joy Schneider
6449 | 2714 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Department QC | 1 hr | 7 days | Wed 1/14/26 | Fri 1/23/26 | 2713 | 2715 |  | Gabriela Gibson
6450 | 2715 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Contract Manager Review | 2 hrs | 2 days | Mon 1/26/26 | Tue 1/27/26 | 2714 | 2716 |  | Sean Buchanan
6451 | 2716 | Future Task |  |  | D375 | Joy Schneider | Accept | DEL D375 - Monthly Performance Report (December 2025) - Accept | 0 hrs | 0 days | Tue 1/27/26 | Tue 1/27/26 | 2715 | 2718 |  | Sean Buchanan
6452 | 2717 | Future Task |  |  | D432 | Joy Schneider |  | D432 - Monthly Performance Report (January 2026) | 10 hrs | 17 days | Mon 2/2/26 | Tue 2/24/26
6479 | 2718 | Future Task |  |  | D432 | Joy Schneider | Create | Create January 2026 Monthly Performance Report | 3 hrs | 7 days | Mon 2/2/26 | Tue 2/10/26 | 2716 | 2719 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6453 | 2719 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 2/11/26 | Wed 2/11/26 | 2718 | 2720 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6454 | 2720 | Future Task |  |  | D432 | Joy Schneider | Submit | DEL D432 - Monthly Performance Report (January 2026) - Submit | 0 hrs | 0 days | Wed 2/11/26 | Wed 2/11/26 | 2719 | 2721 |  | Joy Schneider
6455 | 2721 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Department QC | 1 hr | 7 days | Thu 2/12/26 | Fri 2/20/26 | 2720 | 2722 |  | Gabriela Gibson
6456 | 2722 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 2/23/26 | Tue 2/24/26 | 2721 | 2723 |  | Sean Buchanan
6457 | 2723 | Future Task |  |  | D432 | Joy Schneider | Accept | DEL D432 - Monthly Performance Report (January 2026) - Accept | 0 hrs | 0 days | Tue 2/24/26 | Tue 2/24/26 | 2722 | 2725 |  | Sean Buchanan
6458 | 2724 | Future Task |  |  | D434 | Joy Schneider |  | D434 - Monthly Performance Report (February 2026) | 10 hrs | 17 days | Mon 3/2/26 | Tue 3/24/26
6478 | 2725 | Future Task |  |  | D434 | Joy Schneider | Create | Create February 2026 Monthly Performance Report | 3 hrs | 7 days | Mon 3/2/26 | Tue 3/10/26 | 2723 | 2726 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6459 | 2726 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 3/11/26 | Wed 3/11/26 | 2725 | 2727 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6460 | 2727 | Future Task |  |  | D434 | Joy Schneider | Submit | DEL D434 - Monthly Performance Report (February 2026) - Submit | 0 hrs | 0 days | Wed 3/11/26 | Wed 3/11/26 | 2726 | 2728 |  | Joy Schneider
6461 | 2728 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Department QC | 1 hr | 7 days | Thu 3/12/26 | Fri 3/20/26 | 2727 | 2729 |  | Gabriela Gibson
6462 | 2729 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 3/23/26 | Tue 3/24/26 | 2728 | 2730 |  | Sean Buchanan
6463 | 2730 | Future Task |  |  | D434 | Joy Schneider | Accept | DEL D434 - Monthly Performance Report (February 2026) - Accept | 0 hrs | 0 days | Tue 3/24/26 | Tue 3/24/26 | 2729 | 2732 |  | Sean Buchanan
6464 | 2731 | Future Task |  |  | D435 | Joy Schneider |  | D435 - Monthly Performance Report (March 2026) | 10 hrs | 17 days | Wed 4/1/26 | Thu 4/23/26
6477 | 2732 | Future Task |  |  | D435 | Joy Schneider | Create | Create March 2026 Monthly Performance Report | 3 hrs | 7 days | Wed 4/1/26 | Thu 4/9/26 | 2730 | 2733 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6465 | 2733 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 4/10/26 | Fri 4/10/26 | 2732 | 2734 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6466 | 2734 | Future Task |  |  | D435 | Joy Schneider | Submit | DEL D435 - Monthly Performance Report (March 2026) - Submit | 0 hrs | 0 days | Fri 4/10/26 | Fri 4/10/26 | 2733 | 2735 |  | Joy Schneider
6467 | 2735 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Department QC | 1 hr | 7 days | Mon 4/13/26 | Tue 4/21/26 | 2734 | 2736 |  | Gabriela Gibson
6468 | 2736 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 4/22/26 | Thu 4/23/26 | 2735 | 2737 |  | Sean Buchanan
6469 | 2737 | Future Task |  |  | D435 | Joy Schneider | Accept | DEL D435 - Monthly Performance Report (March 2026) - Accept | 0 hrs | 0 days | Thu 4/23/26 | Thu 4/23/26 | 2736 | 2739 |  | Sean Buchanan
6470 | 2738 | Future Task |  |  | D437 | Joy Schneider |  | D437 - Monthly Performance Report (April 2026) | 10 hrs | 17 days | Fri 5/1/26 | Tue 5/26/26
6476 | 2739 | Future Task |  |  | D437 | Joy Schneider | Create | Create April 2026 Monthly Performance Report | 3 hrs | 7 days | Fri 5/1/26 | Mon 5/11/26 | 2737 | 2740 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6471 | 2740 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 5/12/26 | Tue 5/12/26 | 2739 | 2741 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6472 | 2741 | Future Task |  |  | D437 | Joy Schneider | Submit | DEL D437 - Monthly Performance Report (April 2026) - Submit | 0 hrs | 0 days | Tue 5/12/26 | Tue 5/12/26 | 2740 | 2742 |  | Joy Schneider
6473 | 2742 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Department QC | 1 hr | 7 days | Wed 5/13/26 | Thu 5/21/26 | 2741 | 2743 |  | Gabriela Gibson
6474 | 2743 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Contract Manager Review | 2 hrs | 2 days | Fri 5/22/26 | Tue 5/26/26 | 2742 | 2744 |  | Sean Buchanan
6475 | 2744 | Future Task |  |  | D437 | Joy Schneider | Accept | DEL D437 - Monthly Performance Report (April 2026) - Accept | 0 hrs | 0 days | Tue 5/26/26 | Tue 5/26/26 | 2743 | 2746 |  | Sean Buchanan
6491 | 2745 | Future Task |  |  | D438 | Joy Schneider |  | D438 - Monthly Performance Report (May 2026) | 10 hrs | 17 days | Mon 6/1/26 | Tue 6/23/26
6595 | 2746 | Future Task |  |  | D438 | Joy Schneider | Create | Create May 2026 Monthly Performance Report | 3 hrs | 7 days | Mon 6/1/26 | Tue 6/9/26 | 2744 | 2747 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6492 | 2747 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 6/10/26 | Wed 6/10/26 | 2746 | 2748 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6493 | 2748 | Future Task |  |  | D438 | Joy Schneider | Submit | DEL D438 - Monthly Performance Report (May 2026) - Submit | 0 hrs | 0 days | Wed 6/10/26 | Wed 6/10/26 | 2747 | 2749 |  | Joy Schneider
6494 | 2749 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Department QC | 1 hr | 7 days | Thu 6/11/26 | Fri 6/19/26 | 2748 | 2750 |  | Gabriela Gibson
6495 | 2750 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 6/22/26 | Tue 6/23/26 | 2749 | 2751 |  | Sean Buchanan
6496 | 2751 | Future Task |  |  | D438 | Joy Schneider | Accept | DEL D438 - Monthly Performance Report (May 2026) - Accept | 0 hrs | 0 days | Tue 6/23/26 | Tue 6/23/26 | 2750 | 2753 |  | Sean Buchanan
6497 | 2752 | Future Task |  |  | D439 | Joy Schneider |  | D439 - Monthly Performance Report (June 2026) | 10 hrs | 17 days | Wed 7/1/26 | Fri 7/24/26
6594 | 2753 | Future Task |  |  | D439 | Joy Schneider | Create | Create June 2026 Monthly Performance Report | 3 hrs | 7 days | Wed 7/1/26 | Fri 7/10/26 | 2751 | 2754 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6498 | 2754 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 7/13/26 | Mon 7/13/26 | 2753 | 2755 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6499 | 2755 | Future Task |  |  | D439 | Joy Schneider | Submit | DEL D439 - Monthly Performance Report (June 2026) - Submit | 0 hrs | 0 days | Mon 7/13/26 | Mon 7/13/26 | 2754 | 2756 |  | Joy Schneider
6500 | 2756 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Department QC | 1 hr | 7 days | Tue 7/14/26 | Wed 7/22/26 | 2755 | 2757 |  | Gabriela Gibson
6501 | 2757 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Contract Manager Review | 2 hrs | 2 days | Thu 7/23/26 | Fri 7/24/26 | 2756 | 2758 |  | Sean Buchanan
6502 | 2758 | Future Task |  |  | D439 | Joy Schneider | Accept | DEL D439 - Monthly Performance Report (June 2026) - Accept | 0 hrs | 0 days | Fri 7/24/26 | Fri 7/24/26 | 2757 | 2760 |  | Sean Buchanan
6503 | 2759 | Future Task |  |  | D441 | Joy Schneider |  | D441 - Monthly Performance Report (July 2026) | 10 hrs | 17 days | Mon 8/3/26 | Tue 8/25/26
6593 | 2760 | Future Task |  |  | D441 | Joy Schneider | Create | Create July 2026 Monthly Performance Report | 3 hrs | 7 days | Mon 8/3/26 | Tue 8/11/26 | 2758 | 2761 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6504 | 2761 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 8/12/26 | Wed 8/12/26 | 2760 | 2762 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6505 | 2762 | Future Task |  |  | D441 | Joy Schneider | Submit | DEL D441 - Monthly Performance Report (July 2026) - Submit | 0 hrs | 0 days | Wed 8/12/26 | Wed 8/12/26 | 2761 | 2763 |  | Joy Schneider
6506 | 2763 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Department QC | 1 hr | 7 days | Thu 8/13/26 | Fri 8/21/26 | 2762 | 2764 |  | Gabriela Gibson
6507 | 2764 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Contract Manager Review | 2 hrs | 2 days | Mon 8/24/26 | Tue 8/25/26 | 2763 | 2765 |  | Sean Buchanan
6508 | 2765 | Future Task |  |  | D441 | Joy Schneider | Accept | DEL D441 - Monthly Performance Report (July 2026) - Accept | 0 hrs | 0 days | Tue 8/25/26 | Tue 8/25/26 | 2764 | 2767 |  | Sean Buchanan
6509 | 2766 | Future Task |  |  | D442 | Joy Schneider |  | D442 - Monthly Performance Report (August 2026) | 10 hrs | 17 days | Tue 9/1/26 | Thu 9/24/26
6592 | 2767 | Future Task |  |  | D442 | Joy Schneider | Create | Create August 2026 Monthly Performance Report | 3 hrs | 7 days | Tue 9/1/26 | Thu 9/10/26 | 2765 | 2768 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6510 | 2768 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 9/11/26 | Fri 9/11/26 | 2767 | 2769 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6511 | 2769 | Future Task |  |  | D442 | Joy Schneider | Submit | DEL D442 - Monthly Performance Report (August 2026) - Submit | 0 hrs | 0 days | Fri 9/11/26 | Fri 9/11/26 | 2768 | 2770 |  | Joy Schneider
6512 | 2770 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Department QC | 1 hr | 7 days | Mon 9/14/26 | Tue 9/22/26 | 2769 | 2771 |  | Gabriela Gibson
6513 | 2771 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Contract Manager Review | 2 hrs | 2 days | Wed 9/23/26 | Thu 9/24/26 | 2770 | 2772 |  | Sean Buchanan
6514 | 2772 | Future Task |  |  | D442 | Joy Schneider | Accept | DEL D442 - Monthly Performance Report (August 2026) - Accept | 0 hrs | 0 days | Thu 9/24/26 | Thu 9/24/26 | 2771 | 2774 |  | Sean Buchanan
6515 | 2773 | Future Task |  |  | D443 | Joy Schneider |  | D443 - Monthly Performance Report (September 2026) | 10 hrs | 17 days | Thu 10/1/26 | Fri 10/23/26
6591 | 2774 | Future Task |  |  | D443 | Joy Schneider | Create | Create September 2026 Monthly Performance Report | 3 hrs | 7 days | Thu 10/1/26 | Fri 10/9/26 | 2772 | 2775 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6516 | 2775 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 10/12/26 | Mon 10/12/26 | 2774 | 2776 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6517 | 2776 | Future Task |  |  | D443 | Joy Schneider | Submit | DEL D443 - Monthly Performance Report (September 2026) - Submit | 0 hrs | 0 days | Mon 10/12/26 | Mon 10/12/26 | 2775 | 2777 |  | Joy Schneider
6518 | 2777 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Department QC | 1 hr | 7 days | Tue 10/13/26 | Wed 10/21/26 | 2776 | 2778 |  | Gabriela Gibson
6519 | 2778 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Contract Manager Review | 2 hrs | 2 days | Thu 10/22/26 | Fri 10/23/26 | 2777 | 2779 |  | Sean Buchanan
6520 | 2779 | Future Task |  |  | D443 | Joy Schneider | Accept | DEL D443 - Monthly Performance Report (September 2026) - Accept | 0 hrs | 0 days | Fri 10/23/26 | Fri 10/23/26 | 2778 | 2781 |  | Sean Buchanan
6521 | 2780 | Future Task |  |  | D444 | Joy Schneider |  | D444 - Monthly Performance Report (October 2026) | 10 hrs | 17 days | Mon 11/2/26 | Wed 11/25/26
6590 | 2781 | Future Task |  |  | D444 | Joy Schneider | Create | Create October 2026 Monthly Performance Report | 3 hrs | 7 days | Mon 11/2/26 | Tue 11/10/26 | 2779 | 2782 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6522 | 2782 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 11/12/26 | Thu 11/12/26 | 2781 | 2783 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6523 | 2783 | Future Task |  |  | D444 | Joy Schneider | Submit | DEL D444 - Monthly Performance Report (October 2026) - Submit | 0 hrs | 0 days | Thu 11/12/26 | Thu 11/12/26 | 2782 | 2784 |  | Joy Schneider
6524 | 2784 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Department QC | 1 hr | 7 days | Fri 11/13/26 | Mon 11/23/26 | 2783 | 2785 |  | Gabriela Gibson
6525 | 2785 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Contract Manager Review | 2 hrs | 2 days | Tue 11/24/26 | Wed 11/25/26 | 2784 | 2786 |  | Sean Buchanan
6526 | 2786 | Future Task |  |  | D444 | Joy Schneider | Accept | DEL D444 - Monthly Performance Report (October 2026) - Accept | 0 hrs | 0 days | Wed 11/25/26 | Wed 11/25/26 | 2785 | 2788 |  | Sean Buchanan
6527 | 2787 | Future Task |  |  | D445 | Joy Schneider |  | D445 - Monthly Performance Report (November 2026) | 10 hrs | 17 days | Tue 12/1/26 | Wed 12/23/26
6589 | 2788 | Future Task |  |  | D445 | Joy Schneider | Create | Create November 2026 Monthly Performance Report | 3 hrs | 7 days | Tue 12/1/26 | Wed 12/9/26 | 2786 | 2789 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6528 | 2789 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Thu 12/10/26 | Thu 12/10/26 | 2788 | 2790 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6529 | 2790 | Future Task |  |  | D445 | Joy Schneider | Submit | DEL D445 - Monthly Performance Report (November 2026) - Submit | 0 hrs | 0 days | Thu 12/10/26 | Thu 12/10/26 | 2789 | 2791 |  | Joy Schneider
6530 | 2791 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Department QC | 1 hr | 7 days | Fri 12/11/26 | Mon 12/21/26 | 2790 | 2792 |  | Gabriela Gibson
6531 | 2792 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Contract Manager Review | 2 hrs | 2 days | Tue 12/22/26 | Wed 12/23/26 | 2791 | 2793 |  | Sean Buchanan
6532 | 2793 | Future Task |  |  | D445 | Joy Schneider | Accept | DEL D445 - Monthly Performance Report (November 2026) - Accept | 0 hrs | 0 days | Wed 12/23/26 | Wed 12/23/26 | 2792 | 2795 |  | Sean Buchanan
6533 | 2794 | Future Task |  |  | D446 | Joy Schneider |  | D446 - Monthly Performance Report (December 2026) | 10 hrs | 17 days | Mon 1/4/27 | Wed 1/27/27
6588 | 2795 | Future Task |  |  | D446 | Joy Schneider | Create | Create December 2026 Monthly Performance Report | 3 hrs | 7 days | Mon 1/4/27 | Tue 1/12/27 | 2793 | 2796 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6534 | 2796 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 1/13/27 | Wed 1/13/27 | 2795 | 2797 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6535 | 2797 | Future Task |  |  | D446 | Joy Schneider | Submit | DEL D446 - Monthly Performance Report (December 2026) - Submit | 0 hrs | 0 days | Wed 1/13/27 | Wed 1/13/27 | 2796 | 2798 |  | Joy Schneider
6536 | 2798 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Department QC | 1 hr | 7 days | Thu 1/14/27 | Mon 1/25/27 | 2797 | 2799 |  | Gabriela Gibson
6537 | 2799 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Contract Manager Review | 2 hrs | 2 days | Tue 1/26/27 | Wed 1/27/27 | 2798 | 2800 |  | Sean Buchanan
6538 | 2800 | Future Task |  |  | D446 | Joy Schneider | Accept | DEL D446 - Monthly Performance Report (December 2026) - Accept | 0 hrs | 0 days | Wed 1/27/27 | Wed 1/27/27 | 2799 | 2802 |  | Sean Buchanan
6539 | 2801 | Future Task |  |  | D447 | Joy Schneider |  | D447 - Monthly Performance Report (January 2027) | 10 hrs | 17 days | Mon 2/1/27 | Tue 2/23/27
6587 | 2802 | Future Task |  |  | D447 | Joy Schneider | Create | Create January 2027 Monthly Performance Report | 3 hrs | 7 days | Mon 2/1/27 | Tue 2/9/27 | 2800 | 2803 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6540 | 2803 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 2/10/27 | Wed 2/10/27 | 2802 | 2804 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6541 | 2804 | Future Task |  |  | D447 | Joy Schneider | Submit | DEL D447 - Monthly Performance Report (January 2027) - Submit | 0 hrs | 0 days | Wed 2/10/27 | Wed 2/10/27 | 2803 | 2805 |  | Joy Schneider
6542 | 2805 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Department QC | 1 hr | 7 days | Thu 2/11/27 | Fri 2/19/27 | 2804 | 2806 |  | Gabriela Gibson
6543 | 2806 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Contract Manager Review | 2 hrs | 2 days | Mon 2/22/27 | Tue 2/23/27 | 2805 | 2807 |  | Sean Buchanan
6544 | 2807 | Future Task |  |  | D447 | Joy Schneider | Accept | DEL D447 - Monthly Performance Report (January 2027) - Accept | 0 hrs | 0 days | Tue 2/23/27 | Tue 2/23/27 | 2806 | 2809 |  | Sean Buchanan
6545 | 2808 | Future Task |  |  | D448 | Joy Schneider |  | D448 - Monthly Performance Report (February 2027) | 10 hrs | 17 days | Mon 3/1/27 | Tue 3/23/27
6586 | 2809 | Future Task |  |  | D448 | Joy Schneider | Create | Create February 2027 Monthly Performance Report | 3 hrs | 7 days | Mon 3/1/27 | Tue 3/9/27 | 2807 | 2810 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6546 | 2810 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 3/10/27 | Wed 3/10/27 | 2809 | 2811 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6547 | 2811 | Future Task |  |  | D448 | Joy Schneider | Submit | DEL D448 - Monthly Performance Report (February 2027) - Submit | 0 hrs | 0 days | Wed 3/10/27 | Wed 3/10/27 | 2810 | 2812 |  | Joy Schneider
6548 | 2812 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Department QC | 1 hr | 7 days | Thu 3/11/27 | Fri 3/19/27 | 2811 | 2813 |  | Gabriela Gibson
6549 | 2813 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Contract Manager Review | 2 hrs | 2 days | Mon 3/22/27 | Tue 3/23/27 | 2812 | 2814 |  | Sean Buchanan
6550 | 2814 | Future Task |  |  | D448 | Joy Schneider | Accept | DEL D448 - Monthly Performance Report (February 2027) - Accept | 0 hrs | 0 days | Tue 3/23/27 | Tue 3/23/27 | 2813 | 2816 |  | Sean Buchanan
6551 | 2815 | Future Task |  |  | D449 | Joy Schneider |  | D449 - Monthly Performance Report (March 2027) | 10 hrs | 17 days | Thu 4/1/27 | Fri 4/23/27
6585 | 2816 | Future Task |  |  | D449 | Joy Schneider | Create | Create March 2027 Monthly Performance Report | 3 hrs | 7 days | Thu 4/1/27 | Fri 4/9/27 | 2814 | 2817 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6552 | 2817 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Mon 4/12/27 | Mon 4/12/27 | 2816 | 2818 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6553 | 2818 | Future Task |  |  | D449 | Joy Schneider | Submit | DEL D449 - Monthly Performance Report (March 2027) - Submit | 0 hrs | 0 days | Mon 4/12/27 | Mon 4/12/27 | 2817 | 2819 |  | Joy Schneider
6554 | 2819 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Department QC | 1 hr | 7 days | Tue 4/13/27 | Wed 4/21/27 | 2818 | 2820 |  | Gabriela Gibson
6555 | 2820 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Contract Manager Review | 2 hrs | 2 days | Thu 4/22/27 | Fri 4/23/27 | 2819 | 2821 |  | Sean Buchanan
6556 | 2821 | Future Task |  |  | D449 | Joy Schneider | Accept | DEL D449 - Monthly Performance Report (March 2027) - Accept | 0 hrs | 0 days | Fri 4/23/27 | Fri 4/23/27 | 2820 | 2823 |  | Sean Buchanan
6557 | 2822 | Future Task |  |  | D450 | Joy Schneider |  | D450 - Monthly Performance Report (April 2027) | 10 hrs | 17 days | Mon 5/3/27 | Tue 5/25/27
6584 | 2823 | Future Task |  |  | D450 | Joy Schneider | Create | Create April 2027 Monthly Performance Report | 3 hrs | 7 days | Mon 5/3/27 | Tue 5/11/27 | 2821 | 2824 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6558 | 2824 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 5/12/27 | Wed 5/12/27 | 2823 | 2825 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6559 | 2825 | Future Task |  |  | D450 | Joy Schneider | Submit | DEL D450 - Monthly Performance Report (April 2027) - Submit | 0 hrs | 0 days | Wed 5/12/27 | Wed 5/12/27 | 2824 | 2826 |  | Joy Schneider
6560 | 2826 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Department QC | 1 hr | 7 days | Thu 5/13/27 | Fri 5/21/27 | 2825 | 2827 |  | Gabriela Gibson
6561 | 2827 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Contract Manager Review | 2 hrs | 2 days | Mon 5/24/27 | Tue 5/25/27 | 2826 | 2828 |  | Sean Buchanan
6562 | 2828 | Future Task |  |  | D450 | Joy Schneider | Accept | DEL D450 - Monthly Performance Report (April 2027) - Accept | 0 hrs | 0 days | Tue 5/25/27 | Tue 5/25/27 | 2827 | 2830 |  | Sean Buchanan
6563 | 2829 | Future Task |  |  | D451 | Joy Schneider |  | D451 - Monthly Performance Report (May 2027) | 10 hrs | 17 days | Wed 6/2/27 | Thu 6/24/27
6583 | 2830 | Future Task |  |  | D451 | Joy Schneider | Create | Create May 2027 Monthly Performance Report | 3 hrs | 7 days | Wed 6/2/27 | Thu 6/10/27 | 2828 | 2831 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6564 | 2831 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Fri 6/11/27 | Fri 6/11/27 | 2830 | 2832 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6565 | 2832 | Future Task |  |  | D451 | Joy Schneider | Submit | DEL D451 - Monthly Performance Report (May 2027) - Submit | 0 hrs | 0 days | Fri 6/11/27 | Fri 6/11/27 | 2831 | 2833 |  | Joy Schneider
6566 | 2833 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Department QC | 1 hr | 7 days | Mon 6/14/27 | Tue 6/22/27 | 2832 | 2834 |  | Gabriela Gibson
6567 | 2834 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Contract Manager Review | 2 hrs | 2 days | Wed 6/23/27 | Thu 6/24/27 | 2833 | 2835 |  | Sean Buchanan
6568 | 2835 | Future Task |  |  | D451 | Joy Schneider | Accept | DEL D451 - Monthly Performance Report (May 2027) - Accept | 0 hrs | 0 days | Thu 6/24/27 | Thu 6/24/27 | 2834 | 2837 |  | Sean Buchanan
6569 | 2836 | Future Task |  |  | D694 | Joy Schneider |  | D694 - Monthly Performance Report (June 2027) | 10 hrs | 17 days | Thu 7/1/27 | Mon 7/26/27
6582 | 2837 | Future Task |  |  | D694 | Joy Schneider | Create | Create June 2027 Monthly Performance Report | 3 hrs | 7 days | Thu 7/1/27 | Mon 7/12/27 | 2835 | 2838 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6570 | 2838 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Tue 7/13/27 | Tue 7/13/27 | 2837 | 2839 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6571 | 2839 | Future Task |  |  | D694 | Joy Schneider | Submit | DEL D694 - Monthly Performance Report (June 2027) - Submit | 0 hrs | 0 days | Tue 7/13/27 | Tue 7/13/27 | 2838 | 2840 |  | Joy Schneider
6572 | 2840 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Department QC | 1 hr | 7 days | Wed 7/14/27 | Thu 7/22/27 | 2839 | 2841 |  | Gabriela Gibson
6573 | 2841 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Contract Manager Review | 2 hrs | 2 days | Fri 7/23/27 | Mon 7/26/27 | 2840 | 2842 |  | Sean Buchanan
6574 | 2842 | Future Task |  |  | D694 | Joy Schneider | Accept | DEL D694 - Monthly Performance Report (June 2027) - Accept | 0 hrs | 0 days | Mon 7/26/27 | Mon 7/26/27 | 2841 | 2844 |  | Sean Buchanan
6575 | 2843 | Future Task |  |  | D695 | Joy Schneider |  | D695 - Monthly Performance Report (July 2027) | 10 hrs | 17 days | Mon 8/2/27 | Tue 8/24/27
6581 | 2844 | Future Task |  |  | D695 | Joy Schneider | Create | Create July 2027 Monthly Performance Report | 3 hrs | 7 days | Mon 8/2/27 | Tue 8/10/27 | 2842 | 2845 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6576 | 2845 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | Wed 8/11/27 | Wed 8/11/27 | 2844 | 2846 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6577 | 2846 | Future Task |  |  | D695 | Joy Schneider | Submit | DEL D695 - Monthly Performance Report (July 2027) - Submit | 0 hrs | 0 days | Wed 8/11/27 | Wed 8/11/27 | 2845 | 2847 |  | Joy Schneider
6578 | 2847 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Department QC | 1 hr | 7 days | Thu 8/12/27 | Fri 8/20/27 | 2846 | 2848 |  | Gabriela Gibson
6579 | 2848 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Contract Manager Review | 2 hrs | 2 days | Mon 8/23/27 | Tue 8/24/27 | 2847 | 2849 |  | Sean Buchanan
6580 | 2849 | Future Task |  |  | D695 | Joy Schneider | Accept | DEL D695 - Monthly Performance Report (July 2027) - Accept | 0 hrs | 0 days | Tue 8/24/27 | Tue 8/24/27 | 2848 |  |  | Sean Buchanan
4047 | 2850 | Future Task | [5 empty] | Quarterly Newsletter for DDI of Reporting Functionality | 132 hrs | 658 days | Wed 6/21/23 | Mon 2/2/26
4048 | 2851 | Future Task | [5 empty] | Quarterly Newsletter | 132 hrs | 658 days | Wed 6/21/23 | Mon 2/2/26
4049 | 2852 | Future Task | [5 empty] | Quarterly Newsletter FY 22-23 Q4 | 12 hrs | 17 days | Wed 6/21/23 | Fri 7/14/23
4050 | 2853 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Wed 6/21/23 | Tue 6/27/23 |  | 2854 |  | Jennifer Grant,Jennifer Reeves
4051 | 2854 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | Wed 6/28/23 | Wed 7/5/23 | 2853 | 2855 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4052 | 2855 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Thu 7/6/23 | Wed 7/12/23 | 2854 | 2856 |  | Jimmy Cox,Steven Fielder
4053 | 2856 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | Thu 7/13/23 | Fri 7/14/23 | 2855 | 2858 |  | Dusti Kincl
4054 | 2857 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q1 | 12 hrs | 17 days | Fri 9/22/23 | Mon 10/16/23
4055 | 2858 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 9/22/23 | Thu 9/28/23 | 2856 | 2859 |  | Jennifer Grant,Jennifer Reeves
4056 | 2859 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 9/29/23 | Thu 10/5/23 | 2858 | 2860 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4057 | 2860 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 10/6/23 | Thu 10/12/23 | 2859 | 2861 |  | Jimmy Cox,Steven Fielder
4058 | 2861 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 10/13/23 | Mon 10/16/23 | 2860 | 2863 |  | Dusti Kincl
4059 | 2862 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q2 | 12 hrs | 17 days | Mon 12/18/23 | Thu 1/11/24
4060 | 2863 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 12/18/23 | Fri 12/22/23 | 2861 | 2864 |  | Jennifer Grant,Jennifer Reeves
4061 | 2864 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | Tue 12/26/23 | Tue 1/2/24 | 2863 | 2865 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4062 | 2865 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Wed 1/3/24 | Tue 1/9/24 | 2864 | 2866 |  | Jimmy Cox,Steven Fielder
4063 | 2866 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | Wed 1/10/24 | Thu 1/11/24 | 2865 | 2868 |  | Dusti Kincl
4064 | 2867 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q3 | 12 hrs | 17 days | Fri 3/22/24 | Mon 4/15/24
4065 | 2868 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 3/22/24 | Thu 3/28/24 | 2866 | 2869 |  | Jennifer Grant,Jennifer Reeves
4066 | 2869 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 3/29/24 | Thu 4/4/24 | 2868 | 2870 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4067 | 2870 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 4/5/24 | Thu 4/11/24 | 2869 | 2871 |  | Jimmy Cox,Steven Fielder
4068 | 2871 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 4/12/24 | Mon 4/15/24 | 2870 | 2873 |  | Dusti Kincl
4069 | 2872 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q4 | 12 hrs | 17 days | Thu 6/20/24 | Mon 7/15/24
4070 | 2873 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Thu 6/20/24 | Wed 6/26/24 | 2871 | 2874 |  | Jennifer Grant,Jennifer Reeves
4071 | 2874 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | Thu 6/27/24 | Wed 7/3/24 | 2873 | 2875 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4072 | 2875 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 7/5/24 | Thu 7/11/24 | 2874 | 2876 |  | Jimmy Cox,Steven Fielder
4073 | 2876 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 7/12/24 | Mon 7/15/24 | 2875 | 2878 |  | Dusti Kincl
4074 | 2877 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q1 | 12 hrs | 17 days | Mon 9/23/24 | Tue 10/15/24
4075 | 2878 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 9/23/24 | Fri 9/27/24 | 2876 | 2879 |  | Jennifer Grant,Jennifer Reeves
4076 | 2879 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | Mon 9/30/24 | Fri 10/4/24 | 2878 | 2880 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4077 | 2880 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Mon 10/7/24 | Fri 10/11/24 | 2879 | 2881 |  | Jimmy Cox,Steven Fielder
4078 | 2881 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | Mon 10/14/24 | Tue 10/15/24 | 2880 | 2883 |  | Dusti Kincl
4079 | 2882 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q2 | 12 hrs | 17 days | Mon 12/16/24 | Thu 1/9/25
4080 | 2883 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 12/16/24 | Fri 12/20/24 | 2881 | 2884 |  | Jennifer Grant,Jennifer Reeves
4081 | 2884 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | Mon 12/23/24 | Mon 12/30/24 | 2883 | 2885 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4082 | 2885 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Tue 12/31/24 | Tue 1/7/25 | 2884 | 2886 |  | Jimmy Cox,Steven Fielder
4083 | 2886 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | Wed 1/8/25 | Thu 1/9/25 | 2885 | 2888 |  | Dusti Kincl
4084 | 2887 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q3 | 12 hrs | 17 days | Mon 3/24/25 | Tue 4/15/25
4085 | 2888 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Mon 3/24/25 | Fri 3/28/25 | 2886 | 2889 |  | Jennifer Grant,Jennifer Reeves
4086 | 2889 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | Mon 3/31/25 | Fri 4/4/25 | 2888 | 2890 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4087 | 2890 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Mon 4/7/25 | Fri 4/11/25 | 2889 | 2891 |  | Jimmy Cox,Steven Fielder
4088 | 2891 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | Mon 4/14/25 | Tue 4/15/25 | 2890 | 2893 |  | Dusti Kincl
4089 | 2892 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q4 | 12 hrs | 17 days | Fri 6/20/25 | Tue 7/15/25
4090 | 2893 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 6/20/25 | Thu 6/26/25 | 2891 | 2894 |  | Jennifer Grant,Jennifer Reeves
4091 | 2894 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 6/27/25 | Thu 7/3/25 | 2893 | 2895 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4092 | 2895 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Mon 7/7/25 | Fri 7/11/25 | 2894 | 2896 |  | Jimmy Cox,Steven Fielder
4093 | 2896 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | Mon 7/14/25 | Tue 7/15/25 | 2895 | 2898 |  | Dusti Kincl
4094 | 2897 | Future Task | [5 empty] | Quarterly Newsletter FY 25-26 Q1 | 12 hrs | 17 days | Fri 9/26/25 | Mon 10/20/25
4095 | 2898 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Fri 9/26/25 | Thu 10/2/25 | 2896 | 2899 |  | Jennifer Grant,Jennifer Reeves
4096 | 2899 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | Fri 10/3/25 | Thu 10/9/25 | 2898 | 2900 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4097 | 2900 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 10/10/25 | Thu 10/16/25 | 2899 | 2901 |  | Jimmy Cox,Steven Fielder
4098 | 2901 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 10/17/25 | Mon 10/20/25 | 2900 | 2903 |  | Dusti Kincl
4099 | 2902 | Future Task | [5 empty] | Quarterly Newsletter FY 25-26 Q2 | 12 hrs | 17 days | Thu 1/8/26 | Mon 2/2/26
4100 | 2903 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | Thu 1/8/26 | Wed 1/14/26 | 2901 | 2904 |  | Jennifer Grant,Jennifer Reeves
4101 | 2904 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | Thu 1/15/26 | Thu 1/22/26 | 2903 | 2905 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4102 | 2905 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | Fri 1/23/26 | Thu 1/29/26 | 2904 | 2906 |  | Jimmy Cox,Steven Fielder
4103 | 2906 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | Fri 1/30/26 | Mon 2/2/26 | 2905 |  |  | Dusti Kincl

## DO NOT EDIT - Prior to 6.5.23 (hidden)
Unique ID | ID | Status | Critical Path | RW | DEL, WP, SG # | Task Coordinator | Task Type | Task Name | Work | Duration | Start | Finish | Predecessors | Successors | Notes | Resource Names | Requested Updates | Requested By
0 | 0 | Late | [5 empty] | Project Schedule (Financials, Payroll, Data Warehouse and Business Intelligence) | 23,243.58 hrs | 1177 days | 2023-04-26 | 2027-12-28
7152 | 1 | Complete |  |  |  | Jimmy Cox |  | Amendment 8 Executed | 0 hrs | 0 days | 2023-04-26 | 2023-04-26 |  | 6,30FS+3 days,49FS+47 days,86FS+27 days,107FS+27 days,212FS+90 days,355FS+112 days,185FS+27 days,199FS+27 days,587FS+47 days,68FS+27 days,147,166,225,239,253,330,342,395,451,473,493,513,533,546,640,682,741,781,806,825,843,885,910,929,1001,1019,1044,1058... |  | Jimmy Cox
2 | 2 | Late | [5 empty] | Implementation | 16,003.58 hrs | 699 days | 2023-04-26 | 2026-02-04
3769 | 3 | Late | [5 empty] | Design | 5,188 hrs | 475 days | 2023-04-26 | 2025-03-14
7155 | 4 | Future Task | Yes |  | SG1 | Jimmy Cox | Milestone | Stage Gate 1: Ready to Start Build | 0 hrs | 0 days | 2023-10-23 | 2023-10-23 | 47,57 |  | Nov/Dec 2023 | Jimmy Cox,Angie Robertson,Matt Cole
3793 | 5 | Late | Yes |  | D635 | Joy Schneider |  | D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) | 450 hrs | 38 days | 2023-05-08 | 2023-06-29
7130 | 6 | Complete |  |  | D635 | Joy Schneider |  | Develop Outline of Project Schedule | 2 hrs | 1 day | 2023-05-08 | 2023-05-08 | 1 | 7SS |  | Joy Schneider,Francisca Li
7131 | 7 | Complete |  |  | D635 | Joy Schneider |  | Create New Schedule Tasks Workbook | 4 hrs | 1 day | 2023-05-08 | 2023-05-08 | 6SS | 8,9,10FS+1 day |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner
7132 | 8 | Complete |  |  | D635 | Joy Schneider |  | Gather Tasks from State Architects | 60 hrs | 4 days | 2023-05-09 | 2023-05-12 | 7 | 19 |  | Julian Gotreaux,Gabriela Gibson,Tommy Werner,Angie Robertson,Deana Metcalf,Carolyn Hicks,Jennifer Reeves,Matthew Breeding
7133 | 9 | Complete |  |  | D635 | Joy Schneider |  | Load Amendment 8 Deliverables and Work Products to Project Schedule | 4 hrs | 2 days | 2023-05-09 | 2023-05-10 | 7 | 19 |  | Joy Schneider,Francisca Li
7134 | 10 | Complete |  |  | D635 | Joy Schneider |  | Load Resources into Project Schedule | 8 hrs | 1 day | 2023-05-10 | 2023-05-10 | 7FS+1 day | 11 |  | Joy Schneider,Francisca Li
7135 | 11 | Complete |  |  | D635 | Joy Schneider |  | Add and Refine Work Activities for Amendment 8 Deliverables | 17 hrs | 2 days | 2023-05-11 | 2023-05-12 | 10 | 12SS+1 day |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole
7136 | 12 | Complete |  |  | D635 | Joy Schneider |  | Add Tasks from State Architects | 10 hrs | 1 day | 2023-05-12 | 2023-05-12 | 11SS+1 day | 13 |  | Joy Schneider,Francisca Li
7137 | 13 | Late |  |  | D635 | Joy Schneider |  | Provide Project Schedule Export Reports | 2 hrs | 1 day | 2023-05-15 | 2023-05-15 | 12 | 14SS,15SS |  | Joy Schneider,Francisca Li
7138 | 14 | Late |  |  | D635 | Joy Schneider |  | Add and Refine Work Activities for Amendment 8 Work Products | 60 hrs | 5 days | 2023-05-15 | 2023-05-19 | 13SS | 19 |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole
7139 | 15 | Complete |  |  | D635 | Joy Schneider |  | Project Schedule Working Sessions | 85 hrs | 5 days | 2023-05-15 | 2023-05-19 | 13SS | 16 |  | Joy Schneider,Francisca Li,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Manojkumar Gurjar,Yogesh Deshmukh,Matt Cole,Angie Robertson,Deana Metcalf,Matthew Breeding,Carolyn Hicks,Jimmy Cox,Jennifer Reeves
7140 | 16 | Late |  |  | D635 | Joy Schneider |  | Refine Work Activities for Non-SSI Deliverables and Work Products | 26 hrs | 5 days | 2023-05-22 | 2023-05-26 | 15 | 17SS+2 days |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Gabriela Gibson
7141 | 17 | Late |  |  | D635 | Joy Schneider |  | Define Tasks to Assign to Critical Path Column | 25 hrs | 3 days | 2023-05-24 | 2023-05-26 | 16SS+2 days | 18 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Jimmy Cox,Matt Cole
7142 | 18 | Future Task |  |  | D635 | Joy Schneider |  | Provide Project Schedule Export Reports and Refine Based on Input | 70 hrs | 9 days | 2023-05-30 | 2023-06-09 | 17 | 19 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Deana Metcalf,Matthew Breeding,Carlos Luis,Jimmy Cox,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Manojkumar Gurjar,Yogesh Deshmukh,Matt Cole,Jennifer Reeves
7143 | 19 | Future Task |  |  | D635 | Joy Schneider |  | Conduct Project Schedule Baseline Prep Meeting | 36 hrs | 1 day | 2023-06-12 | 2023-06-12 | 18,8,9,14 | 20 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Angie Robertson,Deana Metcalf,Matthew Breeding,Carolyn Hicks,Jimmy Cox,Mary Punty,Stacey Terry,Bryan Sohayda,Kurt Meisner,Yogesh Deshmukh,Manojkumar Gurjar,Matt Cole,Gabriela Gibson,Jennifer Reeves
4271 | 20 | Future Task |  |  | D635 | Joy Schneider | Submit | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Draft Submission | 0 hrs | 0 days | 2023-06-12 | 2023-06-12 | 19 | 21 |  | Joy Schneider
4272 | 21 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Pre-Submission Collaborative Review | 14 hrs | 3 days | 2023-06-13 | 2023-06-15 | 20 | 22 |  | Joy Schneider,Francisca Li,Julian Gotreaux,Tommy Werner,Gabriela Gibson,Jenifer Hartsfield,Angie Robertson
4273 | 22 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Style Guide Review | 1 hr | 1 day | 2023-06-16 | 2023-06-16 | 21 | 23 |  | Dusti Kincl
4274 | 23 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Final Collaborative Review | 10 hrs | 3 days | 2023-06-19 | 2023-06-21 | 22 | 24 |  | Joy Schneider,Francisca Li,Angie Robertson,Jimmy Cox,Jennifer Reeves,Deana Metcalf,Matthew Breeding,Carolyn Hicks
4275 | 24 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Accenture QC | 4 hrs | 2 days | 2023-06-22 | 2023-06-23 | 23 | 25 |  | Joy Schneider
4276 | 25 | Future Task |  |  | D635 | Joy Schneider | Submit | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Submit | 0 hrs | 0 days | 2023-06-23 | 2023-06-23 | 24 | 26 |  | Joy Schneider
4277 | 26 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Department QC | 4 hrs | 1 day | 2023-06-26 | 2023-06-26 | 25 | 27 |  | Tommy Werner,Gabriela Gibson
4278 | 27 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Contract Manager Review | 8 hrs | 3 days | 2023-06-27 | 2023-06-29 | 26 | 28 |  | Sean Buchanan
4279 | 28 | Future Task |  |  | D635 | Joy Schneider | Accept | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Accept | 0 hrs | 0 days | 2023-06-29 | 2023-06-29 | 27 | 2291 | 2023-06-01 | Sean Buchanan
4280 | 29 | Late | Yes |  | D636 | Stacey Terry |  | D636 - Completion of Solution Design (Requirements) Segment I | 309 hrs | 82 days | 2023-05-01 | 2023-08-24
4308 | 30 | Late |  |  | D636 | Stacey Terry |  | Identify Functional Designs (Segment I) | 50 hrs | 10 days | 2023-05-01 | 2023-05-12 | 1FS+3 days | 31 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4281 | 31 | Late |  |  | D636 | Stacey Terry | Create | DED D636 - Completion of Solution Design (Requirements) Segment I - Create | 8 hrs | 10 days | 2023-05-15 | 2023-05-26 | 30 | 32 |  | Stacey Terry,Mary Punty
4282 | 32 | Future Task |  |  | D636 | Stacey Terry | Submit | DED D636 - Completion of Solution Design (Requirements) Segment I - Submit | 0 hrs | 0 days | 2023-05-26 | 2023-05-26 | 31 | 33 |  | Stacey Terry,Joy Schneider
4283 | 33 | Future Task |  |  | D636 | Stacey Terry | Review | DED D636 - Completion of Solution Design (Requirements) Segment I - Collaborative Review | 24 hrs | 4 days | 2023-05-30 | 2023-06-02 | 32 | 34 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4284 | 34 | Future Task |  |  | D636 | Stacey Terry | Approve | DED D636 - Completion of Solution Design (Requirements) Segment I - Approve | 0 hrs | 0 days | 2023-06-02 | 2023-06-02 | 33 | 35 |  | Jimmy Cox
4309 | 35 | Future Task |  |  | D636 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs (Segment I) | 50 hrs | 5 days | 2023-06-05 | 2023-06-09 | 34 | 36 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4310 | 36 | Future Task |  |  | D636 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment I) | 50 hrs | 4 days | 2023-06-12 | 2023-06-15 | 35 | 37 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4311 | 37 | Future Task |  |  | D636 | Stacey Terry |  | Create, Review and Approve Functional Design Documents (Segment I) | 50 hrs | 32 days | 2023-06-16 | 2023-08-01 | 36 | 38FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis... | RW/Communication - Segment 1 Workshop? | NK
4312 | 38 | Future Task |  |  | D636 | Stacey Terry |  | Create Summary Document | 20 hrs | 11 days | 2023-07-18 | 2023-08-01 | 37FS-11 days | 39,1542SS,1586SS,1629SS,1454,1499 |  | Deana Metcalf,Stacey Terry,Mary Punty
4285 | 39 | Future Task |  |  | D636 | Stacey Terry | Submit | DEL D636 - Completion of Solution Design (Requirements) Segment I - Draft Submission | 0 hrs | 0 days | 2023-08-01 | 2023-08-01 | 38 | 40 |  | Stacey Terry,Joy Schneider
4286 | 40 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2023-08-02 | 2023-08-08 | 39 | 41 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4287 | 41 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Style Guide Review | 1 hr | 1 day | 2023-08-09 | 2023-08-09 | 40 | 42 |  | Dusti Kincl
4288 | 42 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Final Collaborative Review | 20 hrs | 5 days | 2023-08-10 | 2023-08-16 | 41 | 43 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4289 | 43 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Accenture QC | 4 hrs | 2 days | 2023-08-17 | 2023-08-18 | 42 | 44 |  | Joy Schneider
4290 | 44 | Future Task |  |  | D636 | Stacey Terry | Submit | DEL D636 - Completion of Solution Design (Requirements) Segment I - Submit | 0 hrs | 0 days | 2023-08-18 | 2023-08-18 | 43 | 451664 |  | Joy Schneider
4291 | 45 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Department QC | 4 hrs | 1 day | 2023-08-21 | 2023-08-21 | 44 | 46 |  | Tommy Werner,Gabriela Gibson
4292 | 46 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Contract Manager Review | 8 hrs | 3 days | 2023-08-22 | 2023-08-24 | 45 | 47 |  | Sean Buchanan
4293 | 47 | Future Task |  |  | D636 | Stacey Terry | Accept | DEL D636 - Completion of Solution Design (Requirements) Segment I - Accept | 0 hrs | 0 days | 2023-08-24 | 2023-08-24 | 46 | 216,580,584,585,4 | July 2023 (Aug 2023) | Sean Buchanan
4294 | 48 | Future Task | Yes |  | D637 | Stacey Terry |  | D637 - Completion of Solution Design (Requirements) Segment II | 342 hrs | 96 days | 2023-07-03 | 2023-11-16
4313 | 49 | Future Task |  |  | D637 | Stacey Terry |  | Identify Functional Designs (Segment II) | 50 hrs | 10 days | 2023-07-03 | 2023-07-17 | 1FS+47 days | 50 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4295 | 50 | Future Task |  |  | D637 | Stacey Terry | Create | DED D637 - Completion of Solution Design (Requirements) Segment II - Create | 16 hrs | 10 days | 2023-07-18 | 2023-07-31 | 49 | 51 |  | Stacey Terry,Mary Punty
4296 | 51 | Future Task |  |  | D637 | Stacey Terry | Submit | DED D637 - Completion of Solution Design (Requirements) Segment II - Submit | 0 hrs | 0 days | 2023-07-31 | 2023-07-31 | 50 | 52 |  | Stacey Terry,Joy Schneider
4297 | 52 | Future Task |  |  | D637 | Stacey Terry | Review | DED D637 - Completion of Solution Design (Requirements) Segment II - Collaborative Review | 24 hrs | 10 days | 2023-08-01 | 2023-08-14 | 51 | 53 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4298 | 53 | Future Task |  |  | D637 | Stacey Terry | Approve | DED D637 - Completion of Solution Design (Requirements) Segment II - Approve | 0 hrs | 0 days | 2023-08-14 | 2023-08-14 | 52 | 54 |  | Jimmy Cox
4314 | 54 | Future Task |  |  | D637 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs (Segment II) | 50 hrs | 4 days | 2023-08-15 | 2023-08-18 | 53 | 55 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4315 | 55 | Future Task |  |  | D637 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment II) | 50 hrs | 5 days | 2023-08-21 | 2023-08-25 | 54 | 56 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4316 | 56 | Future Task |  |  | D637 | Stacey Terry |  | Create, Review and Approve Functional Design Documents (Segment II) | 50 hrs | 40 days | 2023-08-28 | 2023-10-23 | 55 | 57FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis... | RW/Communication - Segment 1 Workshop? | NK
4317 | 57 | Future Task |  |  | D637 | Stacey Terry |  | Create Summary Document | 50 hrs | 11 days | 2023-10-09 | 2023-10-23 | 56FS-11 days | 58,1545SS,1411SS,1589SS+2 days,1632SS+5 days,1457,1502,4 |  | Deana Metcalf,Stacey Terry,Mary Punty
4299 | 58 | Future Task |  |  | D637 | Stacey Terry | Submit | DEL D637 - Completion of Solution Design (Requirements) Segment II - Draft Submission | 0 hrs | 0 days | 2023-10-23 | 2023-10-23 | 57 | 59 |  | Stacey Terry,Joy Schneider
4300 | 59 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2023-10-24 | 2023-10-30 | 58 | 60 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4301 | 60 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Style Guide Review | 1 hr | 1 day | 2023-10-31 | 2023-10-31 | 59 | 61 |  | Dusti Kincl
4302 | 61 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Final Collaborative Review | 20 hrs | 5 days | 2023-11-01 | 2023-11-07 | 60 | 62 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4303 | 62 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Accenture QC | 1 hr | 2 days | 2023-11-08 | 2023-11-09 | 61 | 63 |  | Francisca Li
4304 | 63 | Future Task |  |  | D637 | Stacey Terry | Submit | DEL D637 - Completion of Solution Design (Requirements) Segment II - Submit | 0 hrs | 0 days | 2023-11-09 | 2023-11-09 | 62 | 64 |  | Joy Schneider
4305 | 64 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Department QC | 2 hrs | 1 day | 2023-11-13 | 2023-11-13 | 63 | 65 |  | Tommy Werner,Gabriela Gibson
4306 | 65 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Contract Manager Review | 8 hrs | 3 days | 2023-11-14 | 2023-11-16 | 64 | 66 |  | Sean Buchanan
4307 | 66 | Future Task |  |  | D637 | Stacey Terry | Accept | DEL D637 - Completion of Solution Design (Requirements) Segment II - Accept | 0 hrs | 0 days | 2023-11-16 | 2023-11-16 | 65 | 580584585 | October 2023 (Nov 2023) | Sean Buchanan
5585 | 67 | Future Task |  |  | D638 | Manojkumar Gurjar |  | D638 - Updated Data Conversion and Migration Strategy | 213 hrs | 80 days | 2023-06-05 | 2023-09-26
5586 | 68 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | DED D638 - Updated Data Conversion and Migration Strategy - Create | 16 hrs | 10 days | 2023-06-05 | 2023-06-16 | 1FS+27 days | 69 |  | Manojkumar Gurjar,Kurt Meisner
5587 | 69 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DED D638 - Updated Data Conversion and Migration Strategy - Submit | 0 hrs | 0 days | 2023-06-16 | 2023-06-16 | 68 | 70 |  | Manojkumar Gurjar,Joy Schneider
5588 | 70 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DED D638 - Updated Data Conversion and Migration Strategy - Collaborative Review | 24 hrs | 10 days | 2023-06-19 | 2023-06-30 | 69 | 71 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5589 | 71 | Future Task |  |  | D638 | Manojkumar Gurjar | Approve | DED D638 - Updated Data Conversion and Migration Strategy - Approve | 0 hrs | 0 days | 2023-06-30 | 2023-06-30 | 70 | 72 |  | Jimmy Cox
5590 | 72 | Future Task |  |  | D638 | Manojkumar Gurjar |  | Define the approach for Data Cleansing | 8 hrs | 14 days | 2023-07-03 | 2023-07-21 | 71 | 73SS+4 days |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5591 | 73 | Future Task |  |  | D638 | Manojkumar Gurjar |  | Define Communication/Collaboration for Data Conversion approach | 8 hrs | 10 days | 2023-07-10 | 2023-07-21 | 72SS+4 days | 74 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5592 | 74 | Future Task |  |  | D638 | Manojkumar Gurjar |  | Identify Data Conversion Resources | 50 hrs | 10 days | 2023-07-24 | 2023-08-04 | 73 | 75 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer,Jeevan Mahajan,Janmejay Khare
5593 | 75 | Future Task |  |  | D638 | Manojkumar Gurjar |  | Updated Data Conversion and Migration Strategy Document | 50 hrs | 19 days | 2023-08-07 | 2023-08-31 | 74 | 76 |  | Manojkumar Gurjar,Kurt Meisner,Stacey Terry,Tim Elmer
5594 | 76 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DEL D638 - Updated Data Conversion and Migration Strategy - Draft Submission | 0 hrs | 0 days | 2023-08-31 | 2023-08-31 | 75 | 77 |  | Manojkumar Gurjar,Joy Schneider
5595 | 77 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2023-09-01 | 2023-09-08 | 76 | 78 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5596 | 78 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Style Guide Review | 1 hr | 1 day | 2023-09-11 | 2023-09-11 | 77 | 79 |  | Dusti Kincl
5597 | 79 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Final Collaborative Review | 20 hrs | 5 days | 2023-09-12 | 2023-09-18 | 78 | 80 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5598 | 80 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Accenture QC | 4 hrs | 2 days | 2023-09-19 | 2023-09-20 | 79 | 81 |  | Joy Schneider
5599 | 81 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DEL D638 - Updated Data Conversion and Migration Strategy - Submit | 0 hrs | 0 days | 2023-09-20 | 2023-09-20 | 80 | 82 |  | Joy Schneider
5600 | 82 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Department QC | 4 hrs | 1 day | 2023-09-21 | 2023-09-21 | 81 | 83 |  | Tommy Werner,Gabriela Gibson
5601 | 83 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Contract Manager Review | 8 hrs | 3 days | 2023-09-22 | 2023-09-26 | 82 | 84 |  | Sean Buchanan
5602 | 84 | Future Task |  |  | D638 | Manojkumar Gurjar | Accept | DEL D638 - Updated Data Conversion and Migration Strategy - Accept | 0 hrs | 0 days | 2023-09-26 | 2023-09-26 | 83 |  | 2023-10-01 | Sean Buchanan
4375 | 85 | Future Task | Yes |  | D639 | Stacey Terry |  | D639 - Development of Standardized Business Process Models – Payroll | 241 hrs | 94 days | 2023-06-05 | 2023-10-16
4376 | 86 | Future Task |  |  | D639 | Stacey Terry | Create | DED D639 - Development of Standardized Business Process Models – Payroll - Create | 16 hrs | 10 days | 2023-06-05 | 2023-06-16 | 1FS+27 days | 87 |  | Stacey Terry,Mary Punty
4377 | 87 | Future Task |  |  | D639 | Stacey Terry | Submit | DED D639 - Development of Standardized Business Process Models – Payroll - Submit | 0 hrs | 0 days | 2023-06-16 | 2023-06-16 | 86 | 88 |  | Stacey Terry,Joy Schneider
4378 | 88 | Future Task |  |  | D639 | Stacey Terry | Review | DED D639 - Development of Standardized Business Process Models – Payroll - Collaborative Review | 24 hrs | 10 days | 2023-06-19 | 2023-06-30 | 87 | 89 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4379 | 89 | Future Task |  |  | D639 | Stacey Terry | Approve | DED D639 - Development of Standardized Business Process Models – Payroll - Approve | 0 hrs | 0 days | 2023-06-30 | 2023-06-30 | 88 | 90 |  | Jimmy Cox
4417 | 90 | Future Task |  |  | D639 | Stacey Terry |  | Identify Payroll Wave Business Processes and Subprocesses | 25 hrs | 5 days | 2023-07-03 | 2023-07-10 | 89 | 91SS+2 days |  | Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari
4418 | 91 | Future Task |  |  | D639 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Payroll Wave Business Processes and Subprocesses | 4 hrs | 5 days | 2023-07-06 | 2023-07-12 | 90SS+2 days | 92 |  | Stacey Terry,Yogesh Deshmukh
4419 | 92 | Future Task |  |  | D639 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Payroll Wave Business Processes and Subprocesses | 20 hrs | 5 days | 2023-07-13 | 2023-07-19 | 91 | 93SS |  | Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4420 | 93 | Future Task |  |  | D639 | Stacey Terry |  | Create Payroll Wave Business Process Models | 30 hrs | 30 days | 2023-07-13 | 2023-08-23 | 92SS | 94 |  | Jimmy Cox,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari,Heather Cleary,Joanne Lane,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Donnie Doctor,Ryan R...
4421 | 94 | Future Task |  |  | D639 | Stacey Terry |  | Prepare Materials / Conduct Office Hours | 25 hrs | 10 days | 2023-08-24 | 2023-09-07 | 93 | 95 |  | Jimmy Cox,Angie Robertson,Carolyn Hicks,Dusti Kincl,Kimberly Kemp,Deana Metcalf,Stacey Terry,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Janice Jackson,LaVondria Norton,Robert Hic...
4422 | 95 | Future Task |  |  | D639 | Stacey Terry |  | Refine Payroll Wave Business Process Models | 20 hrs | 5 days | 2023-09-08 | 2023-09-14 | 94 | 96 |  | Brendan Jones,Jennifer Peddicord,Lee Boatwright,Tim Elmer,Justin Randolph,Nandini Adhikari
4423 | 96 | Future Task |  |  | D639 | Stacey Terry |  | Create Summary Document | 20 hrs | 5 days | 2023-09-15 | 2023-09-21 | 95 | 97 |  | Deana Metcalf,Stacey Terry,Mary Punty
4380 | 97 | Future Task |  |  | D639 | Stacey Terry | Submit | DEL D639 - Development of Standardized Business Process Models – Payroll - Draft Submission | 0 hrs | 0 days | 2023-09-21 | 2023-09-21 | 96 | 98 |  | Stacey Terry,Joy Schneider
4381 | 98 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2023-09-22 | 2023-09-28 | 97 | 99 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4382 | 99 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Style Guide Review | 1 hr | 1 day | 2023-09-29 | 2023-09-29 | 98 | 100 |  | Dusti Kincl
4383 | 100 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Final Collaborative Review | 20 hrs | 5 days | 2023-10-02 | 2023-10-06 | 99 | 101 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4384 | 101 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Accenture QC | 4 hrs | 2 days | 2023-10-09 | 2023-10-10 | 100 | 102 |  | Joy Schneider
4385 | 102 | Future Task |  |  | D639 | Stacey Terry | Submit | DEL D639 - Development of Standardized Business Process Models – Payroll - Submit | 0 hrs | 0 days | 2023-10-10 | 2023-10-10 | 101 | 103 |  | Joy Schneider
4386 | 103 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Department QC | 4 hrs | 1 day | 2023-10-11 | 2023-10-11 | 102 | 104 |  | Tommy Werner,Gabriela Gibson
4387 | 104 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Contract Manager Review | 8 hrs | 3 days | 2023-10-12 | 2023-10-16 | 103 | 105 |  | Sean Buchanan
4388 | 105 | Future Task |  |  | D639 | Stacey Terry | Accept | DEL D639 - Development of Standardized Business Process Models – Payroll - Accept | 0 hrs | 0 days | 2023-10-16 | 2023-10-16 | 104 | 1803580 | 2023-10-01 | Sean Buchanan
4389 | 106 | Future Task | Yes |  | D640 | Stacey Terry |  | D640 - Development of the Master Data Configuration Workbooks | 311 hrs | 142 days | 2023-06-05 | 2023-12-27
4390 | 107 | Future Task |  |  | D640 | Stacey Terry | Create | DED D640 - Development of the Master Data Configuration Workbooks - Create | 16 hrs | 10 days | 2023-06-05 | 2023-06-16 | 1FS+27 days | 108,111SS+9 days |  | Stacey Terry,Mary Punty
4391 | 108 | Future Task |  |  | D640 | Stacey Terry | Submit | DED D640 - Development of the Master Data Configuration Workbooks - Submit | 0 hrs | 0 days | 2023-06-16 | 2023-06-16 | 107 | 109 |  | Stacey Terry,Joy Schneider
4392 | 109 | Future Task |  |  | D640 | Stacey Terry | Review | DED D640 - Development of the Master Data Configuration Workbooks - Collaborative Review | 24 hrs | 10 days | 2023-06-19 | 2023-06-30 | 108 | 110 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4393 | 110 | Future Task |  |  | D640 | Stacey Terry | Approve | DED D640 - Development of the Master Data Configuration Workbooks - Approve | 0 hrs | 0 days | 2023-06-30 | 2023-06-30 | 109 |  |  | Jimmy Cox
4424 | 111 | Future Task |  |  | D640 | Stacey Terry |  | Identify Configuration Inventory | 20 hrs | 10 days | 2023-06-16 | 2023-06-29 | 107SS+9 days | 112 |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Donnie Doctor,Ryan Raagas,Pooj... | This first task is set to begin before the DED approves. This should begin after. | Angie
4425 | 112 | Future Task |  |  | D640 | Stacey Terry |  | Update Design Work Unit Tracker for Configuration | 4 hrs | 5 days | 2023-06-30 | 2023-07-07 | 111 | 113 |  | Stacey Terry,Yogesh Deshmukh
4426 | 113 | Future Task |  |  | D640 | Stacey Terry |  | Review and Confirm Design Work Unit Tracker for Configuration | 50 hrs | 4 days | 2023-07-10 | 2023-07-13 | 112 | 114 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4427 | 114 | Future Task |  |  | D640 | Stacey Terry |  | Create, Review, and Confirm Configuration Workbooks and Agency Configuration Workbook Templates (this is a WU) | 40 hrs | 80 days | 2023-07-14 | 2023-11-03 | 113 | 115SS+20 days |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Jennifer Peddicord,Lee Boatwright,Heather Cleary,Joanne Lane,Tim Elmer,Justin Randolph,Nandini Adhikari,Donnie Doctor,Ryan Raagas,Pooj...
4428 | 115 | Future Task |  |  | D640 | Stacey Terry |  | Configure Application | 40 hrs | 70 days | 2023-08-11 | 2023-11-20 | 114SS+20 days | 116 |  | Apoorva Panchanadikar,Divya Gupta,Supriya Vaddi,Suyesh Shingare,Purushottam Karambelkar,Ankita Sarang,Yash Jamkhedkar,Sajal Saurabh,Timtim Goel
4429 | 116 | Future Task |  |  | D640 | Stacey Terry |  | Finalize Configuration Workbooks | 30 hrs | 10 days | 2023-11-21 | 2023-12-06 | 115 | 117FS-10 days |  | Apoorva Panchanadikar,Divya Gupta,Supriya Vasudevan,Suyesh Shingare,Purushottam Karambelkar,Ankita Sarang,Yash Jamkhedkar,Sajal Saurabh,Timtim Goel,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Jack Je...
4430 | 117 | Future Task |  |  | D640 | Stacey Terry |  | Create Summary Document | 30 hrs | 7 days | 2023-11-21 | 2023-12-01 | 116FS-10 days | 118 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Mary Punty
4394 | 118 | Future Task |  |  | D640 | Stacey Terry | Submit | DEL D640 - Development of the Master Data Configuration Workbooks - Draft Submission | 0 hrs | 0 days | 2023-12-01 | 2023-12-01 | 117 | 119 |  | Stacey Terry,Joy Schneider
4395 | 119 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2023-12-04 | 2023-12-08 | 118 | 120 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4396 | 120 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Style Guide Review | 1 hr | 1 day | 2023-12-11 | 2023-12-11 | 119 | 121 |  | Dusti Kincl
4397 | 121 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Final Collaborative Review | 20 hrs | 5 days | 2023-12-12 | 2023-12-18 | 120 | 122 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4398 | 122 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Accenture QC | 4 hrs | 2 days | 2023-12-19 | 2023-12-20 | 121 | 123 |  | Joy Schneider
4399 | 123 | Future Task |  |  | D640 | Stacey Terry | Submit | DEL D640 - Development of the Master Data Configuration Workbooks - Submit | 0 hrs | 0 days | 2023-12-20 | 2023-12-20 | 122 | 124 |  | Joy Schneider
4400 | 124 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Department QC | 4 hrs | 1 day | 2023-12-21 | 2023-12-21 | 123 | 125 |  | Tommy Werner,Gabriela Gibson
4401 | 125 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Contract Manager Review | 8 hrs | 3 days | 2023-12-22 | 2023-12-27 | 124 | 126 |  | Sean Buchanan
4402 | 126 | Future Task |  |  | D640 | Stacey Terry | Accept | DEL D640 - Development of the Master Data Configuration Workbooks - Accept | 0 hrs | 0 days | 2023-12-27 | 2023-12-27 | 125 | 577FS+6 days | 2023-12-01 | Sean Buchanan
4318 | 127 | Future Task | Yes |  | D641 | Stacey Terry |  | D641 - Completion of Solution Design (Requirements) Segment III | 327 hrs | 96 days | 2023-10-02 | 2024-02-20
4332 | 128 | Future Task |  |  | D641 | Stacey Terry |  | Identify Functional Designs (Segment III) | 50 hrs | 10 days | 2023-10-02 | 2023-10-13 | 1 | 129 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4319 | 129 | Future Task |  |  | D641 | Stacey Terry | Create | DED D641 - Completion of Solution Design (Requirements) Segment III - Create | 16 hrs | 10 days | 2023-10-16 | 2023-10-27 | 128 | 130 |  | Stacey Terry,Mary Punty
4320 | 130 | Future Task |  |  | D641 | Stacey Terry | Submit | DED D641 - Completion of Solution Design (Requirements) Segment III - Submit | 0 hrs | 0 days | 2023-10-27 | 2023-10-27 | 129 | 131 |  | Stacey Terry,Joy Schneider
4321 | 131 | Future Task |  |  | D641 | Stacey Terry | Review | DED D641 - Completion of Solution Design (Requirements) Segment III - Collaborative Review | 24 hrs | 10 days | 2023-10-30 | 2023-11-13 | 130 | 132 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4322 | 132 | Future Task |  |  | D641 | Stacey Terry | Approve | DED D641 - Completion of Solution Design (Requirements) Segment III - Approve | 0 hrs | 0 days | 2023-11-13 | 2023-11-13 | 131 | 133 |  | Jimmy Cox
4333 | 133 | Future Task |  |  | D641 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs (Segment III) | 40 hrs | 4 days | 2023-11-14 | 2023-11-17 | 132 | 134 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4334 | 134 | Future Task |  |  | D641 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment III) | 40 hrs | 5 days | 2023-11-20 | 2023-11-28 | 133 | 135 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4335 | 135 | Future Task |  |  | D641 | Stacey Terry |  | Create, Review and Approve Functional Design Documents (Segment III) | 50 hrs | 40 days | 2023-11-29 | 2024-01-26 | 134 | 136FS-11 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4336 | 136 | Future Task |  |  | D641 | Stacey Terry |  | Create Summary Document | 50 hrs | 11 days | 2024-01-11 | 2024-01-26 | 135FS-11 days | 137,1548SS,1592SS,1635SS+5 days,1460SS,1505 |  | Deana Metcalf,Stacey Terry,Mary Punty
4323 | 137 | Future Task |  |  | D641 | Stacey Terry | Submit | DEL D641 - Completion of Solution Design (Requirements) Segment III - Draft Submission | 0 hrs | 0 days | 2024-01-26 | 2024-01-26 | 136 | 138 |  | Stacey Terry,Joy Schneider
4324 | 138 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-01-29 | 2024-02-02 | 137 | 139 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4325 | 139 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Style Guide Review | 1 hr | 1 day | 2024-02-05 | 2024-02-05 | 138 | 140 |  | Dusti Kincl
4326 | 140 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Final Collaborative Review | 20 hrs | 5 days | 2024-02-06 | 2024-02-12 | 139 | 141 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4327 | 141 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Accenture QC | 4 hrs | 2 days | 2024-02-13 | 2024-02-14 | 140 | 142 |  | Joy Schneider
4328 | 142 | Future Task |  |  | D641 | Stacey Terry | Submit | DEL D641 - Completion of Solution Design (Requirements) Segment III - Submit | 0 hrs | 0 days | 2024-02-14 | 2024-02-14 | 141 | 143 |  | Joy Schneider
4329 | 143 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Department QC | 4 hrs | 1 day | 2024-02-15 | 2024-02-15 | 142 | 144 |  | Tommy Werner,Gabriela Gibson
4330 | 144 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Contract Manager Review | 8 hrs | 3 days | 2024-02-16 | 2024-02-20 | 143 | 145 |  | Sean Buchanan
4331 | 145 | Future Task |  |  | D641 | Stacey Terry | Accept | DEL D641 - Completion of Solution Design (Requirements) Segment III - Accept | 0 hrs | 0 days | 2024-02-20 | 2024-02-20 | 144 | 580584585 | January 2024 (Feb 2024) | Sean Buchanan
4337 | 146 | Future Task | Yes |  | D644 | Stacey Terry |  | D644 - Completion of Solution Design (Requirements) Segment IV | 337 hrs | 85 days | 2024-01-29 | 2024-05-24
4351 | 147 | Future Task |  |  | D644 | Stacey Terry |  | Identify Functional Designs (Segment IV) | 50 hrs | 10 days | 2024-01-29 | 2024-02-09 | 1 | 148 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh,Jennifer Reeves,Matthew Breeding
4338 | 148 | Future Task |  |  | D644 | Stacey Terry | Create | DED D644 - Completion of Solution Design (Requirements) Segment IV - Create | 16 hrs | 10 days | 2024-02-12 | 2024-02-23 | 147 | 149 |  | Stacey Terry,Mary Punty
4339 | 149 | Future Task |  |  | D644 | Stacey Terry | Submit | DED D644 - Completion of Solution Design (Requirements) Segment IV - Submit | 0 hrs | 0 days | 2024-02-23 | 2024-02-23 | 148 | 150 |  | Stacey Terry,Joy Schneider
4340 | 150 | Future Task |  |  | D644 | Stacey Terry | Review | DED D644 - Completion of Solution Design (Requirements) Segment IV - Collaborative Review | 24 hrs | 10 days | 2024-02-26 | 2024-03-08 | 149 | 151 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4341 | 151 | Future Task |  |  | D644 | Stacey Terry | Approve | DED D644 - Completion of Solution Design (Requirements) Segment IV - Approve | 0 hrs | 0 days | 2024-03-08 | 2024-03-08 | 150 | 152 |  | Jimmy Cox
4352 | 152 | Future Task |  |  | D644 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs (Segment IV) | 50 hrs | 4 days | 2024-03-11 | 2024-03-14 | 151 | 153 |  | Stacey Terry,Yogesh Deshmukh,Tommy Werner,Gabriela Gibson
4353 | 153 | Future Task |  |  | D644 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment IV) | 50 hrs | 4 days | 2024-03-15 | 2024-03-20 | 152 | 154 |  | Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Stacey Terry,Yogesh Deshmukh
4354 | 154 | Future Task |  |  | D644 | Stacey Terry |  | Create, Review and Approve Functional Design Documents (Segment IV) | 50 hrs | 30 days | 2024-03-21 | 2024-05-01 | 153 | 155FS-8 days |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4355 | 155 | Future Task |  |  | D644 | Stacey Terry |  | Create Summary Document | 40 hrs | 8 days | 2024-04-22 | 2024-05-01 | 154FS-8 days | 156,1561SS,1605SS,1648SS+5 days,1473SS,1518SS |  | Deana Metcalf,Stacey Terry,Mary Punty
4342 | 156 | Future Task |  |  | D644 | Stacey Terry | Submit | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Draft Submission | 0 hrs | 0 days | 2024-05-01 | 2024-05-01 | 155 | 157 |  | Stacey Terry,Joy Schneider
4343 | 157 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-05-02 | 2024-05-08 | 156 | 158584 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4344 | 158 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Style Guide Review | 1 hr | 1 day | 2024-05-09 | 2024-05-09 | 157 | 159 |  | Dusti Kincl
4345 | 159 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Final Collaborative Review | 20 hrs | 5 days | 2024-05-10 | 2024-05-16 | 158 | 160 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4346 | 160 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Accenture QC | 4 hrs | 2 days | 2024-05-17 | 2024-05-20 | 159 | 161 |  | Joy Schneider
4347 | 161 | Future Task |  |  | D644 | Stacey Terry | Submit | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Submit | 0 hrs | 0 days | 2024-05-20 | 2024-05-20 | 160 | 162 |  | Joy Schneider
4348 | 162 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Department QC | 4 hrs | 1 day | 2024-05-21 | 2024-05-21 | 161 | 163 |  | Tommy Werner,Gabriela Gibson
4349 | 163 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Contract Manager Review | 8 hrs | 3 days | 2024-05-22 | 2024-05-24 | 162 | 164 |  | Sean Buchanan
4350 | 164 | Future Task |  |  | D644 | Stacey Terry | Accept | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Accept | 0 hrs | 0 days | 2024-05-24 | 2024-05-24 | 163 | 580FS+24 days,585 | April 2024 (May 2024) | Sean Buchanan
4356 | 165 | Future Task | Yes |  | D650 | Stacey Terry |  | D650 - Completion of Solution Design (Requirements) DW/BI | 347 hrs | 160 days | 2024-03-01 | 2024-10-15
4357 | 166 | Future Task |  |  | D650 | Stacey Terry | Create | DED D650 - Completion of Solution Design (Requirements) DW/BI - Create | 16 hrs | 10 days | 2024-03-01 | 2024-03-14 | 1 | 167 |  | Stacey Terry,Mary Punty
4358 | 167 | Future Task |  |  | D650 | Stacey Terry | Submit | DED D650 - Completion of Solution Design (Requirements) DW/BI - Submit | 0 hrs | 0 days | 2024-03-14 | 2024-03-14 | 166 | 168 |  | Stacey Terry,Joy Schneider
4359 | 168 | Future Task |  |  | D650 | Stacey Terry | Review | DED D650 - Completion of Solution Design (Requirements) DW/BI - Collaborative Review | 24 hrs | 10 days | 2024-03-15 | 2024-03-28 | 167 | 169 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4360 | 169 | Future Task |  |  | D650 | Stacey Terry | Approve | DED D650 - Completion of Solution Design (Requirements) DW/BI - Approve | 0 hrs | 0 days | 2024-03-28 | 2024-03-28 | 168 | 170 |  | Jimmy Cox
4370 | 170 | Future Task |  |  | D650 | Stacey Terry |  | Identify Functional Designs DW/BI | 50 hrs | 10 days | 2024-03-29 | 2024-04-11 | 169 | 171 |  | Stacey Terry,Yogesh Deshmukh
4371 | 171 | Future Task |  |  | D650 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs DW/BI | 50 hrs | 10 days | 2024-04-12 | 2024-04-25 | 170 | 172 |  | Stacey Terry,Yogesh Deshmukh
4372 | 172 | Future Task |  |  | D650 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs DW/BI | 50 hrs | 10 days | 2024-04-26 | 2024-05-09 | 171 | 173 |  | Stacey Terry,Yogesh Deshmukh
4373 | 173 | Future Task |  |  | D650 | Stacey Terry |  | Create, Review and Approve Functional Design Documents DW/BI | 50 hrs | 82 days | 2024-05-10 | 2024-09-05 | 172 | 174 |  | Stacey Terry,Yogesh Deshmukh
4374 | 174 | Future Task |  |  | D650 | Stacey Terry |  | Create Summary Document | 50 hrs | 11 days | 2024-09-06 | 2024-09-20 | 173 | 175 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4361 | 175 | Future Task |  |  | D650 | Stacey Terry | Submit | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Draft Submission | 0 hrs | 0 days | 2024-09-20 | 2024-09-20 | 174 | 176 |  | Stacey Terry,Joy Schneider
4362 | 176 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-09-23 | 2024-09-27 | 175 | 177 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4363 | 177 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Style Guide Review | 1 hr | 1 day | 2024-09-30 | 2024-09-30 | 176 | 178 |  | Dusti Kincl
4364 | 178 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Final Collaborative Review | 20 hrs | 5 days | 2024-10-01 | 2024-10-07 | 177 | 179 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4365 | 179 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Accenture QC | 4 hrs | 2 days | 2024-10-08 | 2024-10-09 | 178 | 180 |  | Joy Schneider
4366 | 180 | Future Task |  |  | D650 | Stacey Terry | Submit | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Submit | 0 hrs | 0 days | 2024-10-09 | 2024-10-09 | 179 | 181 |  | Joy Schneider
4367 | 181 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Department QC | 4 hrs | 1 day | 2024-10-10 | 2024-10-10 | 180 | 182 |  | Tommy Werner,Gabriela Gibson
4368 | 182 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Contract Manager Review | 8 hrs | 3 days | 2024-10-11 | 2024-10-15 | 181 | 183 |  | Sean Buchanan
4369 | 183 | Future Task |  |  | D650 | Stacey Terry | Accept | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Accept | 0 hrs | 0 days | 2024-10-15 | 2024-10-15 | 182 |  | 2024-10-01 | Sean Buchanan
4431 | 184 | Future Task |  |  | WP402 | Stacey Terry |  | WP402 - Requirements Traceability Matrix | 98 hrs | 55 days | 2023-06-05 | 2023-08-21
4432 | 185 | Future Task |  |  | WP402 | Stacey Terry | Create | WPED WP402 - Requirements Traceability Matrix - Create | 8 hrs | 5 days | 2023-06-05 | 2023-06-09 | 1FS+27 days | 186 |  | Stacey Terry,Mary Punty
4433 | 186 | Future Task |  |  | WP402 | Stacey Terry | Submit | WPED WP402 - Requirements Traceability Matrix - Submit | 0 hrs | 0 days | 2023-06-09 | 2023-06-09 | 185 | 187 |  | Joy Schneider,Stacey Terry
4434 | 187 | Future Task |  |  | WP402 | Stacey Terry | Review | WPED WP402 - Requirements Traceability Matrix - Review | 12 hrs | 5 days | 2023-06-12 | 2023-06-16 | 186 | 188 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4435 | 188 | Future Task |  |  | WP402 | Stacey Terry | Approve | WPED WP402 - Requirements Traceability Matrix - Approve | 0 hrs | 0 days | 2023-06-16 | 2023-06-16 | 187 | 189 |  | Jimmy Cox
4449 | 189 | Future Task |  |  | WP402 | Stacey Terry |  | Create Requirements Traceability Matrix Template | 2 hrs | 3 days | 2023-06-19 | 2023-06-21 | 188 | 190 |  | Stacey Terry,Yogesh Deshmukh
4450 | 190 | Future Task |  |  | WP402 | Stacey Terry |  | Populate Requirements Traceability Matrix Template | 10 hrs | 5 days | 2023-06-22 | 2023-06-28 | 189 | 191 |  | Stacey Terry,Yogesh Deshmukh
4451 | 191 | Future Task |  |  | WP402 | Stacey Terry |  | Create Summary Document | 6 hrs | 2 days | 2023-06-29 | 2023-06-30 | 190 | 192 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4436 | 192 | Future Task |  |  | WP402 | Stacey Terry | Submit | WP WP402 - Requirements Traceability Matrix - Submit | 0 hrs | 0 days | 2023-06-30 | 2023-06-30 | 191 | 193 |  | Joy Schneider,Stacey Terry
4437 | 193 | Future Task |  |  | WP402 | Stacey Terry | Review | WP WP402 - Requirements Traceability Matrix - Collaborative Review & Update | 20 hrs | 10 days | 2023-07-03 | 2023-07-17 | 192 | 194 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4438 | 194 | Future Task |  |  | WP402 | Stacey Terry | Review | WP WP402 - Requirements Traceability Matrix - Final Review & Edits | 20 hrs | 5 days | 2023-07-18 | 2023-07-24 | 193 | 195 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4439 | 195 | Future Task |  |  | WP402 | Stacey Terry | Approve | WP WP402 - Requirements Traceability Matrix - Approve | 0 hrs | 0 days | 2023-07-24 | 2023-07-24 | 194 | 373,412,431,722,196FS+5 days | 2023-06-01 | Jimmy Cox
7147 | 196 | Future Task |  |  | WP402 | Stacey Terry |  | Load Requirements in Requirements Traceability Tool | 10 hrs | 5 days | 2023-08-01 | 2023-08-07 | 195FS+5 days | 197 |  | Mary Punty,Joy Schneider
7148 | 197 | Future Task |  |  | WP402 | Stacey Terry |  | Validate Requirements in Requirements Traceability Tool | 10 hrs | 10 days | 2023-08-08 | 2023-08-21 | 196 |  |  | Deana Metcalf,Stacey Terry
4440 | 198 | Future Task |  |  | WP403 | Stacey Terry |  | WP403 - RICEFW Inventory | 200 hrs | 64 days | 2023-06-05 | 2023-09-01
4441 | 199 | Future Task |  |  | WP403 | Stacey Terry | Create | WPED WP403 - RICEFW Inventory - Create | 16 hrs | 10 days | 2023-06-05 | 2023-06-16 | 1FS+27 days | 200 |  | Stacey Terry,Mary Punty
4442 | 200 | Future Task |  |  | WP403 | Stacey Terry | Submit | WPED WP403 - RICEFW Inventory - Submit | 0 hrs | 0 days | 2023-06-16 | 2023-06-16 | 199 | 201 |  | Joy Schneider,Stacey Terry
4443 | 201 | Future Task |  |  | WP403 | Stacey Terry | Review | WPED WP403 - RICEFW Inventory - Review | 24 hrs | 10 days | 2023-06-19 | 2023-06-30 | 200 | 202 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4444 | 202 | Future Task |  |  | WP403 | Stacey Terry | Approve | WPED WP403 - RICEFW Inventory - Approve | 0 hrs | 0 days | 2023-06-30 | 2023-06-30 | 201 | 203 |  | Jimmy Cox
4454 | 203 | Future Task |  |  | WP403 | Stacey Terry |  | Create RICEFW Inventory Template | 20 hrs | 5 days | 2023-07-03 | 2023-07-10 | 202 | 204 |  | Deana Metcalf,Stacey Terry
4455 | 204 | Future Task |  |  | WP403 | Stacey Terry |  | Define and document RICEFW Inventory | 50 hrs | 14 days | 2023-07-11 | 2023-07-28 | 203 | 205 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4456 | 205 | Future Task |  |  | WP403 | Stacey Terry |  | Populate RICEFW Inventory Template | 20 hrs | 5 days | 2023-07-31 | 2023-08-04 | 204 | 206 |  | Deana Metcalf,Stacey Terry
4457 | 206 | Future Task |  |  | WP403 | Stacey Terry |  | Create Summary Document | 30 hrs | 5 days | 2023-08-07 | 2023-08-11 | 205 | 207 |  | Deana Metcalf,Stacey Terry,Mary Punty
4445 | 207 | Future Task |  |  | WP403 | Stacey Terry | Submit | WP WP403 - RICEFW Inventory - Submit | 0 hrs | 0 days | 2023-08-11 | 2023-08-11 | 206 | 208 |  | Joy Schneider,Stacey Terry
4446 | 208 | Future Task |  |  | WP403 | Stacey Terry | Review | WP WP403 - RICEFW Inventory - Collaborative Review & Update | 20 hrs | 10 days | 2023-08-14 | 2023-08-25 | 207 | 209 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4447 | 209 | Future Task |  |  | WP403 | Stacey Terry | Review | WP WP403 - RICEFW Inventory - Final Review & Edits | 20 hrs | 5 days | 2023-08-28 | 2023-09-01 | 208 | 210 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4448 | 210 | Future Task |  |  | WP403 | Stacey Terry | Approve | WP WP403 - RICEFW Inventory - Approve | 0 hrs | 0 days | 2023-09-01 | 2023-09-01 | 209 |  | 2024-04-01 | Jimmy Cox
5667 | 211 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | WP404 - Data Conversion Inventory | 250 hrs | 108 days | 2023-09-01 | 2024-02-08
5668 | 212 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WPED WP404 - Data Conversion Inventory - Create | 16 hrs | 10 days | 2023-09-01 | 2023-09-15 | 1FS+90 days | 213 |  | Manojkumar Gurjar,Kurt Meisner
5669 | 213 | Future Task |  |  | WP404 | Manojkumar Gurjar | Submit | WPED WP404 - Data Conversion Inventory - Submit | 0 hrs | 0 days | 2023-09-15 | 2023-09-15 | 212 | 214 |  | Manojkumar Gurjar,Joy Schneider
5670 | 214 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WPED WP404 - Data Conversion Inventory - Review | 24 hrs | 10 days | 2023-09-18 | 2023-09-29 | 213 | 215 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5671 | 215 | Future Task |  |  | WP404 | Manojkumar Gurjar | Approve | WPED WP404 - Data Conversion Inventory - Approve | 0 hrs | 0 days | 2023-09-29 | 2023-09-29 | 214 | 216 |  | Jimmy Cox
5672 | 216 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | Create Data Conversion Inventory Template | 50 hrs | 32 days | 2023-10-02 | 2023-11-15 | 215,47 | 217 |  | Manojkumar Gurjar,Kurt Meisner
5673 | 217 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | Populate Data Conversion Inventory with RICEFW Inventory conversion items | 50 hrs | 16 days | 2023-11-16 | 2023-12-11 | 216 | 218 |  | Manojkumar Gurjar,Kurt Meisner
5674 | 218 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | Identify/confirm Anticipated Source Systems and Legacy Tables | 50 hrs | 20 days | 2023-12-12 | 2024-01-10 | 217 | 219 |  | Kurt Meisner,Manojkumar Gurjar
5675 | 219 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | Create Data Conversion Inventory Summary Document | 20 hrs | 5 days | 2024-01-11 | 2024-01-18 | 218 | 220 |  | Manojkumar Gurjar,Kurt Meisner
5676 | 220 | Future Task |  |  | WP404 | Manojkumar Gurjar | Submit | WP WP404 - Data Conversion Inventory - Submit | 0 hrs | 0 days | 2024-01-18 | 2024-01-18 | 219 | 221 |  | Manojkumar Gurjar,Joy Schneider
5677 | 221 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WP WP404 - Data Conversion Inventory - Collaborative Review & Update | 20 hrs | 10 days | 2024-01-19 | 2024-02-01 | 220 | 222 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5678 | 222 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WP WP404 - Data Conversion Inventory - Final Review & Edits | 20 hrs | 5 days | 2024-02-02 | 2024-02-08 | 221 | 223 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5679 | 223 | Future Task |  |  | WP404 | Manojkumar Gurjar | Approve | WP WP404 - Data Conversion Inventory - Approve | 0 hrs | 0 days | 2024-02-08 | 2024-02-08 | 222 |  | 2024-01-01 | Jimmy Cox
4458 | 224 | Future Task | Yes |  | WP405 | Stacey Terry |  | WP405 - Security Roles Matrix | 280 hrs | 85 days | 2024-04-01 | 2024-07-30
4459 | 225 | Future Task |  |  | WP405 | Stacey Terry | Create | WPED WP405 - Security Roles Matrix - Create | 16 hrs | 10 days | 2024-04-01 | 2024-04-12 | 1 | 226 |  | Stacey Terry,Mary Punty | Can we begin/create this (the DED) earlier? | Angie
4460 | 226 | Future Task |  |  | WP405 | Stacey Terry | Submit | WPED WP405 - Security Roles Matrix - Submit | 0 hrs | 0 days | 2024-04-12 | 2024-04-12 | 225 | 227 |  | Joy Schneider,Stacey Terry
4461 | 227 | Future Task |  |  | WP405 | Stacey Terry | Review | WPED WP405 - Security Roles Matrix - Review | 24 hrs | 10 days | 2024-04-15 | 2024-04-26 | 226 | 228 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4462 | 228 | Future Task |  |  | WP405 | Stacey Terry | Approve | WPED WP405 - Security Roles Matrix - Approve | 0 hrs | 0 days | 2024-04-26 | 2024-04-26 | 227 | 229 |  | Jimmy Cox
4467 | 229 | Future Task |  |  | WP405 | Stacey Terry |  | Create Security Roles Matrix Template | 20 hrs | 5 days | 2024-04-29 | 2024-05-03 | 228 | 230 |  | Stacey Terry,Yogesh Deshmukh
4468 | 230 | Future Task |  |  | WP405 | Stacey Terry |  | Design, Review, and Confirm Security Roles Matrix | 50 hrs | 20 days | 2024-05-06 | 2024-06-03 | 229 | 231 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4469 | 231 | Future Task |  |  | WP405 | Stacey Terry |  | Finalize Security Roles Matrix Design | 50 hrs | 5 days | 2024-06-04 | 2024-06-10 | 230 | 232 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
4470 | 232 | Future Task |  |  | WP405 | Stacey Terry |  | Configure Security Roles and Permission Lists | 50 hrs | 15 days | 2024-06-11 | 2024-07-01 | 231 | 233 |  | Manojkumar Gurjar,Paul Jureidini
4471 | 233 | Future Task |  |  | WP405 | Stacey Terry |  | Create Security Roles Matrix Summary Document | 30 hrs | 5 days | 2024-07-02 | 2024-07-09 | 232 | 234 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4463 | 234 | Future Task |  |  | WP405 | Stacey Terry | Submit | WP WP405 - Security Roles Matrix - Submit | 0 hrs | 0 days | 2024-07-09 | 2024-07-09 | 233 | 235 |  | Joy Schneider,Stacey Terry
4464 | 235 | Future Task |  |  | WP405 | Stacey Terry | Review | WP WP405 - Security Roles Matrix - Collaborative Review & Update | 20 hrs | 10 days | 2024-07-10 | 2024-07-23 | 234 | 236 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4465 | 236 | Future Task |  |  | WP405 | Stacey Terry | Review | WP WP405 - Security Roles Matrix - Final Review & Edits | 20 hrs | 5 days | 2024-07-24 | 2024-07-30 | 235 | 237 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4466 | 237 | Future Task |  |  | WP405 | Stacey Terry | Approve | WP WP405 - Security Roles Matrix - Approve | 0 hrs | 0 days | 2024-07-30 | 2024-07-30 | 236 | 579 | 2024-07-01 | Jimmy Cox
5680 | 238 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | WP411 - Batch and Interface Procedures | 109 hrs | 92 days | 2024-10-30 | 2025-03-14
5681 | 239 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WPED WP411 - Batch and Interface Procedures - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1 | 240 |  | Manojkumar Gurjar,Kurt Meisner
5682 | 240 | Future Task |  |  | WP411 | Manojkumar Gurjar | Submit | WPED WP411 - Batch and Interface Procedures - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 239 | 241 |  | Manojkumar Gurjar,Joy Schneider
5683 | 241 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WPED WP411 - Batch and Interface Procedures - Review | 24 hrs | 10 days | 2024-11-14 | 2024-11-27 | 240 | 242 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5684 | 242 | Future Task |  |  | WP411 | Manojkumar Gurjar | Approve | WPED WP411 - Batch and Interface Procedures - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 241 | 243 |  | Jimmy Cox
6701 | 243 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | Define Interface Procedures | 3 hrs | 28 days | 2024-12-02 | 2025-01-10 | 242 | 244 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
6702 | 244 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | Create Batch Flow Diagram | 6 hrs | 9 days | 2025-01-13 | 2025-01-24 | 243 | 245 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
6703 | 245 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | Create Batch and Interface Procedures Document | 20 hrs | 20 days | 2025-01-27 | 2025-02-21 | 244 | 246 |  | Manojkumar Gurjar,Kurt Meisner,Bryan Sohayda
5685 | 246 | Future Task |  |  | WP411 | Manojkumar Gurjar | Submit | WP WP411 - Batch and Interface Procedures - Submit | 0 hrs | 0 days | 2025-02-21 | 2025-02-21 | 245 | 247 |  | Manojkumar Gurjar,Joy Schneider
5686 | 247 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WP WP411 - Batch and Interface Procedures - Collaborative Review & Update | 20 hrs | 10 days | 2025-02-24 | 2025-03-07 | 246 | 248 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5687 | 248 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WP WP411 - Batch and Interface Procedures - Final Review & Edits | 20 hrs | 5 days | 2025-03-10 | 2025-03-14 | 247 | 249 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5688 | 249 | Future Task |  |  | WP411 | Manojkumar Gurjar | Approve | WP WP411 - Batch and Interface Procedures - Approve | 0 hrs | 0 days | 2025-03-14 | 2025-03-14 | 248 |  |  | Jimmy Cox
6596 | 250 | Late | Yes |  | I-WP101 | Deana Metcalf |  | I-WP101 Update Financials BPMs | 1,336 hrs | 294 days | 2023-04-26 | 2024-06-24
6597 | 251 | Late |  |  | I-WP101 | Deana Metcalf | Create | Identify BPMs by module | 6 hrs | 3 days | 2023-04-26 | 2023-04-28 | 1 | 258259 |  | Deana Metcalf,Stacey Terry,Tiffany Porter,Janice Jackson,Brendan Jones
6598 | 252 | Late |  |  | I-WP101 | Deana Metcalf |  | WPED - I-WP101 Update Financials BPMs | 1,072 hrs | 274 days | 2023-05-01 | 2024-05-30
6599 | 253 | On Schedule |  |  | I-WP101 | Deana Metcalf | Create | WPED - I-WP101 Update Financials BPMs - Create | 8 hrs | 2 days | 2023-05-26 | 2023-05-30 | 1 | 254 |  | Deana Metcalf | Finished 5/22/23 | TW
6600 | 254 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | WPED - I-WP101 Update Financials BPMs - Submit | 0 hrs | 0 days | 2023-05-30 | 2023-05-30 | 253 | 255 |  | Deana Metcalf | Finished 5/22/23 | TW
6601 | 255 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WPED - I-WP101 Update Financials BPMs - Collaborative Review and Update | 10 hrs | 8 days | 2023-05-31 | 2023-06-09 | 254 | 256 |  | Tiffany Porter,Janice Jackson,Brendan Jones,Angie Robertson,Jimmy Cox,Tommy Werner | Finished 5/24/23 | TW
6602 | 256 | Future Task |  |  | I-WP101 | Deana Metcalf | Approve | WPED - I-WP101 Update Financials BPMs - Approve | 0 hrs | 0 days | 2023-06-09 | 2023-06-09 | 255 |  |  | Jimmy Cox | Successor U-6066 | TW
6603 | 257 | Late |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 1 - Financials Wave Business Process Models | 176 hrs | 86 days | 2023-05-01 | 2023-08-30
6604 | 258 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - May | 20 hrs | 22 days | 2023-05-01 | 2023-05-31 | 251 | 260 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6605 | 259 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - May | 20 hrs | 22 days | 2023-05-01 | 2023-05-31 | 251 | 261 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6606 | 260 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - June | 20 hrs | 22 days | 2023-06-01 | 2023-06-30 | 258 | 262 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6607 | 261 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - June | 20 hrs | 22 days | 2023-06-01 | 2023-06-30 | 259 | 263 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6608 | 262 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - July | 20 hrs | 20 days | 2023-07-03 | 2023-07-31 | 260 | 264 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6609 | 263 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - July | 20 hrs | 20 days | 2023-07-03 | 2023-07-31 | 261 | 264 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6610 | 264 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 1 - Submit | 0 hrs | 0 days | 2023-07-31 | 2023-07-31 | 262263 | 265270271272 |  | Deana Metcalf
6611 | 265 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Financials Wave Business Process Models - Segment 1 - Collaborative Review and Update | 20 hrs | 4 days | 2023-08-01 | 2023-08-04 | 264 | 266 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6789 | 266 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Financials Wave Business Process Models - Segment 1 - Advisory Council Review and Updates | 14 hrs | 12 days | 2023-08-07 | 2023-08-22 | 265 | 267 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson,Dusti Kincl
6612 | 267 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Financials Wave Business Process Models - Segment 1 - Style Guide Updates | 2 hrs | 1 day | 2023-08-23 | 2023-08-23 | 266 | 268 |  | Dusti Kincl
6613 | 268 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Financials Wave Business Process Models - Segment 1 - Final Review and Update | 20 hrs | 5 days | 2023-08-24 | 2023-08-30 | 267 | 323 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6614 | 269 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 2 - Financials Wave Business Process Models | 274 hrs | 210 days | 2023-08-01 | 2024-05-30
6615 | 270 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - August | 20 hrs | 23 days | 2023-08-01 | 2023-08-31 | 264 | 273 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6616 | 271 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - August | 20 hrs | 23 days | 2023-08-01 | 2023-08-31 | 264 | 274 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6617 | 272 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - August | 20 hrs | 23 days | 2023-08-01 | 2023-08-31 | 264 | 275 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6618 | 273 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - September | 20 hrs | 20 days | 2023-09-01 | 2023-09-29 | 270 | 276279280 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6619 | 274 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - September | 20 hrs | 20 days | 2023-09-01 | 2023-09-29 | 271 | 277 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6620 | 275 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - September | 20 hrs | 20 days | 2023-09-01 | 2023-09-29 | 272 | 278 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6621 | 276 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - October | 20 hrs | 20 days | 2023-10-02 | 2023-10-27 | 273 | 281 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6622 | 277 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - October | 20 hrs | 20 days | 2023-10-02 | 2023-10-27 | 274 | 281 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6623 | 278 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - October | 20 hrs | 20 days | 2023-10-02 | 2023-10-27 | 275 | 281 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6624 | 279 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment LMC models Impacted by Segment 2 | 20 hrs | 20 days | 2023-10-02 | 2023-10-27 | 273 | 281 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6625 | 280 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment PPA models Impacted by Segment 2 | 20 hrs | 20 days | 2023-10-02 | 2023-10-27 | 273 | 281 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6626 | 281 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 2 - Submit | 0 hrs | 0 days | 2023-10-27 | 2023-10-27 | 276277278279280 | 282,287FS+2 days,288FS+2 days,289FS+2 days |  | Deana Metcalf
6627 | 282 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Collaborative Review and Update | 20 hrs | 5 days | 2023-10-30 | 2023-11-03 | 281 | 283 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6790 | 283 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Advisory Council Review and Updates | 20 hrs | 11 days | 2023-11-06 | 2023-11-21 | 282 | 284 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6628 | 284 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 1 - Style Guide Updates | 2 hrs | 1 day | 2024-05-22 | 2024-05-22 | 283301319 | 285 |  | Dusti Kincl | This date seems off. It should be November 21st or 22nd of 2023. Also, the title says "Segment I" instead of "Segment II". Note from Joy: all dates mirror the WPED on SP. Note that the second SG is labeled as SG 1 on the WPED, in the schedule we have updated to reflect the correct segment. | Angie
6629 | 285 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Final Review and Update | 12 hrs | 5 days | 2024-05-23 | 2024-05-30 | 284 | 323 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6630 | 286 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 3 - Financials Wave Business Process Models | 302 hrs | 145 days | 2023-11-01 | 2024-05-30
6631 | 287 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - November | 20 hrs | 19 days | 2023-11-01 | 2023-11-30 | 281FS+2 days | 290 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6632 | 288 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - November | 20 hrs | 19 days | 2023-11-01 | 2023-11-30 | 281FS+2 days | 291 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6633 | 289 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - November | 20 hrs | 19 days | 2023-11-01 | 2023-11-30 | 281FS+2 days | 292 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6634 | 290 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - December | 20 hrs | 20 days | 2023-12-01 | 2023-12-29 | 287 | 293296 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6635 | 291 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - December | 20 hrs | 20 days | 2023-12-01 | 2023-12-29 | 288 | 294297 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6636 | 292 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - December | 20 hrs | 20 days | 2023-12-01 | 2023-12-29 | 289 | 295298 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6637 | 293 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - January | 20 hrs | 18 days | 2024-01-02 | 2024-01-26 | 290 | 299 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6638 | 294 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - January | 20 hrs | 18 days | 2024-01-02 | 2024-01-26 | 291 | 299 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6639 | 295 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - January | 20 hrs | 18 days | 2024-01-02 | 2024-01-26 | 292 | 299 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6640 | 296 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 3 | 20 hrs | 18 days | 2024-01-02 | 2024-01-26 | 290 | 299 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6641 | 297 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 3 | 20 hrs | 18 days | 2024-01-02 | 2024-01-26 | 291 | 299 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6642 | 298 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 3 | 20 hrs | 18 days | 2024-01-02 | 2024-01-26 | 292 | 299 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6643 | 299 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 3 - Submit | 0 hrs | 0 days | 2024-01-26 | 2024-01-26 | 2.9329e+17 | 300,305FS+3 days,306FS+3 days,307FS+3 days |  | Deana Metcalf
6644 | 300 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Collaborative Review and Update | 20 hrs | 5 days | 2024-01-29 | 2024-02-02 | 299 | 301 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6792 | 301 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Advisory Council Review and Updates | 20 hrs | 17 days | 2024-02-05 | 2024-02-27 | 300 | 284302 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6645 | 302 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Style Guide Updates | 2 hrs | 1 day | 2024-05-22 | 2024-05-22 | 301319 | 303 |  | Dusti Kincl | This date seems off. It should be March 2024. | Angie
6646 | 303 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Final Review and Update | 20 hrs | 5 days | 2024-05-23 | 2024-05-30 | 302 | 323 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6647 | 304 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 4 - Financials Wave Business Process Models | 302 hrs | 85 days | 2024-02-01 | 2024-05-30
6648 | 305 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - February | 20 hrs | 21 days | 2024-02-01 | 2024-02-29 | 299FS+3 days | 308 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6649 | 306 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - February | 20 hrs | 21 days | 2024-02-01 | 2024-02-29 | 299FS+3 days | 309 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6650 | 307 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - February | 20 hrs | 21 days | 2024-02-01 | 2024-02-29 | 299FS+3 days | 310 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6651 | 308 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - March | 20 hrs | 21 days | 2024-03-01 | 2024-03-29 | 305 | 311314 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6652 | 309 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - March | 20 hrs | 21 days | 2024-03-01 | 2024-03-29 | 306 | 312315 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6653 | 310 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - March | 20 hrs | 21 days | 2024-03-01 | 2024-03-29 | 307 | 313316 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6654 | 311 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - April | 20 hrs | 20 days | 2024-04-01 | 2024-04-26 | 308 | 317 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6655 | 312 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - April | 20 hrs | 20 days | 2024-04-01 | 2024-04-26 | 309 | 317 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6656 | 313 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - April | 20 hrs | 20 days | 2024-04-01 | 2024-04-26 | 310 | 317 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6657 | 314 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 4 | 20 hrs | 20 days | 2024-04-01 | 2024-04-26 | 308 | 317 |  | Shelisa Harris,LaVondria Norton,Janice Jackson,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Robert Hicks
6658 | 315 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 4 | 20 hrs | 20 days | 2024-04-01 | 2024-04-26 | 309 | 317 |  | Heather Cleary,Joanne Lane,Brendan Jones,Donnie Doctor,Ryan Raagas,Pooja Barde,Al Brown
6659 | 316 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 4 | 20 hrs | 20 days | 2024-04-01 | 2024-04-26 | 310 | 317 |  | Yorke Davis,Kathryn Harrell,Tiffany Porter,Sandeep Gottam,Jack Jenkins,Michael Carino,Hari Balijachinna,Dawna Johnson,Abdel El Bacha,Anthony Bastidas
6660 | 317 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 4 - Submit | 0 hrs | 0 days | 2024-04-26 | 2024-04-26 | 3.1131e+17 | 318 |  | Deana Metcalf
6661 | 318 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Collaborative Review and Update | 20 hrs | 5 days | 2024-04-29 | 2024-05-03 | 317 | 319 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6793 | 319 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Advisory Council Review and Updates | 20 hrs | 12 days | 2024-05-06 | 2024-05-21 | 318 | 284302320 |  | Dusti Kincl,Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Janice Jackson
6662 | 320 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Style Guide Updates | 2 hrs | 1 day | 2024-05-22 | 2024-05-22 | 319 | 321 |  | Dusti Kincl
6663 | 321 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Final Review and Update | 20 hrs | 5 days | 2024-05-23 | 2024-05-30 | 320 | 323 |  | Deana Metcalf,Jennifer Reeves,Matthew Breeding,Tiffany Porter,Brendan Jones,Angie Robertson
6664 | 322 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Update Financials BPMs Review Tasks | 44 hrs | 17 days | 2024-05-30 | 2024-06-24
6665 | 323 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | DEL - I-WP101 Update Financials BPMs - Submit | 0 hrs | 0 days | 2024-05-30 | 2024-05-30 | 268285303321 | 324 |  | Deana Metcalf | These should say "WP" as the first word in the title, not "DEL" | Angie
6666 | 324 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | DEL - I-WP101 Update Financials BPMs - Dept QC | 2 hrs | 1 day | 2024-05-31 | 2024-05-31 | 323 | 325 |  | Gabriela Gibson | These should say "WP" as the first word in the title, not "DEL" | Angie
6667 | 325 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | DEL - I-WP101 Update Financials BPMs - Collaborative Review and Update | 20 hrs | 10 days | 2024-06-03 | 2024-06-14 | 324 | 326 |  | Deana Metcalf,Stacey Terry,Tiffany Porter,Janice Jackson,Brendan Jones | These should say "WP" as the first word in the title, not "DEL" | Angie
6668 | 326 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | DEL - I-WP101 Update Financials BPMs - Style Guide Review | 2 hrs | 1 day | 2024-06-17 | 2024-06-17 | 325 | 327 |  | Dusti Kincl | These should say "WP" as the first word in the title, not "DEL" | Angie
6669 | 327 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | DEL - I-WP101 Update Financials BPMs - Final Review and Update | 20 hrs | 5 days | 2024-06-18 | 2024-06-24 | 326 | 328 |  | Jimmy Cox,Angie Robertson | These should say "WP" as the first word in the title, not "DEL" | Angie
6670 | 328 | Future Task |  |  | I-WP101 | Deana Metcalf | Approve | DEL - I-WP101 Update Financials BPMs - Approve | 0 hrs | 0 days | 2024-06-24 | 2024-06-24 | 327 |  |  | Jimmy Cox | These should say "WP" as the first word in the title, not "DEL" | Angie
6671 | 329 | Future Task | Yes |  | I-WP125 | Deana Metcalf |  | I-WP125 - Updated D66 Chart of Accounts Design | 214 hrs | 63 days | 2023-06-05 | 2023-08-31
6672 | 330 | Future Task |  |  | I-WP125 | Deana Metcalf | Create | WPED - I-WP125 - Update D66 Chart of Accounts Design - Create | 2 hrs | 10 days | 2023-06-05 | 2023-06-16 | 1 | 331 |  | Deana Metcalf
6673 | 331 | Future Task |  |  | I-WP125 | Deana Metcalf | Submit | WPED - I-WP125 - Update D66 Chart of Accounts Design - Submit | 0 hrs | 0 days | 2023-06-16 | 2023-06-16 | 330 | 332 |  | Deana Metcalf
6674 | 332 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WPED - I-WP125 - Update D66 Chart of Accounts Design - Collaborative Review and Update | 8 hrs | 10 days | 2023-06-19 | 2023-06-30 | 331 | 333 |  | Janice Jackson,LaWanda Warren,Robert Hicks,Tommy Werner
6675 | 333 | Future Task |  |  | I-WP125 | Deana Metcalf | Approve | WPED - I-WP125 - Update D66 Chart of Accounts Design - Approve | 0 hrs | 0 days | 2023-06-30 | 2023-06-30 | 332 | 334 |  | Angie Robertson,Jimmy Cox
6676 | 334 | Future Task |  |  | I-WP125 | Deana Metcalf | Create | I-WP125 Update D66 Chart of Accounts Design <Activities per WPED> | 100 hrs | 26 days | 2023-07-03 | 2023-08-08 | 333 | 335 |  | Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp
6677 | 335 | Future Task |  |  | I-WP125 | Deana Metcalf | Submit | I-WP125 Update D66 Chart of Accounts Design - Submit | 0 hrs | 0 days | 2023-08-08 | 2023-08-08 | 334 | 336 |  | Janice Jackson
6678 | 336 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | I-WP125 Update D66 Chart of Accounts Design - Dept QC | 1 hr | 1 day | 2023-08-09 | 2023-08-09 | 335 | 337 |  | Gabriela Gibson
6679 | 337 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | I-WP125Update D66 Chart of Accounts Design - Collaborative Review and Update | 100 hrs | 10 days | 2023-08-10 | 2023-08-23 | 336 | 338 |  | Deana Metcalf,Janice Jackson,Jennifer Reeves,Angie Robertson
6680 | 338 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | I-WP125 Update D66 Chart of Accounts Design - Style Guide Review | 1 hr | 1 day | 2023-08-24 | 2023-08-24 | 337 | 339 |  | Tatiana Eubanks
6681 | 339 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | I-WP125 Update D66 Chart of Accounts Design - Final Review and Update | 2 hrs | 5 days | 2023-08-25 | 2023-08-31 | 338 | 340 |  | Angie Robertson,Jimmy Cox
6682 | 340 | Future Task |  |  | I-WP125 | Deana Metcalf | Approve | I-WP125 Update D66 Chart of Accounts Design - Approve | 0 hrs | 0 days | 2023-08-31 | 2023-08-31 | 339 |  |  | Jimmy Cox
6795 | 341 | Future Task |  |  | I-WP120 | Deana Metcalf |  | I-WP120 - Knowledge Base Plan | 38 hrs | 49 days | 2023-05-30 | 2023-08-07 |  |  |  |  | Remove I-WP120. We will create an AI to procure the software, and add an I-WP once we have procured | TW
6796 | 342 | Future Task |  |  | I-WP120 | Deana Metcalf | Create | WPED- I-WP120 - Knowledge Base Plan - Create | 2 hrs | 9 days | 2023-05-30 | 2023-06-09 | 1 | 343 |  | Daylin Reyes,Matthew Breeding,Jennifer Reeves,Nikki Klein,Carolyn Hicks,Kimberly Kemp
6797 | 343 | Future Task |  |  | I-WP120 | Deana Metcalf | Submit | WPED- I-WP120 - Knowledge Base Plan - Submit | 0 hrs | 0 days | 2023-06-09 | 2023-06-09 | 342 | 344 |  | Daylin Reyes
6798 | 344 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WPED- I-WP120 - Knowledge Base Plan - Review | 8 hrs | 9 days | 2023-06-12 | 2023-06-22 | 343 | 345 |  | Tommy Werner,Angie Robertson,Jimmy Cox,Deana Metcalf,Matthew Breeding,Jennifer Reeves
6799 | 345 | Future Task |  |  | I-WP120 | Deana Metcalf | Approve | WPED- I-WP120 - Knowledge Base Plan - Approve | 0 hrs | 0 days | 2023-06-22 | 2023-06-22 | 344 | 346 |  | Jimmy Cox
6800 | 346 | Future Task |  |  | I-WP120 | Deana Metcalf | Create | WP- I-WP120 - Knowledge Base Plan - Create | 20 hrs | 15 days | 2023-06-23 | 2023-07-14 | 345 | 347 |  | Daylin Reyes,Matthew Breeding,Jennifer Reeves,Nikki Klein,Carolyn Hicks,Kimberly Kemp
6801 | 347 | Future Task |  |  | I-WP120 | Deana Metcalf | Submit | WP- I-WP120 - Knowledge Base Plan - Submit | 0 hrs | 0 days | 2023-07-14 | 2023-07-14 | 346 | 348 |  | Daylin Reyes
6802 | 348 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WP- I-WP120 - Knowledge Base Plan - Department QC | 1 hr | 1 day | 2023-07-17 | 2023-07-17 | 347 | 349 |  | Tommy Werner
6803 | 349 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WP- I-WP120 - Knowledge Base Plan - Collaborative Review & Update | 4 hrs | 9 days | 2023-07-18 | 2023-07-28 | 348 | 350 |  | Deana Metcalf,Angie Robertson,Jimmy Cox,Matthew Breeding,Jennifer Reeves
6804 | 350 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WP- I-WP120 - Knowledge Base Plan - Style Guide Review | 1 hr | 1 day | 2023-07-31 | 2023-07-31 | 349 | 351 |  | Dusti Kincl
6805 | 351 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WP- I-WP120 - Knowledge Base Plan - Final Review & Edits | 2 hrs | 5 days | 2023-08-01 | 2023-08-07 | 350 | 352 |  | Angie Robertson,Jimmy Cox
6806 | 352 | Future Task |  |  | I-WP120 | Deana Metcalf | Approve | WP- I-WP120 - Knowledge Base Plan - Approve | 0 hrs | 0 days | 2023-08-07 | 2023-08-07 | 351 |  |  | Jimmy Cox
3770 | 353 | Future Task | [5 empty] | Build | 2,496 hrs | 598 days | 2023-08-07 | 2025-12-19
5534 | 354 | Future Task | Yes |  | D642 | Jarad Hermann |  | D642 - Updated Technical Architecture Design | 169 hrs | 77 days | 2023-10-04 | 2024-01-26
5535 | 355 | Future Task |  |  | D642 | Jarad Hermann | Create | DED D642 - Updated Technical Architecture Design - Create | 8 hrs | 10 days | 2023-10-04 | 2023-10-17 | 1FS+112 days | 356 |  | Jarad Hermann,Manojkumar Gurjar | Can we begin/create this (the DED) earlier? | Angie
5536 | 356 | Future Task |  |  | D642 | Jarad Hermann | Submit | DED D642 - Updated Technical Architecture Design - Submit | 0 hrs | 0 days | 2023-10-17 | 2023-10-17 | 355 | 357 |  | Jarad Hermann,Joy Schneider
5537 | 357 | Future Task |  |  | D642 | Jarad Hermann | Review | DED D642 - Updated Technical Architecture Design - Collaborative Review | 24 hrs | 10 days | 2023-10-18 | 2023-10-31 | 356 | 358 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5538 | 358 | Future Task |  |  | D642 | Jarad Hermann | Approve | DED D642 - Updated Technical Architecture Design - Approve | 0 hrs | 0 days | 2023-10-31 | 2023-10-31 | 357 | 359 |  | Jimmy Cox
5539 | 359 | Future Task |  |  | D642 | Jarad Hermann |  | Confirm content to be migrated from D80 | 20 hrs | 40 days | 2023-11-01 | 2024-01-02 | 358 | 360SS,361SS,362SS |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5540 | 360 | Future Task |  |  | D642 | Jarad Hermann |  | Review, update, and document run time architecture design | 20 hrs | 40 days | 2023-11-01 | 2024-01-02 | 359SS | 363 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5541 | 361 | Future Task |  |  | D642 | Jarad Hermann |  | Review, update, and document development and operational architecture design | 20 hrs | 40 days | 2023-11-01 | 2024-01-02 | 359SS | 363 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5542 | 362 | Future Task |  |  | D642 | Jarad Hermann |  | Review, update, and document architecture blueprint diagrams | 20 hrs | 40 days | 2023-11-01 | 2024-01-02 | 359SS | 363 |  | Jarad Hermann,Bryan Sohayda,Manojkumar Gurjar
5543 | 363 | Future Task |  |  | D642 | Jarad Hermann | Submit | DEL D642 - Updated Technical Architecture Design - Draft Submission | 0 hrs | 0 days | 2024-01-02 | 2024-01-02 | 362360361 | 364 |  | Jarad Hermann,Joy Schneider
5544 | 364 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-01-03 | 2024-01-09 | 363 | 365 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
5545 | 365 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Style Guide Review | 1 hr | 1 day | 2024-01-10 | 2024-01-10 | 364 | 366 |  | Dusti Kincl
5546 | 366 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Final Collaborative Review | 20 hrs | 5 days | 2024-01-11 | 2024-01-18 | 365 | 367 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
5547 | 367 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Accenture QC | 4 hrs | 2 days | 2024-01-19 | 2024-01-22 | 366 | 368 |  | Joy Schneider
5548 | 368 | Future Task |  |  | D642 | Jarad Hermann | Submit | DEL D642 - Updated Technical Architecture Design - Submit | 0 hrs | 0 days | 2024-01-22 | 2024-01-22 | 367 | 369 |  | Joy Schneider
5549 | 369 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Department QC | 4 hrs | 1 day | 2024-01-23 | 2024-01-23 | 368 | 370 |  | Tommy Werner,Gabriela Gibson
5550 | 370 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Contract Manager Review | 8 hrs | 3 days | 2024-01-24 | 2024-01-26 | 369 | 371 |  | Sean Buchanan
5551 | 371 | Future Task |  |  | D642 | Jarad Hermann | Accept | DEL D642 - Updated Technical Architecture Design - Accept | 0 hrs | 0 days | 2024-01-26 | 2024-01-26 | 370 |  | 2024-03-01 | Sean Buchanan
4486 | 372 | Future Task | Yes |  | D646 | Manojkumar Gurjar |  | D646 - Completion of Build Segment I | 257 hrs | 137 days | 2023-10-13 | 2024-04-30
4487 | 373 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | DED D646 - Completion of Build Segment I - Create | 16 hrs | 10 days | 2023-10-13 | 2023-10-26 | 195 | 374 |  | Manojkumar Gurjar,Kurt Meisner | Can we begin/create this (the DED) earlier? | Angie
4488 | 374 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DED D646 - Completion of Build Segment I - Submit | 0 hrs | 0 days | 2023-10-26 | 2023-10-26 | 373 | 375 |  | Manojkumar Gurjar,Joy Schneider
4489 | 375 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DED D646 - Completion of Build Segment I - Collaborative Review | 24 hrs | 10 days | 2023-10-27 | 2023-11-09 | 374 | 376 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4490 | 376 | Future Task |  |  | D646 | Manojkumar Gurjar | Approve | DED D646 - Completion of Build Segment I - Approve | 0 hrs | 0 days | 2023-11-09 | 2023-11-09 | 375 | 377 |  | Jimmy Cox
4500 | 377 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment I | 20 hrs | 8 days | 2023-11-13 | 2023-11-22 | 376 | 378 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4501 | 378 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment I | 20 hrs | 5 days | 2023-11-27 | 2023-12-01 | 377 | 379 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4502 | 379 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment I | 20 hrs | 10 days | 2023-12-04 | 2023-12-15 | 378 | 380 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4503 | 380 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Conduct Kick-Off meeting for Build Segment I | 20 hrs | 9 days | 2023-12-18 | 2023-12-29 | 379 | 381 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4504 | 381 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I - Group 1 | 20 hrs | 21 days | 2024-01-02 | 2024-01-31 | 380 | 382 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4505 | 382 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I - Group 2 | 20 hrs | 21 days | 2024-02-01 | 2024-02-29 | 381 | 383 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4506 | 383 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I - Group 3 | 20 hrs | 21 days | 2024-03-01 | 2024-03-29 | 382 | 384FS-5 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4507 | 384 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Create Summary Document for Build Segment I | 20 hrs | 10 days | 2024-03-25 | 2024-04-05 | 383FS-5 days | 385 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4491 | 385 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DEL D646 - Completion of Build Segment I - Draft Submission | 0 hrs | 0 days | 2024-04-05 | 2024-04-05 | 384 | 386 |  | Manojkumar Gurjar,Joy Schneider
4492 | 386 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-04-08 | 2024-04-12 | 385 | 387 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4493 | 387 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Style Guide Review | 1 hr | 1 day | 2024-04-15 | 2024-04-15 | 386 | 388 |  | Dusti Kincl
4494 | 388 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Final Collaborative Review | 20 hrs | 5 days | 2024-04-16 | 2024-04-22 | 387 | 389 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4495 | 389 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Accenture QC | 4 hrs | 2 days | 2024-04-23 | 2024-04-24 | 388 | 390 |  | Joy Schneider
4496 | 390 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DEL D646 - Completion of Build Segment I - Submit | 0 hrs | 0 days | 2024-04-24 | 2024-04-24 | 389 | 391 |  | Joy Schneider
4497 | 391 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Department QC | 4 hrs | 1 day | 2024-04-25 | 2024-04-25 | 390 | 392 |  | Tommy Werner,Gabriela Gibson
4498 | 392 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Contract Manager Review | 8 hrs | 3 days | 2024-04-26 | 2024-04-30 | 391 | 393 |  | Sean Buchanan
4499 | 393 | Future Task |  |  | D646 | Manojkumar Gurjar | Accept | DEL D646 - Completion of Build Segment I - Accept | 0 hrs | 0 days | 2024-04-30 | 2024-04-30 | 392 | 584585 | 2024-04-01 | Sean Buchanan
4629 | 394 | Future Task | Yes |  | D647 | Manojkumar Gurjar |  | D647 - Establish DW/BI Environments | 149 hrs | 96 days | 2023-12-07 | 2024-04-23
4630 | 395 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | DED D647 - Establish DW/BI Environments - Create | 8 hrs | 10 days | 2023-12-07 | 2023-12-20 | 1 | 396 |  | Jarad Hermann,Manojkumar Gurjar
4631 | 396 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DED D647 - Establish DW/BI Environments - Submit | 0 hrs | 0 days | 2023-12-20 | 2023-12-20 | 395 | 397 |  | Manojkumar Gurjar,Joy Schneider
4632 | 397 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DED D647 - Establish DW/BI Environments - Collaborative Review | 24 hrs | 10 days | 2023-12-21 | 2024-01-05 | 396 | 398 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4633 | 398 | Future Task |  |  | D647 | Manojkumar Gurjar | Approve | DED D647 - Establish DW/BI Environments - Approve | 0 hrs | 0 days | 2024-01-05 | 2024-01-05 | 397 | 399 |  | Jimmy Cox
4643 | 399 | Future Task |  |  | D647 | Manojkumar Gurjar |  | Establish DW/BI Environment Connections | 20 hrs | 19 days | 2024-01-08 | 2024-02-02 | 398 | 400 |  | Jarad Hermann,Manojkumar Gurjar
4644 | 400 | Future Task |  |  | D647 | Manojkumar Gurjar |  | Environment build and stand up | 20 hrs | 20 days | 2024-02-05 | 2024-03-01 | 399 | 401 |  | Jarad Hermann,Manojkumar Gurjar
4645 | 401 | Future Task |  |  | D647 | Manojkumar Gurjar |  | Verify access to DW/BI Environments | 20 hrs | 20 days | 2024-03-04 | 2024-03-29 | 400 | 402 |  | Jarad Hermann,Manojkumar Gurjar
4634 | 402 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DEL D647 - Establish DW/BI Environments - Draft Submission | 0 hrs | 0 days | 2024-03-29 | 2024-03-29 | 401 | 403 |  | Manojkumar Gurjar,Joy Schneider
4635 | 403 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-04-01 | 2024-04-05 | 402 | 404 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
4636 | 404 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Style Guide Review | 1 hr | 1 day | 2024-04-08 | 2024-04-08 | 403 | 405 |  | Dusti Kincl
4637 | 405 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Final Collaborative Review | 20 hrs | 5 days | 2024-04-09 | 2024-04-15 | 404 | 406 |  | Jarad Hermann,Manojkumar Gurjar,Matthew Breeding,Jimmy Cox,Angie Robertson
4638 | 406 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Accenture QC | 4 hrs | 2 days | 2024-04-16 | 2024-04-17 | 405 | 407 |  | Joy Schneider
4639 | 407 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DEL D647 - Establish DW/BI Environments - Submit | 0 hrs | 0 days | 2024-04-17 | 2024-04-17 | 406 | 408 |  | Joy Schneider
4640 | 408 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Department QC | 4 hrs | 1 day | 2024-04-18 | 2024-04-18 | 407 | 409 |  | Tommy Werner,Gabriela Gibson
4641 | 409 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Contract Manager Review | 8 hrs | 3 days | 2024-04-19 | 2024-04-23 | 408 | 410 |  | Sean Buchanan
4642 | 410 | Future Task |  |  | D647 | Manojkumar Gurjar | Accept | DEL D647 - Establish DW/BI Environments - Accept | 0 hrs | 0 days | 2024-04-23 | 2024-04-23 | 409 |  | 2024-05-01 | Sean Buchanan
4508 | 411 | Future Task | Yes |  | D648 | Manojkumar Gurjar |  | D648 - Completion of Build Segment II | 197 hrs | 90 days | 2024-03-11 | 2024-07-16
4509 | 412 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | DED D648 - Completion of Build Segment II - Create | 16 hrs | 10 days | 2024-03-11 | 2024-03-22 | 195 | 413 |  | Manojkumar Gurjar,Kurt Meisner
4510 | 413 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DED D648 - Completion of Build Segment II - Submit | 0 hrs | 0 days | 2024-03-22 | 2024-03-22 | 412 | 414 |  | Manojkumar Gurjar,Joy Schneider
4511 | 414 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DED D648 - Completion of Build Segment II - Collaborative Review | 24 hrs | 10 days | 2024-03-25 | 2024-04-05 | 413 | 415 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4512 | 415 | Future Task |  |  | D648 | Manojkumar Gurjar | Approve | DED D648 - Completion of Build Segment II - Approve | 0 hrs | 0 days | 2024-04-05 | 2024-04-05 | 414 | 416 |  | Jimmy Cox
4536 | 416 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment II | 20 hrs | 7 days | 2024-04-08 | 2024-04-16 | 415 | 417 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4537 | 417 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment II | 20 hrs | 8 days | 2024-04-17 | 2024-04-26 | 416 | 418 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4538 | 418 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment II - Group 1 | 20 hrs | 19 days | 2024-04-29 | 2024-05-23 | 417 | 419 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4539 | 419 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment II - Group 2 | 20 hrs | 19 days | 2024-05-24 | 2024-06-20 | 418 | 420FS-9 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4540 | 420 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Create Summary Document for Build Segment II | 20 hrs | 9 days | 2024-06-10 | 2024-06-20 | 419FS-9 days | 421 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4513 | 421 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DEL D648 - Completion of Build Segment II - Draft Submission | 0 hrs | 0 days | 2024-06-20 | 2024-06-20 | 420 | 422 |  | Manojkumar Gurjar,Joy Schneider
4514 | 422 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-06-21 | 2024-06-27 | 421 | 423 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4515 | 423 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Style Guide Review | 1 hr | 1 day | 2024-06-28 | 2024-06-28 | 422 | 424 |  | Dusti Kincl
4516 | 424 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Final Collaborative Review | 20 hrs | 5 days | 2024-07-01 | 2024-07-08 | 423 | 425 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4517 | 425 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Accenture QC | 4 hrs | 2 days | 2024-07-09 | 2024-07-10 | 424 | 426 |  | Joy Schneider
4518 | 426 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DEL D648 - Completion of Build Segment II - Submit | 0 hrs | 0 days | 2024-07-10 | 2024-07-10 | 425 | 427 |  | Joy Schneider
4519 | 427 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Department QC | 4 hrs | 1 day | 2024-07-11 | 2024-07-11 | 426 | 428 |  | Tommy Werner,Gabriela Gibson
4520 | 428 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Contract Manager Review | 8 hrs | 3 days | 2024-07-12 | 2024-07-16 | 427 | 429 |  | Sean Buchanan
4521 | 429 | Future Task |  |  | D648 | Manojkumar Gurjar | Accept | DEL D648 - Completion of Build Segment II - Accept | 0 hrs | 0 days | 2024-07-16 | 2024-07-16 | 428 | 585 | 2024-07-01 | Sean Buchanan
4522 | 430 | Future Task | Yes |  | D649 | Manojkumar Gurjar |  | D649 - Completion of Build Segment III | 217 hrs | 101 days | 2024-06-07 | 2024-10-29
4523 | 431 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | DED D649 - Completion of Build Segment III - Create | 16 hrs | 10 days | 2024-06-07 | 2024-06-20 | 195 | 432 |  | Manojkumar Gurjar,Kurt Meisner
4524 | 432 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DED D649 - Completion of Build Segment III - Submit | 0 hrs | 0 days | 2024-06-20 | 2024-06-20 | 431 | 433 |  | Manojkumar Gurjar,Joy Schneider
4525 | 433 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DED D649 - Completion of Build Segment III - Collaborative Review | 24 hrs | 10 days | 2024-06-21 | 2024-07-05 | 432 | 434 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4526 | 434 | Future Task |  |  | D649 | Manojkumar Gurjar | Approve | DED D649 - Completion of Build Segment III - Approve | 0 hrs | 0 days | 2024-07-05 | 2024-07-05 | 433 | 435 |  | Jimmy Cox
4541 | 435 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment III | 20 hrs | 10 days | 2024-07-08 | 2024-07-19 | 434 | 436 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4542 | 436 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment III | 20 hrs | 5 days | 2024-07-22 | 2024-07-26 | 435 | 437 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4543 | 437 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment III | 20 hrs | 10 days | 2024-07-29 | 2024-08-09 | 436 | 438 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4544 | 438 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment III - Group 1 | 20 hrs | 19 days | 2024-08-12 | 2024-09-06 | 437 | 439 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4545 | 439 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment III - Group 2 | 20 hrs | 20 days | 2024-09-09 | 2024-10-04 | 438 | 440FS-10 days |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4546 | 440 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Create Summary Document for Build Segment III | 20 hrs | 10 days | 2024-09-23 | 2024-10-04 | 439FS-10 days | 441 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4527 | 441 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DEL D649 - Completion of Build Segment III - Draft Submission | 0 hrs | 0 days | 2024-10-04 | 2024-10-04 | 440 | 442 |  | Manojkumar Gurjar,Joy Schneider
4528 | 442 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-10-07 | 2024-10-11 | 441 | 443 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4529 | 443 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Style Guide Review | 1 hr | 1 day | 2024-10-14 | 2024-10-14 | 442 | 444 |  | Dusti Kincl
4530 | 444 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Final Collaborative Review | 20 hrs | 5 days | 2024-10-15 | 2024-10-21 | 443 | 445 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4531 | 445 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Accenture QC | 4 hrs | 2 days | 2024-10-22 | 2024-10-23 | 444 | 446 |  | Joy Schneider
4532 | 446 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DEL D649 - Completion of Build Segment III - Submit | 0 hrs | 0 days | 2024-10-23 | 2024-10-23 | 445 | 447 |  | Joy Schneider
4533 | 447 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Department QC | 4 hrs | 1 day | 2024-10-24 | 2024-10-24 | 446 | 448 |  | Tommy Werner,Gabriela Gibson
4534 | 448 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Contract Manager Review | 8 hrs | 3 days | 2024-10-25 | 2024-10-29 | 447 | 449 |  | Sean Buchanan
4535 | 449 | Future Task |  |  | D649 | Manojkumar Gurjar | Accept | DEL D649 - Completion of Build Segment III - Accept | 0 hrs | 0 days | 2024-10-29 | 2024-10-29 | 448 | 585 | 2024-10-01 | Sean Buchanan
4547 | 450 | Future Task | Yes |  | D653 | Manojkumar Gurjar |  | D653 - Completion of Build Segment I DW/BI | 297 hrs | 147 days | 2024-06-03 | 2025-01-02
4548 | 451 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | DED D653 - Completion of Build Segment I DW/BI - Create | 16 hrs | 10 days | 2024-06-03 | 2024-06-14 | 1 | 452 |  | Manojkumar Gurjar,Kurt Meisner
4549 | 452 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DED D653 - Completion of Build Segment I DW/BI - Submit | 0 hrs | 0 days | 2024-06-14 | 2024-06-14 | 451 | 453 |  | Manojkumar Gurjar,Joy Schneider
4550 | 453 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DED D653 - Completion of Build Segment I DW/BI - Collaborative Review | 24 hrs | 10 days | 2024-06-17 | 2024-06-28 | 452 | 454 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4551 | 454 | Future Task |  |  | D653 | Manojkumar Gurjar | Approve | DED D653 - Completion of Build Segment I DW/BI - Approve | 0 hrs | 0 days | 2024-06-28 | 2024-06-28 | 453 | 455 |  | Jimmy Cox
4575 | 455 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment I DW/BI | 36 hrs | 9 days | 2024-07-01 | 2024-07-12 | 454 | 456 |  | Manojkumar Gurjar,Kurt Meisner
4576 | 456 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment I DW/BI | 20 hrs | 5 days | 2024-07-15 | 2024-07-19 | 455 | 457 |  | Manojkumar Gurjar,Kurt Meisner
4577 | 457 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment I DW/BI | 40 hrs | 10 days | 2024-07-22 | 2024-08-02 | 456 | 458 |  | Manojkumar Gurjar,Kurt Meisner
4578 | 458 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Conduct Kick-Off meeting for Build Segment I DW/BI | 40 hrs | 5 days | 2024-08-05 | 2024-08-09 | 457 | 459 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4579 | 459 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I DW/BI - Group 1 | 20 hrs | 19 days | 2024-08-12 | 2024-09-06 | 458 | 460 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4580 | 460 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I DW/BI - Group 2 | 20 hrs | 20 days | 2024-09-09 | 2024-10-04 | 459 | 461 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4581 | 461 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I DW/BI - Group 3 | 20 hrs | 20 days | 2024-10-07 | 2024-11-01 | 460 | 462 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4582 | 462 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Create Summary Document for Build Segment I DW/BI | 4 hrs | 22 days | 2024-11-04 | 2024-12-06 | 461 | 463 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4552 | 463 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DEL D653 - Completion of Build Segment I DW/BI - Draft Submission | 0 hrs | 0 days | 2024-12-06 | 2024-12-06 | 462 | 464 |  | Manojkumar Gurjar,Joy Schneider
4553 | 464 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-12-09 | 2024-12-13 | 463 | 465 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4554 | 465 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Style Guide Review | 1 hr | 1 day | 2024-12-16 | 2024-12-16 | 464 | 466 |  | Dusti Kincl
4555 | 466 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Final Collaborative Review | 20 hrs | 5 days | 2024-12-17 | 2024-12-23 | 465 | 467 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4556 | 467 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Accenture QC | 4 hrs | 2 days | 2024-12-24 | 2024-12-26 | 466 | 468 |  | Joy Schneider
4557 | 468 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DEL D653 - Completion of Build Segment I DW/BI - Submit | 0 hrs | 0 days | 2024-12-26 | 2024-12-26 | 467 | 469 |  | Joy Schneider
4558 | 469 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Department QC | 4 hrs | 1 day | 2024-12-27 | 2024-12-27 | 468 | 470 |  | Tommy Werner,Gabriela Gibson
4559 | 470 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Contract Manager Review | 8 hrs | 3 days | 2024-12-30 | 2025-01-02 | 469 | 471 |  | Sean Buchanan
4560 | 471 | Future Task |  |  | D653 | Manojkumar Gurjar | Accept | DEL D653 - Completion of Build Segment I DW/BI - Accept | 0 hrs | 0 days | 2025-01-02 | 2025-01-02 | 470 | 585 | 2025-01-01 | Sean Buchanan
4561 | 472 | Future Task | Yes |  | D654 | Manojkumar Gurjar |  | D654 - Completion of Build Segment IV | 217 hrs | 98 days | 2024-09-09 | 2025-01-30
4562 | 473 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | DED D654 - Completion of Build Segment IV - Create | 16 hrs | 10 days | 2024-09-09 | 2024-09-20 | 1 | 474 |  | Manojkumar Gurjar,Kurt Meisner
4563 | 474 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DED D654 - Completion of Build Segment IV - Submit | 0 hrs | 0 days | 2024-09-20 | 2024-09-20 | 473 | 475 |  | Manojkumar Gurjar,Joy Schneider
4564 | 475 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DED D654 - Completion of Build Segment IV - Collaborative Review | 24 hrs | 10 days | 2024-09-23 | 2024-10-04 | 474 | 476 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4565 | 476 | Future Task |  |  | D654 | Manojkumar Gurjar | Approve | DED D654 - Completion of Build Segment IV - Approve | 0 hrs | 0 days | 2024-10-04 | 2024-10-04 | 475 | 477 |  | Jimmy Cox
4583 | 477 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment IV | 20 hrs | 10 days | 2024-10-07 | 2024-10-18 | 476 | 478 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4584 | 478 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment IV | 20 hrs | 5 days | 2024-10-21 | 2024-10-25 | 477 | 479 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4585 | 479 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment IV | 20 hrs | 10 days | 2024-10-28 | 2024-11-08 | 478 | 480 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4586 | 480 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment IV - Group 1 | 20 hrs | 17 days | 2024-11-12 | 2024-12-06 | 479 | 481 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4587 | 481 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment IV - Group 2 | 20 hrs | 19 days | 2024-12-09 | 2025-01-06 | 480 | 482FS-14 days,483 |  | Nilesh Choudhari,Roxanne Camba,Claudio Rosado,Glaiza Barnes
4588 | 482 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Create Summary Document for Build Segment IV | 20 hrs | 13 days | 2024-12-16 | 2025-01-03 | 481FS-14 days | 483 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4566 | 483 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DEL D654 - Completion of Build Segment IV - Draft Submission | 0 hrs | 0 days | 2025-01-06 | 2025-01-06 | 481482 | 484 |  | Manojkumar Gurjar,Joy Schneider
4567 | 484 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-01-07 | 2025-01-13 | 483 | 485 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4568 | 485 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Style Guide Review | 1 hr | 1 day | 2025-01-14 | 2025-01-14 | 484 | 486 |  | Dusti Kincl
4569 | 486 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Final Collaborative Review | 20 hrs | 5 days | 2025-01-15 | 2025-01-22 | 485 | 487 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4570 | 487 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Accenture QC | 4 hrs | 2 days | 2025-01-23 | 2025-01-24 | 486 | 488 |  | Joy Schneider
4571 | 488 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DEL D654 - Completion of Build Segment IV - Submit | 0 hrs | 0 days | 2025-01-24 | 2025-01-24 | 487 | 489 |  | Joy Schneider
4572 | 489 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Department QC | 4 hrs | 1 day | 2025-01-27 | 2025-01-27 | 488 | 490 |  | Tommy Werner,Gabriela Gibson
4573 | 490 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Contract Manager Review | 8 hrs | 3 days | 2025-01-28 | 2025-01-30 | 489 | 491 |  | Sean Buchanan
4574 | 491 | Future Task |  |  | D654 | Manojkumar Gurjar | Accept | DEL D654 - Completion of Build Segment IV - Accept | 0 hrs | 0 days | 2025-01-30 | 2025-01-30 | 490 | 585 | 2025-01-01 | Sean Buchanan
4589 | 492 | Future Task | Yes |  | D659 | Manojkumar Gurjar |  | D659 - Completion of Build Segment II DW/BI | 219 hrs | 116 days | 2024-09-09 | 2025-02-25
4590 | 493 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | DED D659 - Completion of Build Segment II DW/BI - Create | 16 hrs | 10 days | 2024-09-09 | 2024-09-20 | 1 | 494 |  | Manojkumar Gurjar,Kurt Meisner
4591 | 494 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DED D659 - Completion of Build Segment II DW/BI - Submit | 0 hrs | 0 days | 2024-09-20 | 2024-09-20 | 493 | 495 |  | Manojkumar Gurjar,Joy Schneider
4592 | 495 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DED D659 - Completion of Build Segment II DW/BI - Collaborative Review | 24 hrs | 10 days | 2024-09-23 | 2024-10-04 | 494 | 496 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4593 | 496 | Future Task |  |  | D659 | Manojkumar Gurjar | Approve | DED D659 - Completion of Build Segment II DW/BI - Approve | 0 hrs | 0 days | 2024-10-04 | 2024-10-04 | 495 | 497 |  | Jimmy Cox
4603 | 497 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment II DW/BI | 40 hrs | 10 days | 2024-10-07 | 2024-10-18 | 496 | 498 |  | Manojkumar Gurjar,Kurt Meisner
4604 | 498 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment II DW/BI | 20 hrs | 5 days | 2024-10-21 | 2024-10-25 | 497 | 499 |  | Manojkumar Gurjar,Kurt Meisner
4605 | 499 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment II DW/BI | 20 hrs | 5 days | 2024-10-28 | 2024-11-01 | 498 | 500 |  | Manojkumar Gurjar,Kurt Meisner
4606 | 500 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment II DW/BI - Group 1 | 20 hrs | 17 days | 2024-11-04 | 2024-11-27 | 499 | 501 |  | Manojkumar Gurjar,Kurt Meisner
4607 | 501 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment II DW/BI - Group 2 | 2 hrs | 23 days | 2024-12-02 | 2025-01-03 | 500 | 502 |  | Manojkumar Gurjar,Kurt Meisner
4608 | 502 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Create Summary Document for Build Segment II DW/BI | 20 hrs | 19 days | 2025-01-06 | 2025-01-31 | 501 | 503 |  | Manojkumar Gurjar,Kurt Meisner
4594 | 503 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DEL D659 - Completion of Build Segment II DW/BI - Draft Submission | 0 hrs | 0 days | 2025-01-31 | 2025-01-31 | 502 | 504 |  | Manojkumar Gurjar,Joy Schneider
4595 | 504 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-02-03 | 2025-02-07 | 503 | 505 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4596 | 505 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Style Guide Review | 1 hr | 1 day | 2025-02-10 | 2025-02-10 | 504 | 506 |  | Dusti Kincl
4597 | 506 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Final Collaborative Review | 20 hrs | 5 days | 2025-02-11 | 2025-02-17 | 505 | 507 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4598 | 507 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Accenture QC | 4 hrs | 2 days | 2025-02-18 | 2025-02-19 | 506 | 508 |  | Joy Schneider
4599 | 508 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DEL D659 - Completion of Build Segment II DW/BI - Submit | 0 hrs | 0 days | 2025-02-19 | 2025-02-19 | 507 | 509 |  | Joy Schneider
4600 | 509 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Department QC | 4 hrs | 1 day | 2025-02-20 | 2025-02-20 | 508 | 510 |  | Tommy Werner,Gabriela Gibson
4601 | 510 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Contract Manager Review | 8 hrs | 3 days | 2025-02-21 | 2025-02-25 | 509 | 511 |  | Sean Buchanan
4602 | 511 | Future Task |  |  | D659 | Manojkumar Gurjar | Accept | DEL D659 - Completion of Build Segment II DW/BI - Accept | 0 hrs | 0 days | 2025-02-25 | 2025-02-25 | 510 | 585 | 2025-04-01 | Sean Buchanan
4609 | 512 | Future Task | Yes |  | D668 | Manojkumar Gurjar |  | D668 - Completion of Build Segment III DW/BI | 281 hrs | 93 days | 2024-10-30 | 2025-03-17
4610 | 513 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | DED D668 - Completion of Build Segment III DW/BI - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1 | 514 |  | Manojkumar Gurjar,Kurt Meisner
4611 | 514 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DED D668 - Completion of Build Segment III DW/BI - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 513 | 515 |  | Manojkumar Gurjar,Joy Schneider
4612 | 515 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DED D668 - Completion of Build Segment III DW/BI - Collaborative Review | 24 hrs | 10 days | 2024-11-14 | 2024-11-27 | 514 | 516 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4613 | 516 | Future Task |  |  | D668 | Manojkumar Gurjar | Approve | DED D668 - Completion of Build Segment III DW/BI - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 515 | 517 |  | Jimmy Cox
4623 | 517 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment III DW/BI | 40 hrs | 5 days | 2024-12-02 | 2024-12-06 | 516 | 518SS+2 days |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4624 | 518 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment III DW/BI | 40 hrs | 5 days | 2024-12-04 | 2024-12-10 | 517SS+2 days | 519 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4625 | 519 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment III DW/BI | 24 hrs | 3 days | 2024-12-11 | 2024-12-13 | 518 | 520 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4626 | 520 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment III DW/BI - Group 1 | 20 hrs | 18 days | 2024-12-16 | 2025-01-10 | 519 | 521 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4627 | 521 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment III DW/BI - Group 2 | 20 hrs | 18 days | 2025-01-13 | 2025-02-06 | 520 | 522 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4628 | 522 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Create Summary Document for Build Segment III DW/BI | 40 hrs | 10 days | 2025-02-07 | 2025-02-20 | 521 | 523 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4614 | 523 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DEL D668 - Completion of Build Segment III DW/BI - Draft Submission | 0 hrs | 0 days | 2025-02-20 | 2025-02-20 | 522 | 524 |  | Manojkumar Gurjar,Joy Schneider
4615 | 524 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-02-21 | 2025-02-27 | 523 | 525 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4616 | 525 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Style Guide Review | 1 hr | 1 day | 2025-02-28 | 2025-02-28 | 524 | 526 |  | Dusti Kincl
4617 | 526 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Final Collaborative Review | 20 hrs | 5 days | 2025-03-03 | 2025-03-07 | 525 | 527 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4618 | 527 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Accenture QC | 4 hrs | 2 days | 2025-03-10 | 2025-03-11 | 526 | 528 |  | Joy Schneider
4619 | 528 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DEL D668 - Completion of Build Segment III DW/BI - Submit | 0 hrs | 0 days | 2025-03-11 | 2025-03-11 | 527 | 529 |  | Joy Schneider
4620 | 529 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Department QC | 4 hrs | 1 day | 2025-03-12 | 2025-03-12 | 528 | 530 |  | Tommy Werner,Gabriela Gibson
4621 | 530 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Contract Manager Review | 8 hrs | 3 days | 2025-03-13 | 2025-03-17 | 529 | 531 |  | Sean Buchanan
4622 | 531 | Future Task |  |  | D668 | Manojkumar Gurjar | Accept | DEL D668 - Completion of Build Segment III DW/BI - Accept | 0 hrs | 0 days | 2025-03-17 | 2025-03-17 | 530 | 585 | 2025-08-01 | Sean Buchanan
4646 | 532 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | WP410 - Integration and Interface Strategy | 160 hrs | 95 days | 2023-08-07 | 2023-12-21
4647 | 533 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WPED WP410 - Integration and Interface Strategy - Create | 16 hrs | 10 days | 2023-08-07 | 2023-08-18 | 1 | 534 |  | Manojkumar Gurjar,Kurt Meisner
4648 | 534 | Future Task |  |  | WP410 | Manojkumar Gurjar | Submit | WPED WP410 - Integration and Interface Strategy - Submit | 0 hrs | 0 days | 2023-08-18 | 2023-08-18 | 533 | 535 |  | Manojkumar Gurjar,Joy Schneider
4649 | 535 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WPED WP410 - Integration and Interface Strategy - Review | 24 hrs | 10 days | 2023-08-21 | 2023-09-01 | 534 | 536 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4650 | 536 | Future Task |  |  | WP410 | Manojkumar Gurjar | Approve | WPED WP410 - Integration and Interface Strategy - Approve | 0 hrs | 0 days | 2023-09-01 | 2023-09-01 | 535 | 537 |  | Jimmy Cox
4655 | 537 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | Define Interface and Integration Approach | 20 hrs | 19 days | 2023-09-05 | 2023-09-29 | 536 | 538 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4656 | 538 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | Create Interface and Integration Architecture Diagram | 20 hrs | 15 days | 2023-10-02 | 2023-10-20 | 537 | 539540 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4657 | 539 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | Review and update Interface and Integration Operations | 20 hrs | 19 days | 2023-10-23 | 2023-11-17 | 538 | 540 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4658 | 540 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | Finalize the Interface and Integration Strategy Document | 20 hrs | 7 days | 2023-11-20 | 2023-11-30 | 538539 | 541 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4651 | 541 | Future Task |  |  | WP410 | Manojkumar Gurjar | Submit | WP WP410 - Integration and Interface Strategy - Submit | 0 hrs | 0 days | 2023-11-30 | 2023-11-30 | 540 | 542 |  | Manojkumar Gurjar,Joy Schneider
4652 | 542 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WP WP410 - Integration and Interface Strategy - Collaborative Review & Update | 20 hrs | 10 days | 2023-12-01 | 2023-12-14 | 541 | 543 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4653 | 543 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WP WP410 - Integration and Interface Strategy - Final Review & Edits | 20 hrs | 5 days | 2023-12-15 | 2023-12-21 | 542 | 544 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4654 | 544 | Future Task |  |  | WP410 | Manojkumar Gurjar | Approve | WP WP410 - Integration and Interface Strategy - Approve | 0 hrs | 0 days | 2023-12-21 | 2023-12-21 | 543 | 1070FS+92 days | 2023-11-01 | Jimmy Cox
5603 | 545 | Future Task |  |  | WP426 | Jarad Hermann |  | WP426 - System Infrastructure Capacity Plan | 148 hrs | 52 days | 2025-10-06 | 2025-12-19
5604 | 546 | Future Task |  |  | WP426 | Jarad Hermann | Create | WPED WP426 - System Infrastructure Capacity Plan - Create | 8 hrs | 10 days | 2025-10-06 | 2025-10-17 | 1 | 547 |  | Jarad Hermann
5605 | 547 | Future Task |  |  | WP426 | Jarad Hermann | Submit | WPED WP426 - System Infrastructure Capacity Plan - Submit | 0 hrs | 0 days | 2025-10-17 | 2025-10-17 | 546 | 548 |  | Joy Schneider,Jarad Hermann
5606 | 548 | Future Task |  |  | WP426 | Jarad Hermann | Review | WPED WP426 - System Infrastructure Capacity Plan - Review | 16 hrs | 10 days | 2025-10-20 | 2025-10-31 | 547 | 549 |  | Jarad Hermann,Jimmy Cox,Angie Robertson,Sean Buchanan
5607 | 549 | Future Task |  |  | WP426 | Jarad Hermann | Approve | WPED WP426 - System Infrastructure Capacity Plan - Approve | 0 hrs | 0 days | 2025-10-31 | 2025-10-31 | 548 | 550 |  | Jimmy Cox
5608 | 550 | Future Task |  |  | WP426 | Jarad Hermann |  | Review and refine the excel doc | 20 hrs | 17 days | 2025-11-03 | 2025-11-26 | 549 | 551SS,552SS,553SS,554SS |  | Jarad Hermann,Bryan Sohayda | To address JC comment sent via email on 5/31, please update task name to "Review and refine the FL PALM Capacity Plan ( excel doc)" | Mary
5609 | 551 | Future Task |  |  | WP426 | Jarad Hermann |  | Review and refine the FL PALM Capacity Plan | 20 hrs | 17 days | 2025-11-03 | 2025-11-26 | 550SS | 555 |  | Jarad Hermann,Bryan Sohayda | To address JC comment sent via email on 5/31, please update task name to "Review and refine the FL PALM Capacity Plan ( word doc)" | Mary
5610 | 552 | Future Task |  |  | WP426 | Jarad Hermann |  | Define and document current infrastructure demand | 20 hrs | 17 days | 2025-11-03 | 2025-11-26 | 550SS | 555 |  | Jarad Hermann,Bryan Sohayda
5611 | 553 | Future Task |  |  | WP426 | Jarad Hermann |  | Define and document current infrastructure capacity | 20 hrs | 17 days | 2025-11-03 | 2025-11-26 | 550SS | 555 |  | Jarad Hermann,Bryan Sohayda
5612 | 554 | Future Task |  |  | WP426 | Jarad Hermann |  | Define and document projected infrastructure demand | 20 hrs | 17 days | 2025-11-03 | 2025-11-26 | 550SS | 555 |  | Jarad Hermann,Bryan Sohayda
5613 | 555 | Future Task |  |  | WP426 | Jarad Hermann | Submit | WP WP426 - System Infrastructure Capacity Plan - Submit | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 554551552553 | 556 |  | Joy Schneider,Jarad Hermann
5614 | 556 | Future Task |  |  | WP426 | Jarad Hermann | Review | WP WP426 - System Infrastructure Capacity Plan - Collaborative Review & Update | 12 hrs | 10 days | 2025-12-01 | 2025-12-12 | 555 | 557 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5615 | 557 | Future Task |  |  | WP426 | Jarad Hermann | Review | WP WP426 - System Infrastructure Capacity Plan - Final Review & Edits | 12 hrs | 5 days | 2025-12-15 | 2025-12-19 | 556 | 558 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5616 | 558 | Future Task |  |  | WP426 | Jarad Hermann | Approve | WP WP426 - System Infrastructure Capacity Plan - Approve | 0 hrs | 0 days | 2025-12-19 | 2025-12-19 | 557 |  |  | Jimmy Cox
3868 | 559 | Future Task | Yes |  |  |  |  | Environment Builds | 137 hrs | 207 days | 2024-08-05 | 2025-05-30 |  |  |  |  | Is this related to a WP? | TW
4203 | 560 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure System Test Environment | 10 hrs | 15 days | 2024-08-05 | 2024-08-23 | 605 | 561 |  | Manojkumar Gurjar,Jarad Hermann | Is this the correct naming convention? | TW
4204 | 561 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate System Test Environment | 8 hrs | 5 days | 2024-08-26 | 2024-08-30 | 560 | 648 |  | Manojkumar Gurjar,Jarad Hermann
4195 | 562 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Interface Test Environment | 10 hrs | 14 days | 2024-09-03 | 2024-09-20 | 1083FS-10 days | 563 |  | Manojkumar Gurjar,Jarad Hermann
4196 | 563 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Interface Test Environment | 8 hrs | 5 days | 2024-09-23 | 2024-09-27 | 562 | 789 |  | Manojkumar Gurjar,Jarad Hermann
4197 | 564 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Mock Conversion Test Environment | 10 hrs | 15 days | 2024-08-05 | 2024-08-23 | 1030 | 565 |  | Manojkumar Gurjar,Jarad Hermann
4198 | 565 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Mock Conversion Test Environment | 8 hrs | 5 days | 2024-08-26 | 2024-08-30 | 564 | 627 |  | Manojkumar Gurjar,Jarad Hermann
4199 | 566 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure UAT Test Environment | 10 hrs | 10 days | 2025-02-03 | 2025-02-14 | 1248FS+46 days | 567 |  | Manojkumar Gurjar,Jarad Hermann
4200 | 567 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate UAT Test Environment | 10 hrs | 10 days | 2025-02-17 | 2025-02-28 | 566 | 568 |  | Manojkumar Gurjar,Jarad Hermann
4201 | 568 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Load Security Roles to ForgeRock for UAT | 4 hrs | 4 days | 2025-03-11 | 2025-03-14 | 5671821 | 569 |  | Jarad Hermann
4202 | 569 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Security Roles in ForgeRock for UAT | 5 hrs | 5 days | 2025-03-17 | 2025-03-21 | 568 | 1250585 |  | Jarad Hermann
4191 | 570 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Dry Run Test Environment | 10 hrs | 14 days | 2025-05-05 | 2025-05-22 |  | 571 |  | Manojkumar Gurjar,Jarad Hermann
4192 | 571 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Dry Run Test Environment | 8 hrs | 5 days | 2025-05-23 | 2025-05-30 | 570 | 829 |  | Manojkumar Gurjar,Jarad Hermann
4193 | 572 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Performance Test Environment | 10 hrs | 15 days | 2025-05-05 | 2025-05-23 | 1186 | 573 |  | Manojkumar Gurjar,Jarad Hermann
4194 | 573 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Performance Test Environment | 8 hrs | 4 days | 2025-05-27 | 2025-05-30 | 572 | 969 |  | Manojkumar Gurjar,Jarad Hermann
4189 | 574 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Disaster Recovery Test Environment | 10 hrs | 15 days | 2025-03-03 | 2025-03-21 | 1172 | 575 |  | Manojkumar Gurjar,Jarad Hermann
4190 | 575 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Disaster Recovery Test Environment | 8 hrs | 5 days | 2025-03-24 | 2025-03-28 | 574 | 987 |  | Manojkumar Gurjar,Jarad Hermann
6809 | 576 | Future Task | [5 empty] | Other | 48 hrs | 187 days | 2024-01-08 | 2024-09-30 |  |  |  |  | Discuss | Angie
7144 | 577 | Future Task |  |  |  | Stacey Terry |  | Support Agency Configuration Workbook | 20 hrs | 103 days | 2024-01-08 | 2024-05-31 | 126FS+6 days | 578 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
7145 | 578 | Future Task |  |  |  | Stacey Terry |  | Load Agency Configuration Workbook | 20 hrs | 64 days | 2024-06-03 | 2024-08-30 | 577 |  |  | Stacey Terry,Yogesh Deshmukh,Mary Punty | 1. Add a new task after task 577. New task: "Confirm completeness of agency configuration workbooks" Start May 6, 2024, End June 28, 2024 2. Task 578 - Update task name to "Update configuration workbooks and load agency configurations" | Mary/Stacey
6808 | 579 | Future Task |  |  |  | Stacey Terry |  | Define User Preferences | 2 hrs | 10 days | 2024-07-31 | 2024-08-13 | 237 | 1815 |  | Stacey Terry
6810 | 580 | Future Task |  |  |  | Stacey Terry |  | Create Batch Design/Online | 2 hrs | 22 days | 2024-07-01 | 2024-07-31 | 47,66,105,145,164FS+24 days | 581 |  | Stacey Terry,Manojkumar Gurjar
6807 | 581 | Future Task |  |  |  | Stacey Terry |  | Create Batch Design/Interface | 2 hrs | 22 days | 2024-08-01 | 2024-08-30 | 580 | 582 |  | Stacey Terry,Manojkumar Gurjar
6811 | 582 | Future Task |  |  |  | Stacey Terry |  | Review and Confirm Batch Design | 2 hrs | 20 days | 2024-09-03 | 2024-09-30 | 581 |  |  | Stacey Terry,Manojkumar Gurjar
3771 | 583 | Future Task | [5 empty] | Test | 6,513.58 hrs | 617 days | 2023-07-03 | 2025-12-12
7153 | 584 | Future Task | Yes |  | SG2 | Jimmy Cox | Milestone | Stage Gate 2: Ready to Begin System Testing | 0 hrs | 0 days | 2024-05-08 | 2024-05-08 | 47,66,145,157,393 |  | July/August 2024 | Jimmy Cox,Angie Robertson,Matt Cole | This should be July / August 2024, per the SOW Per conversations the week of 5/30, we will baseline the SGs at their actual date or the last business day in the month. We will then update to start as soon as possible, which will allow us to see date shifts based on predecessor and successor links. | Angie
7154 | 585 | Future Task | Yes |  | SG3 | Jimmy Cox | Milestone | Stage Gate 3: Ready to Begin UAT | 0 hrs | 0 days | 2025-03-28 | 2025-03-28 | 47,66,145,164,393,429,449,471,491,511,531,1248,747,688,648,569 |  | March 2025 - ESC | Jimmy Cox,Angie Robertson,Matt Cole | This should be March 2025 per the SOW. The Resource Names include the ESC and we need tasks / dates for ESC review prior to milestone date. Per conversations the week of 5/30, we will baseline the SGs at their actual date or the last business day in the month. We will then update to start as soon as possible, which will allow us to see date shifts based on predecessor and successor links. | Angie
4662 | 586 | Future Task |  |  | D643 | Stacey Terry |  | D643 - Updated System Testing Plan | 343 hrs | 361 days | 2023-07-03 | 2024-12-06
4663 | 587 | Future Task |  |  | D643 | Stacey Terry | Create | DED D643 - Updated System Testing Plan - Create | 16 hrs | 10 days | 2023-07-03 | 2023-07-17 | 1FS+47 days | 588 |  | Stacey Terry,Mary Punty
4664 | 588 | Future Task |  |  | D643 | Stacey Terry | Submit | DED D643 - Updated System Testing Plan - Submit | 0 hrs | 0 days | 2023-07-17 | 2023-07-17 | 587 | 589 |  | Stacey Terry,Joy Schneider
4665 | 589 | Future Task |  |  | D643 | Stacey Terry | Review | DED D643 - Updated System Testing Plan - Collaborative Review | 24 hrs | 10 days | 2023-07-18 | 2023-07-31 | 588 | 590 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4666 | 590 | Future Task |  |  | D643 | Stacey Terry | Approve | DED D643 - Updated System Testing Plan - Approve | 0 hrs | 0 days | 2023-07-31 | 2023-07-31 | 589 | 591FS+80 days |  | Jimmy Cox
4685 | 591 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test approach for Financials and Payroll | 20 hrs | 15 days | 2023-11-27 | 2023-12-15 | 590FS+80 days | 592 |  | Yogesh Deshmukh,Stacey Terry,Mary Punty,Manojkumar Gurjar,Kurt Meisner,Matt Cole
4686 | 592 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test Cycles for Financials and Payroll | 20 hrs | 9 days | 2023-12-18 | 2023-12-29 | 591 | 593FS-4 days |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Mary Punty
4687 | 593 | Future Task |  |  | D643 | Stacey Terry |  | Identify System Test Resources for Financials and Payroll | 20 hrs | 11 days | 2023-12-26 | 2024-01-10 | 592FS-4 days | 594SS+4 days |  | Stacey Terry,Manojkumar Gurjar,Janice Jackson,Tiffany Porter,Brendan Jones,Jennifer Reeves,Deana Metcalf,Matthew Breeding,Carolyn Hicks
4688 | 594 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test Tools and Test Management processes | 20 hrs | 11 days | 2024-01-02 | 2024-01-17 | 593SS+4 days | 595FS-2 days |  | Yogesh Deshmukh,Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jennifer Reeves
4689 | 595 | Future Task |  |  | D643 | Stacey Terry |  | Create Initial List of System Test Scenarios for Financials and Payroll | 20 hrs | 24 days | 2024-01-16 | 2024-02-16 | 594FS-2 days | 596FS-5 days |  | Yogesh Deshmukh,Stacey Terry,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4690 | 596 | Future Task |  |  | D643 | Stacey Terry |  | Define requirements traceability approach for system testing | 20 hrs | 10 days | 2024-02-12 | 2024-02-23 | 595FS-5 days | 597 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Mary Punty,Jennifer Reeves
4667 | 597 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 - Updated System Testing Plan - Draft Submission | 0 hrs | 0 days | 2024-02-23 | 2024-02-23 | 596 | 598 |  | Stacey Terry,Joy Schneider
4668 | 598 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-02-26 | 2024-03-01 | 597 | 599 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4669 | 599 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Style Guide Review | 1 hr | 1 day | 2024-03-04 | 2024-03-04 | 598 | 600 |  | Dusti Kincl
4670 | 600 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Final Collaborative Review | 20 hrs | 5 days | 2024-03-05 | 2024-03-11 | 599 | 601 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4671 | 601 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Accenture QC | 4 hrs | 2 days | 2024-03-12 | 2024-03-13 | 600 | 602 |  | Joy Schneider
4672 | 602 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 - Updated System Testing Plan - Submit | 0 hrs | 0 days | 2024-03-13 | 2024-03-13 | 601 | 603 |  | Joy Schneider
4673 | 603 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Department QC | 4 hrs | 1 day | 2024-03-14 | 2024-03-14 | 602 | 604 |  | Tommy Werner,Gabriela Gibson
4674 | 604 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Contract Manager Review | 8 hrs | 3 days | 2024-03-15 | 2024-03-19 | 603 | 605 |  | Sean Buchanan
4675 | 605 | Future Task |  |  | D643 | Stacey Terry | Accept | DEL D643 - Updated System Testing Plan - Accept | 0 hrs | 0 days | 2024-03-19 | 2024-03-19 | 604 | 606FS+101 days,560 | 2024-03-01 | Sean Buchanan
4691 | 606 | Future Task |  |  | D643 | Stacey Terry |  | Update DED D643 to include the system testing plan for DW and BI | 20 hrs | 10 days | 2024-08-12 | 2024-08-23 | 605FS+101 days | 607FS+9 days |  | Mary Punty,Stacey Terry
4692 | 607 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test approach for DW & BI | 20 hrs | 20 days | 2024-09-09 | 2024-10-04 | 606FS+9 days | 608SS+10 days |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
4693 | 608 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test Cycles for DW & BI | 20 hrs | 15 days | 2024-09-23 | 2024-10-11 | 607SS+10 days | 609SS+5 days |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
4694 | 609 | Future Task |  |  | D643 | Stacey Terry |  | Identify System Test Resources for DW & BI | 20 hrs | 10 days | 2024-09-30 | 2024-10-11 | 608SS+5 days | 610 |  | Jennifer Reeves,Mary Punty,Stacey Terry,Deana Metcalf,Manojkumar Gurjar
4695 | 610 | Future Task |  |  | D643 | Stacey Terry |  | Create Initial List of DW & BI System Test Scenarios | 4 hrs | 20 days | 2024-10-14 | 2024-11-08 | 609 | 611 |  | Jennifer Reeves,Manojkumar Gurjar
4676 | 611 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 2.0 - Updated System Testing Plan - Draft Submission | 0 hrs | 0 days | 2024-11-08 | 2024-11-08 | 610 | 612 |  | Stacey Terry,Joy Schneider
4677 | 612 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Pre-Submission Collaborative Review | 5 hrs | 5 days | 2024-11-12 | 2024-11-18 | 611 | 613 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4678 | 613 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Style Guide Review | 1 hr | 1 day | 2024-11-19 | 2024-11-19 | 612 | 614 |  | Dusti Kincl
4679 | 614 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Final Collaborative Review | 20 hrs | 5 days | 2024-11-20 | 2024-11-26 | 613 | 615 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4680 | 615 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Accenture QC | 4 hrs | 2 days | 2024-11-27 | 2024-12-02 | 614 | 616 |  | Joy Schneider
4681 | 616 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 2.0 - Updated System Testing Plan - Submit | 0 hrs | 0 days | 2024-12-02 | 2024-12-02 | 615 | 617 |  | Joy Schneider
4682 | 617 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Department QC | 4 hrs | 1 day | 2024-12-03 | 2024-12-03 | 616 | 618 |  | Tommy Werner,Gabriela Gibson
4683 | 618 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Contract Manager Review | 8 hrs | 3 days | 2024-12-04 | 2024-12-06 | 617 | 619 |  | Sean Buchanan
4684 | 619 | Future Task |  |  | D643 | Stacey Terry | Accept | DEL D643 2.0 - Updated System Testing Plan - Accept | 0 hrs | 0 days | 2024-12-06 | 2024-12-06 | 618 |  |  | Sean Buchanan
5004 | 620 | Future Task | Yes |  | D651 | Manojkumar Gurjar |  | D651 - Completion of Mock Conversion I | 197 hrs | 71 days | 2024-07-15 | 2024-10-22
5005 | 621 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | DED D651 - Completion of Mock Conversion I - Create | 16 hrs | 10 days | 2024-07-15 | 2024-07-26 | 1042FS-28 days | 622 |  | Manojkumar Gurjar,Kurt Meisner
5006 | 622 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DED D651 - Completion of Mock Conversion I - Submit | 0 hrs | 0 days | 2024-07-26 | 2024-07-26 | 621 | 623 |  | Manojkumar Gurjar,Joy Schneider
5007 | 623 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DED D651 - Completion of Mock Conversion I - Collaborative Review | 24 hrs | 10 days | 2024-07-29 | 2024-08-09 | 622 | 624 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5008 | 624 | Future Task |  |  | D651 | Manojkumar Gurjar | Approve | DED D651 - Completion of Mock Conversion I - Approve | 0 hrs | 0 days | 2024-08-09 | 2024-08-09 | 623 | 625 |  | Jimmy Cox
5018 | 625 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Confirm Mock 1 Conversion Test Environment Readiness | 20 hrs | 5 days | 2024-08-12 | 2024-08-16 | 624 | 626 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5019 | 626 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Create Mock 1 Conversion Checklist | 20 hrs | 10 days | 2024-08-19 | 2024-08-30 | 625 | 627 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5020 | 627 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Execute Mock 1 – Conversion | 20 hrs | 9 days | 2024-09-03 | 2024-09-13 | 626565 | 628 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5021 | 628 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Validate Mock 1 – Conversion | 20 hrs | 5 days | 2024-09-16 | 2024-09-20 | 627 | 629 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5022 | 629 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Conduct Mock 1 - Conversion Test Exit Criteria Review Meeting | 20 hrs | 5 days | 2024-09-23 | 2024-09-27 | 628 | 630 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
5009 | 630 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DEL D651 - Completion of Mock Conversion I - Draft Submission | 0 hrs | 0 days | 2024-09-27 | 2024-09-27 | 629 | 631 |  | Manojkumar Gurjar,Joy Schneider
5010 | 631 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-09-30 | 2024-10-04 | 630 | 632 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5011 | 632 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Style Guide Review | 1 hr | 1 day | 2024-10-07 | 2024-10-07 | 631 | 633 |  | Dusti Kincl
5012 | 633 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Final Collaborative Review | 20 hrs | 5 days | 2024-10-08 | 2024-10-14 | 632 | 634 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
5013 | 634 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Accenture QC | 4 hrs | 2 days | 2024-10-15 | 2024-10-16 | 633 | 635 |  | Joy Schneider
5014 | 635 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DEL D651 - Completion of Mock Conversion I - Submit | 0 hrs | 0 days | 2024-10-16 | 2024-10-16 | 634 | 636 |  | Joy Schneider
5015 | 636 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Department QC | 4 hrs | 1 day | 2024-10-17 | 2024-10-17 | 635 | 637 |  | Tommy Werner,Gabriela Gibson
5016 | 637 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Contract Manager Review | 8 hrs | 3 days | 2024-10-18 | 2024-10-22 | 636 | 638 |  | Sean Buchanan
5017 | 638 | Future Task |  |  | D651 | Manojkumar Gurjar | Accept | DEL D651 - Completion of Mock Conversion I - Accept | 0 hrs | 0 days | 2024-10-22 | 2024-10-22 | 637 | 663FS-3 days | 2024-11-01 | Sean Buchanan
4696 | 639 | Future Task | Yes |  | D652 | Stacey Terry |  | D652 - Completion of System Test Segment I | 206 hrs | 123 days | 2024-07-08 | 2025-01-02
4697 | 640 | Future Task |  |  | D652 | Stacey Terry | Create | DED D652 - Completion of System Test Segment I - Create | 16 hrs | 10 days | 2024-07-08 | 2024-07-19 | 1 | 641 |  | Stacey Terry,Mary Punty
4698 | 641 | Future Task |  |  | D652 | Stacey Terry | Submit | DED D652 - Completion of System Test Segment I - Submit | 0 hrs | 0 days | 2024-07-19 | 2024-07-19 | 640 | 642 |  | Stacey Terry,Joy Schneider
4699 | 642 | Future Task |  |  | D652 | Stacey Terry | Review | DED D652 - Completion of System Test Segment I - Collaborative Review | 24 hrs | 10 days | 2024-07-22 | 2024-08-02 | 641 | 643 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4700 | 643 | Future Task |  |  | D652 | Stacey Terry | Approve | DED D652 - Completion of System Test Segment I - Approve | 0 hrs | 0 days | 2024-08-02 | 2024-08-02 | 642 | 644 |  | Jimmy Cox
4752 | 644 | Future Task |  |  | D652 | Stacey Terry |  | Create Work Unit Tracker for System Test Segment 1 Execution | 20 hrs | 10 days | 2024-08-05 | 2024-08-16 | 643 | 645 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4753 | 645 | Future Task |  |  | D652 | Stacey Terry |  | Review, Update and confirm Work Unit Tracker for System Test Segment 1 Execution | 20 hrs | 10 days | 2024-08-19 | 2024-08-30 | 644 | 646SS+5 days |  | Mary Punty,Stacey Terry,Deana Metcalf,Janice Jackson,Tiffany Porter,Brendan Jones
4754 | 646 | Future Task |  |  | D652 | Stacey Terry |  | Confirm System Test Environment Readiness | 20 hrs | 5 days | 2024-08-26 | 2024-08-30 | 645SS+5 days | 647SS |  | Manojkumar Gurjar,Jarad Hermann
4755 | 647 | Future Task |  |  | D652 | Stacey Terry |  | Conduct System Test Kick Off Meeting | 30 hrs | 5 days | 2024-08-26 | 2024-08-30 | 646SS | 648 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4756 | 648 | Future Task |  |  | D652 | Stacey Terry |  | Execute System Test Segment 1 - this is a WU | 10 hrs | 51 days | 2024-09-17 | 2024-11-27 | 6471056561 | 649,650FS-3 days,585 |  | Yogesh Deshmukh,Stacey Terry,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4757 | 649 | Future Task |  |  | D652 | Stacey Terry | Milestone | Milestone: System Test Segment 1 Execution Complete | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 648 | 1713 |  | Stacey Terry
4758 | 650 | Future Task |  |  | D652 | Stacey Terry |  | Create Completion of System Testing Segment 1 Summary Document | 3 hrs | 8 days | 2024-11-25 | 2024-12-06 | 648FS-3 days | 651SS+3 days,652SS+3 days,653 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4759 | 651 | Future Task |  |  | D652 | Stacey Terry |  | Conduct System Test Segment 1 Exit Criteria Review Meeting | 3 hrs | 5 days | 2024-12-02 | 2024-12-06 | 650SS+3 days | 653 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4760 | 652 | Future Task |  |  | D652 | Stacey Terry |  | Confirm requirements traceability for System Test Segment 1 | 3 hrs | 5 days | 2024-12-02 | 2024-12-06 | 650SS+3 days | 653 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4701 | 653 | Future Task |  |  | D652 | Stacey Terry | Submit | DEL D652 - Completion of System Test Segment I - Draft Submission | 0 hrs | 0 days | 2024-12-06 | 2024-12-06 | 650651652 | 654 |  | Stacey Terry,Joy Schneider
4702 | 654 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-12-09 | 2024-12-13 | 653 | 655 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4703 | 655 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Style Guide Review | 1 hr | 1 day | 2024-12-16 | 2024-12-16 | 654 | 656 |  | Dusti Kincl
4704 | 656 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Final Collaborative Review | 20 hrs | 5 days | 2024-12-17 | 2024-12-23 | 655 | 657 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4705 | 657 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Accenture QC | 4 hrs | 2 days | 2024-12-24 | 2024-12-26 | 656 | 658 |  | Joy Schneider
4706 | 658 | Future Task |  |  | D652 | Stacey Terry | Submit | DEL D652 - Completion of System Test Segment I - Submit | 0 hrs | 0 days | 2024-12-26 | 2024-12-26 | 657 | 659 |  | Joy Schneider
4707 | 659 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Department QC | 4 hrs | 1 day | 2024-12-27 | 2024-12-27 | 658 | 660 |  | Tommy Werner,Gabriela Gibson
4708 | 660 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Contract Manager Review | 8 hrs | 3 days | 2024-12-30 | 2025-01-02 | 659 | 661 |  | Sean Buchanan
4709 | 661 | Future Task |  |  | D652 | Stacey Terry | Accept | DEL D652 - Completion of System Test Segment I - Accept | 0 hrs | 0 days | 2025-01-02 | 2025-01-02 | 660 |  | 2024-12-01 | Sean Buchanan
4710 | 662 | Future Task | Yes |  | D655 | Manojkumar Gurjar |  | D655 - Completion of Mock Conversion II (System Test Environment) | 197 hrs | 65 days | 2024-10-18 | 2025-01-24
4711 | 663 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | DED D655 - Completion of Mock Conversion II (System Test Environment) - Create | 16 hrs | 10 days | 2024-10-18 | 2024-10-31 | 638FS-3 days | 664 |  | Manojkumar Gurjar,Kurt Meisner
4712 | 664 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DED D655 - Completion of Mock Conversion II (System Test Environment) - Submit | 0 hrs | 0 days | 2024-10-31 | 2024-10-31 | 663 | 665 |  | Manojkumar Gurjar,Joy Schneider
4713 | 665 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DED D655 - Completion of Mock Conversion II (System Test Environment) - Collaborative Review | 24 hrs | 10 days | 2024-11-01 | 2024-11-15 | 664 | 666 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4714 | 666 | Future Task |  |  | D655 | Manojkumar Gurjar | Approve | DED D655 - Completion of Mock Conversion II (System Test Environment) - Approve | 0 hrs | 0 days | 2024-11-15 | 2024-11-15 | 665 | 667 |  | Jimmy Cox
4761 | 667 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Confirm Mock 2 Conversion - System Test Environment Readiness | 20 hrs | 4 days | 2024-11-18 | 2024-11-21 | 666 | 668 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4762 | 668 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Create Mock 2 Conversion Checklist (System Test Environment) | 20 hrs | 5 days | 2024-11-22 | 2024-12-02 | 667 | 669 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4763 | 669 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Execute Mock 2 – Conversion (System Test Environment) | 20 hrs | 10 days | 2024-12-03 | 2024-12-16 | 668 | 670 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4764 | 670 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Validate Mock 2 – Conversion (System Test Environment) | 20 hrs | 4 days | 2024-12-17 | 2024-12-20 | 669 | 671 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4765 | 671 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Conduct Mock 2 - Conversion (System Test Environment) Test Exit Criteria Review Meeting | 20 hrs | 5 days | 2024-12-23 | 2024-12-30 | 670 | 672 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4715 | 672 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Draft Submission | 0 hrs | 0 days | 2024-12-30 | 2024-12-30 | 671 | 673 |  | Manojkumar Gurjar,Joy Schneider
4716 | 673 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-12-31 | 2025-01-07 | 672 | 674 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4717 | 674 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Style Guide Review | 1 hr | 1 day | 2025-01-08 | 2025-01-08 | 673 | 675 |  | Dusti Kincl
4718 | 675 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Final Collaborative Review | 20 hrs | 5 days | 2025-01-09 | 2025-01-15 | 674 | 676 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4719 | 676 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Accenture QC | 4 hrs | 2 days | 2025-01-16 | 2025-01-17 | 675 | 677 |  | Joy Schneider
4720 | 677 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Submit | 0 hrs | 0 days | 2025-01-17 | 2025-01-17 | 676 | 678 |  | Joy Schneider
4721 | 678 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Department QC | 4 hrs | 1 day | 2025-01-21 | 2025-01-21 | 677 | 679 |  | Tommy Werner,Gabriela Gibson
4722 | 679 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Contract Manager Review | 8 hrs | 3 days | 2025-01-22 | 2025-01-24 | 678 | 680 |  | Sean Buchanan
4723 | 680 | Future Task |  |  | D655 | Manojkumar Gurjar | Accept | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Accept | 0 hrs | 0 days | 2025-01-24 | 2025-01-24 | 679 | 703FS-40 days | 2025-01-01 | Sean Buchanan
4724 | 681 | Future Task | Yes |  | D656 | Stacey Terry |  | D656 - Completion of System Test Segment II | 154 hrs | 99 days | 2024-10-07 | 2025-02-28
4725 | 682 | Future Task |  |  | D656 | Stacey Terry | Create | DED D656 - Completion of System Test Segment II - Create | 16 hrs | 10 days | 2024-10-07 | 2024-10-18 | 1 | 683 |  | Stacey Terry,Mary Punty
4726 | 683 | Future Task |  |  | D656 | Stacey Terry | Submit | DED D656 - Completion of System Test Segment II - Submit | 0 hrs | 0 days | 2024-10-18 | 2024-10-18 | 682 | 684 |  | Stacey Terry,Joy Schneider
4727 | 684 | Future Task |  |  | D656 | Stacey Terry | Review | DED D656 - Completion of System Test Segment II - Collaborative Review | 20 hrs | 10 days | 2024-10-21 | 2024-11-01 | 683 | 685 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4728 | 685 | Future Task |  |  | D656 | Stacey Terry | Approve | DED D656 - Completion of System Test Segment II - Approve | 0 hrs | 0 days | 2024-11-01 | 2024-11-01 | 684 | 686 |  | Jimmy Cox
4766 | 686 | Future Task |  |  | D656 | Stacey Terry |  | Create Work Unit Tracker for System Test Segment 2 Execution | 6 hrs | 9 days | 2024-11-04 | 2024-11-15 | 685 | 687 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4767 | 687 | Future Task |  |  | D656 | Stacey Terry |  | Review, Update and confirm Work Unit Tracker for System Test Segment 2 Execution | 20 hrs | 8 days | 2024-11-18 | 2024-11-27 | 686 | 688 |  | Mary Punty,Stacey Terry,Deana Metcalf,Janice Jackson,Tiffany Porter,Brendan Jones
4768 | 688 | Future Task |  |  | D656 | Stacey Terry |  | Execute System Test Segment 2 - this is a WU | 20 hrs | 40 days | 2024-12-02 | 2025-01-29 | 687 | 689,690FS-5 days,585 |  | Yogesh Deshmukh,Stacey Terry,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Tim Elmer,Justin Randolph,Donnie Doctor,Ryan Raagas,Pooja Barde,Sandeep Gottam,Michael Carino,Jack Jenkins,Abdel El Bacha,Anthony Bastidas,Hari Balijachinna
4769 | 689 | Future Task |  |  | D656 | Stacey Terry | Milestone | Milestone: System Test Segment 2 Execution Complete | 0 hrs | 0 days | 2025-01-29 | 2025-01-29 | 688 |  |  | Stacey Terry
4770 | 690 | Future Task |  |  | D656 | Stacey Terry |  | Create Completion of System Testing Segment 2 Summary Document | 6 hrs | 10 days | 2025-01-23 | 2025-02-05 | 688FS-5 days | 691SS+5 days,692SS+5 days,693 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4771 | 691 | Future Task |  |  | D656 | Stacey Terry |  | Conduct System Test Segment 2 Exit Criteria Review Meeting | 3 hrs | 5 days | 2025-01-30 | 2025-02-05 | 690SS+5 days | 693 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4772 | 692 | Future Task |  |  | D656 | Stacey Terry |  | Confirm requirements traceability for System Test Segment 2 | 6 hrs | 5 days | 2025-01-30 | 2025-02-05 | 690SS+5 days | 693 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
4729 | 693 | Future Task |  |  | D656 | Stacey Terry | Submit | DEL D656 - Completion of System Test Segment II - Draft Submission | 0 hrs | 0 days | 2025-02-05 | 2025-02-05 | 690691692 | 694 |  | Stacey Terry,Joy Schneider
4730 | 694 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-02-06 | 2025-02-12 | 693 | 695 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4731 | 695 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Style Guide Review | 1 hr | 1 day | 2025-02-13 | 2025-02-13 | 694 | 696 |  | Dusti Kincl
4732 | 696 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Final Collaborative Review | 20 hrs | 5 days | 2025-02-14 | 2025-02-20 | 695 | 697 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4733 | 697 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Accenture QC | 4 hrs | 2 days | 2025-02-21 | 2025-02-24 | 696 | 698 |  | Joy Schneider
4734 | 698 | Future Task |  |  | D656 | Stacey Terry | Submit | DEL D656 - Completion of System Test Segment II - Submit | 0 hrs | 0 days | 2025-02-24 | 2025-02-24 | 697 | 699 |  | Joy Schneider
4735 | 699 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Department QC | 4 hrs | 1 day | 2025-02-25 | 2025-02-25 | 698 | 700 |  | Tommy Werner,Gabriela Gibson
4736 | 700 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Contract Manager Review | 8 hrs | 3 days | 2025-02-26 | 2025-02-28 | 699 | 701 |  | Sean Buchanan
4737 | 701 | Future Task |  |  | D656 | Stacey Terry | Accept | DEL D656 - Completion of System Test Segment II - Accept | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 700 |  | 2025-02-01 | Sean Buchanan
4738 | 702 | Future Task | Yes |  | D657 | Manojkumar Gurjar |  | D657 - Completion of Mock Conversion III (UAT) | 151 hrs | 77 days | 2024-11-25 | 2025-03-18
4739 | 703 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | DED D657 - Completion of Mock Conversion III (UAT) - Create | 16 hrs | 10 days | 2024-11-25 | 2024-12-10 | 680FS-40 days | 704 |  | Manojkumar Gurjar,Kurt Meisner
4740 | 704 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DED D657 - Completion of Mock Conversion III (UAT) - Submit | 0 hrs | 0 days | 2024-12-10 | 2024-12-10 | 703 | 705 |  | Manojkumar Gurjar,Joy Schneider
4741 | 705 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DED D657 - Completion of Mock Conversion III (UAT) - Collaborative Review | 24 hrs | 10 days | 2024-12-11 | 2024-12-24 | 704 | 706 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4742 | 706 | Future Task |  |  | D657 | Manojkumar Gurjar | Approve | DED D657 - Completion of Mock Conversion III (UAT) - Approve | 0 hrs | 0 days | 2024-12-24 | 2024-12-24 | 705 | 707 |  | Jimmy Cox
4773 | 707 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Confirm Mock 3 Conversion - UAT Environment Readiness | 2 hrs | 5 days | 2024-12-26 | 2025-01-02 | 706 | 708 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4774 | 708 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Create Mock 3 Conversion Checklist (UAT) | 2 hrs | 6 days | 2025-01-03 | 2025-01-10 | 707 | 709 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4775 | 709 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Execute Mock 3 – Conversion (UAT) | 10 hrs | 21 days | 2025-01-13 | 2025-02-11 | 708 | 710 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4776 | 710 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Validate Mock 3 – Conversion (UAT) | 20 hrs | 4 days | 2025-02-12 | 2025-02-17 | 709 | 711 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4777 | 711 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Conduct Mock 3 - Conversion UAT Exit Criteria Review Meeting | 20 hrs | 4 days | 2025-02-18 | 2025-02-21 | 710 | 712 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4743 | 712 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DEL D657 - Completion of Mock Conversion III (UAT) - Draft Submission | 0 hrs | 0 days | 2025-02-21 | 2025-02-21 | 711 | 713 |  | Manojkumar Gurjar,Joy Schneider
4744 | 713 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-02-24 | 2025-02-28 | 712 | 714 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4745 | 714 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Style Guide Review | 1 hr | 1 day | 2025-03-03 | 2025-03-03 | 713 | 715 |  | Dusti Kincl
4746 | 715 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Final Collaborative Review | 20 hrs | 5 days | 2025-03-04 | 2025-03-10 | 714 | 716 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4747 | 716 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Accenture QC | 4 hrs | 2 days | 2025-03-11 | 2025-03-12 | 715 | 717 |  | Joy Schneider
4748 | 717 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DEL D657 - Completion of Mock Conversion III (UAT) - Submit | 0 hrs | 0 days | 2025-03-12 | 2025-03-12 | 716 | 718 |  | Joy Schneider
4749 | 718 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Department QC | 4 hrs | 1 day | 2025-03-13 | 2025-03-13 | 717 | 719 |  | Tommy Werner,Gabriela Gibson
4750 | 719 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Contract Manager Review | 8 hrs | 3 days | 2025-03-14 | 2025-03-18 | 718 | 720 |  | Sean Buchanan
4751 | 720 | Future Task |  |  | D657 | Manojkumar Gurjar | Accept | DEL D657 - Completion of Mock Conversion III (UAT) - Accept | 0 hrs | 0 days | 2025-03-18 | 2025-03-18 | 719 | 762FS-22 days,1252 | 2025-02-01 | Sean Buchanan
5023 | 721 | Future Task |  |  | D660 | Stacey Terry |  | D660 - Payroll Parallel Testing Plan | 182 hrs | 72 days | 2025-01-03 | 2025-04-15
5024 | 722 | Future Task |  |  | D660 | Stacey Terry | Create | DED D660 - Payroll Parallel Testing Plan - Create | 16 hrs | 10 days | 2025-01-03 | 2025-01-16 | 195 | 723 |  | Stacey Terry,Mary Punty
5025 | 723 | Future Task |  |  | D660 | Stacey Terry | Submit | DED D660 - Payroll Parallel Testing Plan - Submit | 0 hrs | 0 days | 2025-01-16 | 2025-01-16 | 722 | 724,1099SS-4 days |  | Stacey Terry,Joy Schneider
5026 | 724 | Future Task |  |  | D660 | Stacey Terry | Review | DED D660 - Payroll Parallel Testing Plan - Collaborative Review | 24 hrs | 10 days | 2025-01-17 | 2025-01-31 | 723 | 725 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5027 | 725 | Future Task |  |  | D660 | Stacey Terry | Approve | DED D660 - Payroll Parallel Testing Plan - Approve | 0 hrs | 0 days | 2025-01-31 | 2025-01-31 | 724 | 726 |  | Jimmy Cox
5037 | 726 | Future Task |  |  | D660 | Stacey Terry |  | Define Payroll Parallel Test approach | 20 hrs | 20 days | 2025-02-03 | 2025-02-28 | 725 | 727FS-5 days |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5038 | 727 | Future Task |  |  | D660 | Stacey Terry |  | Define Payroll Parallel Test Cycles | 15 hrs | 5 days | 2025-02-24 | 2025-02-28 | 726FS-5 days | 728 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5039 | 728 | Future Task |  |  | D660 | Stacey Terry |  | Identify Test Resources for Payroll Parallel Test | 20 hrs | 5 days | 2025-03-03 | 2025-03-07 | 727 | 729 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5040 | 729 | Future Task |  |  | D660 | Stacey Terry |  | Define Payroll Parallel Test Tools and Test Management processes | 20 hrs | 5 days | 2025-03-10 | 2025-03-14 | 728 | 730FS-5 days |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5041 | 730 | Future Task |  |  | D660 | Stacey Terry |  | Create Initial List of Payroll Parallel Test Scenarios | 20 hrs | 10 days | 2025-03-10 | 2025-03-21 | 729FS-5 days | 731 |  | Mary Punty,Stacey Terry,Yogesh Deshmukh
5028 | 731 | Future Task |  |  | D660 | Stacey Terry | Submit | DEL D660 - Payroll Parallel Testing Plan - Draft Submission | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 730 | 732 |  | Stacey Terry,Joy Schneider
5029 | 732 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-03-24 | 2025-03-28 | 731 | 733 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5030 | 733 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Style Guide Review | 1 hr | 1 day | 2025-03-31 | 2025-03-31 | 732 | 734 |  | Dusti Kincl
5031 | 734 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Final Collaborative Review | 10 hrs | 5 days | 2025-04-01 | 2025-04-07 | 733 | 735 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5032 | 735 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Accenture QC | 4 hrs | 2 days | 2025-04-08 | 2025-04-09 | 734 | 736 |  | Joy Schneider
5033 | 736 | Future Task |  |  | D660 | Stacey Terry | Submit | DEL D660 - Payroll Parallel Testing Plan - Submit | 0 hrs | 0 days | 2025-04-09 | 2025-04-09 | 735 | 737 |  | Joy Schneider
5034 | 737 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Department QC | 4 hrs | 1 day | 2025-04-10 | 2025-04-10 | 736 | 738 |  | Tommy Werner,Gabriela Gibson
5035 | 738 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Contract Manager Review | 8 hrs | 3 days | 2025-04-11 | 2025-04-15 | 737 | 739 |  | Sean Buchanan
5036 | 739 | Future Task |  |  | D660 | Stacey Terry | Accept | DEL D660 - Payroll Parallel Testing Plan - Accept | 0 hrs | 0 days | 2025-04-15 | 2025-04-15 | 738 | 862FS-37 days | 2025-04-01 | Sean Buchanan
4778 | 740 | Future Task | Yes |  | D661 | Stacey Terry |  | D661 - Completion of System Test DW/BI | 207 hrs | 120 days | 2024-11-04 | 2025-04-28
4779 | 741 | Future Task |  |  | D661 | Stacey Terry | Create | DED D661 - Completion of System Test DW/BI - Create | 16 hrs | 10 days | 2024-11-04 | 2024-11-18 | 1 | 742 |  | Stacey Terry,Mary Punty | This should be earlier than immediately before work begins. | Angie
4780 | 742 | Future Task |  |  | D661 | Stacey Terry | Submit | DED D661 - Completion of System Test DW/BI - Submit | 0 hrs | 0 days | 2024-11-18 | 2024-11-18 | 741 | 743 |  | Stacey Terry,Joy Schneider
4781 | 743 | Future Task |  |  | D661 | Stacey Terry | Review | DED D661 - Completion of System Test DW/BI - Collaborative Review | 24 hrs | 10 days | 2024-11-19 | 2024-12-04 | 742 | 744 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4782 | 744 | Future Task |  |  | D661 | Stacey Terry | Approve | DED D661 - Completion of System Test DW/BI - Approve | 0 hrs | 0 days | 2024-12-04 | 2024-12-04 | 743 | 745 |  | Jimmy Cox
4820 | 745 | Future Task |  |  | D661 | Stacey Terry |  | Create Work Unit Tracker for System Test DW/BI Execution | 36 hrs | 9 days | 2024-12-05 | 2024-12-17 | 744 | 746 |  | Manojkumar Gurjar,Mary Punty
4821 | 746 | Future Task |  |  | D661 | Stacey Terry |  | Review, Update and confirm Work Unit Tracker for System Test DW/BI Execution | 20 hrs | 10 days | 2024-12-18 | 2025-01-02 | 745 | 747 |  | Manojkumar Gurjar,Mary Punty
4822 | 747 | Future Task |  |  | D661 | Stacey Terry |  | Execute System Test DW/BI - This is a WU | 20 hrs | 60 days | 2025-01-03 | 2025-03-28 | 746 | 748,749FS-6 days,585 |  | Manojkumar Gurjar,Mary Punty
4823 | 748 | Future Task |  |  | D661 | Stacey Terry | Milestone | Milestone: System Test DW/BI Execution Complete | 0 hrs | 0 days | 2025-03-28 | 2025-03-28 | 747 |  |  | Stacey Terry
4824 | 749 | Future Task |  |  | D661 | Stacey Terry |  | Create Completion of System Testing DW/BI Summary Document | 4 hrs | 10 days | 2025-03-21 | 2025-04-03 | 747FS-6 days | 750SS+5 days,752 |  | Manojkumar Gurjar,Mary Punty
4825 | 750 | Future Task |  |  | D661 | Stacey Terry |  | Conduct System Test DW/BI Exit Criteria Review Meeting | 10 hrs | 5 days | 2025-03-28 | 2025-04-03 | 749SS+5 days | 751SS,752 |  | Manojkumar Gurjar,Mary Punty
4826 | 751 | Future Task |  |  | D661 | Stacey Terry |  | Confirm requirements traceability for System Test DW/BI | 20 hrs | 5 days | 2025-03-28 | 2025-04-03 | 750SS | 752 |  | Manojkumar Gurjar,Mary Punty
4783 | 752 | Future Task |  |  | D661 | Stacey Terry | Submit | DEL D661 - Completion of System Test DW/BI - Draft Submission | 0 hrs | 0 days | 2025-04-03 | 2025-04-03 | 749750751 | 753 |  | Stacey Terry,Joy Schneider
4784 | 753 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-04-04 | 2025-04-10 | 752 | 754 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4785 | 754 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Style Guide Review | 1 hr | 1 day | 2025-04-11 | 2025-04-11 | 753 | 755 |  | Dusti Kincl
4786 | 755 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Final Collaborative Review | 20 hrs | 5 days | 2025-04-14 | 2025-04-18 | 754 | 756 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4787 | 756 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Accenture QC | 4 hrs | 2 days | 2025-04-21 | 2025-04-22 | 755 | 757 |  | Joy Schneider
4788 | 757 | Future Task |  |  | D661 | Stacey Terry | Submit | DEL D661 - Completion of System Test DW/BI - Submit | 0 hrs | 0 days | 2025-04-22 | 2025-04-22 | 756 | 758 |  | Joy Schneider
4789 | 758 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Department QC | 4 hrs | 1 day | 2025-04-23 | 2025-04-23 | 757 | 759 |  | Tommy Werner,Gabriela Gibson
4790 | 759 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Contract Manager Review | 8 hrs | 3 days | 2025-04-24 | 2025-04-28 | 758 | 760 |  | Sean Buchanan
4791 | 760 | Future Task |  |  | D661 | Stacey Terry | Accept | DEL D661 - Completion of System Test DW/BI - Accept | 0 hrs | 0 days | 2025-04-28 | 2025-04-28 | 759 |  | 2025-05-01 | Sean Buchanan
4792 | 761 | Future Task | Yes |  | D662 | Manojkumar Gurjar |  | D662 - Completion of Dress Rehearsal (Mock Conversion IV) | 197 hrs | 72 days | 2025-02-17 | 2025-05-28
4793 | 762 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Create | 16 hrs | 10 days | 2025-02-17 | 2025-02-28 | 720FS-22 days | 763 |  | Manojkumar Gurjar,Kurt Meisner
4794 | 763 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Submit | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 762 | 764 |  | Manojkumar Gurjar,Joy Schneider
4795 | 764 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Collaborative Review | 24 hrs | 10 days | 2025-03-03 | 2025-03-14 | 763 | 765 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4796 | 765 | Future Task |  |  | D662 | Manojkumar Gurjar | Approve | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Approve | 0 hrs | 0 days | 2025-03-14 | 2025-03-14 | 764 | 766 |  | Jimmy Cox
4827 | 766 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Confirm Mock 4 Conversion - (Dress Rehearsal) Environment Readiness | 20 hrs | 5 days | 2025-03-17 | 2025-03-21 | 765 | 767 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4828 | 767 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Create Mock 4 Conversion Checklist (Dress Rehearsal) | 20 hrs | 5 days | 2025-03-24 | 2025-03-28 | 766 | 768 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4829 | 768 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Execute Mock 4 – Conversion (Dress Rehearsal) | 20 hrs | 10 days | 2025-03-31 | 2025-04-11 | 767 | 769 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4830 | 769 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Validate Mock 4 – Conversion (Dress Rehearsal) | 20 hrs | 10 days | 2025-04-14 | 2025-04-25 | 768 | 770 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4831 | 770 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Conduct Mock 4 - Conversion (Dress Rehearsal) Exit Criteria Review Meeting | 20 hrs | 5 days | 2025-04-28 | 2025-05-02 | 769 | 771 |  | Manojkumar Gurjar,Kurt Meisner,Jeevan Mahajan,Janmejay Khare
4797 | 771 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Draft Submission | 0 hrs | 0 days | 2025-05-02 | 2025-05-02 | 770 | 772 |  | Manojkumar Gurjar,Joy Schneider
4798 | 772 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-05-05 | 2025-05-09 | 771 | 773 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4799 | 773 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Style Guide Review | 1 hr | 1 day | 2025-05-12 | 2025-05-12 | 772 | 774 |  | Dusti Kincl
4800 | 774 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Final Collaborative Review | 20 hrs | 5 days | 2025-05-13 | 2025-05-19 | 773 | 775 |  | Manojkumar Gurjar,Kurt Meisner,Matthew Breeding,Jimmy Cox,Angie Robertson
4801 | 775 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Accenture QC | 4 hrs | 2 days | 2025-05-20 | 2025-05-21 | 774 | 776 |  | Joy Schneider
4802 | 776 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Submit | 0 hrs | 0 days | 2025-05-21 | 2025-05-21 | 775 | 777 |  | Joy Schneider
4803 | 777 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Department QC | 4 hrs | 1 day | 2025-05-22 | 2025-05-22 | 776 | 778 |  | Tommy Werner,Gabriela Gibson
4804 | 778 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Contract Manager Review | 8 hrs | 3 days | 2025-05-23 | 2025-05-28 | 777 | 779 |  | Sean Buchanan
4805 | 779 | Future Task |  |  | D662 | Manojkumar Gurjar | Accept | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Accept | 0 hrs | 0 days | 2025-05-28 | 2025-05-28 | 778 | 1252 | 2025-05-01 | Sean Buchanan
4806 | 780 | Future Task | Yes |  | D663 | Manojkumar Gurjar |  | D663 - Completion of Interface Testing Segment I | 236.58 hrs | 204 days | 2024-09-09 | 2025-06-30
4807 | 781 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | DED D663 - Completion of Interface Testing Segment I - Create | 24 hrs | 10 days | 2024-09-09 | 2024-09-20 | 1 | 782 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4808 | 782 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DED D663 - Completion of Interface Testing Segment I - Submit | 0 hrs | 0 days | 2024-09-20 | 2024-09-20 | 781 | 783 |  | Manojkumar Gurjar,Joy Schneider
4809 | 783 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DED D663 - Completion of Interface Testing Segment I - Collaborative Review | 28 hrs | 10 days | 2024-09-23 | 2024-10-04 | 782 | 784 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4810 | 784 | Future Task |  |  | D663 | Manojkumar Gurjar | Approve | DED D663 - Completion of Interface Testing Segment I - Approve | 0 hrs | 0 days | 2024-10-04 | 2024-10-04 | 783 | 785 |  | Jimmy Cox
4832 | 785 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Create Interface Testing Segment 1 Execution Work Unit Tracker | 30 hrs | 10 days | 2024-10-07 | 2024-10-18 | 784 | 786,790SS |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4833 | 786 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Review/Confirm Interface Testing Segment 1 Execution Work Unit Tracker | 15 hrs | 5 days | 2024-10-21 | 2024-10-25 | 785 | 787 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4834 | 787 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Conduct Interface Testing Segment 1 Readiness Review Meeting | 15 hrs | 5 days | 2024-10-28 | 2024-11-01 | 786 | 788 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4835 | 788 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Conduct Interface Test Kickoff Meeting with Integration Partners | 3 hrs | 9 days | 2024-11-04 | 2024-11-15 | 787 | 789 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4836 | 789 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Confirm Interface Test Environment Readiness | 15 hrs | 5 days | 2024-11-18 | 2024-11-22 | 788563 | 791 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4837 | 790 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Establish Interface Connectivity Segment 1 | 20 hrs | 20 days | 2024-10-07 | 2024-11-01 | 785SS | 791FS+17 days |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4838 | 791 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Execute Interface Testing Segment 1 - This is WU | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 790FS+17 days,789 | 792793 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4839 | 792 | Future Task |  |  | D663 | Manojkumar Gurjar | Milestone | Milestone: Interface Testing Segment 1 Complete | 0 hrs | 0 days | 2025-04-30 | 2025-04-30 | 791 | 795 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4840 | 793 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Conduct Test Exit Criteria Review Meeting | 15 hrs | 5 days | 2025-05-01 | 2025-05-07 | 791 | 794 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4841 | 794 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Confirm requirements traceability for Interface Testing Segment 1 | 15 hrs | 10 days | 2025-05-08 | 2025-05-21 | 793 | 795 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4842 | 795 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Create Completion of Interface Testing Segment 1 Summary Document | 1.58 hrs | 10 days | 2025-05-22 | 2025-06-05 | 794792 | 796 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4811 | 796 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DEL D663 - Completion of Interface Testing Segment I - Draft Submission | 0 hrs | 0 days | 2025-06-05 | 2025-06-05 | 795 | 797 |  | Manojkumar Gurjar,Joy Schneider
4812 | 797 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Pre-Submission Collaborative Review | 6 hrs | 5 days | 2025-06-06 | 2025-06-12 | 796 | 798 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4813 | 798 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Style Guide Review | 1 hr | 1 day | 2025-06-13 | 2025-06-13 | 797 | 799 |  | Dusti Kincl
4814 | 799 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Final Collaborative Review | 12 hrs | 5 days | 2025-06-16 | 2025-06-20 | 798 | 800 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4815 | 800 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Accenture QC | 4 hrs | 2 days | 2025-06-23 | 2025-06-24 | 799 | 801 |  | Joy Schneider
4816 | 801 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DEL D663 - Completion of Interface Testing Segment I - Submit | 0 hrs | 0 days | 2025-06-24 | 2025-06-24 | 800 | 802 |  | Joy Schneider
4817 | 802 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Department QC | 4 hrs | 1 day | 2025-06-25 | 2025-06-25 | 801 | 803 |  | Tommy Werner,Gabriela Gibson
4818 | 803 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Contract Manager Review | 8 hrs | 3 days | 2025-06-26 | 2025-06-30 | 802 | 804 |  | Sean Buchanan
4819 | 804 | Future Task |  |  | D663 | Manojkumar Gurjar | Accept | DEL D663 - Completion of Interface Testing Segment I - Accept | 0 hrs | 0 days | 2025-06-30 | 2025-06-30 | 803 |  | 2025-06-01 | Sean Buchanan
5042 | 805 | Future Task | Yes |  | D666 | Stacey Terry |  | D666 - Support of UAT Segment I | 111 hrs | 95 days | 2025-02-17 | 2025-06-30
5043 | 806 | Future Task |  |  | D666 | Stacey Terry | Create | DED D666 - Support of UAT Segment I - Create | 16 hrs | 10 days | 2025-02-17 | 2025-02-28 | 1 | 807 |  | Stacey Terry,Mary Punty
5044 | 807 | Future Task |  |  | D666 | Stacey Terry | Submit | DED D666 - Support of UAT Segment I - Submit | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 806 | 808 |  | Stacey Terry,Joy Schneider
5045 | 808 | Future Task |  |  | D666 | Stacey Terry | Review | DED D666 - Support of UAT Segment I - Collaborative Review | 24 hrs | 10 days | 2025-03-03 | 2025-03-14 | 807 | 809 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5046 | 809 | Future Task |  |  | D666 | Stacey Terry | Approve | DED D666 - Support of UAT Segment I - Approve | 0 hrs | 0 days | 2025-03-14 | 2025-03-14 | 808 | 810 |  | Jimmy Cox
5056 | 810 | Future Task |  |  | D666 | Stacey Terry |  | Identify UAT support resources for UAT Segment 1 | 20 hrs | 11 days | 2025-03-17 | 2025-03-31 | 809 | 811 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5057 | 811 | Future Task |  |  | D666 | Stacey Terry |  | Participate in UAT sessions for UAT Segment 1 | 6 hrs | 43 days | 2025-04-01 | 2025-05-30 | 810 | 812SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp
5058 | 812 | Future Task |  |  | D666 | Stacey Terry |  | Support resolution of UAT issues for UAT Segment 1 | 7 hrs | 42 days | 2025-04-01 | 2025-05-29 | 811SS | 813FS-4 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
5059 | 813 | Future Task |  |  | D666 | Stacey Terry |  | Confirm requirements traceability for UAT Segment 1 | 3 hrs | 4 days | 2025-05-23 | 2025-05-29 | 812FS-4 days | 814SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5060 | 814 | Future Task |  |  | D666 | Stacey Terry |  | Create UAT Segment 1 Summary Document | 3 hrs | 9 days | 2025-05-23 | 2025-06-05 | 813SS | 815 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5047 | 815 | Future Task |  |  | D666 | Stacey Terry | Submit | DEL D666 - Support of UAT Segment I - Draft Submission | 0 hrs | 0 days | 2025-06-05 | 2025-06-05 | 814 | 816 |  | Stacey Terry,Joy Schneider
5048 | 816 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Pre-Submission Collaborative Review | 5 hrs | 5 days | 2025-06-06 | 2025-06-12 | 815 | 817 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5049 | 817 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Style Guide Review | 1 hr | 1 day | 2025-06-13 | 2025-06-13 | 816 | 818 |  | Dusti Kincl
5050 | 818 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Final Collaborative Review | 10 hrs | 5 days | 2025-06-16 | 2025-06-20 | 817 | 819 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5051 | 819 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Accenture QC | 4 hrs | 2 days | 2025-06-23 | 2025-06-24 | 818 | 820 |  | Joy Schneider
5052 | 820 | Future Task |  |  | D666 | Stacey Terry | Submit | DEL D666 - Support of UAT Segment I - Submit | 0 hrs | 0 days | 2025-06-24 | 2025-06-24 | 819 | 821 |  | Joy Schneider
5053 | 821 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Department QC | 4 hrs | 1 day | 2025-06-25 | 2025-06-25 | 820 | 822 |  | Tommy Werner,Gabriela Gibson
5054 | 822 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Contract Manager Review | 8 hrs | 3 days | 2025-06-26 | 2025-06-30 | 821 | 823 |  | Sean Buchanan
5055 | 823 | Future Task |  |  | D666 | Stacey Terry | Accept | DEL D666 - Support of UAT Segment I - Accept | 0 hrs | 0 days | 2025-06-30 | 2025-06-30 | 822 |  | 2025-06-01 | Sean Buchanan
5520 | 824 | Future Task | Yes |  | D667 | Stacey Terry |  | D667 - Completion of Mock Go-Lives (Dry Run #1) | 108 hrs | 62 days | 2025-05-02 | 2025-07-30
5521 | 825 | Future Task |  |  | D667 | Stacey Terry | Create | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Create | 6 hrs | 10 days | 2025-05-02 | 2025-05-15 | 1 | 826 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5522 | 826 | Future Task |  |  | D667 | Stacey Terry | Submit | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Submit | 0 hrs | 0 days | 2025-05-15 | 2025-05-15 | 825 | 827 |  | Stacey Terry,Joy Schneider
5523 | 827 | Future Task |  |  | D667 | Stacey Terry | Review | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Collaborative Review | 8 hrs | 10 days | 2025-05-16 | 2025-05-30 | 826 | 828 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5524 | 828 | Future Task |  |  | D667 | Stacey Terry | Approve | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Approve | 0 hrs | 0 days | 2025-05-30 | 2025-05-30 | 827 | 829 |  | Jimmy Cox
6697 | 829 | Future Task |  |  | D667 | Stacey Terry |  | Confirm Mock Go-Live Dry Run #1 Execution Readiness | 3 hrs | 5 days | 2025-06-02 | 2025-06-06 | 828571 | 830 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6698 | 830 | Future Task |  |  | D667 | Stacey Terry |  | Execute Mock Go-Live Dry Run #1 | 6 hrs | 10 days | 2025-06-09 | 2025-06-20 | 829 | 831 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6699 | 831 | Future Task |  |  | D667 | Stacey Terry |  | Document Mock Go-Live Dry Run Results #1 | 6 hrs | 5 days | 2025-06-23 | 2025-06-27 | 830 | 832 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
6700 | 832 | Future Task |  |  | D667 | Stacey Terry |  | Create Mock Go-Live Dry Run #1 Summary Document | 6 hrs | 5 days | 2025-06-30 | 2025-07-07 | 831 | 833 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5525 | 833 | Future Task |  |  | D667 | Stacey Terry | Submit | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Draft Submission | 0 hrs | 0 days | 2025-07-07 | 2025-07-07 | 832 | 834 |  | Stacey Terry,Joy Schneider
5526 | 834 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Pre-Submission Collaborative Review | 28 hrs | 5 days | 2025-07-08 | 2025-07-14 | 833 | 835 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5527 | 835 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Style Guide Review | 1 hr | 1 day | 2025-07-15 | 2025-07-15 | 834 | 836 |  | Dusti Kincl
5528 | 836 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Final Collaborative Review | 28 hrs | 5 days | 2025-07-16 | 2025-07-22 | 835 | 837 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5529 | 837 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Accenture QC | 4 hrs | 2 days | 2025-07-23 | 2025-07-24 | 836 | 838 |  | Joy Schneider
5530 | 838 | Future Task |  |  | D667 | Stacey Terry | Submit | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Submit | 0 hrs | 0 days | 2025-07-24 | 2025-07-24 | 837 | 839 |  | Joy Schneider
5531 | 839 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Department QC | 4 hrs | 1 day | 2025-07-25 | 2025-07-25 | 838 | 840 |  | Tommy Werner,Gabriela Gibson
5532 | 840 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Contract Manager Review | 8 hrs | 3 days | 2025-07-28 | 2025-07-30 | 839 | 841 |  | Sean Buchanan
5533 | 841 | Future Task |  |  | D667 | Stacey Terry | Accept | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Accept | 0 hrs | 0 days | 2025-07-30 | 2025-07-30 | 840 | 1252 | 2025-07-01 | Sean Buchanan
5061 | 842 | Future Task | Yes |  | D669 | Stacey Terry |  | D669 - Support of UAT Segment II | 132 hrs | 72 days | 2025-05-19 | 2025-08-28
5062 | 843 | Future Task |  |  | D669 | Stacey Terry | Create | DED D669 - Support of UAT Segment II - Create | 2 hrs | 10 days | 2025-05-19 | 2025-06-02 | 1 | 844 |  | Stacey Terry,Mary Punty
5063 | 844 | Future Task |  |  | D669 | Stacey Terry | Submit | DED D669 - Support of UAT Segment II - Submit | 0 hrs | 0 days | 2025-06-02 | 2025-06-02 | 843 | 845 |  | Stacey Terry,Joy Schneider
5064 | 845 | Future Task |  |  | D669 | Stacey Terry | Review | DED D669 - Support of UAT Segment II - Collaborative Review | 12 hrs | 10 days | 2025-06-03 | 2025-06-16 | 844 | 846 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5065 | 846 | Future Task |  |  | D669 | Stacey Terry | Approve | DED D669 - Support of UAT Segment II - Approve | 0 hrs | 0 days | 2025-06-16 | 2025-06-16 | 845 | 847FS+4 days |  | Jimmy Cox
5075 | 847 | Future Task |  |  | D669 | Stacey Terry |  | Identify UAT support resources for UAT Segment 2 | 6 hrs | 5 days | 2025-06-23 | 2025-06-27 | 846FS+4 days | 848 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
5076 | 848 | Future Task |  |  | D669 | Stacey Terry |  | Participate in UAT sessions for UAT Segment 2 | 6 hrs | 23 days | 2025-06-30 | 2025-07-31 | 847 | 849SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp | This should start when Segment 1 support ends, not after the segment 1 deliverable is accepted | AR
5077 | 849 | Future Task |  |  | D669 | Stacey Terry |  | Support resolution of UAT issues for UAT Segment 2 | 7 hrs | 23 days | 2025-06-30 | 2025-07-31 | 848SS | 850FS-4 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
5078 | 850 | Future Task |  |  | D669 | Stacey Terry |  | Confirm requirements traceability for UAT Segment 2 | 21 hrs | 7 days | 2025-07-28 | 2025-08-05 | 849FS-4 days | 851SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5079 | 851 | Future Task |  |  | D669 | Stacey Terry |  | Create UAT Segment 2 Summary Document | 21 hrs | 7 days | 2025-07-28 | 2025-08-05 | 850SS | 852 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5066 | 852 | Future Task |  |  | D669 | Stacey Terry | Submit | DEL D669 - Support of UAT Segment II - Draft Submission | 0 hrs | 0 days | 2025-08-05 | 2025-08-05 | 851 | 853 |  | Stacey Terry,Joy Schneider
5067 | 853 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-08-06 | 2025-08-12 | 852 | 854 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5068 | 854 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Style Guide Review | 1 hr | 1 day | 2025-08-13 | 2025-08-13 | 853 | 855 |  | Dusti Kincl
5069 | 855 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Final Collaborative Review | 20 hrs | 5 days | 2025-08-14 | 2025-08-20 | 854 | 856 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5070 | 856 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Accenture QC | 4 hrs | 2 days | 2025-08-21 | 2025-08-22 | 855 | 857 |  | Joy Schneider
5071 | 857 | Future Task |  |  | D669 | Stacey Terry | Submit | DEL D669 - Support of UAT Segment II - Submit | 0 hrs | 0 days | 2025-08-22 | 2025-08-22 | 856 | 858 |  | Joy Schneider
5072 | 858 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Department QC | 4 hrs | 1 day | 2025-08-25 | 2025-08-25 | 857 | 859 |  | Tommy Werner,Gabriela Gibson
5073 | 859 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Contract Manager Review | 8 hrs | 3 days | 2025-08-26 | 2025-08-28 | 858 | 860 |  | Sean Buchanan
5074 | 860 | Future Task |  |  | D669 | Stacey Terry | Accept | DEL D669 - Support of UAT Segment II - Accept | 0 hrs | 0 days | 2025-08-28 | 2025-08-28 | 859 |  | 2025-08-01 | Sean Buchanan
4843 | 861 | Future Task | Yes |  | D670 | Stacey Terry |  | D670 - Completion of Payroll Parallel Testing | 254 hrs | 133 days | 2025-02-24 | 2025-08-29
4844 | 862 | Future Task |  |  | D670 | Stacey Terry | Create | DED D670 - Completion of Payroll Parallel Testing - Create | 16 hrs | 10 days | 2025-02-24 | 2025-03-07 | 739FS-37 days | 863 |  | Stacey Terry,Mary Punty
4845 | 863 | Future Task |  |  | D670 | Stacey Terry | Submit | DED D670 - Completion of Payroll Parallel Testing - Submit | 0 hrs | 0 days | 2025-03-07 | 2025-03-07 | 862 | 864 |  | Stacey Terry,Joy Schneider
4846 | 864 | Future Task |  |  | D670 | Stacey Terry | Review | DED D670 - Completion of Payroll Parallel Testing - Collaborative Review | 24 hrs | 10 days | 2025-03-10 | 2025-03-21 | 863 | 865 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4847 | 865 | Future Task |  |  | D670 | Stacey Terry | Approve | DED D670 - Completion of Payroll Parallel Testing - Approve | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 864 | 866 |  | Jimmy Cox
4955 | 866 | Future Task |  |  | D670 | Stacey Terry |  | Create Work Unit Tracker for Payroll Parallel Test Execution | 40 hrs | 10 days | 2025-03-24 | 2025-04-04 | 865 | 867 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty
4956 | 867 | Future Task |  |  | D670 | Stacey Terry |  | Review, Update and confirm Work Unit Tracker for Payroll Parallel Test Execution | 20 hrs | 10 days | 2025-04-07 | 2025-04-18 | 866 | 868 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Jennifer Peddicord
4957 | 868 | Future Task |  |  | D670 | Stacey Terry |  | Confirm Payroll Parallel Test Environment Readiness | 20 hrs | 5 days | 2025-04-21 | 2025-04-25 | 867 | 869 |  | Manojkumar Gurjar,Jarad Hermann
4958 | 869 | Future Task |  |  | D670 | Stacey Terry |  | Conduct Parallel Payroll Test Kick Off Meeting | 12 hrs | 5 days | 2025-04-28 | 2025-05-02 | 868 | 870 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Jennifer Peddicord
4959 | 870 | Future Task |  |  | D670 | Stacey Terry |  | Execute Parallel Payroll Testing - this is a WU | 5 hrs | 60 days | 2025-05-05 | 2025-07-29 | 869 | 871,872FS-4 days |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
4960 | 871 | Future Task |  |  | D670 | Stacey Terry | Milestone | Milestone: Payroll Parallel Test Execution Complete | 0 hrs | 0 days | 2025-07-29 | 2025-07-29 | 870 | 875 |  | Stacey Terry
4961 | 872 | Future Task |  |  | D670 | Stacey Terry |  | Conduct Payroll Parallel Test Exit Criteria Review Meeting | 10 hrs | 10 days | 2025-07-24 | 2025-08-06 | 870FS-4 days | 873SS,874SS,875 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
4962 | 873 | Future Task |  |  | D670 | Stacey Terry |  | Confirm requirements traceability for Payroll Parallel test | 20 hrs | 10 days | 2025-07-24 | 2025-08-06 | 872SS | 875 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Mary Punty
4963 | 874 | Future Task |  |  | D670 | Stacey Terry |  | Create Completion of Payroll Parallel Test Summary Document | 30 hrs | 10 days | 2025-07-24 | 2025-08-06 | 872SS | 875 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4848 | 875 | Future Task |  |  | D670 | Stacey Terry | Submit | DEL D670 - Completion of Payroll Parallel Testing - Draft Submission | 0 hrs | 0 days | 2025-08-06 | 2025-08-06 | 871872874873 | 876 |  | Stacey Terry,Joy Schneider
4849 | 876 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-08-07 | 2025-08-13 | 875 | 877 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4850 | 877 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Style Guide Review | 1 hr | 1 day | 2025-08-14 | 2025-08-14 | 876 | 878 |  | Dusti Kincl
4851 | 878 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Final Collaborative Review | 20 hrs | 5 days | 2025-08-15 | 2025-08-21 | 877 | 879 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4852 | 879 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Accenture QC | 4 hrs | 2 days | 2025-08-22 | 2025-08-25 | 878 | 880 |  | Joy Schneider
4853 | 880 | Future Task |  |  | D670 | Stacey Terry | Submit | DEL D670 - Completion of Payroll Parallel Testing - Submit | 0 hrs | 0 days | 2025-08-25 | 2025-08-25 | 879 | 881 |  | Joy Schneider
4854 | 881 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Department QC | 4 hrs | 1 day | 2025-08-26 | 2025-08-26 | 880 | 882 |  | Tommy Werner,Gabriela Gibson
4855 | 882 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Contract Manager Review | 8 hrs | 3 days | 2025-08-27 | 2025-08-29 | 881 | 883 |  | Sean Buchanan
4856 | 883 | Future Task |  |  | D670 | Stacey Terry | Accept | DEL D670 - Completion of Payroll Parallel Testing - Accept | 0 hrs | 0 days | 2025-08-29 | 2025-08-29 | 882 |  | 2025-08-01 | Sean Buchanan
4857 | 884 | Future Task | Yes |  | D671 | Manojkumar Gurjar |  | D671 - Completion of Interface Testing Segment II | 291 hrs | 160 days | 2025-03-03 | 2025-10-15
4858 | 885 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | DED D671 - Completion of Interface Testing Segment II - Create | 6 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1 | 886 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
4859 | 886 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DED D671 - Completion of Interface Testing Segment II - Submit | 0 hrs | 0 days | 2025-03-14 | 2025-03-14 | 885 | 887 |  | Manojkumar Gurjar,Joy Schneider
4860 | 887 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DED D671 - Completion of Interface Testing Segment II - Collaborative Review | 8 hrs | 10 days | 2025-03-17 | 2025-03-28 | 886 | 888 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4861 | 888 | Future Task |  |  | D671 | Manojkumar Gurjar | Approve | DED D671 - Completion of Interface Testing Segment II - Approve | 0 hrs | 0 days | 2025-03-28 | 2025-03-28 | 887 | 889 |  | Jimmy Cox
4964 | 889 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Create Interface Testing Segment 2 Execution Work Unit Tracker | 6 hrs | 4 days | 2025-03-31 | 2025-04-03 | 888 | 890 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4965 | 890 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Review/Confirm Interface Testing Segment 2 Execution Work Unit Tracker | 6 hrs | 4 days | 2025-04-04 | 2025-04-09 | 889 | 891 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4966 | 891 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Conduct Interface Testing Segment 2 Readiness Review Meeting | 15 hrs | 5 days | 2025-04-10 | 2025-04-16 | 890 | 892 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4967 | 892 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Conduct Interface Test Kickoff Meeting with Integration Partners | 30 hrs | 5 days | 2025-04-17 | 2025-04-23 | 891 | 893 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4968 | 893 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Confirm Interface Test Environment Readiness | 15 hrs | 5 days | 2025-04-24 | 2025-04-30 | 892 | 894 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4969 | 894 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Establish Interface Connectivity Segment 2 | 20 hrs | 7 days | 2025-05-01 | 2025-05-09 | 893 | 895 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4970 | 895 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Execute Interface Testing Segment 2 - This is WU | 10 hrs | 78 days | 2025-05-12 | 2025-08-29 | 894 | 896 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4971 | 896 | Future Task |  |  | D671 | Manojkumar Gurjar | Milestone | Milestone: Interface Testing Segment 2 Complete | 0 hrs | 0 days | 2025-08-29 | 2025-08-29 | 895 | 897 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4972 | 897 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Conduct Test Exit Criteria Review Meeting | 30 hrs | 5 days | 2025-09-02 | 2025-09-08 | 896 | 898 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4973 | 898 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Confirm requirements traceability for Interface Testing Segment 2 | 40 hrs | 5 days | 2025-09-09 | 2025-09-15 | 897 | 899 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4974 | 899 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Create Completion of Interface Testing Segment 2 deliverable (D671) | 40 hrs | 5 days | 2025-09-16 | 2025-09-22 | 898 | 900 |  | Kurt Meisner,Manojkumar Gurjar,Mary Punty
4862 | 900 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DEL D671 - Completion of Interface Testing Segment II - Draft Submission | 0 hrs | 0 days | 2025-09-22 | 2025-09-22 | 899 | 901 |  | Manojkumar Gurjar,Joy Schneider
4863 | 901 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Pre-Submission Collaborative Review | 24 hrs | 5 days | 2025-09-23 | 2025-09-29 | 900 | 902 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4864 | 902 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Style Guide Review | 1 hr | 1 day | 2025-09-30 | 2025-09-30 | 901 | 903 |  | Dusti Kincl
4865 | 903 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Final Collaborative Review | 24 hrs | 5 days | 2025-10-01 | 2025-10-07 | 902 | 904 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
4866 | 904 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Accenture QC | 4 hrs | 2 days | 2025-10-08 | 2025-10-09 | 903 | 905 |  | Joy Schneider
4867 | 905 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DEL D671 - Completion of Interface Testing Segment II - Submit | 0 hrs | 0 days | 2025-10-09 | 2025-10-09 | 904 | 906 |  | Joy Schneider
4868 | 906 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Department QC | 4 hrs | 1 day | 2025-10-10 | 2025-10-10 | 905 | 907 |  | Tommy Werner,Gabriela Gibson
4869 | 907 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Contract Manager Review | 8 hrs | 3 days | 2025-10-13 | 2025-10-15 | 906 | 908 |  | Sean Buchanan
4870 | 908 | Future Task |  |  | D671 | Manojkumar Gurjar | Accept | DEL D671 - Completion of Interface Testing Segment II - Accept | 0 hrs | 0 days | 2025-10-15 | 2025-10-15 | 907 |  | 2025-10-01 | Sean Buchanan
4871 | 909 | Future Task | Yes |  | D672 | Stacey Terry |  | D672 - Support of UAT Segment III | 122 hrs | 67 days | 2025-08-22 | 2025-11-26
4872 | 910 | Future Task |  |  | D672 | Stacey Terry | Create | DED D672 - Support of UAT Segment III - Create | 16 hrs | 10 days | 2025-08-22 | 2025-09-05 | 1 | 911 |  | Stacey Terry,Mary Punty
4873 | 911 | Future Task |  |  | D672 | Stacey Terry | Submit | DED D672 - Support of UAT Segment III - Submit | 0 hrs | 0 days | 2025-09-05 | 2025-09-05 | 910 | 912 |  | Stacey Terry,Joy Schneider
4874 | 912 | Future Task |  |  | D672 | Stacey Terry | Review | DED D672 - Support of UAT Segment III - Collaborative Review | 24 hrs | 10 days | 2025-09-08 | 2025-09-19 | 911 | 913 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
4875 | 913 | Future Task |  |  | D672 | Stacey Terry | Approve | DED D672 - Support of UAT Segment III - Approve | 0 hrs | 0 days | 2025-09-19 | 2025-09-19 | 912 | 914 |  | Jimmy Cox
4975 | 914 | Future Task |  |  | D672 | Stacey Terry |  | Identify UAT support resources for UAT Segment 3 | 12 hrs | 7 days | 2025-09-22 | 2025-09-30 | 913 | 915 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4976 | 915 | Future Task |  |  | D672 | Stacey Terry |  | Participate in UAT sessions for UAT Segment 3 | 6 hrs | 21 days | 2025-10-01 | 2025-10-29 | 914 | 916SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp
4977 | 916 | Future Task |  |  | D672 | Stacey Terry |  | Support resolution of UAT issues for UAT Segment 3 | 7 hrs | 21 days | 2025-10-01 | 2025-10-29 | 915SS | 917FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Donnie Doctor,Abdel El Bacha,Matthew Culp,Manojkumar Gurjar
4978 | 917 | Future Task |  |  | D672 | Stacey Terry |  | Confirm requirements traceability for UAT Segment 3 | 3 hrs | 7 days | 2025-10-23 | 2025-10-31 | 916FS-5 days | 918SS |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4979 | 918 | Future Task |  |  | D672 | Stacey Terry |  | Create UAT Segment 3 Summary Document | 3 hrs | 7 days | 2025-10-23 | 2025-10-31 | 917SS | 919 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
4876 | 919 | Future Task |  |  | D672 | Stacey Terry | Submit | DEL D672 - Support of UAT Segment III - Draft Submission | 0 hrs | 0 days | 2025-10-31 | 2025-10-31 | 918 | 920 |  | Stacey Terry,Joy Schneider
4877 | 920 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-11-03 | 2025-11-07 | 919 | 921 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4878 | 921 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Style Guide Review | 1 hr | 1 day | 2025-11-10 | 2025-11-10 | 920 | 922 |  | Dusti Kincl
4879 | 922 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Final Collaborative Review | 20 hrs | 5 days | 2025-11-12 | 2025-11-18 | 921 | 923 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
4880 | 923 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Accenture QC | 4 hrs | 2 days | 2025-11-19 | 2025-11-20 | 922 | 924 |  | Francisca Li
4881 | 924 | Future Task |  |  | D672 | Stacey Terry | Submit | DEL D672 - Support of UAT Segment III - Submit | 0 hrs | 0 days | 2025-11-20 | 2025-11-20 | 923 | 925 |  | Joy Schneider
4882 | 925 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Department QC | 4 hrs | 1 day | 2025-11-21 | 2025-11-21 | 924 | 926 |  | Tommy Werner,Gabriela Gibson
4883 | 926 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Contract Manager Review | 2 hrs | 3 days | 2025-11-24 | 2025-11-26 | 925 | 927 |  | Sean Buchanan
4884 | 927 | Future Task |  |  | D672 | Stacey Terry | Accept | DEL D672 - Support of UAT Segment III - Accept | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 926 |  | 2025-11-01 | Sean Buchanan
4885 | 928 | Future Task | Yes |  | D673 | Stacey Terry |  | D673 - Completion of Mock Go-Lives (Dry Run #2) | 223 hrs | 66 days | 2025-08-04 | 2025-11-04
4886 | 929 | Future Task |  |  | D673 | Stacey Terry | Create | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Create | 24 hrs | 10 days | 2025-08-04 | 2025-08-15 | 1 | 930 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4887 | 930 | Future Task |  |  | D673 | Stacey Terry | Submit | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Submit | 0 hrs | 0 days | 2025-08-15 | 2025-08-15 | 929 | 931 |  | Stacey Terry,Joy Schneider
4888 | 931 | Future Task |  |  | D673 | Stacey Terry | Review | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Collaborative Review | 32 hrs | 10 days | 2025-08-18 | 2025-08-29 | 930 | 932 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4889 | 932 | Future Task |  |  | D673 | Stacey Terry | Approve | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Approve | 0 hrs | 0 days | 2025-08-29 | 2025-08-29 | 931 | 933 |  | Jimmy Cox
4980 | 933 | Future Task |  |  | D673 | Stacey Terry |  | Confirm Mock Go-Live Dry Run #2 Execution Readiness | 24 hrs | 4 days | 2025-09-02 | 2025-09-05 | 932 | 934 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4981 | 934 | Future Task |  |  | D673 | Stacey Terry |  | Execute Mock Go-Live Dry Run #2 | 20 hrs | 10 days | 2025-09-08 | 2025-09-19 | 933 | 935 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4982 | 935 | Future Task |  |  | D673 | Stacey Terry |  | Document Mock Go-Live Dry Run Results #2 | 30 hrs | 5 days | 2025-09-22 | 2025-09-26 | 934 | 936 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4983 | 936 | Future Task |  |  | D673 | Stacey Terry |  | Create Mock Go-Live Dry Run #2 Summary Document | 20 hrs | 10 days | 2025-09-29 | 2025-10-10 | 935 | 937 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4890 | 937 | Future Task |  |  | D673 | Stacey Terry | Submit | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Draft Submission | 0 hrs | 0 days | 2025-10-10 | 2025-10-10 | 936 | 938 |  | Stacey Terry,Joy Schneider
4891 | 938 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Pre-Submission Collaborative Review | 28 hrs | 5 days | 2025-10-13 | 2025-10-17 | 937 | 939 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4892 | 939 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Style Guide Review | 1 hr | 1 day | 2025-10-20 | 2025-10-20 | 938 | 940 |  | Dusti Kincl
4893 | 940 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Final Collaborative Review | 28 hrs | 5 days | 2025-10-21 | 2025-10-27 | 939 | 941 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4894 | 941 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Accenture QC | 4 hrs | 2 days | 2025-10-28 | 2025-10-29 | 940 | 942 |  | Joy Schneider
4895 | 942 | Future Task |  |  | D673 | Stacey Terry | Submit | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Submit | 0 hrs | 0 days | 2025-10-29 | 2025-10-29 | 941 | 943 |  | Joy Schneider
4896 | 943 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Department QC | 4 hrs | 1 day | 2025-10-30 | 2025-10-30 | 942 | 944 |  | Tommy Werner,Gabriela Gibson
4897 | 944 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Contract Manager Review | 8 hrs | 3 days | 2025-10-31 | 2025-11-04 | 943 | 945 |  | Sean Buchanan
4898 | 945 | Future Task |  |  | D673 | Stacey Terry | Accept | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Accept | 0 hrs | 0 days | 2025-11-04 | 2025-11-04 | 944 | 1252 | 2025-11-01 | Sean Buchanan
4899 | 946 | Future Task | Yes |  | D674 | Jarad Hermann |  | D674 - Completion of Penetration Testing | 100 hrs | 145 days | 2025-05-02 | 2025-11-26
4900 | 947 | Future Task |  |  | D674 | Jarad Hermann | Create | DED D674 - Completion of Penetration Testing - Create | 2 hrs | 10 days | 2025-05-02 | 2025-05-15 | 1201FS+29 days,1236FS+29 days | 948 | Note: should be in version we go live with | Jarad Hermann,Mary Punty
4901 | 948 | Future Task |  |  | D674 | Jarad Hermann | Submit | DED D674 - Completion of Penetration Testing - Submit | 0 hrs | 0 days | 2025-05-15 | 2025-05-15 | 947 | 949 |  | Jarad Hermann,Joy Schneider
4902 | 949 | Future Task |  |  | D674 | Jarad Hermann | Review | DED D674 - Completion of Penetration Testing - Collaborative Review | 5 hrs | 10 days | 2025-05-16 | 2025-05-30 | 948 | 950 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4903 | 950 | Future Task |  |  | D674 | Jarad Hermann | Approve | DED D674 - Completion of Penetration Testing - Approve | 0 hrs | 0 days | 2025-05-30 | 2025-05-30 | 949 | 951 |  | Jimmy Cox
4984 | 951 | Future Task |  |  | D674 | Jarad Hermann |  | Execute/Complete Penetration Test | 10 hrs | 64 days | 2025-06-02 | 2025-08-29 | 950 | 952 |  | Jarad Hermann,Bryan Sohayda
4985 | 952 | Future Task |  |  | D674 | Jarad Hermann |  | Review Penetration Test Outcome | 10 hrs | 20 days | 2025-09-02 | 2025-09-29 | 951 | 953SS |  | Jarad Hermann,Bryan Sohayda
4986 | 953 | Future Task |  |  | D674 | Jarad Hermann |  | Remediate Penetration Test | 10 hrs | 44 days | 2025-09-02 | 2025-10-31 | 952SS | 954SS |  | Jarad Hermann,Bryan Sohayda
4987 | 954 | Future Task |  |  | D674 | Jarad Hermann |  | Create Final Pen Testing Results/Remediation Summary Report | 20 hrs | 44 days | 2025-09-02 | 2025-10-31 | 953SS | 955 |  | Jarad Hermann,Bryan Sohayda
4904 | 955 | Future Task |  |  | D674 | Jarad Hermann | Submit | DEL D674 - Completion of Penetration Testing - Draft Submission | 0 hrs | 0 days | 2025-10-31 | 2025-10-31 | 954 | 956 |  | Jarad Hermann,Joy Schneider
4905 | 956 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2025-11-03 | 2025-11-07 | 955 | 957 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4906 | 957 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Style Guide Review | 1 hr | 1 day | 2025-11-10 | 2025-11-10 | 956 | 958 |  | Dusti Kincl
4907 | 958 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Final Collaborative Review | 16 hrs | 5 days | 2025-11-12 | 2025-11-18 | 957 | 959 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4908 | 959 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Accenture QC | 4 hrs | 2 days | 2025-11-19 | 2025-11-20 | 958 | 960 |  | Joy Schneider
4909 | 960 | Future Task |  |  | D674 | Jarad Hermann | Submit | DEL D674 - Completion of Penetration Testing - Submit | 0 hrs | 0 days | 2025-11-20 | 2025-11-20 | 959 | 961 |  | Joy Schneider
4910 | 961 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Department QC | 4 hrs | 1 day | 2025-11-21 | 2025-11-21 | 960 | 962 |  | Tommy Werner,Gabriela Gibson
4911 | 962 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Contract Manager Review | 2 hrs | 3 days | 2025-11-24 | 2025-11-26 | 961 | 963 |  | Sean Buchanan
4912 | 963 | Future Task |  |  | D674 | Jarad Hermann | Accept | DEL D674 - Completion of Penetration Testing - Accept | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 962 | 1252 | 2025-11-01 | Sean Buchanan
4913 | 964 | Future Task | Yes |  | D675 | Jarad Hermann |  | D675 - Completion of Performance Testing | 180 hrs | 145 days | 2025-05-02 | 2025-11-26
4914 | 965 | Future Task |  |  | D675 | Jarad Hermann | Create | DED D675 - Completion of Performance Testing - Create | 2 hrs | 10 days | 2025-05-02 | 2025-05-15 | 1189FS-14 days,1225FS-14 days | 966 |  | Jarad Hermann,Mary Punty
4915 | 966 | Future Task |  |  | D675 | Jarad Hermann | Submit | DED D675 - Completion of Performance Testing - Submit | 0 hrs | 0 days | 2025-05-15 | 2025-05-15 | 965 | 967 |  | Jarad Hermann,Joy Schneider
4916 | 967 | Future Task |  |  | D675 | Jarad Hermann | Review | DED D675 - Completion of Performance Testing - Collaborative Review | 5 hrs | 10 days | 2025-05-16 | 2025-05-30 | 966 | 968 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4917 | 968 | Future Task |  |  | D675 | Jarad Hermann | Approve | DED D675 - Completion of Performance Testing - Approve | 0 hrs | 0 days | 2025-05-30 | 2025-05-30 | 967 | 969 |  | Jimmy Cox
4988 | 969 | Future Task |  |  | D675 | Jarad Hermann |  | Execute Performance Testing | 4 hrs | 108 days | 2025-06-02 | 2025-10-31 | 968573 | 970FS-10 days,973 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4989 | 970 | Future Task |  |  | D675 | Jarad Hermann |  | Create Completion of Performance Testing Summary Document | 40 hrs | 10 days | 2025-10-20 | 2025-10-31 | 969FS-10 days | 971SS,972SS,973 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4990 | 971 | Future Task |  |  | D675 | Jarad Hermann |  | Conduct Performance Testing Exit Criteria Review Meeting | 40 hrs | 10 days | 2025-10-20 | 2025-10-31 | 970SS | 973 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4991 | 972 | Future Task |  |  | D675 | Jarad Hermann |  | Confirm requirements traceability for Performance Testing | 40 hrs | 10 days | 2025-10-20 | 2025-10-31 | 970SS | 973 |  | Jarad Hermann,Vivek Sharma,Stacey Terry,Yogesh Deshmukh
4918 | 973 | Future Task |  |  | D675 | Jarad Hermann | Submit | DEL D675 - Completion of Performance Testing - Draft Submission | 0 hrs | 0 days | 2025-10-31 | 2025-10-31 | 972969970971 | 974 |  | Jarad Hermann,Joy Schneider
4919 | 974 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2025-11-03 | 2025-11-07 | 973 | 975 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4920 | 975 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Style Guide Review | 1 hr | 1 day | 2025-11-10 | 2025-11-10 | 974 | 976 |  | Dusti Kincl
4921 | 976 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Final Collaborative Review | 16 hrs | 5 days | 2025-11-12 | 2025-11-18 | 975 | 977 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4922 | 977 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Accenture QC | 4 hrs | 2 days | 2025-11-19 | 2025-11-20 | 976 | 978 |  | Joy Schneider
4923 | 978 | Future Task |  |  | D675 | Jarad Hermann | Submit | DEL D675 - Completion of Performance Testing - Submit | 0 hrs | 0 days | 2025-11-20 | 2025-11-20 | 977 | 979 |  | Joy Schneider
4924 | 979 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Department QC | 4 hrs | 1 day | 2025-11-21 | 2025-11-21 | 978 | 980 |  | Tommy Werner,Gabriela Gibson
4925 | 980 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Contract Manager Review | 8 hrs | 3 days | 2025-11-24 | 2025-11-26 | 979 | 981 |  | Sean Buchanan
4926 | 981 | Future Task |  |  | D675 | Jarad Hermann | Accept | DEL D675 - Completion of Performance Testing - Accept | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 980 | 1252 | 2025-11-01 | Sean Buchanan
4927 | 982 | Future Task | Yes |  | D676 | Jarad Hermann |  | D676 - Completion of Disaster Recovery Testing | 158 hrs | 114 days | 2025-03-04 | 2025-08-12
4928 | 983 | Future Task |  |  | D676 | Jarad Hermann | Create | DED D676 - Completion of Disaster Recovery Testing - Create | 8 hrs | 10 days | 2025-03-04 | 2025-03-17 | 1213FS-14 days,1175FS-14 days,1162 | 984 |  | Jarad Hermann,Mary Punty
4929 | 984 | Future Task |  |  | D676 | Jarad Hermann | Submit | DED D676 - Completion of Disaster Recovery Testing - Submit | 0 hrs | 0 days | 2025-03-17 | 2025-03-17 | 983 | 985 |  | Jarad Hermann,Joy Schneider
4930 | 985 | Future Task |  |  | D676 | Jarad Hermann | Review | DED D676 - Completion of Disaster Recovery Testing - Collaborative Review | 20 hrs | 10 days | 2025-03-18 | 2025-03-31 | 984 | 986 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
4931 | 986 | Future Task |  |  | D676 | Jarad Hermann | Approve | DED D676 - Completion of Disaster Recovery Testing - Approve | 0 hrs | 0 days | 2025-03-31 | 2025-03-31 | 985 | 987 |  | Jimmy Cox
4992 | 987 | Future Task |  |  | D676 | Jarad Hermann |  | Execute Disaster Recovery Testing | 3 hrs | 64 days | 2025-04-01 | 2025-06-30 | 986575 | 988 |  | Jarad Hermann,Vivek Sharma,Stacey Terry
4993 | 988 | Future Task |  |  | D676 | Jarad Hermann |  | Create Completion of Disaster Recovery Testing Summary Document | 26 hrs | 13 days | 2025-07-01 | 2025-07-18 | 987 | 989SS,990SS,991 |  | Jarad Hermann,Vivek Sharma
4994 | 989 | Future Task |  |  | D676 | Jarad Hermann |  | Conduct Disaster Recovery Testing Exit Criteria Review Meeting | 26 hrs | 13 days | 2025-07-01 | 2025-07-18 | 988SS | 991 |  | Jarad Hermann,Vivek Sharma
4995 | 990 | Future Task |  |  | D676 | Jarad Hermann |  | Confirm requirements traceability for Disaster Recovery Testing | 26 hrs | 13 days | 2025-07-01 | 2025-07-18 | 988SS | 991 |  | Jarad Hermann,Vivek Sharma
4932 | 991 | Future Task |  |  | D676 | Jarad Hermann | Submit | DEL D676 - Completion of Disaster Recovery Testing - Draft Submission | 0 hrs | 0 days | 2025-07-18 | 2025-07-18 | 990988989 | 992 |  | Jarad Hermann,Joy Schneider
4933 | 992 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2025-07-21 | 2025-07-25 | 991 | 993 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4934 | 993 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Style Guide Review | 1 hr | 1 day | 2025-07-28 | 2025-07-28 | 992 | 994 |  | Dusti Kincl
4935 | 994 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Final Collaborative Review | 16 hrs | 5 days | 2025-07-29 | 2025-08-04 | 993 | 995 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
4936 | 995 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Accenture QC | 4 hrs | 2 days | 2025-08-05 | 2025-08-06 | 994 | 996 |  | Joy Schneider
4937 | 996 | Future Task |  |  | D676 | Jarad Hermann | Submit | DEL D676 - Completion of Disaster Recovery Testing - Submit | 0 hrs | 0 days | 2025-08-06 | 2025-08-06 | 995 | 997 |  | Joy Schneider
4938 | 997 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Department QC | 4 hrs | 1 day | 2025-08-07 | 2025-08-07 | 996 | 998 |  | Tommy Werner,Jenifer Hartsfield
4939 | 998 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Contract Manager Review | 8 hrs | 3 days | 2025-08-08 | 2025-08-12 | 997 | 999 |  | Sean Buchanan
4940 | 999 | Future Task |  |  | D676 | Jarad Hermann | Accept | DEL D676 - Completion of Disaster Recovery Testing - Accept | 0 hrs | 0 days | 2025-08-12 | 2025-08-12 | 998 | 1252 | 2025-11-01 | Sean Buchanan
4941 | 1000 | Future Task | Yes |  | D677 | Stacey Terry |  | D677 - Completion of Mock Go-Lives (Dry Run #3) | 229 hrs | 52 days | 2025-09-29 | 2025-12-12
4942 | 1001 | Future Task |  |  | D677 | Stacey Terry | Create | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Create | 24 hrs | 10 days | 2025-09-29 | 2025-10-10 | 1 | 1002 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty
4943 | 1002 | Future Task |  |  | D677 | Stacey Terry | Submit | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Submit | 0 hrs | 0 days | 2025-10-10 | 2025-10-10 | 1001 | 1003 |  | Stacey Terry,Joy Schneider
4944 | 1003 | Future Task |  |  | D677 | Stacey Terry | Review | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Collaborative Review | 32 hrs | 10 days | 2025-10-13 | 2025-10-24 | 1002 | 1004 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
4945 | 1004 | Future Task |  |  | D677 | Stacey Terry | Approve | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Approve | 0 hrs | 0 days | 2025-10-24 | 2025-10-24 | 1003 | 1005 |  | Jimmy Cox
5000 | 1005 | Future Task |  |  | D677 | Stacey Terry |  | Confirm Mock Go-Live Dry Run #3 Readiness | 40 hrs | 4 days | 2025-10-27 | 2025-10-30 | 1004 | 1006FS+1 day |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5001 | 1006 | Future Task |  |  | D677 | Stacey Terry |  | Execute Mock Go-Live Dry Run #3 | 10 hrs | 10 days | 2025-11-03 | 2025-11-17 | 1005FS+1 day | 1007 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5002 | 1007 | Future Task |  |  | D677 | Stacey Terry |  | Document Mock Go-Live Dry Run Results #3 | 30 hrs | 3 days | 2025-11-18 | 2025-11-20 | 1006 | 1008 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5003 | 1008 | Future Task |  |  | D677 | Stacey Terry |  | Create Mock Go-Live Dry Run #3 Summary Document | 20 hrs | 2 days | 2025-11-21 | 2025-11-24 | 1007 | 1009 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
4946 | 1009 | Future Task |  |  | D677 | Stacey Terry | Submit | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Draft Submission | 0 hrs | 0 days | 2025-11-24 | 2025-11-24 | 1008 | 1010 |  | Stacey Terry,Joy Schneider
4947 | 1010 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Pre-Submission Collaborative Review | 28 hrs | 3 days | 2025-11-25 | 2025-12-01 | 1009 | 1011 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4948 | 1011 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Style Guide Review | 1 hr | 1 day | 2025-12-02 | 2025-12-02 | 1010 | 1012 |  | Dusti Kincl
4949 | 1012 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Final Collaborative Review | 28 hrs | 3 days | 2025-12-03 | 2025-12-05 | 1011 | 1013 |  | Stacey Terry,Manojkumar Gurjar,Mary Punty,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
4950 | 1013 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Accenture QC | 4 hrs | 1 day | 2025-12-08 | 2025-12-08 | 1012 | 1014 |  | Joy Schneider
4951 | 1014 | Future Task |  |  | D677 | Stacey Terry | Submit | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Submit | 0 hrs | 0 days | 2025-12-08 | 2025-12-08 | 1013 | 1015 |  | Joy Schneider
4952 | 1015 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Department QC | 4 hrs | 1 day | 2025-12-09 | 2025-12-09 | 1014 | 1016 |  | Tommy Werner,Gabriela Gibson
4953 | 1016 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Contract Manager Review | 8 hrs | 3 days | 2025-12-10 | 2025-12-12 | 1015 | 1017 |  | Sean Buchanan
4954 | 1017 | Future Task |  |  | D677 | Stacey Terry | Accept | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Accept | 0 hrs | 0 days | 2025-12-12 | 2025-12-12 | 1016 | 1252 | 2025-12-01 | Sean Buchanan
5080 | 1018 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | WP406 - Mock Conversion Testing Plan | 180 hrs | 94 days | 2024-03-11 | 2024-07-22
5081 | 1019 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WPED WP406 - Mock Conversion Testing Plan - Create | 24 hrs | 10 days | 2024-03-11 | 2024-03-22 | 1 | 1020 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5082 | 1020 | Future Task |  |  | WP406 | Manojkumar Gurjar | Submit | WPED WP406 - Mock Conversion Testing Plan - Submit | 0 hrs | 0 days | 2024-03-22 | 2024-03-22 | 1019 | 1021 |  | Joy Schneider,Manojkumar Gurjar
5083 | 1021 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WPED WP406 - Mock Conversion Testing Plan - Review | 28 hrs | 10 days | 2024-03-25 | 2024-04-05 | 1020 | 1022 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5084 | 1022 | Future Task |  |  | WP406 | Manojkumar Gurjar | Approve | WPED WP406 - Mock Conversion Testing Plan - Approve | 0 hrs | 0 days | 2024-04-05 | 2024-04-05 | 1021 | 1023 |  | Jimmy Cox
5116 | 1023 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | Define Mock Conversion Testing Approach | 20 hrs | 10 days | 2024-04-08 | 2024-04-19 | 1022 | 1024 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5117 | 1024 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | Identify Resources for Mock Conversion Testing | 20 hrs | 10 days | 2024-04-22 | 2024-05-03 | 1023 | 1025 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5118 | 1025 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | Define Test Cycles and Scenarios | 20 hrs | 24 days | 2024-05-06 | 2024-06-07 | 1024 | 1026 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5119 | 1026 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | Define and review Entry/Exit Criteria for Mock Conversion Testing | 20 hrs | 15 days | 2024-06-10 | 2024-06-28 | 1025 | 1027 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5085 | 1027 | Future Task |  |  | WP406 | Manojkumar Gurjar | Submit | WP WP406 - Mock Conversion Testing Plan - Submit | 0 hrs | 0 days | 2024-06-28 | 2024-06-28 | 1026 | 1028 |  | Joy Schneider,Manojkumar Gurjar
5086 | 1028 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WP WP406 - Mock Conversion Testing Plan - Collaborative Review & Update | 24 hrs | 10 days | 2024-07-01 | 2024-07-15 | 1027 | 1029 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5087 | 1029 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WP WP406 - Mock Conversion Testing Plan - Final Review & Edits | 24 hrs | 5 days | 2024-07-16 | 2024-07-22 | 1028 | 1030 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5088 | 1030 | Future Task |  |  | WP406 | Manojkumar Gurjar | Approve | WP WP406 - Mock Conversion Testing Plan - Approve | 0 hrs | 0 days | 2024-07-22 | 2024-07-22 | 1029 | 1032FS-45 days,564 | 2024-05-01 | Jimmy Cox
5089 | 1031 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | WP407 - Mock Conversion Scripts | 160 hrs | 67 days | 2024-05-17 | 2024-08-21
5090 | 1032 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WPED WP407 - Mock Conversion Scripts - Create | 24 hrs | 10 days | 2024-05-17 | 2024-05-31 | 1030FS-45 days | 1033 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5091 | 1033 | Future Task |  |  | WP407 | Manojkumar Gurjar | Submit | WPED WP407 - Mock Conversion Scripts - Submit | 0 hrs | 0 days | 2024-05-31 | 2024-05-31 | 1032 | 1034 |  | Joy Schneider,Manojkumar Gurjar
5092 | 1034 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WPED WP407 - Mock Conversion Scripts - Review | 28 hrs | 10 days | 2024-06-03 | 2024-06-14 | 1033 | 1035 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5093 | 1035 | Future Task |  |  | WP407 | Manojkumar Gurjar | Approve | WPED WP407 - Mock Conversion Scripts - Approve | 0 hrs | 0 days | 2024-06-14 | 2024-06-14 | 1034 | 1036 |  | Jimmy Cox
5120 | 1036 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | Create Test Scripts | 20 hrs | 19 days | 2024-06-17 | 2024-07-12 | 1035 | 1037 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5121 | 1037 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | Identify System Test Scripts for Mock Conversion Testing | 20 hrs | 8 days | 2024-07-15 | 2024-07-24 | 1036 | 1038 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5122 | 1038 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | Review System Test Scripts for Mock Conversion Testing | 20 hrs | 5 days | 2024-07-25 | 2024-07-31 | 1037 | 1039 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5094 | 1039 | Future Task |  |  | WP407 | Manojkumar Gurjar | Submit | WP WP407 - Mock Conversion Scripts - Submit | 0 hrs | 0 days | 2024-07-31 | 2024-07-31 | 1038 | 1040 |  | Joy Schneider,Manojkumar Gurjar
5095 | 1040 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WP WP407 - Mock Conversion Scripts - Collaborative Review & Update | 24 hrs | 10 days | 2024-08-01 | 2024-08-14 | 1039 | 1041 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5096 | 1041 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WP WP407 - Mock Conversion Scripts - Final Review & Edits | 24 hrs | 5 days | 2024-08-15 | 2024-08-21 | 1040 | 1042 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5097 | 1042 | Future Task |  |  | WP407 | Manojkumar Gurjar | Approve | WP WP407 - Mock Conversion Scripts - Approve | 0 hrs | 0 days | 2024-08-21 | 2024-08-21 | 1041 | 621FS-28 days | 2024-07-01 | Jimmy Cox
5098 | 1043 | Future Task |  |  | WP408 | Stacey Terry |  | WP408 - System Test Scripts | 188 hrs | 153 days | 2024-02-12 | 2024-09-16
5099 | 1044 | Future Task |  |  | WP408 | Stacey Terry | Create | WPED WP408 - System Test Scripts - Create | 16 hrs | 10 days | 2024-02-12 | 2024-02-23 | 1 | 1045 |  | Stacey Terry,Mary Punty
5100 | 1045 | Future Task |  |  | WP408 | Stacey Terry | Submit | WPED WP408 - System Test Scripts - Submit | 0 hrs | 0 days | 2024-02-23 | 2024-02-23 | 1044 | 1046 |  | Joy Schneider,Stacey Terry
5101 | 1046 | Future Task |  |  | WP408 | Stacey Terry | Review | WPED WP408 - System Test Scripts - Review | 12 hrs | 10 days | 2024-02-26 | 2024-03-08 | 1045 | 1047 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5102 | 1047 | Future Task |  |  | WP408 | Stacey Terry | Approve | WPED WP408 - System Test Scripts - Approve | 0 hrs | 0 days | 2024-03-08 | 2024-03-08 | 1046 | 1048 |  | Jimmy Cox
5123 | 1048 | Future Task |  |  | WP408 | Stacey Terry |  | Create Work Unit Tracker for System Test Preparation | 20 hrs | 10 days | 2024-03-11 | 2024-03-22 | 1047 | 1049 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5124 | 1049 | Future Task |  |  | WP408 | Stacey Terry |  | Review, update, & confirm Work Unit Tracker for System Test Preparation | 20 hrs | 10 days | 2024-03-25 | 2024-04-05 | 1048 | 1050FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter
5125 | 1050 | Future Task |  |  | WP408 | Stacey Terry |  | Create System Test Script Template | 30 hrs | 5 days | 2024-04-01 | 2024-04-05 | 1049FS-5 days | 1051 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5126 | 1051 | Future Task |  |  | WP408 | Stacey Terry |  | Create, Review and Confirm System Test Scripts and Data (this is a WU) | 20 hrs | 93 days | 2024-04-08 | 2024-08-16 | 1050 | 1052 |  | Deana Metcalf,Stacey Terry,Yogesh Deshmukh,Janice Jackson,LaVondria Norton,Robert Hicks,Shelisa Harris,Matthew Culp,Taryn Mroczkowski,Shayne Dennis,Brendan Jones,Heather Cleary,Joanne Lane,Donnie Doctor,Ryan Raagas,Pooja Barde,Tiffany Porter,Yorke Davis...
5127 | 1052 | Future Task |  |  | WP408 | Stacey Terry |  | Create System Test Script Summary Document | 30 hrs | 5 days | 2024-08-19 | 2024-08-23 | 1051 | 1053 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5103 | 1053 | Future Task |  |  | WP408 | Stacey Terry | Submit | WP WP408 - System Test Scripts - Submit | 0 hrs | 0 days | 2024-08-23 | 2024-08-23 | 1052 | 1054 |  | Joy Schneider,Stacey Terry
5104 | 1054 | Future Task |  |  | WP408 | Stacey Terry | Review | WP WP408 - System Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | 2024-08-26 | 2024-09-09 | 1053 | 1055 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5105 | 1055 | Future Task |  |  | WP408 | Stacey Terry | Review | WP WP408 - System Test Scripts - Final Review & Edits | 20 hrs | 5 days | 2024-09-10 | 2024-09-16 | 1054 | 1056 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5106 | 1056 | Future Task |  |  | WP408 | Stacey Terry | Approve | WP WP408 - System Test Scripts - Approve | 0 hrs | 0 days | 2024-09-16 | 2024-09-16 | 1055 | 648 | 2024-09-01 | Jimmy Cox
5107 | 1057 | Future Task |  |  | WP409 | Stacey Terry |  | WP409 - Regression Testing Plan | 116 hrs | 58 days | 2024-09-03 | 2024-11-22
5108 | 1058 | Future Task |  |  | WP409 | Stacey Terry | Create | WPED WP409 - Regression Testing Plan - Create | 2 hrs | 9 days | 2024-09-03 | 2024-09-13 | 1 | 1059 |  | Stacey Terry,Mary Punty
5109 | 1059 | Future Task |  |  | WP409 | Stacey Terry | Submit | WPED WP409 - Regression Testing Plan - Submit | 0 hrs | 0 days | 2024-09-13 | 2024-09-13 | 1058 | 1060 |  | Joy Schneider,Stacey Terry
5110 | 1060 | Future Task |  |  | WP409 | Stacey Terry | Review | WPED WP409 - Regression Testing Plan - Review | 24 hrs | 10 days | 2024-09-16 | 2024-09-27 | 1059 | 1061 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5111 | 1061 | Future Task |  |  | WP409 | Stacey Terry | Approve | WPED WP409 - Regression Testing Plan - Approve | 0 hrs | 0 days | 2024-09-27 | 2024-09-27 | 1060 | 1062 |  | Jimmy Cox
5128 | 1062 | Future Task |  |  | WP409 | Stacey Terry |  | Create Regression Testing Approach/Plan | 20 hrs | 24 days | 2024-09-30 | 2024-10-31 | 1061 | 1063SS+10 days,1065 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5129 | 1063 | Future Task |  |  | WP409 | Stacey Terry |  | Define the scope of the Regression Test suite | 20 hrs | 10 days | 2024-10-14 | 2024-10-25 | 1062SS+10 days | 1064SS+5 days,1065 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5130 | 1064 | Future Task |  |  | WP409 | Stacey Terry |  | Identify testing resources for Regression Testing | 20 hrs | 5 days | 2024-10-21 | 2024-10-25 | 1063SS+5 days | 1065 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5112 | 1065 | Future Task |  |  | WP409 | Stacey Terry | Submit | WP WP409 - Regression Testing Plan - Submit | 0 hrs | 0 days | 2024-10-31 | 2024-10-31 | 106210631064 | 1066 |  | Joy Schneider,Stacey Terry
5113 | 1066 | Future Task |  |  | WP409 | Stacey Terry | Review | WP WP409 - Regression Testing Plan - Collaborative Review & Update | 10 hrs | 10 days | 2024-11-01 | 2024-11-15 | 1065 | 1067 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5114 | 1067 | Future Task |  |  | WP409 | Stacey Terry | Review | WP WP409 - Regression Testing Plan - Final Review & Edits | 20 hrs | 5 days | 2024-11-18 | 2024-11-22 | 1066 | 1068 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5115 | 1068 | Future Task |  |  | WP409 | Stacey Terry | Approve | WP WP409 - Regression Testing Plan - Approve | 0 hrs | 0 days | 2024-11-22 | 2024-11-22 | 1067 | 1112FS-17 days,1124FS+5 days | 2024-12-01 | Jimmy Cox
5257 | 1069 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | WP412 - Interface Testing Plan | 220 hrs | 94 days | 2024-05-03 | 2024-09-16
5258 | 1070 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WPED WP412 - Interface Testing Plan - Create | 24 hrs | 10 days | 2024-05-03 | 2024-05-16 | 544FS+92 days | 1071,1085SS+29 days |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5259 | 1071 | Future Task |  |  | WP412 | Manojkumar Gurjar | Submit | WPED WP412 - Interface Testing Plan - Submit | 0 hrs | 0 days | 2024-05-16 | 2024-05-16 | 1070 | 1072 |  | Joy Schneider,Manojkumar Gurjar
5260 | 1072 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WPED WP412 - Interface Testing Plan - Review | 28 hrs | 10 days | 2024-05-17 | 2024-05-31 | 1071 | 1073 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5261 | 1073 | Future Task |  |  | WP412 | Manojkumar Gurjar | Approve | WPED WP412 - Interface Testing Plan - Approve | 0 hrs | 0 days | 2024-05-31 | 2024-05-31 | 1072 | 1074 |  | Jimmy Cox
5284 | 1074 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Define Interface Test approach | 20 hrs | 15 days | 2024-06-03 | 2024-06-21 | 1073 | 1075 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5285 | 1075 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Define Interface Test Cycles | 20 hrs | 14 days | 2024-06-24 | 2024-07-12 | 1074 | 1076 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5286 | 1076 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Identify Test Resources for Interface Testing | 20 hrs | 5 days | 2024-07-15 | 2024-07-19 | 1075 | 1077 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5287 | 1077 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Define Test Tools and Test Management processes for Interface Testing | 20 hrs | 5 days | 2024-07-22 | 2024-07-26 | 1076 | 1078 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5288 | 1078 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Create Initial List of Interface Test Scenarios | 20 hrs | 10 days | 2024-07-29 | 2024-08-09 | 1077 | 1079 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5289 | 1079 | Future Task |  | RW | WP412 | Manojkumar Gurjar |  | Prepare High-level Interface Test Approach for Integration Partners | 20 hrs | 10 days | 2024-08-12 | 2024-08-23 | 1078 | 1080 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty
5262 | 1080 | Future Task |  |  | WP412 | Manojkumar Gurjar | Submit | WP WP412 - Interface Testing Plan - Submit | 0 hrs | 0 days | 2024-08-23 | 2024-08-23 | 1079 | 1081 |  | Joy Schneider,Manojkumar Gurjar
5263 | 1081 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WP WP412 - Interface Testing Plan - Collaborative Review & Update | 24 hrs | 10 days | 2024-08-26 | 2024-09-09 | 1080 | 1082 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5264 | 1082 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WP WP412 - Interface Testing Plan - Final Review & Edits | 24 hrs | 5 days | 2024-09-10 | 2024-09-16 | 1081 | 1083 |  | Manojkumar Gurjar,Kurt Meisner,Mary Punty,Matthew Breeding,Jimmy Cox,Angie Robertson
5265 | 1083 | Future Task |  |  | WP412 | Manojkumar Gurjar | Approve | WP WP412 - Interface Testing Plan - Approve | 0 hrs | 0 days | 2024-09-16 | 2024-09-16 | 1082 | 562FS-10 days | 2024-08-01 | Jimmy Cox
5266 | 1084 | Future Task |  |  | WP413 | Stacey Terry |  | WP413 - Interface Test Scripts | 180 hrs | 89 days | 2024-06-14 | 2024-10-18
5267 | 1085 | Future Task |  |  | WP413 | Stacey Terry | Create | WPED WP413 - Interface Test Scripts - Create | 16 hrs | 10 days | 2024-06-14 | 2024-06-27 | 1070SS+29 days | 1086 |  | Stacey Terry,Mary Punty
5268 | 1086 | Future Task |  |  | WP413 | Stacey Terry | Submit | WPED WP413 - Interface Test Scripts - Submit | 0 hrs | 0 days | 2024-06-27 | 2024-06-27 | 1085 | 1087 |  | Joy Schneider,Stacey Terry
5269 | 1087 | Future Task |  |  | WP413 | Stacey Terry | Review | WPED WP413 - Interface Test Scripts - Review | 24 hrs | 10 days | 2024-06-28 | 2024-07-12 | 1086 | 1088 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5270 | 1088 | Future Task |  |  | WP413 | Stacey Terry | Approve | WPED WP413 - Interface Test Scripts - Approve | 0 hrs | 0 days | 2024-07-12 | 2024-07-12 | 1087 | 1089 |  | Jimmy Cox
5290 | 1089 | Future Task |  |  | WP413 | Stacey Terry |  | Create Work Unit Tracker for Interface Test Preparation | 20 hrs | 10 days | 2024-07-15 | 2024-07-26 | 1088 | 1090 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5291 | 1090 | Future Task |  |  | WP413 | Stacey Terry |  | Review, update, & confirm Work Unit Tracker for Interface Test Preparation | 20 hrs | 5 days | 2024-07-29 | 2024-08-02 | 1089 | 1091 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5292 | 1091 | Future Task |  |  | WP413 | Stacey Terry |  | Create, Review and Confirm Interface Test Scenarios/Scripts and Data (this is a WU) | 20 hrs | 24 days | 2024-08-05 | 2024-09-06 | 1090 | 1092 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5293 | 1092 | Future Task |  |  | WP413 | Stacey Terry |  | Create Interface Test Scripts Summary Document | 20 hrs | 5 days | 2024-09-09 | 2024-09-13 | 1091 | 1093 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5271 | 1093 | Future Task |  |  | WP413 | Stacey Terry | Submit | WP WP413 - Interface Test Scripts - Submit | 0 hrs | 0 days | 2024-09-13 | 2024-09-13 | 1092 | 1094 |  | Joy Schneider,Stacey Terry
5272 | 1094 | Future Task |  |  | WP413 | Stacey Terry | Review | WP WP413 - Interface Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | 2024-09-16 | 2024-09-27 | 1093 | 1095 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5273 | 1095 | Future Task |  |  | WP413 | Stacey Terry | Review | WP WP413 - Interface Test Scripts - Final Review & Edits | 20 hrs | 5 days | 2024-09-30 | 2024-10-04 | 1094 | 1096 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5274 | 1096 | Future Task |  |  | WP413 | Stacey Terry | Approve | WP WP413 - Interface Test Scripts - Approve | 0 hrs | 0 days | 2024-10-04 | 2024-10-04 | 1095 | 1097 | 2024-08-01 | Jimmy Cox
7149 | 1097 | Future Task |  | RW | WP413 | Stacey Terry |  | Prepare and share Test Scenarios and Scripts with Integration partners | 20 hrs | 10 days | 2024-10-07 | 2024-10-18 | 1096 |  |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar
5275 | 1098 | Future Task |  |  | WP414 | Stacey Terry |  | WP414 - Payroll Parallel Test Scripts | 160 hrs | 80 days | 2025-01-13 | 2025-05-05
5276 | 1099 | Future Task |  |  | WP414 | Stacey Terry | Create | WPED WP414 - Payroll Parallel Test Scripts - Create | 16 hrs | 10 days | 2025-01-13 | 2025-01-27 | 723SS-4 days | 1100 |  | Stacey Terry,Mary Punty
5277 | 1100 | Future Task |  |  | WP414 | Stacey Terry | Submit | WPED WP414 - Payroll Parallel Test Scripts - Submit | 0 hrs | 0 days | 2025-01-27 | 2025-01-27 | 1099 | 1101 |  | Joy Schneider,Stacey Terry
5278 | 1101 | Future Task |  |  | WP414 | Stacey Terry | Review | WPED WP414 - Payroll Parallel Test Scripts - Review | 24 hrs | 10 days | 2025-01-28 | 2025-02-10 | 1100 | 1102 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5279 | 1102 | Future Task |  |  | WP414 | Stacey Terry | Approve | WPED WP414 - Payroll Parallel Test Scripts - Approve | 0 hrs | 0 days | 2025-02-10 | 2025-02-10 | 1101 | 1103 |  | Jimmy Cox
5295 | 1103 | Future Task |  |  | WP414 | Stacey Terry |  | Create Work Unit Tracker for Payroll Parallel Test Preparation | 20 hrs | 5 days | 2025-02-11 | 2025-02-17 | 1102 | 1104 |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh
5296 | 1104 | Future Task |  |  | WP414 | Stacey Terry |  | Review, update, & confirm Work Unit Tracker for Payroll Parallel Test Preparation | 20 hrs | 10 days | 2025-02-18 | 2025-03-03 | 1103 | 1105FS-5 days |  | Stacey Terry,Yogesh Deshmukh,Deana Metcalf,Jennifer Peddicord
5297 | 1105 | Future Task |  |  | WP414 | Stacey Terry |  | Create, Review and Confirm Payroll Parallel Test Scenarios/Scripts and Data - this is a WU | 20 hrs | 30 days | 2025-02-25 | 2025-04-07 | 1104FS-5 days | 1106FS-5 days |  | Tim Elmer,Stacey Terry,Yogesh Deshmukh,Jennifer Peddicord
5298 | 1106 | Future Task |  |  | WP414 | Stacey Terry |  | Create Payroll Parallel Test Script Summary Document | 20 hrs | 10 days | 2025-04-01 | 2025-04-14 | 1105FS-5 days | 1107 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5280 | 1107 | Future Task |  |  | WP414 | Stacey Terry | Submit | WP WP414 - Payroll Parallel Test Scripts - Submit | 0 hrs | 0 days | 2025-04-14 | 2025-04-14 | 1106 | 1108 |  | Joy Schneider,Stacey Terry
5281 | 1108 | Future Task |  |  | WP414 | Stacey Terry | Review | WP WP414 - Payroll Parallel Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | 2025-04-15 | 2025-04-28 | 1107 | 1109 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5282 | 1109 | Future Task |  |  | WP414 | Stacey Terry | Review | WP WP414 - Payroll Parallel Test Scripts - Final Review & Edits | 20 hrs | 5 days | 2025-04-29 | 2025-05-05 | 1108 | 1110 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5283 | 1110 | Future Task |  |  | WP414 | Stacey Terry | Approve | WP WP414 - Payroll Parallel Test Scripts - Approve | 0 hrs | 0 days | 2025-05-05 | 2025-05-05 | 1109 |  | 2025-03-01 | Jimmy Cox
5131 | 1111 | Future Task |  |  | WP415 | Stacey Terry |  | WP415 - Regression Test Scripts | 140 hrs | 63 days | 2024-10-30 | 2025-02-03
5132 | 1112 | Future Task |  |  | WP415 | Stacey Terry | Create | WPED WP415 - Regression Test Scripts - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1068FS-17 days | 1113 |  | Stacey Terry,Mary Punty
5133 | 1113 | Future Task |  |  | WP415 | Stacey Terry | Submit | WPED WP415 - Regression Test Scripts - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 1112 | 1114 |  | Joy Schneider,Stacey Terry
5134 | 1114 | Future Task |  |  | WP415 | Stacey Terry | Review | WPED WP415 - Regression Test Scripts - Review | 24 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1113 | 1115 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5135 | 1115 | Future Task |  |  | WP415 | Stacey Terry | Approve | WPED WP415 - Regression Test Scripts - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1114 | 1116 |  | Jimmy Cox
5221 | 1116 | Future Task |  |  | WP415 | Stacey Terry |  | Create Regression Test Suite | 20 hrs | 10 days | 2024-12-02 | 2024-12-13 | 1115 | 1117 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5222 | 1117 | Future Task |  |  | WP415 | Stacey Terry |  | Review, update & confirm Regression Test Suite | 20 hrs | 9 days | 2024-12-16 | 2024-12-27 | 1116 | 1118 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter
5223 | 1118 | Future Task |  |  | WP415 | Stacey Terry |  | Create Regression Test Scripts Summary Document | 20 hrs | 9 days | 2024-12-30 | 2025-01-10 | 1117 | 1119 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5136 | 1119 | Future Task |  |  | WP415 | Stacey Terry | Submit | WP WP415 - Regression Test Scripts - Submit | 0 hrs | 0 days | 2025-01-10 | 2025-01-10 | 1118 | 1120 |  | Joy Schneider,Stacey Terry
5137 | 1120 | Future Task |  |  | WP415 | Stacey Terry | Review | WP WP415 - Regression Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | 2025-01-13 | 2025-01-27 | 1119 | 1121 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5138 | 1121 | Future Task |  |  | WP415 | Stacey Terry | Review | WP WP415 - Regression Test Scripts - Final Review & Edits | 20 hrs | 5 days | 2025-01-28 | 2025-02-03 | 1120 | 1122 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5139 | 1122 | Future Task |  |  | WP415 | Stacey Terry | Approve | WP WP415 - Regression Test Scripts - Approve | 0 hrs | 0 days | 2025-02-03 | 2025-02-03 | 1121 |  | 2024-12-01 | Jimmy Cox
5140 | 1123 | Future Task | Yes |  | WP416 | Stacey Terry |  | WP416 - Completion of Regression Testing | 123 hrs | 160 days | 2024-12-04 | 2025-07-22
5141 | 1124 | Future Task |  |  | WP416 | Stacey Terry | Create | WPED WP416 - Completion of Regression Testing - Create | 16 hrs | 10 days | 2024-12-04 | 2024-12-17 | 1068FS+5 days | 1125 |  | Stacey Terry,Mary Punty
5142 | 1125 | Future Task |  |  | WP416 | Stacey Terry | Submit | WPED WP416 - Completion of Regression Testing - Submit | 0 hrs | 0 days | 2024-12-17 | 2024-12-17 | 1124 | 1126 |  | Joy Schneider,Stacey Terry
5143 | 1126 | Future Task |  |  | WP416 | Stacey Terry | Review | WPED WP416 - Completion of Regression Testing - Review | 24 hrs | 10 days | 2024-12-18 | 2025-01-02 | 1125 | 1127 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
5144 | 1127 | Future Task |  |  | WP416 | Stacey Terry | Approve | WPED WP416 - Completion of Regression Testing - Approve | 0 hrs | 0 days | 2025-01-02 | 2025-01-02 | 1126 | 1128 |  | Jimmy Cox
5224 | 1128 | Future Task |  |  | WP416 | Stacey Terry |  | Create Work Unit Tracker for Regression Test Execution | 20 hrs | 10 days | 2025-01-03 | 2025-01-16 | 1127 | 1129 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5225 | 1129 | Future Task |  |  | WP416 | Stacey Terry |  | Review, update, and confirm Work Unit Tracker for Regression Test Execution | 20 hrs | 10 days | 2025-01-17 | 2025-01-31 | 1128 | 1130 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5226 | 1130 | Future Task |  |  | WP416 | Stacey Terry |  | Conduct Regression Test Execution Kickoff Meeting | 20 hrs | 5 days | 2025-02-03 | 2025-02-07 | 1129 | 1131 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Manojkumar Gurjar,Deana Metcalf,Janice Jackson,Brendan Jones,Tiffany Porter,Matthew Breeding
5227 | 1131 | Future Task |  |  | WP416 | Stacey Terry |  | Execute Regression Test - this is a WU | 10 hrs | 90 days | 2025-02-10 | 2025-06-16 | 1130 | 1132 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty,Matthew Culp,Abdel El Bacha,Donnie Doctor
5228 | 1132 | Future Task |  |  | WP416 | Stacey Terry |  | Create Completion of Regression Test Execution Summary Document | 3 hrs | 10 days | 2025-06-17 | 2025-06-30 | 1131 | 1133 |  | Stacey Terry,Yogesh Deshmukh,Mary Punty
5145 | 1133 | Future Task |  |  | WP416 | Stacey Terry | Submit | WP WP416 - Completion of Regression Testing - Submit | 0 hrs | 0 days | 2025-06-30 | 2025-06-30 | 1132 | 1134 |  | Joy Schneider,Stacey Terry
5146 | 1134 | Future Task |  |  | WP416 | Stacey Terry | Review | WP WP416 - Completion of Regression Testing - Collaborative Review & Update | 5 hrs | 10 days | 2025-07-01 | 2025-07-15 | 1133 | 1135 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5147 | 1135 | Future Task |  |  | WP416 | Stacey Terry | Review | WP WP416 - Completion of Regression Testing - Final Review & Edits | 5 hrs | 5 days | 2025-07-16 | 2025-07-22 | 1134 | 1136 |  | Stacey Terry,Mary Punty,Deana Metcalf,Jimmy Cox,Angie Robertson
5148 | 1136 | Future Task |  |  | WP416 | Stacey Terry | Approve | WP WP416 - Completion of Regression Testing - Approve | 0 hrs | 0 days | 2025-07-22 | 2025-07-22 | 1135 |  | 2025-06-01 | Jimmy Cox
5149 | 1137 | Future Task |  |  | WP417 | Stacey Terry |  | WP417 - Data Dictionary | 192 hrs | 112 days | 2024-10-30 | 2025-04-11
5150 | 1138 | Future Task |  |  | WP417 | Stacey Terry | Create | WPED WP417 - Data Dictionary - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1 | 1139 |  | Stacey Terry,Manojkumar Gurjar
5151 | 1139 | Future Task |  |  | WP417 | Stacey Terry | Submit | WPED WP417 - Data Dictionary - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 1138 | 1140 |  | Joy Schneider,Stacey Terry
5152 | 1140 | Future Task |  |  | WP417 | Stacey Terry | Review | WPED WP417 - Data Dictionary - Review | 28 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1139 | 1141 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5153 | 1141 | Future Task |  |  | WP417 | Stacey Terry | Approve | WPED WP417 - Data Dictionary - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1140 | 1142 |  | Jimmy Cox
5229 | 1142 | Future Task |  |  | WP417 | Stacey Terry |  | Update data dictionary with latest tables and data elements as needed - Financials | 20 hrs | 21 days | 2024-12-02 | 2024-12-31 | 1141 | 1143 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5230 | 1143 | Future Task |  |  | WP417 | Stacey Terry |  | Update data dictionary with latest tables and data elements as needed - Payroll | 20 hrs | 21 days | 2025-01-02 | 2025-01-31 | 1142 | 1144 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5231 | 1144 | Future Task |  |  | WP417 | Stacey Terry |  | Update data dictionary with latest tables and data elements as needed - DW Related | 20 hrs | 20 days | 2025-02-03 | 2025-02-28 | 1143 | 1145 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5232 | 1145 | Future Task |  |  | WP417 | Stacey Terry |  | Review and confirm data dictionary | 20 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1144 | 1146 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5233 | 1146 | Future Task |  |  | WP417 | Stacey Terry |  | Share Data Dictionary | 20 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1145 | 1147 |  | Stacey Terry,Manojkumar Gurjar,Matthew Breeding,Brian Andrews
5154 | 1147 | Future Task |  |  | WP417 | Stacey Terry | Submit | WP WP417 - Data Dictionary - Submit | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 1146 | 1148 |  | Joy Schneider,Stacey Terry
5155 | 1148 | Future Task |  |  | WP417 | Stacey Terry | Review | WP WP417 - Data Dictionary - Collaborative Review & Update | 24 hrs | 10 days | 2025-03-24 | 2025-04-04 | 1147 | 1149 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5156 | 1149 | Future Task |  |  | WP417 | Stacey Terry | Review | WP WP417 - Data Dictionary - Final Review & Edits | 24 hrs | 5 days | 2025-04-07 | 2025-04-11 | 1148 | 1150 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5157 | 1150 | Future Task |  |  | WP417 | Stacey Terry | Approve | WP WP417 - Data Dictionary - Approve | 0 hrs | 0 days | 2025-04-11 | 2025-04-11 | 1149 |  | 2025-02-01 | Jimmy Cox
5158 | 1151 | Future Task |  |  | WP418 | Jarad Hermann |  | WP418 - Disaster Recovery Plan | 102 hrs | 81 days | 2024-08-26 | 2024-12-20
5159 | 1152 | Future Task |  |  | WP418 | Jarad Hermann | Create | WPED WP418 - Disaster Recovery Plan - Create | 2 hrs | 10 days | 2024-08-26 | 2024-09-09 | 1 | 1153,1164SS+5 days |  | Jarad Hermann
5160 | 1153 | Future Task |  |  | WP418 | Jarad Hermann | Submit | WPED WP418 - Disaster Recovery Plan - Submit | 0 hrs | 0 days | 2024-09-09 | 2024-09-09 | 1152 | 1154 |  | Joy Schneider,Jarad Hermann
5161 | 1154 | Future Task |  |  | WP418 | Jarad Hermann | Review | WPED WP418 - Disaster Recovery Plan - Review | 16 hrs | 10 days | 2024-09-10 | 2024-09-23 | 1153 | 1155 |  | Jarad Hermann,Jimmy Cox,Angie Robertson,Sean Buchanan
5162 | 1155 | Future Task |  |  | WP418 | Jarad Hermann | Approve | WPED WP418 - Disaster Recovery Plan - Approve | 0 hrs | 0 days | 2024-09-23 | 2024-09-23 | 1154 | 1156FS+4 days |  | Jimmy Cox
5234 | 1156 | Future Task |  |  | WP418 | Jarad Hermann |  | Design/Update Disaster Recovery (DR) Plan | 20 hrs | 15 days | 2024-09-30 | 2024-10-18 | 1155FS+4 days | 1157 |  | Jarad Hermann,Vivek Sharma
5235 | 1157 | Future Task |  |  | WP418 | Jarad Hermann |  | Review Financials Disaster Recovery Plan | 20 hrs | 15 days | 2024-10-21 | 2024-11-08 | 1156 | 1158 |  | Jarad Hermann,Vivek Sharma
5236 | 1158 | Future Task |  |  | WP418 | Jarad Hermann |  | Create Payroll Disaster Recovery Plan | 20 hrs | 12 days | 2024-11-12 | 2024-11-27 | 1157 | 1159 |  | Jarad Hermann,Vivek Sharma
5163 | 1159 | Future Task |  |  | WP418 | Jarad Hermann | Submit | WP WP418 - Disaster Recovery Plan - Submit | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1158 | 1160 |  | Joy Schneider,Jarad Hermann
5164 | 1160 | Future Task |  |  | WP418 | Jarad Hermann | Review | WP WP418 - Disaster Recovery Plan - Collaborative Review & Update | 12 hrs | 10 days | 2024-12-02 | 2024-12-13 | 1159 | 1161 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5165 | 1161 | Future Task |  |  | WP418 | Jarad Hermann | Review | WP WP418 - Disaster Recovery Plan - Final Review & Edits | 12 hrs | 5 days | 2024-12-16 | 2024-12-20 | 1160 | 1162 |  | Jarad Hermann,Jimmy Cox,Angie Robertson
5166 | 1162 | Future Task |  |  | WP418 | Jarad Hermann | Approve | WP WP418 - Disaster Recovery Plan - Approve | 0 hrs | 0 days | 2024-12-20 | 2024-12-20 | 1161 | 983 | 2024-11-01 | Jimmy Cox
5167 | 1163 | Future Task |  |  | WP419 | Jarad Hermann |  | WP419 - Disaster Recovery Testing Plan | 116 hrs | 138 days | 2024-09-03 | 2025-03-21
5168 | 1164 | Future Task |  |  | WP419 | Jarad Hermann | Create | WPED WP419 - Disaster Recovery Testing Plan - Create | 16 hrs | 10 days | 2024-09-03 | 2024-09-16 | 1152SS+5 days | 1165 |  | Jarad Hermann,Mary Punty
5169 | 1165 | Future Task |  |  | WP419 | Jarad Hermann | Submit | WPED WP419 - Disaster Recovery Testing Plan - Submit | 0 hrs | 0 days | 2024-09-16 | 2024-09-16 | 1164 | 1166 |  | Joy Schneider,Jarad Hermann
5170 | 1166 | Future Task |  |  | WP419 | Jarad Hermann | Review | WPED WP419 - Disaster Recovery Testing Plan - Review | 20 hrs | 10 days | 2024-09-17 | 2024-09-30 | 1165 | 1167 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5171 | 1167 | Future Task |  |  | WP419 | Jarad Hermann | Approve | WPED WP419 - Disaster Recovery Testing Plan - Approve | 0 hrs | 0 days | 2024-09-30 | 2024-09-30 | 1166 | 1168 |  | Jimmy Cox
5237 | 1168 | Future Task |  |  | WP419 | Jarad Hermann |  | Define and Document Disaster Recovery Test Tasks including Test Planning, Preparation, Execution, and Closure | 20 hrs | 62 days | 2024-10-01 | 2024-12-31 | 1167 | 1169SS,1203SS+42 days |  | Jarad Hermann,Bryan Sohayda
5238 | 1169 | Future Task |  |  | WP419 | Jarad Hermann |  | Define Disaster Recovery Testing Tools | 20 hrs | 62 days | 2024-10-01 | 2024-12-31 | 1168SS | 1170 |  | Jarad Hermann,Bryan Sohayda
5239 | 1170 | Future Task |  |  | WP419 | Jarad Hermann |  | Define and Document Disaster Recovery Test Management | 4 hrs | 41 days | 2025-01-02 | 2025-02-28 | 1169 | 1171SS |  | Jarad Hermann,Bryan Sohayda
5240 | 1171 | Future Task |  |  | WP419 | Jarad Hermann |  | Define and Document Disaster Recovery Test Resources and Responsibilities | 4 hrs | 41 days | 2025-01-02 | 2025-02-28 | 1170SS | 1172 |  | Jarad Hermann,Bryan Sohayda
5172 | 1172 | Future Task |  |  | WP419 | Jarad Hermann | Submit | WP WP419 - Disaster Recovery Testing Plan - Submit | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 1171 | 1173574 |  | Joy Schneider,Jarad Hermann
5173 | 1173 | Future Task |  |  | WP419 | Jarad Hermann | Review | WP WP419 - Disaster Recovery Testing Plan - Collaborative Review & Update | 16 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1172 | 1174 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5174 | 1174 | Future Task |  |  | WP419 | Jarad Hermann | Review | WP WP419 - Disaster Recovery Testing Plan - Final Review & Edits | 16 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1173 | 1175 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5175 | 1175 | Future Task |  |  | WP419 | Jarad Hermann | Approve | WP WP419 - Disaster Recovery Testing Plan - Approve | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 1174 | 983FS-14 days | 2025-02-01 | Jimmy Cox
5176 | 1176 | Future Task |  |  | WP420 | Jarad Hermann |  | WP420 - Performance Testing Plan | 128 hrs | 140 days | 2024-10-30 | 2025-05-21
5177 | 1177 | Future Task |  |  | WP420 | Jarad Hermann | Create | WPED WP420 - Performance Testing Plan - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1 | 1178,1215SS |  | Jarad Hermann,Mary Punty
5178 | 1178 | Future Task |  |  | WP420 | Jarad Hermann | Submit | WPED WP420 - Performance Testing Plan - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 1177 | 1179 |  | Joy Schneider,Jarad Hermann
5179 | 1179 | Future Task |  |  | WP420 | Jarad Hermann | Review | WPED WP420 - Performance Testing Plan - Review | 20 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1178 | 1180 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5180 | 1180 | Future Task |  |  | WP420 | Jarad Hermann | Approve | WPED WP420 - Performance Testing Plan - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1179 | 1181,1182SS,1183SS,1184SS,1185SS |  | Jimmy Cox
5241 | 1181 | Future Task |  |  | WP420 | Jarad Hermann |  | Identify and establish the projected load of the system | 4 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1180 | 1186 |  | Jarad Hermann,Bryan Sohayda
5242 | 1182 | Future Task |  |  | WP420 | Jarad Hermann |  | Define test cycles to be included | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1180SS | 1186 |  | Jarad Hermann,Bryan Sohayda
5243 | 1183 | Future Task |  |  | WP420 | Jarad Hermann |  | Define Performance Testing objectives, scope, environments, and metrics | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1180SS | 1186 |  | Jarad Hermann,Bryan Sohayda
5244 | 1184 | Future Task |  |  | WP420 | Jarad Hermann |  | Identify performance testing project team members and responsibilities | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1180SS | 1186 |  | Jarad Hermann,Bryan Sohayda
5245 | 1185 | Future Task |  |  | WP420 | Jarad Hermann |  | Define and document Performance Testing entry and exit criteria | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1180SS | 1186 |  | Jarad Hermann,Bryan Sohayda
5181 | 1186 | Future Task |  |  | WP420 | Jarad Hermann | Submit | WP WP420 - Performance Testing Plan - Submit | 0 hrs | 0 days | 2025-04-30 | 2025-04-30 | 1.1851e+19 | 1187572 |  | Joy Schneider,Jarad Hermann
5182 | 1187 | Future Task |  |  | WP420 | Jarad Hermann | Review | WP WP420 - Performance Testing Plan - Collaborative Review & Update | 4 hrs | 10 days | 2025-05-01 | 2025-05-14 | 1186 | 1188 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5183 | 1188 | Future Task |  |  | WP420 | Jarad Hermann | Review | WP WP420 - Performance Testing Plan - Final Review & Edits | 4 hrs | 5 days | 2025-05-15 | 2025-05-21 | 1187 | 1189 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5184 | 1189 | Future Task |  |  | WP420 | Jarad Hermann | Approve | WP WP420 - Performance Testing Plan - Approve | 0 hrs | 0 days | 2025-05-21 | 2025-05-21 | 1188 | 965FS-14 days | 2025-04-01 | Jimmy Cox
5185 | 1190 | Future Task |  |  | WP421 | Jarad Hermann |  | WP421 - Penetration Testing Plan | 128 hrs | 97 days | 2024-10-30 | 2025-03-21
5186 | 1191 | Future Task |  |  | WP421 | Jarad Hermann | Create | WPED WP421 - Penetration Testing Plan - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1 | 1192,1227SS |  | Jarad Hermann,Mary Punty
5187 | 1192 | Future Task |  |  | WP421 | Jarad Hermann | Submit | WPED WP421 - Penetration Testing Plan - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 1191 | 1193 |  | Joy Schneider,Jarad Hermann
5188 | 1193 | Future Task |  |  | WP421 | Jarad Hermann | Review | WPED WP421 - Penetration Testing Plan - Review | 20 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1192 | 1194 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5189 | 1194 | Future Task |  |  | WP421 | Jarad Hermann | Approve | WPED WP421 - Penetration Testing Plan - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1193 | 1195 |  | Jimmy Cox
5246 | 1195 | Future Task |  |  | WP421 | Jarad Hermann |  | Create Penetration Testing Plan/approach | 20 hrs | 62 days | 2024-12-02 | 2025-02-28 | 1194 | 1196SS,1197SS,1198 |  | Jarad Hermann,Bryan Sohayda
5247 | 1196 | Future Task |  |  | WP421 | Jarad Hermann |  | Identify resources for Penetration Testing | 20 hrs | 62 days | 2024-12-02 | 2025-02-28 | 1195SS | 1198 |  | Jarad Hermann,Bryan Sohayda
5248 | 1197 | Future Task |  |  | WP421 | Jarad Hermann |  | Define Penetration Testing entry and exit criteria | 20 hrs | 62 days | 2024-12-02 | 2025-02-28 | 1195SS | 1198 |  | Jarad Hermann,Bryan Sohayda
5190 | 1198 | Future Task |  |  | WP421 | Jarad Hermann | Submit | WP WP421 - Penetration Testing Plan - Submit | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 119711951196 | 1199 |  | Joy Schneider,Jarad Hermann
5191 | 1199 | Future Task |  |  | WP421 | Jarad Hermann | Review | WP WP421 - Penetration Testing Plan - Collaborative Review & Update | 16 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1198 | 1200 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5192 | 1200 | Future Task |  |  | WP421 | Jarad Hermann | Review | WP WP421 - Penetration Testing Plan - Final Review & Edits | 16 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1199 | 1201 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5193 | 1201 | Future Task |  |  | WP421 | Jarad Hermann | Approve | WP WP421 - Penetration Testing Plan - Approve | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 1200 | 947FS+29 days | 2025-02-01 | Jimmy Cox
5194 | 1202 | Future Task |  |  | WP422 | Jarad Hermann |  | WP422 - Disaster Recovery Test Scripts | 128 hrs | 76 days | 2024-12-03 | 2025-03-21
5195 | 1203 | Future Task |  |  | WP422 | Jarad Hermann | Create | WPED WP422 - Disaster Recovery Test Scripts - Create | 16 hrs | 10 days | 2024-12-03 | 2024-12-16 | 1168SS+42 days | 1204 |  | Jarad Hermann,Mary Punty
5196 | 1204 | Future Task |  |  | WP422 | Jarad Hermann | Submit | WPED WP422 - Disaster Recovery Test Scripts - Submit | 0 hrs | 0 days | 2024-12-16 | 2024-12-16 | 1203 | 1205 |  | Joy Schneider,Jarad Hermann
5197 | 1205 | Future Task |  |  | WP422 | Jarad Hermann | Review | WPED WP422 - Disaster Recovery Test Scripts - Review | 20 hrs | 10 days | 2024-12-17 | 2024-12-31 | 1204 | 1206 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5198 | 1206 | Future Task |  |  | WP422 | Jarad Hermann | Approve | WPED WP422 - Disaster Recovery Test Scripts - Approve | 0 hrs | 0 days | 2024-12-31 | 2024-12-31 | 1205 | 1207 |  | Jimmy Cox
5249 | 1207 | Future Task |  |  | WP422 | Jarad Hermann |  | Finalize Disaster Recovery Test Scripts Inventory | 20 hrs | 41 days | 2025-01-02 | 2025-02-28 | 1206 | 1208SS,1209SS,1210 |  | Jarad Hermann,Bryan Sohayda
5250 | 1208 | Future Task |  |  | WP422 | Jarad Hermann |  | Create, review, and confirm DR Test Script Work Unit Tracker | 20 hrs | 41 days | 2025-01-02 | 2025-02-28 | 1207SS | 1210 |  | Jarad Hermann,Bryan Sohayda
5251 | 1209 | Future Task |  |  | WP422 | Jarad Hermann |  | Create, Review and Confirm Disaster Recovery Test Scripts | 20 hrs | 41 days | 2025-01-02 | 2025-02-28 | 1207SS | 1210 |  | Jarad Hermann,Bryan Sohayda
5199 | 1210 | Future Task |  |  | WP422 | Jarad Hermann | Submit | WP WP422 - Disaster Recovery Test Scripts - Submit | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 120912071208 | 1211 |  | Joy Schneider,Jarad Hermann
5200 | 1211 | Future Task |  |  | WP422 | Jarad Hermann | Review | WP WP422 - Disaster Recovery Test Scripts - Collaborative Review & Update | 16 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1210 | 1212 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5201 | 1212 | Future Task |  |  | WP422 | Jarad Hermann | Review | WP WP422 - Disaster Recovery Test Scripts - Final Review & Edits | 16 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1211 | 1213 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5202 | 1213 | Future Task |  |  | WP422 | Jarad Hermann | Approve | WP WP422 - Disaster Recovery Test Scripts - Approve | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 1212 | 983FS-14 days |  | Jimmy Cox
5203 | 1214 | Future Task |  |  | WP423 | Jarad Hermann |  | WP423 - Performance Test Scripts | 104 hrs | 140 days | 2024-10-30 | 2025-05-21
5204 | 1215 | Future Task |  |  | WP423 | Jarad Hermann | Create | WPED WP423 - Performance Test Scripts - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1177SS | 1216 |  | Jarad Hermann,Mary Punty
5205 | 1216 | Future Task |  |  | WP423 | Jarad Hermann | Submit | WPED WP423 - Performance Test Scripts - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 1215 | 1217 |  | Joy Schneider,Jarad Hermann
5206 | 1217 | Future Task |  |  | WP423 | Jarad Hermann | Review | WPED WP423 - Performance Test Scripts - Review | 20 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1216 | 1218 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5207 | 1218 | Future Task |  |  | WP423 | Jarad Hermann | Approve | WPED WP423 - Performance Test Scripts - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1217 | 1219 |  | Jimmy Cox
5252 | 1219 | Future Task |  |  | WP423 | Jarad Hermann |  | Finalize Performance Test Scripts Inventory | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1218 | 1220SS,1221SS,1222 |  | Jarad Hermann,Bryan Sohayda
5253 | 1220 | Future Task |  |  | WP423 | Jarad Hermann |  | Create, review, and confirm Performance Test Script Work Unit Tracker | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1219SS | 1222 |  | Jarad Hermann,Bryan Sohayda
5254 | 1221 | Future Task |  |  | WP423 | Jarad Hermann |  | Create, Review and Confirm Performance Test Scripts | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1219SS | 1222 |  | Jarad Hermann,Bryan Sohayda
5208 | 1222 | Future Task |  |  | WP423 | Jarad Hermann | Submit | WP WP423 - Performance Test Scripts - Submit | 0 hrs | 0 days | 2025-04-30 | 2025-04-30 | 122112191220 | 1223 |  | Joy Schneider,Jarad Hermann
5209 | 1223 | Future Task |  |  | WP423 | Jarad Hermann | Review | WP WP423 - Performance Test Scripts - Collaborative Review & Update | 4 hrs | 10 days | 2025-05-01 | 2025-05-14 | 1222 | 1224 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5210 | 1224 | Future Task |  |  | WP423 | Jarad Hermann | Review | WP WP423 - Performance Test Scripts - Final Review & Edits | 4 hrs | 5 days | 2025-05-15 | 2025-05-21 | 1223 | 1225 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5211 | 1225 | Future Task |  |  | WP423 | Jarad Hermann | Approve | WP WP423 - Performance Test Scripts - Approve | 0 hrs | 0 days | 2025-05-21 | 2025-05-21 | 1224 | 965FS-14 days |  | Jimmy Cox
5212 | 1226 | Future Task |  |  | WP424 | Jarad Hermann |  | WP424 - Penetration Test Scripts/Scenarios | 108 hrs | 97 days | 2024-10-30 | 2025-03-21
5213 | 1227 | Future Task |  |  | WP424 | Jarad Hermann | Create | WPED WP424 - Penetration Test Scripts/Scenarios - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1191SS | 1228 |  | Jarad Hermann,Mary Punty
5214 | 1228 | Future Task |  |  | WP424 | Jarad Hermann | Submit | WPED WP424 - Penetration Test Scripts/Scenarios - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 1227 | 1229 |  | Joy Schneider,Jarad Hermann
5215 | 1229 | Future Task |  |  | WP424 | Jarad Hermann | Review | WPED WP424 - Penetration Test Scripts/Scenarios - Review | 20 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1228 | 1230 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
5216 | 1230 | Future Task |  |  | WP424 | Jarad Hermann | Approve | WPED WP424 - Penetration Test Scripts/Scenarios - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1229 | 1231 |  | Jimmy Cox
5255 | 1231 | Future Task |  |  | WP424 | Jarad Hermann |  | Finalize Penetration Test Scripts Inventory | 20 hrs | 62 days | 2024-12-02 | 2025-02-28 | 1230 | 1232SS |  | Jarad Hermann,Bryan Sohayda
5256 | 1232 | Future Task |  |  | WP424 | Jarad Hermann |  | Create, review, and confirm Penetration Test Scripts/Scenarios | 20 hrs | 62 days | 2024-12-02 | 2025-02-28 | 1231SS | 1233 |  | Jarad Hermann,Bryan Sohayda
5217 | 1233 | Future Task |  |  | WP424 | Jarad Hermann | Submit | WP WP424 - Penetration Test Scripts/Scenarios - Submit | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 1232 | 1234 |  | Joy Schneider,Jarad Hermann
5218 | 1234 | Future Task |  |  | WP424 | Jarad Hermann | Review | WP WP424 - Penetration Test Scripts/Scenarios - Collaborative Review & Update | 16 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1233 | 1235 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5219 | 1235 | Future Task |  |  | WP424 | Jarad Hermann | Review | WP WP424 - Penetration Test Scripts/Scenarios - Final Review & Edits | 16 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1234 | 1236 |  | Jarad Hermann,Mary Punty,Jimmy Cox,Angie Robertson
5220 | 1236 | Future Task |  |  | WP424 | Jarad Hermann | Approve | WP WP424 - Penetration Test Scripts/Scenarios - Approve | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 1235 | 947FS+29 days |  | Jimmy Cox
5299 | 1237 | Future Task |  |  | I-WP127 | Angie Robertson |  | I-WP127 - User Acceptance Testing Plan | 61 hrs | 77 days | 2024-08-05 | 2024-11-21
5300 | 1238 | Future Task |  |  | I-WP127 | Angie Robertson | Create | WPED - I-WP127 - User Acceptance Testing Plan - Create | 4 hrs | 10 days | 2024-08-05 | 2024-08-16 | 1 | 1239 |  | Angie Robertson,Jimmy Cox
5301 | 1239 | Future Task |  |  | I-WP127 | Angie Robertson | Submit | WPED - I-WP127 - User Acceptance Testing Plan - Submit | 0 hrs | 0 days | 2024-08-16 | 2024-08-16 | 1238 | 1240 |  | Angie Robertson
5302 | 1240 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WPED - I-WP127 - User Acceptance Testing Plan - Collaborative Review and Update | 17 hrs | 10 days | 2024-08-19 | 2024-08-30 | 1239 | 1241 |  | Carolyn Hicks,Angie Robertson,Matthew Breeding,Jennifer Reeves,Deana Metcalf,Julian Gotreaux,Tommy Werner,Matt Cole,Mary Punty,Stacey Terry
5303 | 1241 | Future Task |  |  | I-WP127 | Angie Robertson | Approve | WPED - I-WP127 - User Acceptance Testing Plan - Approve | 0 hrs | 0 days | 2024-08-30 | 2024-08-30 | 1240 | 1242 |  | Jimmy Cox
5310 | 1242 | Future Task |  |  | I-WP127 | Angie Robertson |  | Create User Acceptance Plan | 10 hrs | 40 days | 2024-09-03 | 2024-10-28 | 1241 | 1243 |  | Matthew Breeding,Jennifer Reeves,Carolyn Hicks,Deana Metcalf,Angie Robertson
5304 | 1243 | Future Task |  |  | I-WP127 | Angie Robertson | Submit | I-WP127 - User Acceptance Testing Plan - Submit | 0 hrs | 0 days | 2024-10-28 | 2024-10-28 | 1242 | 1244 |  | Matthew Breeding
5305 | 1244 | Future Task |  |  | I-WP127 | Angie Robertson | Review | I-WP127 - User Acceptance Testing Plan - Dept QC | 8 hrs | 1 day | 2024-10-29 | 2024-10-29 | 1243 | 1245 |  | Gabriela Gibson
5306 | 1245 | Future Task |  |  | I-WP127 | Angie Robertson | Review | I-WP127 - User Acceptance Testing Plan - Collaborative Review and Update | 10 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1244 | 1246 |  | Matthew Breeding,Jennifer Reeves,Carolyn Hicks,Deana Metcalf,Angie Robertson
5307 | 1246 | Future Task |  |  | I-WP127 | Angie Robertson | Review | I-WP127 - User Acceptance Testing Plan - Style Guide Review | 2 hrs | 1 day | 2024-11-14 | 2024-11-14 | 1245 | 1247 |  | Tatiana Eubanks
5308 | 1247 | Future Task |  |  | I-WP127 | Angie Robertson | Review | I-WP127 - User Acceptance Testing Plan - Final Review and Update | 10 hrs | 5 days | 2024-11-15 | 2024-11-21 | 1246 | 1248 |  | Angie Robertson,Jimmy Cox
5309 | 1248 | Future Task |  |  | I-WP127 | Angie Robertson | Approve | I-WP127 - User Acceptance Testing Plan - Approve | 0 hrs | 0 days | 2024-11-21 | 2024-11-21 | 1247 | 1250,566FS+46 days,585 |  | Jimmy Cox
3967 | 1249 | Future Task | [5 empty] | UAT | 1 hr | 163 days | 2025-04-01 | 2025-11-19
4002 | 1250 | Future Task |  |  | UAT | Matt Breeding |  | UAT Testing | 1 hr | 163 days | 2025-04-01 | 2025-11-19 | 17075691248 | 1738,1791SS+30 days |  | Jimmy Cox,Angie Robertson
3772 | 1251 | Future Task | [5 empty] | Deploy | 1,806 hrs | 548 days | 2023-12-01 | 2026-02-04
7156 | 1252 | Future Task | Yes |  | SG5 | Jimmy Cox | Milestone | Stage Gate 5: Deployment Readiness | 0 hrs | 0 days | 2025-12-12 | 2025-12-12 | 7.2078e+32 |  | December 17, 2025 - ESC | Jimmy Cox,Angie Robertson,Matt Cole | This should be December 17, 2025 per the SOW. The Resource Names include the ESC and we need tasks / dates for ESC review prior to milestone date. Per conversations the week of 5/30, we will baseline the SGs at their actual date or the last business day in the month. We will then update to start as soon as possible, which will allow us to see date shifts based on predecessor and successor links. | Angie
7157 | 1253 | Future Task | Yes |  | SG6 | Jimmy Cox | Milestone | Stage Gate 6: Confirm Deployment | 0 hrs | 0 days | 2025-12-19 | 2025-12-19 | 137313881339 | 1254 | 2025-12-30 | Jimmy Cox,Angie Robertson,Matt Cole | This should be December 30, 2025 per the SOW. Per conversations the week of 5/30, we will baseline the SGs at their actual date or the last business day in the month. We will then update to start as soon as possible, which will allow us to see date shifts based on predecessor and successor links. | Angie
7158 | 1254 | Future Task | Yes |  | SG7 | Jimmy Cox | Milestone | Stage Gate 7: Go-Live | 0 hrs | 0 days | 2025-12-19 | 2025-12-19 | 1253 |  | Janaury 6, 2026 | Jimmy Cox,Angie Robertson,Matt Cole | This should be January 6, 2026 per the SOW. The Resource Names include the ESC and we need tasks / dates for ESC review prior to milestone date. Per conversations the week of 5/30, we will baseline the SGs at their actual date or the last business day in the month. We will then update to start as soon as possible, which will allow us to see date shifts based on predecessor and successor links. | Angie
5311 | 1255 | Future Task |  |  | D645 | Mary Punty |  | D645 - Updated Deployment Strategy | 265 hrs | 105 days | 2023-12-01 | 2024-04-30
5312 | 1256 | Future Task |  |  | D645 | Mary Punty | Create | DED D645 - Updated Deployment Strategy - Create | 16 hrs | 10 days | 2023-12-01 | 2023-12-14 | 1 | 1257 |  | Mary Punty,Bryan Sohayda
5313 | 1257 | Future Task |  |  | D645 | Mary Punty | Submit | DED D645 - Updated Deployment Strategy - Submit | 0 hrs | 0 days | 2023-12-14 | 2023-12-14 | 1256 | 1258 |  | Mary Punty,Joy Schneider
5314 | 1258 | Future Task |  |  | D645 | Mary Punty | Review | DED D645 - Updated Deployment Strategy - Collaborative Review | 20 hrs | 10 days | 2023-12-15 | 2023-12-29 | 1257 | 1259 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5315 | 1259 | Future Task |  |  | D645 | Mary Punty | Approve | DED D645 - Updated Deployment Strategy - Approve | 0 hrs | 0 days | 2023-12-29 | 2023-12-29 | 1258 | 1260 |  | Jimmy Cox
5339 | 1260 | Future Task |  |  | D645 | Mary Punty |  | Document assumptions about deployment | 20 hrs | 9 days | 2024-01-02 | 2024-01-12 | 1259 | 1261 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5340 | 1261 | Future Task |  |  | D645 | Mary Punty |  | Create Deployment Kickoff Presentation | 20 hrs | 9 days | 2024-01-16 | 2024-01-26 | 1260 | 1262 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5341 | 1262 | Future Task |  |  | D645 | Mary Punty |  | Review Deployment Kickoff Presentation | 20 hrs | 5 days | 2024-01-29 | 2024-02-02 | 1261 | 1263 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5342 | 1263 | Future Task |  |  | D645 | Mary Punty |  | Describe Deployment Calendar | 20 hrs | 10 days | 2024-02-05 | 2024-02-16 | 1262 | 1264 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5343 | 1264 | Future Task |  |  | D645 | Mary Punty |  | Review Deployment Calendar | 20 hrs | 5 days | 2024-02-19 | 2024-02-23 | 1263 | 1265 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5344 | 1265 | Future Task |  |  | D645 | Mary Punty |  | Describe Cutover Checklist | 20 hrs | 10 days | 2024-02-26 | 2024-03-08 | 1264 | 1266 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5345 | 1266 | Future Task |  |  | D645 | Mary Punty |  | Review Cutover Checklist | 20 hrs | 10 days | 2024-03-11 | 2024-03-22 | 1265 | 1267 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5346 | 1267 | Future Task |  |  | D645 | Mary Punty |  | Finalize Draft - Deployment Strategy | 20 hrs | 5 days | 2024-03-25 | 2024-03-29 | 1266 | 1268 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5347 | 1268 | Future Task |  |  | D645 | Mary Punty |  | Review Draft - Deployment Strategy | 20 hrs | 5 days | 2024-04-01 | 2024-04-05 | 1267 | 1269 |  | Bryan Sohayda,Mary Punty,Manojkumar Gurjar,Jarad Hermann
5316 | 1269 | Future Task |  |  | D645 | Mary Punty | Submit | DEL D645 - Updated Deployment Strategy - Draft Submission | 0 hrs | 0 days | 2024-04-05 | 2024-04-05 | 1268 | 1270 |  | Mary Punty,Joy Schneider
5317 | 1270 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2024-04-08 | 2024-04-12 | 1269 | 1271 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5318 | 1271 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Style Guide Review | 1 hr | 1 day | 2024-04-15 | 2024-04-15 | 1270 | 1272 |  | Dusti Kincl
5319 | 1272 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Final Collaborative Review | 16 hrs | 5 days | 2024-04-16 | 2024-04-22 | 1271 | 1273 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5320 | 1273 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Accenture QC | 4 hrs | 2 days | 2024-04-23 | 2024-04-24 | 1272 | 1274 |  | Joy Schneider
5321 | 1274 | Future Task |  |  | D645 | Mary Punty | Submit | DEL D645 - Updated Deployment Strategy - Submit | 0 hrs | 0 days | 2024-04-24 | 2024-04-24 | 1273 | 1275 |  | Joy Schneider
5322 | 1275 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Department QC | 4 hrs | 1 day | 2024-04-25 | 2024-04-25 | 1274 | 1276 |  | Tommy Werner,Gabriela Gibson
5323 | 1276 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Contract Manager Review | 8 hrs | 3 days | 2024-04-26 | 2024-04-30 | 1275 | 12771279 |  | Sean Buchanan
5324 | 1277 | Future Task |  |  | D645 | Mary Punty | Accept | DEL D645 - Updated Deployment Strategy - Accept | 0 hrs | 0 days | 2024-04-30 | 2024-04-30 | 1276 |  | 2024-04-01 | Sean Buchanan
5325 | 1278 | Future Task | Yes |  | D658 | Mary Punty |  | D658 - Develop the Deployment and Contingency Plan | 498 hrs | 125 days | 2024-09-30 | 2025-03-31 |  |  |  |  | There are lots of "create" tasks already defined below. This seems very detailed considering the DED has not been created or approved. | Angie
5326 | 1279 | Future Task |  |  | D658 | Mary Punty | Create | DED D658 - Develop the Deployment and Contingency Plan - Create | 16 hrs | 10 days | 2024-09-30 | 2024-10-11 | 1276 | 1280 |  | Mary Punty,Bryan Sohayda
5327 | 1280 | Future Task |  |  | D658 | Mary Punty | Submit | DED D658 - Develop the Deployment and Contingency Plan - Submit | 0 hrs | 0 days | 2024-10-11 | 2024-10-11 | 1279 | 1281 |  | Mary Punty,Joy Schneider
5328 | 1281 | Future Task |  |  | D658 | Mary Punty | Review | DED D658 - Develop the Deployment and Contingency Plan - Collaborative Review | 20 hrs | 10 days | 2024-10-14 | 2024-10-25 | 1280 | 1282 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5329 | 1282 | Future Task |  |  | D658 | Mary Punty | Approve | DED D658 - Develop the Deployment and Contingency Plan - Approve | 0 hrs | 0 days | 2024-10-25 | 2024-10-25 | 1281 | 1283 |  | Jimmy Cox
5348 | 1283 | Future Task |  |  | D658 | Mary Punty |  | Create Deployment and Contingency Plan pitch deck | 18 hrs | 9 days | 2024-10-28 | 2024-11-07 | 1282 | 1284 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5349 | 1284 | Future Task |  |  | D658 | Mary Punty |  | Review Deployment and Contingency Plan pitch deck | 40 hrs | 4 days | 2024-11-08 | 2024-11-14 | 1283 | 1285FS+8 days,1289 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5350 | 1285 | Future Task |  |  | D658 | Mary Punty |  | Prepare materials for Dec Sponsor Meeting and Review | 25 hrs | 5 days | 2024-11-27 | 2024-12-05 | 1284FS+8 days | 1286 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5351 | 1286 | Future Task |  |  | D658 | Mary Punty |  | Plan for and hold December Sponsor Meeting | 25 hrs | 5 days | 2024-12-06 | 2024-12-12 | 1285 | 1287FS+11 days |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5352 | 1287 | Future Task |  |  | D658 | Mary Punty |  | Gather Deployment and Contingency Plan materials for January ESC Meeting | 35 hrs | 7 days | 2024-12-31 | 2025-01-09 | 1286FS+11 days | 1288,1293SS |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5353 | 1288 | Future Task |  |  | D658 | Mary Punty |  | Review Deployment and Contingency Plan materials for January ESC Meeting | 25 hrs | 5 days | 2025-01-10 | 2025-01-16 | 1287 | 1297 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5354 | 1289 | Future Task |  |  | D658 | Mary Punty |  | Identify and document deployment and post-implementation support activities | 20 hrs | 8 days | 2024-11-15 | 2024-11-26 | 1284 | 1290 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5355 | 1290 | Future Task |  |  | D658 | Mary Punty |  | Review and document deployment and post-implementation support activities | 25 hrs | 5 days | 2024-11-27 | 2024-12-05 | 1289 | 1291 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5356 | 1291 | Future Task |  |  | D658 | Mary Punty |  | Identify and document timing of cutover activities | 25 hrs | 5 days | 2024-12-06 | 2024-12-12 | 1290 | 1292 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5357 | 1292 | Future Task |  |  | D658 | Mary Punty |  | Review and document timing of cutover activities | 25 hrs | 5 days | 2024-12-13 | 2024-12-19 | 1291 | 1293 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5358 | 1293 | Future Task |  |  | D658 | Mary Punty |  | Identify and document contingency scenarios | 20 hrs | 7 days | 2024-12-31 | 2025-01-09 | 1287SS,1292 | 1294 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5359 | 1294 | Future Task |  |  | D658 | Mary Punty |  | Review contingency scenarios | 25 hrs | 5 days | 2025-01-10 | 2025-01-16 | 1293 | 1295 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5360 | 1295 | Future Task |  |  | D658 | Mary Punty |  | Define and document the approach to revert changes | 20 hrs | 4 days | 2025-01-17 | 2025-01-23 | 1294 | 1296 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5361 | 1296 | Future Task |  |  | D658 | Mary Punty |  | Review the approach to revert changes | 25 hrs | 5 days | 2025-01-24 | 2025-01-30 | 1295 | 1297 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5362 | 1297 | Future Task |  |  | D658 | Mary Punty |  | Gather Deployment and Contingency Plan materials for February ESC Meeting | 25 hrs | 5 days | 2025-01-31 | 2025-02-06 | 12961288 | 1298 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5363 | 1298 | Future Task |  |  | D658 | Mary Punty |  | Review Deployment and Contingency Plan materials for February ESC Meeting | 15 hrs | 3 days | 2025-02-07 | 2025-02-11 | 1297 | 1299FS+12 days |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5364 | 1299 | Future Task |  |  | D658 | Mary Punty |  | Confirm approach to Deployment and Contingency | 20 hrs | 5 days | 2025-02-28 | 2025-03-06 | 1298FS+12 days | 1300 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Tim Elmer,Jarad Hermann
5330 | 1300 | Future Task |  |  | D658 | Mary Punty | Submit | DEL D658 - Develop the Deployment and Contingency Plan - Draft Submission | 0 hrs | 0 days | 2025-03-06 | 2025-03-06 | 1299 | 1301 |  | Mary Punty,Joy Schneider
5331 | 1301 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2025-03-07 | 2025-03-13 | 1300 | 1302 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5332 | 1302 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Style Guide Review | 1 hr | 1 day | 2025-03-14 | 2025-03-14 | 1301 | 1303 |  | Dusti Kincl
5333 | 1303 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Final Collaborative Review | 16 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1302 | 1304 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5334 | 1304 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Accenture QC | 4 hrs | 2 days | 2025-03-24 | 2025-03-25 | 1303 | 1305 |  | Joy Schneider
5335 | 1305 | Future Task |  |  | D658 | Mary Punty | Submit | DEL D658 - Develop the Deployment and Contingency Plan - Submit | 0 hrs | 0 days | 2025-03-25 | 2025-03-25 | 1304 | 1306 |  | Joy Schneider
5336 | 1306 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Department QC | 4 hrs | 1 day | 2025-03-26 | 2025-03-26 | 1305 | 1307 |  | Tommy Werner,Gabriela Gibson
5337 | 1307 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Contract Manager Review | 8 hrs | 3 days | 2025-03-27 | 2025-03-31 | 1306 | 1308 |  | Sean Buchanan
5338 | 1308 | Future Task |  |  | D658 | Mary Punty | Accept | DEL D658 - Develop the Deployment and Contingency Plan - Accept | 0 hrs | 0 days | 2025-03-31 | 2025-03-31 | 1307 | 1252 | 2025-03-01 | Sean Buchanan
5365 | 1309 | Future Task | Yes |  | D678 | Bryan Sohayda |  | D678 - Final Known Issues & Enhancements Lists | 350 hrs | 65 days | 2025-09-03 | 2025-12-05
5366 | 1310 | Future Task |  |  | D678 | Bryan Sohayda | Create | DED D678 - Final Known Issues & Enhancements Lists - Create | 16 hrs | 10 days | 2025-09-03 | 2025-09-16 | 1 | 1311 |  | Mary Punty,Bryan Sohayda
5367 | 1311 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DED D678 - Final Known Issues & Enhancements Lists - Submit | 0 hrs | 0 days | 2025-09-16 | 2025-09-16 | 1310 | 1312 |  | Bryan Sohayda,Joy Schneider
5368 | 1312 | Future Task |  |  | D678 | Bryan Sohayda | Review | DED D678 - Final Known Issues & Enhancements Lists - Collaborative Review | 20 hrs | 10 days | 2025-09-17 | 2025-09-30 | 1311 | 1313 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5369 | 1313 | Future Task |  |  | D678 | Bryan Sohayda | Approve | DED D678 - Final Known Issues & Enhancements Lists - Approve | 0 hrs | 0 days | 2025-09-30 | 2025-09-30 | 1312 | 1314 |  | Jimmy Cox
5393 | 1314 | Future Task |  |  | D678 | Bryan Sohayda |  | Initial Known Issues & Enhancements Lists | 20 hrs | 22 days | 2025-10-01 | 2025-10-30 | 1313 | 1315SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5394 | 1315 | Future Task |  |  | D678 | Bryan Sohayda |  | Review Open SIRs - Candidates for Known Issues List | 25 hrs | 5 days | 2025-10-01 | 2025-10-07 | 1314SS | 1316,1317SS |  | Bryan Sohayda,Mary Punty,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5395 | 1316 | Future Task |  |  | D678 | Bryan Sohayda |  | Finalize Open SIRs - Candidates for Known Issues List | 24 hrs | 4 days | 2025-10-08 | 2025-10-13 | 1315 | 1318SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5396 | 1317 | Future Task |  |  | D678 | Bryan Sohayda |  | Review Open SIRs - Candidates for Known Enhancements List | 30 hrs | 5 days | 2025-10-01 | 2025-10-07 | 1315SS | 1319 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5397 | 1318 | Future Task |  |  | D678 | Bryan Sohayda |  | Finalize Open SIRs - Candidates for Known Enhancements List | 20 hrs | 4 days | 2025-10-08 | 2025-10-13 | 1316SS | 1319 |  | Bryan Sohayda,Mary Punty,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5398 | 1319 | Future Task |  |  | D678 | Bryan Sohayda |  | Confirm Agreed Upon Known Issues | 30 hrs | 5 days | 2025-10-14 | 2025-10-20 | 13181317 | 1320SS,1321SS |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5399 | 1320 | Future Task |  |  | D678 | Bryan Sohayda |  | Confirm Agreed Upon Known Enhancements | 30 hrs | 5 days | 2025-10-14 | 2025-10-20 | 1319SS | 1323 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5400 | 1321 | Future Task |  |  | D678 | Bryan Sohayda |  | Create DEL Draft - Wrapper Document and Known Issues/Enhancements Lists | 20 hrs | 5 days | 2025-10-14 | 2025-10-20 | 1319SS | 1322 |  | Bryan Sohayda,Mary Punty
5401 | 1322 | Future Task |  |  | D678 | Bryan Sohayda |  | Review DEL Draft - Wrapper Document and Known Issues/Enhancements Lists | 48 hrs | 8 days | 2025-10-21 | 2025-10-30 | 1321 | 1323 |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5370 | 1323 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DEL D678 - Final Known Issues & Enhancements Lists - Draft Submission | 0 hrs | 0 days | 2025-10-30 | 2025-10-30 | 13221320 | 1324 |  | Bryan Sohayda,Joy Schneider
5371 | 1324 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2025-10-31 | 2025-11-06 | 1323 | 1325 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5372 | 1325 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Style Guide Review | 1 hr | 1 day | 2025-11-07 | 2025-11-07 | 1324 | 1326 |  | Dusti Kincl
5373 | 1326 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Final Collaborative Review | 16 hrs | 5 days | 2025-11-10 | 2025-11-17 | 1325 | 1327 |  | Mary Punty,Bryan Sohayda,Jimmy Cox,Angie Robertson
5374 | 1327 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Accenture QC | 4 hrs | 2 days | 2025-11-18 | 2025-11-19 | 1326 | 1328 |  | Joy Schneider
5375 | 1328 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DEL D678 - Final Known Issues & Enhancements Lists - Submit | 0 hrs | 0 days | 2025-11-19 | 2025-11-19 | 1327 | 1329 |  | Joy Schneider
5376 | 1329 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Department QC | 4 hrs | 1 day | 2025-11-20 | 2025-11-20 | 1328 | 1330 |  | Tommy Werner,Gabriela Gibson
5377 | 1330 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Contract Manager Review | 8 hrs | 3 days | 2025-11-21 | 2025-11-25 | 1329 | 1331 |  | Sean Buchanan
5378 | 1331 | Future Task |  |  | D678 | Bryan Sohayda | Accept | DEL D678 - Final Known Issues & Enhancements Lists - Accept | 0 hrs | 0 days | 2025-11-25 | 2025-11-25 | 1330 | 1332FS+1 day,1252 | 2025-12-01 | Sean Buchanan
5407 | 1332 | Future Task |  |  | D678 | Bryan Sohayda |  | Refresh Known Issues/Enhancements List to Prep for Stage Gate 5 | 18 hrs | 5 days | 2025-12-01 | 2025-12-05 | 1331FS+1 day |  |  | Bryan Sohayda,Mary Punty,Shelley McCabe,Stacey Terry,Yogesh Deshmukh,Tim Elmer
5379 | 1333 | Future Task | Maybe |  | D679 | Stacey Terry |  | D679 - Go-Live of Financials and Payroll Waves | 169 hrs | 60 days | 2025-11-05 | 2026-02-04
5380 | 1334 | Future Task |  |  | D679 | Stacey Terry | Create | DED D679 - Go-Live of Financials and Payroll Waves - Create | 16 hrs | 10 days | 2025-11-05 | 2025-11-19 | 1 | 1335 |  | Stacey Terry,Manojkumar Gurjar
5381 | 1335 | Future Task |  |  | D679 | Stacey Terry | Submit | DED D679 - Go-Live of Financials and Payroll Waves - Submit | 0 hrs | 0 days | 2025-11-19 | 2025-11-19 | 1334 | 1336 |  | Stacey Terry,Joy Schneider
5382 | 1336 | Future Task |  |  | D679 | Stacey Terry | Review | DED D679 - Go-Live of Financials and Payroll Waves - Collaborative Review | 28 hrs | 10 days | 2025-11-20 | 2025-12-05 | 1335 | 1337 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson,Sean Buchanan
5383 | 1337 | Future Task |  |  | D679 | Stacey Terry | Approve | DED D679 - Go-Live of Financials and Payroll Waves - Approve | 0 hrs | 0 days | 2025-12-05 | 2025-12-05 | 1336 | 1338 |  | Jimmy Cox
5403 | 1338 | Future Task |  |  | D679 | Stacey Terry |  | Go-Live of Financials and Payroll Waves | 15 hrs | 5 days | 2025-12-08 | 2025-12-12 | 1337 | 1339 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5404 | 1339 | Future Task |  |  | D679 | Stacey Terry |  | Document Go-Live Applications Listing | 15 hrs | 5 days | 2025-12-15 | 2025-12-19 | 1338 | 1340FS+8 days,1253 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5405 | 1340 | Future Task |  |  | D679 | Stacey Terry |  | Document Go-Live Tasks completed | 15 hrs | 5 days | 2026-01-05 | 2026-01-09 | 1339FS+8 days | 1341SS |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5406 | 1341 | Future Task |  |  | D679 | Stacey Terry |  | Document Go-List of Agencies Participated | 15 hrs | 5 days | 2026-01-05 | 2026-01-09 | 1340SS | 1342 |  | Stacey Terry,Manojkumar Gurjar,Bryan Sohayda,Kurt Meisner,Mary Punty
5384 | 1342 | Future Task |  |  | D679 | Stacey Terry | Submit | DEL D679 - Go-Live of Financials and Payroll Waves - Draft Submission | 0 hrs | 0 days | 2026-01-09 | 2026-01-09 | 1341 | 1343 |  | Stacey Terry,Joy Schneider
5385 | 1343 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Pre-Submission Collaborative Review | 24 hrs | 5 days | 2026-01-12 | 2026-01-16 | 1342 | 1344 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5386 | 1344 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Style Guide Review | 1 hr | 1 day | 2026-01-20 | 2026-01-20 | 1343 | 1345 |  | Dusti Kincl
5387 | 1345 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Final Collaborative Review | 24 hrs | 5 days | 2026-01-21 | 2026-01-27 | 1344 | 1346 |  | Stacey Terry,Manojkumar Gurjar,Deana Metcalf,Matthew Breeding,Jimmy Cox,Angie Robertson
5388 | 1346 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Accenture QC | 4 hrs | 2 days | 2026-01-28 | 2026-01-29 | 1345 | 1347 |  | Joy Schneider
5389 | 1347 | Future Task |  |  | D679 | Stacey Terry | Submit | DEL D679 - Go-Live of Financials and Payroll Waves - Submit | 0 hrs | 0 days | 2026-01-29 | 2026-01-29 | 1346 | 1348 |  | Joy Schneider
5390 | 1348 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Department QC | 4 hrs | 1 day | 2026-01-30 | 2026-01-30 | 1347 | 1349 |  | Tommy Werner,Gabriela Gibson
5391 | 1349 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Contract Manager Review | 8 hrs | 3 days | 2026-02-02 | 2026-02-04 | 1348 | 1350 |  | Sean Buchanan
5392 | 1350 | Future Task |  |  | D679 | Stacey Terry | Accept | DEL D679 - Go-Live of Financials and Payroll Waves - Accept | 0 hrs | 0 days | 2026-02-04 | 2026-02-04 | 1349 |  | 2026-01-01 | Sean Buchanan
6739 | 1351 | Future Task |  |  | WP425 | Bryan Sohayda |  | WP425 - Production Support Operations Plan | 356 hrs | 107 days | 2024-11-14 | 2025-04-18
6740 | 1352 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WPED WP425 - Production Support Operations Plan - Create | 8 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1 | 1353 |  | Bryan Sohayda
6741 | 1353 | Future Task |  |  | WP425 | Bryan Sohayda | Submit | WPED WP425 - Production Support Operations Plan - Submit | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1352 | 1354 |  | Joy Schneider,Bryan Sohayda
6742 | 1354 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WPED WP425 - Production Support Operations Plan - Review | 16 hrs | 10 days | 2024-12-02 | 2024-12-13 | 1353 | 1355 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
6743 | 1355 | Future Task |  |  | WP425 | Bryan Sohayda | Approve | WPED WP425 - Production Support Operations Plan - Approve | 0 hrs | 0 days | 2024-12-13 | 2024-12-13 | 1354 | 1356 |  | Jimmy Cox
6744 | 1356 | Future Task |  |  | WP425 | Bryan Sohayda |  | Update Production Support Operations Plan | 20 hrs | 72 days | 2024-12-16 | 2025-03-28 | 1355 | 1357SS |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6745 | 1357 | Future Task |  |  | WP425 | Bryan Sohayda |  | Introduction, Overview, Collab taken with partners, team R&R | 20 hrs | 5 days | 2024-12-16 | 2024-12-20 | 1356SS | 1358FS+8 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6746 | 1358 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document Production Support services provided | 20 hrs | 5 days | 2025-01-06 | 2025-01-10 | 1357FS+8 days | 1359 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6747 | 1359 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review and provide feedback on Production Support Services Provided draft | 20 hrs | 5 days | 2025-01-13 | 2025-01-17 | 1358 | 1360 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6748 | 1360 | Future Task |  |  | WP425 | Bryan Sohayda |  | Create Maintenance Calendar template | 48 hrs | 4 days | 2025-01-21 | 2025-01-24 | 1359 | 1361 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6749 | 1361 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review Maintenance Calendar template | 20 hrs | 5 days | 2025-01-27 | 2025-01-31 | 1360 | 1362 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6750 | 1362 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document production support business processes and tools list | 20 hrs | 5 days | 2025-02-03 | 2025-02-07 | 1361 | 1363 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6751 | 1363 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review and provide feedback on Production Support business processes and tools list draft | 20 hrs | 5 days | 2025-02-10 | 2025-02-14 | 1362 | 1364 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6752 | 1364 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document production support schedule of activities | 20 hrs | 5 days | 2025-02-17 | 2025-02-21 | 1363 | 1365 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6753 | 1365 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review and provide feedback on Production Support schedule of activities draft | 20 hrs | 5 days | 2025-02-24 | 2025-02-28 | 1364 | 1366 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6754 | 1366 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document production support performance expectations | 20 hrs | 5 days | 2025-03-03 | 2025-03-07 | 1365 | 1367 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6755 | 1367 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review and provide feedback on Production Support performance expectations draft | 20 hrs | 5 days | 2025-03-10 | 2025-03-14 | 1366 | 1368 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6756 | 1368 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document production support team roles, responsibilities, and staffing | 20 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1367 | 1369 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6757 | 1369 | Future Task |  |  | WP425 | Bryan Sohayda |  | Full walkthrough of Production Support Operations Plan through facilitated meetings | 20 hrs | 5 days | 2025-03-24 | 2025-03-28 | 1368 | 1370 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6758 | 1370 | Future Task |  |  | WP425 | Bryan Sohayda | Submit | WP WP425 - Production Support Operations Plan - Submit | 0 hrs | 0 days | 2025-03-28 | 2025-03-28 | 1369 | 1371 |  | Joy Schneider,Bryan Sohayda
6759 | 1371 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WP WP425 - Production Support Operations Plan - Collaborative Review & Update | 12 hrs | 10 days | 2025-03-31 | 2025-04-11 | 1370 | 1372 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6760 | 1372 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WP WP425 - Production Support Operations Plan - Final Review & Edits | 12 hrs | 5 days | 2025-04-14 | 2025-04-18 | 1371 | 1373 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6761 | 1373 | Future Task |  |  | WP425 | Bryan Sohayda | Approve | WP WP425 - Production Support Operations Plan - Approve | 0 hrs | 0 days | 2025-04-18 | 2025-04-18 | 1372 | 1253 | 2025-04-01 | Jimmy Cox
6762 | 1374 | Future Task |  |  | WP427 | Bryan Sohayda |  | WP427 - Production Support Application Configuration Management Plan | 168 hrs | 85 days | 2025-01-03 | 2025-05-02
6763 | 1375 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WPED WP427 - Production Support Application Configuration Management Plan - Create | 8 hrs | 10 days | 2025-01-03 | 2025-01-16 | 1 | 1376 |  | Bryan Sohayda
6764 | 1376 | Future Task |  |  | WP427 | Bryan Sohayda | Submit | WPED WP427 - Production Support Application Configuration Management Plan - Submit | 0 hrs | 0 days | 2025-01-16 | 2025-01-16 | 1375 | 1377 |  | Joy Schneider,Bryan Sohayda
6765 | 1377 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WPED WP427 - Production Support Application Configuration Management Plan - Review | 16 hrs | 10 days | 2025-01-17 | 2025-01-31 | 1376 | 1378 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
6766 | 1378 | Future Task |  |  | WP427 | Bryan Sohayda | Approve | WPED WP427 - Production Support Application Configuration Management Plan - Approve | 0 hrs | 0 days | 2025-01-31 | 2025-01-31 | 1377 | 1379 |  | Jimmy Cox
6767 | 1379 | Future Task |  |  | WP427 | Bryan Sohayda |  | Updated Configuration Management Processes for Release and Maintenance | 20 hrs | 50 days | 2025-02-03 | 2025-04-11 | 1378 | 1380SS,1385,1381SS+10 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6768 | 1380 | Future Task |  |  | WP427 | Bryan Sohayda |  | Define and Document Application Configuration Management Processes for Release and Maintenance | 20 hrs | 10 days | 2025-02-03 | 2025-02-14 | 1379SS | 1381 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6769 | 1381 | Future Task |  |  | WP427 | Bryan Sohayda |  | Review and confirm Application and Infrastructure Configuration Management Processes for Release and Maintenance | 20 hrs | 5 days | 2025-02-17 | 2025-02-21 | 1379SS+10 days,1380 | 1382 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6770 | 1382 | Future Task |  |  | WP427 | Bryan Sohayda |  | Define and document System Configuration Control Process Steps and Diagram | 20 hrs | 5 days | 2025-02-24 | 2025-02-28 | 1381 | 1383 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6771 | 1383 | Future Task |  |  | WP427 | Bryan Sohayda |  | Review System Configuration Control Process Steps and Diagram | 20 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1382 | 1384FS+10 days |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6772 | 1384 | Future Task |  |  | WP427 | Bryan Sohayda |  | Full draft review pre-submission | 20 hrs | 10 days | 2025-03-31 | 2025-04-11 | 1383FS+10 days | 1385 |  | Bryan Sohayda,Chetna Dewan,Jarad Hermann
6773 | 1385 | Future Task |  |  | WP427 | Bryan Sohayda | Submit | WP WP427 - Production Support Application Configuration Management Plan - Submit | 0 hrs | 0 days | 2025-04-11 | 2025-04-11 | 13791384 | 1386 |  | Joy Schneider,Bryan Sohayda
6774 | 1386 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WP WP427 - Production Support Application Configuration Management Plan - Collaborative Review & Update | 12 hrs | 10 days | 2025-04-14 | 2025-04-25 | 1385 | 1387 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6775 | 1387 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WP WP427 - Production Support Application Configuration Management Plan - Final Review & Edits | 12 hrs | 5 days | 2025-04-28 | 2025-05-02 | 1386 | 1388 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
6776 | 1388 | Future Task |  |  | WP427 | Bryan Sohayda | Approve | WP WP427 - Production Support Application Configuration Management Plan - Approve | 0 hrs | 0 days | 2025-05-02 | 2025-05-02 | 1387 | 1253 | 2025-04-01 | Jimmy Cox
2953 | 1389 | Late | [5 empty] | Stakeholder Engagement | 3,213 hrs | 936 days | 2023-05-08 | 2027-01-26
2972 | 1390 | Late | [5 empty] | Training | 2,336 hrs | 928 days | 2023-05-18 | 2027-01-26
6906 | 1391 | Late |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Data Inventory for Financials and Payroll Wave | 105 hrs | 277 days | 2023-05-18 | 2024-06-21
6907 | 1392 | Late |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Data Inventory for Financials and Payroll Wave | 22 hrs | 277 days | 2023-05-18 | 2024-06-21
6908 | 1393 | Late |  |  | I-WP102 | Jennifer Reeves | Create | WPED - I-WP102 Data Inventory for Financials and Payroll Wave - Create | 2 hrs | 10 days | 2023-05-18 | 2023-06-01 | 1 | 1394 |  | Jennifer Grant,Jennifer Reeves
6909 | 1394 | Future Task |  |  | I-WP102 | Jennifer Reeves | Submit | WPED - I-WP102 Data Inventory for Financials and Payroll Wave - Submit | 0 hrs | 0 days | 2023-06-01 | 2023-06-01 | 1393 | 1395 |  | Jennifer Grant,Jennifer Reeves
6910 | 1395 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WPED - I-WP102 Data Inventory for Financials and Payroll Wave - Collaborative Review and Update | 8 hrs | 10 days | 2023-06-02 | 2023-06-15 | 1394 | 1396 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Reeves,Jennifer Grant
6911 | 1396 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | WPED - I-WP102 Data Inventory for Financials and Payroll Wave - Approve | 0 hrs | 0 days | 2023-06-15 | 2023-06-15 | 1395 | 1405 |  | Jimmy Cox
6912 | 1397 | Future Task |  |  | I-WP102 | Jennifer Reeves | Milestone | WP - IWP102 Data Inventory for Financials and Payroll Wave - Submit | 0 hrs | 0 days | 2024-05-29 | 2024-05-29 | 1436 | 1398 |  | Jennifer Grant,Jennifer Reeves | Why is this task a Milestone? | Angie
6913 | 1398 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP - IWP102 Data Inventory for Financials and Payroll Wave - Dept QC | 2 hrs | 1 day | 2024-05-30 | 2024-05-30 | 1397 | 1399 |  | Gabriela Gibson
6914 | 1399 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP - IWP102 Data Inventory for Financials and Payroll Wave - Collaborative Review and Update | 7 hrs | 10 days | 2024-05-31 | 2024-06-13 | 1398 | 1400 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Nikki Klein,Daylin Reyes,Angie Robertson
6915 | 1400 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP - IWP102 Data Inventory for Financials and Payroll Wave - Style Guide Review | 1 hr | 1 day | 2024-06-14 | 2024-06-14 | 1399 | 1401 |  | Tatiana Eubanks
6916 | 1401 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP - IWP102 Data Inventory for Financials and Payroll Wave - Final Review and Update | 2 hrs | 5 days | 2024-06-17 | 2024-06-21 | 1400 | 1402 |  | Angie Robertson,Jimmy Cox
6917 | 1402 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | WP - IWP102 Data Inventory for Financials and Payroll Wave - Approve | 0 hrs | 0 days | 2024-06-21 | 2024-06-21 | 1401 |  |  | Jimmy Cox
6918 | 1403 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | Data Inventory for Financials and Payroll Wave | 83 hrs | 245 days | 2023-06-16 | 2024-06-05
6919 | 1404 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 1 - Data | 20 hrs | 45 days | 2023-06-16 | 2023-08-18
6920 | 1405 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create - Data Inventory Format | 7 hrs | 5 days | 2023-06-16 | 2023-06-22 | 1396 | 1406 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Nikki Klein,Daylin Reyes,Angie Robertson
6921 | 1406 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory Format | 5 hrs | 5 days | 2023-06-23 | 2023-06-29 | 1405 | 1407 |  | Jennifer Reeves,Matthew Breeding,Carolyn Hicks,Daylin Reyes,Angie Robertson
6922 | 1407 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory Format | 1 hr | 5 days | 2023-06-30 | 2023-07-07 | 1406 | 1408 |  | Jimmy Cox
6923 | 1408 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | 2023-07-10 | 2023-07-28 | 1407 | 1409 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6924 | 1409 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 15 days | 2023-07-31 | 2023-08-18 | 1408 |  |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes | Successor UID-6926 | TW
6925 | 1410 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 2 - Data | 7 hrs | 20 days | 2023-10-09 | 2023-11-03
6926 | 1411 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | 2023-10-09 | 2023-10-27 | 57SS | 1412 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6927 | 1412 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 5 days | 2023-10-30 | 2023-11-03 | 1411 |  |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes | Successor UID-6929 | TW
6928 | 1413 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 3 - Data | 13 hrs | 25 days | 2024-01-11 | 2024-02-15
6929 | 1414 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | 2024-01-11 | 2024-02-01 | 1 | 14151421 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves | Change Predecessor to 4336ss (Remove 1, and keep UID-6927) | TW
6930 | 1415 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 5 days | 2024-02-02 | 2024-02-08 | 1414 | 14161422 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6931 | 1416 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Functional Teams | 6 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1415 | 1418 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6932 | 1417 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Update & Publish Data Inventory | 18 hrs | 25 days | 2024-02-02 | 2024-03-07
6933 | 1418 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 5 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1416 | 1419 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6934 | 1419 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory | 1 hr | 5 days | 2024-02-23 | 2024-02-29 | 1418 | 1420 |  | Jimmy Cox
6935 | 1420 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Coordinate Knowledge Base Update | 2 hrs | 5 days | 2024-03-01 | 2024-03-07 | 1419 |  |  | Jennifer Reeves,Daylin Reyes | Successor UID-6948 | TW
6936 | 1421 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create Communication for Data Inventory | 2 hrs | 5 days | 2024-02-02 | 2024-02-08 | 1414 |  |  | Jennifer Grant,Jennifer Reeves | Successor UID-6937 | TW
6937 | 1422 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review for Communication for Data Inventory | 2 hrs | 9 days | 2024-02-09 | 2024-02-21 | 1415 | 1423 |  | Dusti Kincl,Angie Robertson
6938 | 1423 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Communication | 1 hr | 5 days | 2024-02-22 | 2024-02-28 | 1422 | 1424 |  | Jimmy Cox
6939 | 1424 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Publish Data Inventory | 4 hrs | 2 days | 2024-02-29 | 2024-03-01 | 1423 | 1425 |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6940 | 1425 | Future Task |  | RW-Communication | I-WP102 | Jennifer Reeves | Create | I-WP102 Share - Communication for Data Inventory | 1 hr | 2 days | 2024-03-04 | 2024-03-05 | 1424 |  |  | Dusti Kincl | Successor UID-6942 | TW
6941 | 1426 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 4 - Data | 11 hrs | 25 days | 2024-04-10 | 2024-05-14
6942 | 1427 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 3 hrs | 15 days | 2024-04-10 | 2024-04-30 | 1 | 14281434 |  | Jennifer Reeves,Pradeep Koul,Tanya McCarty | Remove Predecessor 1 | TW
6943 | 1428 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 2 hrs | 5 days | 2024-05-01 | 2024-05-07 | 1427 | 1429 |  | Jennifer Reeves,Matthew Breeding
6944 | 1429 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 6 hrs | 5 days | 2024-05-08 | 2024-05-14 | 1428 | 1431 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6945 | 1430 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Update & Publish Data Inventory | 14 hrs | 25 days | 2024-05-01 | 2024-06-05
6946 | 1431 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 3 hrs | 5 days | 2024-05-15 | 2024-05-21 | 1429 | 1432 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves
6947 | 1432 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory | 2 hrs | 5 days | 2024-05-22 | 2024-05-29 | 1431 | 1433 |  | Angie Robertson,Jimmy Cox
6948 | 1433 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Coordinate Knowledge Base Update | 2 hrs | 5 days | 2024-05-30 | 2024-06-05 | 1432 |  |  | Jennifer Reeves,Daylin Reyes | Successor UID-6916 | TW
6949 | 1434 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create Communication - Data Inventory | 2 hrs | 5 days | 2024-05-01 | 2024-05-07 | 1427 | 1435 |  | Jennifer Grant,Jennifer Reeves
6950 | 1435 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Communication for Data Inventory | 2 hrs | 10 days | 2024-05-08 | 2024-05-21 | 1434 | 1436 |  | Dusti Kincl,Angie Robertson
6951 | 1436 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Communication for Data Inventory | 2 hrs | 5 days | 2024-05-22 | 2024-05-29 | 1435 | 13971437 |  | Jennifer Grant,Jennifer Reeves
6952 | 1437 | Future Task |  | RW-Communication | I-WP102 | Jennifer Reeves | Create | I-WP102 Share Communication for Data Inventory | 1 hr | 2 days | 2024-05-30 | 2024-05-31 | 1436 |  |  | Dusti Kincl | Successor UID-6916 | TW
7039 | 1438 | Late |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Accounting Entry Inventory | 271 hrs | 285 days | 2023-05-18 | 2024-07-03
7040 | 1439 | Late |  |  | I-WP103 | Jennifer Reeves | Create | WPED - I-WP103 Accounting Entry Inventory - Create | 10 hrs | 10 days | 2023-05-18 | 2023-06-01 | 1 | 1440 |  | Jennifer Grant,Jennifer Reeves
7041 | 1440 | Future Task |  |  | I-WP103 | Jennifer Reeves | Submit | WPED - I-WP103 Accounting Entry Inventory - Submit | 0 hrs | 0 days | 2023-06-01 | 2023-06-01 | 1439 | 1441 |  | Jennifer Grant,Jennifer Reeves
7042 | 1441 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WPED - I-WP103 Accounting Entry Inventory - Collaborative Review and Update | 10 hrs | 10 days | 2023-06-02 | 2023-06-15 | 1440 | 1442 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7043 | 1442 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | WPED - I-WP103 Accounting Entry Inventory - Approve | 0 hrs | 0 days | 2023-06-15 | 2023-06-15 | 1441 | 1451FS+37 days |  | Jimmy Cox
7044 | 1443 | Future Task |  |  | I-WP103 | Jennifer Reeves | Submit | WP - IWP103 Accounting Entry Inventory - Submit | 0 hrs | 0 days | 2024-06-10 | 2024-06-10 | 1482 | 1444 |  | Jennifer Grant,Jennifer Reeves
7045 | 1444 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP - IWP103 Accounting Entry Inventory - Dept QC | 1 hr | 1 day | 2024-06-11 | 2024-06-11 | 1443 | 1445 |  | Gabriela Gibson
7046 | 1445 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP - IWP103 Accounting Entry Inventory - Collaborative Review and Update | 10 hrs | 10 days | 2024-06-12 | 2024-06-25 | 1444 | 1446 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7047 | 1446 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP - IWP103 Accounting Entry Inventory - Style Guide Review | 1 hr | 1 day | 2024-06-26 | 2024-06-26 | 1445 | 1447 |  | Tatiana Eubanks
7048 | 1447 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP - IWP103 Accounting Entry Inventory - Final Review and Update | 2 hrs | 5 days | 2024-06-27 | 2024-07-03 | 1446 | 1448 |  | Angie Robertson,Jimmy Cox
7049 | 1448 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | WP - IWP103 Accounting Entry Inventory - Approve | 0 hrs | 0 days | 2024-07-03 | 2024-07-03 | 1447 |  |  | Jimmy Cox
7050 | 1449 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | Accounting Entry Inventory | 237 hrs | 216 days | 2023-08-09 | 2024-06-17
7051 | 1450 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 1 | 48 hrs | 37 days | 2023-08-09 | 2023-09-29
7052 | 1451 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Accounting Entry Inventory Format | 10 hrs | 5 days | 2023-08-09 | 2023-08-15 | 1442FS+37 days | 1452 |  | Jennifer Reeves,Daylin Reyes
7053 | 1452 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory Format | 10 hrs | 6 days | 2023-08-16 | 2023-08-23 | 1451 | 1453 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7054 | 1453 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory Format | 10 hrs | 5 days | 2023-08-24 | 2023-08-30 | 1452 | 1454 |  | Jimmy Cox
7055 | 1454 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 16 days | 2023-08-31 | 2023-09-22 | 1453,38 | 1455 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7056 | 1455 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | 2023-09-25 | 2023-09-29 | 1454 |  |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes | Successor UID-7044 | TW
7057 | 1456 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 2 | 18 hrs | 20 days | 2023-10-24 | 2023-11-21
7058 | 1457 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | 2023-10-24 | 2023-11-14 | 57 | 1458 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7059 | 1458 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | 2023-11-15 | 2023-11-21 | 1457 |  |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes | Successor UID-7044 | TW
7060 | 1459 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 3 | 28 hrs | 25 days | 2024-01-11 | 2024-02-15
7061 | 1460 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | 2024-01-11 | 2024-02-01 | 136SS | 14611467 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7062 | 1461 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | 2024-02-02 | 2024-02-08 | 1460 | 1462 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7063 | 1462 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Functional Teams | 10 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1461 | 1464 |  | Brendan Jones,Janice Jackson,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7064 | 1463 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Update & Publish Accounting Entry Inventory | 54 hrs | 25 days | 2024-02-02 | 2024-03-07
7065 | 1464 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory | 10 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1462 | 1465 |  | Jennifer Reeves,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson
7066 | 1465 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory | 2 hrs | 5 days | 2024-02-23 | 2024-02-29 | 1464 | 1466 |  | Jimmy Cox
7067 | 1466 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Coordinate Knowledge Base Update | 10 hrs | 5 days | 2024-03-01 | 2024-03-07 | 1465 |  |  | Jennifer Reeves,Daylin Reyes | Successor UID-7080 | TW
7068 | 1467 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Communication for Accounting Entry Inventory | 10 hrs | 5 days | 2024-02-02 | 2024-02-08 | 1460 | 1468 |  | Jennifer Grant,Jennifer Reeves
7069 | 1468 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review for Communication for Accounting Entry Inventory | 10 hrs | 9 days | 2024-02-09 | 2024-02-21 | 1467 | 1469 |  | Dusti Kincl,Angie Robertson
7070 | 1469 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Communication for Accounting Entry Inventory | 10 hrs | 5 days | 2024-02-22 | 2024-02-28 | 1468 | 1470 |  | Jimmy Cox
7071 | 1470 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Publish - Accounting Entry Inventory | 1 hr | 2 days | 2024-02-29 | 2024-03-01 | 1469 | 1471 |  | Pradeep Koul,Richard Saltford,Daylin Reyes,Dusti Kincl
7072 | 1471 | Future Task |  | RW-Communication | I-WP103 | Jennifer Reeves | Create | I-WP103 Share - Communication for Accounting Entry Inventory | 1 hr | 2 days | 2024-03-04 | 2024-03-05 | 1470 |  |  | Dusti Kincl | Successor UID-7044
7073 | 1472 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 4 | 28 hrs | 25 days | 2024-04-22 | 2024-05-24
7074 | 1473 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | 2024-04-22 | 2024-05-10 | 155SS | 14741480 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7075 | 1474 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | 2024-05-13 | 2024-05-17 | 1473 | 1475 |  | Matthew Breeding,Jennifer Reeves
7076 | 1475 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Functional Teams | 10 hrs | 5 days | 2024-05-20 | 2024-05-24 | 1474 | 1477 |  | Brendan Jones,Janice Jackson,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7077 | 1476 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Update & Publish Accounting Entry Inventory | 61 hrs | 25 days | 2024-05-13 | 2024-06-17
7078 | 1477 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review -Accounting Entry Inventory | 10 hrs | 5 days | 2024-05-28 | 2024-06-03 | 1475 | 1478 |  | Jennifer Reeves,Matthew Breeding,Deana Metcalf
7079 | 1478 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory | 10 hrs | 5 days | 2024-06-04 | 2024-06-10 | 1477 | 1479 |  | Jimmy Cox,Angie Robertson
7080 | 1479 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Coordinate Knowledge Base Update | 10 hrs | 5 days | 2024-06-11 | 2024-06-17 | 1478 |  |  | Jennifer Reeves,Daylin Reyes
7081 | 1480 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Communication for Accounting Entry Inventory | 10 hrs | 5 days | 2024-05-13 | 2024-05-17 | 1473 | 1481 |  | Jennifer Grant,Jennifer Reeves
7082 | 1481 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Communication for Accounting Entry Inventory | 10 hrs | 10 days | 2024-05-20 | 2024-06-03 | 1480 | 1482 |  | Dusti Kincl,Angie Robertson
7083 | 1482 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Communication for Accounting Entry Inventory | 10 hrs | 5 days | 2024-06-04 | 2024-06-10 | 1481 | 14431483 |  | Jennifer Grant,Jennifer Reeves
7084 | 1483 | Future Task |  | RW-Communication | I-WP103 | Jennifer Reeves | Create | I-WP103 Share Communication for Accounting Entry Inventory | 1 hr | 2 days | 2024-06-11 | 2024-06-12 | 1482 |  |  | Dusti Kincl
7085 | 1484 | Late |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Error Matrix | 113 hrs | 287 days | 2023-05-18 | 2024-07-08
7086 | 1485 | Late |  |  | I-WP104 | Jennifer Reeves | Create | WPED - I-WP104 Error Matrix - Create | 9 hrs | 9 days | 2023-05-18 | 2023-05-31 | 1 | 1486 |  | Jennifer Grant,Jennifer Reeves
7087 | 1486 | Future Task |  |  | I-WP104 | Jennifer Reeves | Submit | WPED - I-WP104 Error Matrix - Submit | 0 hrs | 0 days | 2023-05-31 | 2023-05-31 | 1485 | 1487 |  | Jennifer Grant,Jennifer Reeves
7088 | 1487 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WPED - I-WP104 Error Matrix - Collaborative Review and Update | 10 hrs | 10 days | 2023-06-01 | 2023-06-14 | 1486 | 14881496 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7089 | 1488 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | WPED - I-WP104 Error Matrix - Approve | 0 hrs | 0 days | 2023-06-14 | 2023-06-14 | 1487 |  |  | Jimmy Cox
7090 | 1489 | Future Task |  |  | I-WP104 | Jennifer Reeves | Submit | WP - IWP104 Error Matrix - Submit | 0 hrs | 0 days | 2024-06-12 | 2024-06-12 | 15271528 | 1490 |  | Jennifer Grant,Jennifer Reeves
7091 | 1490 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP - IWP104 Error Matrix - Dept QC | 1 hr | 1 day | 2024-06-13 | 2024-06-13 | 1489 | 1491 |  | Gabriela Gibson
7092 | 1491 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP - IWP104 Error Matrix - Collaborative Review and Update | 10 hrs | 10 days | 2024-06-14 | 2024-06-27 | 1490 | 1492 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7093 | 1492 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP - IWP104 Error Matrix - Style Guide Review | 1 hr | 1 day | 2024-06-28 | 2024-06-28 | 1491 | 1493 |  | Tatiana Eubanks
7094 | 1493 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP - IWP104 Error Matrix - Final Review and Update | 2 hrs | 5 days | 2024-07-01 | 2024-07-08 | 1492 | 1494 |  | Angie Robertson,Jimmy Cox
7095 | 1494 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | WP - IWP104 Error Matrix - Approve | 0 hrs | 0 days | 2024-07-08 | 2024-07-08 | 1493 |  |  | Jimmy Cox
7096 | 1495 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 1 | 15 hrs | 63 days | 2023-06-15 | 2023-09-13
7097 | 1496 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Error Matrix Format | 2 hrs | 5 days | 2023-06-15 | 2023-06-21 | 1487 | 1497 |  | Jennifer Reeves,Daylin Reyes
7098 | 1497 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 5 hrs | 5 days | 2023-06-22 | 2023-06-28 | 1496 | 1498 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7099 | 1498 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix Format | 1 hr | 5 days | 2023-06-29 | 2023-07-06 | 1497 | 1499 |  | Jimmy Cox
7100 | 1499 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | 2023-08-02 | 2023-08-22 | 1498,38 | 1500 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7101 | 1500 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 15 days | 2023-08-23 | 2023-09-13 | 1499 |  |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7102 | 1501 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 2 | 7 hrs | 20 days | 2023-10-24 | 2023-11-21
7103 | 1502 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | 2023-10-24 | 2023-11-14 | 57 | 1503 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7104 | 1503 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | 2023-11-15 | 2023-11-21 | 1502 |  |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7105 | 1504 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 3 | 13 hrs | 25 days | 2024-01-29 | 2024-03-01
7106 | 1505 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | 2024-01-29 | 2024-02-16 | 136 | 15061512 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7107 | 1506 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | 2024-02-19 | 2024-02-23 | 1505 | 1507 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7108 | 1507 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Functional Teams | 6 hrs | 5 days | 2024-02-26 | 2024-03-01 | 1506 | 1509 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7109 | 1508 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Update & Publish Error Matrix | 18 hrs | 25 days | 2024-02-19 | 2024-03-22
7110 | 1509 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 5 hrs | 5 days | 2024-03-04 | 2024-03-08 | 1507 | 1510 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
7111 | 1510 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix | 1 hr | 5 days | 2024-03-11 | 2024-03-15 | 1509 | 1511 |  | Jimmy Cox
7112 | 1511 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Coordinate Knowledge Base Update | 2 hrs | 5 days | 2024-03-18 | 2024-03-22 | 1510 |  |  | Jennifer Reeves,Daylin Reyes
7113 | 1512 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Communication for Error Matrix | 2 hrs | 5 days | 2024-02-19 | 2024-02-23 | 1505 | 1513 |  | Jennifer Grant,Jennifer Reeves
7114 | 1513 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review for Communication for Error Matrix | 2 hrs | 9 days | 2024-02-26 | 2024-03-07 | 1512 | 1514 |  | Dusti Kincl,Angie Robertson
7115 | 1514 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Communication for Error Matrix | 1 hr | 5 days | 2024-03-08 | 2024-03-14 | 1513 | 1515 |  | Jimmy Cox
7116 | 1515 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Publish - Error Matrix | 4 hrs | 2 days | 2024-03-15 | 2024-03-18 | 1514 | 1516 |  | Pradeep Koul,Richard Saltford,Daylin Reyes,Dusti Kincl
7117 | 1516 | Future Task |  | RW-Communication | I-WP104 | Jennifer Reeves | Create | I-WP104 Share - Communication for Error Matrix | 1 hr | 2 days | 2024-03-19 | 2024-03-20 | 1515 |  |  | Dusti Kincl
7118 | 1517 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 4 | 13 hrs | 25 days | 2024-04-22 | 2024-05-24
7119 | 1518 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | 2024-04-22 | 2024-05-10 | 155SS | 15191525 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
7120 | 1519 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | 2024-05-13 | 2024-05-17 | 1518 | 1520 |  | Jennifer Grant,Jennifer Reeves,Daylin Reyes
7121 | 1520 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Functional Teams | 6 hrs | 5 days | 2024-05-20 | 2024-05-24 | 1519 | 1522 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
7122 | 1521 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Update & Publish Error Matrix | 14 hrs | 25 days | 2024-05-13 | 2024-06-17
7123 | 1522 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 3 hrs | 5 days | 2024-05-28 | 2024-06-03 | 1520 | 1523 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves
7124 | 1523 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix | 2 hrs | 5 days | 2024-06-04 | 2024-06-10 | 1522 | 1524 |  | Angie Robertson,Jimmy Cox
7125 | 1524 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Coordinate Knowledge Base Update | 2 hrs | 5 days | 2024-06-11 | 2024-06-17 | 1523 |  |  | Jennifer Reeves,Daylin Reyes
7126 | 1525 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Task Instructions & Communication for Error Matrix | 2 hrs | 5 days | 2024-05-13 | 2024-05-17 | 1518 | 1526 |  | Jennifer Reeves,Nikki Klein
7127 | 1526 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Communication for Error Matrix | 2 hrs | 10 days | 2024-05-20 | 2024-06-03 | 1525 | 1527 |  | Dusti Kincl,Angie Robertson
7128 | 1527 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Task Instructions & Communication for Error Matrix | 2 hrs | 5 days | 2024-06-04 | 2024-06-10 | 1526 | 14891528 |  | Jennifer Grant,Jennifer Reeves
7129 | 1528 | Future Task |  | RW-Communication | I-WP104 | Jennifer Reeves | Create | I-WP104 Share Communication for Error Matrix | 1 hr | 2 days | 2024-06-11 | 2024-06-12 | 1527 | 1489 |  | Dusti Kincl
6862 | 1529 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Maintain Catalogs | 239 hrs | 272 days | 2023-06-09 | 2024-07-08
6863 | 1530 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Report Catalog | 51 hrs | 272 days | 2023-06-09 | 2024-07-08
6864 | 1531 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | WPED - I-WP105 Report Catalog - Create | 2 hrs | 10 days | 2023-06-09 | 2023-06-22 | 1 | 1532 |  | Jennifer Grant,Jennifer Reeves
6865 | 1532 | Future Task |  |  | I-WP105 | Jennifer Reeves | Submit | WPED - I-WP105 Report Catalog - Submit | 0 hrs | 0 days | 2023-06-22 | 2023-06-22 | 1531 | 1533 |  | Jennifer Grant,Jennifer Reeves
6866 | 1533 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WPED - I-WP105 Report Catalog - Collaborative Review and Update | 8 hrs | 10 days | 2023-06-23 | 2023-07-07 | 1532 | 1534 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Reeves,Jennifer Grant
6867 | 1534 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | WPED - I-WP105 Report Catalog - Approve | 0 hrs | 0 days | 2023-07-07 | 2023-07-07 | 1533 |  |  | Jimmy Cox
6868 | 1535 | Future Task |  |  | I-WP105 | Jennifer Reeves | Milestone | WP - IWP105 Report Catalog - Submit | 0 hrs | 0 days | 2024-06-12 | 2024-06-12 | 15581571 | 1536 |  | Jennifer Grant,Jennifer Reeves | Why is this task a Milestone? | Angie
6869 | 1536 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP - IWP105 Report Catalog - Dept QC | 1 hr | 1 day | 2024-06-13 | 2024-06-13 | 1535 | 1537 |  | Jenifer Hartsfield
6870 | 1537 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP - IWP105 Report Catalog - Collaborative Review and Update | 2 hrs | 10 days | 2024-06-14 | 2024-06-27 | 1536 | 1538 |  | Jennifer Grant,Jennifer Reeves
6871 | 1538 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP - IWP105 Report Catalog - Style Guide Review | 1 hr | 1 day | 2024-06-28 | 2024-06-28 | 1537 | 1539 |  | Tatiana Eubanks
6872 | 1539 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP - IWP105 Report Catalog - Final Review and Update | 2 hrs | 5 days | 2024-07-01 | 2024-07-08 | 1538 | 1540 |  | Angie Robertson,Jimmy Cox
6873 | 1540 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | WP - IWP105 Report Catalog - Approve | 0 hrs | 0 days | 2024-07-08 | 2024-07-08 | 1539 |  |  | Jimmy Cox
6874 | 1541 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 1 - Reports | 35 hrs | 20 days | 2023-07-18 | 2023-08-14
6875 | 1542 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | 2023-07-18 | 2023-08-07 | 38SS | 1543 |  | Pradeep Koul,Tanya McCarty,Stanton Beazley,Jennifer Reeves,Elizabeth Sargent
6876 | 1543 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | 2023-08-08 | 2023-08-14 | 1542 |  |  | Jennifer Grant,Jennifer Reeves
6877 | 1544 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 2 - Reports | 35 hrs | 20 days | 2023-10-09 | 2023-11-03
6878 | 1545 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | 2023-10-09 | 2023-10-27 | 57SS | 1546 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6879 | 1546 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | 2023-10-30 | 2023-11-03 | 1545 |  |  | Jennifer Grant,Jennifer Reeves
6880 | 1547 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 3 - Reports | 55 hrs | 25 days | 2024-01-11 | 2024-02-15
6881 | 1548 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | 2024-01-11 | 2024-02-01 | 136SS | 1549 |  | Pradeep Koul,Tanya McCarty,Elizabeth Sargent,Jennifer Reeves
6882 | 1549 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | 2024-02-02 | 2024-02-08 | 1548 | 15501556 |  | Jennifer Grant,Jennifer Reeves
6883 | 1550 | Future Task |  |  |  | Jennifer Reeves | Review | I-WP105 Collaborative Review - Functional Teams | 20 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1549 | 1552 |  | Jennifer Grant,Jennifer Reeves,Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
6884 | 1551 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Update & Publish Report Catalog | 41 hrs | 22 days | 2024-02-09 | 2024-03-11
6885 | 1552 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Report Catalog | 10 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1550 | 1553 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6886 | 1553 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Report Catalog | 2 hrs | 5 days | 2024-02-23 | 2024-02-29 | 1552 | 1554 |  | Jimmy Cox
6887 | 1554 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Coordinate Knowledge Base Update | 18 hrs | 5 days | 2024-03-01 | 2024-03-07 | 1553 | 1555 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6888 | 1555 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Publish - Report Catalog | 4 hrs | 2 days | 2024-03-08 | 2024-03-11 | 1554 |  |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6889 | 1556 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Create Communication for Report Catalog | 2 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1549 | 1557 |  | Jennifer Grant,Jennifer Reeves
6890 | 1557 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review for Communication | 3 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1556 | 1558 |  | Dusti Kincl,Angie Robertson,Jennifer Reeves
6891 | 1558 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Communication for Report Catalog | 1 hr | 5 days | 2024-02-23 | 2024-02-29 | 1557 | 15351559 |  | Jimmy Cox
6892 | 1559 | Future Task |  | RW-Communication | I-WP105 | Jennifer Reeves | Create | I-WP105 Share Communication for Report Catalog | 1 hr | 2 days | 2024-03-01 | 2024-03-04 | 1558 |  |  | Dusti Kincl
6893 | 1560 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 4 - Reports | 32 hrs | 27 days | 2024-04-22 | 2024-05-29
6894 | 1561 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 10 hrs | 16 days | 2024-04-22 | 2024-05-13 | 155SS | 1562 |  | Pradeep Koul,Tanya McCarty,Jennifer Grant,Elizabeth Sargent
6895 | 1562 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 2 hrs | 6 days | 2024-05-14 | 2024-05-21 | 1561 | 15631569 |  | Jennifer Grant,Jennifer Reeves
6896 | 1563 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Functional Teams | 20 hrs | 5 days | 2024-05-22 | 2024-05-29 | 1562 | 1565 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes,Jennifer Grant,Jennifer Reeves
6897 | 1564 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Update & Publish Report Catalog | 25 hrs | 22 days | 2024-05-22 | 2024-06-21
6898 | 1565 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Report Catalog | 10 hrs | 5 days | 2024-05-30 | 2024-06-05 | 1563 | 1566 |  | Matthew Breeding,Deana Metcalf,Carolyn Hicks,Angie Robertson,Jennifer Reeves
6899 | 1566 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Report Catalog | 1 hr | 5 days | 2024-06-06 | 2024-06-12 | 1565 | 1567 |  | Jimmy Cox
6900 | 1567 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Coordinate Knowledge Base Update | 3 hrs | 5 days | 2024-06-13 | 2024-06-19 | 1566 | 1568 |  | Jennifer Reeves,Jennifer Grant,Daylin Reyes
6901 | 1568 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Publish - Report Catalog | 4 hrs | 2 days | 2024-06-20 | 2024-06-21 | 1567 |  |  | Pradeep Koul,Dusti Kincl,Richard Saltford,Daylin Reyes
6902 | 1569 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Create Communication for Report Catalog | 2 hrs | 5 days | 2024-05-22 | 2024-05-29 | 1562 | 1570 |  | Jennifer Grant,Jennifer Reeves
6903 | 1570 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review for Communication | 3 hrs | 5 days | 2024-05-30 | 2024-06-05 | 1569 | 1571 |  | Dusti Kincl,Angie Robertson,Jennifer Reeves
6904 | 1571 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Communication for Report Catalog | 1 hr | 5 days | 2024-06-06 | 2024-06-12 | 1570 | 15351572 |  | Jimmy Cox
6905 | 1572 | Future Task |  | RW-Communication | I-WP105 | Jennifer Reeves | Create | I-WP105 Share Communication for Report Catalog | 1 hr | 2 days | 2024-06-13 | 2024-06-14 | 1571 |  |  | Dusti Kincl
6953 | 1573 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Interface Catalog | 210 hrs | 272 days | 2023-06-09 | 2024-07-08
6954 | 1574 | Future Task |  |  | I-WP106 | Matt Breeding | Create | WPED - I-WP106 Interface Catalog - Create | 10 hrs | 10 days | 2023-06-09 | 2023-06-22 | 1 | 1575 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding
6955 | 1575 | Future Task |  |  | I-WP106 | Matt Breeding | Submit | WPED - I-WP106 Interface Catalog - Submit | 0 hrs | 0 days | 2023-06-22 | 2023-06-22 | 1574 | 1576 |  | Matthew Breeding
6956 | 1576 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WPED - I-WP106 Interface Catalog - Collaborative Review and Update | 10 hrs | 10 days | 2023-06-23 | 2023-07-07 | 1575 | 1577 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
6957 | 1577 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | WPED - I-WP106 Interface Catalog - Approve | 0 hrs | 0 days | 2023-07-07 | 2023-07-07 | 1576 |  |  | Jimmy Cox
6958 | 1578 | Future Task |  |  | I-WP106 | Matt Breeding | Submit | WP - IWP106 Interface Catalog - Submit | 0 hrs | 0 days | 2024-06-03 | 2024-06-03 | 1614 | 1579 |  | Matthew Breeding
6959 | 1579 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP - IWP106 Interface Catalog - Dept QC | 1 hr | 1 day | 2024-06-04 | 2024-06-04 | 1578 | 1580 |  | Gabriela Gibson
6960 | 1580 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP - IWP106 Interface Catalog - Collaborative Review and Update | 10 hrs | 10 days | 2024-06-05 | 2024-06-18 | 1579 | 1581 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
6961 | 1581 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP - IWP106 Interface Catalog - Style Guide Review | 2 hrs | 1 day | 2024-06-19 | 2024-06-19 | 1580 | 1582 |  | Tatiana Eubanks
6962 | 1582 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP - IWP106 Interface Catalog - Final Review and Update | 10 hrs | 5 days | 2024-06-20 | 2024-06-26 | 1581 | 1583 |  | Angie Robertson,Jimmy Cox
6963 | 1583 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | WP - IWP106 Interface Catalog - Approve | 0 hrs | 0 days | 2024-06-26 | 2024-06-26 | 1582 |  |  | Jimmy Cox
6964 | 1584 | Future Task |  |  | I-WP106 | Matt Breeding |  | Interface Catalog | 167 hrs | 272 days | 2023-06-09 | 2024-07-08
6965 | 1585 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 1 - Interfaces | 12 hrs | 20 days | 2023-07-18 | 2023-08-14
6966 | 1586 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | 2023-07-18 | 2023-08-07 | 38SS | 1587 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6967 | 1587 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | 2023-08-08 | 2023-08-14 | 1586 |  |  | Matthew Breeding
6968 | 1588 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 2 - Interfaces | 12 hrs | 20 days | 2023-10-11 | 2023-11-07
6969 | 1589 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | 2023-10-11 | 2023-10-31 | 57SS+2 days | 1590 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6970 | 1590 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | 2023-11-01 | 2023-11-07 | 1589 |  |  | Matthew Breeding
6971 | 1591 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 3 - Interfaces | 22 hrs | 25 days | 2024-01-11 | 2024-02-15
6972 | 1592 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | 2024-01-11 | 2024-02-01 | 136SS | 1593 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6973 | 1593 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | 2024-02-02 | 2024-02-08 | 1592 | 15941600 |  | Matthew Breeding
6974 | 1594 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Functional Teams | 10 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1593 | 1596 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
6975 | 1595 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Update & Publish Interface Catalog | 45 hrs | 24 days | 2024-02-09 | 2024-03-13
6976 | 1596 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Interface Catalog | 10 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1594 | 1597 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6977 | 1597 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Interface Catalog | 1 hr | 5 days | 2024-02-23 | 2024-02-29 | 1596 | 1598 |  | Jimmy Cox
6978 | 1598 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Coordinate Knowledge Base Update | 10 hrs | 5 days | 2024-03-01 | 2024-03-07 | 1597 | 1599 |  | Matthew Breeding,Daylin Reyes
6979 | 1599 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Publish - Interface Catalog | 10 hrs | 2 days | 2024-03-08 | 2024-03-11 | 1598 | 1603 |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
6980 | 1600 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Create Communication for Interface Catalog | 2 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1593 | 1601 |  | Matthew Breeding,Dusti Kincl
6981 | 1601 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review for Communication for Interface Catalog | 10 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1600 | 1602 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6982 | 1602 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Communication for Interface Catalog | 1 hr | 5 days | 2024-02-23 | 2024-02-29 | 1601 |  |  | Jimmy Cox
6983 | 1603 | Future Task |  | RW-Communication | I-WP106 | Matt Breeding | Create | I-WP106 Share Communication for Interface Catalog | 1 hr | 2 days | 2024-03-12 | 2024-03-13 | 1599 |  |  | Dusti Kincl
6984 | 1604 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 4 - Interfaces | 12 hrs | 20 days | 2024-04-22 | 2024-05-17
6985 | 1605 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | 2024-04-22 | 2024-05-10 | 155SS | 16061612 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
6986 | 1606 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | 2024-05-13 | 2024-05-17 | 1605 | 1608 |  | Matthew Breeding
6987 | 1607 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Update & Publish Interface Catalog | 64 hrs | 272 days | 2023-06-09 | 2024-07-08
6988 | 1608 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Interface Catalog | 10 hrs | 5 days | 2024-05-20 | 2024-05-24 | 1606 | 1609 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
6989 | 1609 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Interface Catalog | 1 hr | 5 days | 2024-05-28 | 2024-06-03 | 1608 | 1610 |  | Jimmy Cox
6990 | 1610 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Coordinate Knowledge Base Update | 2 hrs | 5 days | 2024-06-04 | 2024-06-10 | 1609 | 1611 |  | Matthew Breeding,Daylin Reyes
6991 | 1611 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Publish Interface Catalog | 1 hr | 2 days | 2024-06-11 | 2024-06-12 | 1610 |  |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
6992 | 1612 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Create Communication for Interface Catalog | 2 hrs | 5 days | 2024-05-13 | 2024-05-17 | 1605 | 1613 |  | Matthew Breeding,Dusti Kincl
6993 | 1613 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review for Communication for Interface Catalog | 3 hrs | 5 days | 2024-05-20 | 2024-05-24 | 1612 | 1614 |  | Dusti Kincl,Angie Robertson,Matthew Breeding
6994 | 1614 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Communication for Interface Catalog | 1 hr | 5 days | 2024-05-28 | 2024-06-03 | 1613 | 15781615 |  | Jimmy Cox
6995 | 1615 | Future Task |  | RW-Communication | I-WP106 | Matt Breeding | Create | I-WP106 Share Communication for Interface Catalog | 1 hr | 2 days | 2024-06-04 | 2024-06-05 | 1614 |  |  | Dusti Kincl
6996 | 1616 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Conversions Inventory | 43 hrs | 272 days | 2023-06-09 | 2024-07-08
6997 | 1617 | Future Task |  |  | I-WP107 | Matt Breeding | Create | WPED - I-WP107 Conversions Inventory - Create | 10 hrs | 10 days | 2023-06-09 | 2023-06-22 | 1 | 1618 |  | Jennifer Grant,Jennifer Reeves,Matthew Breeding
6998 | 1618 | Future Task |  |  | I-WP107 | Matt Breeding | Submit | WPED - I-WP107 Conversions Inventory - Submit | 0 hrs | 0 days | 2023-06-22 | 2023-06-22 | 1617 | 1619 |  | Matthew Breeding
6999 | 1619 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WPED - I-WP107 Conversions Inventory - Collaborative Review and Update | 10 hrs | 10 days | 2023-06-23 | 2023-07-07 | 1618 | 1620 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7000 | 1620 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | WPED - I-WP107 Conversions Inventory - Approve | 0 hrs | 0 days | 2023-07-07 | 2023-07-07 | 1619 |  |  | Jimmy Cox
7001 | 1621 | Future Task |  |  | I-WP107 | Matt Breeding | Submit | WP - IWP107 Conversions Inventory - Submit | 0 hrs | 0 days | 2024-06-12 | 2024-06-12 | 1657 | 1622 |  | Matthew Breeding
7002 | 1622 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP - IWP107 Conversions Inventory - Dept QC | 1 hr | 1 day | 2024-06-13 | 2024-06-13 | 1621 | 1623 |  | Gabriela Gibson
7003 | 1623 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP - IWP107 Conversions Inventory - Collaborative Review and Update | 10 hrs | 10 days | 2024-06-14 | 2024-06-27 | 1622 | 1624 |  | Matthew Breeding,Carolyn Hicks,Nikki Klein,Deana Metcalf,Daylin Reyes,Angie Robertson,Jennifer Grant,Jennifer Reeves
7004 | 1624 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP - IWP107 Conversions Inventory - Style Guide Review | 2 hrs | 1 day | 2024-06-28 | 2024-06-28 | 1623 | 1625 |  | Tatiana Eubanks
7005 | 1625 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP - IWP107 Conversions Inventory - Final Review and Update | 10 hrs | 5 days | 2024-07-01 | 2024-07-08 | 1624 | 1626 |  | Angie Robertson,Jimmy Cox
7006 | 1626 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | WP - IWP107 Conversions Inventory - Approve | 0 hrs | 0 days | 2024-07-08 | 2024-07-08 | 1625 |  |  | Jimmy Cox
7007 | 1627 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Conversions Inventory | 124 hrs | 234 days | 2023-07-18 | 2024-06-19
7008 | 1628 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 1 - Conversions | 11 hrs | 20 days | 2023-07-18 | 2023-08-14
7009 | 1629 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | 2023-07-18 | 2023-08-07 | 38SS | 1630 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7010 | 1630 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 1 hr | 5 days | 2023-08-08 | 2023-08-14 | 1629 |  |  | Matthew Breeding
7011 | 1631 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 2 - Conversions | 15 hrs | 20 days | 2023-10-16 | 2023-11-13
7012 | 1632 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | 2023-10-16 | 2023-11-03 | 57SS+5 days | 1633 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7013 | 1633 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 5 hrs | 5 days | 2023-11-06 | 2023-11-13 | 1632 |  |  | Matthew Breeding
7014 | 1634 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 3 - Conversions | 25 hrs | 25 days | 2024-01-19 | 2024-02-22
7015 | 1635 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | 2024-01-19 | 2024-02-08 | 136SS+5 days | 1636 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7016 | 1636 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 5 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1635 | 16371643 |  | Matthew Breeding
7017 | 1637 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Functional Teams | 10 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1636 | 1639 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
7018 | 1638 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Update & Publish Conversion Catalog | 26 hrs | 27 days | 2024-02-16 | 2024-03-25
7019 | 1639 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Conversion Catalog | 10 hrs | 5 days | 2024-02-23 | 2024-02-29 | 1637 | 1640 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7020 | 1640 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Conversion Catalog | 1 hr | 5 days | 2024-03-01 | 2024-03-07 | 1639 | 1641 |  | Jimmy Cox
7021 | 1641 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Coordinate Knowledge Base Update | 2 hrs | 5 days | 2024-03-08 | 2024-03-14 | 1640 | 1642 |  | Matthew Breeding,Daylin Reyes
7022 | 1642 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Publish - Conversion Catalog | 4 hrs | 5 days | 2024-03-15 | 2024-03-21 | 1641 | 1646 |  | Richard Saltford,Pradeep Koul,Daylin Reyes,Dusti Kincl
7023 | 1643 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create Communication for Conversion Catalog | 2 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1636 | 1644 |  | Matthew Breeding,Dusti Kincl
7024 | 1644 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review for Communication for Conversion Catalog | 5 hrs | 5 days | 2024-02-23 | 2024-02-29 | 1643 | 1645 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7025 | 1645 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Communication | 1 hr | 5 days | 2024-03-01 | 2024-03-07 | 1644 |  |  | Jimmy Cox
7026 | 1646 | Future Task |  | RW-Communication | I-WP107 | Matt Breeding | Create | I-WP107 Share Communication | 1 hr | 2 days | 2024-03-22 | 2024-03-25 | 1642 |  |  | Dusti Kincl
7027 | 1647 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 4 - Conversions | 15 hrs | 25 days | 2024-04-29 | 2024-06-03
7028 | 1648 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create & Maintain - Conversion Catalog | 10 hrs | 15 days | 2024-04-29 | 2024-05-17 | 155SS+5 days | 1649 |  | John Moyle,Shaivi Nandineni,Richard Saltford,Chris Slay,LaWanda Warren
7029 | 1649 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 1 hr | 5 days | 2024-05-20 | 2024-05-24 | 1648 | 16501655 |  | Matthew Breeding
7030 | 1650 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Functional Teams | 4 hrs | 5 days | 2024-05-28 | 2024-06-03 | 1649 | 1652 |  | Janice Jackson,Brendan Jones,Tiffany Porter,Daylin Reyes
7031 | 1651 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Update & Publish Conversions Catalog | 32 hrs | 17 days | 2024-05-28 | 2024-06-19
7032 | 1652 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Conversion Catalog | 10 hrs | 5 days | 2024-06-04 | 2024-06-10 | 1650 | 1653 |  | Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Matthew Breeding
7033 | 1653 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Conversion Catalog | 1 hr | 5 days | 2024-06-11 | 2024-06-17 | 1652 | 1654 |  | Jimmy Cox
7034 | 1654 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Publish - Conversion Catalog | 4 hrs | 2 days | 2024-06-18 | 2024-06-19 | 1653 |  |  | Daylin Reyes,Richard Saltford,Pradeep Koul,Dusti Kincl
7035 | 1655 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create Communication for Conversions Catalog | 3 hrs | 2 days | 2024-05-28 | 2024-05-29 | 1649 | 1656 |  | Dusti Kincl,Pradeep Koul,Richard Barnes
7036 | 1656 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review for Communication for Conversions Catalog | 10 hrs | 5 days | 2024-05-30 | 2024-06-05 | 1655 | 1657 |  | Matthew Breeding,Deana Metcalf,Jennifer Reeves,Carolyn Hicks,Angie Robertson,Nikki Klein,Daylin Reyes,Jennifer Grant
7037 | 1657 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Communication | 3 hrs | 5 days | 2024-06-06 | 2024-06-12 | 1656 | 16211658 |  | Dusti Kincl,Angie Robertson,Matthew Breeding
7038 | 1658 | Future Task |  | RW-Communication | I-WP107 | Matt Breeding | Create | I-WP107 Share Communication for Conversions Catalog | 1 hr | 5 days | 2024-06-13 | 2024-06-19 | 1657 |  |  | Jimmy Cox
2973 | 1659 | Future Task |  |  | I-WP108 | Kimberly Kemp |  | I-WP108 Training Curriculum | 53 hrs | 360 days | 2023-06-01 | 2024-10-31
2974 | 1660 | Future Task |  |  | I-WP108 | Carolyn Hicks | Create | WPED - I-WP108 - Training Curriculum - Create | 10 hrs | 10 days | 2023-06-01 | 2023-06-14 | 1 | 1661 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
2975 | 1661 | Future Task |  |  | I-WP108 | Carolyn Hicks | Submit | WPED - I-WP108 - Training Curriculum - Submit | 0 hrs | 0 days | 2023-06-14 | 2023-06-14 | 1660 | 1662 |  | Carolyn Hicks
2976 | 1662 | Future Task |  |  | I-WP108 | Carolyn Hicks | Review | WPED - I-WP108 - Training Curriculum - Collaborative Review and Update | 10 hrs | 10 days | 2023-06-15 | 2023-06-28 | 1661 | 1663 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
2977 | 1663 | Future Task |  |  | I-WP108 | Carolyn Hicks | Approve | WPED - I-WP108 - Training Curriculum - Approve | 0 hrs | 0 days | 2023-06-28 | 2023-06-28 | 1662 | 1664 |  | Angie Robertson,Jimmy Cox
5689 | 1664 | Future Task |  |  | I-WP108 | Kimberly Kemp | Create | I-WP108 Training Curriculum <Activities per WPED> | 10 hrs | 287 days | 2023-08-21 | 2024-10-08 | 1663,44 | 1665,1676SS+30 days |  | Kimberly Kemp
2978 | 1665 | Future Task |  |  | I-WP108 | Kimberly Kemp | Submit | I-WP108 Training Curriculum - Submit | 0 hrs | 0 days | 2024-10-08 | 2024-10-08 | 1664 | 1666 |  | Kimberly Kemp
2979 | 1666 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | I-WP108 Training Curriculum - Dept QC | 1 hr | 1 day | 2024-10-09 | 2024-10-09 | 1665 | 1667 |  | Tommy Werner
2980 | 1667 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | I-WP108 Training Curriculum - Collaborative Review and Update | 10 hrs | 10 days | 2024-10-10 | 2024-10-23 | 1666 | 1668 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
2981 | 1668 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | I-WP108 Training Curriculum - Style Guide Review | 2 hrs | 1 day | 2024-10-24 | 2024-10-24 | 1667 | 1669 |  | Dusti Kincl
2982 | 1669 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | I-WP108 Training Curriculum - Final Review and Update | 10 hrs | 5 days | 2024-10-25 | 2024-10-31 | 1668 | 1670 |  | Angie Robertson,Jimmy Cox
2983 | 1670 | Future Task |  |  | I-WP108 | Kimberly Kemp | Approve | I-WP108 Training Curriculum - Approve | 0 hrs | 0 days | 2024-10-31 | 2024-10-31 | 1669 |  |  | Jimmy Cox
2984 | 1671 | Future Task |  |  | I-WP109 | Kimberly Kemp |  | I-WP109 Training Designs | 66 hrs | 315 days | 2023-07-03 | 2024-09-30
2985 | 1672 | Future Task |  |  | I-WP109 | Carolyn Hicks | Create | WPED - I-WP109 - Training Designs - Create | 10 hrs | 10 days | 2023-07-03 | 2023-07-17 | 1 | 1673 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila
2986 | 1673 | Future Task |  |  | I-WP109 | Carolyn Hicks | Submit | WPED - I-WP109 - Training Designs - Submit | 0 hrs | 0 days | 2023-07-17 | 2023-07-17 | 1672 | 1674 |  | Carolyn Hicks
2987 | 1674 | Future Task |  |  | I-WP109 | Carolyn Hicks | Review | WPED - I-WP109 - Training Designs - Collaborative Review and Update | 10 hrs | 10 days | 2023-07-18 | 2023-07-31 | 1673 | 1675 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
2988 | 1675 | Future Task |  |  | I-WP109 | Carolyn Hicks | Approve | WPED - I-WP109 - Training Designs - Approve | 0 hrs | 0 days | 2023-07-31 | 2023-07-31 | 1674 | 1676 |  | Angie Robertson,Jimmy Cox
5690 | 1676 | Future Task |  |  | I-WP109 | Kimberly Kemp | Create | I-WP109 Training Designs <Activities per WPED> | 10 hrs | 234 days | 2023-10-03 | 2024-09-05 | 1675,1664SS+30 days | 1677,1688SS |  | Kimberly Kemp
2989 | 1677 | Future Task |  |  | I-WP109 | Kimberly Kemp | Submit | I-WP109 Training Designs - Submit | 0 hrs | 0 days | 2024-09-05 | 2024-09-05 | 1676 | 1678 |  | Kimberly Kemp
2990 | 1678 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | I-WP109 Training Designs - Dept QC | 8 hrs | 1 day | 2024-09-06 | 2024-09-06 | 1677 | 1679 |  | Gabriela Gibson
2991 | 1679 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | I-WP109 Training Designs - Collaborative Review and Update | 10 hrs | 10 days | 2024-09-09 | 2024-09-20 | 1678 | 1680 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
2992 | 1680 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | I-WP109 Training Designs - Style Guide Review | 8 hrs | 1 day | 2024-09-23 | 2024-09-23 | 1679 | 1681 |  | Tatiana Eubanks
2993 | 1681 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | I-WP109 Training Designs - Final Review and Update | 10 hrs | 5 days | 2024-09-24 | 2024-09-30 | 1680 | 1682 |  | Angie Robertson,Jimmy Cox
2994 | 1682 | Future Task |  |  | I-WP109 | Kimberly Kemp | Approve | I-WP109 Training Designs - Approve | 0 hrs | 0 days | 2024-09-30 | 2024-09-30 | 1681 | 1750 |  | Jimmy Cox
2995 | 1683 | Future Task | Yes |  | I-WP110 | Kimberly Kemp |  | I-WP110 Training Build | 136 hrs | 401 days | 2024-03-01 | 2025-09-30
2996 | 1684 | Future Task |  |  | I-WP110 | Carolyn Hicks | Create | WPED - I-WP110 - Training Build - Create | 10 hrs | 10 days | 2024-03-01 | 2024-03-14 | 1 | 1685 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
2997 | 1685 | Future Task |  |  | I-WP110 | Carolyn Hicks | Submit | WPED - I-WP110 - Training Build - Submit | 0 hrs | 0 days | 2024-03-14 | 2024-03-14 | 1684 | 1686 |  | Carolyn Hicks
2998 | 1686 | Future Task |  |  | I-WP110 | Carolyn Hicks | Review | WPED - I-WP110 - Training Build - Collaborative Review and Update | 10 hrs | 10 days | 2024-03-15 | 2024-03-28 | 1685 | 1687 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
2999 | 1687 | Future Task |  |  | I-WP110 | Carolyn Hicks | Approve | WPED - I-WP110 - Training Build - Approve | 0 hrs | 0 days | 2024-03-28 | 2024-03-28 | 1686 | 1688 |  | Angie Robertson,Jimmy Cox
5691 | 1688 | Future Task |  |  | I-WP110 | Kimberly Kemp | Create | I-WP110 Training Build <Activities per WPED> | 80 hrs | 364 days | 2024-03-29 | 2025-09-05 | 1687,1676SS | 1689 |  | Kimberly Kemp
3000 | 1689 | Future Task |  |  | I-WP110 | Kimberly Kemp | Submit | I-WP110 Training Build - Submit | 0 hrs | 0 days | 2025-09-05 | 2025-09-05 | 1688 | 1690 |  | Kimberly Kemp
3001 | 1690 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | I-WP110 Training Build - Dept QC | 8 hrs | 1 day | 2025-09-08 | 2025-09-08 | 1689 | 1691 |  | Gabriela Gibson
3002 | 1691 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | I-WP110 Training Build - Collaborative Review and Update | 10 hrs | 10 days | 2025-09-09 | 2025-09-22 | 1690 | 1692 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3003 | 1692 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | I-WP110 Training Build - Style Guide Review | 8 hrs | 1 day | 2025-09-23 | 2025-09-23 | 1691 | 1693 |  | Tatiana Eubanks
3004 | 1693 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | I-WP110 Training Build - Final Review and Update | 10 hrs | 5 days | 2025-09-24 | 2025-09-30 | 1692 | 1694 |  | Angie Robertson,Jimmy Cox
3005 | 1694 | Future Task |  |  | I-WP110 | Kimberly Kemp | Approve | I-WP110 Training Build - Approve | 0 hrs | 0 days | 2025-09-30 | 2025-09-30 | 1693 |  |  | Jimmy Cox
3006 | 1695 | Future Task |  |  | I-WP111 | Kimberly Kemp |  | I-WP111 UAT Training Materials | 129 hrs | 154 days | 2024-08-01 | 2025-03-13
3007 | 1696 | Future Task |  |  | I-WP111 | Carolyn Hicks | Create | WPED - I-WP111 - UAT Training Materials - Create | 10 hrs | 10 days | 2024-08-01 | 2024-08-14 | 1 | 1697 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila
3008 | 1697 | Future Task |  |  | I-WP111 | Carolyn Hicks | Submit | WPED - I-WP111 - UAT Training Materials - Submit | 0 hrs | 0 days | 2024-08-14 | 2024-08-14 | 1696 | 1698 |  | Carolyn Hicks
3009 | 1698 | Future Task |  |  | I-WP111 | Carolyn Hicks | Review | WPED - I-WP111 - UAT Training Materials - Collaborative Review and Update | 10 hrs | 10 days | 2024-08-15 | 2024-08-28 | 1697 | 1699 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
3010 | 1699 | Future Task |  |  | I-WP111 | Carolyn Hicks | Approve | WPED - I-WP111 - UAT Training Materials - Approve | 0 hrs | 0 days | 2024-08-28 | 2024-08-28 | 1698 | 1700 |  | Angie Robertson,Jimmy Cox
5692 | 1700 | Future Task |  |  | I-WP111 | Kimberly Kemp | Create | I-WP111 UAT Training Materials <Activities per WPED> | 80 hrs | 117 days | 2024-08-29 | 2025-02-18 | 1699 | 1701 |  | Kimberly Kemp
3011 | 1701 | Future Task |  |  | I-WP111 | Kimberly Kemp | Submit | I-WP111 UAT Training Materials - Submit | 0 hrs | 0 days | 2025-02-18 | 2025-02-18 | 1700 | 1702 |  | Kimberly Kemp
3012 | 1702 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | I-WP111 UAT Training Materials - Dept QC | 1 hr | 1 day | 2025-02-19 | 2025-02-19 | 1701 | 1703 |  | Tommy Werner
3013 | 1703 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | I-WP111 UAT Training Materials - Collaborative Review and Update | 10 hrs | 10 days | 2025-02-20 | 2025-03-05 | 1702 | 1704 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3014 | 1704 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | I-WP111 UAT Training Materials - Style Guide Review | 8 hrs | 1 day | 2025-03-06 | 2025-03-06 | 1703 | 1705 |  | Tatiana Eubanks
3015 | 1705 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | I-WP111 UAT Training Materials - Final Review and Update | 10 hrs | 5 days | 2025-03-07 | 2025-03-13 | 1704 | 1706 |  | Angie Robertson,Jimmy Cox
3016 | 1706 | Future Task |  |  | I-WP111 | Kimberly Kemp | Approve | I-WP111 UAT Training Materials - Approve | 0 hrs | 0 days | 2025-03-13 | 2025-03-13 | 1705 | 1707 |  | Jimmy Cox
3017 | 1707 | Future Task |  |  | I-WP111 | Kimberly Kemp | Milestone | I-WP111 UAT Training Materials Complete | 0 hrs | 0 days | 2025-03-13 | 2025-03-13 | 1706 | 1250 |  | Kimberly Kemp | Why is this task a Milestone? --> remove | Angie
3018 | 1708 | Future Task |  |  | I-WP112 | Kimberly Kemp |  | I-WP112 End User Manual | 143 hrs | 210 days | 2025-01-31 | 2025-11-26
3019 | 1709 | Future Task |  |  | I-WP112 | Carolyn Hicks | Create | WPED - I-WP112 - End User Manual - Create | 10 hrs | 10 days | 2025-01-31 | 2025-02-13 | 1 | 1710 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3020 | 1710 | Future Task |  |  | I-WP112 | Carolyn Hicks | Submit | WPED - I-WP112 - End User Manual - Submit | 0 hrs | 0 days | 2025-02-13 | 2025-02-13 | 1709 | 1711 |  | Carolyn Hicks
3021 | 1711 | Future Task |  |  | I-WP112 | Carolyn Hicks | Review | WPED - I-WP112 - End User Manual - Collaborative Review and Update | 10 hrs | 10 days | 2025-02-14 | 2025-02-27 | 1710 | 1712 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3022 | 1712 | Future Task |  |  | I-WP112 | Carolyn Hicks | Approve | WPED - I-WP112 - End User Manual - Approve | 0 hrs | 0 days | 2025-02-27 | 2025-02-27 | 1711 | 1713 |  | Angie Robertson,Jimmy Cox
5693 | 1713 | Future Task |  |  | I-WP112 | Kimberly Kemp | Create | I-WP112 End User Manual <Activities per WPED> | 100 hrs | 173 days | 2025-02-28 | 2025-10-31 | 1712649 | 1714 |  | Kimberly Kemp
3023 | 1714 | Future Task |  |  | I-WP112 | Kimberly Kemp | Submit | I-WP112 End User Manual - Submit | 0 hrs | 0 days | 2025-10-31 | 2025-10-31 | 1713 | 1715 |  | Kimberly Kemp
3024 | 1715 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | I-WP112 End User Manual - Dept QC | 1 hr | 1 day | 2025-11-03 | 2025-11-03 | 1714 | 1716 |  | Tommy Werner
3025 | 1716 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | I-WP112 End User Manual - Collaborative Review and Update | 10 hrs | 10 days | 2025-11-04 | 2025-11-18 | 1715 | 1717 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3026 | 1717 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | I-WP112 End User Manual - Style Guide Review | 2 hrs | 1 day | 2025-11-19 | 2025-11-19 | 1716 | 1718 |  | Tatiana Eubanks
3027 | 1718 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | I-WP112 End User Manual - Final Review and Update | 10 hrs | 5 days | 2025-11-20 | 2025-11-26 | 1717 | 1719 |  | Angie Robertson,Jimmy Cox
3028 | 1719 | Future Task |  |  | I-WP112 | Kimberly Kemp | Approve | I-WP112 End User Manual - Approve | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 1718 | 1720 |  | Jimmy Cox
3029 | 1720 | Future Task |  |  | I-WP112 | Kimberly Kemp | Milestone | I-WP112 End User Manual Complete | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 1719 |  |  | Kimberly Kemp | Why is this task a Milestone? --> remove | Angie
3030 | 1721 | Future Task |  |  | I-WP113 | Kimberly Kemp |  | I-WP113 ILT Training Delivery Plan | 156 hrs | 85 days | 2025-05-01 | 2025-08-29
3031 | 1722 | Future Task |  |  | I-WP113 | Carolyn Hicks | Create | WPED - I-WP113 - ILT Training Delivery Plan - Create | 10 hrs | 10 days | 2025-05-01 | 2025-05-14 | 1 | 1723 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
3032 | 1723 | Future Task |  |  | I-WP113 | Carolyn Hicks | Submit | WPED - I-WP113 - ILT Training Delivery Plan - Submit | 0 hrs | 0 days | 2025-05-14 | 2025-05-14 | 1722 | 1724 |  | Carolyn Hicks
3033 | 1724 | Future Task |  |  | I-WP113 | Carolyn Hicks | Review | WPED - I-WP113 - ILT Training Delivery Plan - Collaborative Review and Update | 10 hrs | 10 days | 2025-05-15 | 2025-05-29 | 1723 | 1725 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
3034 | 1725 | Future Task |  |  | I-WP113 | Carolyn Hicks | Approve | WPED - I-WP113- ILT Training Delivery Plan - Approve | 0 hrs | 0 days | 2025-05-29 | 2025-05-29 | 1724 | 1726 |  | Angie Robertson,Jimmy Cox
5694 | 1726 | Future Task |  |  | I-WP113 | Kimberly Kemp | Create | I-WP113 ILT Training Delivery Plan <Activities per WPED> | 100 hrs | 48 days | 2025-05-30 | 2025-08-06 | 1725 | 1727 |  | Kimberly Kemp
3035 | 1727 | Future Task |  |  | I-WP113 | Kimberly Kemp | Submit | I-WP113 ILT Training Delivery Plan - Submit | 0 hrs | 0 days | 2025-08-06 | 2025-08-06 | 1726 | 1728 |  | Kimberly Kemp
3036 | 1728 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | I-WP113 ILT Training Delivery Plan - Dept QC | 8 hrs | 1 day | 2025-08-07 | 2025-08-07 | 1727 | 1729 |  | Gabriela Gibson
3037 | 1729 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | I-WP113 ILT Training Delivery Plan - Collaborative Review and Update | 10 hrs | 10 days | 2025-08-08 | 2025-08-21 | 1728 | 1730 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3038 | 1730 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | I-WP113 ILT Training Delivery Plan - Style Guide Review | 8 hrs | 1 day | 2025-08-22 | 2025-08-22 | 1729 | 1731 |  | Tatiana Eubanks
3039 | 1731 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | I-WP113 ILT Training Delivery Plan - Final Review and Update | 10 hrs | 5 days | 2025-08-25 | 2025-08-29 | 1730 | 1732 |  | Angie Robertson,Jimmy Cox
3040 | 1732 | Future Task |  |  | I-WP113 | Kimberly Kemp | Approve | I-WP113 ILT Training Delivery Plan - Approve | 0 hrs | 0 days | 2025-08-29 | 2025-08-29 | 1731 |  |  | Jimmy Cox
3041 | 1733 | Future Task |  |  | I-WP114 | Kimberly Kemp |  | I-WP114 Training Measurement Report | 143 hrs | 104 days | 2025-10-29 | 2026-03-31
3042 | 1734 | Future Task |  |  | I-WP114 | Carolyn Hicks | Create | WPED - I-WP114 - Training Measurement Report - Create | 10 hrs | 10 days | 2025-10-29 | 2025-11-12 | 1 | 1735 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell
3043 | 1735 | Future Task |  |  | I-WP114 | Kimberly Kemp | Submit | WPED - I-WP114 - Training Measurement Report - Submit | 0 hrs | 0 days | 2025-11-12 | 2025-11-12 | 1734 | 1736 |  | Carolyn Hicks
3044 | 1736 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WPED - I-WP114 - Training Measurement Report - Collaborative Review and Update | 10 hrs | 10 days | 2025-11-13 | 2025-11-26 | 1735 | 1737 |  | Carolyn Hicks,Kimberly Kemp,Renee Whitsell,Angie Robertson
3045 | 1737 | Future Task |  |  | I-WP114 | Kimberly Kemp | Approve | WPED - I-WP114 - Training Measurement Report - Approve | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 1736 | 1738 |  | Angie Robertson,Jimmy Cox
5695 | 1738 | Future Task |  |  | I-WP114 | Kimberly Kemp | Create | I-WP114 Training Measurement Report <Activities per WPED> | 100 hrs | 67 days | 2025-12-01 | 2026-03-06 | 17371250 | 1739 |  | Kimberly Kemp
3046 | 1739 | Future Task |  |  | I-WP114 | Kimberly Kemp | Submit | I-WP114 Training Measurement Report - Submit | 0 hrs | 0 days | 2026-03-06 | 2026-03-06 | 1738 | 1740 |  | Kimberly Kemp
3047 | 1740 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | I-WP114 Training Measurement Report - Dept QC | 1 hr | 1 day | 2026-03-09 | 2026-03-09 | 1739 | 1741 |  | Tommy Werner
3048 | 1741 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | I-WP114 Training Measurement Report - Collaborative Review and Update | 10 hrs | 10 days | 2026-03-10 | 2026-03-23 | 1740 | 1742 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3049 | 1742 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | I-WP114 Training Measurement Report - Style Guide Review | 2 hrs | 1 day | 2026-03-24 | 2026-03-24 | 1741 | 1743 |  | Dusti Kincl
3050 | 1743 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | I-WP114 Training Measurement Report - Final Review and Update | 10 hrs | 5 days | 2026-03-25 | 2026-03-31 | 1742 | 1744 |  | Angie Robertson,Jimmy Cox
3051 | 1744 | Future Task |  |  | I-WP114 | Kimberly Kemp | Approve | Training Measurement Report - Approve | 0 hrs | 0 days | 2026-03-31 | 2026-03-31 | 1743 |  |  | Jimmy Cox
3052 | 1745 | Future Task |  |  | I-WP115 | Kimberly Kemp |  | I-WP115 Train the Trainer | 156 hrs | 372 days | 2025-08-01 | 2027-01-26
3053 | 1746 | Future Task |  |  | I-WP115 | Carolyn Hicks | Create | WPED - I-WP115 - Train the Trainer - Create | 10 hrs | 10 days | 2025-08-01 | 2025-08-14 | 1 | 1747 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila
3054 | 1747 | Future Task |  |  | I-WP115 | Carolyn Hicks | Submit | WPED - I-WP115 - Train the Trainer - Submit | 0 hrs | 0 days | 2025-08-14 | 2025-08-14 | 1746 | 1748 |  | Carolyn Hicks
3055 | 1748 | Future Task |  |  | I-WP115 | Carolyn Hicks | Review | WPED - I-WP115 - Train the Trainer - Collaborative Review and Update | 10 hrs | 10 days | 2025-08-15 | 2025-08-28 | 1747 | 1749 |  | Carolyn Hicks,Kimberly Kemp,Brenda Vila,Angie Robertson
3056 | 1749 | Future Task |  |  | I-WP115 | Carolyn Hicks | Approve | WPED - I-WP115 - Train the Trainer - Approve | 0 hrs | 0 days | 2025-08-28 | 2025-08-28 | 1748 | 1750 |  | Angie Robertson,Jimmy Cox
5696 | 1750 | Future Task |  |  | I-WP115 | Kimberly Kemp | Create | I-WP115 Train the Trainer <Activities per WPED> | 100 hrs | 324 days | 2025-08-29 | 2026-12-14 | 17491682 | 1751FS+11 days |  | Kimberly Kemp
3057 | 1751 | Future Task |  |  | I-WP115 | Kimberly Kemp | Submit | I-WP115 Train the Trainer - Submit | 0 hrs | 0 days | 2026-12-30 | 2026-12-30 | 1750FS+11 days | 1752 |  | Kimberly Kemp
3058 | 1752 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | I-WP115 Train the Trainer - Dept QC | 8 hrs | 1 day | 2026-12-31 | 2026-12-31 | 1751 | 1753 |  | Gabriela Gibson
3059 | 1753 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | I-WP115 Train the Trainer - Collaborative Review and Update | 10 hrs | 10 days | 2027-01-04 | 2027-01-15 | 1752 | 1754 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3060 | 1754 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | I-WP115 Train the Trainer - Style Guide Review | 8 hrs | 1 day | 2027-01-19 | 2027-01-19 | 1753 | 1755 |  | Tatiana Eubanks
3061 | 1755 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | I-WP115 Train the Trainer - Final Review and Update | 10 hrs | 5 days | 2027-01-20 | 2027-01-26 | 1754 | 1756 |  | Angie Robertson,Jimmy Cox
3062 | 1756 | Future Task |  |  | I-WP115 | Kimberly Kemp | Approve | I-WP115 Train the Trainer - Approve | 0 hrs | 0 days | 2027-01-26 | 2027-01-26 | 1755 | 1757 |  | Jimmy Cox
3063 | 1757 | Future Task |  |  | I-WP115 | Kimberly Kemp | Milestone | Train the Trainer Complete | 0 hrs | 0 days | 2027-01-26 | 2027-01-26 | 1756 |  |  | Kimberly Kemp | Why is this task a Milestone? --> remove | Angie
3064 | 1758 | Future Task |  |  | I-WP122 | Carolyn Hicks |  | I-WP122 - Update D33 Training Strategy | 143 hrs | 81 days | 2023-11-01 | 2024-02-29
3065 | 1759 | Future Task |  |  | I-WP122 | Carolyn Hicks | Create | WPED - I-WP122 - Update D33 Training Strategy - Create | 10 hrs | 10 days | 2023-11-01 | 2023-11-15 | 1 | 1760 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3066 | 1760 | Future Task |  |  | I-WP122 | Carolyn Hicks | Submit | WPED - I-WP122 - Update D33 Training Strategy - Submit | 0 hrs | 0 days | 2023-11-15 | 2023-11-15 | 1759 | 1761 |  | Carolyn Hicks
3067 | 1761 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WPED - I-WP122 - Update D33 Training Strategy - Collaborative Review and Update | 10 hrs | 10 days | 2023-11-16 | 2023-12-01 | 1760 | 1762 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3068 | 1762 | Future Task |  |  | I-WP122 | Carolyn Hicks | Approve | WPED - I-WP122 - Update D33 Training Strategy - Approve | 0 hrs | 0 days | 2023-12-01 | 2023-12-01 | 1761 | 1763 |  | Angie Robertson,Jimmy Cox
5697 | 1763 | Future Task |  |  | I-WP122 | Carolyn Hicks | Create | I-WP122 Update D33 Training Strategy <Activities per WPED> | 100 hrs | 44 days | 2023-12-04 | 2024-02-06 | 1762 | 1764 |  | Kimberly Kemp
3069 | 1764 | Future Task |  |  | I-WP122 | Carolyn Hicks | Submit | I-WP122 Update D33 Training Strategy - Submit | 0 hrs | 0 days | 2024-02-06 | 2024-02-06 | 1763 | 1765 |  | Kimberly Kemp
3070 | 1765 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | I-WP122 Update D33 Training Strategy - Dept QC | 1 hr | 1 day | 2024-02-07 | 2024-02-07 | 1764 | 1766 |  | Tommy Werner
3071 | 1766 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | I-WP122Update D33 Training Strategy - Collaborative Review and Update | 10 hrs | 10 days | 2024-02-08 | 2024-02-21 | 1765 | 1767 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3072 | 1767 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | I-WP122 Update D33 Training Strategy - Style Guide Review | 2 hrs | 1 day | 2024-02-22 | 2024-02-22 | 1766 | 1768 |  | Dusti Kincl
3073 | 1768 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | I-WP122 Update D33 Training Strategy - Final Review and Update | 10 hrs | 5 days | 2024-02-23 | 2024-02-29 | 1767 | 1769 |  | Angie Robertson,Jimmy Cox
3074 | 1769 | Future Task |  |  | I-WP122 | Carolyn Hicks | Approve | I-WP122 Update D33 Training Strategy - Approve | 0 hrs | 0 days | 2024-02-29 | 2024-02-29 | 1768 |  |  | Jimmy Cox
3075 | 1770 | Future Task |  |  | I-WP123 | Carolyn Hicks |  | I-WP123 - Update D112 Training Deployment and Measurement Plan | 149 hrs | 81 days | 2023-11-01 | 2024-02-29
3076 | 1771 | Future Task |  |  | I-WP123 | Carolyn Hicks | Create | WPED - I-WP123 - Update D112 Training Deployment and Measurement Plan - Create | 10 hrs | 10 days | 2023-11-01 | 2023-11-15 | 1 | 1772 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3077 | 1772 | Future Task |  |  | I-WP123 | Carolyn Hicks | Submit | WPED - I-WP123 - Update D112 Training Deployment and Measurement Plan - Submit | 0 hrs | 0 days | 2023-11-15 | 2023-11-15 | 1771 | 1773 |  | Carolyn Hicks
3078 | 1773 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WPED - I-WP123 - Update D112 Training Deployment and Measurement Plan - Collaborative Review and Update | 10 hrs | 10 days | 2023-11-16 | 2023-12-01 | 1772 | 1774 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3079 | 1774 | Future Task |  |  | I-WP123 | Carolyn Hicks | Approve | WPED - I-WP123 - Update D112 Training Deployment and Measurement Plan - Approve | 0 hrs | 0 days | 2023-12-01 | 2023-12-01 | 1773 | 1775 |  | Angie Robertson,Jimmy Cox
5698 | 1775 | Future Task |  |  | I-WP123 | Carolyn Hicks | Create | I-WP123 Update D112 Training Deployment and Measurement Plan <Activities per WPED> | 100 hrs | 44 days | 2023-12-04 | 2024-02-06 | 1774 | 1776 |  | Kimberly Kemp
3080 | 1776 | Future Task |  |  | I-WP123 | Carolyn Hicks | Submit | I-WP123 Update D112 Training Deployment and Measurement Plan - Submit | 0 hrs | 0 days | 2024-02-06 | 2024-02-06 | 1775 | 1777 |  | Kimberly Kemp
3081 | 1777 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | I-WP123 Update D112 Training Deployment and Measurement Plan - Dept QC | 1 hr | 1 day | 2024-02-07 | 2024-02-07 | 1776 | 1778 |  | Tommy Werner
3082 | 1778 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | I-WP123Update D112 Training Deployment and Measurement Plan - Collaborative Review and Update | 10 hrs | 10 days | 2024-02-08 | 2024-02-21 | 1777 | 1779 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3083 | 1779 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | I-WP123 Update D112 Training Deployment and Measurement Plan - Style Guide Review | 8 hrs | 1 day | 2024-02-22 | 2024-02-22 | 1778 | 1780 |  | Tatiana Eubanks
3084 | 1780 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | I-WP123 Update D112 Training Deployment and Measurement Plan - Final Review and Update | 10 hrs | 5 days | 2024-02-23 | 2024-02-29 | 1779 | 1781 |  | Angie Robertson,Jimmy Cox
3085 | 1781 | Future Task |  |  | I-WP123 | Carolyn Hicks | Approve | I-WP123 Update D112 Training Deployment and Measurement Plan - Approve | 0 hrs | 0 days | 2024-02-29 | 2024-02-29 | 1780 |  |  | Jimmy Cox
6812 | 1782 | Future Task | [5 empty] | Training | 1 hr | 104 days | 2025-07-01 | 2025-11-26
6813 | 1783 | Future Task |  |  |  | Carolyn Hicks |  | Conduct Training | 1 hr | 104 days | 2025-07-01 | 2025-11-26 | 1 |  | July - Nov 2025 | Carolyn Hicks
3086 | 1784 | Late | [5 empty] | Readiness | 876 hrs | 730 days | 2023-05-08 | 2026-03-31
7159 | 1785 | Future Task | Yes |  | SG4 | Jimmy Cox | Milestone | Stage Gate 4: Agency Readiness | 0 hrs | 0 days | 2025-11-03 | 2025-11-03 | 1 |  | November 2025 - ESC | Jimmy Cox,Angie Robertson,Matt Cole | The Resource Names include the ESC and we need tasks / dates for ESC review prior to milestone date. | Angie
3087 | 1786 | Future Task |  |  | I-WP116 | Kimberly Kemp |  | I-WP116 User Support Sessions | 156 hrs | 209 days | 2025-06-02 | 2026-03-31
3088 | 1787 | Future Task |  |  | I-WP116 | Carolyn Hicks | Create | WPED - I-WP116 - User Support Sessions - Create | 10 hrs | 10 days | 2025-06-02 | 2025-06-13 | 1 | 1788 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling
3089 | 1788 | Future Task |  |  | I-WP116 | Carolyn Hicks | Submit | WPED - I-WP116 - User Support Sessions - Submit | 0 hrs | 0 days | 2025-06-13 | 2025-06-13 | 1787 | 1789 |  | Carolyn Hicks
3090 | 1789 | Future Task |  |  | I-WP116 | Carolyn Hicks | Review | WPED - I-WP116 - User Support Sessions - Collaborative Review and Update | 10 hrs | 10 days | 2025-06-16 | 2025-06-27 | 1788 | 1790 |  | Carolyn Hicks,Kimberly Kemp,TJ Darling,Angie Robertson
3091 | 1790 | Future Task |  |  | I-WP116 | Carolyn Hicks | Approve | WPED - I-WP116 - User Support Sessions - Approve | 0 hrs | 0 days | 2025-06-27 | 2025-06-27 | 1789 | 1791 |  | Angie Robertson,Jimmy Cox
5699 | 1791 | Future Task |  |  | I-WP116 | Kimberly Kemp | Create | I-WP116 User Support Sessions <Activities per WPED> | 100 hrs | 172 days | 2025-06-30 | 2026-03-06 | 1790,1250SS+30 days | 1792 |  | Kimberly Kemp
3092 | 1792 | Future Task |  |  | I-WP116 | Kimberly Kemp | Submit | I-WP116 User Support Sessions - Submit | 0 hrs | 0 days | 2026-03-06 | 2026-03-06 | 1791 | 1793 |  | Kimberly Kemp
3093 | 1793 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | I-WP116 User Support Sessions - Dept QC | 8 hrs | 1 day | 2026-03-09 | 2026-03-09 | 1792 | 1794 |  | Gabriela Gibson
3094 | 1794 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | I-WP116 User Support Sessions - Collaborative Review and Update | 10 hrs | 10 days | 2026-03-10 | 2026-03-23 | 1793 | 1795 |  | Kimberly Kemp,Brenda Vila,TJ Darling,Renee Whitsell
3095 | 1795 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | I-WP116 User Support Sessions - Style Guide Review | 8 hrs | 1 day | 2026-03-24 | 2026-03-24 | 1794 | 1796 |  | Tatiana Eubanks
3096 | 1796 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | I-WP116User Support Sessions - Final Review and Update | 10 hrs | 5 days | 2026-03-25 | 2026-03-31 | 1795 | 1797 |  | Angie Robertson,Jimmy Cox
3097 | 1797 | Future Task |  |  | I-WP116 | Kimberly Kemp | Approve | I-WP116 User Support Sessions - Approve | 0 hrs | 0 days | 2026-03-31 | 2026-03-31 | 1796 |  |  | Jimmy Cox
3098 | 1798 | Future Task |  |  | I-WP117 | Nikki Klein |  | I-WP117 Role Mapping Handbook | 149 hrs | 193 days | 2024-02-01 | 2024-10-31
3099 | 1799 | Future Task |  |  | I-WP117 | Carolyn Hicks | Create | WPED - I-WP117- Role Mapping Handbook - Create | 10 hrs | 10 days | 2024-02-01 | 2024-02-14 | 1 | 1800 |  | Carolyn Hicks,Nikki Klein,Felicia Hall
3100 | 1800 | Future Task |  |  | I-WP117 | Carolyn Hicks | Submit | WPED - I-WP117 - Role Mapping Handbook - Submit | 0 hrs | 0 days | 2024-02-14 | 2024-02-14 | 1799 | 1801 |  | Carolyn Hicks
3101 | 1801 | Future Task |  |  | I-WP117 | Carolyn Hicks | Review | WPED - I-WP117 - Role Mapping Handbook - Collaborative Review and Update | 10 hrs | 10 days | 2024-02-15 | 2024-02-28 | 1800 | 1802 |  | Carolyn Hicks,Nikki Klein,Felicia Hall,Angie Robertson
3102 | 1802 | Future Task |  |  | I-WP117 | Carolyn Hicks | Approve | WPED - I-WP117 - Role Mapping Handbook - Approve | 0 hrs | 0 days | 2024-02-28 | 2024-02-28 | 1801 | 1803 |  | Angie Robertson,Jimmy Cox
5700 | 1803 | Future Task |  |  | I-WP117 | Nikki Klein | Create | I-WP117 Role Mapping Handbook <Activities per WPED> | 100 hrs | 156 days | 2024-02-29 | 2024-10-08 | 1802105 | 1804,1815SS+40 days |  | Nikki Klein
3103 | 1804 | Future Task |  |  | I-WP117 | Nikki Klein | Submit | I-WP117 Role Mapping Handbook - Submit | 0 hrs | 0 days | 2024-10-08 | 2024-10-08 | 1803 | 1805 |  | Nikki Klein
3104 | 1805 | Future Task |  |  | I-WP117 | Nikki Klein | Review | I-WP117 Role Mapping Handbook - Dept QC | 1 hr | 1 day | 2024-10-09 | 2024-10-09 | 1804 | 1806 |  | Gabriela Gibson
3105 | 1806 | Future Task |  |  | I-WP117 | Nikki Klein | Review | I-WP117 Role Mapping Handbook - Collaborative Review and Update | 10 hrs | 10 days | 2024-10-10 | 2024-10-23 | 1805 | 1807 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3106 | 1807 | Future Task |  |  | I-WP117 | Nikki Klein | Review | I-WP117 Role Mapping Handbook - Style Guide Review | 8 hrs | 1 day | 2024-10-24 | 2024-10-24 | 1806 | 1808 |  | Tatiana Eubanks
3107 | 1808 | Future Task |  |  | I-WP117 | Nikki Klein | Review | I-WP117 Role Mapping Handbook - Final Review and Update | 10 hrs | 5 days | 2024-10-25 | 2024-10-31 | 1807 | 1809 |  | Angie Robertson,Jimmy Cox
3108 | 1809 | Future Task |  |  | I-WP117 | Nikki Klein | Approve | I-WP117 Role Mapping Handbook - Approve | 0 hrs | 0 days | 2024-10-31 | 2024-10-31 | 1808 |  |  | Jimmy Cox
3109 | 1810 | Future Task | Yes |  | I-WP118 | Nikki Klein |  | I-WP118 Role Mapping Worksheet | 156 hrs | 193 days | 2024-06-03 | 2025-03-10
3110 | 1811 | Future Task |  |  | I-WP118 | Carolyn Hicks | Create | WPED - I-WP118 - Role Mapping Worksheet - Create | 10 hrs | 10 days | 2024-06-03 | 2024-06-14 | 1 | 1812 |  | Carolyn Hicks,Nikki Klein,Felicia Hall
3111 | 1812 | Future Task |  |  | I-WP118 | Carolyn Hicks | Submit | WPED - I-WP118 - Role Mapping Worksheet - Submit | 0 hrs | 0 days | 2024-06-14 | 2024-06-14 | 1811 | 1813 |  | Carolyn Hicks
3112 | 1813 | Future Task |  |  | I-WP118 | Carolyn Hicks | Review | WPED - I-WP118 - Role Mapping Worksheet - Collaborative Review and Update | 10 hrs | 10 days | 2024-06-17 | 2024-06-28 | 1812 | 1814 |  | Carolyn Hicks,Nikki Klein,Felicia Hall,Angie Robertson
3113 | 1814 | Future Task |  |  | I-WP118 | Carolyn Hicks | Approve | WPED - I-WP118 - Role Mapping Worksheet - Approve | 0 hrs | 0 days | 2024-06-28 | 2024-06-28 | 1813 | 1815 |  | Angie Robertson,Jimmy Cox
5701 | 1815 | Future Task |  |  | I-WP118 | Nikki Klein | Create | I-WP118 Role Mapping Worksheet <Activities per WPED> | 100 hrs | 125 days | 2024-08-14 | 2025-02-13 | 1814,1803SS+40 days,1863SS+40 days,579 | 1816 |  | Nikki Klein
3114 | 1816 | Future Task |  |  | I-WP118 | Nikki Klein | Submit | I-WP118 Role Mapping Worksheet - Submit | 0 hrs | 0 days | 2025-02-13 | 2025-02-13 | 1815 | 1817 |  | Nikki Klein
3115 | 1817 | Future Task |  |  | I-WP118 | Nikki Klein | Review | I-WP118 Role Mapping Worksheet - Dept QC | 8 hrs | 1 day | 2025-02-14 | 2025-02-14 | 1816 | 1818 |  | Gabriela Gibson
3116 | 1818 | Future Task |  |  | I-WP118 | Nikki Klein | Review | I-WP118 Role Mapping Worksheet - Collaborative Review and Update | 10 hrs | 10 days | 2025-02-17 | 2025-02-28 | 1817 | 1819 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3117 | 1819 | Future Task |  |  | I-WP118 | Nikki Klein | Review | I-WP118 Role Mapping Worksheet - Style Guide Review | 8 hrs | 1 day | 2025-03-03 | 2025-03-03 | 1818 | 1820 |  | Tatiana Eubanks
3118 | 1820 | Future Task |  |  | I-WP118 | Nikki Klein | Review | I-WP118 Role Mapping Worksheet - Final Review and Update | 10 hrs | 5 days | 2025-03-04 | 2025-03-10 | 1819 | 1821 |  | Angie Robertson,Jimmy Cox
3119 | 1821 | Future Task |  |  | I-WP118 | Nikki Klein | Approve | I-WP118 Role Mapping Worksheet - Approve | 0 hrs | 0 days | 2025-03-10 | 2025-03-10 | 1820 | 568 |  | Jimmy Cox | Role Mapping Worksheet needs to be approved by 12/15/2024, so agencies can role map before UAT I updated the duration of the work tasks (which needs to be defined) to 67 days instead of 125. This has the WP accept on Friday December 13, 2024. Where are the details to show the agency work? Will this be a new WP or should there be some milestone tasks following the accept of this WP that could tie to the RW. For example "Send Role Mapping Worksheets to Agencies" and then a work task for the team to consilidate the worksheets, etc. | NK
3120 | 1822 | Future Task |  |  | I-WP119 | Nikki Klein |  | I-WP119 Change Impact Analysis | 66 hrs | 188 days | 2023-11-01 | 2024-07-31 |  |  |  |  | Change name to Change Analysis | NK
3121 | 1823 | Future Task |  |  | I-WP119 | Carolyn Hicks | Create | WPED - I-WP119 - Change Impact Analysis - Create | 10 hrs | 10 days | 2023-11-01 | 2023-11-15 | 1 | 1824 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas
3122 | 1824 | Future Task |  |  | I-WP119 | Carolyn Hicks | Submit | WPED - I-WP119 - Change Impact Analysis - Submit | 0 hrs | 0 days | 2023-11-15 | 2023-11-15 | 1823 | 1825 |  | Carolyn Hicks
3123 | 1825 | Future Task |  |  | I-WP119 | Carolyn Hicks | Review | WPED - I-WP119 - Change Impact Analysis - Collaborative Review and Update | 10 hrs | 10 days | 2023-11-16 | 2023-12-01 | 1824 | 1826 |  | Carolyn Hicks,Nikki Klein,Kim York,Angie Robertson,Dora Thomas
3124 | 1826 | Future Task |  |  | I-WP119 | Carolyn Hicks | Approve | WPED - I-WP119 - Change Impact Analysis | 0 hrs | 0 days | 2023-12-01 | 2023-12-01 | 1825 | 1827 |  | Angie Robertson,Jimmy Cox
6814 | 1827 | Future Task |  |  | I-WP119 | Nikki Klein | Submit | I-WP119 Change Impact Analysis <Activities per WPED> | 10 hrs | 151 days | 2023-12-04 | 2024-07-08 | 1826 | 1828 |  | Nikki Klein
3125 | 1828 | Future Task |  |  | I-WP119 | Nikki Klein | Submit | I-WP119 Change Impact Analysis - Submit | 0 hrs | 0 days | 2024-07-08 | 2024-07-08 | 1827 | 1829 |  | Nikki Klein
3126 | 1829 | Future Task |  |  | I-WP119 | Nikki Klein | Review | I-WP119 Change Impact Analysis - Dept QC | 8 hrs | 1 day | 2024-07-09 | 2024-07-09 | 1828 | 1830 |  | Gabriela Gibson
3127 | 1830 | Future Task |  |  | I-WP119 | Nikki Klein | Review | I-WP119 Change Impact Analysis - Collaborative Review and Update | 10 hrs | 10 days | 2024-07-10 | 2024-07-23 | 1829 | 1831 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3128 | 1831 | Future Task |  |  | I-WP119 | Nikki Klein | Review | I-WP119 Change Impact Analysis - Style Guide Review | 8 hrs | 1 day | 2024-07-24 | 2024-07-24 | 1830 | 1832 |  | Tatiana Eubanks
3129 | 1832 | Future Task |  |  | I-WP119 | Nikki Klein | Review | I-WP119 Change Impact Analysis - Final Review and Update | 10 hrs | 5 days | 2024-07-25 | 2024-07-31 | 1831 | 1833 |  | Angie Robertson,Jimmy Cox
3130 | 1833 | Future Task |  |  | I-WP119 | Nikki Klein | Approve | I-WP119 Change Impact Analysis - Approve | 0 hrs | 0 days | 2024-07-31 | 2024-07-31 | 1832 |  |  | Jimmy Cox
3131 | 1834 | Future Task |  |  | I-WP121 | Carolyn Hicks |  | I-WP121 Updated D27 Readiness Plan | 143 hrs | 82 days | 2023-10-02 | 2024-01-31
3132 | 1835 | Future Task |  |  | I-WP121 | Carolyn Hicks | Create | WPED - I-WP121 - Update D27 Readiness Plan - Create | 10 hrs | 10 days | 2023-10-02 | 2023-10-13 | 1 | 1836 |  | Carolyn Hicks,Nikki Klein
3133 | 1836 | Future Task |  |  | I-WP121 | Carolyn Hicks | Submit | WPED - I-WP121 - Update D27 Readiness Plan - Submit | 0 hrs | 0 days | 2023-10-13 | 2023-10-13 | 1835 | 1837 |  | Carolyn Hicks
3134 | 1837 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WPED - I-WP121 - Update D27 Readiness Plan - Collaborative Review and Update | 10 hrs | 10 days | 2023-10-16 | 2023-10-27 | 1836 | 1838 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas,Angie Robertson
3135 | 1838 | Future Task |  |  | I-WP121 | Carolyn Hicks | Approve | WPED - I-WP121 - Update D27 Readiness Plan - Approve | 0 hrs | 0 days | 2023-10-27 | 2023-10-27 | 1837 | 1839 |  | Angie Robertson,Jimmy Cox
5702 | 1839 | Future Task |  |  | I-WP121 | Carolyn Hicks | Create | I-WP121 Update D27 Readiness Plan <Activities per WPED> | 100 hrs | 45 days | 2023-10-30 | 2024-01-05 | 1838 | 1840 |  | Nikki Klein
3136 | 1840 | Future Task |  |  | I-WP121 | Carolyn Hicks | Submit | I-WP121 Update D27 Readiness Plan - Submit | 0 hrs | 0 days | 2024-01-05 | 2024-01-05 | 1839 | 1841 |  | Nikki Klein
3137 | 1841 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | I-WP121 Update D27 Readiness Plan - Dept QC | 1 hr | 1 day | 2024-01-08 | 2024-01-08 | 1840 | 1842 |  | Gabriela Gibson
3138 | 1842 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | I-WP121Update D27 Readiness Plan - Collaborative Review and Update | 10 hrs | 10 days | 2024-01-09 | 2024-01-23 | 1841 | 1843 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3139 | 1843 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | I-WP121 Update D27 Readiness Plan - Style Guide Review | 2 hrs | 1 day | 2024-01-24 | 2024-01-24 | 1842 | 1844 |  | Dusti Kincl
3140 | 1844 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | I-WP121 Update D27 Readiness Plan - Final Review and Update | 10 hrs | 5 days | 2024-01-25 | 2024-01-31 | 1843 | 1845 |  | Angie Robertson,Jimmy Cox
3141 | 1845 | Future Task |  |  | I-WP121 | Carolyn Hicks | Approve | I-WP121 Update D27 Readiness Plan - Approve | 0 hrs | 0 days | 2024-01-31 | 2024-01-31 | 1844 |  |  | Jimmy Cox
3142 | 1846 | Future Task |  |  | I-WP124 | Carolyn Hicks |  | I-WP124 Update D62 Workforce Transition Plan | 149 hrs | 82 days | 2023-10-02 | 2024-01-31
3143 | 1847 | Future Task |  |  | I-WP124 | Carolyn Hicks | Create | WPED - I-WP124 - Update D62 Workforce Transition Plan - Create | 10 hrs | 10 days | 2023-10-02 | 2023-10-13 | 1 | 1848 |  | Carolyn Hicks,Nikki Klein,Kim York,Dora Thomas
3144 | 1848 | Future Task |  |  | I-WP124 | Carolyn Hicks | Submit | WPED - I-WP124 - Update D62 Workforce Transition Plan - Submit | 0 hrs | 0 days | 2023-10-13 | 2023-10-13 | 1847 | 1849 |  | Carolyn Hicks
3145 | 1849 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WPED - I-WP124 - Update D62 Workforce Transition Plan - Collaborative Review and Update | 10 hrs | 10 days | 2023-10-16 | 2023-10-27 | 1848 | 1850 |  | Carolyn Hicks,Nikki Klein,Kim York,Angie Robertson,Dora Thomas
3146 | 1850 | Future Task |  |  | I-WP124 | Carolyn Hicks | Approve | WPED - I-WP124 - Update D62 Workforce Transition Plan - Approve | 0 hrs | 0 days | 2023-10-27 | 2023-10-27 | 1849 | 1851 |  | Angie Robertson,Jimmy Cox
5703 | 1851 | Future Task |  |  | I-WP124 | Carolyn Hicks | Create | I-WP124 Update D62 Workforce Transition Plan <Activities per WPED> | 100 hrs | 45 days | 2023-10-30 | 2024-01-05 | 1850 | 1852 |  | Nikki Klein
3147 | 1852 | Future Task |  |  | I-WP124 | Carolyn Hicks | Submit | I-WP124 Update D62 Workforce Transition Plan - Submit | 0 hrs | 0 days | 2024-01-05 | 2024-01-05 | 1851 | 1853 |  | Nikki Klein
3148 | 1853 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | I-WP124 Update D62 Workforce Transition Plan - Dept QC | 1 hr | 1 day | 2024-01-08 | 2024-01-08 | 1852 | 1854 |  | Gabriela Gibson
3149 | 1854 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | I-WP124Update D62 Workforce Transition Plan - Collaborative Review and Update | 10 hrs | 10 days | 2024-01-09 | 2024-01-23 | 1853 | 1855 |  | Nikki Klein,Felicia Hall,Kim York,Jordan Nobles,Vincent Cicco,Dora Thomas
3150 | 1855 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | I-WP124 Update D62 Workforce Transition Plan - Style Guide Review | 8 hrs | 1 day | 2024-01-24 | 2024-01-24 | 1854 | 1856 |  | Tatiana Eubanks
3151 | 1856 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | I-WP124 Update D62 Workforce Transition Plan - Final Review and Update | 10 hrs | 5 days | 2024-01-25 | 2024-01-31 | 1855 | 1857 |  | Angie Robertson,Jimmy Cox
3152 | 1857 | Future Task |  |  | I-WP124 | Carolyn Hicks | Approve | I-WP124 Update D62 Workforce Transition Plan - Approve | 0 hrs | 0 days | 2024-01-31 | 2024-01-31 | 1856 |  |  | Jimmy Cox
6777 | 1858 | Late | Yes |  | I-WP126 | Nikki Klein |  | I-WP126 Readiness Workplan | 57 hrs | 62 days | 2023-05-08 | 2023-08-03
6778 | 1859 | Late |  |  | I-WP126 | Carolyn Hicks | Create | WPED - I-WP126 - Readiness Workplan - Create | 10 hrs | 10 days | 2023-05-08 | 2023-05-19 | 1 | 1860 |  | Carolyn Hicks,Nikki Klein,Jordan Nobles
6779 | 1860 | Late |  |  | I-WP126 | Carolyn Hicks | Submit | WPED - I-WP126 - Readiness Workplan - Submit | 0 hrs | 0 days | 2023-05-19 | 2023-05-19 | 1859 | 1861 |  | Carolyn Hicks
6780 | 1861 | Late |  |  | I-WP126 | Carolyn Hicks | Review | WPED - I-WP126 - Readiness Workplan - Collaborative Review and Update | 10 hrs | 10 days | 2023-05-22 | 2023-06-05 | 1860 | 1862 |  | Carolyn Hicks,Nikki Klein,Jordan Nobles,Angie Robertson
6781 | 1862 | Future Task |  |  | I-WP126 | Carolyn Hicks | Approve | WPED - I-WP126 - Readiness Workplan - Approve | 0 hrs | 0 days | 2023-06-05 | 2023-06-05 | 1861 | 1863 |  | Angie Robertson,Jimmy Cox
6782 | 1863 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 Readiness Workplan <Activities per WPED> | 10 hrs | 25 days | 2023-06-06 | 2023-07-11 | 1862 | 1864,1815SS+40 days |  | Nikki Klein
6783 | 1864 | Future Task |  |  | I-WP126 | Nikki Klein | Submit | I-WP126 Readiness Workplan - Submit | 0 hrs | 0 days | 2023-07-11 | 2023-07-11 | 1863 | 1865 |  | Nikki Klein
6784 | 1865 | Future Task |  |  | I-WP126 | Nikki Klein | Review | I-WP126 Readiness Workplan - Dept QC | 1 hr | 1 day | 2023-07-12 | 2023-07-12 | 1864 | 1866 |  | Gabriela Gibson
6785 | 1866 | Future Task |  |  | I-WP126 | Nikki Klein | Review | I-WP126 Readiness Workplan - Collaborative Review and Update | 8 hrs | 10 days | 2023-07-13 | 2023-07-26 | 1865 | 1867 |  | Nikki Klein,Jordan Nobles,Carolyn Hicks,Angie Robertson
6786 | 1867 | Future Task |  |  | I-WP126 | Nikki Klein | Review | I-WP126 Readiness Workplan - Style Guide Review | 8 hrs | 1 day | 2023-07-27 | 2023-07-27 | 1866 | 1868 |  | Tatiana Eubanks
6787 | 1868 | Future Task |  |  | I-WP126 | Nikki Klein | Review | I-WP126 Readiness Workplan - Final Review and Update | 10 hrs | 5 days | 2023-07-28 | 2023-08-03 | 1867 | 1869 |  | Angie Robertson,Jimmy Cox
6788 | 1869 | Future Task |  |  | I-WP126 | Nikki Klein | Approve | I-WP126 Readiness Workplan - Approve | 0 hrs | 0 days | 2023-08-03 | 2023-08-03 | 1868 |  |  | Jimmy Cox
3 | 1870 | Future Task | [5 empty] | Production Support | 1,863 hrs | 619 days | 2025-02-03 | 2027-07-15
5850 | 1871 | Future Task | [5 empty] | Hypercare | 517 hrs | 336 days | 2025-02-03 | 2026-06-01
5852 | 1872 | Future Task |  |  | D664 | Bryan Sohayda |  | D664 - Development of the Hypercare Support Plan | 205 hrs | 87 days | 2025-02-03 | 2025-06-04
5853 | 1873 | Future Task |  |  | D664 | Bryan Sohayda | Create | DED D664 - Development of the Hypercare Support Plan - Create | 8 hrs | 10 days | 2025-02-03 | 2025-02-14 | 1 | 1874,1943SS | 2025-02-03 | Bryan Sohayda
5854 | 1874 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DED D664 - Development of the Hypercare Support Plan - Submit | 0 hrs | 0 days | 2025-02-14 | 2025-02-14 | 1873 | 1875 |  | Bryan Sohayda,Joy Schneider
5855 | 1875 | Future Task |  |  | D664 | Bryan Sohayda | Review | DED D664 - Development of the Hypercare Support Plan - Collaborative Review | 16 hrs | 10 days | 2025-02-17 | 2025-02-28 | 1874 | 1876 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5856 | 1876 | Future Task |  |  | D664 | Bryan Sohayda | Approve | DED D664 - Development of the Hypercare Support Plan - Approve | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 1875 | 1877 |  | Jimmy Cox
5857 | 1877 | Future Task |  |  | D664 | Bryan Sohayda |  | Development of the Hypercare Support Plan | 20 hrs | 50 days | 2025-03-03 | 2025-05-09 | 1876 | 1878SS,1884 |  | Bryan Sohayda,Chetna Dewan
5858 | 1878 | Future Task |  |  | D664 | Bryan Sohayda |  | Define and document hypercare support processes and procedures | 20 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1877SS | 1879 |  | Bryan Sohayda,Chetna Dewan
5859 | 1879 | Future Task |  |  | D664 | Bryan Sohayda |  | Review hypercare support processes and procedures draft | 20 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1878 | 1880 |  | Bryan Sohayda,Chetna Dewan
5860 | 1880 | Future Task |  |  | D664 | Bryan Sohayda |  | Define and document tools used for hypercare support activities | 20 hrs | 5 days | 2025-03-24 | 2025-03-28 | 1879 | 1881 |  | Bryan Sohayda,Chetna Dewan
5861 | 1881 | Future Task |  |  | D664 | Bryan Sohayda |  | Review tools used for hypercare activities draft | 20 hrs | 5 days | 2025-03-31 | 2025-04-04 | 1880 | 1882 |  | Bryan Sohayda,Chetna Dewan
5862 | 1882 | Future Task |  |  | D664 | Bryan Sohayda |  | Determine and document resource capacity and skills needed | 20 hrs | 5 days | 2025-04-07 | 2025-04-11 | 1881 | 1883 |  | Bryan Sohayda,Chetna Dewan
5863 | 1883 | Future Task |  |  | D664 | Bryan Sohayda |  | Review resource capacity and skills needed draft | 20 hrs | 5 days | 2025-04-14 | 2025-04-18 | 1882 | 1884 |  | Bryan Sohayda,Chetna Dewan
5864 | 1884 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DEL D664 - Development of the Hypercare Support Plan - Draft Submission | 0 hrs | 0 days | 2025-05-09 | 2025-05-09 | 18771883 | 1885 |  | Bryan Sohayda,Joy Schneider
5865 | 1885 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Pre-Submission Collaborative Review | 12 hrs | 5 days | 2025-05-12 | 2025-05-16 | 1884 | 1886 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5866 | 1886 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Style Guide Review | 1 hr | 1 day | 2025-05-19 | 2025-05-19 | 1885 | 1887 |  | Dusti Kincl
5867 | 1887 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Final Collaborative Review | 12 hrs | 5 days | 2025-05-20 | 2025-05-27 | 1886 | 1888 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5868 | 1888 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Accenture QC | 4 hrs | 2 days | 2025-05-28 | 2025-05-29 | 1887 | 1889 |  | Joy Schneider
5869 | 1889 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DEL D664 - Development of the Hypercare Support Plan - Submit | 0 hrs | 0 days | 2025-05-29 | 2025-05-29 | 1888 | 1890 |  | Joy Schneider
5870 | 1890 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Department QC | 4 hrs | 1 day | 2025-05-30 | 2025-05-30 | 1889 | 1891 |  | Tommy Werner,Gabriela Gibson
5871 | 1891 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Contract Manager Review | 8 hrs | 3 days | 2025-06-02 | 2025-06-04 | 1890 | 1892 |  | Sean Buchanan
5872 | 1892 | Future Task |  |  | D664 | Bryan Sohayda | Accept | DEL D664 - Development of the Hypercare Support Plan - Accept | 0 hrs | 0 days | 2025-06-04 | 2025-06-04 | 1891 | 1894 | 2025-06-01 | Sean Buchanan
5873 | 1893 | Future Task |  |  | D680 | Bryan Sohayda |  | D680 - Hypercare Monthly Deliverable – January 2026 | 153 hrs | 80 days | 2025-11-03 | 2026-03-02
5874 | 1894 | Future Task |  |  | D680-D683 | Bryan Sohayda | Create | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Create | 80 hrs | 10 days | 2025-11-03 | 2025-11-17 | 1892 | 1895 |  | Bryan Sohayda
5875 | 1895 | Future Task |  |  | D680-D683 | Bryan Sohayda | Submit | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Submit | 0 hrs | 0 days | 2025-11-17 | 2025-11-17 | 1894 | 1896 |  | Bryan Sohayda,Joy Schneider
5876 | 1896 | Future Task |  |  | D680-D683 | Bryan Sohayda | Review | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Collaborative Review | 20 hrs | 10 days | 2025-11-18 | 2025-12-03 | 1895 | 1897 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
7150 | 1897 | Future Task |  |  | D680-D683 | Bryan Sohayda | Approve | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Approve | 0 hrs | 0 days | 2025-11-25 | 2025-11-25 | 1896 | 1898FS+44 days |  | Jimmy Cox
5877 | 1898 | Future Task |  |  | D680 | Bryan Sohayda |  | Create D680 - Hypercare Monthly Deliverable – January 2026 | 4 hrs | 4 days | 2026-02-02 | 2026-02-05 | 1897FS+44 days | 1899 |  | Bryan Sohayda
5878 | 1899 | Future Task |  |  | D680 | Bryan Sohayda | Submit | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Draft Submission | 0 hrs | 0 days | 2026-02-05 | 2026-02-05 | 1898 | 1900 |  | Joy Schneider,Bryan Sohayda
5879 | 1900 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-02-06 | 2026-02-12 | 1899 | 1901 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5880 | 1901 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Style Guide Review | 1 hr | 1 day | 2026-02-13 | 2026-02-13 | 1900 | 1902 |  | Dusti Kincl
5881 | 1902 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-02-16 | 2026-02-20 | 1901 | 1903 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5882 | 1903 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Accenture QC | 4 hrs | 2 days | 2026-02-23 | 2026-02-24 | 1902 | 1904 |  | Joy Schneider
5883 | 1904 | Future Task |  |  | D680 | Bryan Sohayda | Submit | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Submit | 0 hrs | 0 days | 2026-02-24 | 2026-02-24 | 1903 | 1905 |  | Joy Schneider
5884 | 1905 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Department QC | 4 hrs | 1 day | 2026-02-25 | 2026-02-25 | 1904 | 1906 |  | Tommy Werner
5885 | 1906 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-02-26 | 2026-03-02 | 1905 | 1907 |  | Sean Buchanan
5886 | 1907 | Future Task |  |  | D680 | Bryan Sohayda | Accept | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Accept | 0 hrs | 0 days | 2026-03-02 | 2026-03-02 | 1906 | 1909FS-1 day |  | Sean Buchanan
5887 | 1908 | Future Task |  |  | D681 | Bryan Sohayda |  | D681 - Hypercare Monthly Deliverable – February 2026 | 53 hrs | 21 days | 2026-03-02 | 2026-03-30
5888 | 1909 | Future Task |  |  | D681 | Bryan Sohayda |  | Create D681 - Hypercare Monthly Deliverable – February 2026 | 4 hrs | 4 days | 2026-03-02 | 2026-03-05 | 1907FS-1 day | 1910 |  | Bryan Sohayda
5889 | 1910 | Future Task |  |  | D681 | Bryan Sohayda | Submit | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Draft Submission | 0 hrs | 0 days | 2026-03-05 | 2026-03-05 | 1909 | 1911 |  | Joy Schneider,Bryan Sohayda
5890 | 1911 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-03-06 | 2026-03-12 | 1910 | 1912 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5891 | 1912 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Style Guide Review | 1 hr | 1 day | 2026-03-13 | 2026-03-13 | 1911 | 1913 |  | Dusti Kincl
5892 | 1913 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-03-16 | 2026-03-20 | 1912 | 1914 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5893 | 1914 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Accenture QC | 4 hrs | 2 days | 2026-03-23 | 2026-03-24 | 1913 | 1915 |  | Joy Schneider
5894 | 1915 | Future Task |  |  | D681 | Bryan Sohayda | Submit | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Submit | 0 hrs | 0 days | 2026-03-24 | 2026-03-24 | 1914 | 1916 |  | Joy Schneider
5895 | 1916 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Department QC | 4 hrs | 1 day | 2026-03-25 | 2026-03-25 | 1915 | 1917 |  | Tommy Werner
5896 | 1917 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-03-26 | 2026-03-30 | 1916 | 1918 |  | Sean Buchanan
5897 | 1918 | Future Task |  |  | D681 | Bryan Sohayda | Accept | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Accept | 0 hrs | 0 days | 2026-03-30 | 2026-03-30 | 1917 | 1920 |  | Sean Buchanan
5898 | 1919 | Future Task |  |  | D682 | Bryan Sohayda |  | D682 - Hypercare Monthly Deliverable – March 2026 | 53 hrs | 21 days | 2026-04-01 | 2026-04-29
5899 | 1920 | Future Task |  |  | D682 | Bryan Sohayda |  | Create D682 - Hypercare Monthly Deliverable – March 2026 | 4 hrs | 4 days | 2026-04-01 | 2026-04-06 | 1918 | 1921 |  | Bryan Sohayda
5900 | 1921 | Future Task |  |  | D682 | Bryan Sohayda | Submit | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Draft Submission | 0 hrs | 0 days | 2026-04-06 | 2026-04-06 | 1920 | 1922 |  | Joy Schneider,Bryan Sohayda
5901 | 1922 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-04-07 | 2026-04-13 | 1921 | 1923 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5902 | 1923 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Style Guide Review | 1 hr | 1 day | 2026-04-14 | 2026-04-14 | 1922 | 1924 |  | Dusti Kincl
5903 | 1924 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-04-15 | 2026-04-21 | 1923 | 1925 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5904 | 1925 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Accenture QC | 4 hrs | 2 days | 2026-04-22 | 2026-04-23 | 1924 | 1926 |  | Joy Schneider
5905 | 1926 | Future Task |  |  | D682 | Bryan Sohayda | Submit | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Submit | 0 hrs | 0 days | 2026-04-23 | 2026-04-23 | 1925 | 1927 |  | Joy Schneider
5906 | 1927 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Department QC | 4 hrs | 1 day | 2026-04-24 | 2026-04-24 | 1926 | 1928 |  | Tommy Werner
5907 | 1928 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-04-27 | 2026-04-29 | 1927 | 1929 |  | Sean Buchanan
5908 | 1929 | Future Task |  |  | D682 | Bryan Sohayda | Accept | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Accept | 0 hrs | 0 days | 2026-04-29 | 2026-04-29 | 1928 | 1931 |  | Sean Buchanan
5909 | 1930 | Future Task |  |  | D683 | Bryan Sohayda |  | D683 - Hypercare Monthly Deliverable – April 2026 | 53 hrs | 21 days | 2026-05-01 | 2026-06-01
5910 | 1931 | Future Task |  |  | D683 | Bryan Sohayda |  | Create D683 - Hypercare Monthly Deliverable – April 2026 | 4 hrs | 4 days | 2026-05-01 | 2026-05-06 | 1929 | 1932 |  | Bryan Sohayda
5911 | 1932 | Future Task |  |  | D683 | Bryan Sohayda | Submit | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Draft Submission | 0 hrs | 0 days | 2026-05-06 | 2026-05-06 | 1931 | 1933 |  | Joy Schneider,Bryan Sohayda
5912 | 1933 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-05-07 | 2026-05-13 | 1932 | 1934 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5913 | 1934 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Style Guide Review | 1 hr | 1 day | 2026-05-14 | 2026-05-14 | 1933 | 1935 |  | Dusti Kincl
5914 | 1935 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-05-15 | 2026-05-21 | 1934 | 1936 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5915 | 1936 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Accenture QC | 4 hrs | 2 days | 2026-05-22 | 2026-05-26 | 1935 | 1937 |  | Joy Schneider
5916 | 1937 | Future Task |  |  | D683 | Bryan Sohayda | Submit | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Submit | 0 hrs | 0 days | 2026-05-26 | 2026-05-26 | 1936 | 1938 |  | Joy Schneider
5917 | 1938 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Department QC | 4 hrs | 1 day | 2026-05-27 | 2026-05-27 | 1937 | 1939 |  | Tommy Werner
5918 | 1939 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-05-28 | 2026-06-01 | 1938 | 1940 |  | Sean Buchanan
5919 | 1940 | Future Task |  |  | D683 | Bryan Sohayda | Accept | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Accept | 0 hrs | 0 days | 2026-06-01 | 2026-06-01 | 1939 |  |  | Sean Buchanan
5851 | 1941 | Future Task | [5 empty] | Post-Implementation Support | 1,346 hrs | 619 days | 2025-02-03 | 2027-07-15
5488 | 1942 | Future Task |  |  | D665 | Bryan Sohayda |  | D665 - Updated Post-Implementation Support Plan | 154 hrs | 92 days | 2025-02-03 | 2025-06-11
5489 | 1943 | Future Task |  |  | D665 | Bryan Sohayda | Create | DED D665 - Updated Post-Implementation Support Plan - Create | 8 hrs | 10 days | 2025-02-03 | 2025-02-14 | 1873SS | 1944 |  | Bryan Sohayda
5490 | 1944 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DED D665 - Updated Post-Implementation Support Plan - Submit | 0 hrs | 0 days | 2025-02-14 | 2025-02-14 | 1943 | 1945 |  | Bryan Sohayda,Joy Schneider
5491 | 1945 | Future Task |  |  | D665 | Bryan Sohayda | Review | DED D665 - Updated Post-Implementation Support Plan - Collaborative Review | 16 hrs | 10 days | 2025-02-17 | 2025-02-28 | 1944 | 1946 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5492 | 1946 | Future Task |  |  | D665 | Bryan Sohayda | Approve | DED D665 - Updated Post-Implementation Support Plan - Approve | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 1945 | 1947 |  | Jimmy Cox
5493 | 1947 | Future Task |  |  | D665 | Bryan Sohayda |  | Create Post Implementation Support Processes and Procedures | 20 hrs | 15 days | 2025-03-03 | 2025-03-21 | 1946 | 1948 |  | Bryan Sohayda,Chetna Dewan
5494 | 1948 | Future Task |  |  | D665 | Bryan Sohayda |  | Document Post Implementation Support Tools | 20 hrs | 10 days | 2025-03-24 | 2025-04-04 | 1947 | 1949 |  | Bryan Sohayda,Chetna Dewan
5495 | 1949 | Future Task |  |  | D665 | Bryan Sohayda |  | Post-Implementation Support Resource Capacity and Skills | 20 hrs | 10 days | 2025-04-07 | 2025-04-18 | 1948 | 1950 |  | Bryan Sohayda,Chetna Dewan
5496 | 1950 | Future Task |  |  | D665 | Bryan Sohayda |  | Full draft review pre-submission | 20 hrs | 20 days | 2025-04-21 | 2025-05-16 | 1949 | 1951 |  | Bryan Sohayda,Chetna Dewan
5497 | 1951 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DEL D665 - Updated Post-Implementation Support Plan - Draft Submission | 0 hrs | 0 days | 2025-05-16 | 2025-05-16 | 1950 | 1952 |  | Bryan Sohayda,Joy Schneider
5498 | 1952 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Pre-Submission Collaborative Review | 12 hrs | 5 days | 2025-05-19 | 2025-05-23 | 1951 | 1953 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5499 | 1953 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Style Guide Review | 1 hr | 1 day | 2025-05-27 | 2025-05-27 | 1952 | 1954 |  | Dusti Kincl
5500 | 1954 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Final Collaborative Review | 21 hrs | 5 days | 2025-05-28 | 2025-06-03 | 1953 | 1955 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5501 | 1955 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Accenture QC | 4 hrs | 2 days | 2025-06-04 | 2025-06-05 | 1954 | 1956 |  | Joy Schneider
5502 | 1956 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DEL D665 - Updated Post-Implementation Support Plan - Submit | 0 hrs | 0 days | 2025-06-05 | 2025-06-05 | 1955 | 1957 |  | Joy Schneider
5503 | 1957 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Department QC | 4 hrs | 1 day | 2025-06-06 | 2025-06-06 | 1956 | 1958 |  | Tommy Werner,Gabriela Gibson
5504 | 1958 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Contract Manager Review | 8 hrs | 3 days | 2025-06-09 | 2025-06-11 | 1957 | 1959 |  | Sean Buchanan
5505 | 1959 | Future Task |  |  | D665 | Bryan Sohayda | Accept | DEL D665 - Updated Post-Implementation Support Plan - Accept | 0 hrs | 0 days | 2025-06-11 | 2025-06-11 | 1958 |  | 2025-06-01 | Sean Buchanan
5759 | 1960 | Future Task |  |  | D684 | Bryan Sohayda |  | D684 - Post-Implementation Support Monthly Deliverable – May 2026 | 122 hrs | 85 days | 2026-03-02 | 2026-06-29
5760 | 1961 | Future Task |  |  | D684-D691 | Bryan Sohayda | Create | DED Create - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 8 hrs | 5 days | 2026-03-02 | 2026-03-06 | 1 | 1962 |  | Bryan Sohayda
5761 | 1962 | Future Task |  |  | D684-D691 | Bryan Sohayda | Submit | DED Submit - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 0 hrs | 0 days | 2026-03-06 | 2026-03-06 | 1961 | 1963 |  | Bryan Sohayda,Joy Schneider
5762 | 1963 | Future Task |  |  | D684-D691 | Bryan Sohayda | Review | DED Collaborative Review & Accept - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 20 hrs | 10 days | 2026-03-09 | 2026-03-20 | 1962 | 1964 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson,Sean Buchanan
5763 | 1964 | Future Task |  |  | D684 | Bryan Sohayda |  | Create D684 - Post-Implementation Support Monthly Deliverable – May 2026 | 4 hrs | 4 days | 2026-06-01 | 2026-06-04 | 1963 | 1965 |  | Bryan Sohayda
5764 | 1965 | Future Task |  |  | D684 | Bryan Sohayda | Submit | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Draft Submission | 0 hrs | 0 days | 2026-06-04 | 2026-06-04 | 1964 | 1966 |  | Joy Schneider,Bryan Sohayda
5765 | 1966 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2026-06-05 | 2026-06-11 | 1965 | 1967 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5766 | 1967 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Style Guide Review | 8 hrs | 1 day | 2026-06-12 | 2026-06-12 | 1966 | 1968 |  | Dusti Kincl
5767 | 1968 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Final Collaborative Review | 20 hrs | 5 days | 2026-06-15 | 2026-06-19 | 1967 | 1969 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5768 | 1969 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Accenture QC | 16 hrs | 2 days | 2026-06-22 | 2026-06-23 | 1968 | 1970 |  | Joy Schneider
5769 | 1970 | Future Task |  |  | D684 | Bryan Sohayda | Submit | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Submit | 0 hrs | 0 days | 2026-06-23 | 2026-06-23 | 1969 | 1971 |  | Joy Schneider
5770 | 1971 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Department QC | 2 hrs | 1 day | 2026-06-24 | 2026-06-24 | 1970 | 1972 |  | Tommy Werner
5771 | 1972 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Contract Manager Review | 24 hrs | 3 days | 2026-06-25 | 2026-06-29 | 1971 | 1973 |  | Sean Buchanan
5772 | 1973 | Future Task |  |  | D684 | Bryan Sohayda | Accept | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Accept | 0 hrs | 0 days | 2026-06-29 | 2026-06-29 | 1972 | 1975 |  | Sean Buchanan
5773 | 1974 | Future Task |  |  | D685 | Bryan Sohayda |  | D685 - Post-Implementation Support Monthly Deliverable – June 2026 | 53 hrs | 21 days | 2026-07-01 | 2026-07-30
5774 | 1975 | Future Task |  |  | D685 | Bryan Sohayda |  | Create D685 - Post-Implementation Support Monthly Deliverable – June 2026 | 4 hrs | 4 days | 2026-07-01 | 2026-07-07 | 1973 | 1976 |  | Bryan Sohayda
5775 | 1976 | Future Task |  |  | D685 | Bryan Sohayda | Submit | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Draft Submission | 0 hrs | 0 days | 2026-07-07 | 2026-07-07 | 1975 | 1977 |  | Joy Schneider,Bryan Sohayda
5776 | 1977 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-07-08 | 2026-07-14 | 1976 | 1978 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5777 | 1978 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Style Guide Review | 1 hr | 1 day | 2026-07-15 | 2026-07-15 | 1977 | 1979 |  | Dusti Kincl
5778 | 1979 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-07-16 | 2026-07-22 | 1978 | 1980 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5779 | 1980 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Accenture QC | 4 hrs | 2 days | 2026-07-23 | 2026-07-24 | 1979 | 1981 |  | Joy Schneider
5780 | 1981 | Future Task |  |  | D685 | Bryan Sohayda | Submit | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Submit | 0 hrs | 0 days | 2026-07-24 | 2026-07-24 | 1980 | 1982 |  | Joy Schneider
5781 | 1982 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Department QC | 4 hrs | 1 day | 2026-07-27 | 2026-07-27 | 1981 | 1983 |  | Tommy Werner
5782 | 1983 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-07-28 | 2026-07-30 | 1982 | 1984 |  | Sean Buchanan
5783 | 1984 | Future Task |  |  | D685 | Bryan Sohayda | Accept | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Accept | 0 hrs | 0 days | 2026-07-30 | 2026-07-30 | 1983 | 1986 |  | Sean Buchanan
5784 | 1985 | Future Task |  |  | D686 | Bryan Sohayda |  | D686 - Post-Implementation Support Monthly Deliverable – July 2026 | 53 hrs | 21 days | 2026-08-03 | 2026-08-31
5785 | 1986 | Future Task |  |  | D686 | Bryan Sohayda |  | Create D686 - Post-Implementation Support Monthly Deliverable – July 2026 | 4 hrs | 4 days | 2026-08-03 | 2026-08-06 | 1984 | 1987 |  | Bryan Sohayda
5786 | 1987 | Future Task |  |  | D686 | Bryan Sohayda | Submit | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Draft Submission | 0 hrs | 0 days | 2026-08-06 | 2026-08-06 | 1986 | 1988 |  | Joy Schneider,Bryan Sohayda
5787 | 1988 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-08-07 | 2026-08-13 | 1987 | 1989 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5788 | 1989 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Style Guide Review | 1 hr | 1 day | 2026-08-14 | 2026-08-14 | 1988 | 1990 |  | Dusti Kincl
5789 | 1990 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-08-17 | 2026-08-21 | 1989 | 1991 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5790 | 1991 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Accenture QC | 4 hrs | 2 days | 2026-08-24 | 2026-08-25 | 1990 | 1992 |  | Joy Schneider
5791 | 1992 | Future Task |  |  | D686 | Bryan Sohayda | Submit | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Submit | 0 hrs | 0 days | 2026-08-25 | 2026-08-25 | 1991 | 1993 |  | Joy Schneider
5792 | 1993 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Department QC | 4 hrs | 1 day | 2026-08-26 | 2026-08-26 | 1992 | 1994 |  | Tommy Werner
5793 | 1994 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-08-27 | 2026-08-31 | 1993 | 1995 |  | Sean Buchanan
5794 | 1995 | Future Task |  |  | D686 | Bryan Sohayda | Accept | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Accept | 0 hrs | 0 days | 2026-08-31 | 2026-08-31 | 1994 | 1997 |  | Sean Buchanan
5795 | 1996 | Future Task |  |  | D687 | Bryan Sohayda |  | D687 - Post-Implementation Support Monthly Deliverable – August 2026 | 53 hrs | 21 days | 2026-09-01 | 2026-09-30
5796 | 1997 | Future Task |  |  | D687 | Bryan Sohayda |  | Create D687 - Post-Implementation Support Monthly Deliverable – August 2026 | 4 hrs | 4 days | 2026-09-01 | 2026-09-04 | 1995 | 1998 |  | Bryan Sohayda
5797 | 1998 | Future Task |  |  | D687 | Bryan Sohayda | Submit | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Draft Submission | 0 hrs | 0 days | 2026-09-04 | 2026-09-04 | 1997 | 1999 |  | Joy Schneider,Bryan Sohayda
5798 | 1999 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-09-08 | 2026-09-14 | 1998 | 2000 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5799 | 2000 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Style Guide Review | 1 hr | 1 day | 2026-09-15 | 2026-09-15 | 1999 | 2001 |  | Dusti Kincl
5800 | 2001 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-09-16 | 2026-09-22 | 2000 | 2002 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5801 | 2002 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Accenture QC | 4 hrs | 2 days | 2026-09-23 | 2026-09-24 | 2001 | 2003 |  | Joy Schneider
5802 | 2003 | Future Task |  |  | D687 | Bryan Sohayda | Submit | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Submit | 0 hrs | 0 days | 2026-09-24 | 2026-09-24 | 2002 | 2004 |  | Joy Schneider
5803 | 2004 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Department QC | 4 hrs | 1 day | 2026-09-25 | 2026-09-25 | 2003 | 2005 |  | Tommy Werner
5804 | 2005 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-09-28 | 2026-09-30 | 2004 | 2006 |  | Sean Buchanan
5805 | 2006 | Future Task |  |  | D687 | Bryan Sohayda | Accept | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Accept | 0 hrs | 0 days | 2026-09-30 | 2026-09-30 | 2005 | 2008 |  | Sean Buchanan
5806 | 2007 | Future Task |  |  | D688 | Bryan Sohayda |  | D688 - Post-Implementation Support Monthly Deliverable – September 2026 | 53 hrs | 21 days | 2026-10-01 | 2026-10-29
5807 | 2008 | Future Task |  |  | D688 | Bryan Sohayda |  | Create D688 - Post-Implementation Support Monthly Deliverable – September 2026 | 4 hrs | 4 days | 2026-10-01 | 2026-10-06 | 2006 | 2009 |  | Bryan Sohayda
5808 | 2009 | Future Task |  |  | D688 | Bryan Sohayda | Submit | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Draft Submission | 0 hrs | 0 days | 2026-10-06 | 2026-10-06 | 2008 | 2010 |  | Joy Schneider,Bryan Sohayda
5809 | 2010 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-10-07 | 2026-10-13 | 2009 | 2011 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5810 | 2011 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Style Guide Review | 1 hr | 1 day | 2026-10-14 | 2026-10-14 | 2010 | 2012 |  | Dusti Kincl
5811 | 2012 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-10-15 | 2026-10-21 | 2011 | 2013 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5812 | 2013 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Accenture QC | 4 hrs | 2 days | 2026-10-22 | 2026-10-23 | 2012 | 2014 |  | Joy Schneider
5813 | 2014 | Future Task |  |  | D688 | Bryan Sohayda | Submit | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Submit | 0 hrs | 0 days | 2026-10-23 | 2026-10-23 | 2013 | 2015 |  | Joy Schneider
5814 | 2015 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Department QC | 4 hrs | 1 day | 2026-10-26 | 2026-10-26 | 2014 | 2016 |  | Tommy Werner
5815 | 2016 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-10-27 | 2026-10-29 | 2015 | 2017 |  | Sean Buchanan
5816 | 2017 | Future Task |  |  | D688 | Bryan Sohayda | Accept | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Accept | 0 hrs | 0 days | 2026-10-29 | 2026-10-29 | 2016 | 2019 |  | Sean Buchanan
5817 | 2018 | Future Task |  |  | D689 | Bryan Sohayda |  | D689 - Post-Implementation Support Monthly Deliverable – October 2026 | 53 hrs | 18 days | 2026-11-02 | 2026-11-30
5818 | 2019 | Future Task |  |  | D689 | Bryan Sohayda |  | Create D689 - Post-Implementation Support Monthly Deliverable – October 2026 | 4 hrs | 4 days | 2026-11-02 | 2026-11-05 | 2017 | 2020,2052SS |  | Bryan Sohayda
5819 | 2020 | Future Task |  |  | D689 | Bryan Sohayda | Submit | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Draft Submission | 0 hrs | 0 days | 2026-11-05 | 2026-11-05 | 2019 | 2021 |  | Joy Schneider,Bryan Sohayda
5820 | 2021 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Pre-Submission Collaborative Review | 16 hrs | 4 days | 2026-11-06 | 2026-11-12 | 2020 | 2022 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5821 | 2022 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Style Guide Review | 1 hr | 1 day | 2026-11-13 | 2026-11-13 | 2021 | 2023 |  | Dusti Kincl
5822 | 2023 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Final Collaborative Review | 16 hrs | 3 days | 2026-11-16 | 2026-11-18 | 2022 | 2024 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5823 | 2024 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Accenture QC | 4 hrs | 2 days | 2026-11-19 | 2026-11-20 | 2023 | 2025 |  | Joy Schneider
5824 | 2025 | Future Task |  |  | D689 | Bryan Sohayda | Submit | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Submit | 0 hrs | 0 days | 2026-11-20 | 2026-11-20 | 2024 | 2026 |  | Joy Schneider
5825 | 2026 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Department QC | 4 hrs | 1 day | 2026-11-23 | 2026-11-23 | 2025 | 2027 |  | Tommy Werner
5826 | 2027 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-11-24 | 2026-11-30 | 2026 | 2028 |  | Sean Buchanan
5827 | 2028 | Future Task |  |  | D689 | Bryan Sohayda | Accept | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Accept | 0 hrs | 0 days | 2026-11-30 | 2026-11-30 | 2027 | 2030 |  | Sean Buchanan
5828 | 2029 | Future Task |  |  | D690 | Bryan Sohayda |  | D690 - Post-Implementation Support Monthly Deliverable – November 2026 | 53 hrs | 21 days | 2026-12-01 | 2026-12-30
5829 | 2030 | Future Task |  |  | D690 | Bryan Sohayda |  | Create D690 - Post-Implementation Support Monthly Deliverable – November 2026 | 4 hrs | 4 days | 2026-12-01 | 2026-12-04 | 2028 | 2031 |  | Bryan Sohayda
5830 | 2031 | Future Task |  |  | D690 | Bryan Sohayda | Submit | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Draft Submission | 0 hrs | 0 days | 2026-12-04 | 2026-12-04 | 2030 | 2032 |  | Joy Schneider,Bryan Sohayda
5831 | 2032 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-12-07 | 2026-12-11 | 2031 | 2033 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5832 | 2033 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Style Guide Review | 1 hr | 1 day | 2026-12-14 | 2026-12-14 | 2032 | 2034 |  | Dusti Kincl
5833 | 2034 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-12-15 | 2026-12-21 | 2033 | 2035 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5834 | 2035 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Accenture QC | 4 hrs | 2 days | 2026-12-22 | 2026-12-23 | 2034 | 2036 |  | Joy Schneider
5835 | 2036 | Future Task |  |  | D690 | Bryan Sohayda | Submit | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Submit | 0 hrs | 0 days | 2026-12-23 | 2026-12-23 | 2035 | 2037 |  | Joy Schneider
5836 | 2037 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Department QC | 4 hrs | 1 day | 2026-12-24 | 2026-12-24 | 2036 | 2038 |  | Tommy Werner
5837 | 2038 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-12-28 | 2026-12-30 | 2037 | 2039 |  | Sean Buchanan
5838 | 2039 | Future Task |  |  | D690 | Bryan Sohayda | Accept | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Accept | 0 hrs | 0 days | 2026-12-30 | 2026-12-30 | 2038 | 2041 |  | Sean Buchanan
5839 | 2040 | Future Task |  |  | D691 | Bryan Sohayda |  | D691 - Post-Implementation Support Monthly Deliverable – December 2026 | 53 hrs | 21 days | 2027-01-04 | 2027-02-02
5840 | 2041 | Future Task |  |  | D691 | Bryan Sohayda |  | Create D691 - Post-Implementation Support Monthly Deliverable – December 2026 | 4 hrs | 4 days | 2027-01-04 | 2027-01-07 | 2039 | 2042 |  | Bryan Sohayda
5841 | 2042 | Future Task |  |  | D691 | Bryan Sohayda | Submit | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Draft Submission | 0 hrs | 0 days | 2027-01-07 | 2027-01-07 | 2041 | 2043 |  | Joy Schneider,Bryan Sohayda
5842 | 2043 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2027-01-08 | 2027-01-14 | 2042 | 2044 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5843 | 2044 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Style Guide Review | 1 hr | 1 day | 2027-01-15 | 2027-01-15 | 2043 | 2045 |  | Dusti Kincl
5844 | 2045 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Final Collaborative Review | 16 hrs | 5 days | 2027-01-19 | 2027-01-25 | 2044 | 2046 |  | Bryan Sohayda,Jimmy Cox,Angie Robertson
5845 | 2046 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Accenture QC | 4 hrs | 2 days | 2027-01-26 | 2027-01-27 | 2045 | 2047 |  | Joy Schneider
5846 | 2047 | Future Task |  |  | D691 | Bryan Sohayda | Submit | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Submit | 0 hrs | 0 days | 2027-01-27 | 2027-01-27 | 2046 | 2048 |  | Joy Schneider
5847 | 2048 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Department QC | 4 hrs | 1 day | 2027-01-28 | 2027-01-28 | 2047 | 2049 |  | Tommy Werner
5848 | 2049 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Contract Manager Review | 8 hrs | 3 days | 2027-01-29 | 2027-02-02 | 2048 | 2050 |  | Sean Buchanan
5849 | 2050 | Future Task |  |  | D691 | Bryan Sohayda | Accept | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Accept | 0 hrs | 0 days | 2027-02-02 | 2027-02-02 | 2049 |  |  | Sean Buchanan
6704 | 2051 | Future Task |  |  | D692 | Stacey Terry |  | D692 - Tax Reporting Support CY 2026 (January 2027) | 179 hrs | 69 days | 2026-11-12 | 2027-02-23
6705 | 2052 | Future Task |  |  | D692 | Stacey Terry | Create | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Create | 8 hrs | 10 days | 2026-11-12 | 2026-11-25 | 2019SS | 2053 | 2026-11-12 | Stacey Terry
6706 | 2053 | Future Task |  |  | D692 | Stacey Terry | Submit | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Submit | 0 hrs | 0 days | 2026-11-25 | 2026-11-25 | 2052 | 2054 |  | Stacey Terry,Joy Schneider
6707 | 2054 | Future Task |  |  | D692 | Stacey Terry | Review | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Collaborative Review | 20 hrs | 10 days | 2026-11-30 | 2026-12-11 | 2053 | 2055 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson,Sean Buchanan
6708 | 2055 | Future Task |  |  | D692 | Stacey Terry | Approve | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Approve | 0 hrs | 0 days | 2026-12-11 | 2026-12-11 | 2054 | 2056 |  | Jimmy Cox
6709 | 2056 | Future Task |  |  | D692 | Stacey Terry |  | Create Tax Reporting Checklist (2026) | 36 hrs | 18 days | 2026-12-14 | 2027-01-08 | 2055 | 2057FS-5 days,2058 |  | Stacey Terry,Yogesh Deshmukh
6710 | 2057 | Future Task |  |  | D692 | Stacey Terry |  | Manage Year-end Checklist (2026) | 38 hrs | 19 days | 2027-01-04 | 2027-01-29 | 2056FS-5 days |  |  | Stacey Terry,Yogesh Deshmukh
6711 | 2058 | Future Task |  |  | D692 | Stacey Terry |  | Create initial Year-end Checklist (2027) | 28 hrs | 14 days | 2027-01-11 | 2027-01-29 | 2056 | 2059 |  | Stacey Terry,Yogesh Deshmukh
6712 | 2059 | Future Task |  |  | D692 | Stacey Terry | Submit | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Draft Submission | 0 hrs | 0 days | 2027-01-29 | 2027-01-29 | 2058 | 2060 |  | Stacey Terry,Joy Schneider
6713 | 2060 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2027-02-01 | 2027-02-05 | 2059 | 2061 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson
6714 | 2061 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Style Guide Review | 1 hr | 1 day | 2027-02-08 | 2027-02-08 | 2060 | 2062 |  | Dusti Kincl
6715 | 2062 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Final Collaborative Review | 16 hrs | 5 days | 2027-02-09 | 2027-02-15 | 2061 | 2063 |  | Stacey Terry,Deana Metcalf,Jimmy Cox,Angie Robertson
6716 | 2063 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Accenture QC | 4 hrs | 2 days | 2027-02-16 | 2027-02-17 | 2062 | 2064 |  | Joy Schneider
6717 | 2064 | Future Task |  |  | D692 | Stacey Terry | Submit | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Submit | 0 hrs | 0 days | 2027-02-17 | 2027-02-17 | 2063 | 2065 |  | Joy Schneider
6718 | 2065 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Department QC | 4 hrs | 1 day | 2027-02-18 | 2027-02-18 | 2064 | 2066 |  | Tommy Werner,Gabriela Gibson
6719 | 2066 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Contract Manager Review | 8 hrs | 3 days | 2027-02-19 | 2027-02-23 | 2065 | 2067 |  | Sean Buchanan
6720 | 2067 | Future Task |  |  | D692 | Stacey Terry | Accept | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Accept | 0 hrs | 0 days | 2027-02-23 | 2027-02-23 | 2066 |  | 2027-02-01 | Sean Buchanan
6721 | 2068 | Future Task | Maybe |  | D693 | Joy Schneider |  | D693 - Exit Transition Completion | 122 hrs | 67 days | 2027-04-12 | 2027-07-15
6722 | 2069 | Future Task |  |  | D693 | Joy Schneider | Create | DED D693 - Exit Transition Completion - Create | 6 hrs | 10 days | 2027-04-12 | 2027-04-23 | 2095 | 2070 |  | Joy Schneider,Matt Cole,Mary Punty
6723 | 2070 | Future Task |  |  | D693 | Joy Schneider | Submit | DED D693 - Exit Transition Completion - Submit | 0 hrs | 0 days | 2027-04-23 | 2027-04-23 | 2069 | 2071 |  | Joy Schneider
6724 | 2071 | Future Task |  |  | D693 | Joy Schneider | Review | DED D693 - Exit Transition Completion - Collaborative Review | 12 hrs | 10 days | 2027-04-26 | 2027-05-07 | 2070 | 2072 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6725 | 2072 | Future Task |  |  | D693 | Joy Schneider | Approve | DED D693 - Exit Transition Completion - Approve | 0 hrs | 0 days | 2027-05-07 | 2027-05-07 | 2071 | 2073 |  | Jimmy Cox
6726 | 2073 | Future Task |  |  | D693 | Joy Schneider |  | D693 Review Status of Exit Transition Work Plan | 45 hrs | 15 days | 2027-05-10 | 2027-05-28 | 2072 | 2074 |  | Joy Schneider,Matt Cole,Mary Punty,Jimmy Cox,Angie Robertson,Sean Buchanan
6727 | 2074 | Future Task |  |  | D693 | Joy Schneider |  | D693 Obtain Department Sign Off | 30 hrs | 15 days | 2027-06-01 | 2027-06-21 | 2073 | 2075 |  | Sean Buchanan,Matt Cole
6728 | 2075 | Future Task |  |  | D693 | Joy Schneider | Submit | DEL D693 - Exit Transition Completion - Draft Submission | 0 hrs | 0 days | 2027-06-21 | 2027-06-21 | 2074 | 2076 |  | Joy Schneider
6729 | 2076 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Pre-Submission Collaborative Review | 6 hrs | 5 days | 2027-06-22 | 2027-06-28 | 2075 | 2077 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6730 | 2077 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Style Guide Review | 1 hr | 1 day | 2027-06-29 | 2027-06-29 | 2076 | 2078 |  | Dusti Kincl
6731 | 2078 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Final Collaborative Review | 6 hrs | 5 days | 2027-06-30 | 2027-07-07 | 2077 | 2079 |  | Angie Robertson,Jimmy Cox,Sean Buchanan,Matt Cole,Mary Punty,Joy Schneider
6732 | 2079 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Accenture QC | 4 hrs | 2 days | 2027-07-08 | 2027-07-09 | 2078 | 2080 |  | Joy Schneider
6733 | 2080 | Future Task |  |  | D693 | Joy Schneider | Submit | DEL D693 - Exit Transition Completion - Submit | 0 hrs | 0 days | 2027-07-09 | 2027-07-09 | 2079 | 2081 |  | Joy Schneider
6734 | 2081 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Department QC | 4 hrs | 1 day | 2027-07-12 | 2027-07-12 | 2080 | 2082 |  | Tommy Werner
6735 | 2082 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Contract Manager Review | 8 hrs | 3 days | 2027-07-13 | 2027-07-15 | 2081 | 2083 |  | Sean Buchanan
6736 | 2083 | Future Task |  |  | D693 | Joy Schneider | Accept | DEL D693 - Exit Transition Completion - Accept | 0 hrs | 0 days | 2027-07-15 | 2027-07-15 | 2082 |  | 2027-07-01 | Sean Buchanan
5655 | 2084 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 - Exit Transition Work Plan | 398 hrs | 80 days | 2026-09-01 | 2026-12-28
5656 | 2085 | Future Task |  |  | WP428 | Joy Schneider | Create | WPED WP428 - Exit Transition Work Plan - Create | 8 hrs | 10 days | 2026-09-01 | 2026-09-15 | 1 | 2086 |  | Joy Schneider
5657 | 2086 | Future Task |  |  | WP428 | Joy Schneider | Submit | WPED WP428 - Exit Transition Work Plan - Submit | 0 hrs | 0 days | 2026-09-15 | 2026-09-15 | 2085 | 2087 |  | Joy Schneider
5658 | 2087 | Future Task |  |  | WP428 | Joy Schneider | Review | WPED WP428 - Exit Transition Work Plan - Review | 16 hrs | 10 days | 2026-09-16 | 2026-09-29 | 2086 | 2088 |  | Joy Schneider,Jimmy Cox,Angie Robertson,Sean Buchanan
5659 | 2088 | Future Task |  |  | WP428 | Joy Schneider | Approve | WPED WP428 - Exit Transition Work Plan - Approve | 0 hrs | 0 days | 2026-09-29 | 2026-09-29 | 2087 | 2089 |  | Jimmy Cox
5660 | 2089 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 Develop Exit Transition Work Plan | 210 hrs | 15 days | 2026-09-30 | 2026-10-20 | 2088 | 2090 |  | Joy Schneider,Stacey Terry,Manojkumar Gurjar,Matt Cole,Angie Robertson,Jimmy Cox,Francisca Li
5661 | 2090 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 Determine Entry and Exit Criteria | 120 hrs | 15 days | 2026-10-21 | 2026-11-10 | 2089 | 2091 |  | Joy Schneider,Matt Cole,Angie Robertson,Jimmy Cox
5662 | 2091 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 Review and Confirm Exit Transition Plan | 20 hrs | 15 days | 2026-11-12 | 2026-12-04 | 2090 | 2092 |  | Jimmy Cox,Angie Robertson,Joy Schneider
5663 | 2092 | Future Task |  |  | WP428 | Joy Schneider | Submit | WP WP428 - Exit Transition Work Plan - Submit | 0 hrs | 0 days | 2026-12-04 | 2026-12-04 | 2091 | 2093 |  | Joy Schneider
5664 | 2093 | Future Task |  |  | WP428 | Joy Schneider | Review | WP WP428 - Exit Transition Work Plan - Collaborative Review & Update | 12 hrs | 10 days | 2026-12-07 | 2026-12-18 | 2092 | 2094 |  | Joy Schneider,Jimmy Cox,Angie Robertson
5665 | 2094 | Future Task |  |  | WP428 | Joy Schneider | Review | WP WP428 - Exit Transition Work Plan - Final Review & Edits | 12 hrs | 5 days | 2026-12-21 | 2026-12-28 | 2093 | 2095 |  | Joy Schneider,Jimmy Cox,Angie Robertson
5666 | 2095 | Future Task |  |  | WP428 | Joy Schneider | Approve | WP WP428 - Exit Transition Work Plan - Approve | 0 hrs | 0 days | 2026-12-28 | 2026-12-28 | 2094 | 2069 |  | Jimmy Cox
4 | 2096 | Late | [5 empty] | Administrative Tasks | 2,164 hrs | 1174 days | 2023-05-01 | 2027-12-28
10 | 2097 | Future Task | [5 empty] | Administrative Activities | 1,320 hrs | 1152 days | 2023-06-01 | 2027-12-28
2063 | 2098 | Future Task |  |  |  | Tommy Werner |  | Budget | 308 hrs | 933 days | 2023-06-01 | 2027-02-15
2064 | 2099 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q1 | 14 hrs | 30 days | 2023-06-01 | 2023-07-13
2065 | 2100 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | 2023-06-01 | 2023-06-14 |  | 2101 |  | Tommy Werner,Gabriela Gibson
2066 | 2101 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2023-06-15 | 2023-06-28 | 2100 | 2102 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2067 | 2102 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2023-06-29 | 2023-07-13 | 2101 | 2103 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2068 | 2103 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2023-07-13 | 2023-07-13 | 2102 | 2105SS-8 days |  | Tommy Werner | Add sccessor UID 2071 | TW
2069 | 2104 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q2 | 14 hrs | 30 days | 2023-07-03 | 2023-08-14
2070 | 2105 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | 2023-07-03 | 2023-07-17 | 2103SS-8 days | 2106 |  | Tommy Werner,Gabriela Gibson | Change predecessor to Q1 draft (timing is funny on Q1, but this shouldn't be a true lag) | TW
2071 | 2106 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2023-07-18 | 2023-07-31 | 2105 | 2107 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2072 | 2107 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2023-08-01 | 2023-08-14 | 2106 | 2108 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2073 | 2108 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2023-08-14 | 2023-08-14 | 2107 | 2110 |  | Tommy Werner
2074 | 2109 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q3 | 14 hrs | 30 days | 2023-10-02 | 2023-11-13
2075 | 2110 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | 2023-10-02 | 2023-10-13 | 2108 | 2111 |  | Tommy Werner,Gabriela Gibson
2076 | 2111 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2023-10-16 | 2023-10-27 | 2110 | 2112 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2077 | 2112 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2023-10-30 | 2023-11-13 | 2111 | 2113 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2078 | 2113 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2023-11-13 | 2023-11-13 | 2112 | 2115 |  | Tommy Werner
2079 | 2114 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q4 | 14 hrs | 30 days | 2024-01-02 | 2024-02-13
2080 | 2115 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | 2024-01-02 | 2024-01-16 | 2113 | 2116 |  | Tommy Werner,Gabriela Gibson
2081 | 2116 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2024-01-17 | 2024-01-30 | 2115 | 2117 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2082 | 2117 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2024-01-31 | 2024-02-13 | 2116 | 2118 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2083 | 2118 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2024-02-13 | 2024-02-13 | 2117 | 2130 |  | Tommy Werner
2084 | 2119 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 24-25 | 14 hrs | 30 days | 2024-05-01 | 2024-06-12
2085 | 2120 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 24-25 - Create | 4 hrs | 10 days | 2024-05-01 | 2024-05-14 |  | 2121 |  | Tommy Werner,Gabriela Gibson | Predecessor UID 2093 | TW
2086 | 2121 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 24-25 - Collaborative Review and Update | 4 hrs | 10 days | 2024-05-15 | 2024-05-29 | 2120 | 2122 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2087 | 2122 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 24-25 - Final Review and Edit | 6 hrs | 10 days | 2024-05-30 | 2024-06-12 | 2121 | 2123 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2088 | 2123 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | 2024-06-12 | 2024-06-12 | 2122 | 2150 |  | Tommy Werner | Add successor UID 2097
2089 | 2124 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 24-25 | 14 hrs | 40 days | 2023-06-01 | 2023-07-27
2090 | 2125 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 24-25 - Create | 4 hrs | 20 days | 2023-06-01 | 2023-06-28 |  | 2126 |  | Tommy Werner,Gabriela Gibson
2091 | 2126 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 24-25 - Collaborative Review and Update | 4 hrs | 10 days | 2023-06-29 | 2023-07-13 | 2125 | 2127 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2092 | 2127 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 24-25 - Final Review and Edit | 6 hrs | 10 days | 2023-07-14 | 2023-07-27 | 2126 | 2128 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2093 | 2128 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | 2023-07-27 | 2023-07-27 | 2127 | 2155 |  | Tommy Werner
2094 | 2129 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q1 | 14 hrs | 30 days | 2024-06-03 | 2024-07-15
2095 | 2130 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | 2024-06-03 | 2024-06-14 | 2118 | 2131 |  | Tommy Werner,Gabriela Gibson
2096 | 2131 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2024-06-17 | 2024-06-28 | 2130 | 2132 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2097 | 2132 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2024-07-01 | 2024-07-15 | 2131 | 2133 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2098 | 2133 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2024-07-15 | 2024-07-15 | 2132 | 2135SS-10 days |  | Tommy Werner | Add sccessor UID 2101 | TW
2099 | 2134 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q2 | 14 hrs | 30 days | 2024-07-01 | 2024-08-12
2100 | 2135 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | 2024-07-01 | 2024-07-15 | 2133SS-10 days | 2136 |  | Tommy Werner,Gabriela Gibson | Change predecessor to Q1 draft (timing is funny on Q1, but this shouldn't be a true lag) | TW
2101 | 2136 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2024-07-16 | 2024-07-29 | 2135 | 2137 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2102 | 2137 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2024-07-30 | 2024-08-12 | 2136 | 2138 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2103 | 2138 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2024-08-12 | 2024-08-12 | 2137 | 2140 |  | Tommy Werner
2104 | 2139 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q3 | 14 hrs | 30 days | 2024-10-01 | 2024-11-12
2105 | 2140 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | 2024-10-01 | 2024-10-14 | 2138 | 2141 |  | Tommy Werner,Gabriela Gibson
2106 | 2141 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2024-10-15 | 2024-10-28 | 2140 | 2142 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2107 | 2142 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2024-10-29 | 2024-11-12 | 2141 | 2143 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2108 | 2143 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2024-11-12 | 2024-11-12 | 2142 | 2145 |  | Tommy Werner
2109 | 2144 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q4 | 14 hrs | 30 days | 2025-01-02 | 2025-02-13
2110 | 2145 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | 2025-01-02 | 2025-01-15 | 2143 | 2146 |  | Tommy Werner,Gabriela Gibson
2111 | 2146 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2025-01-16 | 2025-01-30 | 2145 | 2147 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2112 | 2147 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2025-01-31 | 2025-02-13 | 2146 | 2148 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2113 | 2148 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2025-02-13 | 2025-02-13 | 2147 | 2160 |  | Tommy Werner
2114 | 2149 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 25-26 | 14 hrs | 30 days | 2025-05-01 | 2025-06-12
2115 | 2150 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 25-26 - Create | 4 hrs | 10 days | 2025-05-01 | 2025-05-14 | 2123 | 2151 |  | Tommy Werner,Gabriela Gibson | Add predecessor UID 2123 | TW
2116 | 2151 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 25-26 - Collaborative Review and Update | 4 hrs | 10 days | 2025-05-15 | 2025-05-29 | 2150 | 2152 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2117 | 2152 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 25-26 - Final Review and Edit | 6 hrs | 10 days | 2025-05-30 | 2025-06-12 | 2151 | 2153 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2118 | 2153 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | 2025-06-12 | 2025-06-12 | 2152 | 2180 |  | Tommy Werner
2119 | 2154 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 25-26 | 14 hrs | 40 days | 2024-06-03 | 2024-07-29
2120 | 2155 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 25-26 - Create | 4 hrs | 20 days | 2024-06-03 | 2024-06-28 | 2128 | 2156 |  | Tommy Werner,Gabriela Gibson
2121 | 2156 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 25-26 - Collaborative Review and Update | 4 hrs | 10 days | 2024-07-01 | 2024-07-15 | 2155 | 2157 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2122 | 2157 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 25-26 - Final Review and Edit | 6 hrs | 10 days | 2024-07-16 | 2024-07-29 | 2156 | 2158 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2123 | 2158 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | 2024-07-29 | 2024-07-29 | 2157 | 2185 |  | Tommy Werner
2124 | 2159 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q1 | 14 hrs | 30 days | 2025-06-02 | 2025-07-14
2125 | 2160 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | 2025-06-02 | 2025-06-13 | 2148 | 2161 |  | Tommy Werner,Gabriela Gibson
2126 | 2161 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2025-06-16 | 2025-06-27 | 2160 | 2162 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2127 | 2162 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2025-06-30 | 2025-07-14 | 2161 | 2163 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2128 | 2163 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2025-07-14 | 2025-07-14 | 2162 | 2165FS-9 days |  | Tommy Werner | Add sccessor UID 2166 | TW
2129 | 2164 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q2 | 14 hrs | 30 days | 2025-07-01 | 2025-08-12
2130 | 2165 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | 2025-07-01 | 2025-07-15 | 2163FS-9 days | 2166 |  | Tommy Werner,Gabriela Gibson | Change predecessor to Q1 draft (timing is funny on Q1, but this shouldn't be a true lag) | TW
2131 | 2166 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2025-07-16 | 2025-07-29 | 2165 | 2167 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2132 | 2167 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2025-07-30 | 2025-08-12 | 2166 | 2168 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2133 | 2168 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2025-08-12 | 2025-08-12 | 2167 | 2170 |  | Tommy Werner
2134 | 2169 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q3 | 14 hrs | 30 days | 2025-10-01 | 2025-11-12
2135 | 2170 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | 2025-10-01 | 2025-10-14 | 2168 | 2171 |  | Tommy Werner,Gabriela Gibson
2136 | 2171 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2025-10-15 | 2025-10-28 | 2170 | 2172 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2137 | 2172 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2025-10-29 | 2025-11-12 | 2171 | 2173 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2138 | 2173 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2025-11-12 | 2025-11-12 | 2172 | 2175 |  | Tommy Werner
2139 | 2174 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q4 | 14 hrs | 30 days | 2026-01-02 | 2026-02-13
2140 | 2175 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | 2026-01-02 | 2026-01-15 | 2173 | 2176 |  | Tommy Werner,Gabriela Gibson
2141 | 2176 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2026-01-16 | 2026-01-30 | 2175 | 2177 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2142 | 2177 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2026-02-02 | 2026-02-13 | 2176 | 2178 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2143 | 2178 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2026-02-13 | 2026-02-13 | 2177 | 2190 |  | Tommy Werner
2144 | 2179 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 26-27 | 14 hrs | 30 days | 2026-05-01 | 2026-06-12
2145 | 2180 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 26-27 - Create | 4 hrs | 10 days | 2026-05-01 | 2026-05-14 | 2153 | 2181 |  | Tommy Werner,Gabriela Gibson | Add predecessor UID 2153
2146 | 2181 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 26-27 - Collaborative Review and Update | 4 hrs | 10 days | 2026-05-15 | 2026-05-29 | 2180 | 2182 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2147 | 2182 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 26-27 - Final Review and Edit | 6 hrs | 10 days | 2026-06-01 | 2026-06-12 | 2181 | 2183 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2148 | 2183 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | 2026-06-12 | 2026-06-12 | 2182 |  |  | Tommy Werner
2149 | 2184 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 26-27 | 14 hrs | 40 days | 2025-06-02 | 2025-07-28
2150 | 2185 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 26-27 - Create | 4 hrs | 20 days | 2025-06-02 | 2025-06-27 | 2158 | 2186 |  | Tommy Werner,Gabriela Gibson
2151 | 2186 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 26-27 - Collaborative Review and Update | 4 hrs | 10 days | 2025-06-30 | 2025-07-14 | 2185 | 2187 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2152 | 2187 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 26-27 - Final Review and Edit | 6 hrs | 10 days | 2025-07-15 | 2025-07-28 | 2186 | 2188 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2153 | 2188 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | 2025-07-28 | 2025-07-28 | 2187 |  |  | Tommy Werner
2154 | 2189 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q1 | 14 hrs | 30 days | 2026-06-01 | 2026-07-13
2155 | 2190 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | 2026-06-01 | 2026-06-12 | 2178 | 2191 |  | Tommy Werner,Gabriela Gibson
2156 | 2191 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2026-06-15 | 2026-06-26 | 2190 | 2192 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2157 | 2192 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2026-06-29 | 2026-07-13 | 2191 | 2193 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2158 | 2193 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2026-07-13 | 2026-07-13 | 2192 | 2195FS-8 days |  | Tommy Werner | Add sccessor UID 2161 | TW
2159 | 2194 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q2 | 14 hrs | 30 days | 2026-07-01 | 2026-08-12
2160 | 2195 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | 2026-07-01 | 2026-07-15 | 2193FS-8 days | 2196 |  | Tommy Werner,Gabriela Gibson | Change predecessor to Q1 draft (timing is funny on Q1, but this shouldn't be a true lag) | TW
2161 | 2196 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2026-07-16 | 2026-07-29 | 2195 | 2197 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2162 | 2197 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2026-07-30 | 2026-08-12 | 2196 | 2198 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2163 | 2198 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2026-08-12 | 2026-08-12 | 2197 | 2200 |  | Tommy Werner
2164 | 2199 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q3 | 14 hrs | 30 days | 2026-10-01 | 2026-11-12
2165 | 2200 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | 2026-10-01 | 2026-10-14 | 2198 | 2201 |  | Tommy Werner,Gabriela Gibson
2166 | 2201 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2026-10-15 | 2026-10-28 | 2200 | 2202 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2167 | 2202 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2026-10-29 | 2026-11-12 | 2201 | 2203 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2168 | 2203 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2026-11-12 | 2026-11-12 | 2202 | 2205 |  | Tommy Werner
2169 | 2204 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q4 | 14 hrs | 30 days | 2027-01-04 | 2027-02-15
2170 | 2205 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | 2027-01-04 | 2027-01-15 | 2203 | 2206 |  | Tommy Werner,Gabriela Gibson
2171 | 2206 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2027-01-19 | 2027-02-01 | 2205 | 2207 |  | Tommy Werner,Gabriela Gibson,Julian Gotreaux,Jenifer Hartsfield
2172 | 2207 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2027-02-02 | 2027-02-15 | 2206 | 2208 |  | Angie Robertson,Jimmy Cox,Steven Fielder
2173 | 2208 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2027-02-15 | 2027-02-15 | 2207 |  |  | Tommy Werner
2174 | 2209 | Future Task | [5 empty] | Project Resources | 1,012 hrs | 1131 days | 2023-06-30 | 2027-12-28
2175 | 2210 | Future Task |  |  |  | Tommy Werner |  | Project Management Plan | 462 hrs | 1045 days | 2023-11-01 | 2027-12-28
2176 | 2211 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2023 | 54 hrs | 38 days | 2023-11-01 | 2023-12-28
2177 | 2212 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2023-11-01 | 2023-12-01 |  | 2213 |  | Joy Schneider,Tommy Werner,Francisca Li,Jenifer Hartsfield,Gabriela Gibson
2178 | 2213 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2023-12-04 | 2023-12-15 | 2212 | 2214 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2179 | 2214 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2023-12-18 | 2023-12-22 | 2213 | 2215 |  | Jimmy Cox
2180 | 2215 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 4 hrs | 3 days | 2023-12-26 | 2023-12-28 | 2214 | 2217 |  | Tatiana Eubanks
2181 | 2216 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2024 | 51 hrs | 38 days | 2024-05-03 | 2024-06-26
2182 | 2217 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2024-05-03 | 2024-05-31 | 2215 | 2218 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2183 | 2218 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2024-06-03 | 2024-06-14 | 2217 | 2219 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2184 | 2219 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2024-06-17 | 2024-06-21 | 2218 | 2220 |  | Jimmy Cox
2185 | 2220 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2024-06-24 | 2024-06-26 | 2219 | 2222 |  | Tatiana Eubanks
2186 | 2221 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2024 | 51 hrs | 38 days | 2024-11-04 | 2024-12-31
2187 | 2222 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2024-11-04 | 2024-12-04 | 2220 | 2223 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2188 | 2223 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2024-12-05 | 2024-12-18 | 2222 | 2224 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2189 | 2224 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2024-12-19 | 2024-12-26 | 2223 | 2225 |  | Jimmy Cox
2190 | 2225 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2024-12-27 | 2024-12-31 | 2224 | 2227 |  | Tatiana Eubanks
2191 | 2226 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2025 | 51 hrs | 38 days | 2025-05-02 | 2025-06-25
2192 | 2227 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2025-05-02 | 2025-05-30 | 2225 | 2228 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2193 | 2228 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2025-06-02 | 2025-06-13 | 2227 | 2229 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2194 | 2229 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2025-06-16 | 2025-06-20 | 2228 | 2230 |  | Jimmy Cox
2195 | 2230 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2025-06-23 | 2025-06-25 | 2229 | 2232 |  | Tatiana Eubanks
2196 | 2231 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2025 | 51 hrs | 38 days | 2025-11-03 | 2025-12-30
2197 | 2232 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2025-11-03 | 2025-12-03 | 2230 | 2233 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2198 | 2233 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2025-12-04 | 2025-12-17 | 2232 | 2234 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2199 | 2234 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2025-12-18 | 2025-12-24 | 2233 | 2235 |  | Jimmy Cox
2200 | 2235 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2025-12-26 | 2025-12-30 | 2234 | 2237 |  | Tatiana Eubanks
2201 | 2236 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2026 | 51 hrs | 38 days | 2026-05-01 | 2026-06-24
2202 | 2237 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2026-05-01 | 2026-05-29 | 2235 | 2238 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2203 | 2238 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2026-06-01 | 2026-06-12 | 2237 | 2239 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2204 | 2239 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2026-06-15 | 2026-06-19 | 2238 | 2240 |  | Jimmy Cox
2205 | 2240 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2026-06-22 | 2026-06-24 | 2239 | 2242 |  | Tatiana Eubanks
2206 | 2241 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2026 | 51 hrs | 38 days | 2026-11-02 | 2026-12-29
2207 | 2242 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2026-11-02 | 2026-12-02 | 2240 | 2243 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2208 | 2243 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2026-12-03 | 2026-12-16 | 2242 | 2244 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2209 | 2244 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2026-12-17 | 2026-12-23 | 2243 | 2245 |  | Jimmy Cox
2210 | 2245 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2026-12-24 | 2026-12-29 | 2244 | 2247 |  | Tatiana Eubanks
2211 | 2246 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2027 | 51 hrs | 38 days | 2027-05-03 | 2027-06-24
2212 | 2247 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2027-05-03 | 2027-05-28 | 2245 | 2248 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2213 | 2248 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2027-06-01 | 2027-06-14 | 2247 | 2249 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2214 | 2249 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2027-06-15 | 2027-06-21 | 2248 | 2250 |  | Jimmy Cox
2215 | 2250 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2027-06-22 | 2027-06-24 | 2249 | 2252 |  | Tatiana Eubanks
2216 | 2251 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2027 | 51 hrs | 38 days | 2027-11-01 | 2027-12-28
2217 | 2252 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2027-11-01 | 2027-12-01 | 2250 | 2253 |  | Joy Schneider,Francisca Li,Tommy Werner,Jenifer Hartsfield,Gabriela Gibson
2218 | 2253 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2027-12-02 | 2027-12-15 | 2252 | 2254 |  | Joy Schneider,Tommy Werner,Julian Gotreaux,Angie Robertson
2219 | 2254 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2027-12-16 | 2027-12-22 | 2253 | 2255 |  | Jimmy Cox
2220 | 2255 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2027-12-23 | 2027-12-28 | 2254 |  |  | Tatiana Eubanks
2221 | 2256 | Future Task |  |  |  | Dusti Kincl |  | Florida PALM Style Guide | 104 hrs | 910 days | 2023-11-01 | 2027-06-14
2222 | 2257 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 23-24 | 13 hrs | 30 days | 2023-11-01 | 2023-12-15
2223 | 2258 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2023-11-01 | 2023-11-22 |  | 2259 |  | Tatiana Eubanks,Elizabeth Gabert
2224 | 2259 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2023-11-27 | 2023-12-08 | 2258 | 2260 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2225 | 2260 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2023-12-11 | 2023-12-15 | 2259 | 2262 |  | Jimmy Cox
2226 | 2261 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 23-24 | 13 hrs | 30 days | 2024-05-01 | 2024-06-12
2227 | 2262 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2024-05-01 | 2024-05-21 | 2260 | 2263 |  | Tatiana Eubanks,Elizabeth Gabert
2228 | 2263 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2024-05-22 | 2024-06-05 | 2262 | 2264 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2229 | 2264 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2024-06-06 | 2024-06-12 | 2263 | 2266 |  | Jimmy Cox
2230 | 2265 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 24-25 | 13 hrs | 30 days | 2024-11-04 | 2024-12-18
2231 | 2266 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2024-11-04 | 2024-11-25 | 2264 | 2267 |  | Tatiana Eubanks,Elizabeth Gabert
2232 | 2267 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2024-11-26 | 2024-12-11 | 2266 | 2268 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2233 | 2268 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2024-12-12 | 2024-12-18 | 2267 | 2270 |  | Jimmy Cox
2234 | 2269 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 24-25 | 13 hrs | 30 days | 2025-05-01 | 2025-06-12
2235 | 2270 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2025-05-01 | 2025-05-21 | 2268 | 2271 |  | Tatiana Eubanks,Elizabeth Gabert
2236 | 2271 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2025-05-22 | 2025-06-05 | 2270 | 2272 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2237 | 2272 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2025-06-06 | 2025-06-12 | 2271 | 2274 |  | Jimmy Cox
2238 | 2273 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 25-26 | 13 hrs | 30 days | 2025-11-03 | 2025-12-17
2239 | 2274 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2025-11-03 | 2025-11-24 | 2272 | 2275 |  | Tatiana Eubanks,Elizabeth Gabert
2240 | 2275 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2025-11-25 | 2025-12-10 | 2274 | 2276 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2241 | 2276 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2025-12-11 | 2025-12-17 | 2275 | 2278 |  | Jimmy Cox
2242 | 2277 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 25-26 | 13 hrs | 30 days | 2026-04-06 | 2026-05-15
2243 | 2278 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2026-04-06 | 2026-04-24 | 2276 | 2279 |  | Tatiana Eubanks,Elizabeth Gabert
2244 | 2279 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2026-04-27 | 2026-05-08 | 2278 | 2280 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2245 | 2280 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2026-05-11 | 2026-05-15 | 2279 | 2282 |  | Jimmy Cox
2246 | 2281 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 26-27 | 13 hrs | 30 days | 2026-11-02 | 2026-12-16
2247 | 2282 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2026-11-02 | 2026-11-23 | 2280 | 2283 |  | Tatiana Eubanks,Elizabeth Gabert
2248 | 2283 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2026-11-24 | 2026-12-09 | 2282 | 2284 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2249 | 2284 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2026-12-10 | 2026-12-16 | 2283 | 2286 |  | Jimmy Cox
2250 | 2285 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 26-27 | 13 hrs | 30 days | 2027-05-03 | 2027-06-14
2251 | 2286 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2027-05-03 | 2027-05-21 | 2284 | 2287 |  | Tatiana Eubanks,Elizabeth Gabert
2252 | 2287 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2027-05-24 | 2027-06-07 | 2286 | 2288 |  | Dusti Kincl,Julian Gotreaux,Carolyn Hicks
2253 | 2288 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2027-06-08 | 2027-06-14 | 2287 |  |  | Jimmy Cox
2254 | 2289 | Future Task | [5 empty] | Project Team Orientation Guide | 238 hrs | 252 days | 2023-06-30 | 2024-06-28
6683 | 2290 | Future Task |  |  | WP401 | Joy Schneider |  | WP401 - Project Orientation Guide | 88 hrs | 50 days | 2023-06-30 | 2023-09-11
6684 | 2291 | Future Task |  |  | WP401 | Joy Schneider | Create | WPED WP401 - Project Orientation Guide - Create | 8 hrs | 10 days | 2023-06-30 | 2023-07-14 | 28 | 2292 |  | Joy Schneider
6685 | 2292 | Future Task |  |  | WP401 | Joy Schneider | Submit | WPED WP401 - Project Orientation Guide - Submit | 0 hrs | 0 days | 2023-07-14 | 2023-07-14 | 2291 | 2293 |  | Joy Schneider
6686 | 2293 | Future Task |  |  | WP401 | Joy Schneider | Review | WPED WP401 - Project Orientation Guide - Review | 16 hrs | 10 days | 2023-07-17 | 2023-07-28 | 2292 | 2294 |  | Joy Schneider,Jimmy Cox,Angie Robertson,Sean Buchanan
6687 | 2294 | Future Task |  |  | WP401 | Joy Schneider | Approve | WPED WP401 - Project Orientation Guide - Approve | 0 hrs | 0 days | 2023-07-28 | 2023-07-28 | 2293 | 2295 |  | Jimmy Cox
6688 | 2295 | Future Task |  |  | WP401 | Joy Schneider |  | Update Project Team Orientation Guide | 10 hrs | 5 days | 2023-07-31 | 2023-08-04 | 2294 | 2296 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li | Task Type Create | TW
6689 | 2296 | Future Task |  |  | WP401 | Joy Schneider |  | Project Team Orientation Guide - Collaborative Review and Update | 10 hrs | 5 days | 2023-08-07 | 2023-08-11 | 2295 | 2297 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li | Task Type Create | TW
6690 | 2297 | Future Task |  |  | WP401 | Joy Schneider |  | Project Team Orientation Guide - Final Review and Update | 20 hrs | 5 days | 2023-08-14 | 2023-08-18 | 2296 | 2298 |  | Angie Robertson[25%],Jimmy Cox[25%] | Task Type Create | TW
6691 | 2298 | Future Task |  |  | WP401 | Joy Schneider | Submit | WP WP401 - Project Orientation Guide - Submit | 0 hrs | 0 days | 2023-08-18 | 2023-08-18 | 2297 | 2299 |  | Joy Schneider
6692 | 2299 | Future Task |  |  | WP401 | Joy Schneider | Review | WP WP401 - Project Orientation Guide - Collaborative Review & Update | 12 hrs | 10 days | 2023-08-21 | 2023-09-01 | 2298 | 2300 |  | Joy Schneider,Jimmy Cox,Angie Robertson
6693 | 2300 | Future Task |  |  | WP401 | Joy Schneider | Review | WP WP401 - Project Orientation Guide - Final Review & Edits | 12 hrs | 5 days | 2023-09-05 | 2023-09-11 | 2299 | 2301 |  | Joy Schneider,Jimmy Cox,Angie Robertson
6694 | 2301 | Future Task |  |  | WP401 | Joy Schneider | Approve | WP WP401 - Project Orientation Guide - Approve | 0 hrs | 0 days | 2023-09-11 | 2023-09-11 | 2300 | 2303FS-6 days | 2023-10-01 | Jimmy Cox
2255 | 2302 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q1 | 30 hrs | 15 days | 2023-09-01 | 2023-09-22
2257 | 2303 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | 2023-09-01 | 2023-09-08 | 2301FS-6 days | 2304 |  | Jenifer Hartsfield,Gabriela Gibson
2258 | 2304 | Future Task |  |  |  | Julian Gotreaux | Review | FPO - Collaborative Review and Update | 10 hrs | 5 days | 2023-09-11 | 2023-09-15 | 2303 | 2305 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2259 | 2305 | Future Task |  |  |  | Julian Gotreaux | Review | FPO - Final Review and Update | 10 hrs | 5 days | 2023-09-18 | 2023-09-22 | 2304 | 23072407 |  | Angie Robertson,Jimmy Cox
2260 | 2306 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q2 | 40 hrs | 20 days | 2023-12-01 | 2023-12-29
2261 | 2307 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | 2023-12-01 | 2023-12-07 | 2305 | 2308 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2262 | 2308 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | 2023-12-08 | 2023-12-14 | 2307 | 2309 |  | Jenifer Hartsfield,Gabriela Gibson
2263 | 2309 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review and Update | 10 hrs | 5 days | 2023-12-15 | 2023-12-21 | 2308 | 2310 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2264 | 2310 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review and Update | 10 hrs | 5 days | 2023-12-22 | 2023-12-29 | 2309 | 2312 |  | Angie Robertson,Jimmy Cox
2265 | 2311 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q3 | 40 hrs | 20 days | 2024-03-01 | 2024-03-28
2266 | 2312 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | 2024-03-01 | 2024-03-07 | 2310 | 2313 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2267 | 2313 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | 2024-03-08 | 2024-03-14 | 2312 | 2314 |  | Jenifer Hartsfield,Gabriela Gibson
2268 | 2314 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review and Update | 10 hrs | 5 days | 2024-03-15 | 2024-03-21 | 2313 | 2315 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2269 | 2315 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review and Update | 10 hrs | 5 days | 2024-03-22 | 2024-03-28 | 2314 | 2317 |  | Angie Robertson,Jimmy Cox
2270 | 2316 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q4 | 40 hrs | 20 days | 2024-06-03 | 2024-06-28
2271 | 2317 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | 2024-06-03 | 2024-06-07 | 2315 | 2318 |  | Jenifer Hartsfield,Gabriela Gibson,Joy Schneider,Francisca Li
2272 | 2318 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | 2024-06-10 | 2024-06-14 | 2317 | 2319 |  | Jenifer Hartsfield,Gabriela Gibson
2273 | 2319 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review and Update | 10 hrs | 5 days | 2024-06-17 | 2024-06-21 | 2318 | 2320 |  | Julian Gotreaux,Tommy Werner,Joy Schneider,Francisca Li
2274 | 2320 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review and Update | 10 hrs | 5 days | 2024-06-24 | 2024-06-28 | 2319 |  |  | Angie Robertson,Jimmy Cox
2275 | 2321 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 23-24 | 28 hrs | 134 days | 2023-07-17 | 2024-01-29
2276 | 2322 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 23-24 Q1 | 4 hrs | 10 days | 2023-07-17 | 2023-07-28 |  | 23232324 |  | Gabriela Gibson[5%]
2277 | 2323 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 23-24 Q3 | 4 hrs | 10 days | 2024-01-16 | 2024-01-29 | 2322 | 2330 |  | Gabriela Gibson[5%]
2278 | 2324 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 23-24 | 4 hrs | 10 days | 2023-08-15 | 2023-08-28 | 2322 | 2325 |  | Jenifer Hartsfield[5%]
2279 | 2325 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 23-24 | 4 hrs | 10 days | 2023-09-15 | 2023-09-28 | 2324 | 2326 |  | Tommy Werner[5%]
2280 | 2326 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 23-24 | 4 hrs | 10 days | 2023-10-16 | 2023-10-27 | 2325 | 2327 |  | Gabriela Gibson[5%]
2281 | 2327 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 23-24 | 4 hrs | 10 days | 2023-11-15 | 2023-11-30 | 2326 | 2328 |  | Tommy Werner[5%]
2282 | 2328 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 23-24 | 4 hrs | 10 days | 2023-12-15 | 2023-12-29 | 2327 | 2332 |  | Tommy Werner[5%]
2283 | 2329 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 24-25 | 28 hrs | 136 days | 2024-07-15 | 2025-01-29
2284 | 2330 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 24-25 Q1 | 4 hrs | 10 days | 2024-07-15 | 2024-07-26 | 2323 | 2331 |  | Gabriela Gibson[5%]
2285 | 2331 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 24-25 Q3 | 4 hrs | 10 days | 2025-01-15 | 2025-01-29 | 2330 | 2338 |  | Gabriela Gibson[5%]
2286 | 2332 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 24-25 | 4 hrs | 10 days | 2024-08-15 | 2024-08-28 | 2328 | 2333 |  | Jenifer Hartsfield[5%]
2287 | 2333 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 24-25 | 4 hrs | 10 days | 2024-09-16 | 2024-09-27 | 2332 | 2334 |  | Tommy Werner[5%]
2288 | 2334 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 24-25 | 4 hrs | 10 days | 2024-10-15 | 2024-10-28 | 2333 | 2335 |  | Gabriela Gibson[5%]
2289 | 2335 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 24-25 | 4 hrs | 10 days | 2024-11-15 | 2024-12-02 | 2334 | 2336 |  | Tommy Werner[5%]
2290 | 2336 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 24-25 | 4 hrs | 10 days | 2024-12-16 | 2024-12-30 | 2335 | 2340 |  | Tommy Werner[5%]
2291 | 2337 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 25-26 | 28 hrs | 136 days | 2025-07-15 | 2026-01-29
2292 | 2338 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 25-26 Q1 | 4 hrs | 10 days | 2025-07-15 | 2025-07-28 | 2331 | 2339 |  | Gabriela Gibson[5%]
2293 | 2339 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 25-26 Q3 | 4 hrs | 10 days | 2026-01-15 | 2026-01-29 | 2338 | 2346 |  | Gabriela Gibson[5%]
2294 | 2340 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 25-26 | 4 hrs | 10 days | 2025-08-15 | 2025-08-28 | 2336 | 2341 |  | Jenifer Hartsfield[5%]
2295 | 2341 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 25-26 | 4 hrs | 10 days | 2025-09-15 | 2025-09-26 | 2340 | 2342 |  | Tommy Werner[5%]
2296 | 2342 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 25-26 | 4 hrs | 10 days | 2025-10-15 | 2025-10-28 | 2341 | 2343 |  | Gabriela Gibson[5%]
2297 | 2343 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 25-26 | 4 hrs | 10 days | 2025-11-17 | 2025-12-02 | 2342 | 2344 |  | Tommy Werner[5%]
2298 | 2344 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 25-26 | 4 hrs | 10 days | 2025-12-15 | 2025-12-29 | 2343 | 2348 |  | Tommy Werner[5%]
2299 | 2345 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 26-27 | 28 hrs | 136 days | 2026-07-15 | 2027-01-29
2300 | 2346 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 26-27 Q1 | 4 hrs | 10 days | 2026-07-15 | 2026-07-28 | 2339 | 2347 |  | Gabriela Gibson
2301 | 2347 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 26-27 Q3 | 4 hrs | 10 days | 2027-01-15 | 2027-01-29 | 2346 |  |  | Gabriela Gibson
2302 | 2348 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 26-27 | 4 hrs | 10 days | 2026-08-17 | 2026-08-28 | 2344 | 2349 |  | Jenifer Hartsfield
2303 | 2349 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 26-27 | 4 hrs | 10 days | 2026-09-15 | 2026-09-28 | 2348 | 2350 |  | Tommy Werner
2304 | 2350 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 26-27 | 4 hrs | 10 days | 2026-10-15 | 2026-10-28 | 2349 | 2351 |  | Gabriela Gibson
2305 | 2351 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 26-27 | 4 hrs | 10 days | 2026-11-16 | 2026-12-01 | 2350 | 2352 |  | Tommy Werner
2306 | 2352 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 26-27 | 4 hrs | 10 days | 2026-12-15 | 2026-12-29 | 2351 |  |  | Tommy Werner
2307 | 2353 | Future Task |  |  |  | Julian Gotreaux |  | Access Control | 96 hrs | 965 days | 2023-08-15 | 2027-06-14
2308 | 2354 | Future Task |  |  |  | Julian Gotreaux |  | SharePoint Access Control | 32 hrs | 965 days | 2023-08-15 | 2027-06-14
2309 | 2355 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q1 | 2 hrs | 10 days | 2023-08-15 | 2023-08-28 |  | 2356 |  | Jenifer Hartsfield,Gabriela Gibson
2310 | 2356 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q2 | 2 hrs | 10 days | 2023-11-15 | 2023-11-30 | 2355 | 2357 |  | Jenifer Hartsfield,Gabriela Gibson
2311 | 2357 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q3 | 2 hrs | 10 days | 2024-02-15 | 2024-02-28 | 2356 | 2358 |  | Jenifer Hartsfield,Gabriela Gibson
2312 | 2358 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q4 | 2 hrs | 10 days | 2024-05-15 | 2024-05-29 | 2357 | 2359 |  | Jenifer Hartsfield,Gabriela Gibson
2313 | 2359 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q1 | 2 hrs | 10 days | 2024-08-15 | 2024-08-28 | 2358 | 2360 |  | Jenifer Hartsfield,Gabriela Gibson
2314 | 2360 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q2 | 2 hrs | 10 days | 2024-11-15 | 2024-12-02 | 2359 | 2361 |  | Jenifer Hartsfield,Gabriela Gibson
2315 | 2361 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q3 | 2 hrs | 10 days | 2025-02-17 | 2025-02-28 | 2360 | 2362 |  | Jenifer Hartsfield,Gabriela Gibson
2316 | 2362 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q4 | 2 hrs | 10 days | 2025-05-15 | 2025-05-29 | 2361 | 2363 |  | Jenifer Hartsfield,Gabriela Gibson
2317 | 2363 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q1 | 2 hrs | 10 days | 2025-08-15 | 2025-08-28 | 2362 | 2364 |  | Jenifer Hartsfield,Gabriela Gibson
2318 | 2364 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q2 | 2 hrs | 10 days | 2025-11-17 | 2025-12-02 | 2363 | 2365 |  | Jenifer Hartsfield,Gabriela Gibson
2319 | 2365 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q3 | 2 hrs | 10 days | 2026-02-16 | 2026-02-27 | 2364 | 2366 |  | Jenifer Hartsfield,Gabriela Gibson
2320 | 2366 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q4 | 2 hrs | 10 days | 2026-05-15 | 2026-05-29 | 2365 | 2367 |  | Jenifer Hartsfield,Gabriela Gibson
2321 | 2367 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q1 | 2 hrs | 10 days | 2026-08-17 | 2026-08-28 | 2366 | 2368 |  | Jenifer Hartsfield,Gabriela Gibson
2322 | 2368 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q2 | 2 hrs | 10 days | 2026-11-16 | 2026-12-01 | 2367 | 2369 |  | Jenifer Hartsfield,Gabriela Gibson
2323 | 2369 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q3 | 2 hrs | 10 days | 2027-02-15 | 2027-02-26 | 2368 | 2370 |  | Jenifer Hartsfield,Gabriela Gibson
2324 | 2370 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q4 | 2 hrs | 20 days | 2027-05-17 | 2027-06-14 | 2369 |  |  | Jenifer Hartsfield,Gabriela Gibson
2325 | 2371 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2023 | 8 hrs | 35 days | 2023-08-28 | 2023-10-16
2326 | 2372 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2023-08-28 | 2023-09-01 |  | 2373 |  | Daylin Reyes,Richard Saltford
2327 | 2373 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2023-09-05 | 2023-09-18 | 2372 | 2374 |  | Nikki Klein
2328 | 2374 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2023-09-19 | 2023-10-09 | 2373 | 2375 |  | Richard Saltford
2329 | 2375 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2023-10-10 | 2023-10-16 | 2374 |  |  | Daylin Reyes
2330 | 2376 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2024 | 8 hrs | 35 days | 2024-02-27 | 2024-04-15
2331 | 2377 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2024-02-27 | 2024-03-04 |  | 2378 |  | Daylin Reyes,Richard Saltford
2332 | 2378 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2024-03-05 | 2024-03-18 | 2377 | 2379 |  | Nikki Klein
2333 | 2379 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2024-03-19 | 2024-04-08 | 2378 | 2380 |  | Richard Saltford
2334 | 2380 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2024-04-09 | 2024-04-15 | 2379 | 2382 |  | Daylin Reyes
2335 | 2381 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2024 | 8 hrs | 35 days | 2024-08-27 | 2024-10-15
2336 | 2382 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2024-08-27 | 2024-09-03 | 2380 | 2383 |  | Daylin Reyes,Richard Saltford
2337 | 2383 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2024-09-04 | 2024-09-17 | 2382 | 2384 |  | Nikki Klein
2338 | 2384 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2024-09-18 | 2024-10-08 | 2383 | 2385 |  | Richard Saltford
2339 | 2385 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2024-10-09 | 2024-10-15 | 2384 | 2387 |  | Daylin Reyes
2340 | 2386 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2025 | 8 hrs | 35 days | 2025-02-25 | 2025-04-14
2341 | 2387 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2025-02-25 | 2025-03-03 | 2385 | 2388 |  | Daylin Reyes,Richard Saltford
2342 | 2388 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2025-03-04 | 2025-03-17 | 2387 | 2389 |  | Nikki Klein
2343 | 2389 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2025-03-18 | 2025-04-07 | 2388 | 2390 |  | Richard Saltford
2344 | 2390 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2025-04-08 | 2025-04-14 | 2389 | 2392 |  | Daylin Reyes
2345 | 2391 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2025 | 8 hrs | 35 days | 2025-08-26 | 2025-10-14
2346 | 2392 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2025-08-26 | 2025-09-02 | 2390 | 2393 |  | Daylin Reyes,Richard Saltford
2347 | 2393 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2025-09-03 | 2025-09-16 | 2392 | 2394 |  | Nikki Klein
2348 | 2394 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2025-09-17 | 2025-10-07 | 2393 | 2395 |  | Richard Saltford
2349 | 2395 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2025-10-08 | 2025-10-14 | 2394 | 2397 |  | Daylin Reyes
2350 | 2396 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2026 | 8 hrs | 35 days | 2026-02-24 | 2026-04-13
2351 | 2397 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2026-02-24 | 2026-03-02 | 2395 | 2398 |  | Daylin Reyes,Richard Saltford
2352 | 2398 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2026-03-03 | 2026-03-16 | 2397 | 2399 |  | Nikki Klein
2353 | 2399 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2026-03-17 | 2026-04-06 | 2398 | 2400 |  | Richard Saltford
2354 | 2400 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2026-04-07 | 2026-04-13 | 2399 | 2402 |  | Daylin Reyes
2355 | 2401 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2026 | 8 hrs | 35 days | 2026-08-25 | 2026-10-13
2356 | 2402 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2026-08-25 | 2026-08-31 | 2400 | 2403 |  | Daylin Reyes,Richard Saltford
2357 | 2403 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2026-09-01 | 2026-09-15 | 2402 | 2404 |  | Nikki Klein
2358 | 2404 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2026-09-16 | 2026-10-06 | 2403 | 2405 |  | Richard Saltford
2359 | 2405 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2026-10-07 | 2026-10-13 | 2404 |  |  | Daylin Reyes
2360 | 2406 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2027 | 8 hrs | 35 days | 2027-02-23 | 2027-04-12
2361 | 2407 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2027-02-23 | 2027-03-01 | 2305 | 2408 |  | Daylin Reyes,Richard Saltford
2362 | 2408 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2027-03-02 | 2027-03-15 | 2407 | 2409 |  | Nikki Klein
2363 | 2409 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2027-03-16 | 2027-04-05 | 2408 | 2410 |  | Richard Saltford
2364 | 2410 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2027-04-06 | 2027-04-12 | 2409 |  |  | Daylin Reyes
2365 | 2411 | Late | [5 empty] | Proviso Requirements | 844 hrs | 1089 days | 2023-05-01 | 2027-08-24
2366 | 2412 | Future Task |  |  |  | Tommy Werner |  | Monthly Status Reporting | 192 hrs | 241 days | 2023-08-01 | 2024-07-15
2367 | 2413 | Future Task |  |  |  | Tommy Werner |  | July 2023 Monthly Status Reporting | 16 hrs | 11 days | 2023-08-01 | 2023-08-15
2368 | 2414 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | 2023-08-01 | 2023-08-10 |  | 2415SS,2416SS,2417SS |  | Tommy Werner,Gabriela Gibson
2369 | 2415 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | 2023-08-01 | 2023-08-14 | 2414SS | 2418 |  | Tommy Werner,Joy Schneider,Francisca Li,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2370 | 2416 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | 2023-08-01 | 2023-08-10 | 2414SS | 2418 |  | Tommy Werner,Jenifer Hartsfield
2371 | 2417 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | 2023-08-01 | 2023-08-14 | 2414SS | 2418 |  | Dusti Kincl,Nikki Klein
2372 | 2418 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2023-08-15 | 2023-08-15 | 241724152416 | 2420 |  | Dusti Kincl,Jimmy Cox
2373 | 2419 | Future Task |  |  |  | Tommy Werner |  | August 2023 Monthly Status Reporting | 16 hrs | 10 days | 2023-09-01 | 2023-09-15
2374 | 2420 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 5 days | 2023-09-01 | 2023-09-08 | 2418 | 2421SS,2422SS,2423SS,2424 |  | Tommy Werner,Gabriela Gibson
2375 | 2421 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | 2023-09-01 | 2023-09-14 | 2420SS | 2424 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2376 | 2422 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 5 days | 2023-09-01 | 2023-09-08 | 2420SS | 2424 |  | Tommy Werner,Jenifer Hartsfield
2377 | 2423 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | 2023-09-01 | 2023-09-14 | 2420SS | 2424 |  | Dusti Kincl,Nikki Klein
2378 | 2424 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2023-09-15 | 2023-09-15 | 2420242124222420 | 2426 |  | Dusti Kincl,Jimmy Cox
2379 | 2425 | Future Task |  |  |  | Tommy Werner |  | September 2023 Monthly Status Reporting | 16 hrs | 10 days | 2023-10-02 | 2023-10-13
2380 | 2426 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | 2023-10-02 | 2023-10-10 | 2424 | 2427SS,2428SS,2429SS,2430 |  | Tommy Werner,Gabriela Gibson
2381 | 2427 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | 2023-10-02 | 2023-10-12 | 2426SS | 2430 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2382 | 2428 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | 2023-10-02 | 2023-10-10 | 2426SS | 2430 |  | Tommy Werner,Jenifer Hartsfield
2383 | 2429 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | 2023-10-02 | 2023-10-12 | 2426SS | 2430 |  | Dusti Kincl,Nikki Klein
2384 | 2430 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2023-10-13 | 2023-10-13 | 2426242724282420 | 2432 |  | Dusti Kincl,Jimmy Cox
2385 | 2431 | Future Task |  |  |  | Tommy Werner |  | October 2023 Monthly Status Reporting | 16 hrs | 10 days | 2023-11-01 | 2023-11-15
2386 | 2432 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | 2023-11-01 | 2023-11-09 | 2430 | 2433SS,2434SS,2435SS,2436 |  | Tommy Werner,Gabriela Gibson
2387 | 2433 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | 2023-11-01 | 2023-11-14 | 2432SS | 2436 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2388 | 2434 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | 2023-11-01 | 2023-11-09 | 2432SS | 2436 |  | Tommy Werner,Jenifer Hartsfield
2389 | 2435 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | 2023-11-01 | 2023-11-14 | 2432SS | 2436 |  | Dusti Kincl,Nikki Klein
2390 | 2436 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2023-11-15 | 2023-11-15 | 2432243324342430 | 2438 |  | Dusti Kincl,Jimmy Cox
2391 | 2437 | Future Task |  |  |  | Tommy Werner |  | November 2023 Monthly Status Reporting | 16 hrs | 11 days | 2023-12-01 | 2023-12-15
2392 | 2438 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | 2023-12-01 | 2023-12-08 | 2436 | 2439SS,2440SS,2441SS,2442 |  | Tommy Werner,Gabriela Gibson
2393 | 2439 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | 2023-12-01 | 2023-12-14 | 2438SS | 2442 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2394 | 2440 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | 2023-12-01 | 2023-12-08 | 2438SS |  |  | Tommy Werner,Jenifer Hartsfield
2395 | 2441 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | 2023-12-01 | 2023-12-14 | 2438SS | 2442 |  | Dusti Kincl,Nikki Klein
2396 | 2442 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2023-12-15 | 2023-12-15 | 243824392441 | 2444 |  | Dusti Kincl,Jimmy Cox
2397 | 2443 | Future Task |  |  |  | Tommy Werner |  | December 2023 Monthly Status Reporting | 16 hrs | 9 days | 2024-01-02 | 2024-01-12
2398 | 2444 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | 2024-01-02 | 2024-01-09 | 2442 | 2445SS,2448,2446SS,2447SS |  | Tommy Werner,Gabriela Gibson
2399 | 2445 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 8 days | 2024-01-02 | 2024-01-11 | 2444SS | 2448 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2400 | 2446 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | 2024-01-02 | 2024-01-09 | 2444SS | 2448 |  | Tommy Werner,Jenifer Hartsfield
2401 | 2447 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 8 days | 2024-01-02 | 2024-01-11 | 2444SS | 2448 |  | Dusti Kincl,Nikki Klein
2402 | 2448 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-01-12 | 2024-01-12 | 2444244524462440 | 2450 |  | Dusti Kincl,Jimmy Cox
2403 | 2449 | Future Task |  |  |  | Tommy Werner |  | January 2023 Monthly Status Reporting | 16 hrs | 11 days | 2024-02-01 | 2024-02-15
2404 | 2450 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | 2024-02-01 | 2024-02-09 | 2448 | 2451SS,2452SS,2453SS,2454 |  | Tommy Werner,Gabriela Gibson
2405 | 2451 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | 2024-02-01 | 2024-02-14 | 2450SS | 2454 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2406 | 2452 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | 2024-02-01 | 2024-02-09 | 2450SS | 2454 |  | Tommy Werner,Jenifer Hartsfield
2407 | 2453 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | 2024-02-01 | 2024-02-14 | 2450SS | 2454 |  | Dusti Kincl,Nikki Klein
2408 | 2454 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-02-15 | 2024-02-15 | 2450245124522450 | 2456 |  | Dusti Kincl,Jimmy Cox
2409 | 2455 | Future Task |  |  |  | Tommy Werner |  | February 2024 Monthly Status Reporting | 16 hrs | 11 days | 2024-03-01 | 2024-03-15
2410 | 2456 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | 2024-03-01 | 2024-03-08 | 2454 | 2457SS,2458SS,2459SS,2460 |  | Tommy Werner,Gabriela Gibson
2411 | 2457 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | 2024-03-01 | 2024-03-14 | 2456SS | 2460 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2412 | 2458 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | 2024-03-01 | 2024-03-08 | 2456SS | 2460 |  | Tommy Werner,Jenifer Hartsfield
2413 | 2459 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | 2024-03-01 | 2024-03-14 | 2456SS | 2460 |  | Dusti Kincl,Nikki Klein
2414 | 2460 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-03-15 | 2024-03-15 | 2456245724582450 | 2462 |  | Dusti Kincl,Jimmy Cox
2415 | 2461 | Future Task |  |  |  | Tommy Werner |  | March 2024 Monthly Status Reporting | 16 hrs | 11 days | 2024-04-01 | 2024-04-15
2416 | 2462 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | 2024-04-01 | 2024-04-10 | 2460 | 2463SS,2464SS,2465SS,2466 |  | Tommy Werner,Gabriela Gibson
2417 | 2463 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | 2024-04-01 | 2024-04-12 | 2462SS | 2466 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2418 | 2464 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | 2024-04-01 | 2024-04-10 | 2462SS | 2466 |  | Tommy Werner,Jenifer Hartsfield
2419 | 2465 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | 2024-04-01 | 2024-04-12 | 2462SS | 2466 |  | Dusti Kincl,Nikki Klein
2420 | 2466 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-04-15 | 2024-04-15 | 2462246324642460 | 2468 |  | Dusti Kincl,Jimmy Cox
2421 | 2467 | Future Task |  |  |  | Tommy Werner |  | April 2024 Monthly Status Reporting | 16 hrs | 11 days | 2024-05-01 | 2024-05-15
2422 | 2468 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | 2024-05-01 | 2024-05-10 | 2466 | 2469SS,2470SS,2471SS,2472 |  | Tommy Werner,Gabriela Gibson
2423 | 2469 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | 2024-05-01 | 2024-05-14 | 2468SS | 2472 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2424 | 2470 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | 2024-05-01 | 2024-05-10 | 2468SS | 2472 |  | Tommy Werner,Jenifer Hartsfield
2425 | 2471 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | 2024-05-01 | 2024-05-14 | 2468SS | 2472 |  | Dusti Kincl,Nikki Klein
2426 | 2472 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-05-15 | 2024-05-15 | 2468246924702470 | 2474 |  | Dusti Kincl,Jimmy Cox
2427 | 2473 | Future Task |  |  |  | Tommy Werner |  | May 2024 Monthly Status Reporting | 16 hrs | 10 days | 2024-06-03 | 2024-06-14
2428 | 2474 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | 2024-06-03 | 2024-06-10 | 2472 | 2475SS,2476SS,2477SS,2478 |  | Tommy Werner,Gabriela Gibson
2429 | 2475 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | 2024-06-03 | 2024-06-13 | 2474SS |  |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2430 | 2476 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | 2024-06-03 | 2024-06-10 | 2474SS | 2478 |  | Tommy Werner,Jenifer Hartsfield
2431 | 2477 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | 2024-06-03 | 2024-06-13 | 2474SS | 2478 |  | Dusti Kincl,Nikki Klein
2432 | 2478 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-06-14 | 2024-06-14 | 247424762477 | 2480 |  | Dusti Kincl,Jimmy Cox
2433 | 2479 | Future Task |  |  |  | Tommy Werner |  | June 2024 Monthly Status Reporting | 16 hrs | 10 days | 2024-07-01 | 2024-07-15
2434 | 2480 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | 2024-07-01 | 2024-07-10 | 2478 | 2481SS,2482SS,2483SS |  | Tommy Werner,Gabriela Gibson
2435 | 2481 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | 2024-07-01 | 2024-07-12 | 2480SS | 2484 |  | Joy Schneider,Francisca Li,Tommy Werner,Dusti Kincl,Nikki Klein,Deana Metcalf,Jimmy Cox,Shelley McCabe
2436 | 2482 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | 2024-07-01 | 2024-07-10 | 2480SS | 2484 |  | Tommy Werner,Jenifer Hartsfield
2437 | 2483 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | 2024-07-01 | 2024-07-12 | 2480SS | 2484 |  | Dusti Kincl,Nikki Klein
2438 | 2484 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-07-15 | 2024-07-15 | 248124822483 |  |  | Dusti Kincl,Jimmy Cox
9 | 2485 | Late | [5 empty] | Monthly Performance Reporting | 520 hrs | 1089 days | 2023-05-01 | 2027-08-24
6232 | 2486 | Late |  |  | D219 | Joy Schneider |  | D219 - Monthly Performance Report (April 2023) | 10 hrs | 17 days | 2023-05-01 | 2023-05-23
6364 | 2487 | Late |  |  | D219 | Joy Schneider | Create | Create April 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-05-01 | 2023-05-09 | 1 | 2488 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6233 | 2488 | Late |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-05-10 | 2023-05-10 | 2487 | 2489 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6234 | 2489 | Late |  |  | D219 | Joy Schneider | Submit | DEL D219 - Monthly Performance Report (April 2023) - Submit | 0 hrs | 0 days | 2023-05-10 | 2023-05-10 | 2488 | 2490 |  | Joy Schneider
6235 | 2490 | Late |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Department QC | 1 hr | 7 days | 2023-05-11 | 2023-05-19 | 2489 | 2491 |  | Gabriela Gibson
6236 | 2491 | Late |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-05-22 | 2023-05-23 | 2490 | 2492 |  | Sean Buchanan
6237 | 2492 | Late |  |  | D219 | Joy Schneider | Accept | DEL D219 - Monthly Performance Report (April 2023) - Accept | 0 hrs | 0 days | 2023-05-23 | 2023-05-23 | 2491 | 2494 |  | Sean Buchanan
6238 | 2493 | Future Task |  |  | D225 | Joy Schneider |  | D225 - Monthly Performance Report (May 2023) | 10 hrs | 17 days | 2023-06-01 | 2023-06-23
6365 | 2494 | Future Task |  |  | D225 | Joy Schneider | Create | Create May 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-06-01 | 2023-06-09 | 2492 | 2495 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6239 | 2495 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-06-12 | 2023-06-12 | 2494 | 2496 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6240 | 2496 | Future Task |  |  | D225 | Joy Schneider | Submit | DEL D225 - Monthly Performance Report (May 2023) - Submit | 0 hrs | 0 days | 2023-06-12 | 2023-06-12 | 2495 | 2497 |  | Joy Schneider
6241 | 2497 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Department QC | 1 hr | 7 days | 2023-06-13 | 2023-06-21 | 2496 | 2498 |  | Gabriela Gibson
6242 | 2498 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-06-22 | 2023-06-23 | 2497 | 2499 |  | Sean Buchanan
6243 | 2499 | Future Task |  |  | D225 | Joy Schneider | Accept | DEL D225 - Monthly Performance Report (May 2023) - Accept | 0 hrs | 0 days | 2023-06-23 | 2023-06-23 | 2498 | 2501 |  | Sean Buchanan
6244 | 2500 | Future Task |  |  | D232 | Joy Schneider |  | D232 - Monthly Performance Report (June 2023) | 10 hrs | 17 days | 2023-07-03 | 2023-07-26
6366 | 2501 | Future Task |  |  | D232 | Joy Schneider | Create | Create June 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-07-03 | 2023-07-12 | 2499 | 2502 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6245 | 2502 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-07-13 | 2023-07-13 | 2501 | 2503 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6246 | 2503 | Future Task |  |  | D232 | Joy Schneider | Submit | DEL D232 - Monthly Performance Report (June 2023) - Submit | 0 hrs | 0 days | 2023-07-13 | 2023-07-13 | 2502 | 2504 |  | Joy Schneider
6247 | 2504 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Department QC | 1 hr | 7 days | 2023-07-14 | 2023-07-24 | 2503 | 2505 |  | Gabriela Gibson
6248 | 2505 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-07-25 | 2023-07-26 | 2504 | 2506 |  | Sean Buchanan
6249 | 2506 | Future Task |  |  | D232 | Joy Schneider | Accept | DEL D232 - Monthly Performance Report (June 2023) - Accept | 0 hrs | 0 days | 2023-07-26 | 2023-07-26 | 2505 | 2508 |  | Sean Buchanan
6250 | 2507 | Future Task |  |  | D239 | Joy Schneider |  | D239 - Monthly Performance Report (July 2023) | 10 hrs | 17 days | 2023-08-01 | 2023-08-23
6367 | 2508 | Future Task |  |  | D239 | Joy Schneider | Create | Create July 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-08-01 | 2023-08-09 | 2506 | 2509 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6251 | 2509 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-08-10 | 2023-08-10 | 2508 | 2510 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6252 | 2510 | Future Task |  |  | D239 | Joy Schneider | Submit | DEL D239 - Monthly Performance Report (July 2023) - Submit | 0 hrs | 0 days | 2023-08-10 | 2023-08-10 | 2509 | 2511 |  | Joy Schneider
6253 | 2511 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Department QC | 1 hr | 7 days | 2023-08-11 | 2023-08-21 | 2510 | 2512 |  | Gabriela Gibson
6254 | 2512 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-08-22 | 2023-08-23 | 2511 | 2513 |  | Sean Buchanan
6255 | 2513 | Future Task |  |  | D239 | Joy Schneider | Accept | DEL D239 - Monthly Performance Report (July 2023) - Accept | 0 hrs | 0 days | 2023-08-23 | 2023-08-23 | 2512 | 2515 |  | Sean Buchanan
6256 | 2514 | Future Task |  |  | D249 | Joy Schneider |  | D249 - Monthly Performance Report (August 2023) | 10 hrs | 17 days | 2023-09-01 | 2023-09-26
6368 | 2515 | Future Task |  |  | D249 | Joy Schneider | Create | Create August 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-09-01 | 2023-09-12 | 2513 | 2516 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6257 | 2516 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-09-13 | 2023-09-13 | 2515 | 2517 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6258 | 2517 | Future Task |  |  | D249 | Joy Schneider | Submit | DEL D249 - Monthly Performance Report (August 2023) - Submit | 0 hrs | 0 days | 2023-09-13 | 2023-09-13 | 2516 | 2518 |  | Joy Schneider
6259 | 2518 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Department QC | 1 hr | 7 days | 2023-09-14 | 2023-09-22 | 2517 | 2519 |  | Gabriela Gibson
6260 | 2519 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-09-25 | 2023-09-26 | 2518 | 2520 |  | Sean Buchanan
6261 | 2520 | Future Task |  |  | D249 | Joy Schneider | Accept | DEL D249 - Monthly Performance Report (August 2023) - Accept | 0 hrs | 0 days | 2023-09-26 | 2023-09-26 | 2519 | 2522 |  | Sean Buchanan
6262 | 2521 | Future Task |  |  | D253 | Joy Schneider |  | D253 - Monthly Performance Report (September 2023) | 10 hrs | 17 days | 2023-10-02 | 2023-10-24
6369 | 2522 | Future Task |  |  | D253 | Joy Schneider | Create | Create September 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-10-02 | 2023-10-10 | 2520 | 2523 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6263 | 2523 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-10-11 | 2023-10-11 | 2522 | 2524 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6264 | 2524 | Future Task |  |  | D253 | Joy Schneider | Submit | DEL D253 - Monthly Performance Report (September 2023) - Submit | 0 hrs | 0 days | 2023-10-11 | 2023-10-11 | 2523 | 2525 |  | Joy Schneider
6265 | 2525 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Department QC | 1 hr | 7 days | 2023-10-12 | 2023-10-20 | 2524 | 2526 |  | Gabriela Gibson
6266 | 2526 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-10-23 | 2023-10-24 | 2525 | 2527 |  | Sean Buchanan
6267 | 2527 | Future Task |  |  | D253 | Joy Schneider | Accept | DEL D253 - Monthly Performance Report (September 2023) - Accept | 0 hrs | 0 days | 2023-10-24 | 2023-10-24 | 2526 | 2529 |  | Sean Buchanan
6268 | 2528 | Future Task |  |  | D257 | Joy Schneider |  | D257 - Monthly Performance Report (October 2023) | 10 hrs | 17 days | 2023-11-01 | 2023-11-28
6370 | 2529 | Future Task |  |  | D257 | Joy Schneider | Create | Create October 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-11-01 | 2023-11-09 | 2527 | 2530 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6269 | 2530 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-11-13 | 2023-11-13 | 2529 | 2531 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6270 | 2531 | Future Task |  |  | D257 | Joy Schneider | Submit | DEL D257 - Monthly Performance Report (October 2023) - Submit | 0 hrs | 0 days | 2023-11-13 | 2023-11-13 | 2530 | 2532 |  | Joy Schneider
6271 | 2532 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Department QC | 1 hr | 7 days | 2023-11-14 | 2023-11-22 | 2531 | 2533 |  | Gabriela Gibson
6272 | 2533 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-11-27 | 2023-11-28 | 2532 | 2534 |  | Sean Buchanan
6273 | 2534 | Future Task |  |  | D257 | Joy Schneider | Accept | DEL D257 - Monthly Performance Report (October 2023) - Accept | 0 hrs | 0 days | 2023-11-28 | 2023-11-28 | 2533 | 2536 |  | Sean Buchanan
6274 | 2535 | Future Task |  |  | D261 | Joy Schneider |  | D261 - Monthly Performance Report (November 2023) | 10 hrs | 17 days | 2023-12-01 | 2023-12-26
6385 | 2536 | Future Task |  |  | D261 | Joy Schneider | Create | Create November 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-12-01 | 2023-12-11 | 2534 | 2537 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6275 | 2537 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-12-12 | 2023-12-12 | 2536 | 2538 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6276 | 2538 | Future Task |  |  | D261 | Joy Schneider | Submit | DEL D261 - Monthly Performance Report (November 2023) - Submit | 0 hrs | 0 days | 2023-12-12 | 2023-12-12 | 2537 | 2539 |  | Joy Schneider
6277 | 2539 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Department QC | 1 hr | 7 days | 2023-12-13 | 2023-12-21 | 2538 | 2540 |  | Gabriela Gibson
6278 | 2540 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-12-22 | 2023-12-26 | 2539 | 2541 |  | Sean Buchanan
6279 | 2541 | Future Task |  |  | D261 | Joy Schneider | Accept | DEL D261 - Monthly Performance Report (November 2023) - Accept | 0 hrs | 0 days | 2023-12-26 | 2023-12-26 | 2540 | 2543 |  | Sean Buchanan
6280 | 2542 | Future Task |  |  | D267 | Joy Schneider |  | D267 - Monthly Performance Report (December 2023) | 10 hrs | 17 days | 2024-01-02 | 2024-01-25
6384 | 2543 | Future Task |  |  | D267 | Joy Schneider | Create | Create December 2023 Monthly Performance Report | 3 hrs | 7 days | 2024-01-02 | 2024-01-10 | 2541 | 2544 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6281 | 2544 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-01-11 | 2024-01-11 | 2543 | 2545 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6282 | 2545 | Future Task |  |  | D267 | Joy Schneider | Submit | DEL D267 - Monthly Performance Report (December 2023) - Submit | 0 hrs | 0 days | 2024-01-11 | 2024-01-11 | 2544 | 2546 |  | Joy Schneider
6283 | 2546 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Department QC | 1 hr | 7 days | 2024-01-12 | 2024-01-23 | 2545 | 2547 |  | Gabriela Gibson
6284 | 2547 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Contract Manager Review | 2 hrs | 2 days | 2024-01-24 | 2024-01-25 | 2546 | 2548 |  | Sean Buchanan
6285 | 2548 | Future Task |  |  | D267 | Joy Schneider | Accept | DEL D267 - Monthly Performance Report (December 2023) - Accept | 0 hrs | 0 days | 2024-01-25 | 2024-01-25 | 2547 | 2550 |  | Sean Buchanan
6286 | 2549 | Future Task |  |  | D277 | Joy Schneider |  | D277 - Monthly Performance Report (January 2024) | 10 hrs | 17 days | 2024-02-01 | 2024-02-23
6383 | 2550 | Future Task |  |  | D277 | Joy Schneider | Create | Create January 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-02-01 | 2024-02-09 | 2548 | 2551 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6287 | 2551 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-02-12 | 2024-02-12 | 2550 | 2552 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6288 | 2552 | Future Task |  |  | D277 | Joy Schneider | Submit | DEL D277 - Monthly Performance Report (January 2024) - Submit | 0 hrs | 0 days | 2024-02-12 | 2024-02-12 | 2551 | 2553 |  | Joy Schneider
6289 | 2553 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Department QC | 1 hr | 7 days | 2024-02-13 | 2024-02-21 | 2552 | 2554 |  | Gabriela Gibson
6290 | 2554 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-02-22 | 2024-02-23 | 2553 | 2555 |  | Sean Buchanan
6291 | 2555 | Future Task |  |  | D277 | Joy Schneider | Accept | DEL D277 - Monthly Performance Report (January 2024) - Accept | 0 hrs | 0 days | 2024-02-23 | 2024-02-23 | 2554 | 2557 |  | Sean Buchanan
6292 | 2556 | Future Task |  |  | D284 | Joy Schneider |  | D284 - Monthly Performance Report (February 2024) | 10 hrs | 17 days | 2024-03-01 | 2024-03-25
6382 | 2557 | Future Task |  |  | D284 | Joy Schneider | Create | Create February 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-03-01 | 2024-03-11 | 2555 | 2558 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6293 | 2558 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-03-12 | 2024-03-12 | 2557 | 2559 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6294 | 2559 | Future Task |  |  | D284 | Joy Schneider | Submit | DEL D284 - Monthly Performance Report (February 2024) - Submit | 0 hrs | 0 days | 2024-03-12 | 2024-03-12 | 2558 | 2560 |  | Joy Schneider
6295 | 2560 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Department QC | 1 hr | 7 days | 2024-03-13 | 2024-03-21 | 2559 | 2561 |  | Gabriela Gibson
6296 | 2561 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-03-22 | 2024-03-25 | 2560 | 2562 |  | Sean Buchanan
6297 | 2562 | Future Task |  |  | D284 | Joy Schneider | Accept | DEL D284 - Monthly Performance Report (February 2024) - Accept | 0 hrs | 0 days | 2024-03-25 | 2024-03-25 | 2561 | 2564 |  | Sean Buchanan
6298 | 2563 | Future Task |  |  | D288 | Joy Schneider |  | D288 - Monthly Performance Report (March 2024) | 10 hrs | 17 days | 2024-04-01 | 2024-04-23
6381 | 2564 | Future Task |  |  | D288 | Joy Schneider | Create | Create March 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-04-01 | 2024-04-09 | 2562 | 2565 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6299 | 2565 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-04-10 | 2024-04-10 | 2564 | 2566 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6300 | 2566 | Future Task |  |  | D288 | Joy Schneider | Submit | DEL D288 - Monthly Performance Report (March 2024) - Submit | 0 hrs | 0 days | 2024-04-10 | 2024-04-10 | 2565 | 2567 |  | Joy Schneider
6301 | 2567 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Department QC | 1 hr | 7 days | 2024-04-11 | 2024-04-19 | 2566 | 2568 |  | Gabriela Gibson
6302 | 2568 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-04-22 | 2024-04-23 | 2567 | 2569 |  | Sean Buchanan
6303 | 2569 | Future Task |  |  | D288 | Joy Schneider | Accept | DEL D288 - Monthly Performance Report (March 2024) - Accept | 0 hrs | 0 days | 2024-04-23 | 2024-04-23 | 2568 | 2571 |  | Sean Buchanan
6304 | 2570 | Future Task |  |  | D296 | Joy Schneider |  | D296 - Monthly Performance Report (April 2024) | 10 hrs | 17 days | 2024-05-01 | 2024-05-23
6380 | 2571 | Future Task |  |  | D296 | Joy Schneider | Create | Create April 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-05-01 | 2024-05-09 | 2569 | 2572 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6305 | 2572 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-05-10 | 2024-05-10 | 2571 | 2573 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6306 | 2573 | Future Task |  |  | D296 | Joy Schneider | Submit | DEL D296 - Monthly Performance Report (April 2024) - Submit | 0 hrs | 0 days | 2024-05-10 | 2024-05-10 | 2572 | 2574 |  | Joy Schneider
6307 | 2574 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Department QC | 1 hr | 7 days | 2024-05-13 | 2024-05-21 | 2573 | 2575 |  | Gabriela Gibson
6308 | 2575 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-05-22 | 2024-05-23 | 2574 | 2576 |  | Sean Buchanan
6309 | 2576 | Future Task |  |  | D296 | Joy Schneider | Accept | DEL D296 - Monthly Performance Report (April 2024) - Accept | 0 hrs | 0 days | 2024-05-23 | 2024-05-23 | 2575 | 2578 |  | Sean Buchanan
6310 | 2577 | Future Task |  |  | D302 | Joy Schneider |  | D302 - Monthly Performance Report (May 2024) | 10 hrs | 17 days | 2024-06-03 | 2024-06-25
6379 | 2578 | Future Task |  |  | D302 | Joy Schneider | Create | Create May 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-06-03 | 2024-06-11 | 2576 | 2579 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6311 | 2579 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-06-12 | 2024-06-12 | 2578 | 2580 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6312 | 2580 | Future Task |  |  | D302 | Joy Schneider | Submit | DEL D302 - Monthly Performance Report (May 2024) - Submit | 0 hrs | 0 days | 2024-06-12 | 2024-06-12 | 2579 | 2581 |  | Joy Schneider
6313 | 2581 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Department QC | 1 hr | 7 days | 2024-06-13 | 2024-06-21 | 2580 | 2582 |  | Gabriela Gibson
6314 | 2582 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-06-24 | 2024-06-25 | 2581 | 2583 |  | Sean Buchanan
6315 | 2583 | Future Task |  |  | D302 | Joy Schneider | Accept | DEL D302 - Monthly Performance Report (May 2024) - Accept | 0 hrs | 0 days | 2024-06-25 | 2024-06-25 | 2582 | 2585 |  | Sean Buchanan
6316 | 2584 | Future Task |  |  | D311 | Joy Schneider |  | D311 - Monthly Performance Report (June 2024) | 10 hrs | 17 days | 2024-07-01 | 2024-07-24
6378 | 2585 | Future Task |  |  | D311 | Joy Schneider | Create | Create June 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-07-01 | 2024-07-10 | 2583 | 2586 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6317 | 2586 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-07-11 | 2024-07-11 | 2585 | 2587 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6318 | 2587 | Future Task |  |  | D311 | Joy Schneider | Submit | DEL D311 - Monthly Performance Report (June 2024) - Submit | 0 hrs | 0 days | 2024-07-11 | 2024-07-11 | 2586 | 2588 |  | Joy Schneider
6319 | 2588 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Department QC | 1 hr | 7 days | 2024-07-12 | 2024-07-22 | 2587 | 2589 |  | Gabriela Gibson
6320 | 2589 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-07-23 | 2024-07-24 | 2588 | 2590 |  | Sean Buchanan
6321 | 2590 | Future Task |  |  | D311 | Joy Schneider | Accept | DEL D311 - Monthly Performance Report (June 2024) - Accept | 0 hrs | 0 days | 2024-07-24 | 2024-07-24 | 2589 | 2592 |  | Sean Buchanan
6322 | 2591 | Future Task |  |  | D319 | Joy Schneider |  | D319 - Monthly Performance Report (July 2024) | 10 hrs | 17 days | 2024-08-01 | 2024-08-23
6377 | 2592 | Future Task |  |  | D319 | Joy Schneider | Create | Create July 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-08-01 | 2024-08-09 | 2590 | 2593 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6323 | 2593 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-08-12 | 2024-08-12 | 2592 | 2594 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6324 | 2594 | Future Task |  |  | D319 | Joy Schneider | Submit | DEL D319 - Monthly Performance Report (July 2024) - Submit | 0 hrs | 0 days | 2024-08-12 | 2024-08-12 | 2593 | 2595 |  | Joy Schneider
6325 | 2595 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Department QC | 1 hr | 7 days | 2024-08-13 | 2024-08-21 | 2594 | 2596 |  | Gabriela Gibson
6326 | 2596 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-08-22 | 2024-08-23 | 2595 | 2597 |  | Sean Buchanan
6327 | 2597 | Future Task |  |  | D319 | Joy Schneider | Accept | DEL D319 - Monthly Performance Report (July 2024) - Accept | 0 hrs | 0 days | 2024-08-23 | 2024-08-23 | 2596 | 2599 |  | Sean Buchanan
6328 | 2598 | Future Task |  |  | D328 | Joy Schneider |  | D328 - Monthly Performance Report (August 2024) | 10 hrs | 17 days | 2024-09-03 | 2024-09-25
6376 | 2599 | Future Task |  |  | D328 | Joy Schneider | Create | Create August 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-09-03 | 2024-09-11 | 2597 | 2600 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6329 | 2600 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-09-12 | 2024-09-12 | 2599 | 2601 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6330 | 2601 | Future Task |  |  | D328 | Joy Schneider | Submit | DEL D328 - Monthly Performance Report (August 2024) - Submit | 0 hrs | 0 days | 2024-09-12 | 2024-09-12 | 2600 | 2602 |  | Joy Schneider
6331 | 2602 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Department QC | 1 hr | 7 days | 2024-09-13 | 2024-09-23 | 2601 | 2603 |  | Gabriela Gibson
6332 | 2603 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-09-24 | 2024-09-25 | 2602 | 2604 |  | Sean Buchanan
6333 | 2604 | Future Task |  |  | D328 | Joy Schneider | Accept | DEL D328 - Monthly Performance Report (August 2024) - Accept | 0 hrs | 0 days | 2024-09-25 | 2024-09-25 | 2603 | 2606 |  | Sean Buchanan
6334 | 2605 | Future Task |  |  | D334 | Joy Schneider |  | D334 - Monthly Performance Report (September 2024) | 10 hrs | 17 days | 2024-10-01 | 2024-10-23
6375 | 2606 | Future Task |  |  | D334 | Joy Schneider | Create | Create September 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-10-01 | 2024-10-09 | 2604 | 2607 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6335 | 2607 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-10-10 | 2024-10-10 | 2606 | 2608 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6336 | 2608 | Future Task |  |  | D334 | Joy Schneider | Submit | DEL D334 - Monthly Performance Report (September 2024) - Submit | 0 hrs | 0 days | 2024-10-10 | 2024-10-10 | 2607 | 2609 |  | Joy Schneider
6337 | 2609 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Department QC | 1 hr | 7 days | 2024-10-11 | 2024-10-21 | 2608 | 2610 |  | Gabriela Gibson
6338 | 2610 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-10-22 | 2024-10-23 | 2609 | 2611 |  | Sean Buchanan
6339 | 2611 | Future Task |  |  | D334 | Joy Schneider | Accept | DEL D334 - Monthly Performance Report (September 2024) - Accept | 0 hrs | 0 days | 2024-10-23 | 2024-10-23 | 2610 | 2613 |  | Sean Buchanan
6340 | 2612 | Future Task |  |  | D342 | Joy Schneider |  | D342 - Monthly Performance Report (October 2024) | 10 hrs | 17 days | 2024-11-01 | 2024-11-26
6374 | 2613 | Future Task |  |  | D342 | Joy Schneider | Create | Create October 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-11-01 | 2024-11-12 | 2611 | 2614 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6341 | 2614 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-11-13 | 2024-11-13 | 2613 | 2615 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6342 | 2615 | Future Task |  |  | D342 | Joy Schneider | Submit | DEL D342 - Monthly Performance Report (October 2024) - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 2614 | 2616 |  | Joy Schneider
6343 | 2616 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Department QC | 1 hr | 7 days | 2024-11-14 | 2024-11-22 | 2615 | 2617 |  | Gabriela Gibson
6344 | 2617 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-11-25 | 2024-11-26 | 2616 | 2618 |  | Sean Buchanan
6345 | 2618 | Future Task |  |  | D342 | Joy Schneider | Accept | DEL D342 - Monthly Performance Report (October 2024) - Accept | 0 hrs | 0 days | 2024-11-26 | 2024-11-26 | 2617 | 2620 |  | Sean Buchanan
6346 | 2619 | Future Task |  |  | D347 | Joy Schneider |  | D347 - Monthly Performance Report (November 2024) | 10 hrs | 17 days | 2024-12-02 | 2024-12-24
6373 | 2620 | Future Task |  |  | D347 | Joy Schneider | Create | Create November 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-12-02 | 2024-12-10 | 2618 | 2621 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6347 | 2621 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-12-11 | 2024-12-11 | 2620 | 2622 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6348 | 2622 | Future Task |  |  | D347 | Joy Schneider | Submit | DEL D347 - Monthly Performance Report (November 2024) - Submit | 0 hrs | 0 days | 2024-12-11 | 2024-12-11 | 2621 | 2623 |  | Joy Schneider
6349 | 2623 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Department QC | 1 hr | 7 days | 2024-12-12 | 2024-12-20 | 2622 | 2624 |  | Gabriela Gibson
6350 | 2624 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-12-23 | 2024-12-24 | 2623 | 2625 |  | Sean Buchanan
6351 | 2625 | Future Task |  |  | D347 | Joy Schneider | Accept | DEL D347 - Monthly Performance Report (November 2024) - Accept | 0 hrs | 0 days | 2024-12-24 | 2024-12-24 | 2624 | 2627 |  | Sean Buchanan
6352 | 2626 | Future Task |  |  | D353 | Joy Schneider |  | D353 - Monthly Performance Report (December 2024) | 10 hrs | 17 days | 2025-01-02 | 2025-01-27
6372 | 2627 | Future Task |  |  | D353 | Joy Schneider | Create | Create December 2024 Monthly Performance Report | 3 hrs | 7 days | 2025-01-02 | 2025-01-10 | 2625 | 2628 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6353 | 2628 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-01-13 | 2025-01-13 | 2627 | 2629 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6354 | 2629 | Future Task |  |  | D353 | Joy Schneider | Submit | DEL D353 - Monthly Performance Report (December 2024) - Submit | 0 hrs | 0 days | 2025-01-13 | 2025-01-13 | 2628 | 2630 |  | Joy Schneider
6355 | 2630 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Department QC | 1 hr | 7 days | 2025-01-14 | 2025-01-23 | 2629 | 2631 |  | Gabriela Gibson
6356 | 2631 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Contract Manager Review | 2 hrs | 2 days | 2025-01-24 | 2025-01-27 | 2630 | 2632 |  | Sean Buchanan
6357 | 2632 | Future Task |  |  | D353 | Joy Schneider | Accept | DEL D353 - Monthly Performance Report (December 2024) - Accept | 0 hrs | 0 days | 2025-01-27 | 2025-01-27 | 2631 | 2634 |  | Sean Buchanan
6358 | 2633 | Future Task |  |  | D359 | Joy Schneider |  | D359 - Monthly Performance Report (January 2025) | 10 hrs | 17 days | 2025-02-03 | 2025-02-25
6371 | 2634 | Future Task |  |  | D359 | Joy Schneider | Create | Create January 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-02-03 | 2025-02-11 | 2632 | 2635 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6359 | 2635 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-02-12 | 2025-02-12 | 2634 | 2636 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6360 | 2636 | Future Task |  |  | D359 | Joy Schneider | Submit | DEL D359 - Monthly Performance Report (January 2025) - Submit | 0 hrs | 0 days | 2025-02-12 | 2025-02-12 | 2635 | 2637 |  | Joy Schneider
6361 | 2637 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Department QC | 1 hr | 7 days | 2025-02-13 | 2025-02-21 | 2636 | 2638 |  | Gabriela Gibson
6362 | 2638 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-02-24 | 2025-02-25 | 2637 | 2639 |  | Sean Buchanan
6363 | 2639 | Future Task |  |  | D359 | Joy Schneider | Accept | DEL D359 - Monthly Performance Report (January 2025) - Accept | 0 hrs | 0 days | 2025-02-25 | 2025-02-25 | 2638 | 2641 |  | Sean Buchanan
6386 | 2640 | Future Task |  |  | D362 | Joy Schneider |  | D362 - Monthly Performance Report (February 2025) | 10 hrs | 17 days | 2025-03-03 | 2025-03-25
6490 | 2641 | Future Task |  |  | D362 | Joy Schneider | Create | Create February 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-03-03 | 2025-03-11 | 2639 | 2642 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6387 | 2642 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-03-12 | 2025-03-12 | 2641 | 2643 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6388 | 2643 | Future Task |  |  | D362 | Joy Schneider | Submit | DEL D362 - Monthly Performance Report (February 2025) - Submit | 0 hrs | 0 days | 2025-03-12 | 2025-03-12 | 2642 | 2644 |  | Joy Schneider
6389 | 2644 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Department QC | 1 hr | 7 days | 2025-03-13 | 2025-03-21 | 2643 | 2645 |  | Gabriela Gibson
6390 | 2645 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-03-24 | 2025-03-25 | 2644 | 2646 |  | Sean Buchanan
6391 | 2646 | Future Task |  |  | D362 | Joy Schneider | Accept | DEL D362 - Monthly Performance Report (February 2025) - Accept | 0 hrs | 0 days | 2025-03-25 | 2025-03-25 | 2645 | 2648 |  | Sean Buchanan
6392 | 2647 | Future Task |  |  | D364 | Joy Schneider |  | D364 - Monthly Performance Report (March 2025) | 10 hrs | 17 days | 2025-04-01 | 2025-04-23
6489 | 2648 | Future Task |  |  | D364 | Joy Schneider | Create | Create March 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-04-01 | 2025-04-09 | 2646 | 2649 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6393 | 2649 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-04-10 | 2025-04-10 | 2648 | 2650 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6394 | 2650 | Future Task |  |  | D364 | Joy Schneider | Submit | DEL D364 - Monthly Performance Report (March 2025) - Submit | 0 hrs | 0 days | 2025-04-10 | 2025-04-10 | 2649 | 2651 |  | Joy Schneider
6395 | 2651 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Department QC | 1 hr | 7 days | 2025-04-11 | 2025-04-21 | 2650 | 2652 |  | Gabriela Gibson
6396 | 2652 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-04-22 | 2025-04-23 | 2651 | 2653 |  | Sean Buchanan
6397 | 2653 | Future Task |  |  | D364 | Joy Schneider | Accept | DEL D364 - Monthly Performance Report (March 2025) - Accept | 0 hrs | 0 days | 2025-04-23 | 2025-04-23 | 2652 | 2655 |  | Sean Buchanan
6398 | 2654 | Future Task |  |  | D366 | Joy Schneider |  | D366 - Monthly Performance Report (April 2025) | 10 hrs | 17 days | 2025-05-01 | 2025-05-23
6488 | 2655 | Future Task |  |  | D366 | Joy Schneider | Create | Create April 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-05-01 | 2025-05-09 | 2653 | 2656 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6399 | 2656 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-05-12 | 2025-05-12 | 2655 | 2657 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6400 | 2657 | Future Task |  |  | D366 | Joy Schneider | Submit | DEL D366 - Monthly Performance Report (April 2025) - Submit | 0 hrs | 0 days | 2025-05-12 | 2025-05-12 | 2656 | 2658 |  | Joy Schneider
6401 | 2658 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Department QC | 1 hr | 7 days | 2025-05-13 | 2025-05-21 | 2657 | 2659 |  | Gabriela Gibson
6402 | 2659 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-05-22 | 2025-05-23 | 2658 | 2660 |  | Sean Buchanan
6403 | 2660 | Future Task |  |  | D366 | Joy Schneider | Accept | DEL D366 - Monthly Performance Report (April 2025) - Accept | 0 hrs | 0 days | 2025-05-23 | 2025-05-23 | 2659 | 2662 |  | Sean Buchanan
6404 | 2661 | Future Task |  |  | D367 | Joy Schneider |  | D367 - Monthly Performance Report (May 2025) | 10 hrs | 17 days | 2025-06-02 | 2025-06-24
6487 | 2662 | Future Task |  |  | D367 | Joy Schneider | Create | Create May 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-06-02 | 2025-06-10 | 2660 | 2663 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6405 | 2663 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-06-11 | 2025-06-11 | 2662 | 2664 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6406 | 2664 | Future Task |  |  | D367 | Joy Schneider | Submit | DEL D367 - Monthly Performance Report (May 2025) - Submit | 0 hrs | 0 days | 2025-06-11 | 2025-06-11 | 2663 | 2665 |  | Joy Schneider
6407 | 2665 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Department QC | 1 hr | 7 days | 2025-06-12 | 2025-06-20 | 2664 | 2666 |  | Gabriela Gibson
6408 | 2666 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-06-23 | 2025-06-24 | 2665 | 2667 |  | Sean Buchanan
6409 | 2667 | Future Task |  |  | D367 | Joy Schneider | Accept | DEL D367 - Monthly Performance Report (May 2025) - Accept | 0 hrs | 0 days | 2025-06-24 | 2025-06-24 | 2666 | 2669 |  | Sean Buchanan
6410 | 2668 | Future Task |  |  | D368 | Joy Schneider |  | D368 - Monthly Performance Report (June 2025) | 10 hrs | 17 days | 2025-07-01 | 2025-07-24
6486 | 2669 | Future Task |  |  | D368 | Joy Schneider | Create | Create June 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-07-01 | 2025-07-10 | 2667 | 2670 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6411 | 2670 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-07-11 | 2025-07-11 | 2669 | 2671 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6412 | 2671 | Future Task |  |  | D368 | Joy Schneider | Submit | DEL D368 - Monthly Performance Report (June 2025) - Submit | 0 hrs | 0 days | 2025-07-11 | 2025-07-11 | 2670 | 2672 |  | Joy Schneider
6413 | 2672 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Department QC | 1 hr | 7 days | 2025-07-14 | 2025-07-22 | 2671 | 2673 |  | Gabriela Gibson
6414 | 2673 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-07-23 | 2025-07-24 | 2672 | 2674 |  | Sean Buchanan
6415 | 2674 | Future Task |  |  | D368 | Joy Schneider | Accept | DEL D368 - Monthly Performance Report (June 2025) - Accept | 0 hrs | 0 days | 2025-07-24 | 2025-07-24 | 2673 | 2676 |  | Sean Buchanan
6416 | 2675 | Future Task |  |  | D369 | Joy Schneider |  | D369 - Monthly Performance Report (July 2025) | 10 hrs | 17 days | 2025-08-01 | 2025-08-25
6485 | 2676 | Future Task |  |  | D369 | Joy Schneider | Create | Create July 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-08-01 | 2025-08-11 | 2674 | 2677 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6417 | 2677 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-08-12 | 2025-08-12 | 2676 | 2678 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6418 | 2678 | Future Task |  |  | D369 | Joy Schneider | Submit | DEL D369 - Monthly Performance Report (July 2025) - Submit | 0 hrs | 0 days | 2025-08-12 | 2025-08-12 | 2677 | 2679 |  | Joy Schneider
6419 | 2679 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Department QC | 1 hr | 7 days | 2025-08-13 | 2025-08-21 | 2678 | 2680 |  | Gabriela Gibson
6420 | 2680 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-08-22 | 2025-08-25 | 2679 | 2681 |  | Sean Buchanan
6421 | 2681 | Future Task |  |  | D369 | Joy Schneider | Accept | DEL D369 - Monthly Performance Report (July 2025) - Accept | 0 hrs | 0 days | 2025-08-25 | 2025-08-25 | 2680 | 2683 |  | Sean Buchanan
6422 | 2682 | Future Task |  |  | D370 | Joy Schneider |  | D370 - Monthly Performance Report (August 2025) | 10 hrs | 17 days | 2025-09-02 | 2025-09-24
6484 | 2683 | Future Task |  |  | D370 | Joy Schneider | Create | Create August 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-09-02 | 2025-09-10 | 2681 | 2684 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6423 | 2684 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-09-11 | 2025-09-11 | 2683 | 2685 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6424 | 2685 | Future Task |  |  | D370 | Joy Schneider | Submit | DEL D370 - Monthly Performance Report (August 2025) - Submit | 0 hrs | 0 days | 2025-09-11 | 2025-09-11 | 2684 | 2686 |  | Joy Schneider
6425 | 2686 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Department QC | 1 hr | 7 days | 2025-09-12 | 2025-09-22 | 2685 | 2687 |  | Gabriela Gibson
6426 | 2687 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-09-23 | 2025-09-24 | 2686 | 2688 |  | Sean Buchanan
6427 | 2688 | Future Task |  |  | D370 | Joy Schneider | Accept | DEL D370 - Monthly Performance Report (August 2025) - Accept | 0 hrs | 0 days | 2025-09-24 | 2025-09-24 | 2687 | 2690 |  | Sean Buchanan
6428 | 2689 | Future Task |  |  | D371 | Joy Schneider |  | D371 - Monthly Performance Report (September 2025) | 10 hrs | 17 days | 2025-10-01 | 2025-10-23
6483 | 2690 | Future Task |  |  | D371 | Joy Schneider | Create | Create September 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-10-01 | 2025-10-09 | 2688 | 2691 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6429 | 2691 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-10-10 | 2025-10-10 | 2690 | 2692 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6430 | 2692 | Future Task |  |  | D371 | Joy Schneider | Submit | DEL D371 - Monthly Performance Report (September 2025) - Submit | 0 hrs | 0 days | 2025-10-10 | 2025-10-10 | 2691 | 2693 |  | Joy Schneider
6431 | 2693 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Department QC | 1 hr | 7 days | 2025-10-13 | 2025-10-21 | 2692 | 2694 |  | Gabriela Gibson
6432 | 2694 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-10-22 | 2025-10-23 | 2693 | 2695 |  | Sean Buchanan
6433 | 2695 | Future Task |  |  | D371 | Joy Schneider | Accept | DEL D371 - Monthly Performance Report (September 2025) - Accept | 0 hrs | 0 days | 2025-10-23 | 2025-10-23 | 2694 | 2697 |  | Sean Buchanan
6434 | 2696 | Future Task |  |  | D373 | Joy Schneider |  | D373 - Monthly Performance Report (October 2025) | 10 hrs | 17 days | 2025-11-03 | 2025-11-26
6482 | 2697 | Future Task |  |  | D373 | Joy Schneider | Create | Create October 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-11-03 | 2025-11-12 | 2695 | 2698 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6435 | 2698 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-11-13 | 2025-11-13 | 2697 | 2699 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6436 | 2699 | Future Task |  |  | D373 | Joy Schneider | Submit | DEL D373 - Monthly Performance Report (October 2025) - Submit | 0 hrs | 0 days | 2025-11-13 | 2025-11-13 | 2698 | 2700 |  | Joy Schneider
6437 | 2700 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Department QC | 1 hr | 7 days | 2025-11-14 | 2025-11-24 | 2699 | 2701 |  | Gabriela Gibson
6438 | 2701 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-11-25 | 2025-11-26 | 2700 | 2702 |  | Sean Buchanan
6439 | 2702 | Future Task |  |  | D373 | Joy Schneider | Accept | DEL D373 - Monthly Performance Report (October 2025) - Accept | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 2701 | 2704 |  | Sean Buchanan
6440 | 2703 | Future Task |  |  | D374 | Joy Schneider |  | D374 - Monthly Performance Report (November 2025) | 10 hrs | 17 days | 2025-12-01 | 2025-12-23
6481 | 2704 | Future Task |  |  | D374 | Joy Schneider | Create | Create November 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-12-01 | 2025-12-09 | 2702 | 2705 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6441 | 2705 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-12-10 | 2025-12-10 | 2704 | 2706 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6442 | 2706 | Future Task |  |  | D374 | Joy Schneider | Submit | DEL D374 - Monthly Performance Report (November 2025) - Submit | 0 hrs | 0 days | 2025-12-10 | 2025-12-10 | 2705 | 2707 |  | Joy Schneider
6443 | 2707 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Department QC | 1 hr | 7 days | 2025-12-11 | 2025-12-19 | 2706 | 2708 |  | Gabriela Gibson
6444 | 2708 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-12-22 | 2025-12-23 | 2707 | 2709 |  | Sean Buchanan
6445 | 2709 | Future Task |  |  | D374 | Joy Schneider | Accept | DEL D374 - Monthly Performance Report (November 2025) - Accept | 0 hrs | 0 days | 2025-12-23 | 2025-12-23 | 2708 | 2711 |  | Sean Buchanan
6446 | 2710 | Future Task |  |  | D375 | Joy Schneider |  | D375 - Monthly Performance Report (December 2025) | 10 hrs | 17 days | 2026-01-02 | 2026-01-27
6480 | 2711 | Future Task |  |  | D375 | Joy Schneider | Create | Create December 2025 Monthly Performance Report | 3 hrs | 7 days | 2026-01-02 | 2026-01-12 | 2709 | 2712 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6447 | 2712 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-01-13 | 2026-01-13 | 2711 | 2713 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6448 | 2713 | Future Task |  |  | D375 | Joy Schneider | Submit | DEL D375 - Monthly Performance Report (December 2025) - Submit | 0 hrs | 0 days | 2026-01-13 | 2026-01-13 | 2712 | 2714 |  | Joy Schneider
6449 | 2714 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Department QC | 1 hr | 7 days | 2026-01-14 | 2026-01-23 | 2713 | 2715 |  | Gabriela Gibson
6450 | 2715 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Contract Manager Review | 2 hrs | 2 days | 2026-01-26 | 2026-01-27 | 2714 | 2716 |  | Sean Buchanan
6451 | 2716 | Future Task |  |  | D375 | Joy Schneider | Accept | DEL D375 - Monthly Performance Report (December 2025) - Accept | 0 hrs | 0 days | 2026-01-27 | 2026-01-27 | 2715 | 2718 |  | Sean Buchanan
6452 | 2717 | Future Task |  |  | D432 | Joy Schneider |  | D432 - Monthly Performance Report (January 2026) | 10 hrs | 17 days | 2026-02-02 | 2026-02-24
6479 | 2718 | Future Task |  |  | D432 | Joy Schneider | Create | Create January 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-02-02 | 2026-02-10 | 2716 | 2719 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6453 | 2719 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-02-11 | 2026-02-11 | 2718 | 2720 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6454 | 2720 | Future Task |  |  | D432 | Joy Schneider | Submit | DEL D432 - Monthly Performance Report (January 2026) - Submit | 0 hrs | 0 days | 2026-02-11 | 2026-02-11 | 2719 | 2721 |  | Joy Schneider
6455 | 2721 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Department QC | 1 hr | 7 days | 2026-02-12 | 2026-02-20 | 2720 | 2722 |  | Gabriela Gibson
6456 | 2722 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-02-23 | 2026-02-24 | 2721 | 2723 |  | Sean Buchanan
6457 | 2723 | Future Task |  |  | D432 | Joy Schneider | Accept | DEL D432 - Monthly Performance Report (January 2026) - Accept | 0 hrs | 0 days | 2026-02-24 | 2026-02-24 | 2722 | 2725 |  | Sean Buchanan
6458 | 2724 | Future Task |  |  | D434 | Joy Schneider |  | D434 - Monthly Performance Report (February 2026) | 10 hrs | 17 days | 2026-03-02 | 2026-03-24
6478 | 2725 | Future Task |  |  | D434 | Joy Schneider | Create | Create February 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-03-02 | 2026-03-10 | 2723 | 2726 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6459 | 2726 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-03-11 | 2026-03-11 | 2725 | 2727 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6460 | 2727 | Future Task |  |  | D434 | Joy Schneider | Submit | DEL D434 - Monthly Performance Report (February 2026) - Submit | 0 hrs | 0 days | 2026-03-11 | 2026-03-11 | 2726 | 2728 |  | Joy Schneider
6461 | 2728 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Department QC | 1 hr | 7 days | 2026-03-12 | 2026-03-20 | 2727 | 2729 |  | Gabriela Gibson
6462 | 2729 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-03-23 | 2026-03-24 | 2728 | 2730 |  | Sean Buchanan
6463 | 2730 | Future Task |  |  | D434 | Joy Schneider | Accept | DEL D434 - Monthly Performance Report (February 2026) - Accept | 0 hrs | 0 days | 2026-03-24 | 2026-03-24 | 2729 | 2732 |  | Sean Buchanan
6464 | 2731 | Future Task |  |  | D435 | Joy Schneider |  | D435 - Monthly Performance Report (March 2026) | 10 hrs | 17 days | 2026-04-01 | 2026-04-23
6477 | 2732 | Future Task |  |  | D435 | Joy Schneider | Create | Create March 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-04-01 | 2026-04-09 | 2730 | 2733 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6465 | 2733 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-04-10 | 2026-04-10 | 2732 | 2734 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6466 | 2734 | Future Task |  |  | D435 | Joy Schneider | Submit | DEL D435 - Monthly Performance Report (March 2026) - Submit | 0 hrs | 0 days | 2026-04-10 | 2026-04-10 | 2733 | 2735 |  | Joy Schneider
6467 | 2735 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Department QC | 1 hr | 7 days | 2026-04-13 | 2026-04-21 | 2734 | 2736 |  | Gabriela Gibson
6468 | 2736 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-04-22 | 2026-04-23 | 2735 | 2737 |  | Sean Buchanan
6469 | 2737 | Future Task |  |  | D435 | Joy Schneider | Accept | DEL D435 - Monthly Performance Report (March 2026) - Accept | 0 hrs | 0 days | 2026-04-23 | 2026-04-23 | 2736 | 2739 |  | Sean Buchanan
6470 | 2738 | Future Task |  |  | D437 | Joy Schneider |  | D437 - Monthly Performance Report (April 2026) | 10 hrs | 17 days | 2026-05-01 | 2026-05-26
6476 | 2739 | Future Task |  |  | D437 | Joy Schneider | Create | Create April 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-05-01 | 2026-05-11 | 2737 | 2740 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6471 | 2740 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-05-12 | 2026-05-12 | 2739 | 2741 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6472 | 2741 | Future Task |  |  | D437 | Joy Schneider | Submit | DEL D437 - Monthly Performance Report (April 2026) - Submit | 0 hrs | 0 days | 2026-05-12 | 2026-05-12 | 2740 | 2742 |  | Joy Schneider
6473 | 2742 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Department QC | 1 hr | 7 days | 2026-05-13 | 2026-05-21 | 2741 | 2743 |  | Gabriela Gibson
6474 | 2743 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-05-22 | 2026-05-26 | 2742 | 2744 |  | Sean Buchanan
6475 | 2744 | Future Task |  |  | D437 | Joy Schneider | Accept | DEL D437 - Monthly Performance Report (April 2026) - Accept | 0 hrs | 0 days | 2026-05-26 | 2026-05-26 | 2743 | 2746 |  | Sean Buchanan
6491 | 2745 | Future Task |  |  | D438 | Joy Schneider |  | D438 - Monthly Performance Report (May 2026) | 10 hrs | 17 days | 2026-06-01 | 2026-06-23
6595 | 2746 | Future Task |  |  | D438 | Joy Schneider | Create | Create May 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-06-01 | 2026-06-09 | 2744 | 2747 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6492 | 2747 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-06-10 | 2026-06-10 | 2746 | 2748 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6493 | 2748 | Future Task |  |  | D438 | Joy Schneider | Submit | DEL D438 - Monthly Performance Report (May 2026) - Submit | 0 hrs | 0 days | 2026-06-10 | 2026-06-10 | 2747 | 2749 |  | Joy Schneider
6494 | 2749 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Department QC | 1 hr | 7 days | 2026-06-11 | 2026-06-19 | 2748 | 2750 |  | Gabriela Gibson
6495 | 2750 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-06-22 | 2026-06-23 | 2749 | 2751 |  | Sean Buchanan
6496 | 2751 | Future Task |  |  | D438 | Joy Schneider | Accept | DEL D438 - Monthly Performance Report (May 2026) - Accept | 0 hrs | 0 days | 2026-06-23 | 2026-06-23 | 2750 | 2753 |  | Sean Buchanan
6497 | 2752 | Future Task |  |  | D439 | Joy Schneider |  | D439 - Monthly Performance Report (June 2026) | 10 hrs | 17 days | 2026-07-01 | 2026-07-24
6594 | 2753 | Future Task |  |  | D439 | Joy Schneider | Create | Create June 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-07-01 | 2026-07-10 | 2751 | 2754 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6498 | 2754 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-07-13 | 2026-07-13 | 2753 | 2755 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6499 | 2755 | Future Task |  |  | D439 | Joy Schneider | Submit | DEL D439 - Monthly Performance Report (June 2026) - Submit | 0 hrs | 0 days | 2026-07-13 | 2026-07-13 | 2754 | 2756 |  | Joy Schneider
6500 | 2756 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Department QC | 1 hr | 7 days | 2026-07-14 | 2026-07-22 | 2755 | 2757 |  | Gabriela Gibson
6501 | 2757 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-07-23 | 2026-07-24 | 2756 | 2758 |  | Sean Buchanan
6502 | 2758 | Future Task |  |  | D439 | Joy Schneider | Accept | DEL D439 - Monthly Performance Report (June 2026) - Accept | 0 hrs | 0 days | 2026-07-24 | 2026-07-24 | 2757 | 2760 |  | Sean Buchanan
6503 | 2759 | Future Task |  |  | D441 | Joy Schneider |  | D441 - Monthly Performance Report (July 2026) | 10 hrs | 17 days | 2026-08-03 | 2026-08-25
6593 | 2760 | Future Task |  |  | D441 | Joy Schneider | Create | Create July 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-08-03 | 2026-08-11 | 2758 | 2761 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6504 | 2761 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-08-12 | 2026-08-12 | 2760 | 2762 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6505 | 2762 | Future Task |  |  | D441 | Joy Schneider | Submit | DEL D441 - Monthly Performance Report (July 2026) - Submit | 0 hrs | 0 days | 2026-08-12 | 2026-08-12 | 2761 | 2763 |  | Joy Schneider
6506 | 2763 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Department QC | 1 hr | 7 days | 2026-08-13 | 2026-08-21 | 2762 | 2764 |  | Gabriela Gibson
6507 | 2764 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-08-24 | 2026-08-25 | 2763 | 2765 |  | Sean Buchanan
6508 | 2765 | Future Task |  |  | D441 | Joy Schneider | Accept | DEL D441 - Monthly Performance Report (July 2026) - Accept | 0 hrs | 0 days | 2026-08-25 | 2026-08-25 | 2764 | 2767 |  | Sean Buchanan
6509 | 2766 | Future Task |  |  | D442 | Joy Schneider |  | D442 - Monthly Performance Report (August 2026) | 10 hrs | 17 days | 2026-09-01 | 2026-09-24
6592 | 2767 | Future Task |  |  | D442 | Joy Schneider | Create | Create August 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-09-01 | 2026-09-10 | 2765 | 2768 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6510 | 2768 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-09-11 | 2026-09-11 | 2767 | 2769 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6511 | 2769 | Future Task |  |  | D442 | Joy Schneider | Submit | DEL D442 - Monthly Performance Report (August 2026) - Submit | 0 hrs | 0 days | 2026-09-11 | 2026-09-11 | 2768 | 2770 |  | Joy Schneider
6512 | 2770 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Department QC | 1 hr | 7 days | 2026-09-14 | 2026-09-22 | 2769 | 2771 |  | Gabriela Gibson
6513 | 2771 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-09-23 | 2026-09-24 | 2770 | 2772 |  | Sean Buchanan
6514 | 2772 | Future Task |  |  | D442 | Joy Schneider | Accept | DEL D442 - Monthly Performance Report (August 2026) - Accept | 0 hrs | 0 days | 2026-09-24 | 2026-09-24 | 2771 | 2774 |  | Sean Buchanan
6515 | 2773 | Future Task |  |  | D443 | Joy Schneider |  | D443 - Monthly Performance Report (September 2026) | 10 hrs | 17 days | 2026-10-01 | 2026-10-23
6591 | 2774 | Future Task |  |  | D443 | Joy Schneider | Create | Create September 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-10-01 | 2026-10-09 | 2772 | 2775 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6516 | 2775 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-10-12 | 2026-10-12 | 2774 | 2776 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6517 | 2776 | Future Task |  |  | D443 | Joy Schneider | Submit | DEL D443 - Monthly Performance Report (September 2026) - Submit | 0 hrs | 0 days | 2026-10-12 | 2026-10-12 | 2775 | 2777 |  | Joy Schneider
6518 | 2777 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Department QC | 1 hr | 7 days | 2026-10-13 | 2026-10-21 | 2776 | 2778 |  | Gabriela Gibson
6519 | 2778 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-10-22 | 2026-10-23 | 2777 | 2779 |  | Sean Buchanan
6520 | 2779 | Future Task |  |  | D443 | Joy Schneider | Accept | DEL D443 - Monthly Performance Report (September 2026) - Accept | 0 hrs | 0 days | 2026-10-23 | 2026-10-23 | 2778 | 2781 |  | Sean Buchanan
6521 | 2780 | Future Task |  |  | D444 | Joy Schneider |  | D444 - Monthly Performance Report (October 2026) | 10 hrs | 17 days | 2026-11-02 | 2026-11-25
6590 | 2781 | Future Task |  |  | D444 | Joy Schneider | Create | Create October 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-11-02 | 2026-11-10 | 2779 | 2782 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6522 | 2782 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-11-12 | 2026-11-12 | 2781 | 2783 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6523 | 2783 | Future Task |  |  | D444 | Joy Schneider | Submit | DEL D444 - Monthly Performance Report (October 2026) - Submit | 0 hrs | 0 days | 2026-11-12 | 2026-11-12 | 2782 | 2784 |  | Joy Schneider
6524 | 2784 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Department QC | 1 hr | 7 days | 2026-11-13 | 2026-11-23 | 2783 | 2785 |  | Gabriela Gibson
6525 | 2785 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-11-24 | 2026-11-25 | 2784 | 2786 |  | Sean Buchanan
6526 | 2786 | Future Task |  |  | D444 | Joy Schneider | Accept | DEL D444 - Monthly Performance Report (October 2026) - Accept | 0 hrs | 0 days | 2026-11-25 | 2026-11-25 | 2785 | 2788 |  | Sean Buchanan
6527 | 2787 | Future Task |  |  | D445 | Joy Schneider |  | D445 - Monthly Performance Report (November 2026) | 10 hrs | 17 days | 2026-12-01 | 2026-12-23
6589 | 2788 | Future Task |  |  | D445 | Joy Schneider | Create | Create November 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-12-01 | 2026-12-09 | 2786 | 2789 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6528 | 2789 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-12-10 | 2026-12-10 | 2788 | 2790 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6529 | 2790 | Future Task |  |  | D445 | Joy Schneider | Submit | DEL D445 - Monthly Performance Report (November 2026) - Submit | 0 hrs | 0 days | 2026-12-10 | 2026-12-10 | 2789 | 2791 |  | Joy Schneider
6530 | 2791 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Department QC | 1 hr | 7 days | 2026-12-11 | 2026-12-21 | 2790 | 2792 |  | Gabriela Gibson
6531 | 2792 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-12-22 | 2026-12-23 | 2791 | 2793 |  | Sean Buchanan
6532 | 2793 | Future Task |  |  | D445 | Joy Schneider | Accept | DEL D445 - Monthly Performance Report (November 2026) - Accept | 0 hrs | 0 days | 2026-12-23 | 2026-12-23 | 2792 | 2795 |  | Sean Buchanan
6533 | 2794 | Future Task |  |  | D446 | Joy Schneider |  | D446 - Monthly Performance Report (December 2026) | 10 hrs | 17 days | 2027-01-04 | 2027-01-27
6588 | 2795 | Future Task |  |  | D446 | Joy Schneider | Create | Create December 2026 Monthly Performance Report | 3 hrs | 7 days | 2027-01-04 | 2027-01-12 | 2793 | 2796 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6534 | 2796 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-01-13 | 2027-01-13 | 2795 | 2797 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6535 | 2797 | Future Task |  |  | D446 | Joy Schneider | Submit | DEL D446 - Monthly Performance Report (December 2026) - Submit | 0 hrs | 0 days | 2027-01-13 | 2027-01-13 | 2796 | 2798 |  | Joy Schneider
6536 | 2798 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Department QC | 1 hr | 7 days | 2027-01-14 | 2027-01-25 | 2797 | 2799 |  | Gabriela Gibson
6537 | 2799 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Contract Manager Review | 2 hrs | 2 days | 2027-01-26 | 2027-01-27 | 2798 | 2800 |  | Sean Buchanan
6538 | 2800 | Future Task |  |  | D446 | Joy Schneider | Accept | DEL D446 - Monthly Performance Report (December 2026) - Accept | 0 hrs | 0 days | 2027-01-27 | 2027-01-27 | 2799 | 2802 |  | Sean Buchanan
6539 | 2801 | Future Task |  |  | D447 | Joy Schneider |  | D447 - Monthly Performance Report (January 2027) | 10 hrs | 17 days | 2027-02-01 | 2027-02-23
6587 | 2802 | Future Task |  |  | D447 | Joy Schneider | Create | Create January 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-02-01 | 2027-02-09 | 2800 | 2803 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6540 | 2803 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-02-10 | 2027-02-10 | 2802 | 2804 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6541 | 2804 | Future Task |  |  | D447 | Joy Schneider | Submit | DEL D447 - Monthly Performance Report (January 2027) - Submit | 0 hrs | 0 days | 2027-02-10 | 2027-02-10 | 2803 | 2805 |  | Joy Schneider
6542 | 2805 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Department QC | 1 hr | 7 days | 2027-02-11 | 2027-02-19 | 2804 | 2806 |  | Gabriela Gibson
6543 | 2806 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-02-22 | 2027-02-23 | 2805 | 2807 |  | Sean Buchanan
6544 | 2807 | Future Task |  |  | D447 | Joy Schneider | Accept | DEL D447 - Monthly Performance Report (January 2027) - Accept | 0 hrs | 0 days | 2027-02-23 | 2027-02-23 | 2806 | 2809 |  | Sean Buchanan
6545 | 2808 | Future Task |  |  | D448 | Joy Schneider |  | D448 - Monthly Performance Report (February 2027) | 10 hrs | 17 days | 2027-03-01 | 2027-03-23
6586 | 2809 | Future Task |  |  | D448 | Joy Schneider | Create | Create February 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-03-01 | 2027-03-09 | 2807 | 2810 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6546 | 2810 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-03-10 | 2027-03-10 | 2809 | 2811 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6547 | 2811 | Future Task |  |  | D448 | Joy Schneider | Submit | DEL D448 - Monthly Performance Report (February 2027) - Submit | 0 hrs | 0 days | 2027-03-10 | 2027-03-10 | 2810 | 2812 |  | Joy Schneider
6548 | 2812 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Department QC | 1 hr | 7 days | 2027-03-11 | 2027-03-19 | 2811 | 2813 |  | Gabriela Gibson
6549 | 2813 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-03-22 | 2027-03-23 | 2812 | 2814 |  | Sean Buchanan
6550 | 2814 | Future Task |  |  | D448 | Joy Schneider | Accept | DEL D448 - Monthly Performance Report (February 2027) - Accept | 0 hrs | 0 days | 2027-03-23 | 2027-03-23 | 2813 | 2816 |  | Sean Buchanan
6551 | 2815 | Future Task |  |  | D449 | Joy Schneider |  | D449 - Monthly Performance Report (March 2027) | 10 hrs | 17 days | 2027-04-01 | 2027-04-23
6585 | 2816 | Future Task |  |  | D449 | Joy Schneider | Create | Create March 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-04-01 | 2027-04-09 | 2814 | 2817 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6552 | 2817 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-04-12 | 2027-04-12 | 2816 | 2818 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6553 | 2818 | Future Task |  |  | D449 | Joy Schneider | Submit | DEL D449 - Monthly Performance Report (March 2027) - Submit | 0 hrs | 0 days | 2027-04-12 | 2027-04-12 | 2817 | 2819 |  | Joy Schneider
6554 | 2819 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Department QC | 1 hr | 7 days | 2027-04-13 | 2027-04-21 | 2818 | 2820 |  | Gabriela Gibson
6555 | 2820 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-04-22 | 2027-04-23 | 2819 | 2821 |  | Sean Buchanan
6556 | 2821 | Future Task |  |  | D449 | Joy Schneider | Accept | DEL D449 - Monthly Performance Report (March 2027) - Accept | 0 hrs | 0 days | 2027-04-23 | 2027-04-23 | 2820 | 2823 |  | Sean Buchanan
6557 | 2822 | Future Task |  |  | D450 | Joy Schneider |  | D450 - Monthly Performance Report (April 2027) | 10 hrs | 17 days | 2027-05-03 | 2027-05-25
6584 | 2823 | Future Task |  |  | D450 | Joy Schneider | Create | Create April 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-05-03 | 2027-05-11 | 2821 | 2824 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6558 | 2824 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-05-12 | 2027-05-12 | 2823 | 2825 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6559 | 2825 | Future Task |  |  | D450 | Joy Schneider | Submit | DEL D450 - Monthly Performance Report (April 2027) - Submit | 0 hrs | 0 days | 2027-05-12 | 2027-05-12 | 2824 | 2826 |  | Joy Schneider
6560 | 2826 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Department QC | 1 hr | 7 days | 2027-05-13 | 2027-05-21 | 2825 | 2827 |  | Gabriela Gibson
6561 | 2827 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-05-24 | 2027-05-25 | 2826 | 2828 |  | Sean Buchanan
6562 | 2828 | Future Task |  |  | D450 | Joy Schneider | Accept | DEL D450 - Monthly Performance Report (April 2027) - Accept | 0 hrs | 0 days | 2027-05-25 | 2027-05-25 | 2827 | 2830 |  | Sean Buchanan
6563 | 2829 | Future Task |  |  | D451 | Joy Schneider |  | D451 - Monthly Performance Report (May 2027) | 10 hrs | 17 days | 2027-06-02 | 2027-06-24
6583 | 2830 | Future Task |  |  | D451 | Joy Schneider | Create | Create May 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-06-02 | 2027-06-10 | 2828 | 2831 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6564 | 2831 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-06-11 | 2027-06-11 | 2830 | 2832 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6565 | 2832 | Future Task |  |  | D451 | Joy Schneider | Submit | DEL D451 - Monthly Performance Report (May 2027) - Submit | 0 hrs | 0 days | 2027-06-11 | 2027-06-11 | 2831 | 2833 |  | Joy Schneider
6566 | 2833 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Department QC | 1 hr | 7 days | 2027-06-14 | 2027-06-22 | 2832 | 2834 |  | Gabriela Gibson
6567 | 2834 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-06-23 | 2027-06-24 | 2833 | 2835 |  | Sean Buchanan
6568 | 2835 | Future Task |  |  | D451 | Joy Schneider | Accept | DEL D451 - Monthly Performance Report (May 2027) - Accept | 0 hrs | 0 days | 2027-06-24 | 2027-06-24 | 2834 | 2837 |  | Sean Buchanan
6569 | 2836 | Future Task |  |  | D694 | Joy Schneider |  | D694 - Monthly Performance Report (June 2027) | 10 hrs | 17 days | 2027-07-01 | 2027-07-26
6582 | 2837 | Future Task |  |  | D694 | Joy Schneider | Create | Create June 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-07-01 | 2027-07-12 | 2835 | 2838 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6570 | 2838 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-07-13 | 2027-07-13 | 2837 | 2839 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6571 | 2839 | Future Task |  |  | D694 | Joy Schneider | Submit | DEL D694 - Monthly Performance Report (June 2027) - Submit | 0 hrs | 0 days | 2027-07-13 | 2027-07-13 | 2838 | 2840 |  | Joy Schneider
6572 | 2840 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Department QC | 1 hr | 7 days | 2027-07-14 | 2027-07-22 | 2839 | 2841 |  | Gabriela Gibson
6573 | 2841 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-07-23 | 2027-07-26 | 2840 | 2842 |  | Sean Buchanan
6574 | 2842 | Future Task |  |  | D694 | Joy Schneider | Accept | DEL D694 - Monthly Performance Report (June 2027) - Accept | 0 hrs | 0 days | 2027-07-26 | 2027-07-26 | 2841 | 2844 |  | Sean Buchanan
6575 | 2843 | Future Task |  |  | D695 | Joy Schneider |  | D695 - Monthly Performance Report (July 2027) | 10 hrs | 17 days | 2027-08-02 | 2027-08-24
6581 | 2844 | Future Task |  |  | D695 | Joy Schneider | Create | Create July 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-08-02 | 2027-08-10 | 2842 | 2845 |  | Joy Schneider,Bryan Sohayda,Francisca Li
6576 | 2845 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-08-11 | 2027-08-11 | 2844 | 2846 |  | Joy Schneider,Sean Buchanan,Shelley McCabe,Jarad Hermann
6577 | 2846 | Future Task |  |  | D695 | Joy Schneider | Submit | DEL D695 - Monthly Performance Report (July 2027) - Submit | 0 hrs | 0 days | 2027-08-11 | 2027-08-11 | 2845 | 2847 |  | Joy Schneider
6578 | 2847 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Department QC | 1 hr | 7 days | 2027-08-12 | 2027-08-20 | 2846 | 2848 |  | Gabriela Gibson
6579 | 2848 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-08-23 | 2027-08-24 | 2847 | 2849 |  | Sean Buchanan
6580 | 2849 | Future Task |  |  | D695 | Joy Schneider | Accept | DEL D695 - Monthly Performance Report (July 2027) - Accept | 0 hrs | 0 days | 2027-08-24 | 2027-08-24 | 2848 |  |  | Sean Buchanan
4047 | 2850 | Future Task | [5 empty] | Quarterly Newsletter for DDI of Reporting Functionality | 132 hrs | 658 days | 2023-06-21 | 2026-02-02
4048 | 2851 | Future Task | [5 empty] | Quarterly Newsletter | 132 hrs | 658 days | 2023-06-21 | 2026-02-02
4049 | 2852 | Future Task | [5 empty] | Quarterly Newsletter FY 22-23 Q4 | 12 hrs | 17 days | 2023-06-21 | 2023-07-14
4050 | 2853 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2023-06-21 | 2023-06-27 |  | 2854 |  | Jennifer Grant,Jennifer Reeves
4051 | 2854 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2023-06-28 | 2023-07-05 | 2853 | 2855 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4052 | 2855 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2023-07-06 | 2023-07-12 | 2854 | 2856 |  | Jimmy Cox,Steven Fielder
4053 | 2856 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2023-07-13 | 2023-07-14 | 2855 | 2858 |  | Dusti Kincl
4054 | 2857 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q1 | 12 hrs | 17 days | 2023-09-22 | 2023-10-16
4055 | 2858 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2023-09-22 | 2023-09-28 | 2856 | 2859 |  | Jennifer Grant,Jennifer Reeves
4056 | 2859 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2023-09-29 | 2023-10-05 | 2858 | 2860 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4057 | 2860 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2023-10-06 | 2023-10-12 | 2859 | 2861 |  | Jimmy Cox,Steven Fielder
4058 | 2861 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2023-10-13 | 2023-10-16 | 2860 | 2863 |  | Dusti Kincl
4059 | 2862 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q2 | 12 hrs | 17 days | 2023-12-18 | 2024-01-11
4060 | 2863 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2023-12-18 | 2023-12-22 | 2861 | 2864 |  | Jennifer Grant,Jennifer Reeves
4061 | 2864 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2023-12-26 | 2024-01-02 | 2863 | 2865 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4062 | 2865 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2024-01-03 | 2024-01-09 | 2864 | 2866 |  | Jimmy Cox,Steven Fielder
4063 | 2866 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2024-01-10 | 2024-01-11 | 2865 | 2868 |  | Dusti Kincl
4064 | 2867 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q3 | 12 hrs | 17 days | 2024-03-22 | 2024-04-15
4065 | 2868 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2024-03-22 | 2024-03-28 | 2866 | 2869 |  | Jennifer Grant,Jennifer Reeves
4066 | 2869 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2024-03-29 | 2024-04-04 | 2868 | 2870 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4067 | 2870 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2024-04-05 | 2024-04-11 | 2869 | 2871 |  | Jimmy Cox,Steven Fielder
4068 | 2871 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2024-04-12 | 2024-04-15 | 2870 | 2873 |  | Dusti Kincl
4069 | 2872 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q4 | 12 hrs | 17 days | 2024-06-20 | 2024-07-15
4070 | 2873 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2024-06-20 | 2024-06-26 | 2871 | 2874 |  | Jennifer Grant,Jennifer Reeves
4071 | 2874 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2024-06-27 | 2024-07-03 | 2873 | 2875 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4072 | 2875 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2024-07-05 | 2024-07-11 | 2874 | 2876 |  | Jimmy Cox,Steven Fielder
4073 | 2876 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2024-07-12 | 2024-07-15 | 2875 | 2878 |  | Dusti Kincl
4074 | 2877 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q1 | 12 hrs | 17 days | 2024-09-23 | 2024-10-15
4075 | 2878 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2024-09-23 | 2024-09-27 | 2876 | 2879 |  | Jennifer Grant,Jennifer Reeves
4076 | 2879 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2024-09-30 | 2024-10-04 | 2878 | 2880 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4077 | 2880 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2024-10-07 | 2024-10-11 | 2879 | 2881 |  | Jimmy Cox,Steven Fielder
4078 | 2881 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2024-10-14 | 2024-10-15 | 2880 | 2883 |  | Dusti Kincl
4079 | 2882 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q2 | 12 hrs | 17 days | 2024-12-16 | 2025-01-09
4080 | 2883 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2024-12-16 | 2024-12-20 | 2881 | 2884 |  | Jennifer Grant,Jennifer Reeves
4081 | 2884 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2024-12-23 | 2024-12-30 | 2883 | 2885 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4082 | 2885 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2024-12-31 | 2025-01-07 | 2884 | 2886 |  | Jimmy Cox,Steven Fielder
4083 | 2886 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2025-01-08 | 2025-01-09 | 2885 | 2888 |  | Dusti Kincl
4084 | 2887 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q3 | 12 hrs | 17 days | 2025-03-24 | 2025-04-15
4085 | 2888 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2025-03-24 | 2025-03-28 | 2886 | 2889 |  | Jennifer Grant,Jennifer Reeves
4086 | 2889 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2025-03-31 | 2025-04-04 | 2888 | 2890 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4087 | 2890 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2025-04-07 | 2025-04-11 | 2889 | 2891 |  | Jimmy Cox,Steven Fielder
4088 | 2891 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2025-04-14 | 2025-04-15 | 2890 | 2893 |  | Dusti Kincl
4089 | 2892 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q4 | 12 hrs | 17 days | 2025-06-20 | 2025-07-15
4090 | 2893 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2025-06-20 | 2025-06-26 | 2891 | 2894 |  | Jennifer Grant,Jennifer Reeves
4091 | 2894 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2025-06-27 | 2025-07-03 | 2893 | 2895 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4092 | 2895 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2025-07-07 | 2025-07-11 | 2894 | 2896 |  | Jimmy Cox,Steven Fielder
4093 | 2896 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2025-07-14 | 2025-07-15 | 2895 | 2898 |  | Dusti Kincl
4094 | 2897 | Future Task | [5 empty] | Quarterly Newsletter FY 25-26 Q1 | 12 hrs | 17 days | 2025-09-26 | 2025-10-20
4095 | 2898 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2025-09-26 | 2025-10-02 | 2896 | 2899 |  | Jennifer Grant,Jennifer Reeves
4096 | 2899 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2025-10-03 | 2025-10-09 | 2898 | 2900 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4097 | 2900 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2025-10-10 | 2025-10-16 | 2899 | 2901 |  | Jimmy Cox,Steven Fielder
4098 | 2901 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2025-10-17 | 2025-10-20 | 2900 | 2903 |  | Dusti Kincl
4099 | 2902 | Future Task | [5 empty] | Quarterly Newsletter FY 25-26 Q2 | 12 hrs | 17 days | 2026-01-08 | 2026-02-02
4100 | 2903 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2026-01-08 | 2026-01-14 | 2901 | 2904 |  | Jennifer Grant,Jennifer Reeves
4101 | 2904 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2026-01-15 | 2026-01-22 | 2903 | 2905 |  | Dusti Kincl,Matthew Breeding,Deana Metcalf,Carolyn Hicks,Shelley McCabe,Angie Robertson,Jennifer Reeves
4102 | 2905 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2026-01-23 | 2026-01-29 | 2904 | 2906 |  | Jimmy Cox,Steven Fielder
4103 | 2906 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2026-01-30 | 2026-02-02 | 2905 |  |  | Dusti Kincl

## VIEW ONLY 6.5.2023 (hidden)
Unique ID | ID | Status | Critical Path | RW | DEL, WP, SG # | Task Coordinator | Task Type | Task Name | Work | Duration | Start | Finish | Predecessors | Successors | Notes
0 | 0 | Late | [5 empty] | Project Schedule (Financials, Payroll, Data Warehouse and Business Intelligence) | 23,243.58 hrs | 1177 days | 2023-04-26 | 2027-12-28
7152 | 1 | Complete |  |  |  | Jimmy Cox |  | Amendment 8 Executed | 0 hrs | 0 days | 2023-04-26 | 2023-04-26 |  | 6,30FS+3 days,49FS+47 days,86FS+27 days,107FS+27 days,212FS+90 days,355FS+112 days,185FS+27 days,199FS+27 days,587FS+47 days,68FS+27 days,147,166,225,239,253,330,342,395,451,473,493,513,533,546,640,682,741,781,806,825,843,885,910,929,1001,1019,1044,1058...
2 | 2 | Late | [5 empty] | Implementation | 16,003.58 hrs | 699 days | 2023-04-26 | 2026-02-04
3769 | 3 | Late | [5 empty] | Design | 5,188 hrs | 475 days | 2023-04-26 | 2025-03-14
7155 | 4 | Future Task | Yes |  | SG1 | Jimmy Cox | Milestone | Stage Gate 1: Ready to Start Build | 0 hrs | 0 days | 2023-10-23 | 2023-10-23 | 47,57 |  | Nov/Dec 2023
3793 | 5 | Late | Yes |  | D635 | Joy Schneider |  | D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) | 450 hrs | 38 days | 2023-05-08 | 2023-06-29
7130 | 6 | Complete |  |  | D635 | Joy Schneider |  | Develop Outline of Project Schedule | 2 hrs | 1 day | 2023-05-08 | 2023-05-08 | 1 | 7SS
7131 | 7 | Complete |  |  | D635 | Joy Schneider |  | Create New Schedule Tasks Workbook | 4 hrs | 1 day | 2023-05-08 | 2023-05-08 | 6SS | 8,9,10FS+1 day
7132 | 8 | Complete |  |  | D635 | Joy Schneider |  | Gather Tasks from State Architects | 60 hrs | 4 days | 2023-05-09 | 2023-05-12 | 7 | 19
7133 | 9 | Complete |  |  | D635 | Joy Schneider |  | Load Amendment 8 Deliverables and Work Products to Project Schedule | 4 hrs | 2 days | 2023-05-09 | 2023-05-10 | 7 | 19
7134 | 10 | Complete |  |  | D635 | Joy Schneider |  | Load Resources into Project Schedule | 8 hrs | 1 day | 2023-05-10 | 2023-05-10 | 7FS+1 day | 11
7135 | 11 | Complete |  |  | D635 | Joy Schneider |  | Add and Refine Work Activities for Amendment 8 Deliverables | 17 hrs | 2 days | 2023-05-11 | 2023-05-12 | 10 | 12SS+1 day
7136 | 12 | Complete |  |  | D635 | Joy Schneider |  | Add Tasks from State Architects | 10 hrs | 1 day | 2023-05-12 | 2023-05-12 | 11SS+1 day | 13
7137 | 13 | Late |  |  | D635 | Joy Schneider |  | Provide Project Schedule Export Reports | 2 hrs | 1 day | 2023-05-15 | 2023-05-15 | 12 | 14SS,15SS
7138 | 14 | Late |  |  | D635 | Joy Schneider |  | Add and Refine Work Activities for Amendment 8 Work Products | 60 hrs | 5 days | 2023-05-15 | 2023-05-19 | 13SS | 19
7139 | 15 | Complete |  |  | D635 | Joy Schneider |  | Project Schedule Working Sessions | 85 hrs | 5 days | 2023-05-15 | 2023-05-19 | 13SS | 16
7140 | 16 | Late |  |  | D635 | Joy Schneider |  | Refine Work Activities for Non-SSI Deliverables and Work Products | 26 hrs | 5 days | 2023-05-22 | 2023-05-26 | 15 | 17SS+2 days
7141 | 17 | Late |  |  | D635 | Joy Schneider |  | Define Tasks to Assign to Critical Path Column | 25 hrs | 3 days | 2023-05-24 | 2023-05-26 | 16SS+2 days | 18
7142 | 18 | Future Task |  |  | D635 | Joy Schneider |  | Provide Project Schedule Export Reports and Refine Based on Input | 70 hrs | 9 days | 2023-05-30 | 2023-06-09 | 17 | 19
7143 | 19 | Future Task |  |  | D635 | Joy Schneider |  | Conduct Project Schedule Baseline Prep Meeting | 36 hrs | 1 day | 2023-06-12 | 2023-06-12 | 18,8,9,14 | 20
4271 | 20 | Future Task |  |  | D635 | Joy Schneider | Submit | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Draft Submission | 0 hrs | 0 days | 2023-06-12 | 2023-06-12 | 19 | 21
4272 | 21 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Pre-Submission Collaborative Review | 14 hrs | 3 days | 2023-06-13 | 2023-06-15 | 20 | 22
4273 | 22 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Style Guide Review | 1 hr | 1 day | 2023-06-16 | 2023-06-16 | 21 | 23
4274 | 23 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Final Collaborative Review | 10 hrs | 3 days | 2023-06-19 | 2023-06-21 | 22 | 24
4275 | 24 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Accenture QC | 4 hrs | 2 days | 2023-06-22 | 2023-06-23 | 23 | 25
4276 | 25 | Future Task |  |  | D635 | Joy Schneider | Submit | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Submit | 0 hrs | 0 days | 2023-06-23 | 2023-06-23 | 24 | 26
4277 | 26 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Department QC | 4 hrs | 1 day | 2023-06-26 | 2023-06-26 | 25 | 27
4278 | 27 | Future Task |  |  | D635 | Joy Schneider | Review | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Contract Manager Review | 8 hrs | 3 days | 2023-06-27 | 2023-06-29 | 26 | 28
4279 | 28 | Future Task |  |  | D635 | Joy Schneider | Accept | DEL D635 - Update the Financials Project Schedule to include Payroll, Data Warehouse and Business Intelligence Activities (Combined) - Accept | 0 hrs | 0 days | 2023-06-29 | 2023-06-29 | 27 | 2291 | 2023-06-01
4280 | 29 | Late | Yes |  | D636 | Stacey Terry |  | D636 - Completion of Solution Design (Requirements) Segment I | 309 hrs | 82 days | 2023-05-01 | 2023-08-24
4308 | 30 | Late |  |  | D636 | Stacey Terry |  | Identify Functional Designs (Segment I) | 50 hrs | 10 days | 2023-05-01 | 2023-05-12 | 1FS+3 days | 31
4281 | 31 | Late |  |  | D636 | Stacey Terry | Create | DED D636 - Completion of Solution Design (Requirements) Segment I - Create | 8 hrs | 10 days | 2023-05-15 | 2023-05-26 | 30 | 32
4282 | 32 | Future Task |  |  | D636 | Stacey Terry | Submit | DED D636 - Completion of Solution Design (Requirements) Segment I - Submit | 0 hrs | 0 days | 2023-05-26 | 2023-05-26 | 31 | 33
4283 | 33 | Future Task |  |  | D636 | Stacey Terry | Review | DED D636 - Completion of Solution Design (Requirements) Segment I - Collaborative Review | 24 hrs | 4 days | 2023-05-30 | 2023-06-02 | 32 | 34
4284 | 34 | Future Task |  |  | D636 | Stacey Terry | Approve | DED D636 - Completion of Solution Design (Requirements) Segment I - Approve | 0 hrs | 0 days | 2023-06-02 | 2023-06-02 | 33 | 35
4309 | 35 | Future Task |  |  | D636 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs (Segment I) | 50 hrs | 5 days | 2023-06-05 | 2023-06-09 | 34 | 36
4310 | 36 | Future Task |  |  | D636 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment I) | 50 hrs | 4 days | 2023-06-12 | 2023-06-15 | 35 | 37
4311 | 37 | Future Task |  |  | D636 | Stacey Terry |  | Create, Review and Approve Functional Design Documents (Segment I) | 50 hrs | 32 days | 2023-06-16 | 2023-08-01 | 36 | 38FS-11 days
4312 | 38 | Future Task |  |  | D636 | Stacey Terry |  | Create Summary Document | 20 hrs | 11 days | 2023-07-18 | 2023-08-01 | 37FS-11 days | 39,1542SS,1586SS,1629SS,1454,1499
4285 | 39 | Future Task |  |  | D636 | Stacey Terry | Submit | DEL D636 - Completion of Solution Design (Requirements) Segment I - Draft Submission | 0 hrs | 0 days | 2023-08-01 | 2023-08-01 | 38 | 40
4286 | 40 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2023-08-02 | 2023-08-08 | 39 | 41
4287 | 41 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Style Guide Review | 1 hr | 1 day | 2023-08-09 | 2023-08-09 | 40 | 42
4288 | 42 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Final Collaborative Review | 20 hrs | 5 days | 2023-08-10 | 2023-08-16 | 41 | 43
4289 | 43 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Accenture QC | 4 hrs | 2 days | 2023-08-17 | 2023-08-18 | 42 | 44
4290 | 44 | Future Task |  |  | D636 | Stacey Terry | Submit | DEL D636 - Completion of Solution Design (Requirements) Segment I - Submit | 0 hrs | 0 days | 2023-08-18 | 2023-08-18 | 43 | 451664
4291 | 45 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Department QC | 4 hrs | 1 day | 2023-08-21 | 2023-08-21 | 44 | 46
4292 | 46 | Future Task |  |  | D636 | Stacey Terry | Review | DEL D636 - Completion of Solution Design (Requirements) Segment I - Contract Manager Review | 8 hrs | 3 days | 2023-08-22 | 2023-08-24 | 45 | 47
4293 | 47 | Future Task |  |  | D636 | Stacey Terry | Accept | DEL D636 - Completion of Solution Design (Requirements) Segment I - Accept | 0 hrs | 0 days | 2023-08-24 | 2023-08-24 | 46 | 216,580,584,585,4 | July 2023 (Aug 2023)
4294 | 48 | Future Task | Yes |  | D637 | Stacey Terry |  | D637 - Completion of Solution Design (Requirements) Segment II | 342 hrs | 96 days | 2023-07-03 | 2023-11-16
4313 | 49 | Future Task |  |  | D637 | Stacey Terry |  | Identify Functional Designs (Segment II) | 50 hrs | 10 days | 2023-07-03 | 2023-07-17 | 1FS+47 days | 50
4295 | 50 | Future Task |  |  | D637 | Stacey Terry | Create | DED D637 - Completion of Solution Design (Requirements) Segment II - Create | 16 hrs | 10 days | 2023-07-18 | 2023-07-31 | 49 | 51
4296 | 51 | Future Task |  |  | D637 | Stacey Terry | Submit | DED D637 - Completion of Solution Design (Requirements) Segment II - Submit | 0 hrs | 0 days | 2023-07-31 | 2023-07-31 | 50 | 52
4297 | 52 | Future Task |  |  | D637 | Stacey Terry | Review | DED D637 - Completion of Solution Design (Requirements) Segment II - Collaborative Review | 24 hrs | 10 days | 2023-08-01 | 2023-08-14 | 51 | 53
4298 | 53 | Future Task |  |  | D637 | Stacey Terry | Approve | DED D637 - Completion of Solution Design (Requirements) Segment II - Approve | 0 hrs | 0 days | 2023-08-14 | 2023-08-14 | 52 | 54
4314 | 54 | Future Task |  |  | D637 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs (Segment II) | 50 hrs | 4 days | 2023-08-15 | 2023-08-18 | 53 | 55
4315 | 55 | Future Task |  |  | D637 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment II) | 50 hrs | 5 days | 2023-08-21 | 2023-08-25 | 54 | 56
4316 | 56 | Future Task |  |  | D637 | Stacey Terry |  | Create, Review and Approve Functional Design Documents (Segment II) | 50 hrs | 40 days | 2023-08-28 | 2023-10-23 | 55 | 57FS-11 days
4317 | 57 | Future Task |  |  | D637 | Stacey Terry |  | Create Summary Document | 50 hrs | 11 days | 2023-10-09 | 2023-10-23 | 56FS-11 days | 58,1545SS,1411SS,1589SS+2 days,1632SS+5 days,1457,1502,4
4299 | 58 | Future Task |  |  | D637 | Stacey Terry | Submit | DEL D637 - Completion of Solution Design (Requirements) Segment II - Draft Submission | 0 hrs | 0 days | 2023-10-23 | 2023-10-23 | 57 | 59
4300 | 59 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2023-10-24 | 2023-10-30 | 58 | 60
4301 | 60 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Style Guide Review | 1 hr | 1 day | 2023-10-31 | 2023-10-31 | 59 | 61
4302 | 61 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Final Collaborative Review | 20 hrs | 5 days | 2023-11-01 | 2023-11-07 | 60 | 62
4303 | 62 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Accenture QC | 1 hr | 2 days | 2023-11-08 | 2023-11-09 | 61 | 63
4304 | 63 | Future Task |  |  | D637 | Stacey Terry | Submit | DEL D637 - Completion of Solution Design (Requirements) Segment II - Submit | 0 hrs | 0 days | 2023-11-09 | 2023-11-09 | 62 | 64
4305 | 64 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Department QC | 2 hrs | 1 day | 2023-11-13 | 2023-11-13 | 63 | 65
4306 | 65 | Future Task |  |  | D637 | Stacey Terry | Review | DEL D637 - Completion of Solution Design (Requirements) Segment II - Contract Manager Review | 8 hrs | 3 days | 2023-11-14 | 2023-11-16 | 64 | 66
4307 | 66 | Future Task |  |  | D637 | Stacey Terry | Accept | DEL D637 - Completion of Solution Design (Requirements) Segment II - Accept | 0 hrs | 0 days | 2023-11-16 | 2023-11-16 | 65 | 580584585 | October 2023 (Nov 2023)
5585 | 67 | Future Task |  |  | D638 | Manojkumar Gurjar |  | D638 - Updated Data Conversion and Migration Strategy | 213 hrs | 80 days | 2023-06-05 | 2023-09-26
5586 | 68 | Future Task |  |  | D638 | Manojkumar Gurjar | Create | DED D638 - Updated Data Conversion and Migration Strategy - Create | 16 hrs | 10 days | 2023-06-05 | 2023-06-16 | 1FS+27 days | 69
5587 | 69 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DED D638 - Updated Data Conversion and Migration Strategy - Submit | 0 hrs | 0 days | 2023-06-16 | 2023-06-16 | 68 | 70
5588 | 70 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DED D638 - Updated Data Conversion and Migration Strategy - Collaborative Review | 24 hrs | 10 days | 2023-06-19 | 2023-06-30 | 69 | 71
5589 | 71 | Future Task |  |  | D638 | Manojkumar Gurjar | Approve | DED D638 - Updated Data Conversion and Migration Strategy - Approve | 0 hrs | 0 days | 2023-06-30 | 2023-06-30 | 70 | 72
5590 | 72 | Future Task |  |  | D638 | Manojkumar Gurjar |  | Define the approach for Data Cleansing | 8 hrs | 14 days | 2023-07-03 | 2023-07-21 | 71 | 73SS+4 days
5591 | 73 | Future Task |  |  | D638 | Manojkumar Gurjar |  | Define Communication/Collaboration for Data Conversion approach | 8 hrs | 10 days | 2023-07-10 | 2023-07-21 | 72SS+4 days | 74
5592 | 74 | Future Task |  |  | D638 | Manojkumar Gurjar |  | Identify Data Conversion Resources | 50 hrs | 10 days | 2023-07-24 | 2023-08-04 | 73 | 75
5593 | 75 | Future Task |  |  | D638 | Manojkumar Gurjar |  | Updated Data Conversion and Migration Strategy Document | 50 hrs | 19 days | 2023-08-07 | 2023-08-31 | 74 | 76
5594 | 76 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DEL D638 - Updated Data Conversion and Migration Strategy - Draft Submission | 0 hrs | 0 days | 2023-08-31 | 2023-08-31 | 75 | 77
5595 | 77 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2023-09-01 | 2023-09-08 | 76 | 78
5596 | 78 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Style Guide Review | 1 hr | 1 day | 2023-09-11 | 2023-09-11 | 77 | 79
5597 | 79 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Final Collaborative Review | 20 hrs | 5 days | 2023-09-12 | 2023-09-18 | 78 | 80
5598 | 80 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Accenture QC | 4 hrs | 2 days | 2023-09-19 | 2023-09-20 | 79 | 81
5599 | 81 | Future Task |  |  | D638 | Manojkumar Gurjar | Submit | DEL D638 - Updated Data Conversion and Migration Strategy - Submit | 0 hrs | 0 days | 2023-09-20 | 2023-09-20 | 80 | 82
5600 | 82 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Department QC | 4 hrs | 1 day | 2023-09-21 | 2023-09-21 | 81 | 83
5601 | 83 | Future Task |  |  | D638 | Manojkumar Gurjar | Review | DEL D638 - Updated Data Conversion and Migration Strategy - Contract Manager Review | 8 hrs | 3 days | 2023-09-22 | 2023-09-26 | 82 | 84
5602 | 84 | Future Task |  |  | D638 | Manojkumar Gurjar | Accept | DEL D638 - Updated Data Conversion and Migration Strategy - Accept | 0 hrs | 0 days | 2023-09-26 | 2023-09-26 | 83 |  | 2023-10-01
4375 | 85 | Future Task | Yes |  | D639 | Stacey Terry |  | D639 - Development of Standardized Business Process Models – Payroll | 241 hrs | 94 days | 2023-06-05 | 2023-10-16
4376 | 86 | Future Task |  |  | D639 | Stacey Terry | Create | DED D639 - Development of Standardized Business Process Models – Payroll - Create | 16 hrs | 10 days | 2023-06-05 | 2023-06-16 | 1FS+27 days | 87
4377 | 87 | Future Task |  |  | D639 | Stacey Terry | Submit | DED D639 - Development of Standardized Business Process Models – Payroll - Submit | 0 hrs | 0 days | 2023-06-16 | 2023-06-16 | 86 | 88
4378 | 88 | Future Task |  |  | D639 | Stacey Terry | Review | DED D639 - Development of Standardized Business Process Models – Payroll - Collaborative Review | 24 hrs | 10 days | 2023-06-19 | 2023-06-30 | 87 | 89
4379 | 89 | Future Task |  |  | D639 | Stacey Terry | Approve | DED D639 - Development of Standardized Business Process Models – Payroll - Approve | 0 hrs | 0 days | 2023-06-30 | 2023-06-30 | 88 | 90
4417 | 90 | Future Task |  |  | D639 | Stacey Terry |  | Identify Payroll Wave Business Processes and Subprocesses | 25 hrs | 5 days | 2023-07-03 | 2023-07-10 | 89 | 91SS+2 days
4418 | 91 | Future Task |  |  | D639 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Payroll Wave Business Processes and Subprocesses | 4 hrs | 5 days | 2023-07-06 | 2023-07-12 | 90SS+2 days | 92
4419 | 92 | Future Task |  |  | D639 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Payroll Wave Business Processes and Subprocesses | 20 hrs | 5 days | 2023-07-13 | 2023-07-19 | 91 | 93SS
4420 | 93 | Future Task |  |  | D639 | Stacey Terry |  | Create Payroll Wave Business Process Models | 30 hrs | 30 days | 2023-07-13 | 2023-08-23 | 92SS | 94
4421 | 94 | Future Task |  |  | D639 | Stacey Terry |  | Prepare Materials / Conduct Office Hours | 25 hrs | 10 days | 2023-08-24 | 2023-09-07 | 93 | 95
4422 | 95 | Future Task |  |  | D639 | Stacey Terry |  | Refine Payroll Wave Business Process Models | 20 hrs | 5 days | 2023-09-08 | 2023-09-14 | 94 | 96
4423 | 96 | Future Task |  |  | D639 | Stacey Terry |  | Create Summary Document | 20 hrs | 5 days | 2023-09-15 | 2023-09-21 | 95 | 97
4380 | 97 | Future Task |  |  | D639 | Stacey Terry | Submit | DEL D639 - Development of Standardized Business Process Models – Payroll - Draft Submission | 0 hrs | 0 days | 2023-09-21 | 2023-09-21 | 96 | 98
4381 | 98 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2023-09-22 | 2023-09-28 | 97 | 99
4382 | 99 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Style Guide Review | 1 hr | 1 day | 2023-09-29 | 2023-09-29 | 98 | 100
4383 | 100 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Final Collaborative Review | 20 hrs | 5 days | 2023-10-02 | 2023-10-06 | 99 | 101
4384 | 101 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Accenture QC | 4 hrs | 2 days | 2023-10-09 | 2023-10-10 | 100 | 102
4385 | 102 | Future Task |  |  | D639 | Stacey Terry | Submit | DEL D639 - Development of Standardized Business Process Models – Payroll - Submit | 0 hrs | 0 days | 2023-10-10 | 2023-10-10 | 101 | 103
4386 | 103 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Department QC | 4 hrs | 1 day | 2023-10-11 | 2023-10-11 | 102 | 104
4387 | 104 | Future Task |  |  | D639 | Stacey Terry | Review | DEL D639 - Development of Standardized Business Process Models – Payroll - Contract Manager Review | 8 hrs | 3 days | 2023-10-12 | 2023-10-16 | 103 | 105
4388 | 105 | Future Task |  |  | D639 | Stacey Terry | Accept | DEL D639 - Development of Standardized Business Process Models – Payroll - Accept | 0 hrs | 0 days | 2023-10-16 | 2023-10-16 | 104 | 1803580 | 2023-10-01
4389 | 106 | Future Task | Yes |  | D640 | Stacey Terry |  | D640 - Development of the Master Data Configuration Workbooks | 311 hrs | 142 days | 2023-06-05 | 2023-12-27
4390 | 107 | Future Task |  |  | D640 | Stacey Terry | Create | DED D640 - Development of the Master Data Configuration Workbooks - Create | 16 hrs | 10 days | 2023-06-05 | 2023-06-16 | 1FS+27 days | 108,111SS+9 days
4391 | 108 | Future Task |  |  | D640 | Stacey Terry | Submit | DED D640 - Development of the Master Data Configuration Workbooks - Submit | 0 hrs | 0 days | 2023-06-16 | 2023-06-16 | 107 | 109
4392 | 109 | Future Task |  |  | D640 | Stacey Terry | Review | DED D640 - Development of the Master Data Configuration Workbooks - Collaborative Review | 24 hrs | 10 days | 2023-06-19 | 2023-06-30 | 108 | 110
4393 | 110 | Future Task |  |  | D640 | Stacey Terry | Approve | DED D640 - Development of the Master Data Configuration Workbooks - Approve | 0 hrs | 0 days | 2023-06-30 | 2023-06-30 | 109
4424 | 111 | Future Task |  |  | D640 | Stacey Terry |  | Identify Configuration Inventory | 20 hrs | 10 days | 2023-06-16 | 2023-06-29 | 107SS+9 days | 112
4425 | 112 | Future Task |  |  | D640 | Stacey Terry |  | Update Design Work Unit Tracker for Configuration | 4 hrs | 5 days | 2023-06-30 | 2023-07-07 | 111 | 113
4426 | 113 | Future Task |  |  | D640 | Stacey Terry |  | Review and Confirm Design Work Unit Tracker for Configuration | 50 hrs | 4 days | 2023-07-10 | 2023-07-13 | 112 | 114
4427 | 114 | Future Task |  |  | D640 | Stacey Terry |  | Create, Review, and Confirm Configuration Workbooks and Agency Configuration Workbook Templates (this is a WU) | 40 hrs | 80 days | 2023-07-14 | 2023-11-03 | 113 | 115SS+20 days
4428 | 115 | Future Task |  |  | D640 | Stacey Terry |  | Configure Application | 40 hrs | 70 days | 2023-08-11 | 2023-11-20 | 114SS+20 days | 116
4429 | 116 | Future Task |  |  | D640 | Stacey Terry |  | Finalize Configuration Workbooks | 30 hrs | 10 days | 2023-11-21 | 2023-12-06 | 115 | 117FS-10 days
4430 | 117 | Future Task |  |  | D640 | Stacey Terry |  | Create Summary Document | 30 hrs | 7 days | 2023-11-21 | 2023-12-01 | 116FS-10 days | 118
4394 | 118 | Future Task |  |  | D640 | Stacey Terry | Submit | DEL D640 - Development of the Master Data Configuration Workbooks - Draft Submission | 0 hrs | 0 days | 2023-12-01 | 2023-12-01 | 117 | 119
4395 | 119 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2023-12-04 | 2023-12-08 | 118 | 120
4396 | 120 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Style Guide Review | 1 hr | 1 day | 2023-12-11 | 2023-12-11 | 119 | 121
4397 | 121 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Final Collaborative Review | 20 hrs | 5 days | 2023-12-12 | 2023-12-18 | 120 | 122
4398 | 122 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Accenture QC | 4 hrs | 2 days | 2023-12-19 | 2023-12-20 | 121 | 123
4399 | 123 | Future Task |  |  | D640 | Stacey Terry | Submit | DEL D640 - Development of the Master Data Configuration Workbooks - Submit | 0 hrs | 0 days | 2023-12-20 | 2023-12-20 | 122 | 124
4400 | 124 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Department QC | 4 hrs | 1 day | 2023-12-21 | 2023-12-21 | 123 | 125
4401 | 125 | Future Task |  |  | D640 | Stacey Terry | Review | DEL D640 - Development of the Master Data Configuration Workbooks - Contract Manager Review | 8 hrs | 3 days | 2023-12-22 | 2023-12-27 | 124 | 126
4402 | 126 | Future Task |  |  | D640 | Stacey Terry | Accept | DEL D640 - Development of the Master Data Configuration Workbooks - Accept | 0 hrs | 0 days | 2023-12-27 | 2023-12-27 | 125 | 577FS+6 days | 2023-12-01
4318 | 127 | Future Task | Yes |  | D641 | Stacey Terry |  | D641 - Completion of Solution Design (Requirements) Segment III | 327 hrs | 96 days | 2023-10-02 | 2024-02-20
4332 | 128 | Future Task |  |  | D641 | Stacey Terry |  | Identify Functional Designs (Segment III) | 50 hrs | 10 days | 2023-10-02 | 2023-10-13 | 1 | 129
4319 | 129 | Future Task |  |  | D641 | Stacey Terry | Create | DED D641 - Completion of Solution Design (Requirements) Segment III - Create | 16 hrs | 10 days | 2023-10-16 | 2023-10-27 | 128 | 130
4320 | 130 | Future Task |  |  | D641 | Stacey Terry | Submit | DED D641 - Completion of Solution Design (Requirements) Segment III - Submit | 0 hrs | 0 days | 2023-10-27 | 2023-10-27 | 129 | 131
4321 | 131 | Future Task |  |  | D641 | Stacey Terry | Review | DED D641 - Completion of Solution Design (Requirements) Segment III - Collaborative Review | 24 hrs | 10 days | 2023-10-30 | 2023-11-13 | 130 | 132
4322 | 132 | Future Task |  |  | D641 | Stacey Terry | Approve | DED D641 - Completion of Solution Design (Requirements) Segment III - Approve | 0 hrs | 0 days | 2023-11-13 | 2023-11-13 | 131 | 133
4333 | 133 | Future Task |  |  | D641 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs (Segment III) | 40 hrs | 4 days | 2023-11-14 | 2023-11-17 | 132 | 134
4334 | 134 | Future Task |  |  | D641 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment III) | 40 hrs | 5 days | 2023-11-20 | 2023-11-28 | 133 | 135
4335 | 135 | Future Task |  |  | D641 | Stacey Terry |  | Create, Review and Approve Functional Design Documents (Segment III) | 50 hrs | 40 days | 2023-11-29 | 2024-01-26 | 134 | 136FS-11 days
4336 | 136 | Future Task |  |  | D641 | Stacey Terry |  | Create Summary Document | 50 hrs | 11 days | 2024-01-11 | 2024-01-26 | 135FS-11 days | 137,1548SS,1592SS,1635SS+5 days,1460SS,1505
4323 | 137 | Future Task |  |  | D641 | Stacey Terry | Submit | DEL D641 - Completion of Solution Design (Requirements) Segment III - Draft Submission | 0 hrs | 0 days | 2024-01-26 | 2024-01-26 | 136 | 138
4324 | 138 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-01-29 | 2024-02-02 | 137 | 139
4325 | 139 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Style Guide Review | 1 hr | 1 day | 2024-02-05 | 2024-02-05 | 138 | 140
4326 | 140 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Final Collaborative Review | 20 hrs | 5 days | 2024-02-06 | 2024-02-12 | 139 | 141
4327 | 141 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Accenture QC | 4 hrs | 2 days | 2024-02-13 | 2024-02-14 | 140 | 142
4328 | 142 | Future Task |  |  | D641 | Stacey Terry | Submit | DEL D641 - Completion of Solution Design (Requirements) Segment III - Submit | 0 hrs | 0 days | 2024-02-14 | 2024-02-14 | 141 | 143
4329 | 143 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Department QC | 4 hrs | 1 day | 2024-02-15 | 2024-02-15 | 142 | 144
4330 | 144 | Future Task |  |  | D641 | Stacey Terry | Review | DEL D641 - Completion of Solution Design (Requirements) Segment III - Contract Manager Review | 8 hrs | 3 days | 2024-02-16 | 2024-02-20 | 143 | 145
4331 | 145 | Future Task |  |  | D641 | Stacey Terry | Accept | DEL D641 - Completion of Solution Design (Requirements) Segment III - Accept | 0 hrs | 0 days | 2024-02-20 | 2024-02-20 | 144 | 580584585 | January 2024 (Feb 2024)
4337 | 146 | Future Task | Yes |  | D644 | Stacey Terry |  | D644 - Completion of Solution Design (Requirements) Segment IV | 337 hrs | 85 days | 2024-01-29 | 2024-05-24
4351 | 147 | Future Task |  |  | D644 | Stacey Terry |  | Identify Functional Designs (Segment IV) | 50 hrs | 10 days | 2024-01-29 | 2024-02-09 | 1 | 148
4338 | 148 | Future Task |  |  | D644 | Stacey Terry | Create | DED D644 - Completion of Solution Design (Requirements) Segment IV - Create | 16 hrs | 10 days | 2024-02-12 | 2024-02-23 | 147 | 149
4339 | 149 | Future Task |  |  | D644 | Stacey Terry | Submit | DED D644 - Completion of Solution Design (Requirements) Segment IV - Submit | 0 hrs | 0 days | 2024-02-23 | 2024-02-23 | 148 | 150
4340 | 150 | Future Task |  |  | D644 | Stacey Terry | Review | DED D644 - Completion of Solution Design (Requirements) Segment IV - Collaborative Review | 24 hrs | 10 days | 2024-02-26 | 2024-03-08 | 149 | 151
4341 | 151 | Future Task |  |  | D644 | Stacey Terry | Approve | DED D644 - Completion of Solution Design (Requirements) Segment IV - Approve | 0 hrs | 0 days | 2024-03-08 | 2024-03-08 | 150 | 152
4352 | 152 | Future Task |  |  | D644 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs (Segment IV) | 50 hrs | 4 days | 2024-03-11 | 2024-03-14 | 151 | 153
4353 | 153 | Future Task |  |  | D644 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs (Segment IV) | 50 hrs | 4 days | 2024-03-15 | 2024-03-20 | 152 | 154
4354 | 154 | Future Task |  |  | D644 | Stacey Terry |  | Create, Review and Approve Functional Design Documents (Segment IV) | 50 hrs | 30 days | 2024-03-21 | 2024-05-01 | 153 | 155FS-8 days
4355 | 155 | Future Task |  |  | D644 | Stacey Terry |  | Create Summary Document | 40 hrs | 8 days | 2024-04-22 | 2024-05-01 | 154FS-8 days | 156,1561SS,1605SS,1648SS+5 days,1473SS,1518SS
4342 | 156 | Future Task |  |  | D644 | Stacey Terry | Submit | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Draft Submission | 0 hrs | 0 days | 2024-05-01 | 2024-05-01 | 155 | 157
4343 | 157 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-05-02 | 2024-05-08 | 156 | 158584
4344 | 158 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Style Guide Review | 1 hr | 1 day | 2024-05-09 | 2024-05-09 | 157 | 159
4345 | 159 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Final Collaborative Review | 20 hrs | 5 days | 2024-05-10 | 2024-05-16 | 158 | 160
4346 | 160 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Accenture QC | 4 hrs | 2 days | 2024-05-17 | 2024-05-20 | 159 | 161
4347 | 161 | Future Task |  |  | D644 | Stacey Terry | Submit | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Submit | 0 hrs | 0 days | 2024-05-20 | 2024-05-20 | 160 | 162
4348 | 162 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Department QC | 4 hrs | 1 day | 2024-05-21 | 2024-05-21 | 161 | 163
4349 | 163 | Future Task |  |  | D644 | Stacey Terry | Review | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Contract Manager Review | 8 hrs | 3 days | 2024-05-22 | 2024-05-24 | 162 | 164
4350 | 164 | Future Task |  |  | D644 | Stacey Terry | Accept | DEL D644 - Completion of Solution Design (Requirements) Segment IV - Accept | 0 hrs | 0 days | 2024-05-24 | 2024-05-24 | 163 | 580FS+24 days,585 | April 2024 (May 2024)
4356 | 165 | Future Task | Yes |  | D650 | Stacey Terry |  | D650 - Completion of Solution Design (Requirements) DW/BI | 347 hrs | 160 days | 2024-03-01 | 2024-10-15
4357 | 166 | Future Task |  |  | D650 | Stacey Terry | Create | DED D650 - Completion of Solution Design (Requirements) DW/BI - Create | 16 hrs | 10 days | 2024-03-01 | 2024-03-14 | 1 | 167
4358 | 167 | Future Task |  |  | D650 | Stacey Terry | Submit | DED D650 - Completion of Solution Design (Requirements) DW/BI - Submit | 0 hrs | 0 days | 2024-03-14 | 2024-03-14 | 166 | 168
4359 | 168 | Future Task |  |  | D650 | Stacey Terry | Review | DED D650 - Completion of Solution Design (Requirements) DW/BI - Collaborative Review | 24 hrs | 10 days | 2024-03-15 | 2024-03-28 | 167 | 169
4360 | 169 | Future Task |  |  | D650 | Stacey Terry | Approve | DED D650 - Completion of Solution Design (Requirements) DW/BI - Approve | 0 hrs | 0 days | 2024-03-28 | 2024-03-28 | 168 | 170
4370 | 170 | Future Task |  |  | D650 | Stacey Terry |  | Identify Functional Designs DW/BI | 50 hrs | 10 days | 2024-03-29 | 2024-04-11 | 169 | 171
4371 | 171 | Future Task |  |  | D650 | Stacey Terry |  | Update Deliverable Work Unit Tracker for Functional Designs DW/BI | 50 hrs | 10 days | 2024-04-12 | 2024-04-25 | 170 | 172
4372 | 172 | Future Task |  |  | D650 | Stacey Terry |  | Review and Confirm Deliverable Work Unit Tracker for Functional Designs DW/BI | 50 hrs | 10 days | 2024-04-26 | 2024-05-09 | 171 | 173
4373 | 173 | Future Task |  |  | D650 | Stacey Terry |  | Create, Review and Approve Functional Design Documents DW/BI | 50 hrs | 82 days | 2024-05-10 | 2024-09-05 | 172 | 174
4374 | 174 | Future Task |  |  | D650 | Stacey Terry |  | Create Summary Document | 50 hrs | 11 days | 2024-09-06 | 2024-09-20 | 173 | 175
4361 | 175 | Future Task |  |  | D650 | Stacey Terry | Submit | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Draft Submission | 0 hrs | 0 days | 2024-09-20 | 2024-09-20 | 174 | 176
4362 | 176 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-09-23 | 2024-09-27 | 175 | 177
4363 | 177 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Style Guide Review | 1 hr | 1 day | 2024-09-30 | 2024-09-30 | 176 | 178
4364 | 178 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Final Collaborative Review | 20 hrs | 5 days | 2024-10-01 | 2024-10-07 | 177 | 179
4365 | 179 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Accenture QC | 4 hrs | 2 days | 2024-10-08 | 2024-10-09 | 178 | 180
4366 | 180 | Future Task |  |  | D650 | Stacey Terry | Submit | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Submit | 0 hrs | 0 days | 2024-10-09 | 2024-10-09 | 179 | 181
4367 | 181 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Department QC | 4 hrs | 1 day | 2024-10-10 | 2024-10-10 | 180 | 182
4368 | 182 | Future Task |  |  | D650 | Stacey Terry | Review | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Contract Manager Review | 8 hrs | 3 days | 2024-10-11 | 2024-10-15 | 181 | 183
4369 | 183 | Future Task |  |  | D650 | Stacey Terry | Accept | DEL D650 - Completion of Solution Design (Requirements) DW/BI - Accept | 0 hrs | 0 days | 2024-10-15 | 2024-10-15 | 182 |  | 2024-10-01
4431 | 184 | Future Task |  |  | WP402 | Stacey Terry |  | WP402 - Requirements Traceability Matrix | 98 hrs | 55 days | 2023-06-05 | 2023-08-21
4432 | 185 | Future Task |  |  | WP402 | Stacey Terry | Create | WPED WP402 - Requirements Traceability Matrix - Create | 8 hrs | 5 days | 2023-06-05 | 2023-06-09 | 1FS+27 days | 186
4433 | 186 | Future Task |  |  | WP402 | Stacey Terry | Submit | WPED WP402 - Requirements Traceability Matrix - Submit | 0 hrs | 0 days | 2023-06-09 | 2023-06-09 | 185 | 187
4434 | 187 | Future Task |  |  | WP402 | Stacey Terry | Review | WPED WP402 - Requirements Traceability Matrix - Review | 12 hrs | 5 days | 2023-06-12 | 2023-06-16 | 186 | 188
4435 | 188 | Future Task |  |  | WP402 | Stacey Terry | Approve | WPED WP402 - Requirements Traceability Matrix - Approve | 0 hrs | 0 days | 2023-06-16 | 2023-06-16 | 187 | 189
4449 | 189 | Future Task |  |  | WP402 | Stacey Terry |  | Create Requirements Traceability Matrix Template | 2 hrs | 3 days | 2023-06-19 | 2023-06-21 | 188 | 190
4450 | 190 | Future Task |  |  | WP402 | Stacey Terry |  | Populate Requirements Traceability Matrix Template | 10 hrs | 5 days | 2023-06-22 | 2023-06-28 | 189 | 191
4451 | 191 | Future Task |  |  | WP402 | Stacey Terry |  | Create Summary Document | 6 hrs | 2 days | 2023-06-29 | 2023-06-30 | 190 | 192
4436 | 192 | Future Task |  |  | WP402 | Stacey Terry | Submit | WP WP402 - Requirements Traceability Matrix - Submit | 0 hrs | 0 days | 2023-06-30 | 2023-06-30 | 191 | 193
4437 | 193 | Future Task |  |  | WP402 | Stacey Terry | Review | WP WP402 - Requirements Traceability Matrix - Collaborative Review & Update | 20 hrs | 10 days | 2023-07-03 | 2023-07-17 | 192 | 194
4438 | 194 | Future Task |  |  | WP402 | Stacey Terry | Review | WP WP402 - Requirements Traceability Matrix - Final Review & Edits | 20 hrs | 5 days | 2023-07-18 | 2023-07-24 | 193 | 195
4439 | 195 | Future Task |  |  | WP402 | Stacey Terry | Approve | WP WP402 - Requirements Traceability Matrix - Approve | 0 hrs | 0 days | 2023-07-24 | 2023-07-24 | 194 | 373,412,431,722,196FS+5 days | 2023-06-01
7147 | 196 | Future Task |  |  | WP402 | Stacey Terry |  | Load Requirements in Requirements Traceability Tool | 10 hrs | 5 days | 2023-08-01 | 2023-08-07 | 195FS+5 days | 197
7148 | 197 | Future Task |  |  | WP402 | Stacey Terry |  | Validate Requirements in Requirements Traceability Tool | 10 hrs | 10 days | 2023-08-08 | 2023-08-21 | 196
4440 | 198 | Future Task |  |  | WP403 | Stacey Terry |  | WP403 - RICEFW Inventory | 200 hrs | 64 days | 2023-06-05 | 2023-09-01
4441 | 199 | Future Task |  |  | WP403 | Stacey Terry | Create | WPED WP403 - RICEFW Inventory - Create | 16 hrs | 10 days | 2023-06-05 | 2023-06-16 | 1FS+27 days | 200
4442 | 200 | Future Task |  |  | WP403 | Stacey Terry | Submit | WPED WP403 - RICEFW Inventory - Submit | 0 hrs | 0 days | 2023-06-16 | 2023-06-16 | 199 | 201
4443 | 201 | Future Task |  |  | WP403 | Stacey Terry | Review | WPED WP403 - RICEFW Inventory - Review | 24 hrs | 10 days | 2023-06-19 | 2023-06-30 | 200 | 202
4444 | 202 | Future Task |  |  | WP403 | Stacey Terry | Approve | WPED WP403 - RICEFW Inventory - Approve | 0 hrs | 0 days | 2023-06-30 | 2023-06-30 | 201 | 203
4454 | 203 | Future Task |  |  | WP403 | Stacey Terry |  | Create RICEFW Inventory Template | 20 hrs | 5 days | 2023-07-03 | 2023-07-10 | 202 | 204
4455 | 204 | Future Task |  |  | WP403 | Stacey Terry |  | Define and document RICEFW Inventory | 50 hrs | 14 days | 2023-07-11 | 2023-07-28 | 203 | 205
4456 | 205 | Future Task |  |  | WP403 | Stacey Terry |  | Populate RICEFW Inventory Template | 20 hrs | 5 days | 2023-07-31 | 2023-08-04 | 204 | 206
4457 | 206 | Future Task |  |  | WP403 | Stacey Terry |  | Create Summary Document | 30 hrs | 5 days | 2023-08-07 | 2023-08-11 | 205 | 207
4445 | 207 | Future Task |  |  | WP403 | Stacey Terry | Submit | WP WP403 - RICEFW Inventory - Submit | 0 hrs | 0 days | 2023-08-11 | 2023-08-11 | 206 | 208
4446 | 208 | Future Task |  |  | WP403 | Stacey Terry | Review | WP WP403 - RICEFW Inventory - Collaborative Review & Update | 20 hrs | 10 days | 2023-08-14 | 2023-08-25 | 207 | 209
4447 | 209 | Future Task |  |  | WP403 | Stacey Terry | Review | WP WP403 - RICEFW Inventory - Final Review & Edits | 20 hrs | 5 days | 2023-08-28 | 2023-09-01 | 208 | 210
4448 | 210 | Future Task |  |  | WP403 | Stacey Terry | Approve | WP WP403 - RICEFW Inventory - Approve | 0 hrs | 0 days | 2023-09-01 | 2023-09-01 | 209 |  | 2024-04-01
5667 | 211 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | WP404 - Data Conversion Inventory | 250 hrs | 108 days | 2023-09-01 | 2024-02-08
5668 | 212 | Future Task |  |  | WP404 | Manojkumar Gurjar | Create | WPED WP404 - Data Conversion Inventory - Create | 16 hrs | 10 days | 2023-09-01 | 2023-09-15 | 1FS+90 days | 213
5669 | 213 | Future Task |  |  | WP404 | Manojkumar Gurjar | Submit | WPED WP404 - Data Conversion Inventory - Submit | 0 hrs | 0 days | 2023-09-15 | 2023-09-15 | 212 | 214
5670 | 214 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WPED WP404 - Data Conversion Inventory - Review | 24 hrs | 10 days | 2023-09-18 | 2023-09-29 | 213 | 215
5671 | 215 | Future Task |  |  | WP404 | Manojkumar Gurjar | Approve | WPED WP404 - Data Conversion Inventory - Approve | 0 hrs | 0 days | 2023-09-29 | 2023-09-29 | 214 | 216
5672 | 216 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | Create Data Conversion Inventory Template | 50 hrs | 32 days | 2023-10-02 | 2023-11-15 | 215,47 | 217
5673 | 217 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | Populate Data Conversion Inventory with RICEFW Inventory conversion items | 50 hrs | 16 days | 2023-11-16 | 2023-12-11 | 216 | 218
5674 | 218 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | Identify/confirm Anticipated Source Systems and Legacy Tables | 50 hrs | 20 days | 2023-12-12 | 2024-01-10 | 217 | 219
5675 | 219 | Future Task |  |  | WP404 | Manojkumar Gurjar |  | Create Data Conversion Inventory Summary Document | 20 hrs | 5 days | 2024-01-11 | 2024-01-18 | 218 | 220
5676 | 220 | Future Task |  |  | WP404 | Manojkumar Gurjar | Submit | WP WP404 - Data Conversion Inventory - Submit | 0 hrs | 0 days | 2024-01-18 | 2024-01-18 | 219 | 221
5677 | 221 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WP WP404 - Data Conversion Inventory - Collaborative Review & Update | 20 hrs | 10 days | 2024-01-19 | 2024-02-01 | 220 | 222
5678 | 222 | Future Task |  |  | WP404 | Manojkumar Gurjar | Review | WP WP404 - Data Conversion Inventory - Final Review & Edits | 20 hrs | 5 days | 2024-02-02 | 2024-02-08 | 221 | 223
5679 | 223 | Future Task |  |  | WP404 | Manojkumar Gurjar | Approve | WP WP404 - Data Conversion Inventory - Approve | 0 hrs | 0 days | 2024-02-08 | 2024-02-08 | 222 |  | 2024-01-01
4458 | 224 | Future Task | Yes |  | WP405 | Stacey Terry |  | WP405 - Security Roles Matrix | 280 hrs | 85 days | 2024-04-01 | 2024-07-30
4459 | 225 | Future Task |  |  | WP405 | Stacey Terry | Create | WPED WP405 - Security Roles Matrix - Create | 16 hrs | 10 days | 2024-04-01 | 2024-04-12 | 1 | 226
4460 | 226 | Future Task |  |  | WP405 | Stacey Terry | Submit | WPED WP405 - Security Roles Matrix - Submit | 0 hrs | 0 days | 2024-04-12 | 2024-04-12 | 225 | 227
4461 | 227 | Future Task |  |  | WP405 | Stacey Terry | Review | WPED WP405 - Security Roles Matrix - Review | 24 hrs | 10 days | 2024-04-15 | 2024-04-26 | 226 | 228
4462 | 228 | Future Task |  |  | WP405 | Stacey Terry | Approve | WPED WP405 - Security Roles Matrix - Approve | 0 hrs | 0 days | 2024-04-26 | 2024-04-26 | 227 | 229
4467 | 229 | Future Task |  |  | WP405 | Stacey Terry |  | Create Security Roles Matrix Template | 20 hrs | 5 days | 2024-04-29 | 2024-05-03 | 228 | 230
4468 | 230 | Future Task |  |  | WP405 | Stacey Terry |  | Design, Review, and Confirm Security Roles Matrix | 50 hrs | 20 days | 2024-05-06 | 2024-06-03 | 229 | 231
4469 | 231 | Future Task |  |  | WP405 | Stacey Terry |  | Finalize Security Roles Matrix Design | 50 hrs | 5 days | 2024-06-04 | 2024-06-10 | 230 | 232
4470 | 232 | Future Task |  |  | WP405 | Stacey Terry |  | Configure Security Roles and Permission Lists | 50 hrs | 15 days | 2024-06-11 | 2024-07-01 | 231 | 233
4471 | 233 | Future Task |  |  | WP405 | Stacey Terry |  | Create Security Roles Matrix Summary Document | 30 hrs | 5 days | 2024-07-02 | 2024-07-09 | 232 | 234
4463 | 234 | Future Task |  |  | WP405 | Stacey Terry | Submit | WP WP405 - Security Roles Matrix - Submit | 0 hrs | 0 days | 2024-07-09 | 2024-07-09 | 233 | 235
4464 | 235 | Future Task |  |  | WP405 | Stacey Terry | Review | WP WP405 - Security Roles Matrix - Collaborative Review & Update | 20 hrs | 10 days | 2024-07-10 | 2024-07-23 | 234 | 236
4465 | 236 | Future Task |  |  | WP405 | Stacey Terry | Review | WP WP405 - Security Roles Matrix - Final Review & Edits | 20 hrs | 5 days | 2024-07-24 | 2024-07-30 | 235 | 237
4466 | 237 | Future Task |  |  | WP405 | Stacey Terry | Approve | WP WP405 - Security Roles Matrix - Approve | 0 hrs | 0 days | 2024-07-30 | 2024-07-30 | 236 | 579 | 2024-07-01
5680 | 238 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | WP411 - Batch and Interface Procedures | 109 hrs | 92 days | 2024-10-30 | 2025-03-14
5681 | 239 | Future Task |  |  | WP411 | Manojkumar Gurjar | Create | WPED WP411 - Batch and Interface Procedures - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1 | 240
5682 | 240 | Future Task |  |  | WP411 | Manojkumar Gurjar | Submit | WPED WP411 - Batch and Interface Procedures - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 239 | 241
5683 | 241 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WPED WP411 - Batch and Interface Procedures - Review | 24 hrs | 10 days | 2024-11-14 | 2024-11-27 | 240 | 242
5684 | 242 | Future Task |  |  | WP411 | Manojkumar Gurjar | Approve | WPED WP411 - Batch and Interface Procedures - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 241 | 243
6701 | 243 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | Define Interface Procedures | 3 hrs | 28 days | 2024-12-02 | 2025-01-10 | 242 | 244
6702 | 244 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | Create Batch Flow Diagram | 6 hrs | 9 days | 2025-01-13 | 2025-01-24 | 243 | 245
6703 | 245 | Future Task |  |  | WP411 | Manojkumar Gurjar |  | Create Batch and Interface Procedures Document | 20 hrs | 20 days | 2025-01-27 | 2025-02-21 | 244 | 246
5685 | 246 | Future Task |  |  | WP411 | Manojkumar Gurjar | Submit | WP WP411 - Batch and Interface Procedures - Submit | 0 hrs | 0 days | 2025-02-21 | 2025-02-21 | 245 | 247
5686 | 247 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WP WP411 - Batch and Interface Procedures - Collaborative Review & Update | 20 hrs | 10 days | 2025-02-24 | 2025-03-07 | 246 | 248
5687 | 248 | Future Task |  |  | WP411 | Manojkumar Gurjar | Review | WP WP411 - Batch and Interface Procedures - Final Review & Edits | 20 hrs | 5 days | 2025-03-10 | 2025-03-14 | 247 | 249
5688 | 249 | Future Task |  |  | WP411 | Manojkumar Gurjar | Approve | WP WP411 - Batch and Interface Procedures - Approve | 0 hrs | 0 days | 2025-03-14 | 2025-03-14 | 248
6596 | 250 | Late | Yes |  | I-WP101 | Deana Metcalf |  | I-WP101 Update Financials BPMs | 1,336 hrs | 294 days | 2023-04-26 | 2024-06-24
6597 | 251 | Late |  |  | I-WP101 | Deana Metcalf | Create | Identify BPMs by module | 6 hrs | 3 days | 2023-04-26 | 2023-04-28 | 1 | 258259
6598 | 252 | Late |  |  | I-WP101 | Deana Metcalf |  | WPED - I-WP101 Update Financials BPMs | 1,072 hrs | 274 days | 2023-05-01 | 2024-05-30
6599 | 253 | On Schedule |  |  | I-WP101 | Deana Metcalf | Create | WPED - I-WP101 Update Financials BPMs - Create | 8 hrs | 2 days | 2023-05-26 | 2023-05-30 | 1 | 254
6600 | 254 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | WPED - I-WP101 Update Financials BPMs - Submit | 0 hrs | 0 days | 2023-05-30 | 2023-05-30 | 253 | 255
6601 | 255 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | WPED - I-WP101 Update Financials BPMs - Collaborative Review and Update | 10 hrs | 8 days | 2023-05-31 | 2023-06-09 | 254 | 256
6602 | 256 | Future Task |  |  | I-WP101 | Deana Metcalf | Approve | WPED - I-WP101 Update Financials BPMs - Approve | 0 hrs | 0 days | 2023-06-09 | 2023-06-09 | 255
6603 | 257 | Late |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 1 - Financials Wave Business Process Models | 176 hrs | 86 days | 2023-05-01 | 2023-08-30
6604 | 258 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - May | 20 hrs | 22 days | 2023-05-01 | 2023-05-31 | 251 | 260
6605 | 259 | Late |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - May | 20 hrs | 22 days | 2023-05-01 | 2023-05-31 | 251 | 261
6606 | 260 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - June | 20 hrs | 22 days | 2023-06-01 | 2023-06-30 | 258 | 262
6607 | 261 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - June | 20 hrs | 22 days | 2023-06-01 | 2023-06-30 | 259 | 263
6608 | 262 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - July | 20 hrs | 20 days | 2023-07-03 | 2023-07-31 | 260 | 264
6609 | 263 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - July | 20 hrs | 20 days | 2023-07-03 | 2023-07-31 | 261 | 264
6610 | 264 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 1 - Submit | 0 hrs | 0 days | 2023-07-31 | 2023-07-31 | 262263 | 265270271272
6611 | 265 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Financials Wave Business Process Models - Segment 1 - Collaborative Review and Update | 20 hrs | 4 days | 2023-08-01 | 2023-08-04 | 264 | 266
6789 | 266 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Financials Wave Business Process Models - Segment 1 - Advisory Council Review and Updates | 14 hrs | 12 days | 2023-08-07 | 2023-08-22 | 265 | 267
6612 | 267 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Financials Wave Business Process Models - Segment 1 - Style Guide Updates | 2 hrs | 1 day | 2023-08-23 | 2023-08-23 | 266 | 268
6613 | 268 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Financials Wave Business Process Models - Segment 1 - Final Review and Update | 20 hrs | 5 days | 2023-08-24 | 2023-08-30 | 267 | 323
6614 | 269 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 2 - Financials Wave Business Process Models | 274 hrs | 210 days | 2023-08-01 | 2024-05-30
6615 | 270 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - August | 20 hrs | 23 days | 2023-08-01 | 2023-08-31 | 264 | 273
6616 | 271 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - August | 20 hrs | 23 days | 2023-08-01 | 2023-08-31 | 264 | 274
6617 | 272 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - August | 20 hrs | 23 days | 2023-08-01 | 2023-08-31 | 264 | 275
6618 | 273 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - September | 20 hrs | 20 days | 2023-09-01 | 2023-09-29 | 270 | 276279280
6619 | 274 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - September | 20 hrs | 20 days | 2023-09-01 | 2023-09-29 | 271 | 277
6620 | 275 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - September | 20 hrs | 20 days | 2023-09-01 | 2023-09-29 | 272 | 278
6621 | 276 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - October | 20 hrs | 20 days | 2023-10-02 | 2023-10-27 | 273 | 281
6622 | 277 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - October | 20 hrs | 20 days | 2023-10-02 | 2023-10-27 | 274 | 281
6623 | 278 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - October | 20 hrs | 20 days | 2023-10-02 | 2023-10-27 | 275 | 281
6624 | 279 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment LMC models Impacted by Segment 2 | 20 hrs | 20 days | 2023-10-02 | 2023-10-27 | 273 | 281
6625 | 280 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment PPA models Impacted by Segment 2 | 20 hrs | 20 days | 2023-10-02 | 2023-10-27 | 273 | 281
6626 | 281 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 2 - Submit | 0 hrs | 0 days | 2023-10-27 | 2023-10-27 | 276277278279280 | 282,287FS+2 days,288FS+2 days,289FS+2 days
6627 | 282 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Collaborative Review and Update | 20 hrs | 5 days | 2023-10-30 | 2023-11-03 | 281 | 283
6790 | 283 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Advisory Council Review and Updates | 20 hrs | 11 days | 2023-11-06 | 2023-11-21 | 282 | 284
6628 | 284 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 1 - Style Guide Updates | 2 hrs | 1 day | 2024-05-22 | 2024-05-22 | 283301319 | 285
6629 | 285 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 2 - Final Review and Update | 12 hrs | 5 days | 2024-05-23 | 2024-05-30 | 284 | 323
6630 | 286 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 3 - Financials Wave Business Process Models | 302 hrs | 145 days | 2023-11-01 | 2024-05-30
6631 | 287 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - November | 20 hrs | 19 days | 2023-11-01 | 2023-11-30 | 281FS+2 days | 290
6632 | 288 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - November | 20 hrs | 19 days | 2023-11-01 | 2023-11-30 | 281FS+2 days | 291
6633 | 289 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - November | 20 hrs | 19 days | 2023-11-01 | 2023-11-30 | 281FS+2 days | 292
6634 | 290 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - December | 20 hrs | 20 days | 2023-12-01 | 2023-12-29 | 287 | 293296
6635 | 291 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - December | 20 hrs | 20 days | 2023-12-01 | 2023-12-29 | 288 | 294297
6636 | 292 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - December | 20 hrs | 20 days | 2023-12-01 | 2023-12-29 | 289 | 295298
6637 | 293 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - January | 20 hrs | 18 days | 2024-01-02 | 2024-01-26 | 290 | 299
6638 | 294 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - January | 20 hrs | 18 days | 2024-01-02 | 2024-01-26 | 291 | 299
6639 | 295 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - January | 20 hrs | 18 days | 2024-01-02 | 2024-01-26 | 292 | 299
6640 | 296 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 3 | 20 hrs | 18 days | 2024-01-02 | 2024-01-26 | 290 | 299
6641 | 297 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 3 | 20 hrs | 18 days | 2024-01-02 | 2024-01-26 | 291 | 299
6642 | 298 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 3 | 20 hrs | 18 days | 2024-01-02 | 2024-01-26 | 292 | 299
6643 | 299 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 3 - Submit | 0 hrs | 0 days | 2024-01-26 | 2024-01-26 | 2.9329e+17 | 300,305FS+3 days,306FS+3 days,307FS+3 days
6644 | 300 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Collaborative Review and Update | 20 hrs | 5 days | 2024-01-29 | 2024-02-02 | 299 | 301
6792 | 301 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Advisory Council Review and Updates | 20 hrs | 17 days | 2024-02-05 | 2024-02-27 | 300 | 284302
6645 | 302 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Style Guide Updates | 2 hrs | 1 day | 2024-05-22 | 2024-05-22 | 301319 | 303
6646 | 303 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 3 - Final Review and Update | 20 hrs | 5 days | 2024-05-23 | 2024-05-30 | 302 | 323
6647 | 304 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Segment 4 - Financials Wave Business Process Models | 302 hrs | 85 days | 2024-02-01 | 2024-05-30
6648 | 305 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - February | 20 hrs | 21 days | 2024-02-01 | 2024-02-29 | 299FS+3 days | 308
6649 | 306 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - February | 20 hrs | 21 days | 2024-02-01 | 2024-02-29 | 299FS+3 days | 309
6650 | 307 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - February | 20 hrs | 21 days | 2024-02-01 | 2024-02-29 | 299FS+3 days | 310
6651 | 308 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - March | 20 hrs | 21 days | 2024-03-01 | 2024-03-29 | 305 | 311314
6652 | 309 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - March | 20 hrs | 21 days | 2024-03-01 | 2024-03-29 | 306 | 312315
6653 | 310 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - March | 20 hrs | 21 days | 2024-03-01 | 2024-03-29 | 307 | 313316
6654 | 311 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 LMC Process Models - Create - April | 20 hrs | 20 days | 2024-04-01 | 2024-04-26 | 308 | 317
6655 | 312 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 PPA Process Models - Create - April | 20 hrs | 20 days | 2024-04-01 | 2024-04-26 | 309 | 317
6656 | 313 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 TRP Process Models - Create - April | 20 hrs | 20 days | 2024-04-01 | 2024-04-26 | 310 | 317
6657 | 314 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 4 | 20 hrs | 20 days | 2024-04-01 | 2024-04-26 | 308 | 317
6658 | 315 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 4 | 20 hrs | 20 days | 2024-04-01 | 2024-04-26 | 309 | 317
6659 | 316 | Future Task |  |  | I-WP101 | Deana Metcalf | Create | I-WP101 Update prior segment models Impacted by Segment 4 | 20 hrs | 20 days | 2024-04-01 | 2024-04-26 | 310 | 317
6660 | 317 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | I-WP101 Financials Wave Business Process Models - Segment 4 - Submit | 0 hrs | 0 days | 2024-04-26 | 2024-04-26 | 3.1131e+17 | 318
6661 | 318 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Collaborative Review and Update | 20 hrs | 5 days | 2024-04-29 | 2024-05-03 | 317 | 319
6793 | 319 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Advisory Council Review and Updates | 20 hrs | 12 days | 2024-05-06 | 2024-05-21 | 318 | 284302320
6662 | 320 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Style Guide Updates | 2 hrs | 1 day | 2024-05-22 | 2024-05-22 | 319 | 321
6663 | 321 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | I-WP101 Financials Wave Business Process Models - Segment 4 - Final Review and Update | 20 hrs | 5 days | 2024-05-23 | 2024-05-30 | 320 | 323
6664 | 322 | Future Task |  |  | I-WP101 | Deana Metcalf |  | I-WP101 Update Financials BPMs Review Tasks | 44 hrs | 17 days | 2024-05-30 | 2024-06-24
6665 | 323 | Future Task |  |  | I-WP101 | Deana Metcalf | Submit | DEL - I-WP101 Update Financials BPMs - Submit | 0 hrs | 0 days | 2024-05-30 | 2024-05-30 | 268285303321 | 324
6666 | 324 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | DEL - I-WP101 Update Financials BPMs - Dept QC | 2 hrs | 1 day | 2024-05-31 | 2024-05-31 | 323 | 325
6667 | 325 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | DEL - I-WP101 Update Financials BPMs - Collaborative Review and Update | 20 hrs | 10 days | 2024-06-03 | 2024-06-14 | 324 | 326
6668 | 326 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | DEL - I-WP101 Update Financials BPMs - Style Guide Review | 2 hrs | 1 day | 2024-06-17 | 2024-06-17 | 325 | 327
6669 | 327 | Future Task |  |  | I-WP101 | Deana Metcalf | Review | DEL - I-WP101 Update Financials BPMs - Final Review and Update | 20 hrs | 5 days | 2024-06-18 | 2024-06-24 | 326 | 328
6670 | 328 | Future Task |  |  | I-WP101 | Deana Metcalf | Approve | DEL - I-WP101 Update Financials BPMs - Approve | 0 hrs | 0 days | 2024-06-24 | 2024-06-24 | 327
6671 | 329 | Future Task | Yes |  | I-WP125 | Deana Metcalf |  | I-WP125 - Updated D66 Chart of Accounts Design | 214 hrs | 63 days | 2023-06-05 | 2023-08-31
6672 | 330 | Future Task |  |  | I-WP125 | Deana Metcalf | Create | WPED - I-WP125 - Update D66 Chart of Accounts Design - Create | 2 hrs | 10 days | 2023-06-05 | 2023-06-16 | 1 | 331
6673 | 331 | Future Task |  |  | I-WP125 | Deana Metcalf | Submit | WPED - I-WP125 - Update D66 Chart of Accounts Design - Submit | 0 hrs | 0 days | 2023-06-16 | 2023-06-16 | 330 | 332
6674 | 332 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | WPED - I-WP125 - Update D66 Chart of Accounts Design - Collaborative Review and Update | 8 hrs | 10 days | 2023-06-19 | 2023-06-30 | 331 | 333
6675 | 333 | Future Task |  |  | I-WP125 | Deana Metcalf | Approve | WPED - I-WP125 - Update D66 Chart of Accounts Design - Approve | 0 hrs | 0 days | 2023-06-30 | 2023-06-30 | 332 | 334
6676 | 334 | Future Task |  |  | I-WP125 | Deana Metcalf | Create | I-WP125 Update D66 Chart of Accounts Design <Activities per WPED> | 100 hrs | 26 days | 2023-07-03 | 2023-08-08 | 333 | 335
6677 | 335 | Future Task |  |  | I-WP125 | Deana Metcalf | Submit | I-WP125 Update D66 Chart of Accounts Design - Submit | 0 hrs | 0 days | 2023-08-08 | 2023-08-08 | 334 | 336
6678 | 336 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | I-WP125 Update D66 Chart of Accounts Design - Dept QC | 1 hr | 1 day | 2023-08-09 | 2023-08-09 | 335 | 337
6679 | 337 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | I-WP125Update D66 Chart of Accounts Design - Collaborative Review and Update | 100 hrs | 10 days | 2023-08-10 | 2023-08-23 | 336 | 338
6680 | 338 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | I-WP125 Update D66 Chart of Accounts Design - Style Guide Review | 1 hr | 1 day | 2023-08-24 | 2023-08-24 | 337 | 339
6681 | 339 | Future Task |  |  | I-WP125 | Deana Metcalf | Review | I-WP125 Update D66 Chart of Accounts Design - Final Review and Update | 2 hrs | 5 days | 2023-08-25 | 2023-08-31 | 338 | 340
6682 | 340 | Future Task |  |  | I-WP125 | Deana Metcalf | Approve | I-WP125 Update D66 Chart of Accounts Design - Approve | 0 hrs | 0 days | 2023-08-31 | 2023-08-31 | 339
6795 | 341 | Future Task |  |  | I-WP120 | Deana Metcalf |  | I-WP120 - Knowledge Base Plan | 38 hrs | 49 days | 2023-05-30 | 2023-08-07
6796 | 342 | Future Task |  |  | I-WP120 | Deana Metcalf | Create | WPED- I-WP120 - Knowledge Base Plan - Create | 2 hrs | 9 days | 2023-05-30 | 2023-06-09 | 1 | 343
6797 | 343 | Future Task |  |  | I-WP120 | Deana Metcalf | Submit | WPED- I-WP120 - Knowledge Base Plan - Submit | 0 hrs | 0 days | 2023-06-09 | 2023-06-09 | 342 | 344
6798 | 344 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WPED- I-WP120 - Knowledge Base Plan - Review | 8 hrs | 9 days | 2023-06-12 | 2023-06-22 | 343 | 345
6799 | 345 | Future Task |  |  | I-WP120 | Deana Metcalf | Approve | WPED- I-WP120 - Knowledge Base Plan - Approve | 0 hrs | 0 days | 2023-06-22 | 2023-06-22 | 344 | 346
6800 | 346 | Future Task |  |  | I-WP120 | Deana Metcalf | Create | WP- I-WP120 - Knowledge Base Plan - Create | 20 hrs | 15 days | 2023-06-23 | 2023-07-14 | 345 | 347
6801 | 347 | Future Task |  |  | I-WP120 | Deana Metcalf | Submit | WP- I-WP120 - Knowledge Base Plan - Submit | 0 hrs | 0 days | 2023-07-14 | 2023-07-14 | 346 | 348
6802 | 348 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WP- I-WP120 - Knowledge Base Plan - Department QC | 1 hr | 1 day | 2023-07-17 | 2023-07-17 | 347 | 349
6803 | 349 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WP- I-WP120 - Knowledge Base Plan - Collaborative Review & Update | 4 hrs | 9 days | 2023-07-18 | 2023-07-28 | 348 | 350
6804 | 350 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WP- I-WP120 - Knowledge Base Plan - Style Guide Review | 1 hr | 1 day | 2023-07-31 | 2023-07-31 | 349 | 351
6805 | 351 | Future Task |  |  | I-WP120 | Deana Metcalf | Review | WP- I-WP120 - Knowledge Base Plan - Final Review & Edits | 2 hrs | 5 days | 2023-08-01 | 2023-08-07 | 350 | 352
6806 | 352 | Future Task |  |  | I-WP120 | Deana Metcalf | Approve | WP- I-WP120 - Knowledge Base Plan - Approve | 0 hrs | 0 days | 2023-08-07 | 2023-08-07 | 351
3770 | 353 | Future Task | [5 empty] | Build | 2,496 hrs | 598 days | 2023-08-07 | 2025-12-19
5534 | 354 | Future Task | Yes |  | D642 | Jarad Hermann |  | D642 - Updated Technical Architecture Design | 169 hrs | 77 days | 2023-10-04 | 2024-01-26
5535 | 355 | Future Task |  |  | D642 | Jarad Hermann | Create | DED D642 - Updated Technical Architecture Design - Create | 8 hrs | 10 days | 2023-10-04 | 2023-10-17 | 1FS+112 days | 356
5536 | 356 | Future Task |  |  | D642 | Jarad Hermann | Submit | DED D642 - Updated Technical Architecture Design - Submit | 0 hrs | 0 days | 2023-10-17 | 2023-10-17 | 355 | 357
5537 | 357 | Future Task |  |  | D642 | Jarad Hermann | Review | DED D642 - Updated Technical Architecture Design - Collaborative Review | 24 hrs | 10 days | 2023-10-18 | 2023-10-31 | 356 | 358
5538 | 358 | Future Task |  |  | D642 | Jarad Hermann | Approve | DED D642 - Updated Technical Architecture Design - Approve | 0 hrs | 0 days | 2023-10-31 | 2023-10-31 | 357 | 359
5539 | 359 | Future Task |  |  | D642 | Jarad Hermann |  | Confirm content to be migrated from D80 | 20 hrs | 40 days | 2023-11-01 | 2024-01-02 | 358 | 360SS,361SS,362SS
5540 | 360 | Future Task |  |  | D642 | Jarad Hermann |  | Review, update, and document run time architecture design | 20 hrs | 40 days | 2023-11-01 | 2024-01-02 | 359SS | 363
5541 | 361 | Future Task |  |  | D642 | Jarad Hermann |  | Review, update, and document development and operational architecture design | 20 hrs | 40 days | 2023-11-01 | 2024-01-02 | 359SS | 363
5542 | 362 | Future Task |  |  | D642 | Jarad Hermann |  | Review, update, and document architecture blueprint diagrams | 20 hrs | 40 days | 2023-11-01 | 2024-01-02 | 359SS | 363
5543 | 363 | Future Task |  |  | D642 | Jarad Hermann | Submit | DEL D642 - Updated Technical Architecture Design - Draft Submission | 0 hrs | 0 days | 2024-01-02 | 2024-01-02 | 362360361 | 364
5544 | 364 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-01-03 | 2024-01-09 | 363 | 365
5545 | 365 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Style Guide Review | 1 hr | 1 day | 2024-01-10 | 2024-01-10 | 364 | 366
5546 | 366 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Final Collaborative Review | 20 hrs | 5 days | 2024-01-11 | 2024-01-18 | 365 | 367
5547 | 367 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Accenture QC | 4 hrs | 2 days | 2024-01-19 | 2024-01-22 | 366 | 368
5548 | 368 | Future Task |  |  | D642 | Jarad Hermann | Submit | DEL D642 - Updated Technical Architecture Design - Submit | 0 hrs | 0 days | 2024-01-22 | 2024-01-22 | 367 | 369
5549 | 369 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Department QC | 4 hrs | 1 day | 2024-01-23 | 2024-01-23 | 368 | 370
5550 | 370 | Future Task |  |  | D642 | Jarad Hermann | Review | DEL D642 - Updated Technical Architecture Design - Contract Manager Review | 8 hrs | 3 days | 2024-01-24 | 2024-01-26 | 369 | 371
5551 | 371 | Future Task |  |  | D642 | Jarad Hermann | Accept | DEL D642 - Updated Technical Architecture Design - Accept | 0 hrs | 0 days | 2024-01-26 | 2024-01-26 | 370 |  | 2024-03-01
4486 | 372 | Future Task | Yes |  | D646 | Manojkumar Gurjar |  | D646 - Completion of Build Segment I | 257 hrs | 137 days | 2023-10-13 | 2024-04-30
4487 | 373 | Future Task |  |  | D646 | Manojkumar Gurjar | Create | DED D646 - Completion of Build Segment I - Create | 16 hrs | 10 days | 2023-10-13 | 2023-10-26 | 195 | 374
4488 | 374 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DED D646 - Completion of Build Segment I - Submit | 0 hrs | 0 days | 2023-10-26 | 2023-10-26 | 373 | 375
4489 | 375 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DED D646 - Completion of Build Segment I - Collaborative Review | 24 hrs | 10 days | 2023-10-27 | 2023-11-09 | 374 | 376
4490 | 376 | Future Task |  |  | D646 | Manojkumar Gurjar | Approve | DED D646 - Completion of Build Segment I - Approve | 0 hrs | 0 days | 2023-11-09 | 2023-11-09 | 375 | 377
4500 | 377 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment I | 20 hrs | 8 days | 2023-11-13 | 2023-11-22 | 376 | 378
4501 | 378 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment I | 20 hrs | 5 days | 2023-11-27 | 2023-12-01 | 377 | 379
4502 | 379 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment I | 20 hrs | 10 days | 2023-12-04 | 2023-12-15 | 378 | 380
4503 | 380 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Conduct Kick-Off meeting for Build Segment I | 20 hrs | 9 days | 2023-12-18 | 2023-12-29 | 379 | 381
4504 | 381 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I - Group 1 | 20 hrs | 21 days | 2024-01-02 | 2024-01-31 | 380 | 382
4505 | 382 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I - Group 2 | 20 hrs | 21 days | 2024-02-01 | 2024-02-29 | 381 | 383
4506 | 383 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I - Group 3 | 20 hrs | 21 days | 2024-03-01 | 2024-03-29 | 382 | 384FS-5 days
4507 | 384 | Future Task |  |  | D646 | Manojkumar Gurjar |  | Create Summary Document for Build Segment I | 20 hrs | 10 days | 2024-03-25 | 2024-04-05 | 383FS-5 days | 385
4491 | 385 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DEL D646 - Completion of Build Segment I - Draft Submission | 0 hrs | 0 days | 2024-04-05 | 2024-04-05 | 384 | 386
4492 | 386 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-04-08 | 2024-04-12 | 385 | 387
4493 | 387 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Style Guide Review | 1 hr | 1 day | 2024-04-15 | 2024-04-15 | 386 | 388
4494 | 388 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Final Collaborative Review | 20 hrs | 5 days | 2024-04-16 | 2024-04-22 | 387 | 389
4495 | 389 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Accenture QC | 4 hrs | 2 days | 2024-04-23 | 2024-04-24 | 388 | 390
4496 | 390 | Future Task |  |  | D646 | Manojkumar Gurjar | Submit | DEL D646 - Completion of Build Segment I - Submit | 0 hrs | 0 days | 2024-04-24 | 2024-04-24 | 389 | 391
4497 | 391 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Department QC | 4 hrs | 1 day | 2024-04-25 | 2024-04-25 | 390 | 392
4498 | 392 | Future Task |  |  | D646 | Manojkumar Gurjar | Review | DEL D646 - Completion of Build Segment I - Contract Manager Review | 8 hrs | 3 days | 2024-04-26 | 2024-04-30 | 391 | 393
4499 | 393 | Future Task |  |  | D646 | Manojkumar Gurjar | Accept | DEL D646 - Completion of Build Segment I - Accept | 0 hrs | 0 days | 2024-04-30 | 2024-04-30 | 392 | 584585 | 2024-04-01
4629 | 394 | Future Task | Yes |  | D647 | Manojkumar Gurjar |  | D647 - Establish DW/BI Environments | 149 hrs | 96 days | 2023-12-07 | 2024-04-23
4630 | 395 | Future Task |  |  | D647 | Manojkumar Gurjar | Create | DED D647 - Establish DW/BI Environments - Create | 8 hrs | 10 days | 2023-12-07 | 2023-12-20 | 1 | 396
4631 | 396 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DED D647 - Establish DW/BI Environments - Submit | 0 hrs | 0 days | 2023-12-20 | 2023-12-20 | 395 | 397
4632 | 397 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DED D647 - Establish DW/BI Environments - Collaborative Review | 24 hrs | 10 days | 2023-12-21 | 2024-01-05 | 396 | 398
4633 | 398 | Future Task |  |  | D647 | Manojkumar Gurjar | Approve | DED D647 - Establish DW/BI Environments - Approve | 0 hrs | 0 days | 2024-01-05 | 2024-01-05 | 397 | 399
4643 | 399 | Future Task |  |  | D647 | Manojkumar Gurjar |  | Establish DW/BI Environment Connections | 20 hrs | 19 days | 2024-01-08 | 2024-02-02 | 398 | 400
4644 | 400 | Future Task |  |  | D647 | Manojkumar Gurjar |  | Environment build and stand up | 20 hrs | 20 days | 2024-02-05 | 2024-03-01 | 399 | 401
4645 | 401 | Future Task |  |  | D647 | Manojkumar Gurjar |  | Verify access to DW/BI Environments | 20 hrs | 20 days | 2024-03-04 | 2024-03-29 | 400 | 402
4634 | 402 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DEL D647 - Establish DW/BI Environments - Draft Submission | 0 hrs | 0 days | 2024-03-29 | 2024-03-29 | 401 | 403
4635 | 403 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-04-01 | 2024-04-05 | 402 | 404
4636 | 404 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Style Guide Review | 1 hr | 1 day | 2024-04-08 | 2024-04-08 | 403 | 405
4637 | 405 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Final Collaborative Review | 20 hrs | 5 days | 2024-04-09 | 2024-04-15 | 404 | 406
4638 | 406 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Accenture QC | 4 hrs | 2 days | 2024-04-16 | 2024-04-17 | 405 | 407
4639 | 407 | Future Task |  |  | D647 | Manojkumar Gurjar | Submit | DEL D647 - Establish DW/BI Environments - Submit | 0 hrs | 0 days | 2024-04-17 | 2024-04-17 | 406 | 408
4640 | 408 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Department QC | 4 hrs | 1 day | 2024-04-18 | 2024-04-18 | 407 | 409
4641 | 409 | Future Task |  |  | D647 | Manojkumar Gurjar | Review | DEL D647 - Establish DW/BI Environments - Contract Manager Review | 8 hrs | 3 days | 2024-04-19 | 2024-04-23 | 408 | 410
4642 | 410 | Future Task |  |  | D647 | Manojkumar Gurjar | Accept | DEL D647 - Establish DW/BI Environments - Accept | 0 hrs | 0 days | 2024-04-23 | 2024-04-23 | 409 |  | 2024-05-01
4508 | 411 | Future Task | Yes |  | D648 | Manojkumar Gurjar |  | D648 - Completion of Build Segment II | 197 hrs | 90 days | 2024-03-11 | 2024-07-16
4509 | 412 | Future Task |  |  | D648 | Manojkumar Gurjar | Create | DED D648 - Completion of Build Segment II - Create | 16 hrs | 10 days | 2024-03-11 | 2024-03-22 | 195 | 413
4510 | 413 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DED D648 - Completion of Build Segment II - Submit | 0 hrs | 0 days | 2024-03-22 | 2024-03-22 | 412 | 414
4511 | 414 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DED D648 - Completion of Build Segment II - Collaborative Review | 24 hrs | 10 days | 2024-03-25 | 2024-04-05 | 413 | 415
4512 | 415 | Future Task |  |  | D648 | Manojkumar Gurjar | Approve | DED D648 - Completion of Build Segment II - Approve | 0 hrs | 0 days | 2024-04-05 | 2024-04-05 | 414 | 416
4536 | 416 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment II | 20 hrs | 7 days | 2024-04-08 | 2024-04-16 | 415 | 417
4537 | 417 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment II | 20 hrs | 8 days | 2024-04-17 | 2024-04-26 | 416 | 418
4538 | 418 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment II - Group 1 | 20 hrs | 19 days | 2024-04-29 | 2024-05-23 | 417 | 419
4539 | 419 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment II - Group 2 | 20 hrs | 19 days | 2024-05-24 | 2024-06-20 | 418 | 420FS-9 days
4540 | 420 | Future Task |  |  | D648 | Manojkumar Gurjar |  | Create Summary Document for Build Segment II | 20 hrs | 9 days | 2024-06-10 | 2024-06-20 | 419FS-9 days | 421
4513 | 421 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DEL D648 - Completion of Build Segment II - Draft Submission | 0 hrs | 0 days | 2024-06-20 | 2024-06-20 | 420 | 422
4514 | 422 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-06-21 | 2024-06-27 | 421 | 423
4515 | 423 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Style Guide Review | 1 hr | 1 day | 2024-06-28 | 2024-06-28 | 422 | 424
4516 | 424 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Final Collaborative Review | 20 hrs | 5 days | 2024-07-01 | 2024-07-08 | 423 | 425
4517 | 425 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Accenture QC | 4 hrs | 2 days | 2024-07-09 | 2024-07-10 | 424 | 426
4518 | 426 | Future Task |  |  | D648 | Manojkumar Gurjar | Submit | DEL D648 - Completion of Build Segment II - Submit | 0 hrs | 0 days | 2024-07-10 | 2024-07-10 | 425 | 427
4519 | 427 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Department QC | 4 hrs | 1 day | 2024-07-11 | 2024-07-11 | 426 | 428
4520 | 428 | Future Task |  |  | D648 | Manojkumar Gurjar | Review | DEL D648 - Completion of Build Segment II - Contract Manager Review | 8 hrs | 3 days | 2024-07-12 | 2024-07-16 | 427 | 429
4521 | 429 | Future Task |  |  | D648 | Manojkumar Gurjar | Accept | DEL D648 - Completion of Build Segment II - Accept | 0 hrs | 0 days | 2024-07-16 | 2024-07-16 | 428 | 585 | 2024-07-01
4522 | 430 | Future Task | Yes |  | D649 | Manojkumar Gurjar |  | D649 - Completion of Build Segment III | 217 hrs | 101 days | 2024-06-07 | 2024-10-29
4523 | 431 | Future Task |  |  | D649 | Manojkumar Gurjar | Create | DED D649 - Completion of Build Segment III - Create | 16 hrs | 10 days | 2024-06-07 | 2024-06-20 | 195 | 432
4524 | 432 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DED D649 - Completion of Build Segment III - Submit | 0 hrs | 0 days | 2024-06-20 | 2024-06-20 | 431 | 433
4525 | 433 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DED D649 - Completion of Build Segment III - Collaborative Review | 24 hrs | 10 days | 2024-06-21 | 2024-07-05 | 432 | 434
4526 | 434 | Future Task |  |  | D649 | Manojkumar Gurjar | Approve | DED D649 - Completion of Build Segment III - Approve | 0 hrs | 0 days | 2024-07-05 | 2024-07-05 | 433 | 435
4541 | 435 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment III | 20 hrs | 10 days | 2024-07-08 | 2024-07-19 | 434 | 436
4542 | 436 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment III | 20 hrs | 5 days | 2024-07-22 | 2024-07-26 | 435 | 437
4543 | 437 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment III | 20 hrs | 10 days | 2024-07-29 | 2024-08-09 | 436 | 438
4544 | 438 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment III - Group 1 | 20 hrs | 19 days | 2024-08-12 | 2024-09-06 | 437 | 439
4545 | 439 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment III - Group 2 | 20 hrs | 20 days | 2024-09-09 | 2024-10-04 | 438 | 440FS-10 days
4546 | 440 | Future Task |  |  | D649 | Manojkumar Gurjar |  | Create Summary Document for Build Segment III | 20 hrs | 10 days | 2024-09-23 | 2024-10-04 | 439FS-10 days | 441
4527 | 441 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DEL D649 - Completion of Build Segment III - Draft Submission | 0 hrs | 0 days | 2024-10-04 | 2024-10-04 | 440 | 442
4528 | 442 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-10-07 | 2024-10-11 | 441 | 443
4529 | 443 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Style Guide Review | 1 hr | 1 day | 2024-10-14 | 2024-10-14 | 442 | 444
4530 | 444 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Final Collaborative Review | 20 hrs | 5 days | 2024-10-15 | 2024-10-21 | 443 | 445
4531 | 445 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Accenture QC | 4 hrs | 2 days | 2024-10-22 | 2024-10-23 | 444 | 446
4532 | 446 | Future Task |  |  | D649 | Manojkumar Gurjar | Submit | DEL D649 - Completion of Build Segment III - Submit | 0 hrs | 0 days | 2024-10-23 | 2024-10-23 | 445 | 447
4533 | 447 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Department QC | 4 hrs | 1 day | 2024-10-24 | 2024-10-24 | 446 | 448
4534 | 448 | Future Task |  |  | D649 | Manojkumar Gurjar | Review | DEL D649 - Completion of Build Segment III - Contract Manager Review | 8 hrs | 3 days | 2024-10-25 | 2024-10-29 | 447 | 449
4535 | 449 | Future Task |  |  | D649 | Manojkumar Gurjar | Accept | DEL D649 - Completion of Build Segment III - Accept | 0 hrs | 0 days | 2024-10-29 | 2024-10-29 | 448 | 585 | 2024-10-01
4547 | 450 | Future Task | Yes |  | D653 | Manojkumar Gurjar |  | D653 - Completion of Build Segment I DW/BI | 297 hrs | 147 days | 2024-06-03 | 2025-01-02
4548 | 451 | Future Task |  |  | D653 | Manojkumar Gurjar | Create | DED D653 - Completion of Build Segment I DW/BI - Create | 16 hrs | 10 days | 2024-06-03 | 2024-06-14 | 1 | 452
4549 | 452 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DED D653 - Completion of Build Segment I DW/BI - Submit | 0 hrs | 0 days | 2024-06-14 | 2024-06-14 | 451 | 453
4550 | 453 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DED D653 - Completion of Build Segment I DW/BI - Collaborative Review | 24 hrs | 10 days | 2024-06-17 | 2024-06-28 | 452 | 454
4551 | 454 | Future Task |  |  | D653 | Manojkumar Gurjar | Approve | DED D653 - Completion of Build Segment I DW/BI - Approve | 0 hrs | 0 days | 2024-06-28 | 2024-06-28 | 453 | 455
4575 | 455 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment I DW/BI | 36 hrs | 9 days | 2024-07-01 | 2024-07-12 | 454 | 456
4576 | 456 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment I DW/BI | 20 hrs | 5 days | 2024-07-15 | 2024-07-19 | 455 | 457
4577 | 457 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment I DW/BI | 40 hrs | 10 days | 2024-07-22 | 2024-08-02 | 456 | 458
4578 | 458 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Conduct Kick-Off meeting for Build Segment I DW/BI | 40 hrs | 5 days | 2024-08-05 | 2024-08-09 | 457 | 459
4579 | 459 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I DW/BI - Group 1 | 20 hrs | 19 days | 2024-08-12 | 2024-09-06 | 458 | 460
4580 | 460 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I DW/BI - Group 2 | 20 hrs | 20 days | 2024-09-09 | 2024-10-04 | 459 | 461
4581 | 461 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment I DW/BI - Group 3 | 20 hrs | 20 days | 2024-10-07 | 2024-11-01 | 460 | 462
4582 | 462 | Future Task |  |  | D653 | Manojkumar Gurjar |  | Create Summary Document for Build Segment I DW/BI | 4 hrs | 22 days | 2024-11-04 | 2024-12-06 | 461 | 463
4552 | 463 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DEL D653 - Completion of Build Segment I DW/BI - Draft Submission | 0 hrs | 0 days | 2024-12-06 | 2024-12-06 | 462 | 464
4553 | 464 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-12-09 | 2024-12-13 | 463 | 465
4554 | 465 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Style Guide Review | 1 hr | 1 day | 2024-12-16 | 2024-12-16 | 464 | 466
4555 | 466 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Final Collaborative Review | 20 hrs | 5 days | 2024-12-17 | 2024-12-23 | 465 | 467
4556 | 467 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Accenture QC | 4 hrs | 2 days | 2024-12-24 | 2024-12-26 | 466 | 468
4557 | 468 | Future Task |  |  | D653 | Manojkumar Gurjar | Submit | DEL D653 - Completion of Build Segment I DW/BI - Submit | 0 hrs | 0 days | 2024-12-26 | 2024-12-26 | 467 | 469
4558 | 469 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Department QC | 4 hrs | 1 day | 2024-12-27 | 2024-12-27 | 468 | 470
4559 | 470 | Future Task |  |  | D653 | Manojkumar Gurjar | Review | DEL D653 - Completion of Build Segment I DW/BI - Contract Manager Review | 8 hrs | 3 days | 2024-12-30 | 2025-01-02 | 469 | 471
4560 | 471 | Future Task |  |  | D653 | Manojkumar Gurjar | Accept | DEL D653 - Completion of Build Segment I DW/BI - Accept | 0 hrs | 0 days | 2025-01-02 | 2025-01-02 | 470 | 585 | 2025-01-01
4561 | 472 | Future Task | Yes |  | D654 | Manojkumar Gurjar |  | D654 - Completion of Build Segment IV | 217 hrs | 98 days | 2024-09-09 | 2025-01-30
4562 | 473 | Future Task |  |  | D654 | Manojkumar Gurjar | Create | DED D654 - Completion of Build Segment IV - Create | 16 hrs | 10 days | 2024-09-09 | 2024-09-20 | 1 | 474
4563 | 474 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DED D654 - Completion of Build Segment IV - Submit | 0 hrs | 0 days | 2024-09-20 | 2024-09-20 | 473 | 475
4564 | 475 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DED D654 - Completion of Build Segment IV - Collaborative Review | 24 hrs | 10 days | 2024-09-23 | 2024-10-04 | 474 | 476
4565 | 476 | Future Task |  |  | D654 | Manojkumar Gurjar | Approve | DED D654 - Completion of Build Segment IV - Approve | 0 hrs | 0 days | 2024-10-04 | 2024-10-04 | 475 | 477
4583 | 477 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment IV | 20 hrs | 10 days | 2024-10-07 | 2024-10-18 | 476 | 478
4584 | 478 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment IV | 20 hrs | 5 days | 2024-10-21 | 2024-10-25 | 477 | 479
4585 | 479 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment IV | 20 hrs | 10 days | 2024-10-28 | 2024-11-08 | 478 | 480
4586 | 480 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment IV - Group 1 | 20 hrs | 17 days | 2024-11-12 | 2024-12-06 | 479 | 481
4587 | 481 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment IV - Group 2 | 20 hrs | 19 days | 2024-12-09 | 2025-01-06 | 480 | 482FS-14 days,483
4588 | 482 | Future Task |  |  | D654 | Manojkumar Gurjar |  | Create Summary Document for Build Segment IV | 20 hrs | 13 days | 2024-12-16 | 2025-01-03 | 481FS-14 days | 483
4566 | 483 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DEL D654 - Completion of Build Segment IV - Draft Submission | 0 hrs | 0 days | 2025-01-06 | 2025-01-06 | 481482 | 484
4567 | 484 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-01-07 | 2025-01-13 | 483 | 485
4568 | 485 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Style Guide Review | 1 hr | 1 day | 2025-01-14 | 2025-01-14 | 484 | 486
4569 | 486 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Final Collaborative Review | 20 hrs | 5 days | 2025-01-15 | 2025-01-22 | 485 | 487
4570 | 487 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Accenture QC | 4 hrs | 2 days | 2025-01-23 | 2025-01-24 | 486 | 488
4571 | 488 | Future Task |  |  | D654 | Manojkumar Gurjar | Submit | DEL D654 - Completion of Build Segment IV - Submit | 0 hrs | 0 days | 2025-01-24 | 2025-01-24 | 487 | 489
4572 | 489 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Department QC | 4 hrs | 1 day | 2025-01-27 | 2025-01-27 | 488 | 490
4573 | 490 | Future Task |  |  | D654 | Manojkumar Gurjar | Review | DEL D654 - Completion of Build Segment IV - Contract Manager Review | 8 hrs | 3 days | 2025-01-28 | 2025-01-30 | 489 | 491
4574 | 491 | Future Task |  |  | D654 | Manojkumar Gurjar | Accept | DEL D654 - Completion of Build Segment IV - Accept | 0 hrs | 0 days | 2025-01-30 | 2025-01-30 | 490 | 585 | 2025-01-01
4589 | 492 | Future Task | Yes |  | D659 | Manojkumar Gurjar |  | D659 - Completion of Build Segment II DW/BI | 219 hrs | 116 days | 2024-09-09 | 2025-02-25
4590 | 493 | Future Task |  |  | D659 | Manojkumar Gurjar | Create | DED D659 - Completion of Build Segment II DW/BI - Create | 16 hrs | 10 days | 2024-09-09 | 2024-09-20 | 1 | 494
4591 | 494 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DED D659 - Completion of Build Segment II DW/BI - Submit | 0 hrs | 0 days | 2024-09-20 | 2024-09-20 | 493 | 495
4592 | 495 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DED D659 - Completion of Build Segment II DW/BI - Collaborative Review | 24 hrs | 10 days | 2024-09-23 | 2024-10-04 | 494 | 496
4593 | 496 | Future Task |  |  | D659 | Manojkumar Gurjar | Approve | DED D659 - Completion of Build Segment II DW/BI - Approve | 0 hrs | 0 days | 2024-10-04 | 2024-10-04 | 495 | 497
4603 | 497 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment II DW/BI | 40 hrs | 10 days | 2024-10-07 | 2024-10-18 | 496 | 498
4604 | 498 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment II DW/BI | 20 hrs | 5 days | 2024-10-21 | 2024-10-25 | 497 | 499
4605 | 499 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment II DW/BI | 20 hrs | 5 days | 2024-10-28 | 2024-11-01 | 498 | 500
4606 | 500 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment II DW/BI - Group 1 | 20 hrs | 17 days | 2024-11-04 | 2024-11-27 | 499 | 501
4607 | 501 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment II DW/BI - Group 2 | 2 hrs | 23 days | 2024-12-02 | 2025-01-03 | 500 | 502
4608 | 502 | Future Task |  |  | D659 | Manojkumar Gurjar |  | Create Summary Document for Build Segment II DW/BI | 20 hrs | 19 days | 2025-01-06 | 2025-01-31 | 501 | 503
4594 | 503 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DEL D659 - Completion of Build Segment II DW/BI - Draft Submission | 0 hrs | 0 days | 2025-01-31 | 2025-01-31 | 502 | 504
4595 | 504 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-02-03 | 2025-02-07 | 503 | 505
4596 | 505 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Style Guide Review | 1 hr | 1 day | 2025-02-10 | 2025-02-10 | 504 | 506
4597 | 506 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Final Collaborative Review | 20 hrs | 5 days | 2025-02-11 | 2025-02-17 | 505 | 507
4598 | 507 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Accenture QC | 4 hrs | 2 days | 2025-02-18 | 2025-02-19 | 506 | 508
4599 | 508 | Future Task |  |  | D659 | Manojkumar Gurjar | Submit | DEL D659 - Completion of Build Segment II DW/BI - Submit | 0 hrs | 0 days | 2025-02-19 | 2025-02-19 | 507 | 509
4600 | 509 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Department QC | 4 hrs | 1 day | 2025-02-20 | 2025-02-20 | 508 | 510
4601 | 510 | Future Task |  |  | D659 | Manojkumar Gurjar | Review | DEL D659 - Completion of Build Segment II DW/BI - Contract Manager Review | 8 hrs | 3 days | 2025-02-21 | 2025-02-25 | 509 | 511
4602 | 511 | Future Task |  |  | D659 | Manojkumar Gurjar | Accept | DEL D659 - Completion of Build Segment II DW/BI - Accept | 0 hrs | 0 days | 2025-02-25 | 2025-02-25 | 510 | 585 | 2025-04-01
4609 | 512 | Future Task | Yes |  | D668 | Manojkumar Gurjar |  | D668 - Completion of Build Segment III DW/BI | 281 hrs | 93 days | 2024-10-30 | 2025-03-17
4610 | 513 | Future Task |  |  | D668 | Manojkumar Gurjar | Create | DED D668 - Completion of Build Segment III DW/BI - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1 | 514
4611 | 514 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DED D668 - Completion of Build Segment III DW/BI - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 513 | 515
4612 | 515 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DED D668 - Completion of Build Segment III DW/BI - Collaborative Review | 24 hrs | 10 days | 2024-11-14 | 2024-11-27 | 514 | 516
4613 | 516 | Future Task |  |  | D668 | Manojkumar Gurjar | Approve | DED D668 - Completion of Build Segment III DW/BI - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 515 | 517
4623 | 517 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Identify RICEFW items for Build Segment III DW/BI | 40 hrs | 5 days | 2024-12-02 | 2024-12-06 | 516 | 518SS+2 days
4624 | 518 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Create Work Unit Tracker for Build Segment III DW/BI | 40 hrs | 5 days | 2024-12-04 | 2024-12-10 | 517SS+2 days | 519
4625 | 519 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Review, Update and Confirm Work Unit Tracker for Build Segment III DW/BI | 24 hrs | 3 days | 2024-12-11 | 2024-12-13 | 518 | 520
4626 | 520 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment III DW/BI - Group 1 | 20 hrs | 18 days | 2024-12-16 | 2025-01-10 | 519 | 521
4627 | 521 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Build and Unit Test RICEFW for Build Segment III DW/BI - Group 2 | 20 hrs | 18 days | 2025-01-13 | 2025-02-06 | 520 | 522
4628 | 522 | Future Task |  |  | D668 | Manojkumar Gurjar |  | Create Summary Document for Build Segment III DW/BI | 40 hrs | 10 days | 2025-02-07 | 2025-02-20 | 521 | 523
4614 | 523 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DEL D668 - Completion of Build Segment III DW/BI - Draft Submission | 0 hrs | 0 days | 2025-02-20 | 2025-02-20 | 522 | 524
4615 | 524 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-02-21 | 2025-02-27 | 523 | 525
4616 | 525 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Style Guide Review | 1 hr | 1 day | 2025-02-28 | 2025-02-28 | 524 | 526
4617 | 526 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Final Collaborative Review | 20 hrs | 5 days | 2025-03-03 | 2025-03-07 | 525 | 527
4618 | 527 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Accenture QC | 4 hrs | 2 days | 2025-03-10 | 2025-03-11 | 526 | 528
4619 | 528 | Future Task |  |  | D668 | Manojkumar Gurjar | Submit | DEL D668 - Completion of Build Segment III DW/BI - Submit | 0 hrs | 0 days | 2025-03-11 | 2025-03-11 | 527 | 529
4620 | 529 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Department QC | 4 hrs | 1 day | 2025-03-12 | 2025-03-12 | 528 | 530
4621 | 530 | Future Task |  |  | D668 | Manojkumar Gurjar | Review | DEL D668 - Completion of Build Segment III DW/BI - Contract Manager Review | 8 hrs | 3 days | 2025-03-13 | 2025-03-17 | 529 | 531
4622 | 531 | Future Task |  |  | D668 | Manojkumar Gurjar | Accept | DEL D668 - Completion of Build Segment III DW/BI - Accept | 0 hrs | 0 days | 2025-03-17 | 2025-03-17 | 530 | 585 | 2025-08-01
4646 | 532 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | WP410 - Integration and Interface Strategy | 160 hrs | 95 days | 2023-08-07 | 2023-12-21
4647 | 533 | Future Task |  |  | WP410 | Manojkumar Gurjar | Create | WPED WP410 - Integration and Interface Strategy - Create | 16 hrs | 10 days | 2023-08-07 | 2023-08-18 | 1 | 534
4648 | 534 | Future Task |  |  | WP410 | Manojkumar Gurjar | Submit | WPED WP410 - Integration and Interface Strategy - Submit | 0 hrs | 0 days | 2023-08-18 | 2023-08-18 | 533 | 535
4649 | 535 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WPED WP410 - Integration and Interface Strategy - Review | 24 hrs | 10 days | 2023-08-21 | 2023-09-01 | 534 | 536
4650 | 536 | Future Task |  |  | WP410 | Manojkumar Gurjar | Approve | WPED WP410 - Integration and Interface Strategy - Approve | 0 hrs | 0 days | 2023-09-01 | 2023-09-01 | 535 | 537
4655 | 537 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | Define Interface and Integration Approach | 20 hrs | 19 days | 2023-09-05 | 2023-09-29 | 536 | 538
4656 | 538 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | Create Interface and Integration Architecture Diagram | 20 hrs | 15 days | 2023-10-02 | 2023-10-20 | 537 | 539540
4657 | 539 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | Review and update Interface and Integration Operations | 20 hrs | 19 days | 2023-10-23 | 2023-11-17 | 538 | 540
4658 | 540 | Future Task |  |  | WP410 | Manojkumar Gurjar |  | Finalize the Interface and Integration Strategy Document | 20 hrs | 7 days | 2023-11-20 | 2023-11-30 | 538539 | 541
4651 | 541 | Future Task |  |  | WP410 | Manojkumar Gurjar | Submit | WP WP410 - Integration and Interface Strategy - Submit | 0 hrs | 0 days | 2023-11-30 | 2023-11-30 | 540 | 542
4652 | 542 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WP WP410 - Integration and Interface Strategy - Collaborative Review & Update | 20 hrs | 10 days | 2023-12-01 | 2023-12-14 | 541 | 543
4653 | 543 | Future Task |  |  | WP410 | Manojkumar Gurjar | Review | WP WP410 - Integration and Interface Strategy - Final Review & Edits | 20 hrs | 5 days | 2023-12-15 | 2023-12-21 | 542 | 544
4654 | 544 | Future Task |  |  | WP410 | Manojkumar Gurjar | Approve | WP WP410 - Integration and Interface Strategy - Approve | 0 hrs | 0 days | 2023-12-21 | 2023-12-21 | 543 | 1070FS+92 days | 2023-11-01
5603 | 545 | Future Task |  |  | WP426 | Jarad Hermann |  | WP426 - System Infrastructure Capacity Plan | 148 hrs | 52 days | 2025-10-06 | 2025-12-19
5604 | 546 | Future Task |  |  | WP426 | Jarad Hermann | Create | WPED WP426 - System Infrastructure Capacity Plan - Create | 8 hrs | 10 days | 2025-10-06 | 2025-10-17 | 1 | 547
5605 | 547 | Future Task |  |  | WP426 | Jarad Hermann | Submit | WPED WP426 - System Infrastructure Capacity Plan - Submit | 0 hrs | 0 days | 2025-10-17 | 2025-10-17 | 546 | 548
5606 | 548 | Future Task |  |  | WP426 | Jarad Hermann | Review | WPED WP426 - System Infrastructure Capacity Plan - Review | 16 hrs | 10 days | 2025-10-20 | 2025-10-31 | 547 | 549
5607 | 549 | Future Task |  |  | WP426 | Jarad Hermann | Approve | WPED WP426 - System Infrastructure Capacity Plan - Approve | 0 hrs | 0 days | 2025-10-31 | 2025-10-31 | 548 | 550
5608 | 550 | Future Task |  |  | WP426 | Jarad Hermann |  | Review and refine the excel doc | 20 hrs | 17 days | 2025-11-03 | 2025-11-26 | 549 | 551SS,552SS,553SS,554SS
5609 | 551 | Future Task |  |  | WP426 | Jarad Hermann |  | Review and refine the FL PALM Capacity Plan | 20 hrs | 17 days | 2025-11-03 | 2025-11-26 | 550SS | 555
5610 | 552 | Future Task |  |  | WP426 | Jarad Hermann |  | Define and document current infrastructure demand | 20 hrs | 17 days | 2025-11-03 | 2025-11-26 | 550SS | 555
5611 | 553 | Future Task |  |  | WP426 | Jarad Hermann |  | Define and document current infrastructure capacity | 20 hrs | 17 days | 2025-11-03 | 2025-11-26 | 550SS | 555
5612 | 554 | Future Task |  |  | WP426 | Jarad Hermann |  | Define and document projected infrastructure demand | 20 hrs | 17 days | 2025-11-03 | 2025-11-26 | 550SS | 555
5613 | 555 | Future Task |  |  | WP426 | Jarad Hermann | Submit | WP WP426 - System Infrastructure Capacity Plan - Submit | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 554551552553 | 556
5614 | 556 | Future Task |  |  | WP426 | Jarad Hermann | Review | WP WP426 - System Infrastructure Capacity Plan - Collaborative Review & Update | 12 hrs | 10 days | 2025-12-01 | 2025-12-12 | 555 | 557
5615 | 557 | Future Task |  |  | WP426 | Jarad Hermann | Review | WP WP426 - System Infrastructure Capacity Plan - Final Review & Edits | 12 hrs | 5 days | 2025-12-15 | 2025-12-19 | 556 | 558
5616 | 558 | Future Task |  |  | WP426 | Jarad Hermann | Approve | WP WP426 - System Infrastructure Capacity Plan - Approve | 0 hrs | 0 days | 2025-12-19 | 2025-12-19 | 557
3868 | 559 | Future Task | Yes |  |  |  |  | Environment Builds | 137 hrs | 207 days | 2024-08-05 | 2025-05-30
4203 | 560 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure System Test Environment | 10 hrs | 15 days | 2024-08-05 | 2024-08-23 | 605 | 561
4204 | 561 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate System Test Environment | 8 hrs | 5 days | 2024-08-26 | 2024-08-30 | 560 | 648
4195 | 562 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Interface Test Environment | 10 hrs | 14 days | 2024-09-03 | 2024-09-20 | 1083FS-10 days | 563
4196 | 563 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Interface Test Environment | 8 hrs | 5 days | 2024-09-23 | 2024-09-27 | 562 | 789
4197 | 564 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Mock Conversion Test Environment | 10 hrs | 15 days | 2024-08-05 | 2024-08-23 | 1030 | 565
4198 | 565 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Mock Conversion Test Environment | 8 hrs | 5 days | 2024-08-26 | 2024-08-30 | 564 | 627
4199 | 566 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure UAT Test Environment | 10 hrs | 10 days | 2025-02-03 | 2025-02-14 | 1248FS+46 days | 567
4200 | 567 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate UAT Test Environment | 10 hrs | 10 days | 2025-02-17 | 2025-02-28 | 566 | 568
4201 | 568 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Load Security Roles to ForgeRock for UAT | 4 hrs | 4 days | 2025-03-11 | 2025-03-14 | 5671821 | 569
4202 | 569 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Security Roles in ForgeRock for UAT | 5 hrs | 5 days | 2025-03-17 | 2025-03-21 | 568 | 1250585
4191 | 570 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Dry Run Test Environment | 10 hrs | 14 days | 2025-05-05 | 2025-05-22 |  | 571
4192 | 571 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Dry Run Test Environment | 8 hrs | 5 days | 2025-05-23 | 2025-05-30 | 570 | 829
4193 | 572 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Performance Test Environment | 10 hrs | 15 days | 2025-05-05 | 2025-05-23 | 1186 | 573
4194 | 573 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Performance Test Environment | 8 hrs | 4 days | 2025-05-27 | 2025-05-30 | 572 | 969
4189 | 574 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Configure Disaster Recovery Test Environment | 10 hrs | 15 days | 2025-03-03 | 2025-03-21 | 1172 | 575
4190 | 575 | Future Task |  |  | ENV | Manojkumar Gurjar |  | Validate Disaster Recovery Test Environment | 8 hrs | 5 days | 2025-03-24 | 2025-03-28 | 574 | 987
6809 | 576 | Future Task | [5 empty] | Other | 48 hrs | 187 days | 2024-01-08 | 2024-09-30
7144 | 577 | Future Task |  |  |  | Stacey Terry |  | Support Agency Configuration Workbook | 20 hrs | 103 days | 2024-01-08 | 2024-05-31 | 126FS+6 days | 578
7145 | 578 | Future Task |  |  |  | Stacey Terry |  | Load Agency Configuration Workbook | 20 hrs | 64 days | 2024-06-03 | 2024-08-30 | 577
6808 | 579 | Future Task |  |  |  | Stacey Terry |  | Define User Preferences | 2 hrs | 10 days | 2024-07-31 | 2024-08-13 | 237 | 1815
6810 | 580 | Future Task |  |  |  | Stacey Terry |  | Create Batch Design/Online | 2 hrs | 22 days | 2024-07-01 | 2024-07-31 | 47,66,105,145,164FS+24 days | 581
6807 | 581 | Future Task |  |  |  | Stacey Terry |  | Create Batch Design/Interface | 2 hrs | 22 days | 2024-08-01 | 2024-08-30 | 580 | 582
6811 | 582 | Future Task |  |  |  | Stacey Terry |  | Review and Confirm Batch Design | 2 hrs | 20 days | 2024-09-03 | 2024-09-30 | 581
3771 | 583 | Future Task | [5 empty] | Test | 6,513.58 hrs | 617 days | 2023-07-03 | 2025-12-12
7153 | 584 | Future Task | Yes |  | SG2 | Jimmy Cox | Milestone | Stage Gate 2: Ready to Begin System Testing | 0 hrs | 0 days | 2024-05-08 | 2024-05-08 | 47,66,145,157,393 |  | July/August 2024
7154 | 585 | Future Task | Yes |  | SG3 | Jimmy Cox | Milestone | Stage Gate 3: Ready to Begin UAT | 0 hrs | 0 days | 2025-03-28 | 2025-03-28 | 47,66,145,164,393,429,449,471,491,511,531,1248,747,688,648,569 |  | March 2025 - ESC
4662 | 586 | Future Task |  |  | D643 | Stacey Terry |  | D643 - Updated System Testing Plan | 343 hrs | 361 days | 2023-07-03 | 2024-12-06
4663 | 587 | Future Task |  |  | D643 | Stacey Terry | Create | DED D643 - Updated System Testing Plan - Create | 16 hrs | 10 days | 2023-07-03 | 2023-07-17 | 1FS+47 days | 588
4664 | 588 | Future Task |  |  | D643 | Stacey Terry | Submit | DED D643 - Updated System Testing Plan - Submit | 0 hrs | 0 days | 2023-07-17 | 2023-07-17 | 587 | 589
4665 | 589 | Future Task |  |  | D643 | Stacey Terry | Review | DED D643 - Updated System Testing Plan - Collaborative Review | 24 hrs | 10 days | 2023-07-18 | 2023-07-31 | 588 | 590
4666 | 590 | Future Task |  |  | D643 | Stacey Terry | Approve | DED D643 - Updated System Testing Plan - Approve | 0 hrs | 0 days | 2023-07-31 | 2023-07-31 | 589 | 591FS+80 days
4685 | 591 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test approach for Financials and Payroll | 20 hrs | 15 days | 2023-11-27 | 2023-12-15 | 590FS+80 days | 592
4686 | 592 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test Cycles for Financials and Payroll | 20 hrs | 9 days | 2023-12-18 | 2023-12-29 | 591 | 593FS-4 days
4687 | 593 | Future Task |  |  | D643 | Stacey Terry |  | Identify System Test Resources for Financials and Payroll | 20 hrs | 11 days | 2023-12-26 | 2024-01-10 | 592FS-4 days | 594SS+4 days
4688 | 594 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test Tools and Test Management processes | 20 hrs | 11 days | 2024-01-02 | 2024-01-17 | 593SS+4 days | 595FS-2 days
4689 | 595 | Future Task |  |  | D643 | Stacey Terry |  | Create Initial List of System Test Scenarios for Financials and Payroll | 20 hrs | 24 days | 2024-01-16 | 2024-02-16 | 594FS-2 days | 596FS-5 days
4690 | 596 | Future Task |  |  | D643 | Stacey Terry |  | Define requirements traceability approach for system testing | 20 hrs | 10 days | 2024-02-12 | 2024-02-23 | 595FS-5 days | 597
4667 | 597 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 - Updated System Testing Plan - Draft Submission | 0 hrs | 0 days | 2024-02-23 | 2024-02-23 | 596 | 598
4668 | 598 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-02-26 | 2024-03-01 | 597 | 599
4669 | 599 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Style Guide Review | 1 hr | 1 day | 2024-03-04 | 2024-03-04 | 598 | 600
4670 | 600 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Final Collaborative Review | 20 hrs | 5 days | 2024-03-05 | 2024-03-11 | 599 | 601
4671 | 601 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Accenture QC | 4 hrs | 2 days | 2024-03-12 | 2024-03-13 | 600 | 602
4672 | 602 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 - Updated System Testing Plan - Submit | 0 hrs | 0 days | 2024-03-13 | 2024-03-13 | 601 | 603
4673 | 603 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Department QC | 4 hrs | 1 day | 2024-03-14 | 2024-03-14 | 602 | 604
4674 | 604 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 - Updated System Testing Plan - Contract Manager Review | 8 hrs | 3 days | 2024-03-15 | 2024-03-19 | 603 | 605
4675 | 605 | Future Task |  |  | D643 | Stacey Terry | Accept | DEL D643 - Updated System Testing Plan - Accept | 0 hrs | 0 days | 2024-03-19 | 2024-03-19 | 604 | 606FS+101 days,560 | 2024-03-01
4691 | 606 | Future Task |  |  | D643 | Stacey Terry |  | Update DED D643 to include the system testing plan for DW and BI | 20 hrs | 10 days | 2024-08-12 | 2024-08-23 | 605FS+101 days | 607FS+9 days
4692 | 607 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test approach for DW & BI | 20 hrs | 20 days | 2024-09-09 | 2024-10-04 | 606FS+9 days | 608SS+10 days
4693 | 608 | Future Task |  |  | D643 | Stacey Terry |  | Define System Test Cycles for DW & BI | 20 hrs | 15 days | 2024-09-23 | 2024-10-11 | 607SS+10 days | 609SS+5 days
4694 | 609 | Future Task |  |  | D643 | Stacey Terry |  | Identify System Test Resources for DW & BI | 20 hrs | 10 days | 2024-09-30 | 2024-10-11 | 608SS+5 days | 610
4695 | 610 | Future Task |  |  | D643 | Stacey Terry |  | Create Initial List of DW & BI System Test Scenarios | 4 hrs | 20 days | 2024-10-14 | 2024-11-08 | 609 | 611
4676 | 611 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 2.0 - Updated System Testing Plan - Draft Submission | 0 hrs | 0 days | 2024-11-08 | 2024-11-08 | 610 | 612
4677 | 612 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Pre-Submission Collaborative Review | 5 hrs | 5 days | 2024-11-12 | 2024-11-18 | 611 | 613
4678 | 613 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Style Guide Review | 1 hr | 1 day | 2024-11-19 | 2024-11-19 | 612 | 614
4679 | 614 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Final Collaborative Review | 20 hrs | 5 days | 2024-11-20 | 2024-11-26 | 613 | 615
4680 | 615 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Accenture QC | 4 hrs | 2 days | 2024-11-27 | 2024-12-02 | 614 | 616
4681 | 616 | Future Task |  |  | D643 | Stacey Terry | Submit | DEL D643 2.0 - Updated System Testing Plan - Submit | 0 hrs | 0 days | 2024-12-02 | 2024-12-02 | 615 | 617
4682 | 617 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Department QC | 4 hrs | 1 day | 2024-12-03 | 2024-12-03 | 616 | 618
4683 | 618 | Future Task |  |  | D643 | Stacey Terry | Review | DEL D643 2.0 - Updated System Testing Plan - Contract Manager Review | 8 hrs | 3 days | 2024-12-04 | 2024-12-06 | 617 | 619
4684 | 619 | Future Task |  |  | D643 | Stacey Terry | Accept | DEL D643 2.0 - Updated System Testing Plan - Accept | 0 hrs | 0 days | 2024-12-06 | 2024-12-06 | 618
5004 | 620 | Future Task | Yes |  | D651 | Manojkumar Gurjar |  | D651 - Completion of Mock Conversion I | 197 hrs | 71 days | 2024-07-15 | 2024-10-22
5005 | 621 | Future Task |  |  | D651 | Manojkumar Gurjar | Create | DED D651 - Completion of Mock Conversion I - Create | 16 hrs | 10 days | 2024-07-15 | 2024-07-26 | 1042FS-28 days | 622
5006 | 622 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DED D651 - Completion of Mock Conversion I - Submit | 0 hrs | 0 days | 2024-07-26 | 2024-07-26 | 621 | 623
5007 | 623 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DED D651 - Completion of Mock Conversion I - Collaborative Review | 24 hrs | 10 days | 2024-07-29 | 2024-08-09 | 622 | 624
5008 | 624 | Future Task |  |  | D651 | Manojkumar Gurjar | Approve | DED D651 - Completion of Mock Conversion I - Approve | 0 hrs | 0 days | 2024-08-09 | 2024-08-09 | 623 | 625
5018 | 625 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Confirm Mock 1 Conversion Test Environment Readiness | 20 hrs | 5 days | 2024-08-12 | 2024-08-16 | 624 | 626
5019 | 626 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Create Mock 1 Conversion Checklist | 20 hrs | 10 days | 2024-08-19 | 2024-08-30 | 625 | 627
5020 | 627 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Execute Mock 1 – Conversion | 20 hrs | 9 days | 2024-09-03 | 2024-09-13 | 626565 | 628
5021 | 628 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Validate Mock 1 – Conversion | 20 hrs | 5 days | 2024-09-16 | 2024-09-20 | 627 | 629
5022 | 629 | Future Task |  |  | D651 | Manojkumar Gurjar |  | Conduct Mock 1 - Conversion Test Exit Criteria Review Meeting | 20 hrs | 5 days | 2024-09-23 | 2024-09-27 | 628 | 630
5009 | 630 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DEL D651 - Completion of Mock Conversion I - Draft Submission | 0 hrs | 0 days | 2024-09-27 | 2024-09-27 | 629 | 631
5010 | 631 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-09-30 | 2024-10-04 | 630 | 632
5011 | 632 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Style Guide Review | 1 hr | 1 day | 2024-10-07 | 2024-10-07 | 631 | 633
5012 | 633 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Final Collaborative Review | 20 hrs | 5 days | 2024-10-08 | 2024-10-14 | 632 | 634
5013 | 634 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Accenture QC | 4 hrs | 2 days | 2024-10-15 | 2024-10-16 | 633 | 635
5014 | 635 | Future Task |  |  | D651 | Manojkumar Gurjar | Submit | DEL D651 - Completion of Mock Conversion I - Submit | 0 hrs | 0 days | 2024-10-16 | 2024-10-16 | 634 | 636
5015 | 636 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Department QC | 4 hrs | 1 day | 2024-10-17 | 2024-10-17 | 635 | 637
5016 | 637 | Future Task |  |  | D651 | Manojkumar Gurjar | Review | DEL D651 - Completion of Mock Conversion I - Contract Manager Review | 8 hrs | 3 days | 2024-10-18 | 2024-10-22 | 636 | 638
5017 | 638 | Future Task |  |  | D651 | Manojkumar Gurjar | Accept | DEL D651 - Completion of Mock Conversion I - Accept | 0 hrs | 0 days | 2024-10-22 | 2024-10-22 | 637 | 663FS-3 days | 2024-11-01
4696 | 639 | Future Task | Yes |  | D652 | Stacey Terry |  | D652 - Completion of System Test Segment I | 206 hrs | 123 days | 2024-07-08 | 2025-01-02
4697 | 640 | Future Task |  |  | D652 | Stacey Terry | Create | DED D652 - Completion of System Test Segment I - Create | 16 hrs | 10 days | 2024-07-08 | 2024-07-19 | 1 | 641
4698 | 641 | Future Task |  |  | D652 | Stacey Terry | Submit | DED D652 - Completion of System Test Segment I - Submit | 0 hrs | 0 days | 2024-07-19 | 2024-07-19 | 640 | 642
4699 | 642 | Future Task |  |  | D652 | Stacey Terry | Review | DED D652 - Completion of System Test Segment I - Collaborative Review | 24 hrs | 10 days | 2024-07-22 | 2024-08-02 | 641 | 643
4700 | 643 | Future Task |  |  | D652 | Stacey Terry | Approve | DED D652 - Completion of System Test Segment I - Approve | 0 hrs | 0 days | 2024-08-02 | 2024-08-02 | 642 | 644
4752 | 644 | Future Task |  |  | D652 | Stacey Terry |  | Create Work Unit Tracker for System Test Segment 1 Execution | 20 hrs | 10 days | 2024-08-05 | 2024-08-16 | 643 | 645
4753 | 645 | Future Task |  |  | D652 | Stacey Terry |  | Review, Update and confirm Work Unit Tracker for System Test Segment 1 Execution | 20 hrs | 10 days | 2024-08-19 | 2024-08-30 | 644 | 646SS+5 days
4754 | 646 | Future Task |  |  | D652 | Stacey Terry |  | Confirm System Test Environment Readiness | 20 hrs | 5 days | 2024-08-26 | 2024-08-30 | 645SS+5 days | 647SS
4755 | 647 | Future Task |  |  | D652 | Stacey Terry |  | Conduct System Test Kick Off Meeting | 30 hrs | 5 days | 2024-08-26 | 2024-08-30 | 646SS | 648
4756 | 648 | Future Task |  |  | D652 | Stacey Terry |  | Execute System Test Segment 1 - this is a WU | 10 hrs | 51 days | 2024-09-17 | 2024-11-27 | 6471056561 | 649,650FS-3 days,585
4757 | 649 | Future Task |  |  | D652 | Stacey Terry | Milestone | Milestone: System Test Segment 1 Execution Complete | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 648 | 1713
4758 | 650 | Future Task |  |  | D652 | Stacey Terry |  | Create Completion of System Testing Segment 1 Summary Document | 3 hrs | 8 days | 2024-11-25 | 2024-12-06 | 648FS-3 days | 651SS+3 days,652SS+3 days,653
4759 | 651 | Future Task |  |  | D652 | Stacey Terry |  | Conduct System Test Segment 1 Exit Criteria Review Meeting | 3 hrs | 5 days | 2024-12-02 | 2024-12-06 | 650SS+3 days | 653
4760 | 652 | Future Task |  |  | D652 | Stacey Terry |  | Confirm requirements traceability for System Test Segment 1 | 3 hrs | 5 days | 2024-12-02 | 2024-12-06 | 650SS+3 days | 653
4701 | 653 | Future Task |  |  | D652 | Stacey Terry | Submit | DEL D652 - Completion of System Test Segment I - Draft Submission | 0 hrs | 0 days | 2024-12-06 | 2024-12-06 | 650651652 | 654
4702 | 654 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-12-09 | 2024-12-13 | 653 | 655
4703 | 655 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Style Guide Review | 1 hr | 1 day | 2024-12-16 | 2024-12-16 | 654 | 656
4704 | 656 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Final Collaborative Review | 20 hrs | 5 days | 2024-12-17 | 2024-12-23 | 655 | 657
4705 | 657 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Accenture QC | 4 hrs | 2 days | 2024-12-24 | 2024-12-26 | 656 | 658
4706 | 658 | Future Task |  |  | D652 | Stacey Terry | Submit | DEL D652 - Completion of System Test Segment I - Submit | 0 hrs | 0 days | 2024-12-26 | 2024-12-26 | 657 | 659
4707 | 659 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Department QC | 4 hrs | 1 day | 2024-12-27 | 2024-12-27 | 658 | 660
4708 | 660 | Future Task |  |  | D652 | Stacey Terry | Review | DEL D652 - Completion of System Test Segment I - Contract Manager Review | 8 hrs | 3 days | 2024-12-30 | 2025-01-02 | 659 | 661
4709 | 661 | Future Task |  |  | D652 | Stacey Terry | Accept | DEL D652 - Completion of System Test Segment I - Accept | 0 hrs | 0 days | 2025-01-02 | 2025-01-02 | 660 |  | 2024-12-01
4710 | 662 | Future Task | Yes |  | D655 | Manojkumar Gurjar |  | D655 - Completion of Mock Conversion II (System Test Environment) | 197 hrs | 65 days | 2024-10-18 | 2025-01-24
4711 | 663 | Future Task |  |  | D655 | Manojkumar Gurjar | Create | DED D655 - Completion of Mock Conversion II (System Test Environment) - Create | 16 hrs | 10 days | 2024-10-18 | 2024-10-31 | 638FS-3 days | 664
4712 | 664 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DED D655 - Completion of Mock Conversion II (System Test Environment) - Submit | 0 hrs | 0 days | 2024-10-31 | 2024-10-31 | 663 | 665
4713 | 665 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DED D655 - Completion of Mock Conversion II (System Test Environment) - Collaborative Review | 24 hrs | 10 days | 2024-11-01 | 2024-11-15 | 664 | 666
4714 | 666 | Future Task |  |  | D655 | Manojkumar Gurjar | Approve | DED D655 - Completion of Mock Conversion II (System Test Environment) - Approve | 0 hrs | 0 days | 2024-11-15 | 2024-11-15 | 665 | 667
4761 | 667 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Confirm Mock 2 Conversion - System Test Environment Readiness | 20 hrs | 4 days | 2024-11-18 | 2024-11-21 | 666 | 668
4762 | 668 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Create Mock 2 Conversion Checklist (System Test Environment) | 20 hrs | 5 days | 2024-11-22 | 2024-12-02 | 667 | 669
4763 | 669 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Execute Mock 2 – Conversion (System Test Environment) | 20 hrs | 10 days | 2024-12-03 | 2024-12-16 | 668 | 670
4764 | 670 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Validate Mock 2 – Conversion (System Test Environment) | 20 hrs | 4 days | 2024-12-17 | 2024-12-20 | 669 | 671
4765 | 671 | Future Task |  |  | D655 | Manojkumar Gurjar |  | Conduct Mock 2 - Conversion (System Test Environment) Test Exit Criteria Review Meeting | 20 hrs | 5 days | 2024-12-23 | 2024-12-30 | 670 | 672
4715 | 672 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Draft Submission | 0 hrs | 0 days | 2024-12-30 | 2024-12-30 | 671 | 673
4716 | 673 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2024-12-31 | 2025-01-07 | 672 | 674
4717 | 674 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Style Guide Review | 1 hr | 1 day | 2025-01-08 | 2025-01-08 | 673 | 675
4718 | 675 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Final Collaborative Review | 20 hrs | 5 days | 2025-01-09 | 2025-01-15 | 674 | 676
4719 | 676 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Accenture QC | 4 hrs | 2 days | 2025-01-16 | 2025-01-17 | 675 | 677
4720 | 677 | Future Task |  |  | D655 | Manojkumar Gurjar | Submit | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Submit | 0 hrs | 0 days | 2025-01-17 | 2025-01-17 | 676 | 678
4721 | 678 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Department QC | 4 hrs | 1 day | 2025-01-21 | 2025-01-21 | 677 | 679
4722 | 679 | Future Task |  |  | D655 | Manojkumar Gurjar | Review | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Contract Manager Review | 8 hrs | 3 days | 2025-01-22 | 2025-01-24 | 678 | 680
4723 | 680 | Future Task |  |  | D655 | Manojkumar Gurjar | Accept | DEL D655 - Completion of Mock Conversion II (System Test Environment) - Accept | 0 hrs | 0 days | 2025-01-24 | 2025-01-24 | 679 | 703FS-40 days | 2025-01-01
4724 | 681 | Future Task | Yes |  | D656 | Stacey Terry |  | D656 - Completion of System Test Segment II | 154 hrs | 99 days | 2024-10-07 | 2025-02-28
4725 | 682 | Future Task |  |  | D656 | Stacey Terry | Create | DED D656 - Completion of System Test Segment II - Create | 16 hrs | 10 days | 2024-10-07 | 2024-10-18 | 1 | 683
4726 | 683 | Future Task |  |  | D656 | Stacey Terry | Submit | DED D656 - Completion of System Test Segment II - Submit | 0 hrs | 0 days | 2024-10-18 | 2024-10-18 | 682 | 684
4727 | 684 | Future Task |  |  | D656 | Stacey Terry | Review | DED D656 - Completion of System Test Segment II - Collaborative Review | 20 hrs | 10 days | 2024-10-21 | 2024-11-01 | 683 | 685
4728 | 685 | Future Task |  |  | D656 | Stacey Terry | Approve | DED D656 - Completion of System Test Segment II - Approve | 0 hrs | 0 days | 2024-11-01 | 2024-11-01 | 684 | 686
4766 | 686 | Future Task |  |  | D656 | Stacey Terry |  | Create Work Unit Tracker for System Test Segment 2 Execution | 6 hrs | 9 days | 2024-11-04 | 2024-11-15 | 685 | 687
4767 | 687 | Future Task |  |  | D656 | Stacey Terry |  | Review, Update and confirm Work Unit Tracker for System Test Segment 2 Execution | 20 hrs | 8 days | 2024-11-18 | 2024-11-27 | 686 | 688
4768 | 688 | Future Task |  |  | D656 | Stacey Terry |  | Execute System Test Segment 2 - this is a WU | 20 hrs | 40 days | 2024-12-02 | 2025-01-29 | 687 | 689,690FS-5 days,585
4769 | 689 | Future Task |  |  | D656 | Stacey Terry | Milestone | Milestone: System Test Segment 2 Execution Complete | 0 hrs | 0 days | 2025-01-29 | 2025-01-29 | 688
4770 | 690 | Future Task |  |  | D656 | Stacey Terry |  | Create Completion of System Testing Segment 2 Summary Document | 6 hrs | 10 days | 2025-01-23 | 2025-02-05 | 688FS-5 days | 691SS+5 days,692SS+5 days,693
4771 | 691 | Future Task |  |  | D656 | Stacey Terry |  | Conduct System Test Segment 2 Exit Criteria Review Meeting | 3 hrs | 5 days | 2025-01-30 | 2025-02-05 | 690SS+5 days | 693
4772 | 692 | Future Task |  |  | D656 | Stacey Terry |  | Confirm requirements traceability for System Test Segment 2 | 6 hrs | 5 days | 2025-01-30 | 2025-02-05 | 690SS+5 days | 693
4729 | 693 | Future Task |  |  | D656 | Stacey Terry | Submit | DEL D656 - Completion of System Test Segment II - Draft Submission | 0 hrs | 0 days | 2025-02-05 | 2025-02-05 | 690691692 | 694
4730 | 694 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-02-06 | 2025-02-12 | 693 | 695
4731 | 695 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Style Guide Review | 1 hr | 1 day | 2025-02-13 | 2025-02-13 | 694 | 696
4732 | 696 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Final Collaborative Review | 20 hrs | 5 days | 2025-02-14 | 2025-02-20 | 695 | 697
4733 | 697 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Accenture QC | 4 hrs | 2 days | 2025-02-21 | 2025-02-24 | 696 | 698
4734 | 698 | Future Task |  |  | D656 | Stacey Terry | Submit | DEL D656 - Completion of System Test Segment II - Submit | 0 hrs | 0 days | 2025-02-24 | 2025-02-24 | 697 | 699
4735 | 699 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Department QC | 4 hrs | 1 day | 2025-02-25 | 2025-02-25 | 698 | 700
4736 | 700 | Future Task |  |  | D656 | Stacey Terry | Review | DEL D656 - Completion of System Test Segment II - Contract Manager Review | 8 hrs | 3 days | 2025-02-26 | 2025-02-28 | 699 | 701
4737 | 701 | Future Task |  |  | D656 | Stacey Terry | Accept | DEL D656 - Completion of System Test Segment II - Accept | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 700 |  | 2025-02-01
4738 | 702 | Future Task | Yes |  | D657 | Manojkumar Gurjar |  | D657 - Completion of Mock Conversion III (UAT) | 151 hrs | 77 days | 2024-11-25 | 2025-03-18
4739 | 703 | Future Task |  |  | D657 | Manojkumar Gurjar | Create | DED D657 - Completion of Mock Conversion III (UAT) - Create | 16 hrs | 10 days | 2024-11-25 | 2024-12-10 | 680FS-40 days | 704
4740 | 704 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DED D657 - Completion of Mock Conversion III (UAT) - Submit | 0 hrs | 0 days | 2024-12-10 | 2024-12-10 | 703 | 705
4741 | 705 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DED D657 - Completion of Mock Conversion III (UAT) - Collaborative Review | 24 hrs | 10 days | 2024-12-11 | 2024-12-24 | 704 | 706
4742 | 706 | Future Task |  |  | D657 | Manojkumar Gurjar | Approve | DED D657 - Completion of Mock Conversion III (UAT) - Approve | 0 hrs | 0 days | 2024-12-24 | 2024-12-24 | 705 | 707
4773 | 707 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Confirm Mock 3 Conversion - UAT Environment Readiness | 2 hrs | 5 days | 2024-12-26 | 2025-01-02 | 706 | 708
4774 | 708 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Create Mock 3 Conversion Checklist (UAT) | 2 hrs | 6 days | 2025-01-03 | 2025-01-10 | 707 | 709
4775 | 709 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Execute Mock 3 – Conversion (UAT) | 10 hrs | 21 days | 2025-01-13 | 2025-02-11 | 708 | 710
4776 | 710 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Validate Mock 3 – Conversion (UAT) | 20 hrs | 4 days | 2025-02-12 | 2025-02-17 | 709 | 711
4777 | 711 | Future Task |  |  | D657 | Manojkumar Gurjar |  | Conduct Mock 3 - Conversion UAT Exit Criteria Review Meeting | 20 hrs | 4 days | 2025-02-18 | 2025-02-21 | 710 | 712
4743 | 712 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DEL D657 - Completion of Mock Conversion III (UAT) - Draft Submission | 0 hrs | 0 days | 2025-02-21 | 2025-02-21 | 711 | 713
4744 | 713 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-02-24 | 2025-02-28 | 712 | 714
4745 | 714 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Style Guide Review | 1 hr | 1 day | 2025-03-03 | 2025-03-03 | 713 | 715
4746 | 715 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Final Collaborative Review | 20 hrs | 5 days | 2025-03-04 | 2025-03-10 | 714 | 716
4747 | 716 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Accenture QC | 4 hrs | 2 days | 2025-03-11 | 2025-03-12 | 715 | 717
4748 | 717 | Future Task |  |  | D657 | Manojkumar Gurjar | Submit | DEL D657 - Completion of Mock Conversion III (UAT) - Submit | 0 hrs | 0 days | 2025-03-12 | 2025-03-12 | 716 | 718
4749 | 718 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Department QC | 4 hrs | 1 day | 2025-03-13 | 2025-03-13 | 717 | 719
4750 | 719 | Future Task |  |  | D657 | Manojkumar Gurjar | Review | DEL D657 - Completion of Mock Conversion III (UAT) - Contract Manager Review | 8 hrs | 3 days | 2025-03-14 | 2025-03-18 | 718 | 720
4751 | 720 | Future Task |  |  | D657 | Manojkumar Gurjar | Accept | DEL D657 - Completion of Mock Conversion III (UAT) - Accept | 0 hrs | 0 days | 2025-03-18 | 2025-03-18 | 719 | 762FS-22 days,1252 | 2025-02-01
5023 | 721 | Future Task |  |  | D660 | Stacey Terry |  | D660 - Payroll Parallel Testing Plan | 182 hrs | 72 days | 2025-01-03 | 2025-04-15
5024 | 722 | Future Task |  |  | D660 | Stacey Terry | Create | DED D660 - Payroll Parallel Testing Plan - Create | 16 hrs | 10 days | 2025-01-03 | 2025-01-16 | 195 | 723
5025 | 723 | Future Task |  |  | D660 | Stacey Terry | Submit | DED D660 - Payroll Parallel Testing Plan - Submit | 0 hrs | 0 days | 2025-01-16 | 2025-01-16 | 722 | 724,1099SS-4 days
5026 | 724 | Future Task |  |  | D660 | Stacey Terry | Review | DED D660 - Payroll Parallel Testing Plan - Collaborative Review | 24 hrs | 10 days | 2025-01-17 | 2025-01-31 | 723 | 725
5027 | 725 | Future Task |  |  | D660 | Stacey Terry | Approve | DED D660 - Payroll Parallel Testing Plan - Approve | 0 hrs | 0 days | 2025-01-31 | 2025-01-31 | 724 | 726
5037 | 726 | Future Task |  |  | D660 | Stacey Terry |  | Define Payroll Parallel Test approach | 20 hrs | 20 days | 2025-02-03 | 2025-02-28 | 725 | 727FS-5 days
5038 | 727 | Future Task |  |  | D660 | Stacey Terry |  | Define Payroll Parallel Test Cycles | 15 hrs | 5 days | 2025-02-24 | 2025-02-28 | 726FS-5 days | 728
5039 | 728 | Future Task |  |  | D660 | Stacey Terry |  | Identify Test Resources for Payroll Parallel Test | 20 hrs | 5 days | 2025-03-03 | 2025-03-07 | 727 | 729
5040 | 729 | Future Task |  |  | D660 | Stacey Terry |  | Define Payroll Parallel Test Tools and Test Management processes | 20 hrs | 5 days | 2025-03-10 | 2025-03-14 | 728 | 730FS-5 days
5041 | 730 | Future Task |  |  | D660 | Stacey Terry |  | Create Initial List of Payroll Parallel Test Scenarios | 20 hrs | 10 days | 2025-03-10 | 2025-03-21 | 729FS-5 days | 731
5028 | 731 | Future Task |  |  | D660 | Stacey Terry | Submit | DEL D660 - Payroll Parallel Testing Plan - Draft Submission | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 730 | 732
5029 | 732 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-03-24 | 2025-03-28 | 731 | 733
5030 | 733 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Style Guide Review | 1 hr | 1 day | 2025-03-31 | 2025-03-31 | 732 | 734
5031 | 734 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Final Collaborative Review | 10 hrs | 5 days | 2025-04-01 | 2025-04-07 | 733 | 735
5032 | 735 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Accenture QC | 4 hrs | 2 days | 2025-04-08 | 2025-04-09 | 734 | 736
5033 | 736 | Future Task |  |  | D660 | Stacey Terry | Submit | DEL D660 - Payroll Parallel Testing Plan - Submit | 0 hrs | 0 days | 2025-04-09 | 2025-04-09 | 735 | 737
5034 | 737 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Department QC | 4 hrs | 1 day | 2025-04-10 | 2025-04-10 | 736 | 738
5035 | 738 | Future Task |  |  | D660 | Stacey Terry | Review | DEL D660 - Payroll Parallel Testing Plan - Contract Manager Review | 8 hrs | 3 days | 2025-04-11 | 2025-04-15 | 737 | 739
5036 | 739 | Future Task |  |  | D660 | Stacey Terry | Accept | DEL D660 - Payroll Parallel Testing Plan - Accept | 0 hrs | 0 days | 2025-04-15 | 2025-04-15 | 738 | 862FS-37 days | 2025-04-01
4778 | 740 | Future Task | Yes |  | D661 | Stacey Terry |  | D661 - Completion of System Test DW/BI | 207 hrs | 120 days | 2024-11-04 | 2025-04-28
4779 | 741 | Future Task |  |  | D661 | Stacey Terry | Create | DED D661 - Completion of System Test DW/BI - Create | 16 hrs | 10 days | 2024-11-04 | 2024-11-18 | 1 | 742
4780 | 742 | Future Task |  |  | D661 | Stacey Terry | Submit | DED D661 - Completion of System Test DW/BI - Submit | 0 hrs | 0 days | 2024-11-18 | 2024-11-18 | 741 | 743
4781 | 743 | Future Task |  |  | D661 | Stacey Terry | Review | DED D661 - Completion of System Test DW/BI - Collaborative Review | 24 hrs | 10 days | 2024-11-19 | 2024-12-04 | 742 | 744
4782 | 744 | Future Task |  |  | D661 | Stacey Terry | Approve | DED D661 - Completion of System Test DW/BI - Approve | 0 hrs | 0 days | 2024-12-04 | 2024-12-04 | 743 | 745
4820 | 745 | Future Task |  |  | D661 | Stacey Terry |  | Create Work Unit Tracker for System Test DW/BI Execution | 36 hrs | 9 days | 2024-12-05 | 2024-12-17 | 744 | 746
4821 | 746 | Future Task |  |  | D661 | Stacey Terry |  | Review, Update and confirm Work Unit Tracker for System Test DW/BI Execution | 20 hrs | 10 days | 2024-12-18 | 2025-01-02 | 745 | 747
4822 | 747 | Future Task |  |  | D661 | Stacey Terry |  | Execute System Test DW/BI - This is a WU | 20 hrs | 60 days | 2025-01-03 | 2025-03-28 | 746 | 748,749FS-6 days,585
4823 | 748 | Future Task |  |  | D661 | Stacey Terry | Milestone | Milestone: System Test DW/BI Execution Complete | 0 hrs | 0 days | 2025-03-28 | 2025-03-28 | 747
4824 | 749 | Future Task |  |  | D661 | Stacey Terry |  | Create Completion of System Testing DW/BI Summary Document | 4 hrs | 10 days | 2025-03-21 | 2025-04-03 | 747FS-6 days | 750SS+5 days,752
4825 | 750 | Future Task |  |  | D661 | Stacey Terry |  | Conduct System Test DW/BI Exit Criteria Review Meeting | 10 hrs | 5 days | 2025-03-28 | 2025-04-03 | 749SS+5 days | 751SS,752
4826 | 751 | Future Task |  |  | D661 | Stacey Terry |  | Confirm requirements traceability for System Test DW/BI | 20 hrs | 5 days | 2025-03-28 | 2025-04-03 | 750SS | 752
4783 | 752 | Future Task |  |  | D661 | Stacey Terry | Submit | DEL D661 - Completion of System Test DW/BI - Draft Submission | 0 hrs | 0 days | 2025-04-03 | 2025-04-03 | 749750751 | 753
4784 | 753 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-04-04 | 2025-04-10 | 752 | 754
4785 | 754 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Style Guide Review | 1 hr | 1 day | 2025-04-11 | 2025-04-11 | 753 | 755
4786 | 755 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Final Collaborative Review | 20 hrs | 5 days | 2025-04-14 | 2025-04-18 | 754 | 756
4787 | 756 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Accenture QC | 4 hrs | 2 days | 2025-04-21 | 2025-04-22 | 755 | 757
4788 | 757 | Future Task |  |  | D661 | Stacey Terry | Submit | DEL D661 - Completion of System Test DW/BI - Submit | 0 hrs | 0 days | 2025-04-22 | 2025-04-22 | 756 | 758
4789 | 758 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Department QC | 4 hrs | 1 day | 2025-04-23 | 2025-04-23 | 757 | 759
4790 | 759 | Future Task |  |  | D661 | Stacey Terry | Review | DEL D661 - Completion of System Test DW/BI - Contract Manager Review | 8 hrs | 3 days | 2025-04-24 | 2025-04-28 | 758 | 760
4791 | 760 | Future Task |  |  | D661 | Stacey Terry | Accept | DEL D661 - Completion of System Test DW/BI - Accept | 0 hrs | 0 days | 2025-04-28 | 2025-04-28 | 759 |  | 2025-05-01
4792 | 761 | Future Task | Yes |  | D662 | Manojkumar Gurjar |  | D662 - Completion of Dress Rehearsal (Mock Conversion IV) | 197 hrs | 72 days | 2025-02-17 | 2025-05-28
4793 | 762 | Future Task |  |  | D662 | Manojkumar Gurjar | Create | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Create | 16 hrs | 10 days | 2025-02-17 | 2025-02-28 | 720FS-22 days | 763
4794 | 763 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Submit | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 762 | 764
4795 | 764 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Collaborative Review | 24 hrs | 10 days | 2025-03-03 | 2025-03-14 | 763 | 765
4796 | 765 | Future Task |  |  | D662 | Manojkumar Gurjar | Approve | DED D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Approve | 0 hrs | 0 days | 2025-03-14 | 2025-03-14 | 764 | 766
4827 | 766 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Confirm Mock 4 Conversion - (Dress Rehearsal) Environment Readiness | 20 hrs | 5 days | 2025-03-17 | 2025-03-21 | 765 | 767
4828 | 767 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Create Mock 4 Conversion Checklist (Dress Rehearsal) | 20 hrs | 5 days | 2025-03-24 | 2025-03-28 | 766 | 768
4829 | 768 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Execute Mock 4 – Conversion (Dress Rehearsal) | 20 hrs | 10 days | 2025-03-31 | 2025-04-11 | 767 | 769
4830 | 769 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Validate Mock 4 – Conversion (Dress Rehearsal) | 20 hrs | 10 days | 2025-04-14 | 2025-04-25 | 768 | 770
4831 | 770 | Future Task |  |  | D662 | Manojkumar Gurjar |  | Conduct Mock 4 - Conversion (Dress Rehearsal) Exit Criteria Review Meeting | 20 hrs | 5 days | 2025-04-28 | 2025-05-02 | 769 | 771
4797 | 771 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Draft Submission | 0 hrs | 0 days | 2025-05-02 | 2025-05-02 | 770 | 772
4798 | 772 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-05-05 | 2025-05-09 | 771 | 773
4799 | 773 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Style Guide Review | 1 hr | 1 day | 2025-05-12 | 2025-05-12 | 772 | 774
4800 | 774 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Final Collaborative Review | 20 hrs | 5 days | 2025-05-13 | 2025-05-19 | 773 | 775
4801 | 775 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Accenture QC | 4 hrs | 2 days | 2025-05-20 | 2025-05-21 | 774 | 776
4802 | 776 | Future Task |  |  | D662 | Manojkumar Gurjar | Submit | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Submit | 0 hrs | 0 days | 2025-05-21 | 2025-05-21 | 775 | 777
4803 | 777 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Department QC | 4 hrs | 1 day | 2025-05-22 | 2025-05-22 | 776 | 778
4804 | 778 | Future Task |  |  | D662 | Manojkumar Gurjar | Review | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Contract Manager Review | 8 hrs | 3 days | 2025-05-23 | 2025-05-28 | 777 | 779
4805 | 779 | Future Task |  |  | D662 | Manojkumar Gurjar | Accept | DEL D662 - Completion of Dress Rehearsal (Mock Conversion IV) - Accept | 0 hrs | 0 days | 2025-05-28 | 2025-05-28 | 778 | 1252 | 2025-05-01
4806 | 780 | Future Task | Yes |  | D663 | Manojkumar Gurjar |  | D663 - Completion of Interface Testing Segment I | 236.58 hrs | 204 days | 2024-09-09 | 2025-06-30
4807 | 781 | Future Task |  |  | D663 | Manojkumar Gurjar | Create | DED D663 - Completion of Interface Testing Segment I - Create | 24 hrs | 10 days | 2024-09-09 | 2024-09-20 | 1 | 782
4808 | 782 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DED D663 - Completion of Interface Testing Segment I - Submit | 0 hrs | 0 days | 2024-09-20 | 2024-09-20 | 781 | 783
4809 | 783 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DED D663 - Completion of Interface Testing Segment I - Collaborative Review | 28 hrs | 10 days | 2024-09-23 | 2024-10-04 | 782 | 784
4810 | 784 | Future Task |  |  | D663 | Manojkumar Gurjar | Approve | DED D663 - Completion of Interface Testing Segment I - Approve | 0 hrs | 0 days | 2024-10-04 | 2024-10-04 | 783 | 785
4832 | 785 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Create Interface Testing Segment 1 Execution Work Unit Tracker | 30 hrs | 10 days | 2024-10-07 | 2024-10-18 | 784 | 786,790SS
4833 | 786 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Review/Confirm Interface Testing Segment 1 Execution Work Unit Tracker | 15 hrs | 5 days | 2024-10-21 | 2024-10-25 | 785 | 787
4834 | 787 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Conduct Interface Testing Segment 1 Readiness Review Meeting | 15 hrs | 5 days | 2024-10-28 | 2024-11-01 | 786 | 788
4835 | 788 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Conduct Interface Test Kickoff Meeting with Integration Partners | 3 hrs | 9 days | 2024-11-04 | 2024-11-15 | 787 | 789
4836 | 789 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Confirm Interface Test Environment Readiness | 15 hrs | 5 days | 2024-11-18 | 2024-11-22 | 788563 | 791
4837 | 790 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Establish Interface Connectivity Segment 1 | 20 hrs | 20 days | 2024-10-07 | 2024-11-01 | 785SS | 791FS+17 days
4838 | 791 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Execute Interface Testing Segment 1 - This is WU | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 790FS+17 days,789 | 792793
4839 | 792 | Future Task |  |  | D663 | Manojkumar Gurjar | Milestone | Milestone: Interface Testing Segment 1 Complete | 0 hrs | 0 days | 2025-04-30 | 2025-04-30 | 791 | 795
4840 | 793 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Conduct Test Exit Criteria Review Meeting | 15 hrs | 5 days | 2025-05-01 | 2025-05-07 | 791 | 794
4841 | 794 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Confirm requirements traceability for Interface Testing Segment 1 | 15 hrs | 10 days | 2025-05-08 | 2025-05-21 | 793 | 795
4842 | 795 | Future Task |  |  | D663 | Manojkumar Gurjar |  | Create Completion of Interface Testing Segment 1 Summary Document | 1.58 hrs | 10 days | 2025-05-22 | 2025-06-05 | 794792 | 796
4811 | 796 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DEL D663 - Completion of Interface Testing Segment I - Draft Submission | 0 hrs | 0 days | 2025-06-05 | 2025-06-05 | 795 | 797
4812 | 797 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Pre-Submission Collaborative Review | 6 hrs | 5 days | 2025-06-06 | 2025-06-12 | 796 | 798
4813 | 798 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Style Guide Review | 1 hr | 1 day | 2025-06-13 | 2025-06-13 | 797 | 799
4814 | 799 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Final Collaborative Review | 12 hrs | 5 days | 2025-06-16 | 2025-06-20 | 798 | 800
4815 | 800 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Accenture QC | 4 hrs | 2 days | 2025-06-23 | 2025-06-24 | 799 | 801
4816 | 801 | Future Task |  |  | D663 | Manojkumar Gurjar | Submit | DEL D663 - Completion of Interface Testing Segment I - Submit | 0 hrs | 0 days | 2025-06-24 | 2025-06-24 | 800 | 802
4817 | 802 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Department QC | 4 hrs | 1 day | 2025-06-25 | 2025-06-25 | 801 | 803
4818 | 803 | Future Task |  |  | D663 | Manojkumar Gurjar | Review | DEL D663 - Completion of Interface Testing Segment I - Contract Manager Review | 8 hrs | 3 days | 2025-06-26 | 2025-06-30 | 802 | 804
4819 | 804 | Future Task |  |  | D663 | Manojkumar Gurjar | Accept | DEL D663 - Completion of Interface Testing Segment I - Accept | 0 hrs | 0 days | 2025-06-30 | 2025-06-30 | 803 |  | 2025-06-01
5042 | 805 | Future Task | Yes |  | D666 | Stacey Terry |  | D666 - Support of UAT Segment I | 111 hrs | 95 days | 2025-02-17 | 2025-06-30
5043 | 806 | Future Task |  |  | D666 | Stacey Terry | Create | DED D666 - Support of UAT Segment I - Create | 16 hrs | 10 days | 2025-02-17 | 2025-02-28 | 1 | 807
5044 | 807 | Future Task |  |  | D666 | Stacey Terry | Submit | DED D666 - Support of UAT Segment I - Submit | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 806 | 808
5045 | 808 | Future Task |  |  | D666 | Stacey Terry | Review | DED D666 - Support of UAT Segment I - Collaborative Review | 24 hrs | 10 days | 2025-03-03 | 2025-03-14 | 807 | 809
5046 | 809 | Future Task |  |  | D666 | Stacey Terry | Approve | DED D666 - Support of UAT Segment I - Approve | 0 hrs | 0 days | 2025-03-14 | 2025-03-14 | 808 | 810
5056 | 810 | Future Task |  |  | D666 | Stacey Terry |  | Identify UAT support resources for UAT Segment 1 | 20 hrs | 11 days | 2025-03-17 | 2025-03-31 | 809 | 811
5057 | 811 | Future Task |  |  | D666 | Stacey Terry |  | Participate in UAT sessions for UAT Segment 1 | 6 hrs | 43 days | 2025-04-01 | 2025-05-30 | 810 | 812SS
5058 | 812 | Future Task |  |  | D666 | Stacey Terry |  | Support resolution of UAT issues for UAT Segment 1 | 7 hrs | 42 days | 2025-04-01 | 2025-05-29 | 811SS | 813FS-4 days
5059 | 813 | Future Task |  |  | D666 | Stacey Terry |  | Confirm requirements traceability for UAT Segment 1 | 3 hrs | 4 days | 2025-05-23 | 2025-05-29 | 812FS-4 days | 814SS
5060 | 814 | Future Task |  |  | D666 | Stacey Terry |  | Create UAT Segment 1 Summary Document | 3 hrs | 9 days | 2025-05-23 | 2025-06-05 | 813SS | 815
5047 | 815 | Future Task |  |  | D666 | Stacey Terry | Submit | DEL D666 - Support of UAT Segment I - Draft Submission | 0 hrs | 0 days | 2025-06-05 | 2025-06-05 | 814 | 816
5048 | 816 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Pre-Submission Collaborative Review | 5 hrs | 5 days | 2025-06-06 | 2025-06-12 | 815 | 817
5049 | 817 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Style Guide Review | 1 hr | 1 day | 2025-06-13 | 2025-06-13 | 816 | 818
5050 | 818 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Final Collaborative Review | 10 hrs | 5 days | 2025-06-16 | 2025-06-20 | 817 | 819
5051 | 819 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Accenture QC | 4 hrs | 2 days | 2025-06-23 | 2025-06-24 | 818 | 820
5052 | 820 | Future Task |  |  | D666 | Stacey Terry | Submit | DEL D666 - Support of UAT Segment I - Submit | 0 hrs | 0 days | 2025-06-24 | 2025-06-24 | 819 | 821
5053 | 821 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Department QC | 4 hrs | 1 day | 2025-06-25 | 2025-06-25 | 820 | 822
5054 | 822 | Future Task |  |  | D666 | Stacey Terry | Review | DEL D666 - Support of UAT Segment I - Contract Manager Review | 8 hrs | 3 days | 2025-06-26 | 2025-06-30 | 821 | 823
5055 | 823 | Future Task |  |  | D666 | Stacey Terry | Accept | DEL D666 - Support of UAT Segment I - Accept | 0 hrs | 0 days | 2025-06-30 | 2025-06-30 | 822 |  | 2025-06-01
5520 | 824 | Future Task | Yes |  | D667 | Stacey Terry |  | D667 - Completion of Mock Go-Lives (Dry Run #1) | 108 hrs | 62 days | 2025-05-02 | 2025-07-30
5521 | 825 | Future Task |  |  | D667 | Stacey Terry | Create | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Create | 6 hrs | 10 days | 2025-05-02 | 2025-05-15 | 1 | 826
5522 | 826 | Future Task |  |  | D667 | Stacey Terry | Submit | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Submit | 0 hrs | 0 days | 2025-05-15 | 2025-05-15 | 825 | 827
5523 | 827 | Future Task |  |  | D667 | Stacey Terry | Review | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Collaborative Review | 8 hrs | 10 days | 2025-05-16 | 2025-05-30 | 826 | 828
5524 | 828 | Future Task |  |  | D667 | Stacey Terry | Approve | DED D667 - Completion of Mock Go-Lives (Dry Run #1) - Approve | 0 hrs | 0 days | 2025-05-30 | 2025-05-30 | 827 | 829
6697 | 829 | Future Task |  |  | D667 | Stacey Terry |  | Confirm Mock Go-Live Dry Run #1 Execution Readiness | 3 hrs | 5 days | 2025-06-02 | 2025-06-06 | 828571 | 830
6698 | 830 | Future Task |  |  | D667 | Stacey Terry |  | Execute Mock Go-Live Dry Run #1 | 6 hrs | 10 days | 2025-06-09 | 2025-06-20 | 829 | 831
6699 | 831 | Future Task |  |  | D667 | Stacey Terry |  | Document Mock Go-Live Dry Run Results #1 | 6 hrs | 5 days | 2025-06-23 | 2025-06-27 | 830 | 832
6700 | 832 | Future Task |  |  | D667 | Stacey Terry |  | Create Mock Go-Live Dry Run #1 Summary Document | 6 hrs | 5 days | 2025-06-30 | 2025-07-07 | 831 | 833
5525 | 833 | Future Task |  |  | D667 | Stacey Terry | Submit | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Draft Submission | 0 hrs | 0 days | 2025-07-07 | 2025-07-07 | 832 | 834
5526 | 834 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Pre-Submission Collaborative Review | 28 hrs | 5 days | 2025-07-08 | 2025-07-14 | 833 | 835
5527 | 835 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Style Guide Review | 1 hr | 1 day | 2025-07-15 | 2025-07-15 | 834 | 836
5528 | 836 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Final Collaborative Review | 28 hrs | 5 days | 2025-07-16 | 2025-07-22 | 835 | 837
5529 | 837 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Accenture QC | 4 hrs | 2 days | 2025-07-23 | 2025-07-24 | 836 | 838
5530 | 838 | Future Task |  |  | D667 | Stacey Terry | Submit | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Submit | 0 hrs | 0 days | 2025-07-24 | 2025-07-24 | 837 | 839
5531 | 839 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Department QC | 4 hrs | 1 day | 2025-07-25 | 2025-07-25 | 838 | 840
5532 | 840 | Future Task |  |  | D667 | Stacey Terry | Review | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Contract Manager Review | 8 hrs | 3 days | 2025-07-28 | 2025-07-30 | 839 | 841
5533 | 841 | Future Task |  |  | D667 | Stacey Terry | Accept | DEL D667 - Completion of Mock Go-Lives (Dry Run #1) - Accept | 0 hrs | 0 days | 2025-07-30 | 2025-07-30 | 840 | 1252 | 2025-07-01
5061 | 842 | Future Task | Yes |  | D669 | Stacey Terry |  | D669 - Support of UAT Segment II | 132 hrs | 72 days | 2025-05-19 | 2025-08-28
5062 | 843 | Future Task |  |  | D669 | Stacey Terry | Create | DED D669 - Support of UAT Segment II - Create | 2 hrs | 10 days | 2025-05-19 | 2025-06-02 | 1 | 844
5063 | 844 | Future Task |  |  | D669 | Stacey Terry | Submit | DED D669 - Support of UAT Segment II - Submit | 0 hrs | 0 days | 2025-06-02 | 2025-06-02 | 843 | 845
5064 | 845 | Future Task |  |  | D669 | Stacey Terry | Review | DED D669 - Support of UAT Segment II - Collaborative Review | 12 hrs | 10 days | 2025-06-03 | 2025-06-16 | 844 | 846
5065 | 846 | Future Task |  |  | D669 | Stacey Terry | Approve | DED D669 - Support of UAT Segment II - Approve | 0 hrs | 0 days | 2025-06-16 | 2025-06-16 | 845 | 847FS+4 days
5075 | 847 | Future Task |  |  | D669 | Stacey Terry |  | Identify UAT support resources for UAT Segment 2 | 6 hrs | 5 days | 2025-06-23 | 2025-06-27 | 846FS+4 days | 848
5076 | 848 | Future Task |  |  | D669 | Stacey Terry |  | Participate in UAT sessions for UAT Segment 2 | 6 hrs | 23 days | 2025-06-30 | 2025-07-31 | 847 | 849SS
5077 | 849 | Future Task |  |  | D669 | Stacey Terry |  | Support resolution of UAT issues for UAT Segment 2 | 7 hrs | 23 days | 2025-06-30 | 2025-07-31 | 848SS | 850FS-4 days
5078 | 850 | Future Task |  |  | D669 | Stacey Terry |  | Confirm requirements traceability for UAT Segment 2 | 21 hrs | 7 days | 2025-07-28 | 2025-08-05 | 849FS-4 days | 851SS
5079 | 851 | Future Task |  |  | D669 | Stacey Terry |  | Create UAT Segment 2 Summary Document | 21 hrs | 7 days | 2025-07-28 | 2025-08-05 | 850SS | 852
5066 | 852 | Future Task |  |  | D669 | Stacey Terry | Submit | DEL D669 - Support of UAT Segment II - Draft Submission | 0 hrs | 0 days | 2025-08-05 | 2025-08-05 | 851 | 853
5067 | 853 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-08-06 | 2025-08-12 | 852 | 854
5068 | 854 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Style Guide Review | 1 hr | 1 day | 2025-08-13 | 2025-08-13 | 853 | 855
5069 | 855 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Final Collaborative Review | 20 hrs | 5 days | 2025-08-14 | 2025-08-20 | 854 | 856
5070 | 856 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Accenture QC | 4 hrs | 2 days | 2025-08-21 | 2025-08-22 | 855 | 857
5071 | 857 | Future Task |  |  | D669 | Stacey Terry | Submit | DEL D669 - Support of UAT Segment II - Submit | 0 hrs | 0 days | 2025-08-22 | 2025-08-22 | 856 | 858
5072 | 858 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Department QC | 4 hrs | 1 day | 2025-08-25 | 2025-08-25 | 857 | 859
5073 | 859 | Future Task |  |  | D669 | Stacey Terry | Review | DEL D669 - Support of UAT Segment II - Contract Manager Review | 8 hrs | 3 days | 2025-08-26 | 2025-08-28 | 858 | 860
5074 | 860 | Future Task |  |  | D669 | Stacey Terry | Accept | DEL D669 - Support of UAT Segment II - Accept | 0 hrs | 0 days | 2025-08-28 | 2025-08-28 | 859 |  | 2025-08-01
4843 | 861 | Future Task | Yes |  | D670 | Stacey Terry |  | D670 - Completion of Payroll Parallel Testing | 254 hrs | 133 days | 2025-02-24 | 2025-08-29
4844 | 862 | Future Task |  |  | D670 | Stacey Terry | Create | DED D670 - Completion of Payroll Parallel Testing - Create | 16 hrs | 10 days | 2025-02-24 | 2025-03-07 | 739FS-37 days | 863
4845 | 863 | Future Task |  |  | D670 | Stacey Terry | Submit | DED D670 - Completion of Payroll Parallel Testing - Submit | 0 hrs | 0 days | 2025-03-07 | 2025-03-07 | 862 | 864
4846 | 864 | Future Task |  |  | D670 | Stacey Terry | Review | DED D670 - Completion of Payroll Parallel Testing - Collaborative Review | 24 hrs | 10 days | 2025-03-10 | 2025-03-21 | 863 | 865
4847 | 865 | Future Task |  |  | D670 | Stacey Terry | Approve | DED D670 - Completion of Payroll Parallel Testing - Approve | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 864 | 866
4955 | 866 | Future Task |  |  | D670 | Stacey Terry |  | Create Work Unit Tracker for Payroll Parallel Test Execution | 40 hrs | 10 days | 2025-03-24 | 2025-04-04 | 865 | 867
4956 | 867 | Future Task |  |  | D670 | Stacey Terry |  | Review, Update and confirm Work Unit Tracker for Payroll Parallel Test Execution | 20 hrs | 10 days | 2025-04-07 | 2025-04-18 | 866 | 868
4957 | 868 | Future Task |  |  | D670 | Stacey Terry |  | Confirm Payroll Parallel Test Environment Readiness | 20 hrs | 5 days | 2025-04-21 | 2025-04-25 | 867 | 869
4958 | 869 | Future Task |  |  | D670 | Stacey Terry |  | Conduct Parallel Payroll Test Kick Off Meeting | 12 hrs | 5 days | 2025-04-28 | 2025-05-02 | 868 | 870
4959 | 870 | Future Task |  |  | D670 | Stacey Terry |  | Execute Parallel Payroll Testing - this is a WU | 5 hrs | 60 days | 2025-05-05 | 2025-07-29 | 869 | 871,872FS-4 days
4960 | 871 | Future Task |  |  | D670 | Stacey Terry | Milestone | Milestone: Payroll Parallel Test Execution Complete | 0 hrs | 0 days | 2025-07-29 | 2025-07-29 | 870 | 875
4961 | 872 | Future Task |  |  | D670 | Stacey Terry |  | Conduct Payroll Parallel Test Exit Criteria Review Meeting | 10 hrs | 10 days | 2025-07-24 | 2025-08-06 | 870FS-4 days | 873SS,874SS,875
4962 | 873 | Future Task |  |  | D670 | Stacey Terry |  | Confirm requirements traceability for Payroll Parallel test | 20 hrs | 10 days | 2025-07-24 | 2025-08-06 | 872SS | 875
4963 | 874 | Future Task |  |  | D670 | Stacey Terry |  | Create Completion of Payroll Parallel Test Summary Document | 30 hrs | 10 days | 2025-07-24 | 2025-08-06 | 872SS | 875
4848 | 875 | Future Task |  |  | D670 | Stacey Terry | Submit | DEL D670 - Completion of Payroll Parallel Testing - Draft Submission | 0 hrs | 0 days | 2025-08-06 | 2025-08-06 | 871872874873 | 876
4849 | 876 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-08-07 | 2025-08-13 | 875 | 877
4850 | 877 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Style Guide Review | 1 hr | 1 day | 2025-08-14 | 2025-08-14 | 876 | 878
4851 | 878 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Final Collaborative Review | 20 hrs | 5 days | 2025-08-15 | 2025-08-21 | 877 | 879
4852 | 879 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Accenture QC | 4 hrs | 2 days | 2025-08-22 | 2025-08-25 | 878 | 880
4853 | 880 | Future Task |  |  | D670 | Stacey Terry | Submit | DEL D670 - Completion of Payroll Parallel Testing - Submit | 0 hrs | 0 days | 2025-08-25 | 2025-08-25 | 879 | 881
4854 | 881 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Department QC | 4 hrs | 1 day | 2025-08-26 | 2025-08-26 | 880 | 882
4855 | 882 | Future Task |  |  | D670 | Stacey Terry | Review | DEL D670 - Completion of Payroll Parallel Testing - Contract Manager Review | 8 hrs | 3 days | 2025-08-27 | 2025-08-29 | 881 | 883
4856 | 883 | Future Task |  |  | D670 | Stacey Terry | Accept | DEL D670 - Completion of Payroll Parallel Testing - Accept | 0 hrs | 0 days | 2025-08-29 | 2025-08-29 | 882 |  | 2025-08-01
4857 | 884 | Future Task | Yes |  | D671 | Manojkumar Gurjar |  | D671 - Completion of Interface Testing Segment II | 291 hrs | 160 days | 2025-03-03 | 2025-10-15
4858 | 885 | Future Task |  |  | D671 | Manojkumar Gurjar | Create | DED D671 - Completion of Interface Testing Segment II - Create | 6 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1 | 886
4859 | 886 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DED D671 - Completion of Interface Testing Segment II - Submit | 0 hrs | 0 days | 2025-03-14 | 2025-03-14 | 885 | 887
4860 | 887 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DED D671 - Completion of Interface Testing Segment II - Collaborative Review | 8 hrs | 10 days | 2025-03-17 | 2025-03-28 | 886 | 888
4861 | 888 | Future Task |  |  | D671 | Manojkumar Gurjar | Approve | DED D671 - Completion of Interface Testing Segment II - Approve | 0 hrs | 0 days | 2025-03-28 | 2025-03-28 | 887 | 889
4964 | 889 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Create Interface Testing Segment 2 Execution Work Unit Tracker | 6 hrs | 4 days | 2025-03-31 | 2025-04-03 | 888 | 890
4965 | 890 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Review/Confirm Interface Testing Segment 2 Execution Work Unit Tracker | 6 hrs | 4 days | 2025-04-04 | 2025-04-09 | 889 | 891
4966 | 891 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Conduct Interface Testing Segment 2 Readiness Review Meeting | 15 hrs | 5 days | 2025-04-10 | 2025-04-16 | 890 | 892
4967 | 892 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Conduct Interface Test Kickoff Meeting with Integration Partners | 30 hrs | 5 days | 2025-04-17 | 2025-04-23 | 891 | 893
4968 | 893 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Confirm Interface Test Environment Readiness | 15 hrs | 5 days | 2025-04-24 | 2025-04-30 | 892 | 894
4969 | 894 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Establish Interface Connectivity Segment 2 | 20 hrs | 7 days | 2025-05-01 | 2025-05-09 | 893 | 895
4970 | 895 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Execute Interface Testing Segment 2 - This is WU | 10 hrs | 78 days | 2025-05-12 | 2025-08-29 | 894 | 896
4971 | 896 | Future Task |  |  | D671 | Manojkumar Gurjar | Milestone | Milestone: Interface Testing Segment 2 Complete | 0 hrs | 0 days | 2025-08-29 | 2025-08-29 | 895 | 897
4972 | 897 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Conduct Test Exit Criteria Review Meeting | 30 hrs | 5 days | 2025-09-02 | 2025-09-08 | 896 | 898
4973 | 898 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Confirm requirements traceability for Interface Testing Segment 2 | 40 hrs | 5 days | 2025-09-09 | 2025-09-15 | 897 | 899
4974 | 899 | Future Task |  |  | D671 | Manojkumar Gurjar |  | Create Completion of Interface Testing Segment 2 deliverable (D671) | 40 hrs | 5 days | 2025-09-16 | 2025-09-22 | 898 | 900
4862 | 900 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DEL D671 - Completion of Interface Testing Segment II - Draft Submission | 0 hrs | 0 days | 2025-09-22 | 2025-09-22 | 899 | 901
4863 | 901 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Pre-Submission Collaborative Review | 24 hrs | 5 days | 2025-09-23 | 2025-09-29 | 900 | 902
4864 | 902 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Style Guide Review | 1 hr | 1 day | 2025-09-30 | 2025-09-30 | 901 | 903
4865 | 903 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Final Collaborative Review | 24 hrs | 5 days | 2025-10-01 | 2025-10-07 | 902 | 904
4866 | 904 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Accenture QC | 4 hrs | 2 days | 2025-10-08 | 2025-10-09 | 903 | 905
4867 | 905 | Future Task |  |  | D671 | Manojkumar Gurjar | Submit | DEL D671 - Completion of Interface Testing Segment II - Submit | 0 hrs | 0 days | 2025-10-09 | 2025-10-09 | 904 | 906
4868 | 906 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Department QC | 4 hrs | 1 day | 2025-10-10 | 2025-10-10 | 905 | 907
4869 | 907 | Future Task |  |  | D671 | Manojkumar Gurjar | Review | DEL D671 - Completion of Interface Testing Segment II - Contract Manager Review | 8 hrs | 3 days | 2025-10-13 | 2025-10-15 | 906 | 908
4870 | 908 | Future Task |  |  | D671 | Manojkumar Gurjar | Accept | DEL D671 - Completion of Interface Testing Segment II - Accept | 0 hrs | 0 days | 2025-10-15 | 2025-10-15 | 907 |  | 2025-10-01
4871 | 909 | Future Task | Yes |  | D672 | Stacey Terry |  | D672 - Support of UAT Segment III | 122 hrs | 67 days | 2025-08-22 | 2025-11-26
4872 | 910 | Future Task |  |  | D672 | Stacey Terry | Create | DED D672 - Support of UAT Segment III - Create | 16 hrs | 10 days | 2025-08-22 | 2025-09-05 | 1 | 911
4873 | 911 | Future Task |  |  | D672 | Stacey Terry | Submit | DED D672 - Support of UAT Segment III - Submit | 0 hrs | 0 days | 2025-09-05 | 2025-09-05 | 910 | 912
4874 | 912 | Future Task |  |  | D672 | Stacey Terry | Review | DED D672 - Support of UAT Segment III - Collaborative Review | 24 hrs | 10 days | 2025-09-08 | 2025-09-19 | 911 | 913
4875 | 913 | Future Task |  |  | D672 | Stacey Terry | Approve | DED D672 - Support of UAT Segment III - Approve | 0 hrs | 0 days | 2025-09-19 | 2025-09-19 | 912 | 914
4975 | 914 | Future Task |  |  | D672 | Stacey Terry |  | Identify UAT support resources for UAT Segment 3 | 12 hrs | 7 days | 2025-09-22 | 2025-09-30 | 913 | 915
4976 | 915 | Future Task |  |  | D672 | Stacey Terry |  | Participate in UAT sessions for UAT Segment 3 | 6 hrs | 21 days | 2025-10-01 | 2025-10-29 | 914 | 916SS
4977 | 916 | Future Task |  |  | D672 | Stacey Terry |  | Support resolution of UAT issues for UAT Segment 3 | 7 hrs | 21 days | 2025-10-01 | 2025-10-29 | 915SS | 917FS-5 days
4978 | 917 | Future Task |  |  | D672 | Stacey Terry |  | Confirm requirements traceability for UAT Segment 3 | 3 hrs | 7 days | 2025-10-23 | 2025-10-31 | 916FS-5 days | 918SS
4979 | 918 | Future Task |  |  | D672 | Stacey Terry |  | Create UAT Segment 3 Summary Document | 3 hrs | 7 days | 2025-10-23 | 2025-10-31 | 917SS | 919
4876 | 919 | Future Task |  |  | D672 | Stacey Terry | Submit | DEL D672 - Support of UAT Segment III - Draft Submission | 0 hrs | 0 days | 2025-10-31 | 2025-10-31 | 918 | 920
4877 | 920 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2025-11-03 | 2025-11-07 | 919 | 921
4878 | 921 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Style Guide Review | 1 hr | 1 day | 2025-11-10 | 2025-11-10 | 920 | 922
4879 | 922 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Final Collaborative Review | 20 hrs | 5 days | 2025-11-12 | 2025-11-18 | 921 | 923
4880 | 923 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Accenture QC | 4 hrs | 2 days | 2025-11-19 | 2025-11-20 | 922 | 924
4881 | 924 | Future Task |  |  | D672 | Stacey Terry | Submit | DEL D672 - Support of UAT Segment III - Submit | 0 hrs | 0 days | 2025-11-20 | 2025-11-20 | 923 | 925
4882 | 925 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Department QC | 4 hrs | 1 day | 2025-11-21 | 2025-11-21 | 924 | 926
4883 | 926 | Future Task |  |  | D672 | Stacey Terry | Review | DEL D672 - Support of UAT Segment III - Contract Manager Review | 2 hrs | 3 days | 2025-11-24 | 2025-11-26 | 925 | 927
4884 | 927 | Future Task |  |  | D672 | Stacey Terry | Accept | DEL D672 - Support of UAT Segment III - Accept | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 926 |  | 2025-11-01
4885 | 928 | Future Task | Yes |  | D673 | Stacey Terry |  | D673 - Completion of Mock Go-Lives (Dry Run #2) | 223 hrs | 66 days | 2025-08-04 | 2025-11-04
4886 | 929 | Future Task |  |  | D673 | Stacey Terry | Create | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Create | 24 hrs | 10 days | 2025-08-04 | 2025-08-15 | 1 | 930
4887 | 930 | Future Task |  |  | D673 | Stacey Terry | Submit | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Submit | 0 hrs | 0 days | 2025-08-15 | 2025-08-15 | 929 | 931
4888 | 931 | Future Task |  |  | D673 | Stacey Terry | Review | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Collaborative Review | 32 hrs | 10 days | 2025-08-18 | 2025-08-29 | 930 | 932
4889 | 932 | Future Task |  |  | D673 | Stacey Terry | Approve | DED D673 - Completion of Mock Go-Lives (Dry Run #2) - Approve | 0 hrs | 0 days | 2025-08-29 | 2025-08-29 | 931 | 933
4980 | 933 | Future Task |  |  | D673 | Stacey Terry |  | Confirm Mock Go-Live Dry Run #2 Execution Readiness | 24 hrs | 4 days | 2025-09-02 | 2025-09-05 | 932 | 934
4981 | 934 | Future Task |  |  | D673 | Stacey Terry |  | Execute Mock Go-Live Dry Run #2 | 20 hrs | 10 days | 2025-09-08 | 2025-09-19 | 933 | 935
4982 | 935 | Future Task |  |  | D673 | Stacey Terry |  | Document Mock Go-Live Dry Run Results #2 | 30 hrs | 5 days | 2025-09-22 | 2025-09-26 | 934 | 936
4983 | 936 | Future Task |  |  | D673 | Stacey Terry |  | Create Mock Go-Live Dry Run #2 Summary Document | 20 hrs | 10 days | 2025-09-29 | 2025-10-10 | 935 | 937
4890 | 937 | Future Task |  |  | D673 | Stacey Terry | Submit | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Draft Submission | 0 hrs | 0 days | 2025-10-10 | 2025-10-10 | 936 | 938
4891 | 938 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Pre-Submission Collaborative Review | 28 hrs | 5 days | 2025-10-13 | 2025-10-17 | 937 | 939
4892 | 939 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Style Guide Review | 1 hr | 1 day | 2025-10-20 | 2025-10-20 | 938 | 940
4893 | 940 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Final Collaborative Review | 28 hrs | 5 days | 2025-10-21 | 2025-10-27 | 939 | 941
4894 | 941 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Accenture QC | 4 hrs | 2 days | 2025-10-28 | 2025-10-29 | 940 | 942
4895 | 942 | Future Task |  |  | D673 | Stacey Terry | Submit | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Submit | 0 hrs | 0 days | 2025-10-29 | 2025-10-29 | 941 | 943
4896 | 943 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Department QC | 4 hrs | 1 day | 2025-10-30 | 2025-10-30 | 942 | 944
4897 | 944 | Future Task |  |  | D673 | Stacey Terry | Review | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Contract Manager Review | 8 hrs | 3 days | 2025-10-31 | 2025-11-04 | 943 | 945
4898 | 945 | Future Task |  |  | D673 | Stacey Terry | Accept | DEL D673 - Completion of Mock Go-Lives (Dry Run #2) - Accept | 0 hrs | 0 days | 2025-11-04 | 2025-11-04 | 944 | 1252 | 2025-11-01
4899 | 946 | Future Task | Yes |  | D674 | Jarad Hermann |  | D674 - Completion of Penetration Testing | 100 hrs | 145 days | 2025-05-02 | 2025-11-26
4900 | 947 | Future Task |  |  | D674 | Jarad Hermann | Create | DED D674 - Completion of Penetration Testing - Create | 2 hrs | 10 days | 2025-05-02 | 2025-05-15 | 1201FS+29 days,1236FS+29 days | 948 | Note: should be in version we go live with
4901 | 948 | Future Task |  |  | D674 | Jarad Hermann | Submit | DED D674 - Completion of Penetration Testing - Submit | 0 hrs | 0 days | 2025-05-15 | 2025-05-15 | 947 | 949
4902 | 949 | Future Task |  |  | D674 | Jarad Hermann | Review | DED D674 - Completion of Penetration Testing - Collaborative Review | 5 hrs | 10 days | 2025-05-16 | 2025-05-30 | 948 | 950
4903 | 950 | Future Task |  |  | D674 | Jarad Hermann | Approve | DED D674 - Completion of Penetration Testing - Approve | 0 hrs | 0 days | 2025-05-30 | 2025-05-30 | 949 | 951
4984 | 951 | Future Task |  |  | D674 | Jarad Hermann |  | Execute/Complete Penetration Test | 10 hrs | 64 days | 2025-06-02 | 2025-08-29 | 950 | 952
4985 | 952 | Future Task |  |  | D674 | Jarad Hermann |  | Review Penetration Test Outcome | 10 hrs | 20 days | 2025-09-02 | 2025-09-29 | 951 | 953SS
4986 | 953 | Future Task |  |  | D674 | Jarad Hermann |  | Remediate Penetration Test | 10 hrs | 44 days | 2025-09-02 | 2025-10-31 | 952SS | 954SS
4987 | 954 | Future Task |  |  | D674 | Jarad Hermann |  | Create Final Pen Testing Results/Remediation Summary Report | 20 hrs | 44 days | 2025-09-02 | 2025-10-31 | 953SS | 955
4904 | 955 | Future Task |  |  | D674 | Jarad Hermann | Submit | DEL D674 - Completion of Penetration Testing - Draft Submission | 0 hrs | 0 days | 2025-10-31 | 2025-10-31 | 954 | 956
4905 | 956 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2025-11-03 | 2025-11-07 | 955 | 957
4906 | 957 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Style Guide Review | 1 hr | 1 day | 2025-11-10 | 2025-11-10 | 956 | 958
4907 | 958 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Final Collaborative Review | 16 hrs | 5 days | 2025-11-12 | 2025-11-18 | 957 | 959
4908 | 959 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Accenture QC | 4 hrs | 2 days | 2025-11-19 | 2025-11-20 | 958 | 960
4909 | 960 | Future Task |  |  | D674 | Jarad Hermann | Submit | DEL D674 - Completion of Penetration Testing - Submit | 0 hrs | 0 days | 2025-11-20 | 2025-11-20 | 959 | 961
4910 | 961 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Department QC | 4 hrs | 1 day | 2025-11-21 | 2025-11-21 | 960 | 962
4911 | 962 | Future Task |  |  | D674 | Jarad Hermann | Review | DEL D674 - Completion of Penetration Testing - Contract Manager Review | 2 hrs | 3 days | 2025-11-24 | 2025-11-26 | 961 | 963
4912 | 963 | Future Task |  |  | D674 | Jarad Hermann | Accept | DEL D674 - Completion of Penetration Testing - Accept | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 962 | 1252 | 2025-11-01
4913 | 964 | Future Task | Yes |  | D675 | Jarad Hermann |  | D675 - Completion of Performance Testing | 180 hrs | 145 days | 2025-05-02 | 2025-11-26
4914 | 965 | Future Task |  |  | D675 | Jarad Hermann | Create | DED D675 - Completion of Performance Testing - Create | 2 hrs | 10 days | 2025-05-02 | 2025-05-15 | 1189FS-14 days,1225FS-14 days | 966
4915 | 966 | Future Task |  |  | D675 | Jarad Hermann | Submit | DED D675 - Completion of Performance Testing - Submit | 0 hrs | 0 days | 2025-05-15 | 2025-05-15 | 965 | 967
4916 | 967 | Future Task |  |  | D675 | Jarad Hermann | Review | DED D675 - Completion of Performance Testing - Collaborative Review | 5 hrs | 10 days | 2025-05-16 | 2025-05-30 | 966 | 968
4917 | 968 | Future Task |  |  | D675 | Jarad Hermann | Approve | DED D675 - Completion of Performance Testing - Approve | 0 hrs | 0 days | 2025-05-30 | 2025-05-30 | 967 | 969
4988 | 969 | Future Task |  |  | D675 | Jarad Hermann |  | Execute Performance Testing | 4 hrs | 108 days | 2025-06-02 | 2025-10-31 | 968573 | 970FS-10 days,973
4989 | 970 | Future Task |  |  | D675 | Jarad Hermann |  | Create Completion of Performance Testing Summary Document | 40 hrs | 10 days | 2025-10-20 | 2025-10-31 | 969FS-10 days | 971SS,972SS,973
4990 | 971 | Future Task |  |  | D675 | Jarad Hermann |  | Conduct Performance Testing Exit Criteria Review Meeting | 40 hrs | 10 days | 2025-10-20 | 2025-10-31 | 970SS | 973
4991 | 972 | Future Task |  |  | D675 | Jarad Hermann |  | Confirm requirements traceability for Performance Testing | 40 hrs | 10 days | 2025-10-20 | 2025-10-31 | 970SS | 973
4918 | 973 | Future Task |  |  | D675 | Jarad Hermann | Submit | DEL D675 - Completion of Performance Testing - Draft Submission | 0 hrs | 0 days | 2025-10-31 | 2025-10-31 | 972969970971 | 974
4919 | 974 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2025-11-03 | 2025-11-07 | 973 | 975
4920 | 975 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Style Guide Review | 1 hr | 1 day | 2025-11-10 | 2025-11-10 | 974 | 976
4921 | 976 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Final Collaborative Review | 16 hrs | 5 days | 2025-11-12 | 2025-11-18 | 975 | 977
4922 | 977 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Accenture QC | 4 hrs | 2 days | 2025-11-19 | 2025-11-20 | 976 | 978
4923 | 978 | Future Task |  |  | D675 | Jarad Hermann | Submit | DEL D675 - Completion of Performance Testing - Submit | 0 hrs | 0 days | 2025-11-20 | 2025-11-20 | 977 | 979
4924 | 979 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Department QC | 4 hrs | 1 day | 2025-11-21 | 2025-11-21 | 978 | 980
4925 | 980 | Future Task |  |  | D675 | Jarad Hermann | Review | DEL D675 - Completion of Performance Testing - Contract Manager Review | 8 hrs | 3 days | 2025-11-24 | 2025-11-26 | 979 | 981
4926 | 981 | Future Task |  |  | D675 | Jarad Hermann | Accept | DEL D675 - Completion of Performance Testing - Accept | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 980 | 1252 | 2025-11-01
4927 | 982 | Future Task | Yes |  | D676 | Jarad Hermann |  | D676 - Completion of Disaster Recovery Testing | 158 hrs | 114 days | 2025-03-04 | 2025-08-12
4928 | 983 | Future Task |  |  | D676 | Jarad Hermann | Create | DED D676 - Completion of Disaster Recovery Testing - Create | 8 hrs | 10 days | 2025-03-04 | 2025-03-17 | 1213FS-14 days,1175FS-14 days,1162 | 984
4929 | 984 | Future Task |  |  | D676 | Jarad Hermann | Submit | DED D676 - Completion of Disaster Recovery Testing - Submit | 0 hrs | 0 days | 2025-03-17 | 2025-03-17 | 983 | 985
4930 | 985 | Future Task |  |  | D676 | Jarad Hermann | Review | DED D676 - Completion of Disaster Recovery Testing - Collaborative Review | 20 hrs | 10 days | 2025-03-18 | 2025-03-31 | 984 | 986
4931 | 986 | Future Task |  |  | D676 | Jarad Hermann | Approve | DED D676 - Completion of Disaster Recovery Testing - Approve | 0 hrs | 0 days | 2025-03-31 | 2025-03-31 | 985 | 987
4992 | 987 | Future Task |  |  | D676 | Jarad Hermann |  | Execute Disaster Recovery Testing | 3 hrs | 64 days | 2025-04-01 | 2025-06-30 | 986575 | 988
4993 | 988 | Future Task |  |  | D676 | Jarad Hermann |  | Create Completion of Disaster Recovery Testing Summary Document | 26 hrs | 13 days | 2025-07-01 | 2025-07-18 | 987 | 989SS,990SS,991
4994 | 989 | Future Task |  |  | D676 | Jarad Hermann |  | Conduct Disaster Recovery Testing Exit Criteria Review Meeting | 26 hrs | 13 days | 2025-07-01 | 2025-07-18 | 988SS | 991
4995 | 990 | Future Task |  |  | D676 | Jarad Hermann |  | Confirm requirements traceability for Disaster Recovery Testing | 26 hrs | 13 days | 2025-07-01 | 2025-07-18 | 988SS | 991
4932 | 991 | Future Task |  |  | D676 | Jarad Hermann | Submit | DEL D676 - Completion of Disaster Recovery Testing - Draft Submission | 0 hrs | 0 days | 2025-07-18 | 2025-07-18 | 990988989 | 992
4933 | 992 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2025-07-21 | 2025-07-25 | 991 | 993
4934 | 993 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Style Guide Review | 1 hr | 1 day | 2025-07-28 | 2025-07-28 | 992 | 994
4935 | 994 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Final Collaborative Review | 16 hrs | 5 days | 2025-07-29 | 2025-08-04 | 993 | 995
4936 | 995 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Accenture QC | 4 hrs | 2 days | 2025-08-05 | 2025-08-06 | 994 | 996
4937 | 996 | Future Task |  |  | D676 | Jarad Hermann | Submit | DEL D676 - Completion of Disaster Recovery Testing - Submit | 0 hrs | 0 days | 2025-08-06 | 2025-08-06 | 995 | 997
4938 | 997 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Department QC | 4 hrs | 1 day | 2025-08-07 | 2025-08-07 | 996 | 998
4939 | 998 | Future Task |  |  | D676 | Jarad Hermann | Review | DEL D676 - Completion of Disaster Recovery Testing - Contract Manager Review | 8 hrs | 3 days | 2025-08-08 | 2025-08-12 | 997 | 999
4940 | 999 | Future Task |  |  | D676 | Jarad Hermann | Accept | DEL D676 - Completion of Disaster Recovery Testing - Accept | 0 hrs | 0 days | 2025-08-12 | 2025-08-12 | 998 | 1252 | 2025-11-01
4941 | 1000 | Future Task | Yes |  | D677 | Stacey Terry |  | D677 - Completion of Mock Go-Lives (Dry Run #3) | 229 hrs | 52 days | 2025-09-29 | 2025-12-12
4942 | 1001 | Future Task |  |  | D677 | Stacey Terry | Create | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Create | 24 hrs | 10 days | 2025-09-29 | 2025-10-10 | 1 | 1002
4943 | 1002 | Future Task |  |  | D677 | Stacey Terry | Submit | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Submit | 0 hrs | 0 days | 2025-10-10 | 2025-10-10 | 1001 | 1003
4944 | 1003 | Future Task |  |  | D677 | Stacey Terry | Review | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Collaborative Review | 32 hrs | 10 days | 2025-10-13 | 2025-10-24 | 1002 | 1004
4945 | 1004 | Future Task |  |  | D677 | Stacey Terry | Approve | DED D677 - Completion of Mock Go-Lives (Dry Run #3) - Approve | 0 hrs | 0 days | 2025-10-24 | 2025-10-24 | 1003 | 1005
5000 | 1005 | Future Task |  |  | D677 | Stacey Terry |  | Confirm Mock Go-Live Dry Run #3 Readiness | 40 hrs | 4 days | 2025-10-27 | 2025-10-30 | 1004 | 1006FS+1 day
5001 | 1006 | Future Task |  |  | D677 | Stacey Terry |  | Execute Mock Go-Live Dry Run #3 | 10 hrs | 10 days | 2025-11-03 | 2025-11-17 | 1005FS+1 day | 1007
5002 | 1007 | Future Task |  |  | D677 | Stacey Terry |  | Document Mock Go-Live Dry Run Results #3 | 30 hrs | 3 days | 2025-11-18 | 2025-11-20 | 1006 | 1008
5003 | 1008 | Future Task |  |  | D677 | Stacey Terry |  | Create Mock Go-Live Dry Run #3 Summary Document | 20 hrs | 2 days | 2025-11-21 | 2025-11-24 | 1007 | 1009
4946 | 1009 | Future Task |  |  | D677 | Stacey Terry | Submit | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Draft Submission | 0 hrs | 0 days | 2025-11-24 | 2025-11-24 | 1008 | 1010
4947 | 1010 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Pre-Submission Collaborative Review | 28 hrs | 3 days | 2025-11-25 | 2025-12-01 | 1009 | 1011
4948 | 1011 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Style Guide Review | 1 hr | 1 day | 2025-12-02 | 2025-12-02 | 1010 | 1012
4949 | 1012 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Final Collaborative Review | 28 hrs | 3 days | 2025-12-03 | 2025-12-05 | 1011 | 1013
4950 | 1013 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Accenture QC | 4 hrs | 1 day | 2025-12-08 | 2025-12-08 | 1012 | 1014
4951 | 1014 | Future Task |  |  | D677 | Stacey Terry | Submit | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Submit | 0 hrs | 0 days | 2025-12-08 | 2025-12-08 | 1013 | 1015
4952 | 1015 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Department QC | 4 hrs | 1 day | 2025-12-09 | 2025-12-09 | 1014 | 1016
4953 | 1016 | Future Task |  |  | D677 | Stacey Terry | Review | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Contract Manager Review | 8 hrs | 3 days | 2025-12-10 | 2025-12-12 | 1015 | 1017
4954 | 1017 | Future Task |  |  | D677 | Stacey Terry | Accept | DEL D677 - Completion of Mock Go-Lives (Dry Run #3) - Accept | 0 hrs | 0 days | 2025-12-12 | 2025-12-12 | 1016 | 1252 | 2025-12-01
5080 | 1018 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | WP406 - Mock Conversion Testing Plan | 180 hrs | 94 days | 2024-03-11 | 2024-07-22
5081 | 1019 | Future Task |  |  | WP406 | Manojkumar Gurjar | Create | WPED WP406 - Mock Conversion Testing Plan - Create | 24 hrs | 10 days | 2024-03-11 | 2024-03-22 | 1 | 1020
5082 | 1020 | Future Task |  |  | WP406 | Manojkumar Gurjar | Submit | WPED WP406 - Mock Conversion Testing Plan - Submit | 0 hrs | 0 days | 2024-03-22 | 2024-03-22 | 1019 | 1021
5083 | 1021 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WPED WP406 - Mock Conversion Testing Plan - Review | 28 hrs | 10 days | 2024-03-25 | 2024-04-05 | 1020 | 1022
5084 | 1022 | Future Task |  |  | WP406 | Manojkumar Gurjar | Approve | WPED WP406 - Mock Conversion Testing Plan - Approve | 0 hrs | 0 days | 2024-04-05 | 2024-04-05 | 1021 | 1023
5116 | 1023 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | Define Mock Conversion Testing Approach | 20 hrs | 10 days | 2024-04-08 | 2024-04-19 | 1022 | 1024
5117 | 1024 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | Identify Resources for Mock Conversion Testing | 20 hrs | 10 days | 2024-04-22 | 2024-05-03 | 1023 | 1025
5118 | 1025 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | Define Test Cycles and Scenarios | 20 hrs | 24 days | 2024-05-06 | 2024-06-07 | 1024 | 1026
5119 | 1026 | Future Task |  |  | WP406 | Manojkumar Gurjar |  | Define and review Entry/Exit Criteria for Mock Conversion Testing | 20 hrs | 15 days | 2024-06-10 | 2024-06-28 | 1025 | 1027
5085 | 1027 | Future Task |  |  | WP406 | Manojkumar Gurjar | Submit | WP WP406 - Mock Conversion Testing Plan - Submit | 0 hrs | 0 days | 2024-06-28 | 2024-06-28 | 1026 | 1028
5086 | 1028 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WP WP406 - Mock Conversion Testing Plan - Collaborative Review & Update | 24 hrs | 10 days | 2024-07-01 | 2024-07-15 | 1027 | 1029
5087 | 1029 | Future Task |  |  | WP406 | Manojkumar Gurjar | Review | WP WP406 - Mock Conversion Testing Plan - Final Review & Edits | 24 hrs | 5 days | 2024-07-16 | 2024-07-22 | 1028 | 1030
5088 | 1030 | Future Task |  |  | WP406 | Manojkumar Gurjar | Approve | WP WP406 - Mock Conversion Testing Plan - Approve | 0 hrs | 0 days | 2024-07-22 | 2024-07-22 | 1029 | 1032FS-45 days,564 | 2024-05-01
5089 | 1031 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | WP407 - Mock Conversion Scripts | 160 hrs | 67 days | 2024-05-17 | 2024-08-21
5090 | 1032 | Future Task |  |  | WP407 | Manojkumar Gurjar | Create | WPED WP407 - Mock Conversion Scripts - Create | 24 hrs | 10 days | 2024-05-17 | 2024-05-31 | 1030FS-45 days | 1033
5091 | 1033 | Future Task |  |  | WP407 | Manojkumar Gurjar | Submit | WPED WP407 - Mock Conversion Scripts - Submit | 0 hrs | 0 days | 2024-05-31 | 2024-05-31 | 1032 | 1034
5092 | 1034 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WPED WP407 - Mock Conversion Scripts - Review | 28 hrs | 10 days | 2024-06-03 | 2024-06-14 | 1033 | 1035
5093 | 1035 | Future Task |  |  | WP407 | Manojkumar Gurjar | Approve | WPED WP407 - Mock Conversion Scripts - Approve | 0 hrs | 0 days | 2024-06-14 | 2024-06-14 | 1034 | 1036
5120 | 1036 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | Create Test Scripts | 20 hrs | 19 days | 2024-06-17 | 2024-07-12 | 1035 | 1037
5121 | 1037 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | Identify System Test Scripts for Mock Conversion Testing | 20 hrs | 8 days | 2024-07-15 | 2024-07-24 | 1036 | 1038
5122 | 1038 | Future Task |  |  | WP407 | Manojkumar Gurjar |  | Review System Test Scripts for Mock Conversion Testing | 20 hrs | 5 days | 2024-07-25 | 2024-07-31 | 1037 | 1039
5094 | 1039 | Future Task |  |  | WP407 | Manojkumar Gurjar | Submit | WP WP407 - Mock Conversion Scripts - Submit | 0 hrs | 0 days | 2024-07-31 | 2024-07-31 | 1038 | 1040
5095 | 1040 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WP WP407 - Mock Conversion Scripts - Collaborative Review & Update | 24 hrs | 10 days | 2024-08-01 | 2024-08-14 | 1039 | 1041
5096 | 1041 | Future Task |  |  | WP407 | Manojkumar Gurjar | Review | WP WP407 - Mock Conversion Scripts - Final Review & Edits | 24 hrs | 5 days | 2024-08-15 | 2024-08-21 | 1040 | 1042
5097 | 1042 | Future Task |  |  | WP407 | Manojkumar Gurjar | Approve | WP WP407 - Mock Conversion Scripts - Approve | 0 hrs | 0 days | 2024-08-21 | 2024-08-21 | 1041 | 621FS-28 days | 2024-07-01
5098 | 1043 | Future Task |  |  | WP408 | Stacey Terry |  | WP408 - System Test Scripts | 188 hrs | 153 days | 2024-02-12 | 2024-09-16
5099 | 1044 | Future Task |  |  | WP408 | Stacey Terry | Create | WPED WP408 - System Test Scripts - Create | 16 hrs | 10 days | 2024-02-12 | 2024-02-23 | 1 | 1045
5100 | 1045 | Future Task |  |  | WP408 | Stacey Terry | Submit | WPED WP408 - System Test Scripts - Submit | 0 hrs | 0 days | 2024-02-23 | 2024-02-23 | 1044 | 1046
5101 | 1046 | Future Task |  |  | WP408 | Stacey Terry | Review | WPED WP408 - System Test Scripts - Review | 12 hrs | 10 days | 2024-02-26 | 2024-03-08 | 1045 | 1047
5102 | 1047 | Future Task |  |  | WP408 | Stacey Terry | Approve | WPED WP408 - System Test Scripts - Approve | 0 hrs | 0 days | 2024-03-08 | 2024-03-08 | 1046 | 1048
5123 | 1048 | Future Task |  |  | WP408 | Stacey Terry |  | Create Work Unit Tracker for System Test Preparation | 20 hrs | 10 days | 2024-03-11 | 2024-03-22 | 1047 | 1049
5124 | 1049 | Future Task |  |  | WP408 | Stacey Terry |  | Review, update, & confirm Work Unit Tracker for System Test Preparation | 20 hrs | 10 days | 2024-03-25 | 2024-04-05 | 1048 | 1050FS-5 days
5125 | 1050 | Future Task |  |  | WP408 | Stacey Terry |  | Create System Test Script Template | 30 hrs | 5 days | 2024-04-01 | 2024-04-05 | 1049FS-5 days | 1051
5126 | 1051 | Future Task |  |  | WP408 | Stacey Terry |  | Create, Review and Confirm System Test Scripts and Data (this is a WU) | 20 hrs | 93 days | 2024-04-08 | 2024-08-16 | 1050 | 1052
5127 | 1052 | Future Task |  |  | WP408 | Stacey Terry |  | Create System Test Script Summary Document | 30 hrs | 5 days | 2024-08-19 | 2024-08-23 | 1051 | 1053
5103 | 1053 | Future Task |  |  | WP408 | Stacey Terry | Submit | WP WP408 - System Test Scripts - Submit | 0 hrs | 0 days | 2024-08-23 | 2024-08-23 | 1052 | 1054
5104 | 1054 | Future Task |  |  | WP408 | Stacey Terry | Review | WP WP408 - System Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | 2024-08-26 | 2024-09-09 | 1053 | 1055
5105 | 1055 | Future Task |  |  | WP408 | Stacey Terry | Review | WP WP408 - System Test Scripts - Final Review & Edits | 20 hrs | 5 days | 2024-09-10 | 2024-09-16 | 1054 | 1056
5106 | 1056 | Future Task |  |  | WP408 | Stacey Terry | Approve | WP WP408 - System Test Scripts - Approve | 0 hrs | 0 days | 2024-09-16 | 2024-09-16 | 1055 | 648 | 2024-09-01
5107 | 1057 | Future Task |  |  | WP409 | Stacey Terry |  | WP409 - Regression Testing Plan | 116 hrs | 58 days | 2024-09-03 | 2024-11-22
5108 | 1058 | Future Task |  |  | WP409 | Stacey Terry | Create | WPED WP409 - Regression Testing Plan - Create | 2 hrs | 9 days | 2024-09-03 | 2024-09-13 | 1 | 1059
5109 | 1059 | Future Task |  |  | WP409 | Stacey Terry | Submit | WPED WP409 - Regression Testing Plan - Submit | 0 hrs | 0 days | 2024-09-13 | 2024-09-13 | 1058 | 1060
5110 | 1060 | Future Task |  |  | WP409 | Stacey Terry | Review | WPED WP409 - Regression Testing Plan - Review | 24 hrs | 10 days | 2024-09-16 | 2024-09-27 | 1059 | 1061
5111 | 1061 | Future Task |  |  | WP409 | Stacey Terry | Approve | WPED WP409 - Regression Testing Plan - Approve | 0 hrs | 0 days | 2024-09-27 | 2024-09-27 | 1060 | 1062
5128 | 1062 | Future Task |  |  | WP409 | Stacey Terry |  | Create Regression Testing Approach/Plan | 20 hrs | 24 days | 2024-09-30 | 2024-10-31 | 1061 | 1063SS+10 days,1065
5129 | 1063 | Future Task |  |  | WP409 | Stacey Terry |  | Define the scope of the Regression Test suite | 20 hrs | 10 days | 2024-10-14 | 2024-10-25 | 1062SS+10 days | 1064SS+5 days,1065
5130 | 1064 | Future Task |  |  | WP409 | Stacey Terry |  | Identify testing resources for Regression Testing | 20 hrs | 5 days | 2024-10-21 | 2024-10-25 | 1063SS+5 days | 1065
5112 | 1065 | Future Task |  |  | WP409 | Stacey Terry | Submit | WP WP409 - Regression Testing Plan - Submit | 0 hrs | 0 days | 2024-10-31 | 2024-10-31 | 106210631064 | 1066
5113 | 1066 | Future Task |  |  | WP409 | Stacey Terry | Review | WP WP409 - Regression Testing Plan - Collaborative Review & Update | 10 hrs | 10 days | 2024-11-01 | 2024-11-15 | 1065 | 1067
5114 | 1067 | Future Task |  |  | WP409 | Stacey Terry | Review | WP WP409 - Regression Testing Plan - Final Review & Edits | 20 hrs | 5 days | 2024-11-18 | 2024-11-22 | 1066 | 1068
5115 | 1068 | Future Task |  |  | WP409 | Stacey Terry | Approve | WP WP409 - Regression Testing Plan - Approve | 0 hrs | 0 days | 2024-11-22 | 2024-11-22 | 1067 | 1112FS-17 days,1124FS+5 days | 2024-12-01
5257 | 1069 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | WP412 - Interface Testing Plan | 220 hrs | 94 days | 2024-05-03 | 2024-09-16
5258 | 1070 | Future Task |  |  | WP412 | Manojkumar Gurjar | Create | WPED WP412 - Interface Testing Plan - Create | 24 hrs | 10 days | 2024-05-03 | 2024-05-16 | 544FS+92 days | 1071,1085SS+29 days
5259 | 1071 | Future Task |  |  | WP412 | Manojkumar Gurjar | Submit | WPED WP412 - Interface Testing Plan - Submit | 0 hrs | 0 days | 2024-05-16 | 2024-05-16 | 1070 | 1072
5260 | 1072 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WPED WP412 - Interface Testing Plan - Review | 28 hrs | 10 days | 2024-05-17 | 2024-05-31 | 1071 | 1073
5261 | 1073 | Future Task |  |  | WP412 | Manojkumar Gurjar | Approve | WPED WP412 - Interface Testing Plan - Approve | 0 hrs | 0 days | 2024-05-31 | 2024-05-31 | 1072 | 1074
5284 | 1074 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Define Interface Test approach | 20 hrs | 15 days | 2024-06-03 | 2024-06-21 | 1073 | 1075
5285 | 1075 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Define Interface Test Cycles | 20 hrs | 14 days | 2024-06-24 | 2024-07-12 | 1074 | 1076
5286 | 1076 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Identify Test Resources for Interface Testing | 20 hrs | 5 days | 2024-07-15 | 2024-07-19 | 1075 | 1077
5287 | 1077 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Define Test Tools and Test Management processes for Interface Testing | 20 hrs | 5 days | 2024-07-22 | 2024-07-26 | 1076 | 1078
5288 | 1078 | Future Task |  |  | WP412 | Manojkumar Gurjar |  | Create Initial List of Interface Test Scenarios | 20 hrs | 10 days | 2024-07-29 | 2024-08-09 | 1077 | 1079
5289 | 1079 | Future Task |  | RW | WP412 | Manojkumar Gurjar |  | Prepare High-level Interface Test Approach for Integration Partners | 20 hrs | 10 days | 2024-08-12 | 2024-08-23 | 1078 | 1080
5262 | 1080 | Future Task |  |  | WP412 | Manojkumar Gurjar | Submit | WP WP412 - Interface Testing Plan - Submit | 0 hrs | 0 days | 2024-08-23 | 2024-08-23 | 1079 | 1081
5263 | 1081 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WP WP412 - Interface Testing Plan - Collaborative Review & Update | 24 hrs | 10 days | 2024-08-26 | 2024-09-09 | 1080 | 1082
5264 | 1082 | Future Task |  |  | WP412 | Manojkumar Gurjar | Review | WP WP412 - Interface Testing Plan - Final Review & Edits | 24 hrs | 5 days | 2024-09-10 | 2024-09-16 | 1081 | 1083
5265 | 1083 | Future Task |  |  | WP412 | Manojkumar Gurjar | Approve | WP WP412 - Interface Testing Plan - Approve | 0 hrs | 0 days | 2024-09-16 | 2024-09-16 | 1082 | 562FS-10 days | 2024-08-01
5266 | 1084 | Future Task |  |  | WP413 | Stacey Terry |  | WP413 - Interface Test Scripts | 180 hrs | 89 days | 2024-06-14 | 2024-10-18
5267 | 1085 | Future Task |  |  | WP413 | Stacey Terry | Create | WPED WP413 - Interface Test Scripts - Create | 16 hrs | 10 days | 2024-06-14 | 2024-06-27 | 1070SS+29 days | 1086
5268 | 1086 | Future Task |  |  | WP413 | Stacey Terry | Submit | WPED WP413 - Interface Test Scripts - Submit | 0 hrs | 0 days | 2024-06-27 | 2024-06-27 | 1085 | 1087
5269 | 1087 | Future Task |  |  | WP413 | Stacey Terry | Review | WPED WP413 - Interface Test Scripts - Review | 24 hrs | 10 days | 2024-06-28 | 2024-07-12 | 1086 | 1088
5270 | 1088 | Future Task |  |  | WP413 | Stacey Terry | Approve | WPED WP413 - Interface Test Scripts - Approve | 0 hrs | 0 days | 2024-07-12 | 2024-07-12 | 1087 | 1089
5290 | 1089 | Future Task |  |  | WP413 | Stacey Terry |  | Create Work Unit Tracker for Interface Test Preparation | 20 hrs | 10 days | 2024-07-15 | 2024-07-26 | 1088 | 1090
5291 | 1090 | Future Task |  |  | WP413 | Stacey Terry |  | Review, update, & confirm Work Unit Tracker for Interface Test Preparation | 20 hrs | 5 days | 2024-07-29 | 2024-08-02 | 1089 | 1091
5292 | 1091 | Future Task |  |  | WP413 | Stacey Terry |  | Create, Review and Confirm Interface Test Scenarios/Scripts and Data (this is a WU) | 20 hrs | 24 days | 2024-08-05 | 2024-09-06 | 1090 | 1092
5293 | 1092 | Future Task |  |  | WP413 | Stacey Terry |  | Create Interface Test Scripts Summary Document | 20 hrs | 5 days | 2024-09-09 | 2024-09-13 | 1091 | 1093
5271 | 1093 | Future Task |  |  | WP413 | Stacey Terry | Submit | WP WP413 - Interface Test Scripts - Submit | 0 hrs | 0 days | 2024-09-13 | 2024-09-13 | 1092 | 1094
5272 | 1094 | Future Task |  |  | WP413 | Stacey Terry | Review | WP WP413 - Interface Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | 2024-09-16 | 2024-09-27 | 1093 | 1095
5273 | 1095 | Future Task |  |  | WP413 | Stacey Terry | Review | WP WP413 - Interface Test Scripts - Final Review & Edits | 20 hrs | 5 days | 2024-09-30 | 2024-10-04 | 1094 | 1096
5274 | 1096 | Future Task |  |  | WP413 | Stacey Terry | Approve | WP WP413 - Interface Test Scripts - Approve | 0 hrs | 0 days | 2024-10-04 | 2024-10-04 | 1095 | 1097 | 2024-08-01
7149 | 1097 | Future Task |  | RW | WP413 | Stacey Terry |  | Prepare and share Test Scenarios and Scripts with Integration partners | 20 hrs | 10 days | 2024-10-07 | 2024-10-18 | 1096
5275 | 1098 | Future Task |  |  | WP414 | Stacey Terry |  | WP414 - Payroll Parallel Test Scripts | 160 hrs | 80 days | 2025-01-13 | 2025-05-05
5276 | 1099 | Future Task |  |  | WP414 | Stacey Terry | Create | WPED WP414 - Payroll Parallel Test Scripts - Create | 16 hrs | 10 days | 2025-01-13 | 2025-01-27 | 723SS-4 days | 1100
5277 | 1100 | Future Task |  |  | WP414 | Stacey Terry | Submit | WPED WP414 - Payroll Parallel Test Scripts - Submit | 0 hrs | 0 days | 2025-01-27 | 2025-01-27 | 1099 | 1101
5278 | 1101 | Future Task |  |  | WP414 | Stacey Terry | Review | WPED WP414 - Payroll Parallel Test Scripts - Review | 24 hrs | 10 days | 2025-01-28 | 2025-02-10 | 1100 | 1102
5279 | 1102 | Future Task |  |  | WP414 | Stacey Terry | Approve | WPED WP414 - Payroll Parallel Test Scripts - Approve | 0 hrs | 0 days | 2025-02-10 | 2025-02-10 | 1101 | 1103
5295 | 1103 | Future Task |  |  | WP414 | Stacey Terry |  | Create Work Unit Tracker for Payroll Parallel Test Preparation | 20 hrs | 5 days | 2025-02-11 | 2025-02-17 | 1102 | 1104
5296 | 1104 | Future Task |  |  | WP414 | Stacey Terry |  | Review, update, & confirm Work Unit Tracker for Payroll Parallel Test Preparation | 20 hrs | 10 days | 2025-02-18 | 2025-03-03 | 1103 | 1105FS-5 days
5297 | 1105 | Future Task |  |  | WP414 | Stacey Terry |  | Create, Review and Confirm Payroll Parallel Test Scenarios/Scripts and Data - this is a WU | 20 hrs | 30 days | 2025-02-25 | 2025-04-07 | 1104FS-5 days | 1106FS-5 days
5298 | 1106 | Future Task |  |  | WP414 | Stacey Terry |  | Create Payroll Parallel Test Script Summary Document | 20 hrs | 10 days | 2025-04-01 | 2025-04-14 | 1105FS-5 days | 1107
5280 | 1107 | Future Task |  |  | WP414 | Stacey Terry | Submit | WP WP414 - Payroll Parallel Test Scripts - Submit | 0 hrs | 0 days | 2025-04-14 | 2025-04-14 | 1106 | 1108
5281 | 1108 | Future Task |  |  | WP414 | Stacey Terry | Review | WP WP414 - Payroll Parallel Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | 2025-04-15 | 2025-04-28 | 1107 | 1109
5282 | 1109 | Future Task |  |  | WP414 | Stacey Terry | Review | WP WP414 - Payroll Parallel Test Scripts - Final Review & Edits | 20 hrs | 5 days | 2025-04-29 | 2025-05-05 | 1108 | 1110
5283 | 1110 | Future Task |  |  | WP414 | Stacey Terry | Approve | WP WP414 - Payroll Parallel Test Scripts - Approve | 0 hrs | 0 days | 2025-05-05 | 2025-05-05 | 1109 |  | 2025-03-01
5131 | 1111 | Future Task |  |  | WP415 | Stacey Terry |  | WP415 - Regression Test Scripts | 140 hrs | 63 days | 2024-10-30 | 2025-02-03
5132 | 1112 | Future Task |  |  | WP415 | Stacey Terry | Create | WPED WP415 - Regression Test Scripts - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1068FS-17 days | 1113
5133 | 1113 | Future Task |  |  | WP415 | Stacey Terry | Submit | WPED WP415 - Regression Test Scripts - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 1112 | 1114
5134 | 1114 | Future Task |  |  | WP415 | Stacey Terry | Review | WPED WP415 - Regression Test Scripts - Review | 24 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1113 | 1115
5135 | 1115 | Future Task |  |  | WP415 | Stacey Terry | Approve | WPED WP415 - Regression Test Scripts - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1114 | 1116
5221 | 1116 | Future Task |  |  | WP415 | Stacey Terry |  | Create Regression Test Suite | 20 hrs | 10 days | 2024-12-02 | 2024-12-13 | 1115 | 1117
5222 | 1117 | Future Task |  |  | WP415 | Stacey Terry |  | Review, update & confirm Regression Test Suite | 20 hrs | 9 days | 2024-12-16 | 2024-12-27 | 1116 | 1118
5223 | 1118 | Future Task |  |  | WP415 | Stacey Terry |  | Create Regression Test Scripts Summary Document | 20 hrs | 9 days | 2024-12-30 | 2025-01-10 | 1117 | 1119
5136 | 1119 | Future Task |  |  | WP415 | Stacey Terry | Submit | WP WP415 - Regression Test Scripts - Submit | 0 hrs | 0 days | 2025-01-10 | 2025-01-10 | 1118 | 1120
5137 | 1120 | Future Task |  |  | WP415 | Stacey Terry | Review | WP WP415 - Regression Test Scripts - Collaborative Review & Update | 20 hrs | 10 days | 2025-01-13 | 2025-01-27 | 1119 | 1121
5138 | 1121 | Future Task |  |  | WP415 | Stacey Terry | Review | WP WP415 - Regression Test Scripts - Final Review & Edits | 20 hrs | 5 days | 2025-01-28 | 2025-02-03 | 1120 | 1122
5139 | 1122 | Future Task |  |  | WP415 | Stacey Terry | Approve | WP WP415 - Regression Test Scripts - Approve | 0 hrs | 0 days | 2025-02-03 | 2025-02-03 | 1121 |  | 2024-12-01
5140 | 1123 | Future Task | Yes |  | WP416 | Stacey Terry |  | WP416 - Completion of Regression Testing | 123 hrs | 160 days | 2024-12-04 | 2025-07-22
5141 | 1124 | Future Task |  |  | WP416 | Stacey Terry | Create | WPED WP416 - Completion of Regression Testing - Create | 16 hrs | 10 days | 2024-12-04 | 2024-12-17 | 1068FS+5 days | 1125
5142 | 1125 | Future Task |  |  | WP416 | Stacey Terry | Submit | WPED WP416 - Completion of Regression Testing - Submit | 0 hrs | 0 days | 2024-12-17 | 2024-12-17 | 1124 | 1126
5143 | 1126 | Future Task |  |  | WP416 | Stacey Terry | Review | WPED WP416 - Completion of Regression Testing - Review | 24 hrs | 10 days | 2024-12-18 | 2025-01-02 | 1125 | 1127
5144 | 1127 | Future Task |  |  | WP416 | Stacey Terry | Approve | WPED WP416 - Completion of Regression Testing - Approve | 0 hrs | 0 days | 2025-01-02 | 2025-01-02 | 1126 | 1128
5224 | 1128 | Future Task |  |  | WP416 | Stacey Terry |  | Create Work Unit Tracker for Regression Test Execution | 20 hrs | 10 days | 2025-01-03 | 2025-01-16 | 1127 | 1129
5225 | 1129 | Future Task |  |  | WP416 | Stacey Terry |  | Review, update, and confirm Work Unit Tracker for Regression Test Execution | 20 hrs | 10 days | 2025-01-17 | 2025-01-31 | 1128 | 1130
5226 | 1130 | Future Task |  |  | WP416 | Stacey Terry |  | Conduct Regression Test Execution Kickoff Meeting | 20 hrs | 5 days | 2025-02-03 | 2025-02-07 | 1129 | 1131
5227 | 1131 | Future Task |  |  | WP416 | Stacey Terry |  | Execute Regression Test - this is a WU | 10 hrs | 90 days | 2025-02-10 | 2025-06-16 | 1130 | 1132
5228 | 1132 | Future Task |  |  | WP416 | Stacey Terry |  | Create Completion of Regression Test Execution Summary Document | 3 hrs | 10 days | 2025-06-17 | 2025-06-30 | 1131 | 1133
5145 | 1133 | Future Task |  |  | WP416 | Stacey Terry | Submit | WP WP416 - Completion of Regression Testing - Submit | 0 hrs | 0 days | 2025-06-30 | 2025-06-30 | 1132 | 1134
5146 | 1134 | Future Task |  |  | WP416 | Stacey Terry | Review | WP WP416 - Completion of Regression Testing - Collaborative Review & Update | 5 hrs | 10 days | 2025-07-01 | 2025-07-15 | 1133 | 1135
5147 | 1135 | Future Task |  |  | WP416 | Stacey Terry | Review | WP WP416 - Completion of Regression Testing - Final Review & Edits | 5 hrs | 5 days | 2025-07-16 | 2025-07-22 | 1134 | 1136
5148 | 1136 | Future Task |  |  | WP416 | Stacey Terry | Approve | WP WP416 - Completion of Regression Testing - Approve | 0 hrs | 0 days | 2025-07-22 | 2025-07-22 | 1135 |  | 2025-06-01
5149 | 1137 | Future Task |  |  | WP417 | Stacey Terry |  | WP417 - Data Dictionary | 192 hrs | 112 days | 2024-10-30 | 2025-04-11
5150 | 1138 | Future Task |  |  | WP417 | Stacey Terry | Create | WPED WP417 - Data Dictionary - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1 | 1139
5151 | 1139 | Future Task |  |  | WP417 | Stacey Terry | Submit | WPED WP417 - Data Dictionary - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 1138 | 1140
5152 | 1140 | Future Task |  |  | WP417 | Stacey Terry | Review | WPED WP417 - Data Dictionary - Review | 28 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1139 | 1141
5153 | 1141 | Future Task |  |  | WP417 | Stacey Terry | Approve | WPED WP417 - Data Dictionary - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1140 | 1142
5229 | 1142 | Future Task |  |  | WP417 | Stacey Terry |  | Update data dictionary with latest tables and data elements as needed - Financials | 20 hrs | 21 days | 2024-12-02 | 2024-12-31 | 1141 | 1143
5230 | 1143 | Future Task |  |  | WP417 | Stacey Terry |  | Update data dictionary with latest tables and data elements as needed - Payroll | 20 hrs | 21 days | 2025-01-02 | 2025-01-31 | 1142 | 1144
5231 | 1144 | Future Task |  |  | WP417 | Stacey Terry |  | Update data dictionary with latest tables and data elements as needed - DW Related | 20 hrs | 20 days | 2025-02-03 | 2025-02-28 | 1143 | 1145
5232 | 1145 | Future Task |  |  | WP417 | Stacey Terry |  | Review and confirm data dictionary | 20 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1144 | 1146
5233 | 1146 | Future Task |  |  | WP417 | Stacey Terry |  | Share Data Dictionary | 20 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1145 | 1147
5154 | 1147 | Future Task |  |  | WP417 | Stacey Terry | Submit | WP WP417 - Data Dictionary - Submit | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 1146 | 1148
5155 | 1148 | Future Task |  |  | WP417 | Stacey Terry | Review | WP WP417 - Data Dictionary - Collaborative Review & Update | 24 hrs | 10 days | 2025-03-24 | 2025-04-04 | 1147 | 1149
5156 | 1149 | Future Task |  |  | WP417 | Stacey Terry | Review | WP WP417 - Data Dictionary - Final Review & Edits | 24 hrs | 5 days | 2025-04-07 | 2025-04-11 | 1148 | 1150
5157 | 1150 | Future Task |  |  | WP417 | Stacey Terry | Approve | WP WP417 - Data Dictionary - Approve | 0 hrs | 0 days | 2025-04-11 | 2025-04-11 | 1149 |  | 2025-02-01
5158 | 1151 | Future Task |  |  | WP418 | Jarad Hermann |  | WP418 - Disaster Recovery Plan | 102 hrs | 81 days | 2024-08-26 | 2024-12-20
5159 | 1152 | Future Task |  |  | WP418 | Jarad Hermann | Create | WPED WP418 - Disaster Recovery Plan - Create | 2 hrs | 10 days | 2024-08-26 | 2024-09-09 | 1 | 1153,1164SS+5 days
5160 | 1153 | Future Task |  |  | WP418 | Jarad Hermann | Submit | WPED WP418 - Disaster Recovery Plan - Submit | 0 hrs | 0 days | 2024-09-09 | 2024-09-09 | 1152 | 1154
5161 | 1154 | Future Task |  |  | WP418 | Jarad Hermann | Review | WPED WP418 - Disaster Recovery Plan - Review | 16 hrs | 10 days | 2024-09-10 | 2024-09-23 | 1153 | 1155
5162 | 1155 | Future Task |  |  | WP418 | Jarad Hermann | Approve | WPED WP418 - Disaster Recovery Plan - Approve | 0 hrs | 0 days | 2024-09-23 | 2024-09-23 | 1154 | 1156FS+4 days
5234 | 1156 | Future Task |  |  | WP418 | Jarad Hermann |  | Design/Update Disaster Recovery (DR) Plan | 20 hrs | 15 days | 2024-09-30 | 2024-10-18 | 1155FS+4 days | 1157
5235 | 1157 | Future Task |  |  | WP418 | Jarad Hermann |  | Review Financials Disaster Recovery Plan | 20 hrs | 15 days | 2024-10-21 | 2024-11-08 | 1156 | 1158
5236 | 1158 | Future Task |  |  | WP418 | Jarad Hermann |  | Create Payroll Disaster Recovery Plan | 20 hrs | 12 days | 2024-11-12 | 2024-11-27 | 1157 | 1159
5163 | 1159 | Future Task |  |  | WP418 | Jarad Hermann | Submit | WP WP418 - Disaster Recovery Plan - Submit | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1158 | 1160
5164 | 1160 | Future Task |  |  | WP418 | Jarad Hermann | Review | WP WP418 - Disaster Recovery Plan - Collaborative Review & Update | 12 hrs | 10 days | 2024-12-02 | 2024-12-13 | 1159 | 1161
5165 | 1161 | Future Task |  |  | WP418 | Jarad Hermann | Review | WP WP418 - Disaster Recovery Plan - Final Review & Edits | 12 hrs | 5 days | 2024-12-16 | 2024-12-20 | 1160 | 1162
5166 | 1162 | Future Task |  |  | WP418 | Jarad Hermann | Approve | WP WP418 - Disaster Recovery Plan - Approve | 0 hrs | 0 days | 2024-12-20 | 2024-12-20 | 1161 | 983 | 2024-11-01
5167 | 1163 | Future Task |  |  | WP419 | Jarad Hermann |  | WP419 - Disaster Recovery Testing Plan | 116 hrs | 138 days | 2024-09-03 | 2025-03-21
5168 | 1164 | Future Task |  |  | WP419 | Jarad Hermann | Create | WPED WP419 - Disaster Recovery Testing Plan - Create | 16 hrs | 10 days | 2024-09-03 | 2024-09-16 | 1152SS+5 days | 1165
5169 | 1165 | Future Task |  |  | WP419 | Jarad Hermann | Submit | WPED WP419 - Disaster Recovery Testing Plan - Submit | 0 hrs | 0 days | 2024-09-16 | 2024-09-16 | 1164 | 1166
5170 | 1166 | Future Task |  |  | WP419 | Jarad Hermann | Review | WPED WP419 - Disaster Recovery Testing Plan - Review | 20 hrs | 10 days | 2024-09-17 | 2024-09-30 | 1165 | 1167
5171 | 1167 | Future Task |  |  | WP419 | Jarad Hermann | Approve | WPED WP419 - Disaster Recovery Testing Plan - Approve | 0 hrs | 0 days | 2024-09-30 | 2024-09-30 | 1166 | 1168
5237 | 1168 | Future Task |  |  | WP419 | Jarad Hermann |  | Define and Document Disaster Recovery Test Tasks including Test Planning, Preparation, Execution, and Closure | 20 hrs | 62 days | 2024-10-01 | 2024-12-31 | 1167 | 1169SS,1203SS+42 days
5238 | 1169 | Future Task |  |  | WP419 | Jarad Hermann |  | Define Disaster Recovery Testing Tools | 20 hrs | 62 days | 2024-10-01 | 2024-12-31 | 1168SS | 1170
5239 | 1170 | Future Task |  |  | WP419 | Jarad Hermann |  | Define and Document Disaster Recovery Test Management | 4 hrs | 41 days | 2025-01-02 | 2025-02-28 | 1169 | 1171SS
5240 | 1171 | Future Task |  |  | WP419 | Jarad Hermann |  | Define and Document Disaster Recovery Test Resources and Responsibilities | 4 hrs | 41 days | 2025-01-02 | 2025-02-28 | 1170SS | 1172
5172 | 1172 | Future Task |  |  | WP419 | Jarad Hermann | Submit | WP WP419 - Disaster Recovery Testing Plan - Submit | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 1171 | 1173574
5173 | 1173 | Future Task |  |  | WP419 | Jarad Hermann | Review | WP WP419 - Disaster Recovery Testing Plan - Collaborative Review & Update | 16 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1172 | 1174
5174 | 1174 | Future Task |  |  | WP419 | Jarad Hermann | Review | WP WP419 - Disaster Recovery Testing Plan - Final Review & Edits | 16 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1173 | 1175
5175 | 1175 | Future Task |  |  | WP419 | Jarad Hermann | Approve | WP WP419 - Disaster Recovery Testing Plan - Approve | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 1174 | 983FS-14 days | 2025-02-01
5176 | 1176 | Future Task |  |  | WP420 | Jarad Hermann |  | WP420 - Performance Testing Plan | 128 hrs | 140 days | 2024-10-30 | 2025-05-21
5177 | 1177 | Future Task |  |  | WP420 | Jarad Hermann | Create | WPED WP420 - Performance Testing Plan - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1 | 1178,1215SS
5178 | 1178 | Future Task |  |  | WP420 | Jarad Hermann | Submit | WPED WP420 - Performance Testing Plan - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 1177 | 1179
5179 | 1179 | Future Task |  |  | WP420 | Jarad Hermann | Review | WPED WP420 - Performance Testing Plan - Review | 20 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1178 | 1180
5180 | 1180 | Future Task |  |  | WP420 | Jarad Hermann | Approve | WPED WP420 - Performance Testing Plan - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1179 | 1181,1182SS,1183SS,1184SS,1185SS
5241 | 1181 | Future Task |  |  | WP420 | Jarad Hermann |  | Identify and establish the projected load of the system | 4 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1180 | 1186
5242 | 1182 | Future Task |  |  | WP420 | Jarad Hermann |  | Define test cycles to be included | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1180SS | 1186
5243 | 1183 | Future Task |  |  | WP420 | Jarad Hermann |  | Define Performance Testing objectives, scope, environments, and metrics | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1180SS | 1186
5244 | 1184 | Future Task |  |  | WP420 | Jarad Hermann |  | Identify performance testing project team members and responsibilities | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1180SS | 1186
5245 | 1185 | Future Task |  |  | WP420 | Jarad Hermann |  | Define and document Performance Testing entry and exit criteria | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1180SS | 1186
5181 | 1186 | Future Task |  |  | WP420 | Jarad Hermann | Submit | WP WP420 - Performance Testing Plan - Submit | 0 hrs | 0 days | 2025-04-30 | 2025-04-30 | 1.1851e+19 | 1187572
5182 | 1187 | Future Task |  |  | WP420 | Jarad Hermann | Review | WP WP420 - Performance Testing Plan - Collaborative Review & Update | 4 hrs | 10 days | 2025-05-01 | 2025-05-14 | 1186 | 1188
5183 | 1188 | Future Task |  |  | WP420 | Jarad Hermann | Review | WP WP420 - Performance Testing Plan - Final Review & Edits | 4 hrs | 5 days | 2025-05-15 | 2025-05-21 | 1187 | 1189
5184 | 1189 | Future Task |  |  | WP420 | Jarad Hermann | Approve | WP WP420 - Performance Testing Plan - Approve | 0 hrs | 0 days | 2025-05-21 | 2025-05-21 | 1188 | 965FS-14 days | 2025-04-01
5185 | 1190 | Future Task |  |  | WP421 | Jarad Hermann |  | WP421 - Penetration Testing Plan | 128 hrs | 97 days | 2024-10-30 | 2025-03-21
5186 | 1191 | Future Task |  |  | WP421 | Jarad Hermann | Create | WPED WP421 - Penetration Testing Plan - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1 | 1192,1227SS
5187 | 1192 | Future Task |  |  | WP421 | Jarad Hermann | Submit | WPED WP421 - Penetration Testing Plan - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 1191 | 1193
5188 | 1193 | Future Task |  |  | WP421 | Jarad Hermann | Review | WPED WP421 - Penetration Testing Plan - Review | 20 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1192 | 1194
5189 | 1194 | Future Task |  |  | WP421 | Jarad Hermann | Approve | WPED WP421 - Penetration Testing Plan - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1193 | 1195
5246 | 1195 | Future Task |  |  | WP421 | Jarad Hermann |  | Create Penetration Testing Plan/approach | 20 hrs | 62 days | 2024-12-02 | 2025-02-28 | 1194 | 1196SS,1197SS,1198
5247 | 1196 | Future Task |  |  | WP421 | Jarad Hermann |  | Identify resources for Penetration Testing | 20 hrs | 62 days | 2024-12-02 | 2025-02-28 | 1195SS | 1198
5248 | 1197 | Future Task |  |  | WP421 | Jarad Hermann |  | Define Penetration Testing entry and exit criteria | 20 hrs | 62 days | 2024-12-02 | 2025-02-28 | 1195SS | 1198
5190 | 1198 | Future Task |  |  | WP421 | Jarad Hermann | Submit | WP WP421 - Penetration Testing Plan - Submit | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 119711951196 | 1199
5191 | 1199 | Future Task |  |  | WP421 | Jarad Hermann | Review | WP WP421 - Penetration Testing Plan - Collaborative Review & Update | 16 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1198 | 1200
5192 | 1200 | Future Task |  |  | WP421 | Jarad Hermann | Review | WP WP421 - Penetration Testing Plan - Final Review & Edits | 16 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1199 | 1201
5193 | 1201 | Future Task |  |  | WP421 | Jarad Hermann | Approve | WP WP421 - Penetration Testing Plan - Approve | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 1200 | 947FS+29 days | 2025-02-01
5194 | 1202 | Future Task |  |  | WP422 | Jarad Hermann |  | WP422 - Disaster Recovery Test Scripts | 128 hrs | 76 days | 2024-12-03 | 2025-03-21
5195 | 1203 | Future Task |  |  | WP422 | Jarad Hermann | Create | WPED WP422 - Disaster Recovery Test Scripts - Create | 16 hrs | 10 days | 2024-12-03 | 2024-12-16 | 1168SS+42 days | 1204
5196 | 1204 | Future Task |  |  | WP422 | Jarad Hermann | Submit | WPED WP422 - Disaster Recovery Test Scripts - Submit | 0 hrs | 0 days | 2024-12-16 | 2024-12-16 | 1203 | 1205
5197 | 1205 | Future Task |  |  | WP422 | Jarad Hermann | Review | WPED WP422 - Disaster Recovery Test Scripts - Review | 20 hrs | 10 days | 2024-12-17 | 2024-12-31 | 1204 | 1206
5198 | 1206 | Future Task |  |  | WP422 | Jarad Hermann | Approve | WPED WP422 - Disaster Recovery Test Scripts - Approve | 0 hrs | 0 days | 2024-12-31 | 2024-12-31 | 1205 | 1207
5249 | 1207 | Future Task |  |  | WP422 | Jarad Hermann |  | Finalize Disaster Recovery Test Scripts Inventory | 20 hrs | 41 days | 2025-01-02 | 2025-02-28 | 1206 | 1208SS,1209SS,1210
5250 | 1208 | Future Task |  |  | WP422 | Jarad Hermann |  | Create, review, and confirm DR Test Script Work Unit Tracker | 20 hrs | 41 days | 2025-01-02 | 2025-02-28 | 1207SS | 1210
5251 | 1209 | Future Task |  |  | WP422 | Jarad Hermann |  | Create, Review and Confirm Disaster Recovery Test Scripts | 20 hrs | 41 days | 2025-01-02 | 2025-02-28 | 1207SS | 1210
5199 | 1210 | Future Task |  |  | WP422 | Jarad Hermann | Submit | WP WP422 - Disaster Recovery Test Scripts - Submit | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 120912071208 | 1211
5200 | 1211 | Future Task |  |  | WP422 | Jarad Hermann | Review | WP WP422 - Disaster Recovery Test Scripts - Collaborative Review & Update | 16 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1210 | 1212
5201 | 1212 | Future Task |  |  | WP422 | Jarad Hermann | Review | WP WP422 - Disaster Recovery Test Scripts - Final Review & Edits | 16 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1211 | 1213
5202 | 1213 | Future Task |  |  | WP422 | Jarad Hermann | Approve | WP WP422 - Disaster Recovery Test Scripts - Approve | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 1212 | 983FS-14 days
5203 | 1214 | Future Task |  |  | WP423 | Jarad Hermann |  | WP423 - Performance Test Scripts | 104 hrs | 140 days | 2024-10-30 | 2025-05-21
5204 | 1215 | Future Task |  |  | WP423 | Jarad Hermann | Create | WPED WP423 - Performance Test Scripts - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1177SS | 1216
5205 | 1216 | Future Task |  |  | WP423 | Jarad Hermann | Submit | WPED WP423 - Performance Test Scripts - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 1215 | 1217
5206 | 1217 | Future Task |  |  | WP423 | Jarad Hermann | Review | WPED WP423 - Performance Test Scripts - Review | 20 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1216 | 1218
5207 | 1218 | Future Task |  |  | WP423 | Jarad Hermann | Approve | WPED WP423 - Performance Test Scripts - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1217 | 1219
5252 | 1219 | Future Task |  |  | WP423 | Jarad Hermann |  | Finalize Performance Test Scripts Inventory | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1218 | 1220SS,1221SS,1222
5253 | 1220 | Future Task |  |  | WP423 | Jarad Hermann |  | Create, review, and confirm Performance Test Script Work Unit Tracker | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1219SS | 1222
5254 | 1221 | Future Task |  |  | WP423 | Jarad Hermann |  | Create, Review and Confirm Performance Test Scripts | 20 hrs | 105 days | 2024-12-02 | 2025-04-30 | 1219SS | 1222
5208 | 1222 | Future Task |  |  | WP423 | Jarad Hermann | Submit | WP WP423 - Performance Test Scripts - Submit | 0 hrs | 0 days | 2025-04-30 | 2025-04-30 | 122112191220 | 1223
5209 | 1223 | Future Task |  |  | WP423 | Jarad Hermann | Review | WP WP423 - Performance Test Scripts - Collaborative Review & Update | 4 hrs | 10 days | 2025-05-01 | 2025-05-14 | 1222 | 1224
5210 | 1224 | Future Task |  |  | WP423 | Jarad Hermann | Review | WP WP423 - Performance Test Scripts - Final Review & Edits | 4 hrs | 5 days | 2025-05-15 | 2025-05-21 | 1223 | 1225
5211 | 1225 | Future Task |  |  | WP423 | Jarad Hermann | Approve | WP WP423 - Performance Test Scripts - Approve | 0 hrs | 0 days | 2025-05-21 | 2025-05-21 | 1224 | 965FS-14 days
5212 | 1226 | Future Task |  |  | WP424 | Jarad Hermann |  | WP424 - Penetration Test Scripts/Scenarios | 108 hrs | 97 days | 2024-10-30 | 2025-03-21
5213 | 1227 | Future Task |  |  | WP424 | Jarad Hermann | Create | WPED WP424 - Penetration Test Scripts/Scenarios - Create | 16 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1191SS | 1228
5214 | 1228 | Future Task |  |  | WP424 | Jarad Hermann | Submit | WPED WP424 - Penetration Test Scripts/Scenarios - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 1227 | 1229
5215 | 1229 | Future Task |  |  | WP424 | Jarad Hermann | Review | WPED WP424 - Penetration Test Scripts/Scenarios - Review | 20 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1228 | 1230
5216 | 1230 | Future Task |  |  | WP424 | Jarad Hermann | Approve | WPED WP424 - Penetration Test Scripts/Scenarios - Approve | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1229 | 1231
5255 | 1231 | Future Task |  |  | WP424 | Jarad Hermann |  | Finalize Penetration Test Scripts Inventory | 20 hrs | 62 days | 2024-12-02 | 2025-02-28 | 1230 | 1232SS
5256 | 1232 | Future Task |  |  | WP424 | Jarad Hermann |  | Create, review, and confirm Penetration Test Scripts/Scenarios | 20 hrs | 62 days | 2024-12-02 | 2025-02-28 | 1231SS | 1233
5217 | 1233 | Future Task |  |  | WP424 | Jarad Hermann | Submit | WP WP424 - Penetration Test Scripts/Scenarios - Submit | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 1232 | 1234
5218 | 1234 | Future Task |  |  | WP424 | Jarad Hermann | Review | WP WP424 - Penetration Test Scripts/Scenarios - Collaborative Review & Update | 16 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1233 | 1235
5219 | 1235 | Future Task |  |  | WP424 | Jarad Hermann | Review | WP WP424 - Penetration Test Scripts/Scenarios - Final Review & Edits | 16 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1234 | 1236
5220 | 1236 | Future Task |  |  | WP424 | Jarad Hermann | Approve | WP WP424 - Penetration Test Scripts/Scenarios - Approve | 0 hrs | 0 days | 2025-03-21 | 2025-03-21 | 1235 | 947FS+29 days
5299 | 1237 | Future Task |  |  | I-WP127 | Angie Robertson |  | I-WP127 - User Acceptance Testing Plan | 61 hrs | 77 days | 2024-08-05 | 2024-11-21
5300 | 1238 | Future Task |  |  | I-WP127 | Angie Robertson | Create | WPED - I-WP127 - User Acceptance Testing Plan - Create | 4 hrs | 10 days | 2024-08-05 | 2024-08-16 | 1 | 1239
5301 | 1239 | Future Task |  |  | I-WP127 | Angie Robertson | Submit | WPED - I-WP127 - User Acceptance Testing Plan - Submit | 0 hrs | 0 days | 2024-08-16 | 2024-08-16 | 1238 | 1240
5302 | 1240 | Future Task |  |  | I-WP127 | Angie Robertson | Review | WPED - I-WP127 - User Acceptance Testing Plan - Collaborative Review and Update | 17 hrs | 10 days | 2024-08-19 | 2024-08-30 | 1239 | 1241
5303 | 1241 | Future Task |  |  | I-WP127 | Angie Robertson | Approve | WPED - I-WP127 - User Acceptance Testing Plan - Approve | 0 hrs | 0 days | 2024-08-30 | 2024-08-30 | 1240 | 1242
5310 | 1242 | Future Task |  |  | I-WP127 | Angie Robertson |  | Create User Acceptance Plan | 10 hrs | 40 days | 2024-09-03 | 2024-10-28 | 1241 | 1243
5304 | 1243 | Future Task |  |  | I-WP127 | Angie Robertson | Submit | I-WP127 - User Acceptance Testing Plan - Submit | 0 hrs | 0 days | 2024-10-28 | 2024-10-28 | 1242 | 1244
5305 | 1244 | Future Task |  |  | I-WP127 | Angie Robertson | Review | I-WP127 - User Acceptance Testing Plan - Dept QC | 8 hrs | 1 day | 2024-10-29 | 2024-10-29 | 1243 | 1245
5306 | 1245 | Future Task |  |  | I-WP127 | Angie Robertson | Review | I-WP127 - User Acceptance Testing Plan - Collaborative Review and Update | 10 hrs | 10 days | 2024-10-30 | 2024-11-13 | 1244 | 1246
5307 | 1246 | Future Task |  |  | I-WP127 | Angie Robertson | Review | I-WP127 - User Acceptance Testing Plan - Style Guide Review | 2 hrs | 1 day | 2024-11-14 | 2024-11-14 | 1245 | 1247
5308 | 1247 | Future Task |  |  | I-WP127 | Angie Robertson | Review | I-WP127 - User Acceptance Testing Plan - Final Review and Update | 10 hrs | 5 days | 2024-11-15 | 2024-11-21 | 1246 | 1248
5309 | 1248 | Future Task |  |  | I-WP127 | Angie Robertson | Approve | I-WP127 - User Acceptance Testing Plan - Approve | 0 hrs | 0 days | 2024-11-21 | 2024-11-21 | 1247 | 1250,566FS+46 days,585
3967 | 1249 | Future Task | [5 empty] | UAT | 1 hr | 163 days | 2025-04-01 | 2025-11-19
4002 | 1250 | Future Task |  |  | UAT | Matt Breeding |  | UAT Testing | 1 hr | 163 days | 2025-04-01 | 2025-11-19 | 17075691248 | 1738,1791SS+30 days
3772 | 1251 | Future Task | [5 empty] | Deploy | 1,806 hrs | 548 days | 2023-12-01 | 2026-02-04
7156 | 1252 | Future Task | Yes |  | SG5 | Jimmy Cox | Milestone | Stage Gate 5: Deployment Readiness | 0 hrs | 0 days | 2025-12-12 | 2025-12-12 | 7.2078e+32 |  | December 17, 2025 - ESC
7157 | 1253 | Future Task | Yes |  | SG6 | Jimmy Cox | Milestone | Stage Gate 6: Confirm Deployment | 0 hrs | 0 days | 2025-12-19 | 2025-12-19 | 137313881339 | 1254 | 2025-12-30
7158 | 1254 | Future Task | Yes |  | SG7 | Jimmy Cox | Milestone | Stage Gate 7: Go-Live | 0 hrs | 0 days | 2025-12-19 | 2025-12-19 | 1253 |  | Janaury 6, 2026
5311 | 1255 | Future Task |  |  | D645 | Mary Punty |  | D645 - Updated Deployment Strategy | 265 hrs | 105 days | 2023-12-01 | 2024-04-30
5312 | 1256 | Future Task |  |  | D645 | Mary Punty | Create | DED D645 - Updated Deployment Strategy - Create | 16 hrs | 10 days | 2023-12-01 | 2023-12-14 | 1 | 1257
5313 | 1257 | Future Task |  |  | D645 | Mary Punty | Submit | DED D645 - Updated Deployment Strategy - Submit | 0 hrs | 0 days | 2023-12-14 | 2023-12-14 | 1256 | 1258
5314 | 1258 | Future Task |  |  | D645 | Mary Punty | Review | DED D645 - Updated Deployment Strategy - Collaborative Review | 20 hrs | 10 days | 2023-12-15 | 2023-12-29 | 1257 | 1259
5315 | 1259 | Future Task |  |  | D645 | Mary Punty | Approve | DED D645 - Updated Deployment Strategy - Approve | 0 hrs | 0 days | 2023-12-29 | 2023-12-29 | 1258 | 1260
5339 | 1260 | Future Task |  |  | D645 | Mary Punty |  | Document assumptions about deployment | 20 hrs | 9 days | 2024-01-02 | 2024-01-12 | 1259 | 1261
5340 | 1261 | Future Task |  |  | D645 | Mary Punty |  | Create Deployment Kickoff Presentation | 20 hrs | 9 days | 2024-01-16 | 2024-01-26 | 1260 | 1262
5341 | 1262 | Future Task |  |  | D645 | Mary Punty |  | Review Deployment Kickoff Presentation | 20 hrs | 5 days | 2024-01-29 | 2024-02-02 | 1261 | 1263
5342 | 1263 | Future Task |  |  | D645 | Mary Punty |  | Describe Deployment Calendar | 20 hrs | 10 days | 2024-02-05 | 2024-02-16 | 1262 | 1264
5343 | 1264 | Future Task |  |  | D645 | Mary Punty |  | Review Deployment Calendar | 20 hrs | 5 days | 2024-02-19 | 2024-02-23 | 1263 | 1265
5344 | 1265 | Future Task |  |  | D645 | Mary Punty |  | Describe Cutover Checklist | 20 hrs | 10 days | 2024-02-26 | 2024-03-08 | 1264 | 1266
5345 | 1266 | Future Task |  |  | D645 | Mary Punty |  | Review Cutover Checklist | 20 hrs | 10 days | 2024-03-11 | 2024-03-22 | 1265 | 1267
5346 | 1267 | Future Task |  |  | D645 | Mary Punty |  | Finalize Draft - Deployment Strategy | 20 hrs | 5 days | 2024-03-25 | 2024-03-29 | 1266 | 1268
5347 | 1268 | Future Task |  |  | D645 | Mary Punty |  | Review Draft - Deployment Strategy | 20 hrs | 5 days | 2024-04-01 | 2024-04-05 | 1267 | 1269
5316 | 1269 | Future Task |  |  | D645 | Mary Punty | Submit | DEL D645 - Updated Deployment Strategy - Draft Submission | 0 hrs | 0 days | 2024-04-05 | 2024-04-05 | 1268 | 1270
5317 | 1270 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2024-04-08 | 2024-04-12 | 1269 | 1271
5318 | 1271 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Style Guide Review | 1 hr | 1 day | 2024-04-15 | 2024-04-15 | 1270 | 1272
5319 | 1272 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Final Collaborative Review | 16 hrs | 5 days | 2024-04-16 | 2024-04-22 | 1271 | 1273
5320 | 1273 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Accenture QC | 4 hrs | 2 days | 2024-04-23 | 2024-04-24 | 1272 | 1274
5321 | 1274 | Future Task |  |  | D645 | Mary Punty | Submit | DEL D645 - Updated Deployment Strategy - Submit | 0 hrs | 0 days | 2024-04-24 | 2024-04-24 | 1273 | 1275
5322 | 1275 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Department QC | 4 hrs | 1 day | 2024-04-25 | 2024-04-25 | 1274 | 1276
5323 | 1276 | Future Task |  |  | D645 | Mary Punty | Review | DEL D645 - Updated Deployment Strategy - Contract Manager Review | 8 hrs | 3 days | 2024-04-26 | 2024-04-30 | 1275 | 12771279
5324 | 1277 | Future Task |  |  | D645 | Mary Punty | Accept | DEL D645 - Updated Deployment Strategy - Accept | 0 hrs | 0 days | 2024-04-30 | 2024-04-30 | 1276 |  | 2024-04-01
5325 | 1278 | Future Task | Yes |  | D658 | Mary Punty |  | D658 - Develop the Deployment and Contingency Plan | 498 hrs | 125 days | 2024-09-30 | 2025-03-31
5326 | 1279 | Future Task |  |  | D658 | Mary Punty | Create | DED D658 - Develop the Deployment and Contingency Plan - Create | 16 hrs | 10 days | 2024-09-30 | 2024-10-11 | 1276 | 1280
5327 | 1280 | Future Task |  |  | D658 | Mary Punty | Submit | DED D658 - Develop the Deployment and Contingency Plan - Submit | 0 hrs | 0 days | 2024-10-11 | 2024-10-11 | 1279 | 1281
5328 | 1281 | Future Task |  |  | D658 | Mary Punty | Review | DED D658 - Develop the Deployment and Contingency Plan - Collaborative Review | 20 hrs | 10 days | 2024-10-14 | 2024-10-25 | 1280 | 1282
5329 | 1282 | Future Task |  |  | D658 | Mary Punty | Approve | DED D658 - Develop the Deployment and Contingency Plan - Approve | 0 hrs | 0 days | 2024-10-25 | 2024-10-25 | 1281 | 1283
5348 | 1283 | Future Task |  |  | D658 | Mary Punty |  | Create Deployment and Contingency Plan pitch deck | 18 hrs | 9 days | 2024-10-28 | 2024-11-07 | 1282 | 1284
5349 | 1284 | Future Task |  |  | D658 | Mary Punty |  | Review Deployment and Contingency Plan pitch deck | 40 hrs | 4 days | 2024-11-08 | 2024-11-14 | 1283 | 1285FS+8 days,1289
5350 | 1285 | Future Task |  |  | D658 | Mary Punty |  | Prepare materials for Dec Sponsor Meeting and Review | 25 hrs | 5 days | 2024-11-27 | 2024-12-05 | 1284FS+8 days | 1286
5351 | 1286 | Future Task |  |  | D658 | Mary Punty |  | Plan for and hold December Sponsor Meeting | 25 hrs | 5 days | 2024-12-06 | 2024-12-12 | 1285 | 1287FS+11 days
5352 | 1287 | Future Task |  |  | D658 | Mary Punty |  | Gather Deployment and Contingency Plan materials for January ESC Meeting | 35 hrs | 7 days | 2024-12-31 | 2025-01-09 | 1286FS+11 days | 1288,1293SS
5353 | 1288 | Future Task |  |  | D658 | Mary Punty |  | Review Deployment and Contingency Plan materials for January ESC Meeting | 25 hrs | 5 days | 2025-01-10 | 2025-01-16 | 1287 | 1297
5354 | 1289 | Future Task |  |  | D658 | Mary Punty |  | Identify and document deployment and post-implementation support activities | 20 hrs | 8 days | 2024-11-15 | 2024-11-26 | 1284 | 1290
5355 | 1290 | Future Task |  |  | D658 | Mary Punty |  | Review and document deployment and post-implementation support activities | 25 hrs | 5 days | 2024-11-27 | 2024-12-05 | 1289 | 1291
5356 | 1291 | Future Task |  |  | D658 | Mary Punty |  | Identify and document timing of cutover activities | 25 hrs | 5 days | 2024-12-06 | 2024-12-12 | 1290 | 1292
5357 | 1292 | Future Task |  |  | D658 | Mary Punty |  | Review and document timing of cutover activities | 25 hrs | 5 days | 2024-12-13 | 2024-12-19 | 1291 | 1293
5358 | 1293 | Future Task |  |  | D658 | Mary Punty |  | Identify and document contingency scenarios | 20 hrs | 7 days | 2024-12-31 | 2025-01-09 | 1287SS,1292 | 1294
5359 | 1294 | Future Task |  |  | D658 | Mary Punty |  | Review contingency scenarios | 25 hrs | 5 days | 2025-01-10 | 2025-01-16 | 1293 | 1295
5360 | 1295 | Future Task |  |  | D658 | Mary Punty |  | Define and document the approach to revert changes | 20 hrs | 4 days | 2025-01-17 | 2025-01-23 | 1294 | 1296
5361 | 1296 | Future Task |  |  | D658 | Mary Punty |  | Review the approach to revert changes | 25 hrs | 5 days | 2025-01-24 | 2025-01-30 | 1295 | 1297
5362 | 1297 | Future Task |  |  | D658 | Mary Punty |  | Gather Deployment and Contingency Plan materials for February ESC Meeting | 25 hrs | 5 days | 2025-01-31 | 2025-02-06 | 12961288 | 1298
5363 | 1298 | Future Task |  |  | D658 | Mary Punty |  | Review Deployment and Contingency Plan materials for February ESC Meeting | 15 hrs | 3 days | 2025-02-07 | 2025-02-11 | 1297 | 1299FS+12 days
5364 | 1299 | Future Task |  |  | D658 | Mary Punty |  | Confirm approach to Deployment and Contingency | 20 hrs | 5 days | 2025-02-28 | 2025-03-06 | 1298FS+12 days | 1300
5330 | 1300 | Future Task |  |  | D658 | Mary Punty | Submit | DEL D658 - Develop the Deployment and Contingency Plan - Draft Submission | 0 hrs | 0 days | 2025-03-06 | 2025-03-06 | 1299 | 1301
5331 | 1301 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2025-03-07 | 2025-03-13 | 1300 | 1302
5332 | 1302 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Style Guide Review | 1 hr | 1 day | 2025-03-14 | 2025-03-14 | 1301 | 1303
5333 | 1303 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Final Collaborative Review | 16 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1302 | 1304
5334 | 1304 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Accenture QC | 4 hrs | 2 days | 2025-03-24 | 2025-03-25 | 1303 | 1305
5335 | 1305 | Future Task |  |  | D658 | Mary Punty | Submit | DEL D658 - Develop the Deployment and Contingency Plan - Submit | 0 hrs | 0 days | 2025-03-25 | 2025-03-25 | 1304 | 1306
5336 | 1306 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Department QC | 4 hrs | 1 day | 2025-03-26 | 2025-03-26 | 1305 | 1307
5337 | 1307 | Future Task |  |  | D658 | Mary Punty | Review | DEL D658 - Develop the Deployment and Contingency Plan - Contract Manager Review | 8 hrs | 3 days | 2025-03-27 | 2025-03-31 | 1306 | 1308
5338 | 1308 | Future Task |  |  | D658 | Mary Punty | Accept | DEL D658 - Develop the Deployment and Contingency Plan - Accept | 0 hrs | 0 days | 2025-03-31 | 2025-03-31 | 1307 | 1252 | 2025-03-01
5365 | 1309 | Future Task | Yes |  | D678 | Bryan Sohayda |  | D678 - Final Known Issues & Enhancements Lists | 350 hrs | 65 days | 2025-09-03 | 2025-12-05
5366 | 1310 | Future Task |  |  | D678 | Bryan Sohayda | Create | DED D678 - Final Known Issues & Enhancements Lists - Create | 16 hrs | 10 days | 2025-09-03 | 2025-09-16 | 1 | 1311
5367 | 1311 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DED D678 - Final Known Issues & Enhancements Lists - Submit | 0 hrs | 0 days | 2025-09-16 | 2025-09-16 | 1310 | 1312
5368 | 1312 | Future Task |  |  | D678 | Bryan Sohayda | Review | DED D678 - Final Known Issues & Enhancements Lists - Collaborative Review | 20 hrs | 10 days | 2025-09-17 | 2025-09-30 | 1311 | 1313
5369 | 1313 | Future Task |  |  | D678 | Bryan Sohayda | Approve | DED D678 - Final Known Issues & Enhancements Lists - Approve | 0 hrs | 0 days | 2025-09-30 | 2025-09-30 | 1312 | 1314
5393 | 1314 | Future Task |  |  | D678 | Bryan Sohayda |  | Initial Known Issues & Enhancements Lists | 20 hrs | 22 days | 2025-10-01 | 2025-10-30 | 1313 | 1315SS
5394 | 1315 | Future Task |  |  | D678 | Bryan Sohayda |  | Review Open SIRs - Candidates for Known Issues List | 25 hrs | 5 days | 2025-10-01 | 2025-10-07 | 1314SS | 1316,1317SS
5395 | 1316 | Future Task |  |  | D678 | Bryan Sohayda |  | Finalize Open SIRs - Candidates for Known Issues List | 24 hrs | 4 days | 2025-10-08 | 2025-10-13 | 1315 | 1318SS
5396 | 1317 | Future Task |  |  | D678 | Bryan Sohayda |  | Review Open SIRs - Candidates for Known Enhancements List | 30 hrs | 5 days | 2025-10-01 | 2025-10-07 | 1315SS | 1319
5397 | 1318 | Future Task |  |  | D678 | Bryan Sohayda |  | Finalize Open SIRs - Candidates for Known Enhancements List | 20 hrs | 4 days | 2025-10-08 | 2025-10-13 | 1316SS | 1319
5398 | 1319 | Future Task |  |  | D678 | Bryan Sohayda |  | Confirm Agreed Upon Known Issues | 30 hrs | 5 days | 2025-10-14 | 2025-10-20 | 13181317 | 1320SS,1321SS
5399 | 1320 | Future Task |  |  | D678 | Bryan Sohayda |  | Confirm Agreed Upon Known Enhancements | 30 hrs | 5 days | 2025-10-14 | 2025-10-20 | 1319SS | 1323
5400 | 1321 | Future Task |  |  | D678 | Bryan Sohayda |  | Create DEL Draft - Wrapper Document and Known Issues/Enhancements Lists | 20 hrs | 5 days | 2025-10-14 | 2025-10-20 | 1319SS | 1322
5401 | 1322 | Future Task |  |  | D678 | Bryan Sohayda |  | Review DEL Draft - Wrapper Document and Known Issues/Enhancements Lists | 48 hrs | 8 days | 2025-10-21 | 2025-10-30 | 1321 | 1323
5370 | 1323 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DEL D678 - Final Known Issues & Enhancements Lists - Draft Submission | 0 hrs | 0 days | 2025-10-30 | 2025-10-30 | 13221320 | 1324
5371 | 1324 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2025-10-31 | 2025-11-06 | 1323 | 1325
5372 | 1325 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Style Guide Review | 1 hr | 1 day | 2025-11-07 | 2025-11-07 | 1324 | 1326
5373 | 1326 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Final Collaborative Review | 16 hrs | 5 days | 2025-11-10 | 2025-11-17 | 1325 | 1327
5374 | 1327 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Accenture QC | 4 hrs | 2 days | 2025-11-18 | 2025-11-19 | 1326 | 1328
5375 | 1328 | Future Task |  |  | D678 | Bryan Sohayda | Submit | DEL D678 - Final Known Issues & Enhancements Lists - Submit | 0 hrs | 0 days | 2025-11-19 | 2025-11-19 | 1327 | 1329
5376 | 1329 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Department QC | 4 hrs | 1 day | 2025-11-20 | 2025-11-20 | 1328 | 1330
5377 | 1330 | Future Task |  |  | D678 | Bryan Sohayda | Review | DEL D678 - Final Known Issues & Enhancements Lists - Contract Manager Review | 8 hrs | 3 days | 2025-11-21 | 2025-11-25 | 1329 | 1331
5378 | 1331 | Future Task |  |  | D678 | Bryan Sohayda | Accept | DEL D678 - Final Known Issues & Enhancements Lists - Accept | 0 hrs | 0 days | 2025-11-25 | 2025-11-25 | 1330 | 1332FS+1 day,1252 | 2025-12-01
5407 | 1332 | Future Task |  |  | D678 | Bryan Sohayda |  | Refresh Known Issues/Enhancements List to Prep for Stage Gate 5 | 18 hrs | 5 days | 2025-12-01 | 2025-12-05 | 1331FS+1 day
5379 | 1333 | Future Task | Maybe |  | D679 | Stacey Terry |  | D679 - Go-Live of Financials and Payroll Waves | 169 hrs | 60 days | 2025-11-05 | 2026-02-04
5380 | 1334 | Future Task |  |  | D679 | Stacey Terry | Create | DED D679 - Go-Live of Financials and Payroll Waves - Create | 16 hrs | 10 days | 2025-11-05 | 2025-11-19 | 1 | 1335
5381 | 1335 | Future Task |  |  | D679 | Stacey Terry | Submit | DED D679 - Go-Live of Financials and Payroll Waves - Submit | 0 hrs | 0 days | 2025-11-19 | 2025-11-19 | 1334 | 1336
5382 | 1336 | Future Task |  |  | D679 | Stacey Terry | Review | DED D679 - Go-Live of Financials and Payroll Waves - Collaborative Review | 28 hrs | 10 days | 2025-11-20 | 2025-12-05 | 1335 | 1337
5383 | 1337 | Future Task |  |  | D679 | Stacey Terry | Approve | DED D679 - Go-Live of Financials and Payroll Waves - Approve | 0 hrs | 0 days | 2025-12-05 | 2025-12-05 | 1336 | 1338
5403 | 1338 | Future Task |  |  | D679 | Stacey Terry |  | Go-Live of Financials and Payroll Waves | 15 hrs | 5 days | 2025-12-08 | 2025-12-12 | 1337 | 1339
5404 | 1339 | Future Task |  |  | D679 | Stacey Terry |  | Document Go-Live Applications Listing | 15 hrs | 5 days | 2025-12-15 | 2025-12-19 | 1338 | 1340FS+8 days,1253
5405 | 1340 | Future Task |  |  | D679 | Stacey Terry |  | Document Go-Live Tasks completed | 15 hrs | 5 days | 2026-01-05 | 2026-01-09 | 1339FS+8 days | 1341SS
5406 | 1341 | Future Task |  |  | D679 | Stacey Terry |  | Document Go-List of Agencies Participated | 15 hrs | 5 days | 2026-01-05 | 2026-01-09 | 1340SS | 1342
5384 | 1342 | Future Task |  |  | D679 | Stacey Terry | Submit | DEL D679 - Go-Live of Financials and Payroll Waves - Draft Submission | 0 hrs | 0 days | 2026-01-09 | 2026-01-09 | 1341 | 1343
5385 | 1343 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Pre-Submission Collaborative Review | 24 hrs | 5 days | 2026-01-12 | 2026-01-16 | 1342 | 1344
5386 | 1344 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Style Guide Review | 1 hr | 1 day | 2026-01-20 | 2026-01-20 | 1343 | 1345
5387 | 1345 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Final Collaborative Review | 24 hrs | 5 days | 2026-01-21 | 2026-01-27 | 1344 | 1346
5388 | 1346 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Accenture QC | 4 hrs | 2 days | 2026-01-28 | 2026-01-29 | 1345 | 1347
5389 | 1347 | Future Task |  |  | D679 | Stacey Terry | Submit | DEL D679 - Go-Live of Financials and Payroll Waves - Submit | 0 hrs | 0 days | 2026-01-29 | 2026-01-29 | 1346 | 1348
5390 | 1348 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Department QC | 4 hrs | 1 day | 2026-01-30 | 2026-01-30 | 1347 | 1349
5391 | 1349 | Future Task |  |  | D679 | Stacey Terry | Review | DEL D679 - Go-Live of Financials and Payroll Waves - Contract Manager Review | 8 hrs | 3 days | 2026-02-02 | 2026-02-04 | 1348 | 1350
5392 | 1350 | Future Task |  |  | D679 | Stacey Terry | Accept | DEL D679 - Go-Live of Financials and Payroll Waves - Accept | 0 hrs | 0 days | 2026-02-04 | 2026-02-04 | 1349 |  | 2026-01-01
6739 | 1351 | Future Task |  |  | WP425 | Bryan Sohayda |  | WP425 - Production Support Operations Plan | 356 hrs | 107 days | 2024-11-14 | 2025-04-18
6740 | 1352 | Future Task |  |  | WP425 | Bryan Sohayda | Create | WPED WP425 - Production Support Operations Plan - Create | 8 hrs | 10 days | 2024-11-14 | 2024-11-27 | 1 | 1353
6741 | 1353 | Future Task |  |  | WP425 | Bryan Sohayda | Submit | WPED WP425 - Production Support Operations Plan - Submit | 0 hrs | 0 days | 2024-11-27 | 2024-11-27 | 1352 | 1354
6742 | 1354 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WPED WP425 - Production Support Operations Plan - Review | 16 hrs | 10 days | 2024-12-02 | 2024-12-13 | 1353 | 1355
6743 | 1355 | Future Task |  |  | WP425 | Bryan Sohayda | Approve | WPED WP425 - Production Support Operations Plan - Approve | 0 hrs | 0 days | 2024-12-13 | 2024-12-13 | 1354 | 1356
6744 | 1356 | Future Task |  |  | WP425 | Bryan Sohayda |  | Update Production Support Operations Plan | 20 hrs | 72 days | 2024-12-16 | 2025-03-28 | 1355 | 1357SS
6745 | 1357 | Future Task |  |  | WP425 | Bryan Sohayda |  | Introduction, Overview, Collab taken with partners, team R&R | 20 hrs | 5 days | 2024-12-16 | 2024-12-20 | 1356SS | 1358FS+8 days
6746 | 1358 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document Production Support services provided | 20 hrs | 5 days | 2025-01-06 | 2025-01-10 | 1357FS+8 days | 1359
6747 | 1359 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review and provide feedback on Production Support Services Provided draft | 20 hrs | 5 days | 2025-01-13 | 2025-01-17 | 1358 | 1360
6748 | 1360 | Future Task |  |  | WP425 | Bryan Sohayda |  | Create Maintenance Calendar template | 48 hrs | 4 days | 2025-01-21 | 2025-01-24 | 1359 | 1361
6749 | 1361 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review Maintenance Calendar template | 20 hrs | 5 days | 2025-01-27 | 2025-01-31 | 1360 | 1362
6750 | 1362 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document production support business processes and tools list | 20 hrs | 5 days | 2025-02-03 | 2025-02-07 | 1361 | 1363
6751 | 1363 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review and provide feedback on Production Support business processes and tools list draft | 20 hrs | 5 days | 2025-02-10 | 2025-02-14 | 1362 | 1364
6752 | 1364 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document production support schedule of activities | 20 hrs | 5 days | 2025-02-17 | 2025-02-21 | 1363 | 1365
6753 | 1365 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review and provide feedback on Production Support schedule of activities draft | 20 hrs | 5 days | 2025-02-24 | 2025-02-28 | 1364 | 1366
6754 | 1366 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document production support performance expectations | 20 hrs | 5 days | 2025-03-03 | 2025-03-07 | 1365 | 1367
6755 | 1367 | Future Task |  |  | WP425 | Bryan Sohayda |  | Review and provide feedback on Production Support performance expectations draft | 20 hrs | 5 days | 2025-03-10 | 2025-03-14 | 1366 | 1368
6756 | 1368 | Future Task |  |  | WP425 | Bryan Sohayda |  | Define and document production support team roles, responsibilities, and staffing | 20 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1367 | 1369
6757 | 1369 | Future Task |  |  | WP425 | Bryan Sohayda |  | Full walkthrough of Production Support Operations Plan through facilitated meetings | 20 hrs | 5 days | 2025-03-24 | 2025-03-28 | 1368 | 1370
6758 | 1370 | Future Task |  |  | WP425 | Bryan Sohayda | Submit | WP WP425 - Production Support Operations Plan - Submit | 0 hrs | 0 days | 2025-03-28 | 2025-03-28 | 1369 | 1371
6759 | 1371 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WP WP425 - Production Support Operations Plan - Collaborative Review & Update | 12 hrs | 10 days | 2025-03-31 | 2025-04-11 | 1370 | 1372
6760 | 1372 | Future Task |  |  | WP425 | Bryan Sohayda | Review | WP WP425 - Production Support Operations Plan - Final Review & Edits | 12 hrs | 5 days | 2025-04-14 | 2025-04-18 | 1371 | 1373
6761 | 1373 | Future Task |  |  | WP425 | Bryan Sohayda | Approve | WP WP425 - Production Support Operations Plan - Approve | 0 hrs | 0 days | 2025-04-18 | 2025-04-18 | 1372 | 1253 | 2025-04-01
6762 | 1374 | Future Task |  |  | WP427 | Bryan Sohayda |  | WP427 - Production Support Application Configuration Management Plan | 168 hrs | 85 days | 2025-01-03 | 2025-05-02
6763 | 1375 | Future Task |  |  | WP427 | Bryan Sohayda | Create | WPED WP427 - Production Support Application Configuration Management Plan - Create | 8 hrs | 10 days | 2025-01-03 | 2025-01-16 | 1 | 1376
6764 | 1376 | Future Task |  |  | WP427 | Bryan Sohayda | Submit | WPED WP427 - Production Support Application Configuration Management Plan - Submit | 0 hrs | 0 days | 2025-01-16 | 2025-01-16 | 1375 | 1377
6765 | 1377 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WPED WP427 - Production Support Application Configuration Management Plan - Review | 16 hrs | 10 days | 2025-01-17 | 2025-01-31 | 1376 | 1378
6766 | 1378 | Future Task |  |  | WP427 | Bryan Sohayda | Approve | WPED WP427 - Production Support Application Configuration Management Plan - Approve | 0 hrs | 0 days | 2025-01-31 | 2025-01-31 | 1377 | 1379
6767 | 1379 | Future Task |  |  | WP427 | Bryan Sohayda |  | Updated Configuration Management Processes for Release and Maintenance | 20 hrs | 50 days | 2025-02-03 | 2025-04-11 | 1378 | 1380SS,1385,1381SS+10 days
6768 | 1380 | Future Task |  |  | WP427 | Bryan Sohayda |  | Define and Document Application Configuration Management Processes for Release and Maintenance | 20 hrs | 10 days | 2025-02-03 | 2025-02-14 | 1379SS | 1381
6769 | 1381 | Future Task |  |  | WP427 | Bryan Sohayda |  | Review and confirm Application and Infrastructure Configuration Management Processes for Release and Maintenance | 20 hrs | 5 days | 2025-02-17 | 2025-02-21 | 1379SS+10 days,1380 | 1382
6770 | 1382 | Future Task |  |  | WP427 | Bryan Sohayda |  | Define and document System Configuration Control Process Steps and Diagram | 20 hrs | 5 days | 2025-02-24 | 2025-02-28 | 1381 | 1383
6771 | 1383 | Future Task |  |  | WP427 | Bryan Sohayda |  | Review System Configuration Control Process Steps and Diagram | 20 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1382 | 1384FS+10 days
6772 | 1384 | Future Task |  |  | WP427 | Bryan Sohayda |  | Full draft review pre-submission | 20 hrs | 10 days | 2025-03-31 | 2025-04-11 | 1383FS+10 days | 1385
6773 | 1385 | Future Task |  |  | WP427 | Bryan Sohayda | Submit | WP WP427 - Production Support Application Configuration Management Plan - Submit | 0 hrs | 0 days | 2025-04-11 | 2025-04-11 | 13791384 | 1386
6774 | 1386 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WP WP427 - Production Support Application Configuration Management Plan - Collaborative Review & Update | 12 hrs | 10 days | 2025-04-14 | 2025-04-25 | 1385 | 1387
6775 | 1387 | Future Task |  |  | WP427 | Bryan Sohayda | Review | WP WP427 - Production Support Application Configuration Management Plan - Final Review & Edits | 12 hrs | 5 days | 2025-04-28 | 2025-05-02 | 1386 | 1388
6776 | 1388 | Future Task |  |  | WP427 | Bryan Sohayda | Approve | WP WP427 - Production Support Application Configuration Management Plan - Approve | 0 hrs | 0 days | 2025-05-02 | 2025-05-02 | 1387 | 1253 | 2025-04-01
2953 | 1389 | Late | [5 empty] | Stakeholder Engagement | 3,213 hrs | 936 days | 2023-05-08 | 2027-01-26
2972 | 1390 | Late | [5 empty] | Training | 2,336 hrs | 928 days | 2023-05-18 | 2027-01-26
6906 | 1391 | Late |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Data Inventory for Financials and Payroll Wave | 105 hrs | 277 days | 2023-05-18 | 2024-06-21
6907 | 1392 | Late |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Data Inventory for Financials and Payroll Wave | 22 hrs | 277 days | 2023-05-18 | 2024-06-21
6908 | 1393 | Late |  |  | I-WP102 | Jennifer Reeves | Create | WPED - I-WP102 Data Inventory for Financials and Payroll Wave - Create | 2 hrs | 10 days | 2023-05-18 | 2023-06-01 | 1 | 1394
6909 | 1394 | Future Task |  |  | I-WP102 | Jennifer Reeves | Submit | WPED - I-WP102 Data Inventory for Financials and Payroll Wave - Submit | 0 hrs | 0 days | 2023-06-01 | 2023-06-01 | 1393 | 1395
6910 | 1395 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WPED - I-WP102 Data Inventory for Financials and Payroll Wave - Collaborative Review and Update | 8 hrs | 10 days | 2023-06-02 | 2023-06-15 | 1394 | 1396
6911 | 1396 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | WPED - I-WP102 Data Inventory for Financials and Payroll Wave - Approve | 0 hrs | 0 days | 2023-06-15 | 2023-06-15 | 1395 | 1405
6912 | 1397 | Future Task |  |  | I-WP102 | Jennifer Reeves | Milestone | WP - IWP102 Data Inventory for Financials and Payroll Wave - Submit | 0 hrs | 0 days | 2024-05-29 | 2024-05-29 | 1436 | 1398
6913 | 1398 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP - IWP102 Data Inventory for Financials and Payroll Wave - Dept QC | 2 hrs | 1 day | 2024-05-30 | 2024-05-30 | 1397 | 1399
6914 | 1399 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP - IWP102 Data Inventory for Financials and Payroll Wave - Collaborative Review and Update | 7 hrs | 10 days | 2024-05-31 | 2024-06-13 | 1398 | 1400
6915 | 1400 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP - IWP102 Data Inventory for Financials and Payroll Wave - Style Guide Review | 1 hr | 1 day | 2024-06-14 | 2024-06-14 | 1399 | 1401
6916 | 1401 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | WP - IWP102 Data Inventory for Financials and Payroll Wave - Final Review and Update | 2 hrs | 5 days | 2024-06-17 | 2024-06-21 | 1400 | 1402
6917 | 1402 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | WP - IWP102 Data Inventory for Financials and Payroll Wave - Approve | 0 hrs | 0 days | 2024-06-21 | 2024-06-21 | 1401
6918 | 1403 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | Data Inventory for Financials and Payroll Wave | 83 hrs | 245 days | 2023-06-16 | 2024-06-05
6919 | 1404 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 1 - Data | 20 hrs | 45 days | 2023-06-16 | 2023-08-18
6920 | 1405 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create - Data Inventory Format | 7 hrs | 5 days | 2023-06-16 | 2023-06-22 | 1396 | 1406
6921 | 1406 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory Format | 5 hrs | 5 days | 2023-06-23 | 2023-06-29 | 1405 | 1407
6922 | 1407 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory Format | 1 hr | 5 days | 2023-06-30 | 2023-07-07 | 1406 | 1408
6923 | 1408 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | 2023-07-10 | 2023-07-28 | 1407 | 1409
6924 | 1409 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 15 days | 2023-07-31 | 2023-08-18 | 1408
6925 | 1410 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 2 - Data | 7 hrs | 20 days | 2023-10-09 | 2023-11-03
6926 | 1411 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | 2023-10-09 | 2023-10-27 | 57SS | 1412
6927 | 1412 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 5 days | 2023-10-30 | 2023-11-03 | 1411
6928 | 1413 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 3 - Data | 13 hrs | 25 days | 2024-01-11 | 2024-02-15
6929 | 1414 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 4 hrs | 15 days | 2024-01-11 | 2024-02-01 | 1 | 14151421
6930 | 1415 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 3 hrs | 5 days | 2024-02-02 | 2024-02-08 | 1414 | 14161422
6931 | 1416 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Functional Teams | 6 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1415 | 1418
6932 | 1417 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Update & Publish Data Inventory | 18 hrs | 25 days | 2024-02-02 | 2024-03-07
6933 | 1418 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 5 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1416 | 1419
6934 | 1419 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory | 1 hr | 5 days | 2024-02-23 | 2024-02-29 | 1418 | 1420
6935 | 1420 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Coordinate Knowledge Base Update | 2 hrs | 5 days | 2024-03-01 | 2024-03-07 | 1419
6936 | 1421 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create Communication for Data Inventory | 2 hrs | 5 days | 2024-02-02 | 2024-02-08 | 1414
6937 | 1422 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review for Communication for Data Inventory | 2 hrs | 9 days | 2024-02-09 | 2024-02-21 | 1415 | 1423
6938 | 1423 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Communication | 1 hr | 5 days | 2024-02-22 | 2024-02-28 | 1422 | 1424
6939 | 1424 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Publish Data Inventory | 4 hrs | 2 days | 2024-02-29 | 2024-03-01 | 1423 | 1425
6940 | 1425 | Future Task |  | RW-Communication | I-WP102 | Jennifer Reeves | Create | I-WP102 Share - Communication for Data Inventory | 1 hr | 2 days | 2024-03-04 | 2024-03-05 | 1424
6941 | 1426 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Segment 4 - Data | 11 hrs | 25 days | 2024-04-10 | 2024-05-14
6942 | 1427 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Update & Maintain - Data Inventory | 3 hrs | 15 days | 2024-04-10 | 2024-04-30 | 1 | 14281434
6943 | 1428 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Review - Data Inventory | 2 hrs | 5 days | 2024-05-01 | 2024-05-07 | 1427 | 1429
6944 | 1429 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 6 hrs | 5 days | 2024-05-08 | 2024-05-14 | 1428 | 1431
6945 | 1430 | Future Task |  |  | I-WP102 | Jennifer Reeves |  | I-WP102 Update & Publish Data Inventory | 14 hrs | 25 days | 2024-05-01 | 2024-06-05
6946 | 1431 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Data Inventory | 3 hrs | 5 days | 2024-05-15 | 2024-05-21 | 1429 | 1432
6947 | 1432 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Data Inventory | 2 hrs | 5 days | 2024-05-22 | 2024-05-29 | 1431 | 1433
6948 | 1433 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Coordinate Knowledge Base Update | 2 hrs | 5 days | 2024-05-30 | 2024-06-05 | 1432
6949 | 1434 | Future Task |  |  | I-WP102 | Jennifer Reeves | Create | I-WP102 Create Communication - Data Inventory | 2 hrs | 5 days | 2024-05-01 | 2024-05-07 | 1427 | 1435
6950 | 1435 | Future Task |  |  | I-WP102 | Jennifer Reeves | Review | I-WP102 Collaborative Review - Communication for Data Inventory | 2 hrs | 10 days | 2024-05-08 | 2024-05-21 | 1434 | 1436
6951 | 1436 | Future Task |  |  | I-WP102 | Jennifer Reeves | Approve | I-WP102 Approve - Communication for Data Inventory | 2 hrs | 5 days | 2024-05-22 | 2024-05-29 | 1435 | 13971437
6952 | 1437 | Future Task |  | RW-Communication | I-WP102 | Jennifer Reeves | Create | I-WP102 Share Communication for Data Inventory | 1 hr | 2 days | 2024-05-30 | 2024-05-31 | 1436
7039 | 1438 | Late |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Accounting Entry Inventory | 271 hrs | 285 days | 2023-05-18 | 2024-07-03
7040 | 1439 | Late |  |  | I-WP103 | Jennifer Reeves | Create | WPED - I-WP103 Accounting Entry Inventory - Create | 10 hrs | 10 days | 2023-05-18 | 2023-06-01 | 1 | 1440
7041 | 1440 | Future Task |  |  | I-WP103 | Jennifer Reeves | Submit | WPED - I-WP103 Accounting Entry Inventory - Submit | 0 hrs | 0 days | 2023-06-01 | 2023-06-01 | 1439 | 1441
7042 | 1441 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WPED - I-WP103 Accounting Entry Inventory - Collaborative Review and Update | 10 hrs | 10 days | 2023-06-02 | 2023-06-15 | 1440 | 1442
7043 | 1442 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | WPED - I-WP103 Accounting Entry Inventory - Approve | 0 hrs | 0 days | 2023-06-15 | 2023-06-15 | 1441 | 1451FS+37 days
7044 | 1443 | Future Task |  |  | I-WP103 | Jennifer Reeves | Submit | WP - IWP103 Accounting Entry Inventory - Submit | 0 hrs | 0 days | 2024-06-10 | 2024-06-10 | 1482 | 1444
7045 | 1444 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP - IWP103 Accounting Entry Inventory - Dept QC | 1 hr | 1 day | 2024-06-11 | 2024-06-11 | 1443 | 1445
7046 | 1445 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP - IWP103 Accounting Entry Inventory - Collaborative Review and Update | 10 hrs | 10 days | 2024-06-12 | 2024-06-25 | 1444 | 1446
7047 | 1446 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP - IWP103 Accounting Entry Inventory - Style Guide Review | 1 hr | 1 day | 2024-06-26 | 2024-06-26 | 1445 | 1447
7048 | 1447 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | WP - IWP103 Accounting Entry Inventory - Final Review and Update | 2 hrs | 5 days | 2024-06-27 | 2024-07-03 | 1446 | 1448
7049 | 1448 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | WP - IWP103 Accounting Entry Inventory - Approve | 0 hrs | 0 days | 2024-07-03 | 2024-07-03 | 1447
7050 | 1449 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | Accounting Entry Inventory | 237 hrs | 216 days | 2023-08-09 | 2024-06-17
7051 | 1450 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 1 | 48 hrs | 37 days | 2023-08-09 | 2023-09-29
7052 | 1451 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Accounting Entry Inventory Format | 10 hrs | 5 days | 2023-08-09 | 2023-08-15 | 1442FS+37 days | 1452
7053 | 1452 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory Format | 10 hrs | 6 days | 2023-08-16 | 2023-08-23 | 1451 | 1453
7054 | 1453 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory Format | 10 hrs | 5 days | 2023-08-24 | 2023-08-30 | 1452 | 1454
7055 | 1454 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 16 days | 2023-08-31 | 2023-09-22 | 1453,38 | 1455
7056 | 1455 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | 2023-09-25 | 2023-09-29 | 1454
7057 | 1456 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 2 | 18 hrs | 20 days | 2023-10-24 | 2023-11-21
7058 | 1457 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | 2023-10-24 | 2023-11-14 | 57 | 1458
7059 | 1458 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | 2023-11-15 | 2023-11-21 | 1457
7060 | 1459 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 3 | 28 hrs | 25 days | 2024-01-11 | 2024-02-15
7061 | 1460 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | 2024-01-11 | 2024-02-01 | 136SS | 14611467
7062 | 1461 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | 2024-02-02 | 2024-02-08 | 1460 | 1462
7063 | 1462 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Functional Teams | 10 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1461 | 1464
7064 | 1463 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Update & Publish Accounting Entry Inventory | 54 hrs | 25 days | 2024-02-02 | 2024-03-07
7065 | 1464 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Accounting Entry Inventory | 10 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1462 | 1465
7066 | 1465 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory | 2 hrs | 5 days | 2024-02-23 | 2024-02-29 | 1464 | 1466
7067 | 1466 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Coordinate Knowledge Base Update | 10 hrs | 5 days | 2024-03-01 | 2024-03-07 | 1465
7068 | 1467 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Communication for Accounting Entry Inventory | 10 hrs | 5 days | 2024-02-02 | 2024-02-08 | 1460 | 1468
7069 | 1468 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review for Communication for Accounting Entry Inventory | 10 hrs | 9 days | 2024-02-09 | 2024-02-21 | 1467 | 1469
7070 | 1469 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Communication for Accounting Entry Inventory | 10 hrs | 5 days | 2024-02-22 | 2024-02-28 | 1468 | 1470
7071 | 1470 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Publish - Accounting Entry Inventory | 1 hr | 2 days | 2024-02-29 | 2024-03-01 | 1469 | 1471
7072 | 1471 | Future Task |  | RW-Communication | I-WP103 | Jennifer Reeves | Create | I-WP103 Share - Communication for Accounting Entry Inventory | 1 hr | 2 days | 2024-03-04 | 2024-03-05 | 1470
7073 | 1472 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Segment 4 | 28 hrs | 25 days | 2024-04-22 | 2024-05-24
7074 | 1473 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Update & Maintain - Accounting Entry Inventory | 8 hrs | 15 days | 2024-04-22 | 2024-05-10 | 155SS | 14741480
7075 | 1474 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Review - Accounting Entry Inventory | 10 hrs | 5 days | 2024-05-13 | 2024-05-17 | 1473 | 1475
7076 | 1475 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Functional Teams | 10 hrs | 5 days | 2024-05-20 | 2024-05-24 | 1474 | 1477
7077 | 1476 | Future Task |  |  | I-WP103 | Jennifer Reeves |  | I-WP103 Update & Publish Accounting Entry Inventory | 61 hrs | 25 days | 2024-05-13 | 2024-06-17
7078 | 1477 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review -Accounting Entry Inventory | 10 hrs | 5 days | 2024-05-28 | 2024-06-03 | 1475 | 1478
7079 | 1478 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Accounting Entry Inventory | 10 hrs | 5 days | 2024-06-04 | 2024-06-10 | 1477 | 1479
7080 | 1479 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Coordinate Knowledge Base Update | 10 hrs | 5 days | 2024-06-11 | 2024-06-17 | 1478
7081 | 1480 | Future Task |  |  | I-WP103 | Jennifer Reeves | Create | I-WP103 Create - Communication for Accounting Entry Inventory | 10 hrs | 5 days | 2024-05-13 | 2024-05-17 | 1473 | 1481
7082 | 1481 | Future Task |  |  | I-WP103 | Jennifer Reeves | Review | I-WP103 Collaborative Review - Communication for Accounting Entry Inventory | 10 hrs | 10 days | 2024-05-20 | 2024-06-03 | 1480 | 1482
7083 | 1482 | Future Task |  |  | I-WP103 | Jennifer Reeves | Approve | I-WP103 Approve - Communication for Accounting Entry Inventory | 10 hrs | 5 days | 2024-06-04 | 2024-06-10 | 1481 | 14431483
7084 | 1483 | Future Task |  | RW-Communication | I-WP103 | Jennifer Reeves | Create | I-WP103 Share Communication for Accounting Entry Inventory | 1 hr | 2 days | 2024-06-11 | 2024-06-12 | 1482
7085 | 1484 | Late |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Error Matrix | 113 hrs | 287 days | 2023-05-18 | 2024-07-08
7086 | 1485 | Late |  |  | I-WP104 | Jennifer Reeves | Create | WPED - I-WP104 Error Matrix - Create | 9 hrs | 9 days | 2023-05-18 | 2023-05-31 | 1 | 1486
7087 | 1486 | Future Task |  |  | I-WP104 | Jennifer Reeves | Submit | WPED - I-WP104 Error Matrix - Submit | 0 hrs | 0 days | 2023-05-31 | 2023-05-31 | 1485 | 1487
7088 | 1487 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WPED - I-WP104 Error Matrix - Collaborative Review and Update | 10 hrs | 10 days | 2023-06-01 | 2023-06-14 | 1486 | 14881496
7089 | 1488 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | WPED - I-WP104 Error Matrix - Approve | 0 hrs | 0 days | 2023-06-14 | 2023-06-14 | 1487
7090 | 1489 | Future Task |  |  | I-WP104 | Jennifer Reeves | Submit | WP - IWP104 Error Matrix - Submit | 0 hrs | 0 days | 2024-06-12 | 2024-06-12 | 15271528 | 1490
7091 | 1490 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP - IWP104 Error Matrix - Dept QC | 1 hr | 1 day | 2024-06-13 | 2024-06-13 | 1489 | 1491
7092 | 1491 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP - IWP104 Error Matrix - Collaborative Review and Update | 10 hrs | 10 days | 2024-06-14 | 2024-06-27 | 1490 | 1492
7093 | 1492 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP - IWP104 Error Matrix - Style Guide Review | 1 hr | 1 day | 2024-06-28 | 2024-06-28 | 1491 | 1493
7094 | 1493 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | WP - IWP104 Error Matrix - Final Review and Update | 2 hrs | 5 days | 2024-07-01 | 2024-07-08 | 1492 | 1494
7095 | 1494 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | WP - IWP104 Error Matrix - Approve | 0 hrs | 0 days | 2024-07-08 | 2024-07-08 | 1493
7096 | 1495 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 1 | 15 hrs | 63 days | 2023-06-15 | 2023-09-13
7097 | 1496 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Error Matrix Format | 2 hrs | 5 days | 2023-06-15 | 2023-06-21 | 1487 | 1497
7098 | 1497 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 5 hrs | 5 days | 2023-06-22 | 2023-06-28 | 1496 | 1498
7099 | 1498 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix Format | 1 hr | 5 days | 2023-06-29 | 2023-07-06 | 1497 | 1499
7100 | 1499 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | 2023-08-02 | 2023-08-22 | 1498,38 | 1500
7101 | 1500 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 15 days | 2023-08-23 | 2023-09-13 | 1499
7102 | 1501 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 2 | 7 hrs | 20 days | 2023-10-24 | 2023-11-21
7103 | 1502 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | 2023-10-24 | 2023-11-14 | 57 | 1503
7104 | 1503 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | 2023-11-15 | 2023-11-21 | 1502
7105 | 1504 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 3 | 13 hrs | 25 days | 2024-01-29 | 2024-03-01
7106 | 1505 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | 2024-01-29 | 2024-02-16 | 136 | 15061512
7107 | 1506 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | 2024-02-19 | 2024-02-23 | 1505 | 1507
7108 | 1507 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Functional Teams | 6 hrs | 5 days | 2024-02-26 | 2024-03-01 | 1506 | 1509
7109 | 1508 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Update & Publish Error Matrix | 18 hrs | 25 days | 2024-02-19 | 2024-03-22
7110 | 1509 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 5 hrs | 5 days | 2024-03-04 | 2024-03-08 | 1507 | 1510
7111 | 1510 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix | 1 hr | 5 days | 2024-03-11 | 2024-03-15 | 1509 | 1511
7112 | 1511 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Coordinate Knowledge Base Update | 2 hrs | 5 days | 2024-03-18 | 2024-03-22 | 1510
7113 | 1512 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Communication for Error Matrix | 2 hrs | 5 days | 2024-02-19 | 2024-02-23 | 1505 | 1513
7114 | 1513 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review for Communication for Error Matrix | 2 hrs | 9 days | 2024-02-26 | 2024-03-07 | 1512 | 1514
7115 | 1514 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Communication for Error Matrix | 1 hr | 5 days | 2024-03-08 | 2024-03-14 | 1513 | 1515
7116 | 1515 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Publish - Error Matrix | 4 hrs | 2 days | 2024-03-15 | 2024-03-18 | 1514 | 1516
7117 | 1516 | Future Task |  | RW-Communication | I-WP104 | Jennifer Reeves | Create | I-WP104 Share - Communication for Error Matrix | 1 hr | 2 days | 2024-03-19 | 2024-03-20 | 1515
7118 | 1517 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Segment 4 | 13 hrs | 25 days | 2024-04-22 | 2024-05-24
7119 | 1518 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Update & Maintain - Error Matrix | 4 hrs | 15 days | 2024-04-22 | 2024-05-10 | 155SS | 15191525
7120 | 1519 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Review - Error Matrix | 3 hrs | 5 days | 2024-05-13 | 2024-05-17 | 1518 | 1520
7121 | 1520 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Functional Teams | 6 hrs | 5 days | 2024-05-20 | 2024-05-24 | 1519 | 1522
7122 | 1521 | Future Task |  |  | I-WP104 | Jennifer Reeves |  | I-WP104 Update & Publish Error Matrix | 14 hrs | 25 days | 2024-05-13 | 2024-06-17
7123 | 1522 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Error Matrix | 3 hrs | 5 days | 2024-05-28 | 2024-06-03 | 1520 | 1523
7124 | 1523 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Error Matrix | 2 hrs | 5 days | 2024-06-04 | 2024-06-10 | 1522 | 1524
7125 | 1524 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Coordinate Knowledge Base Update | 2 hrs | 5 days | 2024-06-11 | 2024-06-17 | 1523
7126 | 1525 | Future Task |  |  | I-WP104 | Jennifer Reeves | Create | I-WP104 Create - Task Instructions & Communication for Error Matrix | 2 hrs | 5 days | 2024-05-13 | 2024-05-17 | 1518 | 1526
7127 | 1526 | Future Task |  |  | I-WP104 | Jennifer Reeves | Review | I-WP104 Collaborative Review - Communication for Error Matrix | 2 hrs | 10 days | 2024-05-20 | 2024-06-03 | 1525 | 1527
7128 | 1527 | Future Task |  |  | I-WP104 | Jennifer Reeves | Approve | I-WP104 Approve - Task Instructions & Communication for Error Matrix | 2 hrs | 5 days | 2024-06-04 | 2024-06-10 | 1526 | 14891528
7129 | 1528 | Future Task |  | RW-Communication | I-WP104 | Jennifer Reeves | Create | I-WP104 Share Communication for Error Matrix | 1 hr | 2 days | 2024-06-11 | 2024-06-12 | 1527 | 1489
6862 | 1529 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Maintain Catalogs | 239 hrs | 272 days | 2023-06-09 | 2024-07-08
6863 | 1530 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Report Catalog | 51 hrs | 272 days | 2023-06-09 | 2024-07-08
6864 | 1531 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | WPED - I-WP105 Report Catalog - Create | 2 hrs | 10 days | 2023-06-09 | 2023-06-22 | 1 | 1532
6865 | 1532 | Future Task |  |  | I-WP105 | Jennifer Reeves | Submit | WPED - I-WP105 Report Catalog - Submit | 0 hrs | 0 days | 2023-06-22 | 2023-06-22 | 1531 | 1533
6866 | 1533 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WPED - I-WP105 Report Catalog - Collaborative Review and Update | 8 hrs | 10 days | 2023-06-23 | 2023-07-07 | 1532 | 1534
6867 | 1534 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | WPED - I-WP105 Report Catalog - Approve | 0 hrs | 0 days | 2023-07-07 | 2023-07-07 | 1533
6868 | 1535 | Future Task |  |  | I-WP105 | Jennifer Reeves | Milestone | WP - IWP105 Report Catalog - Submit | 0 hrs | 0 days | 2024-06-12 | 2024-06-12 | 15581571 | 1536
6869 | 1536 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP - IWP105 Report Catalog - Dept QC | 1 hr | 1 day | 2024-06-13 | 2024-06-13 | 1535 | 1537
6870 | 1537 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP - IWP105 Report Catalog - Collaborative Review and Update | 2 hrs | 10 days | 2024-06-14 | 2024-06-27 | 1536 | 1538
6871 | 1538 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP - IWP105 Report Catalog - Style Guide Review | 1 hr | 1 day | 2024-06-28 | 2024-06-28 | 1537 | 1539
6872 | 1539 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | WP - IWP105 Report Catalog - Final Review and Update | 2 hrs | 5 days | 2024-07-01 | 2024-07-08 | 1538 | 1540
6873 | 1540 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | WP - IWP105 Report Catalog - Approve | 0 hrs | 0 days | 2024-07-08 | 2024-07-08 | 1539
6874 | 1541 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 1 - Reports | 35 hrs | 20 days | 2023-07-18 | 2023-08-14
6875 | 1542 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | 2023-07-18 | 2023-08-07 | 38SS | 1543
6876 | 1543 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | 2023-08-08 | 2023-08-14 | 1542
6877 | 1544 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 2 - Reports | 35 hrs | 20 days | 2023-10-09 | 2023-11-03
6878 | 1545 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | 2023-10-09 | 2023-10-27 | 57SS | 1546
6879 | 1546 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | 2023-10-30 | 2023-11-03 | 1545
6880 | 1547 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 3 - Reports | 55 hrs | 25 days | 2024-01-11 | 2024-02-15
6881 | 1548 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 25 hrs | 15 days | 2024-01-11 | 2024-02-01 | 136SS | 1549
6882 | 1549 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 10 hrs | 5 days | 2024-02-02 | 2024-02-08 | 1548 | 15501556
6883 | 1550 | Future Task |  |  |  | Jennifer Reeves | Review | I-WP105 Collaborative Review - Functional Teams | 20 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1549 | 1552
6884 | 1551 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Update & Publish Report Catalog | 41 hrs | 22 days | 2024-02-09 | 2024-03-11
6885 | 1552 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Report Catalog | 10 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1550 | 1553
6886 | 1553 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Report Catalog | 2 hrs | 5 days | 2024-02-23 | 2024-02-29 | 1552 | 1554
6887 | 1554 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Coordinate Knowledge Base Update | 18 hrs | 5 days | 2024-03-01 | 2024-03-07 | 1553 | 1555
6888 | 1555 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Publish - Report Catalog | 4 hrs | 2 days | 2024-03-08 | 2024-03-11 | 1554
6889 | 1556 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Create Communication for Report Catalog | 2 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1549 | 1557
6890 | 1557 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review for Communication | 3 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1556 | 1558
6891 | 1558 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Communication for Report Catalog | 1 hr | 5 days | 2024-02-23 | 2024-02-29 | 1557 | 15351559
6892 | 1559 | Future Task |  | RW-Communication | I-WP105 | Jennifer Reeves | Create | I-WP105 Share Communication for Report Catalog | 1 hr | 2 days | 2024-03-01 | 2024-03-04 | 1558
6893 | 1560 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Segment 4 - Reports | 32 hrs | 27 days | 2024-04-22 | 2024-05-29
6894 | 1561 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Update & Maintain - Report Catalog | 10 hrs | 16 days | 2024-04-22 | 2024-05-13 | 155SS | 1562
6895 | 1562 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Review - Report Catalog | 2 hrs | 6 days | 2024-05-14 | 2024-05-21 | 1561 | 15631569
6896 | 1563 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Functional Teams | 20 hrs | 5 days | 2024-05-22 | 2024-05-29 | 1562 | 1565
6897 | 1564 | Future Task |  |  | I-WP105 | Jennifer Reeves |  | I-WP105 Update & Publish Report Catalog | 25 hrs | 22 days | 2024-05-22 | 2024-06-21
6898 | 1565 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review - Report Catalog | 10 hrs | 5 days | 2024-05-30 | 2024-06-05 | 1563 | 1566
6899 | 1566 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Report Catalog | 1 hr | 5 days | 2024-06-06 | 2024-06-12 | 1565 | 1567
6900 | 1567 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Coordinate Knowledge Base Update | 3 hrs | 5 days | 2024-06-13 | 2024-06-19 | 1566 | 1568
6901 | 1568 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Publish - Report Catalog | 4 hrs | 2 days | 2024-06-20 | 2024-06-21 | 1567
6902 | 1569 | Future Task |  |  | I-WP105 | Jennifer Reeves | Create | I-WP105 Create Communication for Report Catalog | 2 hrs | 5 days | 2024-05-22 | 2024-05-29 | 1562 | 1570
6903 | 1570 | Future Task |  |  | I-WP105 | Jennifer Reeves | Review | I-WP105 Collaborative Review for Communication | 3 hrs | 5 days | 2024-05-30 | 2024-06-05 | 1569 | 1571
6904 | 1571 | Future Task |  |  | I-WP105 | Jennifer Reeves | Approve | I-WP105 Approve - Communication for Report Catalog | 1 hr | 5 days | 2024-06-06 | 2024-06-12 | 1570 | 15351572
6905 | 1572 | Future Task |  | RW-Communication | I-WP105 | Jennifer Reeves | Create | I-WP105 Share Communication for Report Catalog | 1 hr | 2 days | 2024-06-13 | 2024-06-14 | 1571
6953 | 1573 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Interface Catalog | 210 hrs | 272 days | 2023-06-09 | 2024-07-08
6954 | 1574 | Future Task |  |  | I-WP106 | Matt Breeding | Create | WPED - I-WP106 Interface Catalog - Create | 10 hrs | 10 days | 2023-06-09 | 2023-06-22 | 1 | 1575
6955 | 1575 | Future Task |  |  | I-WP106 | Matt Breeding | Submit | WPED - I-WP106 Interface Catalog - Submit | 0 hrs | 0 days | 2023-06-22 | 2023-06-22 | 1574 | 1576
6956 | 1576 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WPED - I-WP106 Interface Catalog - Collaborative Review and Update | 10 hrs | 10 days | 2023-06-23 | 2023-07-07 | 1575 | 1577
6957 | 1577 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | WPED - I-WP106 Interface Catalog - Approve | 0 hrs | 0 days | 2023-07-07 | 2023-07-07 | 1576
6958 | 1578 | Future Task |  |  | I-WP106 | Matt Breeding | Submit | WP - IWP106 Interface Catalog - Submit | 0 hrs | 0 days | 2024-06-03 | 2024-06-03 | 1614 | 1579
6959 | 1579 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP - IWP106 Interface Catalog - Dept QC | 1 hr | 1 day | 2024-06-04 | 2024-06-04 | 1578 | 1580
6960 | 1580 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP - IWP106 Interface Catalog - Collaborative Review and Update | 10 hrs | 10 days | 2024-06-05 | 2024-06-18 | 1579 | 1581
6961 | 1581 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP - IWP106 Interface Catalog - Style Guide Review | 2 hrs | 1 day | 2024-06-19 | 2024-06-19 | 1580 | 1582
6962 | 1582 | Future Task |  |  | I-WP106 | Matt Breeding | Review | WP - IWP106 Interface Catalog - Final Review and Update | 10 hrs | 5 days | 2024-06-20 | 2024-06-26 | 1581 | 1583
6963 | 1583 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | WP - IWP106 Interface Catalog - Approve | 0 hrs | 0 days | 2024-06-26 | 2024-06-26 | 1582
6964 | 1584 | Future Task |  |  | I-WP106 | Matt Breeding |  | Interface Catalog | 167 hrs | 272 days | 2023-06-09 | 2024-07-08
6965 | 1585 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 1 - Interfaces | 12 hrs | 20 days | 2023-07-18 | 2023-08-14
6966 | 1586 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | 2023-07-18 | 2023-08-07 | 38SS | 1587
6967 | 1587 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | 2023-08-08 | 2023-08-14 | 1586
6968 | 1588 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 2 - Interfaces | 12 hrs | 20 days | 2023-10-11 | 2023-11-07
6969 | 1589 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | 2023-10-11 | 2023-10-31 | 57SS+2 days | 1590
6970 | 1590 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | 2023-11-01 | 2023-11-07 | 1589
6971 | 1591 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 3 - Interfaces | 22 hrs | 25 days | 2024-01-11 | 2024-02-15
6972 | 1592 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | 2024-01-11 | 2024-02-01 | 136SS | 1593
6973 | 1593 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | 2024-02-02 | 2024-02-08 | 1592 | 15941600
6974 | 1594 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Functional Teams | 10 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1593 | 1596
6975 | 1595 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Update & Publish Interface Catalog | 45 hrs | 24 days | 2024-02-09 | 2024-03-13
6976 | 1596 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Interface Catalog | 10 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1594 | 1597
6977 | 1597 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Interface Catalog | 1 hr | 5 days | 2024-02-23 | 2024-02-29 | 1596 | 1598
6978 | 1598 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Coordinate Knowledge Base Update | 10 hrs | 5 days | 2024-03-01 | 2024-03-07 | 1597 | 1599
6979 | 1599 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Publish - Interface Catalog | 10 hrs | 2 days | 2024-03-08 | 2024-03-11 | 1598 | 1603
6980 | 1600 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Create Communication for Interface Catalog | 2 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1593 | 1601
6981 | 1601 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review for Communication for Interface Catalog | 10 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1600 | 1602
6982 | 1602 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Communication for Interface Catalog | 1 hr | 5 days | 2024-02-23 | 2024-02-29 | 1601
6983 | 1603 | Future Task |  | RW-Communication | I-WP106 | Matt Breeding | Create | I-WP106 Share Communication for Interface Catalog | 1 hr | 2 days | 2024-03-12 | 2024-03-13 | 1599
6984 | 1604 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Segment 4 - Interfaces | 12 hrs | 20 days | 2024-04-22 | 2024-05-17
6985 | 1605 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Update & Maintain - Interface Catalog | 10 hrs | 15 days | 2024-04-22 | 2024-05-10 | 155SS | 16061612
6986 | 1606 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Review - Interface Catalog | 2 hrs | 5 days | 2024-05-13 | 2024-05-17 | 1605 | 1608
6987 | 1607 | Future Task |  |  | I-WP106 | Matt Breeding |  | I-WP106 Update & Publish Interface Catalog | 64 hrs | 272 days | 2023-06-09 | 2024-07-08
6988 | 1608 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review - Interface Catalog | 10 hrs | 5 days | 2024-05-20 | 2024-05-24 | 1606 | 1609
6989 | 1609 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Interface Catalog | 1 hr | 5 days | 2024-05-28 | 2024-06-03 | 1608 | 1610
6990 | 1610 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Coordinate Knowledge Base Update | 2 hrs | 5 days | 2024-06-04 | 2024-06-10 | 1609 | 1611
6991 | 1611 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Publish Interface Catalog | 1 hr | 2 days | 2024-06-11 | 2024-06-12 | 1610
6992 | 1612 | Future Task |  |  | I-WP106 | Matt Breeding | Create | I-WP106 Create Communication for Interface Catalog | 2 hrs | 5 days | 2024-05-13 | 2024-05-17 | 1605 | 1613
6993 | 1613 | Future Task |  |  | I-WP106 | Matt Breeding | Review | I-WP106 Collaborative Review for Communication for Interface Catalog | 3 hrs | 5 days | 2024-05-20 | 2024-05-24 | 1612 | 1614
6994 | 1614 | Future Task |  |  | I-WP106 | Matt Breeding | Approve | I-WP106 Approve - Communication for Interface Catalog | 1 hr | 5 days | 2024-05-28 | 2024-06-03 | 1613 | 15781615
6995 | 1615 | Future Task |  | RW-Communication | I-WP106 | Matt Breeding | Create | I-WP106 Share Communication for Interface Catalog | 1 hr | 2 days | 2024-06-04 | 2024-06-05 | 1614
6996 | 1616 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Conversions Inventory | 43 hrs | 272 days | 2023-06-09 | 2024-07-08
6997 | 1617 | Future Task |  |  | I-WP107 | Matt Breeding | Create | WPED - I-WP107 Conversions Inventory - Create | 10 hrs | 10 days | 2023-06-09 | 2023-06-22 | 1 | 1618
6998 | 1618 | Future Task |  |  | I-WP107 | Matt Breeding | Submit | WPED - I-WP107 Conversions Inventory - Submit | 0 hrs | 0 days | 2023-06-22 | 2023-06-22 | 1617 | 1619
6999 | 1619 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WPED - I-WP107 Conversions Inventory - Collaborative Review and Update | 10 hrs | 10 days | 2023-06-23 | 2023-07-07 | 1618 | 1620
7000 | 1620 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | WPED - I-WP107 Conversions Inventory - Approve | 0 hrs | 0 days | 2023-07-07 | 2023-07-07 | 1619
7001 | 1621 | Future Task |  |  | I-WP107 | Matt Breeding | Submit | WP - IWP107 Conversions Inventory - Submit | 0 hrs | 0 days | 2024-06-12 | 2024-06-12 | 1657 | 1622
7002 | 1622 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP - IWP107 Conversions Inventory - Dept QC | 1 hr | 1 day | 2024-06-13 | 2024-06-13 | 1621 | 1623
7003 | 1623 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP - IWP107 Conversions Inventory - Collaborative Review and Update | 10 hrs | 10 days | 2024-06-14 | 2024-06-27 | 1622 | 1624
7004 | 1624 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP - IWP107 Conversions Inventory - Style Guide Review | 2 hrs | 1 day | 2024-06-28 | 2024-06-28 | 1623 | 1625
7005 | 1625 | Future Task |  |  | I-WP107 | Matt Breeding | Review | WP - IWP107 Conversions Inventory - Final Review and Update | 10 hrs | 5 days | 2024-07-01 | 2024-07-08 | 1624 | 1626
7006 | 1626 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | WP - IWP107 Conversions Inventory - Approve | 0 hrs | 0 days | 2024-07-08 | 2024-07-08 | 1625
7007 | 1627 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Conversions Inventory | 124 hrs | 234 days | 2023-07-18 | 2024-06-19
7008 | 1628 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 1 - Conversions | 11 hrs | 20 days | 2023-07-18 | 2023-08-14
7009 | 1629 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | 2023-07-18 | 2023-08-07 | 38SS | 1630
7010 | 1630 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 1 hr | 5 days | 2023-08-08 | 2023-08-14 | 1629
7011 | 1631 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 2 - Conversions | 15 hrs | 20 days | 2023-10-16 | 2023-11-13
7012 | 1632 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | 2023-10-16 | 2023-11-03 | 57SS+5 days | 1633
7013 | 1633 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 5 hrs | 5 days | 2023-11-06 | 2023-11-13 | 1632
7014 | 1634 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 3 - Conversions | 25 hrs | 25 days | 2024-01-19 | 2024-02-22
7015 | 1635 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Update & Maintain - Conversion Catalog | 10 hrs | 15 days | 2024-01-19 | 2024-02-08 | 136SS+5 days | 1636
7016 | 1636 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 5 hrs | 5 days | 2024-02-09 | 2024-02-15 | 1635 | 16371643
7017 | 1637 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Functional Teams | 10 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1636 | 1639
7018 | 1638 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Update & Publish Conversion Catalog | 26 hrs | 27 days | 2024-02-16 | 2024-03-25
7019 | 1639 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Conversion Catalog | 10 hrs | 5 days | 2024-02-23 | 2024-02-29 | 1637 | 1640
7020 | 1640 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Conversion Catalog | 1 hr | 5 days | 2024-03-01 | 2024-03-07 | 1639 | 1641
7021 | 1641 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Coordinate Knowledge Base Update | 2 hrs | 5 days | 2024-03-08 | 2024-03-14 | 1640 | 1642
7022 | 1642 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Publish - Conversion Catalog | 4 hrs | 5 days | 2024-03-15 | 2024-03-21 | 1641 | 1646
7023 | 1643 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create Communication for Conversion Catalog | 2 hrs | 5 days | 2024-02-16 | 2024-02-22 | 1636 | 1644
7024 | 1644 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review for Communication for Conversion Catalog | 5 hrs | 5 days | 2024-02-23 | 2024-02-29 | 1643 | 1645
7025 | 1645 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Communication | 1 hr | 5 days | 2024-03-01 | 2024-03-07 | 1644
7026 | 1646 | Future Task |  | RW-Communication | I-WP107 | Matt Breeding | Create | I-WP107 Share Communication | 1 hr | 2 days | 2024-03-22 | 2024-03-25 | 1642
7027 | 1647 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Segment 4 - Conversions | 15 hrs | 25 days | 2024-04-29 | 2024-06-03
7028 | 1648 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create & Maintain - Conversion Catalog | 10 hrs | 15 days | 2024-04-29 | 2024-05-17 | 155SS+5 days | 1649
7029 | 1649 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Review - Conversion Catalog | 1 hr | 5 days | 2024-05-20 | 2024-05-24 | 1648 | 16501655
7030 | 1650 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Functional Teams | 4 hrs | 5 days | 2024-05-28 | 2024-06-03 | 1649 | 1652
7031 | 1651 | Future Task |  |  | I-WP107 | Matt Breeding |  | I-WP107 Update & Publish Conversions Catalog | 32 hrs | 17 days | 2024-05-28 | 2024-06-19
7032 | 1652 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review - Conversion Catalog | 10 hrs | 5 days | 2024-06-04 | 2024-06-10 | 1650 | 1653
7033 | 1653 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Conversion Catalog | 1 hr | 5 days | 2024-06-11 | 2024-06-17 | 1652 | 1654
7034 | 1654 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Publish - Conversion Catalog | 4 hrs | 2 days | 2024-06-18 | 2024-06-19 | 1653
7035 | 1655 | Future Task |  |  | I-WP107 | Matt Breeding | Create | I-WP107 Create Communication for Conversions Catalog | 3 hrs | 2 days | 2024-05-28 | 2024-05-29 | 1649 | 1656
7036 | 1656 | Future Task |  |  | I-WP107 | Matt Breeding | Review | I-WP107 Collaborative Review for Communication for Conversions Catalog | 10 hrs | 5 days | 2024-05-30 | 2024-06-05 | 1655 | 1657
7037 | 1657 | Future Task |  |  | I-WP107 | Matt Breeding | Approve | I-WP107 Approve - Communication | 3 hrs | 5 days | 2024-06-06 | 2024-06-12 | 1656 | 16211658
7038 | 1658 | Future Task |  | RW-Communication | I-WP107 | Matt Breeding | Create | I-WP107 Share Communication for Conversions Catalog | 1 hr | 5 days | 2024-06-13 | 2024-06-19 | 1657
2973 | 1659 | Future Task |  |  | I-WP108 | Kimberly Kemp |  | I-WP108 Training Curriculum | 53 hrs | 360 days | 2023-06-01 | 2024-10-31
2974 | 1660 | Future Task |  |  | I-WP108 | Carolyn Hicks | Create | WPED - I-WP108 - Training Curriculum - Create | 10 hrs | 10 days | 2023-06-01 | 2023-06-14 | 1 | 1661
2975 | 1661 | Future Task |  |  | I-WP108 | Carolyn Hicks | Submit | WPED - I-WP108 - Training Curriculum - Submit | 0 hrs | 0 days | 2023-06-14 | 2023-06-14 | 1660 | 1662
2976 | 1662 | Future Task |  |  | I-WP108 | Carolyn Hicks | Review | WPED - I-WP108 - Training Curriculum - Collaborative Review and Update | 10 hrs | 10 days | 2023-06-15 | 2023-06-28 | 1661 | 1663
2977 | 1663 | Future Task |  |  | I-WP108 | Carolyn Hicks | Approve | WPED - I-WP108 - Training Curriculum - Approve | 0 hrs | 0 days | 2023-06-28 | 2023-06-28 | 1662 | 1664
5689 | 1664 | Future Task |  |  | I-WP108 | Kimberly Kemp | Create | I-WP108 Training Curriculum <Activities per WPED> | 10 hrs | 287 days | 2023-08-21 | 2024-10-08 | 1663,44 | 1665,1676SS+30 days
2978 | 1665 | Future Task |  |  | I-WP108 | Kimberly Kemp | Submit | I-WP108 Training Curriculum - Submit | 0 hrs | 0 days | 2024-10-08 | 2024-10-08 | 1664 | 1666
2979 | 1666 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | I-WP108 Training Curriculum - Dept QC | 1 hr | 1 day | 2024-10-09 | 2024-10-09 | 1665 | 1667
2980 | 1667 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | I-WP108 Training Curriculum - Collaborative Review and Update | 10 hrs | 10 days | 2024-10-10 | 2024-10-23 | 1666 | 1668
2981 | 1668 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | I-WP108 Training Curriculum - Style Guide Review | 2 hrs | 1 day | 2024-10-24 | 2024-10-24 | 1667 | 1669
2982 | 1669 | Future Task |  |  | I-WP108 | Kimberly Kemp | Review | I-WP108 Training Curriculum - Final Review and Update | 10 hrs | 5 days | 2024-10-25 | 2024-10-31 | 1668 | 1670
2983 | 1670 | Future Task |  |  | I-WP108 | Kimberly Kemp | Approve | I-WP108 Training Curriculum - Approve | 0 hrs | 0 days | 2024-10-31 | 2024-10-31 | 1669
2984 | 1671 | Future Task |  |  | I-WP109 | Kimberly Kemp |  | I-WP109 Training Designs | 66 hrs | 315 days | 2023-07-03 | 2024-09-30
2985 | 1672 | Future Task |  |  | I-WP109 | Carolyn Hicks | Create | WPED - I-WP109 - Training Designs - Create | 10 hrs | 10 days | 2023-07-03 | 2023-07-17 | 1 | 1673
2986 | 1673 | Future Task |  |  | I-WP109 | Carolyn Hicks | Submit | WPED - I-WP109 - Training Designs - Submit | 0 hrs | 0 days | 2023-07-17 | 2023-07-17 | 1672 | 1674
2987 | 1674 | Future Task |  |  | I-WP109 | Carolyn Hicks | Review | WPED - I-WP109 - Training Designs - Collaborative Review and Update | 10 hrs | 10 days | 2023-07-18 | 2023-07-31 | 1673 | 1675
2988 | 1675 | Future Task |  |  | I-WP109 | Carolyn Hicks | Approve | WPED - I-WP109 - Training Designs - Approve | 0 hrs | 0 days | 2023-07-31 | 2023-07-31 | 1674 | 1676
5690 | 1676 | Future Task |  |  | I-WP109 | Kimberly Kemp | Create | I-WP109 Training Designs <Activities per WPED> | 10 hrs | 234 days | 2023-10-03 | 2024-09-05 | 1675,1664SS+30 days | 1677,1688SS
2989 | 1677 | Future Task |  |  | I-WP109 | Kimberly Kemp | Submit | I-WP109 Training Designs - Submit | 0 hrs | 0 days | 2024-09-05 | 2024-09-05 | 1676 | 1678
2990 | 1678 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | I-WP109 Training Designs - Dept QC | 8 hrs | 1 day | 2024-09-06 | 2024-09-06 | 1677 | 1679
2991 | 1679 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | I-WP109 Training Designs - Collaborative Review and Update | 10 hrs | 10 days | 2024-09-09 | 2024-09-20 | 1678 | 1680
2992 | 1680 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | I-WP109 Training Designs - Style Guide Review | 8 hrs | 1 day | 2024-09-23 | 2024-09-23 | 1679 | 1681
2993 | 1681 | Future Task |  |  | I-WP109 | Kimberly Kemp | Review | I-WP109 Training Designs - Final Review and Update | 10 hrs | 5 days | 2024-09-24 | 2024-09-30 | 1680 | 1682
2994 | 1682 | Future Task |  |  | I-WP109 | Kimberly Kemp | Approve | I-WP109 Training Designs - Approve | 0 hrs | 0 days | 2024-09-30 | 2024-09-30 | 1681 | 1750
2995 | 1683 | Future Task | Yes |  | I-WP110 | Kimberly Kemp |  | I-WP110 Training Build | 136 hrs | 401 days | 2024-03-01 | 2025-09-30
2996 | 1684 | Future Task |  |  | I-WP110 | Carolyn Hicks | Create | WPED - I-WP110 - Training Build - Create | 10 hrs | 10 days | 2024-03-01 | 2024-03-14 | 1 | 1685
2997 | 1685 | Future Task |  |  | I-WP110 | Carolyn Hicks | Submit | WPED - I-WP110 - Training Build - Submit | 0 hrs | 0 days | 2024-03-14 | 2024-03-14 | 1684 | 1686
2998 | 1686 | Future Task |  |  | I-WP110 | Carolyn Hicks | Review | WPED - I-WP110 - Training Build - Collaborative Review and Update | 10 hrs | 10 days | 2024-03-15 | 2024-03-28 | 1685 | 1687
2999 | 1687 | Future Task |  |  | I-WP110 | Carolyn Hicks | Approve | WPED - I-WP110 - Training Build - Approve | 0 hrs | 0 days | 2024-03-28 | 2024-03-28 | 1686 | 1688
5691 | 1688 | Future Task |  |  | I-WP110 | Kimberly Kemp | Create | I-WP110 Training Build <Activities per WPED> | 80 hrs | 364 days | 2024-03-29 | 2025-09-05 | 1687,1676SS | 1689
3000 | 1689 | Future Task |  |  | I-WP110 | Kimberly Kemp | Submit | I-WP110 Training Build - Submit | 0 hrs | 0 days | 2025-09-05 | 2025-09-05 | 1688 | 1690
3001 | 1690 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | I-WP110 Training Build - Dept QC | 8 hrs | 1 day | 2025-09-08 | 2025-09-08 | 1689 | 1691
3002 | 1691 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | I-WP110 Training Build - Collaborative Review and Update | 10 hrs | 10 days | 2025-09-09 | 2025-09-22 | 1690 | 1692
3003 | 1692 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | I-WP110 Training Build - Style Guide Review | 8 hrs | 1 day | 2025-09-23 | 2025-09-23 | 1691 | 1693
3004 | 1693 | Future Task |  |  | I-WP110 | Kimberly Kemp | Review | I-WP110 Training Build - Final Review and Update | 10 hrs | 5 days | 2025-09-24 | 2025-09-30 | 1692 | 1694
3005 | 1694 | Future Task |  |  | I-WP110 | Kimberly Kemp | Approve | I-WP110 Training Build - Approve | 0 hrs | 0 days | 2025-09-30 | 2025-09-30 | 1693
3006 | 1695 | Future Task |  |  | I-WP111 | Kimberly Kemp |  | I-WP111 UAT Training Materials | 129 hrs | 154 days | 2024-08-01 | 2025-03-13
3007 | 1696 | Future Task |  |  | I-WP111 | Carolyn Hicks | Create | WPED - I-WP111 - UAT Training Materials - Create | 10 hrs | 10 days | 2024-08-01 | 2024-08-14 | 1 | 1697
3008 | 1697 | Future Task |  |  | I-WP111 | Carolyn Hicks | Submit | WPED - I-WP111 - UAT Training Materials - Submit | 0 hrs | 0 days | 2024-08-14 | 2024-08-14 | 1696 | 1698
3009 | 1698 | Future Task |  |  | I-WP111 | Carolyn Hicks | Review | WPED - I-WP111 - UAT Training Materials - Collaborative Review and Update | 10 hrs | 10 days | 2024-08-15 | 2024-08-28 | 1697 | 1699
3010 | 1699 | Future Task |  |  | I-WP111 | Carolyn Hicks | Approve | WPED - I-WP111 - UAT Training Materials - Approve | 0 hrs | 0 days | 2024-08-28 | 2024-08-28 | 1698 | 1700
5692 | 1700 | Future Task |  |  | I-WP111 | Kimberly Kemp | Create | I-WP111 UAT Training Materials <Activities per WPED> | 80 hrs | 117 days | 2024-08-29 | 2025-02-18 | 1699 | 1701
3011 | 1701 | Future Task |  |  | I-WP111 | Kimberly Kemp | Submit | I-WP111 UAT Training Materials - Submit | 0 hrs | 0 days | 2025-02-18 | 2025-02-18 | 1700 | 1702
3012 | 1702 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | I-WP111 UAT Training Materials - Dept QC | 1 hr | 1 day | 2025-02-19 | 2025-02-19 | 1701 | 1703
3013 | 1703 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | I-WP111 UAT Training Materials - Collaborative Review and Update | 10 hrs | 10 days | 2025-02-20 | 2025-03-05 | 1702 | 1704
3014 | 1704 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | I-WP111 UAT Training Materials - Style Guide Review | 8 hrs | 1 day | 2025-03-06 | 2025-03-06 | 1703 | 1705
3015 | 1705 | Future Task |  |  | I-WP111 | Kimberly Kemp | Review | I-WP111 UAT Training Materials - Final Review and Update | 10 hrs | 5 days | 2025-03-07 | 2025-03-13 | 1704 | 1706
3016 | 1706 | Future Task |  |  | I-WP111 | Kimberly Kemp | Approve | I-WP111 UAT Training Materials - Approve | 0 hrs | 0 days | 2025-03-13 | 2025-03-13 | 1705 | 1707
3017 | 1707 | Future Task |  |  | I-WP111 | Kimberly Kemp | Milestone | I-WP111 UAT Training Materials Complete | 0 hrs | 0 days | 2025-03-13 | 2025-03-13 | 1706 | 1250
3018 | 1708 | Future Task |  |  | I-WP112 | Kimberly Kemp |  | I-WP112 End User Manual | 143 hrs | 210 days | 2025-01-31 | 2025-11-26
3019 | 1709 | Future Task |  |  | I-WP112 | Carolyn Hicks | Create | WPED - I-WP112 - End User Manual - Create | 10 hrs | 10 days | 2025-01-31 | 2025-02-13 | 1 | 1710
3020 | 1710 | Future Task |  |  | I-WP112 | Carolyn Hicks | Submit | WPED - I-WP112 - End User Manual - Submit | 0 hrs | 0 days | 2025-02-13 | 2025-02-13 | 1709 | 1711
3021 | 1711 | Future Task |  |  | I-WP112 | Carolyn Hicks | Review | WPED - I-WP112 - End User Manual - Collaborative Review and Update | 10 hrs | 10 days | 2025-02-14 | 2025-02-27 | 1710 | 1712
3022 | 1712 | Future Task |  |  | I-WP112 | Carolyn Hicks | Approve | WPED - I-WP112 - End User Manual - Approve | 0 hrs | 0 days | 2025-02-27 | 2025-02-27 | 1711 | 1713
5693 | 1713 | Future Task |  |  | I-WP112 | Kimberly Kemp | Create | I-WP112 End User Manual <Activities per WPED> | 100 hrs | 173 days | 2025-02-28 | 2025-10-31 | 1712649 | 1714
3023 | 1714 | Future Task |  |  | I-WP112 | Kimberly Kemp | Submit | I-WP112 End User Manual - Submit | 0 hrs | 0 days | 2025-10-31 | 2025-10-31 | 1713 | 1715
3024 | 1715 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | I-WP112 End User Manual - Dept QC | 1 hr | 1 day | 2025-11-03 | 2025-11-03 | 1714 | 1716
3025 | 1716 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | I-WP112 End User Manual - Collaborative Review and Update | 10 hrs | 10 days | 2025-11-04 | 2025-11-18 | 1715 | 1717
3026 | 1717 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | I-WP112 End User Manual - Style Guide Review | 2 hrs | 1 day | 2025-11-19 | 2025-11-19 | 1716 | 1718
3027 | 1718 | Future Task |  |  | I-WP112 | Kimberly Kemp | Review | I-WP112 End User Manual - Final Review and Update | 10 hrs | 5 days | 2025-11-20 | 2025-11-26 | 1717 | 1719
3028 | 1719 | Future Task |  |  | I-WP112 | Kimberly Kemp | Approve | I-WP112 End User Manual - Approve | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 1718 | 1720
3029 | 1720 | Future Task |  |  | I-WP112 | Kimberly Kemp | Milestone | I-WP112 End User Manual Complete | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 1719
3030 | 1721 | Future Task |  |  | I-WP113 | Kimberly Kemp |  | I-WP113 ILT Training Delivery Plan | 156 hrs | 85 days | 2025-05-01 | 2025-08-29
3031 | 1722 | Future Task |  |  | I-WP113 | Carolyn Hicks | Create | WPED - I-WP113 - ILT Training Delivery Plan - Create | 10 hrs | 10 days | 2025-05-01 | 2025-05-14 | 1 | 1723
3032 | 1723 | Future Task |  |  | I-WP113 | Carolyn Hicks | Submit | WPED - I-WP113 - ILT Training Delivery Plan - Submit | 0 hrs | 0 days | 2025-05-14 | 2025-05-14 | 1722 | 1724
3033 | 1724 | Future Task |  |  | I-WP113 | Carolyn Hicks | Review | WPED - I-WP113 - ILT Training Delivery Plan - Collaborative Review and Update | 10 hrs | 10 days | 2025-05-15 | 2025-05-29 | 1723 | 1725
3034 | 1725 | Future Task |  |  | I-WP113 | Carolyn Hicks | Approve | WPED - I-WP113- ILT Training Delivery Plan - Approve | 0 hrs | 0 days | 2025-05-29 | 2025-05-29 | 1724 | 1726
5694 | 1726 | Future Task |  |  | I-WP113 | Kimberly Kemp | Create | I-WP113 ILT Training Delivery Plan <Activities per WPED> | 100 hrs | 48 days | 2025-05-30 | 2025-08-06 | 1725 | 1727
3035 | 1727 | Future Task |  |  | I-WP113 | Kimberly Kemp | Submit | I-WP113 ILT Training Delivery Plan - Submit | 0 hrs | 0 days | 2025-08-06 | 2025-08-06 | 1726 | 1728
3036 | 1728 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | I-WP113 ILT Training Delivery Plan - Dept QC | 8 hrs | 1 day | 2025-08-07 | 2025-08-07 | 1727 | 1729
3037 | 1729 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | I-WP113 ILT Training Delivery Plan - Collaborative Review and Update | 10 hrs | 10 days | 2025-08-08 | 2025-08-21 | 1728 | 1730
3038 | 1730 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | I-WP113 ILT Training Delivery Plan - Style Guide Review | 8 hrs | 1 day | 2025-08-22 | 2025-08-22 | 1729 | 1731
3039 | 1731 | Future Task |  |  | I-WP113 | Kimberly Kemp | Review | I-WP113 ILT Training Delivery Plan - Final Review and Update | 10 hrs | 5 days | 2025-08-25 | 2025-08-29 | 1730 | 1732
3040 | 1732 | Future Task |  |  | I-WP113 | Kimberly Kemp | Approve | I-WP113 ILT Training Delivery Plan - Approve | 0 hrs | 0 days | 2025-08-29 | 2025-08-29 | 1731
3041 | 1733 | Future Task |  |  | I-WP114 | Kimberly Kemp |  | I-WP114 Training Measurement Report | 143 hrs | 104 days | 2025-10-29 | 2026-03-31
3042 | 1734 | Future Task |  |  | I-WP114 | Carolyn Hicks | Create | WPED - I-WP114 - Training Measurement Report - Create | 10 hrs | 10 days | 2025-10-29 | 2025-11-12 | 1 | 1735
3043 | 1735 | Future Task |  |  | I-WP114 | Kimberly Kemp | Submit | WPED - I-WP114 - Training Measurement Report - Submit | 0 hrs | 0 days | 2025-11-12 | 2025-11-12 | 1734 | 1736
3044 | 1736 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | WPED - I-WP114 - Training Measurement Report - Collaborative Review and Update | 10 hrs | 10 days | 2025-11-13 | 2025-11-26 | 1735 | 1737
3045 | 1737 | Future Task |  |  | I-WP114 | Kimberly Kemp | Approve | WPED - I-WP114 - Training Measurement Report - Approve | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 1736 | 1738
5695 | 1738 | Future Task |  |  | I-WP114 | Kimberly Kemp | Create | I-WP114 Training Measurement Report <Activities per WPED> | 100 hrs | 67 days | 2025-12-01 | 2026-03-06 | 17371250 | 1739
3046 | 1739 | Future Task |  |  | I-WP114 | Kimberly Kemp | Submit | I-WP114 Training Measurement Report - Submit | 0 hrs | 0 days | 2026-03-06 | 2026-03-06 | 1738 | 1740
3047 | 1740 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | I-WP114 Training Measurement Report - Dept QC | 1 hr | 1 day | 2026-03-09 | 2026-03-09 | 1739 | 1741
3048 | 1741 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | I-WP114 Training Measurement Report - Collaborative Review and Update | 10 hrs | 10 days | 2026-03-10 | 2026-03-23 | 1740 | 1742
3049 | 1742 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | I-WP114 Training Measurement Report - Style Guide Review | 2 hrs | 1 day | 2026-03-24 | 2026-03-24 | 1741 | 1743
3050 | 1743 | Future Task |  |  | I-WP114 | Kimberly Kemp | Review | I-WP114 Training Measurement Report - Final Review and Update | 10 hrs | 5 days | 2026-03-25 | 2026-03-31 | 1742 | 1744
3051 | 1744 | Future Task |  |  | I-WP114 | Kimberly Kemp | Approve | Training Measurement Report - Approve | 0 hrs | 0 days | 2026-03-31 | 2026-03-31 | 1743
3052 | 1745 | Future Task |  |  | I-WP115 | Kimberly Kemp |  | I-WP115 Train the Trainer | 156 hrs | 372 days | 2025-08-01 | 2027-01-26
3053 | 1746 | Future Task |  |  | I-WP115 | Carolyn Hicks | Create | WPED - I-WP115 - Train the Trainer - Create | 10 hrs | 10 days | 2025-08-01 | 2025-08-14 | 1 | 1747
3054 | 1747 | Future Task |  |  | I-WP115 | Carolyn Hicks | Submit | WPED - I-WP115 - Train the Trainer - Submit | 0 hrs | 0 days | 2025-08-14 | 2025-08-14 | 1746 | 1748
3055 | 1748 | Future Task |  |  | I-WP115 | Carolyn Hicks | Review | WPED - I-WP115 - Train the Trainer - Collaborative Review and Update | 10 hrs | 10 days | 2025-08-15 | 2025-08-28 | 1747 | 1749
3056 | 1749 | Future Task |  |  | I-WP115 | Carolyn Hicks | Approve | WPED - I-WP115 - Train the Trainer - Approve | 0 hrs | 0 days | 2025-08-28 | 2025-08-28 | 1748 | 1750
5696 | 1750 | Future Task |  |  | I-WP115 | Kimberly Kemp | Create | I-WP115 Train the Trainer <Activities per WPED> | 100 hrs | 324 days | 2025-08-29 | 2026-12-14 | 17491682 | 1751FS+11 days
3057 | 1751 | Future Task |  |  | I-WP115 | Kimberly Kemp | Submit | I-WP115 Train the Trainer - Submit | 0 hrs | 0 days | 2026-12-30 | 2026-12-30 | 1750FS+11 days | 1752
3058 | 1752 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | I-WP115 Train the Trainer - Dept QC | 8 hrs | 1 day | 2026-12-31 | 2026-12-31 | 1751 | 1753
3059 | 1753 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | I-WP115 Train the Trainer - Collaborative Review and Update | 10 hrs | 10 days | 2027-01-04 | 2027-01-15 | 1752 | 1754
3060 | 1754 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | I-WP115 Train the Trainer - Style Guide Review | 8 hrs | 1 day | 2027-01-19 | 2027-01-19 | 1753 | 1755
3061 | 1755 | Future Task |  |  | I-WP115 | Kimberly Kemp | Review | I-WP115 Train the Trainer - Final Review and Update | 10 hrs | 5 days | 2027-01-20 | 2027-01-26 | 1754 | 1756
3062 | 1756 | Future Task |  |  | I-WP115 | Kimberly Kemp | Approve | I-WP115 Train the Trainer - Approve | 0 hrs | 0 days | 2027-01-26 | 2027-01-26 | 1755 | 1757
3063 | 1757 | Future Task |  |  | I-WP115 | Kimberly Kemp | Milestone | Train the Trainer Complete | 0 hrs | 0 days | 2027-01-26 | 2027-01-26 | 1756
3064 | 1758 | Future Task |  |  | I-WP122 | Carolyn Hicks |  | I-WP122 - Update D33 Training Strategy | 143 hrs | 81 days | 2023-11-01 | 2024-02-29
3065 | 1759 | Future Task |  |  | I-WP122 | Carolyn Hicks | Create | WPED - I-WP122 - Update D33 Training Strategy - Create | 10 hrs | 10 days | 2023-11-01 | 2023-11-15 | 1 | 1760
3066 | 1760 | Future Task |  |  | I-WP122 | Carolyn Hicks | Submit | WPED - I-WP122 - Update D33 Training Strategy - Submit | 0 hrs | 0 days | 2023-11-15 | 2023-11-15 | 1759 | 1761
3067 | 1761 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | WPED - I-WP122 - Update D33 Training Strategy - Collaborative Review and Update | 10 hrs | 10 days | 2023-11-16 | 2023-12-01 | 1760 | 1762
3068 | 1762 | Future Task |  |  | I-WP122 | Carolyn Hicks | Approve | WPED - I-WP122 - Update D33 Training Strategy - Approve | 0 hrs | 0 days | 2023-12-01 | 2023-12-01 | 1761 | 1763
5697 | 1763 | Future Task |  |  | I-WP122 | Carolyn Hicks | Create | I-WP122 Update D33 Training Strategy <Activities per WPED> | 100 hrs | 44 days | 2023-12-04 | 2024-02-06 | 1762 | 1764
3069 | 1764 | Future Task |  |  | I-WP122 | Carolyn Hicks | Submit | I-WP122 Update D33 Training Strategy - Submit | 0 hrs | 0 days | 2024-02-06 | 2024-02-06 | 1763 | 1765
3070 | 1765 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | I-WP122 Update D33 Training Strategy - Dept QC | 1 hr | 1 day | 2024-02-07 | 2024-02-07 | 1764 | 1766
3071 | 1766 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | I-WP122Update D33 Training Strategy - Collaborative Review and Update | 10 hrs | 10 days | 2024-02-08 | 2024-02-21 | 1765 | 1767
3072 | 1767 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | I-WP122 Update D33 Training Strategy - Style Guide Review | 2 hrs | 1 day | 2024-02-22 | 2024-02-22 | 1766 | 1768
3073 | 1768 | Future Task |  |  | I-WP122 | Carolyn Hicks | Review | I-WP122 Update D33 Training Strategy - Final Review and Update | 10 hrs | 5 days | 2024-02-23 | 2024-02-29 | 1767 | 1769
3074 | 1769 | Future Task |  |  | I-WP122 | Carolyn Hicks | Approve | I-WP122 Update D33 Training Strategy - Approve | 0 hrs | 0 days | 2024-02-29 | 2024-02-29 | 1768
3075 | 1770 | Future Task |  |  | I-WP123 | Carolyn Hicks |  | I-WP123 - Update D112 Training Deployment and Measurement Plan | 149 hrs | 81 days | 2023-11-01 | 2024-02-29
3076 | 1771 | Future Task |  |  | I-WP123 | Carolyn Hicks | Create | WPED - I-WP123 - Update D112 Training Deployment and Measurement Plan - Create | 10 hrs | 10 days | 2023-11-01 | 2023-11-15 | 1 | 1772
3077 | 1772 | Future Task |  |  | I-WP123 | Carolyn Hicks | Submit | WPED - I-WP123 - Update D112 Training Deployment and Measurement Plan - Submit | 0 hrs | 0 days | 2023-11-15 | 2023-11-15 | 1771 | 1773
3078 | 1773 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | WPED - I-WP123 - Update D112 Training Deployment and Measurement Plan - Collaborative Review and Update | 10 hrs | 10 days | 2023-11-16 | 2023-12-01 | 1772 | 1774
3079 | 1774 | Future Task |  |  | I-WP123 | Carolyn Hicks | Approve | WPED - I-WP123 - Update D112 Training Deployment and Measurement Plan - Approve | 0 hrs | 0 days | 2023-12-01 | 2023-12-01 | 1773 | 1775
5698 | 1775 | Future Task |  |  | I-WP123 | Carolyn Hicks | Create | I-WP123 Update D112 Training Deployment and Measurement Plan <Activities per WPED> | 100 hrs | 44 days | 2023-12-04 | 2024-02-06 | 1774 | 1776
3080 | 1776 | Future Task |  |  | I-WP123 | Carolyn Hicks | Submit | I-WP123 Update D112 Training Deployment and Measurement Plan - Submit | 0 hrs | 0 days | 2024-02-06 | 2024-02-06 | 1775 | 1777
3081 | 1777 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | I-WP123 Update D112 Training Deployment and Measurement Plan - Dept QC | 1 hr | 1 day | 2024-02-07 | 2024-02-07 | 1776 | 1778
3082 | 1778 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | I-WP123Update D112 Training Deployment and Measurement Plan - Collaborative Review and Update | 10 hrs | 10 days | 2024-02-08 | 2024-02-21 | 1777 | 1779
3083 | 1779 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | I-WP123 Update D112 Training Deployment and Measurement Plan - Style Guide Review | 8 hrs | 1 day | 2024-02-22 | 2024-02-22 | 1778 | 1780
3084 | 1780 | Future Task |  |  | I-WP123 | Carolyn Hicks | Review | I-WP123 Update D112 Training Deployment and Measurement Plan - Final Review and Update | 10 hrs | 5 days | 2024-02-23 | 2024-02-29 | 1779 | 1781
3085 | 1781 | Future Task |  |  | I-WP123 | Carolyn Hicks | Approve | I-WP123 Update D112 Training Deployment and Measurement Plan - Approve | 0 hrs | 0 days | 2024-02-29 | 2024-02-29 | 1780
6812 | 1782 | Future Task | [5 empty] | Training | 1 hr | 104 days | 2025-07-01 | 2025-11-26
6813 | 1783 | Future Task |  |  |  | Carolyn Hicks |  | Conduct Training | 1 hr | 104 days | 2025-07-01 | 2025-11-26 | 1 |  | July - Nov 2025
3086 | 1784 | Late | [5 empty] | Readiness | 876 hrs | 730 days | 2023-05-08 | 2026-03-31
7159 | 1785 | Future Task | Yes |  | SG4 | Jimmy Cox | Milestone | Stage Gate 4: Agency Readiness | 0 hrs | 0 days | 2025-11-03 | 2025-11-03 | 1 |  | November 2025 - ESC
3087 | 1786 | Future Task |  |  | I-WP116 | Kimberly Kemp |  | I-WP116 User Support Sessions | 156 hrs | 209 days | 2025-06-02 | 2026-03-31
3088 | 1787 | Future Task |  |  | I-WP116 | Carolyn Hicks | Create | WPED - I-WP116 - User Support Sessions - Create | 10 hrs | 10 days | 2025-06-02 | 2025-06-13 | 1 | 1788
3089 | 1788 | Future Task |  |  | I-WP116 | Carolyn Hicks | Submit | WPED - I-WP116 - User Support Sessions - Submit | 0 hrs | 0 days | 2025-06-13 | 2025-06-13 | 1787 | 1789
3090 | 1789 | Future Task |  |  | I-WP116 | Carolyn Hicks | Review | WPED - I-WP116 - User Support Sessions - Collaborative Review and Update | 10 hrs | 10 days | 2025-06-16 | 2025-06-27 | 1788 | 1790
3091 | 1790 | Future Task |  |  | I-WP116 | Carolyn Hicks | Approve | WPED - I-WP116 - User Support Sessions - Approve | 0 hrs | 0 days | 2025-06-27 | 2025-06-27 | 1789 | 1791
5699 | 1791 | Future Task |  |  | I-WP116 | Kimberly Kemp | Create | I-WP116 User Support Sessions <Activities per WPED> | 100 hrs | 172 days | 2025-06-30 | 2026-03-06 | 1790,1250SS+30 days | 1792
3092 | 1792 | Future Task |  |  | I-WP116 | Kimberly Kemp | Submit | I-WP116 User Support Sessions - Submit | 0 hrs | 0 days | 2026-03-06 | 2026-03-06 | 1791 | 1793
3093 | 1793 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | I-WP116 User Support Sessions - Dept QC | 8 hrs | 1 day | 2026-03-09 | 2026-03-09 | 1792 | 1794
3094 | 1794 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | I-WP116 User Support Sessions - Collaborative Review and Update | 10 hrs | 10 days | 2026-03-10 | 2026-03-23 | 1793 | 1795
3095 | 1795 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | I-WP116 User Support Sessions - Style Guide Review | 8 hrs | 1 day | 2026-03-24 | 2026-03-24 | 1794 | 1796
3096 | 1796 | Future Task |  |  | I-WP116 | Kimberly Kemp | Review | I-WP116User Support Sessions - Final Review and Update | 10 hrs | 5 days | 2026-03-25 | 2026-03-31 | 1795 | 1797
3097 | 1797 | Future Task |  |  | I-WP116 | Kimberly Kemp | Approve | I-WP116 User Support Sessions - Approve | 0 hrs | 0 days | 2026-03-31 | 2026-03-31 | 1796
3098 | 1798 | Future Task |  |  | I-WP117 | Nikki Klein |  | I-WP117 Role Mapping Handbook | 149 hrs | 193 days | 2024-02-01 | 2024-10-31
3099 | 1799 | Future Task |  |  | I-WP117 | Carolyn Hicks | Create | WPED - I-WP117- Role Mapping Handbook - Create | 10 hrs | 10 days | 2024-02-01 | 2024-02-14 | 1 | 1800
3100 | 1800 | Future Task |  |  | I-WP117 | Carolyn Hicks | Submit | WPED - I-WP117 - Role Mapping Handbook - Submit | 0 hrs | 0 days | 2024-02-14 | 2024-02-14 | 1799 | 1801
3101 | 1801 | Future Task |  |  | I-WP117 | Carolyn Hicks | Review | WPED - I-WP117 - Role Mapping Handbook - Collaborative Review and Update | 10 hrs | 10 days | 2024-02-15 | 2024-02-28 | 1800 | 1802
3102 | 1802 | Future Task |  |  | I-WP117 | Carolyn Hicks | Approve | WPED - I-WP117 - Role Mapping Handbook - Approve | 0 hrs | 0 days | 2024-02-28 | 2024-02-28 | 1801 | 1803
5700 | 1803 | Future Task |  |  | I-WP117 | Nikki Klein | Create | I-WP117 Role Mapping Handbook <Activities per WPED> | 100 hrs | 156 days | 2024-02-29 | 2024-10-08 | 1802105 | 1804,1815SS+40 days
3103 | 1804 | Future Task |  |  | I-WP117 | Nikki Klein | Submit | I-WP117 Role Mapping Handbook - Submit | 0 hrs | 0 days | 2024-10-08 | 2024-10-08 | 1803 | 1805
3104 | 1805 | Future Task |  |  | I-WP117 | Nikki Klein | Review | I-WP117 Role Mapping Handbook - Dept QC | 1 hr | 1 day | 2024-10-09 | 2024-10-09 | 1804 | 1806
3105 | 1806 | Future Task |  |  | I-WP117 | Nikki Klein | Review | I-WP117 Role Mapping Handbook - Collaborative Review and Update | 10 hrs | 10 days | 2024-10-10 | 2024-10-23 | 1805 | 1807
3106 | 1807 | Future Task |  |  | I-WP117 | Nikki Klein | Review | I-WP117 Role Mapping Handbook - Style Guide Review | 8 hrs | 1 day | 2024-10-24 | 2024-10-24 | 1806 | 1808
3107 | 1808 | Future Task |  |  | I-WP117 | Nikki Klein | Review | I-WP117 Role Mapping Handbook - Final Review and Update | 10 hrs | 5 days | 2024-10-25 | 2024-10-31 | 1807 | 1809
3108 | 1809 | Future Task |  |  | I-WP117 | Nikki Klein | Approve | I-WP117 Role Mapping Handbook - Approve | 0 hrs | 0 days | 2024-10-31 | 2024-10-31 | 1808
3109 | 1810 | Future Task | Yes |  | I-WP118 | Nikki Klein |  | I-WP118 Role Mapping Worksheet | 156 hrs | 193 days | 2024-06-03 | 2025-03-10
3110 | 1811 | Future Task |  |  | I-WP118 | Carolyn Hicks | Create | WPED - I-WP118 - Role Mapping Worksheet - Create | 10 hrs | 10 days | 2024-06-03 | 2024-06-14 | 1 | 1812
3111 | 1812 | Future Task |  |  | I-WP118 | Carolyn Hicks | Submit | WPED - I-WP118 - Role Mapping Worksheet - Submit | 0 hrs | 0 days | 2024-06-14 | 2024-06-14 | 1811 | 1813
3112 | 1813 | Future Task |  |  | I-WP118 | Carolyn Hicks | Review | WPED - I-WP118 - Role Mapping Worksheet - Collaborative Review and Update | 10 hrs | 10 days | 2024-06-17 | 2024-06-28 | 1812 | 1814
3113 | 1814 | Future Task |  |  | I-WP118 | Carolyn Hicks | Approve | WPED - I-WP118 - Role Mapping Worksheet - Approve | 0 hrs | 0 days | 2024-06-28 | 2024-06-28 | 1813 | 1815
5701 | 1815 | Future Task |  |  | I-WP118 | Nikki Klein | Create | I-WP118 Role Mapping Worksheet <Activities per WPED> | 100 hrs | 125 days | 2024-08-14 | 2025-02-13 | 1814,1803SS+40 days,1863SS+40 days,579 | 1816
3114 | 1816 | Future Task |  |  | I-WP118 | Nikki Klein | Submit | I-WP118 Role Mapping Worksheet - Submit | 0 hrs | 0 days | 2025-02-13 | 2025-02-13 | 1815 | 1817
3115 | 1817 | Future Task |  |  | I-WP118 | Nikki Klein | Review | I-WP118 Role Mapping Worksheet - Dept QC | 8 hrs | 1 day | 2025-02-14 | 2025-02-14 | 1816 | 1818
3116 | 1818 | Future Task |  |  | I-WP118 | Nikki Klein | Review | I-WP118 Role Mapping Worksheet - Collaborative Review and Update | 10 hrs | 10 days | 2025-02-17 | 2025-02-28 | 1817 | 1819
3117 | 1819 | Future Task |  |  | I-WP118 | Nikki Klein | Review | I-WP118 Role Mapping Worksheet - Style Guide Review | 8 hrs | 1 day | 2025-03-03 | 2025-03-03 | 1818 | 1820
3118 | 1820 | Future Task |  |  | I-WP118 | Nikki Klein | Review | I-WP118 Role Mapping Worksheet - Final Review and Update | 10 hrs | 5 days | 2025-03-04 | 2025-03-10 | 1819 | 1821
3119 | 1821 | Future Task |  |  | I-WP118 | Nikki Klein | Approve | I-WP118 Role Mapping Worksheet - Approve | 0 hrs | 0 days | 2025-03-10 | 2025-03-10 | 1820 | 568
3120 | 1822 | Future Task |  |  | I-WP119 | Nikki Klein |  | I-WP119 Change Impact Analysis | 66 hrs | 188 days | 2023-11-01 | 2024-07-31
3121 | 1823 | Future Task |  |  | I-WP119 | Carolyn Hicks | Create | WPED - I-WP119 - Change Impact Analysis - Create | 10 hrs | 10 days | 2023-11-01 | 2023-11-15 | 1 | 1824
3122 | 1824 | Future Task |  |  | I-WP119 | Carolyn Hicks | Submit | WPED - I-WP119 - Change Impact Analysis - Submit | 0 hrs | 0 days | 2023-11-15 | 2023-11-15 | 1823 | 1825
3123 | 1825 | Future Task |  |  | I-WP119 | Carolyn Hicks | Review | WPED - I-WP119 - Change Impact Analysis - Collaborative Review and Update | 10 hrs | 10 days | 2023-11-16 | 2023-12-01 | 1824 | 1826
3124 | 1826 | Future Task |  |  | I-WP119 | Carolyn Hicks | Approve | WPED - I-WP119 - Change Impact Analysis | 0 hrs | 0 days | 2023-12-01 | 2023-12-01 | 1825 | 1827
6814 | 1827 | Future Task |  |  | I-WP119 | Nikki Klein | Submit | I-WP119 Change Impact Analysis <Activities per WPED> | 10 hrs | 151 days | 2023-12-04 | 2024-07-08 | 1826 | 1828
3125 | 1828 | Future Task |  |  | I-WP119 | Nikki Klein | Submit | I-WP119 Change Impact Analysis - Submit | 0 hrs | 0 days | 2024-07-08 | 2024-07-08 | 1827 | 1829
3126 | 1829 | Future Task |  |  | I-WP119 | Nikki Klein | Review | I-WP119 Change Impact Analysis - Dept QC | 8 hrs | 1 day | 2024-07-09 | 2024-07-09 | 1828 | 1830
3127 | 1830 | Future Task |  |  | I-WP119 | Nikki Klein | Review | I-WP119 Change Impact Analysis - Collaborative Review and Update | 10 hrs | 10 days | 2024-07-10 | 2024-07-23 | 1829 | 1831
3128 | 1831 | Future Task |  |  | I-WP119 | Nikki Klein | Review | I-WP119 Change Impact Analysis - Style Guide Review | 8 hrs | 1 day | 2024-07-24 | 2024-07-24 | 1830 | 1832
3129 | 1832 | Future Task |  |  | I-WP119 | Nikki Klein | Review | I-WP119 Change Impact Analysis - Final Review and Update | 10 hrs | 5 days | 2024-07-25 | 2024-07-31 | 1831 | 1833
3130 | 1833 | Future Task |  |  | I-WP119 | Nikki Klein | Approve | I-WP119 Change Impact Analysis - Approve | 0 hrs | 0 days | 2024-07-31 | 2024-07-31 | 1832
3131 | 1834 | Future Task |  |  | I-WP121 | Carolyn Hicks |  | I-WP121 Updated D27 Readiness Plan | 143 hrs | 82 days | 2023-10-02 | 2024-01-31
3132 | 1835 | Future Task |  |  | I-WP121 | Carolyn Hicks | Create | WPED - I-WP121 - Update D27 Readiness Plan - Create | 10 hrs | 10 days | 2023-10-02 | 2023-10-13 | 1 | 1836
3133 | 1836 | Future Task |  |  | I-WP121 | Carolyn Hicks | Submit | WPED - I-WP121 - Update D27 Readiness Plan - Submit | 0 hrs | 0 days | 2023-10-13 | 2023-10-13 | 1835 | 1837
3134 | 1837 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | WPED - I-WP121 - Update D27 Readiness Plan - Collaborative Review and Update | 10 hrs | 10 days | 2023-10-16 | 2023-10-27 | 1836 | 1838
3135 | 1838 | Future Task |  |  | I-WP121 | Carolyn Hicks | Approve | WPED - I-WP121 - Update D27 Readiness Plan - Approve | 0 hrs | 0 days | 2023-10-27 | 2023-10-27 | 1837 | 1839
5702 | 1839 | Future Task |  |  | I-WP121 | Carolyn Hicks | Create | I-WP121 Update D27 Readiness Plan <Activities per WPED> | 100 hrs | 45 days | 2023-10-30 | 2024-01-05 | 1838 | 1840
3136 | 1840 | Future Task |  |  | I-WP121 | Carolyn Hicks | Submit | I-WP121 Update D27 Readiness Plan - Submit | 0 hrs | 0 days | 2024-01-05 | 2024-01-05 | 1839 | 1841
3137 | 1841 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | I-WP121 Update D27 Readiness Plan - Dept QC | 1 hr | 1 day | 2024-01-08 | 2024-01-08 | 1840 | 1842
3138 | 1842 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | I-WP121Update D27 Readiness Plan - Collaborative Review and Update | 10 hrs | 10 days | 2024-01-09 | 2024-01-23 | 1841 | 1843
3139 | 1843 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | I-WP121 Update D27 Readiness Plan - Style Guide Review | 2 hrs | 1 day | 2024-01-24 | 2024-01-24 | 1842 | 1844
3140 | 1844 | Future Task |  |  | I-WP121 | Carolyn Hicks | Review | I-WP121 Update D27 Readiness Plan - Final Review and Update | 10 hrs | 5 days | 2024-01-25 | 2024-01-31 | 1843 | 1845
3141 | 1845 | Future Task |  |  | I-WP121 | Carolyn Hicks | Approve | I-WP121 Update D27 Readiness Plan - Approve | 0 hrs | 0 days | 2024-01-31 | 2024-01-31 | 1844
3142 | 1846 | Future Task |  |  | I-WP124 | Carolyn Hicks |  | I-WP124 Update D62 Workforce Transition Plan | 149 hrs | 82 days | 2023-10-02 | 2024-01-31
3143 | 1847 | Future Task |  |  | I-WP124 | Carolyn Hicks | Create | WPED - I-WP124 - Update D62 Workforce Transition Plan - Create | 10 hrs | 10 days | 2023-10-02 | 2023-10-13 | 1 | 1848
3144 | 1848 | Future Task |  |  | I-WP124 | Carolyn Hicks | Submit | WPED - I-WP124 - Update D62 Workforce Transition Plan - Submit | 0 hrs | 0 days | 2023-10-13 | 2023-10-13 | 1847 | 1849
3145 | 1849 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | WPED - I-WP124 - Update D62 Workforce Transition Plan - Collaborative Review and Update | 10 hrs | 10 days | 2023-10-16 | 2023-10-27 | 1848 | 1850
3146 | 1850 | Future Task |  |  | I-WP124 | Carolyn Hicks | Approve | WPED - I-WP124 - Update D62 Workforce Transition Plan - Approve | 0 hrs | 0 days | 2023-10-27 | 2023-10-27 | 1849 | 1851
5703 | 1851 | Future Task |  |  | I-WP124 | Carolyn Hicks | Create | I-WP124 Update D62 Workforce Transition Plan <Activities per WPED> | 100 hrs | 45 days | 2023-10-30 | 2024-01-05 | 1850 | 1852
3147 | 1852 | Future Task |  |  | I-WP124 | Carolyn Hicks | Submit | I-WP124 Update D62 Workforce Transition Plan - Submit | 0 hrs | 0 days | 2024-01-05 | 2024-01-05 | 1851 | 1853
3148 | 1853 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | I-WP124 Update D62 Workforce Transition Plan - Dept QC | 1 hr | 1 day | 2024-01-08 | 2024-01-08 | 1852 | 1854
3149 | 1854 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | I-WP124Update D62 Workforce Transition Plan - Collaborative Review and Update | 10 hrs | 10 days | 2024-01-09 | 2024-01-23 | 1853 | 1855
3150 | 1855 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | I-WP124 Update D62 Workforce Transition Plan - Style Guide Review | 8 hrs | 1 day | 2024-01-24 | 2024-01-24 | 1854 | 1856
3151 | 1856 | Future Task |  |  | I-WP124 | Carolyn Hicks | Review | I-WP124 Update D62 Workforce Transition Plan - Final Review and Update | 10 hrs | 5 days | 2024-01-25 | 2024-01-31 | 1855 | 1857
3152 | 1857 | Future Task |  |  | I-WP124 | Carolyn Hicks | Approve | I-WP124 Update D62 Workforce Transition Plan - Approve | 0 hrs | 0 days | 2024-01-31 | 2024-01-31 | 1856
6777 | 1858 | Late | Yes |  | I-WP126 | Nikki Klein |  | I-WP126 Readiness Workplan | 57 hrs | 62 days | 2023-05-08 | 2023-08-03
6778 | 1859 | Late |  |  | I-WP126 | Carolyn Hicks | Create | WPED - I-WP126 - Readiness Workplan - Create | 10 hrs | 10 days | 2023-05-08 | 2023-05-19 | 1 | 1860
6779 | 1860 | Late |  |  | I-WP126 | Carolyn Hicks | Submit | WPED - I-WP126 - Readiness Workplan - Submit | 0 hrs | 0 days | 2023-05-19 | 2023-05-19 | 1859 | 1861
6780 | 1861 | Late |  |  | I-WP126 | Carolyn Hicks | Review | WPED - I-WP126 - Readiness Workplan - Collaborative Review and Update | 10 hrs | 10 days | 2023-05-22 | 2023-06-05 | 1860 | 1862
6781 | 1862 | Future Task |  |  | I-WP126 | Carolyn Hicks | Approve | WPED - I-WP126 - Readiness Workplan - Approve | 0 hrs | 0 days | 2023-06-05 | 2023-06-05 | 1861 | 1863
6782 | 1863 | Future Task |  |  | I-WP126 | Nikki Klein | Create | I-WP126 Readiness Workplan <Activities per WPED> | 10 hrs | 25 days | 2023-06-06 | 2023-07-11 | 1862 | 1864,1815SS+40 days
6783 | 1864 | Future Task |  |  | I-WP126 | Nikki Klein | Submit | I-WP126 Readiness Workplan - Submit | 0 hrs | 0 days | 2023-07-11 | 2023-07-11 | 1863 | 1865
6784 | 1865 | Future Task |  |  | I-WP126 | Nikki Klein | Review | I-WP126 Readiness Workplan - Dept QC | 1 hr | 1 day | 2023-07-12 | 2023-07-12 | 1864 | 1866
6785 | 1866 | Future Task |  |  | I-WP126 | Nikki Klein | Review | I-WP126 Readiness Workplan - Collaborative Review and Update | 8 hrs | 10 days | 2023-07-13 | 2023-07-26 | 1865 | 1867
6786 | 1867 | Future Task |  |  | I-WP126 | Nikki Klein | Review | I-WP126 Readiness Workplan - Style Guide Review | 8 hrs | 1 day | 2023-07-27 | 2023-07-27 | 1866 | 1868
6787 | 1868 | Future Task |  |  | I-WP126 | Nikki Klein | Review | I-WP126 Readiness Workplan - Final Review and Update | 10 hrs | 5 days | 2023-07-28 | 2023-08-03 | 1867 | 1869
6788 | 1869 | Future Task |  |  | I-WP126 | Nikki Klein | Approve | I-WP126 Readiness Workplan - Approve | 0 hrs | 0 days | 2023-08-03 | 2023-08-03 | 1868
3 | 1870 | Future Task | [5 empty] | Production Support | 1,863 hrs | 619 days | 2025-02-03 | 2027-07-15
5850 | 1871 | Future Task | [5 empty] | Hypercare | 517 hrs | 336 days | 2025-02-03 | 2026-06-01
5852 | 1872 | Future Task |  |  | D664 | Bryan Sohayda |  | D664 - Development of the Hypercare Support Plan | 205 hrs | 87 days | 2025-02-03 | 2025-06-04
5853 | 1873 | Future Task |  |  | D664 | Bryan Sohayda | Create | DED D664 - Development of the Hypercare Support Plan - Create | 8 hrs | 10 days | 2025-02-03 | 2025-02-14 | 1 | 1874,1943SS | 2025-02-03
5854 | 1874 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DED D664 - Development of the Hypercare Support Plan - Submit | 0 hrs | 0 days | 2025-02-14 | 2025-02-14 | 1873 | 1875
5855 | 1875 | Future Task |  |  | D664 | Bryan Sohayda | Review | DED D664 - Development of the Hypercare Support Plan - Collaborative Review | 16 hrs | 10 days | 2025-02-17 | 2025-02-28 | 1874 | 1876
5856 | 1876 | Future Task |  |  | D664 | Bryan Sohayda | Approve | DED D664 - Development of the Hypercare Support Plan - Approve | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 1875 | 1877
5857 | 1877 | Future Task |  |  | D664 | Bryan Sohayda |  | Development of the Hypercare Support Plan | 20 hrs | 50 days | 2025-03-03 | 2025-05-09 | 1876 | 1878SS,1884
5858 | 1878 | Future Task |  |  | D664 | Bryan Sohayda |  | Define and document hypercare support processes and procedures | 20 hrs | 10 days | 2025-03-03 | 2025-03-14 | 1877SS | 1879
5859 | 1879 | Future Task |  |  | D664 | Bryan Sohayda |  | Review hypercare support processes and procedures draft | 20 hrs | 5 days | 2025-03-17 | 2025-03-21 | 1878 | 1880
5860 | 1880 | Future Task |  |  | D664 | Bryan Sohayda |  | Define and document tools used for hypercare support activities | 20 hrs | 5 days | 2025-03-24 | 2025-03-28 | 1879 | 1881
5861 | 1881 | Future Task |  |  | D664 | Bryan Sohayda |  | Review tools used for hypercare activities draft | 20 hrs | 5 days | 2025-03-31 | 2025-04-04 | 1880 | 1882
5862 | 1882 | Future Task |  |  | D664 | Bryan Sohayda |  | Determine and document resource capacity and skills needed | 20 hrs | 5 days | 2025-04-07 | 2025-04-11 | 1881 | 1883
5863 | 1883 | Future Task |  |  | D664 | Bryan Sohayda |  | Review resource capacity and skills needed draft | 20 hrs | 5 days | 2025-04-14 | 2025-04-18 | 1882 | 1884
5864 | 1884 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DEL D664 - Development of the Hypercare Support Plan - Draft Submission | 0 hrs | 0 days | 2025-05-09 | 2025-05-09 | 18771883 | 1885
5865 | 1885 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Pre-Submission Collaborative Review | 12 hrs | 5 days | 2025-05-12 | 2025-05-16 | 1884 | 1886
5866 | 1886 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Style Guide Review | 1 hr | 1 day | 2025-05-19 | 2025-05-19 | 1885 | 1887
5867 | 1887 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Final Collaborative Review | 12 hrs | 5 days | 2025-05-20 | 2025-05-27 | 1886 | 1888
5868 | 1888 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Accenture QC | 4 hrs | 2 days | 2025-05-28 | 2025-05-29 | 1887 | 1889
5869 | 1889 | Future Task |  |  | D664 | Bryan Sohayda | Submit | DEL D664 - Development of the Hypercare Support Plan - Submit | 0 hrs | 0 days | 2025-05-29 | 2025-05-29 | 1888 | 1890
5870 | 1890 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Department QC | 4 hrs | 1 day | 2025-05-30 | 2025-05-30 | 1889 | 1891
5871 | 1891 | Future Task |  |  | D664 | Bryan Sohayda | Review | DEL D664 - Development of the Hypercare Support Plan - Contract Manager Review | 8 hrs | 3 days | 2025-06-02 | 2025-06-04 | 1890 | 1892
5872 | 1892 | Future Task |  |  | D664 | Bryan Sohayda | Accept | DEL D664 - Development of the Hypercare Support Plan - Accept | 0 hrs | 0 days | 2025-06-04 | 2025-06-04 | 1891 | 1894 | 2025-06-01
5873 | 1893 | Future Task |  |  | D680 | Bryan Sohayda |  | D680 - Hypercare Monthly Deliverable – January 2026 | 153 hrs | 80 days | 2025-11-03 | 2026-03-02
5874 | 1894 | Future Task |  |  | D680-D683 | Bryan Sohayda | Create | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Create | 80 hrs | 10 days | 2025-11-03 | 2025-11-17 | 1892 | 1895
5875 | 1895 | Future Task |  |  | D680-D683 | Bryan Sohayda | Submit | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Submit | 0 hrs | 0 days | 2025-11-17 | 2025-11-17 | 1894 | 1896
5876 | 1896 | Future Task |  |  | D680-D683 | Bryan Sohayda | Review | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Collaborative Review | 20 hrs | 10 days | 2025-11-18 | 2025-12-03 | 1895 | 1897
7150 | 1897 | Future Task |  |  | D680-D683 | Bryan Sohayda | Approve | DED D680 - D683 - Hypercare Monthly Deliverables – January 2026 - April 2026 - Approve | 0 hrs | 0 days | 2025-11-25 | 2025-11-25 | 1896 | 1898FS+44 days
5877 | 1898 | Future Task |  |  | D680 | Bryan Sohayda |  | Create D680 - Hypercare Monthly Deliverable – January 2026 | 4 hrs | 4 days | 2026-02-02 | 2026-02-05 | 1897FS+44 days | 1899
5878 | 1899 | Future Task |  |  | D680 | Bryan Sohayda | Submit | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Draft Submission | 0 hrs | 0 days | 2026-02-05 | 2026-02-05 | 1898 | 1900
5879 | 1900 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-02-06 | 2026-02-12 | 1899 | 1901
5880 | 1901 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Style Guide Review | 1 hr | 1 day | 2026-02-13 | 2026-02-13 | 1900 | 1902
5881 | 1902 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-02-16 | 2026-02-20 | 1901 | 1903
5882 | 1903 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Accenture QC | 4 hrs | 2 days | 2026-02-23 | 2026-02-24 | 1902 | 1904
5883 | 1904 | Future Task |  |  | D680 | Bryan Sohayda | Submit | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Submit | 0 hrs | 0 days | 2026-02-24 | 2026-02-24 | 1903 | 1905
5884 | 1905 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Department QC | 4 hrs | 1 day | 2026-02-25 | 2026-02-25 | 1904 | 1906
5885 | 1906 | Future Task |  |  | D680 | Bryan Sohayda | Review | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-02-26 | 2026-03-02 | 1905 | 1907
5886 | 1907 | Future Task |  |  | D680 | Bryan Sohayda | Accept | DEL D680 - Hypercare Monthly Deliverable – January 2026 - Accept | 0 hrs | 0 days | 2026-03-02 | 2026-03-02 | 1906 | 1909FS-1 day
5887 | 1908 | Future Task |  |  | D681 | Bryan Sohayda |  | D681 - Hypercare Monthly Deliverable – February 2026 | 53 hrs | 21 days | 2026-03-02 | 2026-03-30
5888 | 1909 | Future Task |  |  | D681 | Bryan Sohayda |  | Create D681 - Hypercare Monthly Deliverable – February 2026 | 4 hrs | 4 days | 2026-03-02 | 2026-03-05 | 1907FS-1 day | 1910
5889 | 1910 | Future Task |  |  | D681 | Bryan Sohayda | Submit | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Draft Submission | 0 hrs | 0 days | 2026-03-05 | 2026-03-05 | 1909 | 1911
5890 | 1911 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-03-06 | 2026-03-12 | 1910 | 1912
5891 | 1912 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Style Guide Review | 1 hr | 1 day | 2026-03-13 | 2026-03-13 | 1911 | 1913
5892 | 1913 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-03-16 | 2026-03-20 | 1912 | 1914
5893 | 1914 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Accenture QC | 4 hrs | 2 days | 2026-03-23 | 2026-03-24 | 1913 | 1915
5894 | 1915 | Future Task |  |  | D681 | Bryan Sohayda | Submit | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Submit | 0 hrs | 0 days | 2026-03-24 | 2026-03-24 | 1914 | 1916
5895 | 1916 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Department QC | 4 hrs | 1 day | 2026-03-25 | 2026-03-25 | 1915 | 1917
5896 | 1917 | Future Task |  |  | D681 | Bryan Sohayda | Review | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-03-26 | 2026-03-30 | 1916 | 1918
5897 | 1918 | Future Task |  |  | D681 | Bryan Sohayda | Accept | DEL D681 - Hypercare Monthly Deliverable – February 2026 - Accept | 0 hrs | 0 days | 2026-03-30 | 2026-03-30 | 1917 | 1920
5898 | 1919 | Future Task |  |  | D682 | Bryan Sohayda |  | D682 - Hypercare Monthly Deliverable – March 2026 | 53 hrs | 21 days | 2026-04-01 | 2026-04-29
5899 | 1920 | Future Task |  |  | D682 | Bryan Sohayda |  | Create D682 - Hypercare Monthly Deliverable – March 2026 | 4 hrs | 4 days | 2026-04-01 | 2026-04-06 | 1918 | 1921
5900 | 1921 | Future Task |  |  | D682 | Bryan Sohayda | Submit | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Draft Submission | 0 hrs | 0 days | 2026-04-06 | 2026-04-06 | 1920 | 1922
5901 | 1922 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-04-07 | 2026-04-13 | 1921 | 1923
5902 | 1923 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Style Guide Review | 1 hr | 1 day | 2026-04-14 | 2026-04-14 | 1922 | 1924
5903 | 1924 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-04-15 | 2026-04-21 | 1923 | 1925
5904 | 1925 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Accenture QC | 4 hrs | 2 days | 2026-04-22 | 2026-04-23 | 1924 | 1926
5905 | 1926 | Future Task |  |  | D682 | Bryan Sohayda | Submit | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Submit | 0 hrs | 0 days | 2026-04-23 | 2026-04-23 | 1925 | 1927
5906 | 1927 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Department QC | 4 hrs | 1 day | 2026-04-24 | 2026-04-24 | 1926 | 1928
5907 | 1928 | Future Task |  |  | D682 | Bryan Sohayda | Review | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-04-27 | 2026-04-29 | 1927 | 1929
5908 | 1929 | Future Task |  |  | D682 | Bryan Sohayda | Accept | DEL D682 - Hypercare Monthly Deliverable – March 2026 - Accept | 0 hrs | 0 days | 2026-04-29 | 2026-04-29 | 1928 | 1931
5909 | 1930 | Future Task |  |  | D683 | Bryan Sohayda |  | D683 - Hypercare Monthly Deliverable – April 2026 | 53 hrs | 21 days | 2026-05-01 | 2026-06-01
5910 | 1931 | Future Task |  |  | D683 | Bryan Sohayda |  | Create D683 - Hypercare Monthly Deliverable – April 2026 | 4 hrs | 4 days | 2026-05-01 | 2026-05-06 | 1929 | 1932
5911 | 1932 | Future Task |  |  | D683 | Bryan Sohayda | Submit | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Draft Submission | 0 hrs | 0 days | 2026-05-06 | 2026-05-06 | 1931 | 1933
5912 | 1933 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-05-07 | 2026-05-13 | 1932 | 1934
5913 | 1934 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Style Guide Review | 1 hr | 1 day | 2026-05-14 | 2026-05-14 | 1933 | 1935
5914 | 1935 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-05-15 | 2026-05-21 | 1934 | 1936
5915 | 1936 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Accenture QC | 4 hrs | 2 days | 2026-05-22 | 2026-05-26 | 1935 | 1937
5916 | 1937 | Future Task |  |  | D683 | Bryan Sohayda | Submit | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Submit | 0 hrs | 0 days | 2026-05-26 | 2026-05-26 | 1936 | 1938
5917 | 1938 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Department QC | 4 hrs | 1 day | 2026-05-27 | 2026-05-27 | 1937 | 1939
5918 | 1939 | Future Task |  |  | D683 | Bryan Sohayda | Review | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-05-28 | 2026-06-01 | 1938 | 1940
5919 | 1940 | Future Task |  |  | D683 | Bryan Sohayda | Accept | DEL D683 - Hypercare Monthly Deliverable – April 2026 - Accept | 0 hrs | 0 days | 2026-06-01 | 2026-06-01 | 1939
5851 | 1941 | Future Task | [5 empty] | Post-Implementation Support | 1,346 hrs | 619 days | 2025-02-03 | 2027-07-15
5488 | 1942 | Future Task |  |  | D665 | Bryan Sohayda |  | D665 - Updated Post-Implementation Support Plan | 154 hrs | 92 days | 2025-02-03 | 2025-06-11
5489 | 1943 | Future Task |  |  | D665 | Bryan Sohayda | Create | DED D665 - Updated Post-Implementation Support Plan - Create | 8 hrs | 10 days | 2025-02-03 | 2025-02-14 | 1873SS | 1944
5490 | 1944 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DED D665 - Updated Post-Implementation Support Plan - Submit | 0 hrs | 0 days | 2025-02-14 | 2025-02-14 | 1943 | 1945
5491 | 1945 | Future Task |  |  | D665 | Bryan Sohayda | Review | DED D665 - Updated Post-Implementation Support Plan - Collaborative Review | 16 hrs | 10 days | 2025-02-17 | 2025-02-28 | 1944 | 1946
5492 | 1946 | Future Task |  |  | D665 | Bryan Sohayda | Approve | DED D665 - Updated Post-Implementation Support Plan - Approve | 0 hrs | 0 days | 2025-02-28 | 2025-02-28 | 1945 | 1947
5493 | 1947 | Future Task |  |  | D665 | Bryan Sohayda |  | Create Post Implementation Support Processes and Procedures | 20 hrs | 15 days | 2025-03-03 | 2025-03-21 | 1946 | 1948
5494 | 1948 | Future Task |  |  | D665 | Bryan Sohayda |  | Document Post Implementation Support Tools | 20 hrs | 10 days | 2025-03-24 | 2025-04-04 | 1947 | 1949
5495 | 1949 | Future Task |  |  | D665 | Bryan Sohayda |  | Post-Implementation Support Resource Capacity and Skills | 20 hrs | 10 days | 2025-04-07 | 2025-04-18 | 1948 | 1950
5496 | 1950 | Future Task |  |  | D665 | Bryan Sohayda |  | Full draft review pre-submission | 20 hrs | 20 days | 2025-04-21 | 2025-05-16 | 1949 | 1951
5497 | 1951 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DEL D665 - Updated Post-Implementation Support Plan - Draft Submission | 0 hrs | 0 days | 2025-05-16 | 2025-05-16 | 1950 | 1952
5498 | 1952 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Pre-Submission Collaborative Review | 12 hrs | 5 days | 2025-05-19 | 2025-05-23 | 1951 | 1953
5499 | 1953 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Style Guide Review | 1 hr | 1 day | 2025-05-27 | 2025-05-27 | 1952 | 1954
5500 | 1954 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Final Collaborative Review | 21 hrs | 5 days | 2025-05-28 | 2025-06-03 | 1953 | 1955
5501 | 1955 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Accenture QC | 4 hrs | 2 days | 2025-06-04 | 2025-06-05 | 1954 | 1956
5502 | 1956 | Future Task |  |  | D665 | Bryan Sohayda | Submit | DEL D665 - Updated Post-Implementation Support Plan - Submit | 0 hrs | 0 days | 2025-06-05 | 2025-06-05 | 1955 | 1957
5503 | 1957 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Department QC | 4 hrs | 1 day | 2025-06-06 | 2025-06-06 | 1956 | 1958
5504 | 1958 | Future Task |  |  | D665 | Bryan Sohayda | Review | DEL D665 - Updated Post-Implementation Support Plan - Contract Manager Review | 8 hrs | 3 days | 2025-06-09 | 2025-06-11 | 1957 | 1959
5505 | 1959 | Future Task |  |  | D665 | Bryan Sohayda | Accept | DEL D665 - Updated Post-Implementation Support Plan - Accept | 0 hrs | 0 days | 2025-06-11 | 2025-06-11 | 1958 |  | 2025-06-01
5759 | 1960 | Future Task |  |  | D684 | Bryan Sohayda |  | D684 - Post-Implementation Support Monthly Deliverable – May 2026 | 122 hrs | 85 days | 2026-03-02 | 2026-06-29
5760 | 1961 | Future Task |  |  | D684-D691 | Bryan Sohayda | Create | DED Create - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 8 hrs | 5 days | 2026-03-02 | 2026-03-06 | 1 | 1962
5761 | 1962 | Future Task |  |  | D684-D691 | Bryan Sohayda | Submit | DED Submit - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 0 hrs | 0 days | 2026-03-06 | 2026-03-06 | 1961 | 1963
5762 | 1963 | Future Task |  |  | D684-D691 | Bryan Sohayda | Review | DED Collaborative Review & Accept - D684 - D691 - Post-Implementation Support Monthly Deliverable – May 2026 - December 2026 | 20 hrs | 10 days | 2026-03-09 | 2026-03-20 | 1962 | 1964
5763 | 1964 | Future Task |  |  | D684 | Bryan Sohayda |  | Create D684 - Post-Implementation Support Monthly Deliverable – May 2026 | 4 hrs | 4 days | 2026-06-01 | 2026-06-04 | 1963 | 1965
5764 | 1965 | Future Task |  |  | D684 | Bryan Sohayda | Submit | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Draft Submission | 0 hrs | 0 days | 2026-06-04 | 2026-06-04 | 1964 | 1966
5765 | 1966 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Pre-Submission Collaborative Review | 20 hrs | 5 days | 2026-06-05 | 2026-06-11 | 1965 | 1967
5766 | 1967 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Style Guide Review | 8 hrs | 1 day | 2026-06-12 | 2026-06-12 | 1966 | 1968
5767 | 1968 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Final Collaborative Review | 20 hrs | 5 days | 2026-06-15 | 2026-06-19 | 1967 | 1969
5768 | 1969 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Accenture QC | 16 hrs | 2 days | 2026-06-22 | 2026-06-23 | 1968 | 1970
5769 | 1970 | Future Task |  |  | D684 | Bryan Sohayda | Submit | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Submit | 0 hrs | 0 days | 2026-06-23 | 2026-06-23 | 1969 | 1971
5770 | 1971 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Department QC | 2 hrs | 1 day | 2026-06-24 | 2026-06-24 | 1970 | 1972
5771 | 1972 | Future Task |  |  | D684 | Bryan Sohayda | Review | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Contract Manager Review | 24 hrs | 3 days | 2026-06-25 | 2026-06-29 | 1971 | 1973
5772 | 1973 | Future Task |  |  | D684 | Bryan Sohayda | Accept | DEL D684 - Post-Implementation Support Monthly Deliverable – May 2026 - Accept | 0 hrs | 0 days | 2026-06-29 | 2026-06-29 | 1972 | 1975
5773 | 1974 | Future Task |  |  | D685 | Bryan Sohayda |  | D685 - Post-Implementation Support Monthly Deliverable – June 2026 | 53 hrs | 21 days | 2026-07-01 | 2026-07-30
5774 | 1975 | Future Task |  |  | D685 | Bryan Sohayda |  | Create D685 - Post-Implementation Support Monthly Deliverable – June 2026 | 4 hrs | 4 days | 2026-07-01 | 2026-07-07 | 1973 | 1976
5775 | 1976 | Future Task |  |  | D685 | Bryan Sohayda | Submit | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Draft Submission | 0 hrs | 0 days | 2026-07-07 | 2026-07-07 | 1975 | 1977
5776 | 1977 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-07-08 | 2026-07-14 | 1976 | 1978
5777 | 1978 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Style Guide Review | 1 hr | 1 day | 2026-07-15 | 2026-07-15 | 1977 | 1979
5778 | 1979 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-07-16 | 2026-07-22 | 1978 | 1980
5779 | 1980 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Accenture QC | 4 hrs | 2 days | 2026-07-23 | 2026-07-24 | 1979 | 1981
5780 | 1981 | Future Task |  |  | D685 | Bryan Sohayda | Submit | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Submit | 0 hrs | 0 days | 2026-07-24 | 2026-07-24 | 1980 | 1982
5781 | 1982 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Department QC | 4 hrs | 1 day | 2026-07-27 | 2026-07-27 | 1981 | 1983
5782 | 1983 | Future Task |  |  | D685 | Bryan Sohayda | Review | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-07-28 | 2026-07-30 | 1982 | 1984
5783 | 1984 | Future Task |  |  | D685 | Bryan Sohayda | Accept | DEL D685 - Post-Implementation Support Monthly Deliverable – June 2026 - Accept | 0 hrs | 0 days | 2026-07-30 | 2026-07-30 | 1983 | 1986
5784 | 1985 | Future Task |  |  | D686 | Bryan Sohayda |  | D686 - Post-Implementation Support Monthly Deliverable – July 2026 | 53 hrs | 21 days | 2026-08-03 | 2026-08-31
5785 | 1986 | Future Task |  |  | D686 | Bryan Sohayda |  | Create D686 - Post-Implementation Support Monthly Deliverable – July 2026 | 4 hrs | 4 days | 2026-08-03 | 2026-08-06 | 1984 | 1987
5786 | 1987 | Future Task |  |  | D686 | Bryan Sohayda | Submit | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Draft Submission | 0 hrs | 0 days | 2026-08-06 | 2026-08-06 | 1986 | 1988
5787 | 1988 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-08-07 | 2026-08-13 | 1987 | 1989
5788 | 1989 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Style Guide Review | 1 hr | 1 day | 2026-08-14 | 2026-08-14 | 1988 | 1990
5789 | 1990 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-08-17 | 2026-08-21 | 1989 | 1991
5790 | 1991 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Accenture QC | 4 hrs | 2 days | 2026-08-24 | 2026-08-25 | 1990 | 1992
5791 | 1992 | Future Task |  |  | D686 | Bryan Sohayda | Submit | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Submit | 0 hrs | 0 days | 2026-08-25 | 2026-08-25 | 1991 | 1993
5792 | 1993 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Department QC | 4 hrs | 1 day | 2026-08-26 | 2026-08-26 | 1992 | 1994
5793 | 1994 | Future Task |  |  | D686 | Bryan Sohayda | Review | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-08-27 | 2026-08-31 | 1993 | 1995
5794 | 1995 | Future Task |  |  | D686 | Bryan Sohayda | Accept | DEL D686 - Post-Implementation Support Monthly Deliverable – July 2026 - Accept | 0 hrs | 0 days | 2026-08-31 | 2026-08-31 | 1994 | 1997
5795 | 1996 | Future Task |  |  | D687 | Bryan Sohayda |  | D687 - Post-Implementation Support Monthly Deliverable – August 2026 | 53 hrs | 21 days | 2026-09-01 | 2026-09-30
5796 | 1997 | Future Task |  |  | D687 | Bryan Sohayda |  | Create D687 - Post-Implementation Support Monthly Deliverable – August 2026 | 4 hrs | 4 days | 2026-09-01 | 2026-09-04 | 1995 | 1998
5797 | 1998 | Future Task |  |  | D687 | Bryan Sohayda | Submit | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Draft Submission | 0 hrs | 0 days | 2026-09-04 | 2026-09-04 | 1997 | 1999
5798 | 1999 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-09-08 | 2026-09-14 | 1998 | 2000
5799 | 2000 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Style Guide Review | 1 hr | 1 day | 2026-09-15 | 2026-09-15 | 1999 | 2001
5800 | 2001 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-09-16 | 2026-09-22 | 2000 | 2002
5801 | 2002 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Accenture QC | 4 hrs | 2 days | 2026-09-23 | 2026-09-24 | 2001 | 2003
5802 | 2003 | Future Task |  |  | D687 | Bryan Sohayda | Submit | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Submit | 0 hrs | 0 days | 2026-09-24 | 2026-09-24 | 2002 | 2004
5803 | 2004 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Department QC | 4 hrs | 1 day | 2026-09-25 | 2026-09-25 | 2003 | 2005
5804 | 2005 | Future Task |  |  | D687 | Bryan Sohayda | Review | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-09-28 | 2026-09-30 | 2004 | 2006
5805 | 2006 | Future Task |  |  | D687 | Bryan Sohayda | Accept | DEL D687 - Post-Implementation Support Monthly Deliverable – August 2026 - Accept | 0 hrs | 0 days | 2026-09-30 | 2026-09-30 | 2005 | 2008
5806 | 2007 | Future Task |  |  | D688 | Bryan Sohayda |  | D688 - Post-Implementation Support Monthly Deliverable – September 2026 | 53 hrs | 21 days | 2026-10-01 | 2026-10-29
5807 | 2008 | Future Task |  |  | D688 | Bryan Sohayda |  | Create D688 - Post-Implementation Support Monthly Deliverable – September 2026 | 4 hrs | 4 days | 2026-10-01 | 2026-10-06 | 2006 | 2009
5808 | 2009 | Future Task |  |  | D688 | Bryan Sohayda | Submit | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Draft Submission | 0 hrs | 0 days | 2026-10-06 | 2026-10-06 | 2008 | 2010
5809 | 2010 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-10-07 | 2026-10-13 | 2009 | 2011
5810 | 2011 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Style Guide Review | 1 hr | 1 day | 2026-10-14 | 2026-10-14 | 2010 | 2012
5811 | 2012 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-10-15 | 2026-10-21 | 2011 | 2013
5812 | 2013 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Accenture QC | 4 hrs | 2 days | 2026-10-22 | 2026-10-23 | 2012 | 2014
5813 | 2014 | Future Task |  |  | D688 | Bryan Sohayda | Submit | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Submit | 0 hrs | 0 days | 2026-10-23 | 2026-10-23 | 2013 | 2015
5814 | 2015 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Department QC | 4 hrs | 1 day | 2026-10-26 | 2026-10-26 | 2014 | 2016
5815 | 2016 | Future Task |  |  | D688 | Bryan Sohayda | Review | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-10-27 | 2026-10-29 | 2015 | 2017
5816 | 2017 | Future Task |  |  | D688 | Bryan Sohayda | Accept | DEL D688 - Post-Implementation Support Monthly Deliverable – September 2026 - Accept | 0 hrs | 0 days | 2026-10-29 | 2026-10-29 | 2016 | 2019
5817 | 2018 | Future Task |  |  | D689 | Bryan Sohayda |  | D689 - Post-Implementation Support Monthly Deliverable – October 2026 | 53 hrs | 18 days | 2026-11-02 | 2026-11-30
5818 | 2019 | Future Task |  |  | D689 | Bryan Sohayda |  | Create D689 - Post-Implementation Support Monthly Deliverable – October 2026 | 4 hrs | 4 days | 2026-11-02 | 2026-11-05 | 2017 | 2020,2052SS
5819 | 2020 | Future Task |  |  | D689 | Bryan Sohayda | Submit | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Draft Submission | 0 hrs | 0 days | 2026-11-05 | 2026-11-05 | 2019 | 2021
5820 | 2021 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Pre-Submission Collaborative Review | 16 hrs | 4 days | 2026-11-06 | 2026-11-12 | 2020 | 2022
5821 | 2022 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Style Guide Review | 1 hr | 1 day | 2026-11-13 | 2026-11-13 | 2021 | 2023
5822 | 2023 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Final Collaborative Review | 16 hrs | 3 days | 2026-11-16 | 2026-11-18 | 2022 | 2024
5823 | 2024 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Accenture QC | 4 hrs | 2 days | 2026-11-19 | 2026-11-20 | 2023 | 2025
5824 | 2025 | Future Task |  |  | D689 | Bryan Sohayda | Submit | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Submit | 0 hrs | 0 days | 2026-11-20 | 2026-11-20 | 2024 | 2026
5825 | 2026 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Department QC | 4 hrs | 1 day | 2026-11-23 | 2026-11-23 | 2025 | 2027
5826 | 2027 | Future Task |  |  | D689 | Bryan Sohayda | Review | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-11-24 | 2026-11-30 | 2026 | 2028
5827 | 2028 | Future Task |  |  | D689 | Bryan Sohayda | Accept | DEL D689 - Post-Implementation Support Monthly Deliverable – October 2026 - Accept | 0 hrs | 0 days | 2026-11-30 | 2026-11-30 | 2027 | 2030
5828 | 2029 | Future Task |  |  | D690 | Bryan Sohayda |  | D690 - Post-Implementation Support Monthly Deliverable – November 2026 | 53 hrs | 21 days | 2026-12-01 | 2026-12-30
5829 | 2030 | Future Task |  |  | D690 | Bryan Sohayda |  | Create D690 - Post-Implementation Support Monthly Deliverable – November 2026 | 4 hrs | 4 days | 2026-12-01 | 2026-12-04 | 2028 | 2031
5830 | 2031 | Future Task |  |  | D690 | Bryan Sohayda | Submit | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Draft Submission | 0 hrs | 0 days | 2026-12-04 | 2026-12-04 | 2030 | 2032
5831 | 2032 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2026-12-07 | 2026-12-11 | 2031 | 2033
5832 | 2033 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Style Guide Review | 1 hr | 1 day | 2026-12-14 | 2026-12-14 | 2032 | 2034
5833 | 2034 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Final Collaborative Review | 16 hrs | 5 days | 2026-12-15 | 2026-12-21 | 2033 | 2035
5834 | 2035 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Accenture QC | 4 hrs | 2 days | 2026-12-22 | 2026-12-23 | 2034 | 2036
5835 | 2036 | Future Task |  |  | D690 | Bryan Sohayda | Submit | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Submit | 0 hrs | 0 days | 2026-12-23 | 2026-12-23 | 2035 | 2037
5836 | 2037 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Department QC | 4 hrs | 1 day | 2026-12-24 | 2026-12-24 | 2036 | 2038
5837 | 2038 | Future Task |  |  | D690 | Bryan Sohayda | Review | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Contract Manager Review | 8 hrs | 3 days | 2026-12-28 | 2026-12-30 | 2037 | 2039
5838 | 2039 | Future Task |  |  | D690 | Bryan Sohayda | Accept | DEL D690 - Post-Implementation Support Monthly Deliverable – November 2026 - Accept | 0 hrs | 0 days | 2026-12-30 | 2026-12-30 | 2038 | 2041
5839 | 2040 | Future Task |  |  | D691 | Bryan Sohayda |  | D691 - Post-Implementation Support Monthly Deliverable – December 2026 | 53 hrs | 21 days | 2027-01-04 | 2027-02-02
5840 | 2041 | Future Task |  |  | D691 | Bryan Sohayda |  | Create D691 - Post-Implementation Support Monthly Deliverable – December 2026 | 4 hrs | 4 days | 2027-01-04 | 2027-01-07 | 2039 | 2042
5841 | 2042 | Future Task |  |  | D691 | Bryan Sohayda | Submit | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Draft Submission | 0 hrs | 0 days | 2027-01-07 | 2027-01-07 | 2041 | 2043
5842 | 2043 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2027-01-08 | 2027-01-14 | 2042 | 2044
5843 | 2044 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Style Guide Review | 1 hr | 1 day | 2027-01-15 | 2027-01-15 | 2043 | 2045
5844 | 2045 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Final Collaborative Review | 16 hrs | 5 days | 2027-01-19 | 2027-01-25 | 2044 | 2046
5845 | 2046 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Accenture QC | 4 hrs | 2 days | 2027-01-26 | 2027-01-27 | 2045 | 2047
5846 | 2047 | Future Task |  |  | D691 | Bryan Sohayda | Submit | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Submit | 0 hrs | 0 days | 2027-01-27 | 2027-01-27 | 2046 | 2048
5847 | 2048 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Department QC | 4 hrs | 1 day | 2027-01-28 | 2027-01-28 | 2047 | 2049
5848 | 2049 | Future Task |  |  | D691 | Bryan Sohayda | Review | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Contract Manager Review | 8 hrs | 3 days | 2027-01-29 | 2027-02-02 | 2048 | 2050
5849 | 2050 | Future Task |  |  | D691 | Bryan Sohayda | Accept | DEL D691 - Post-Implementation Support Monthly Deliverable – December 2026 - Accept | 0 hrs | 0 days | 2027-02-02 | 2027-02-02 | 2049
6704 | 2051 | Future Task |  |  | D692 | Stacey Terry |  | D692 - Tax Reporting Support CY 2026 (January 2027) | 179 hrs | 69 days | 2026-11-12 | 2027-02-23
6705 | 2052 | Future Task |  |  | D692 | Stacey Terry | Create | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Create | 8 hrs | 10 days | 2026-11-12 | 2026-11-25 | 2019SS | 2053 | 2026-11-12
6706 | 2053 | Future Task |  |  | D692 | Stacey Terry | Submit | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Submit | 0 hrs | 0 days | 2026-11-25 | 2026-11-25 | 2052 | 2054
6707 | 2054 | Future Task |  |  | D692 | Stacey Terry | Review | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Collaborative Review | 20 hrs | 10 days | 2026-11-30 | 2026-12-11 | 2053 | 2055
6708 | 2055 | Future Task |  |  | D692 | Stacey Terry | Approve | DED D692 - Tax Reporting Support CY 2026 (January 2027) - Approve | 0 hrs | 0 days | 2026-12-11 | 2026-12-11 | 2054 | 2056
6709 | 2056 | Future Task |  |  | D692 | Stacey Terry |  | Create Tax Reporting Checklist (2026) | 36 hrs | 18 days | 2026-12-14 | 2027-01-08 | 2055 | 2057FS-5 days,2058
6710 | 2057 | Future Task |  |  | D692 | Stacey Terry |  | Manage Year-end Checklist (2026) | 38 hrs | 19 days | 2027-01-04 | 2027-01-29 | 2056FS-5 days
6711 | 2058 | Future Task |  |  | D692 | Stacey Terry |  | Create initial Year-end Checklist (2027) | 28 hrs | 14 days | 2027-01-11 | 2027-01-29 | 2056 | 2059
6712 | 2059 | Future Task |  |  | D692 | Stacey Terry | Submit | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Draft Submission | 0 hrs | 0 days | 2027-01-29 | 2027-01-29 | 2058 | 2060
6713 | 2060 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Pre-Submission Collaborative Review | 16 hrs | 5 days | 2027-02-01 | 2027-02-05 | 2059 | 2061
6714 | 2061 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Style Guide Review | 1 hr | 1 day | 2027-02-08 | 2027-02-08 | 2060 | 2062
6715 | 2062 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Final Collaborative Review | 16 hrs | 5 days | 2027-02-09 | 2027-02-15 | 2061 | 2063
6716 | 2063 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Accenture QC | 4 hrs | 2 days | 2027-02-16 | 2027-02-17 | 2062 | 2064
6717 | 2064 | Future Task |  |  | D692 | Stacey Terry | Submit | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Submit | 0 hrs | 0 days | 2027-02-17 | 2027-02-17 | 2063 | 2065
6718 | 2065 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Department QC | 4 hrs | 1 day | 2027-02-18 | 2027-02-18 | 2064 | 2066
6719 | 2066 | Future Task |  |  | D692 | Stacey Terry | Review | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Contract Manager Review | 8 hrs | 3 days | 2027-02-19 | 2027-02-23 | 2065 | 2067
6720 | 2067 | Future Task |  |  | D692 | Stacey Terry | Accept | DEL D692 - Tax Reporting Support CY 2026 (January 2027) - Accept | 0 hrs | 0 days | 2027-02-23 | 2027-02-23 | 2066 |  | 2027-02-01
6721 | 2068 | Future Task | Maybe |  | D693 | Joy Schneider |  | D693 - Exit Transition Completion | 122 hrs | 67 days | 2027-04-12 | 2027-07-15
6722 | 2069 | Future Task |  |  | D693 | Joy Schneider | Create | DED D693 - Exit Transition Completion - Create | 6 hrs | 10 days | 2027-04-12 | 2027-04-23 | 2095 | 2070
6723 | 2070 | Future Task |  |  | D693 | Joy Schneider | Submit | DED D693 - Exit Transition Completion - Submit | 0 hrs | 0 days | 2027-04-23 | 2027-04-23 | 2069 | 2071
6724 | 2071 | Future Task |  |  | D693 | Joy Schneider | Review | DED D693 - Exit Transition Completion - Collaborative Review | 12 hrs | 10 days | 2027-04-26 | 2027-05-07 | 2070 | 2072
6725 | 2072 | Future Task |  |  | D693 | Joy Schneider | Approve | DED D693 - Exit Transition Completion - Approve | 0 hrs | 0 days | 2027-05-07 | 2027-05-07 | 2071 | 2073
6726 | 2073 | Future Task |  |  | D693 | Joy Schneider |  | D693 Review Status of Exit Transition Work Plan | 45 hrs | 15 days | 2027-05-10 | 2027-05-28 | 2072 | 2074
6727 | 2074 | Future Task |  |  | D693 | Joy Schneider |  | D693 Obtain Department Sign Off | 30 hrs | 15 days | 2027-06-01 | 2027-06-21 | 2073 | 2075
6728 | 2075 | Future Task |  |  | D693 | Joy Schneider | Submit | DEL D693 - Exit Transition Completion - Draft Submission | 0 hrs | 0 days | 2027-06-21 | 2027-06-21 | 2074 | 2076
6729 | 2076 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Pre-Submission Collaborative Review | 6 hrs | 5 days | 2027-06-22 | 2027-06-28 | 2075 | 2077
6730 | 2077 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Style Guide Review | 1 hr | 1 day | 2027-06-29 | 2027-06-29 | 2076 | 2078
6731 | 2078 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Final Collaborative Review | 6 hrs | 5 days | 2027-06-30 | 2027-07-07 | 2077 | 2079
6732 | 2079 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Accenture QC | 4 hrs | 2 days | 2027-07-08 | 2027-07-09 | 2078 | 2080
6733 | 2080 | Future Task |  |  | D693 | Joy Schneider | Submit | DEL D693 - Exit Transition Completion - Submit | 0 hrs | 0 days | 2027-07-09 | 2027-07-09 | 2079 | 2081
6734 | 2081 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Department QC | 4 hrs | 1 day | 2027-07-12 | 2027-07-12 | 2080 | 2082
6735 | 2082 | Future Task |  |  | D693 | Joy Schneider | Review | DEL D693 - Exit Transition Completion - Contract Manager Review | 8 hrs | 3 days | 2027-07-13 | 2027-07-15 | 2081 | 2083
6736 | 2083 | Future Task |  |  | D693 | Joy Schneider | Accept | DEL D693 - Exit Transition Completion - Accept | 0 hrs | 0 days | 2027-07-15 | 2027-07-15 | 2082 |  | 2027-07-01
5655 | 2084 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 - Exit Transition Work Plan | 398 hrs | 80 days | 2026-09-01 | 2026-12-28
5656 | 2085 | Future Task |  |  | WP428 | Joy Schneider | Create | WPED WP428 - Exit Transition Work Plan - Create | 8 hrs | 10 days | 2026-09-01 | 2026-09-15 | 1 | 2086
5657 | 2086 | Future Task |  |  | WP428 | Joy Schneider | Submit | WPED WP428 - Exit Transition Work Plan - Submit | 0 hrs | 0 days | 2026-09-15 | 2026-09-15 | 2085 | 2087
5658 | 2087 | Future Task |  |  | WP428 | Joy Schneider | Review | WPED WP428 - Exit Transition Work Plan - Review | 16 hrs | 10 days | 2026-09-16 | 2026-09-29 | 2086 | 2088
5659 | 2088 | Future Task |  |  | WP428 | Joy Schneider | Approve | WPED WP428 - Exit Transition Work Plan - Approve | 0 hrs | 0 days | 2026-09-29 | 2026-09-29 | 2087 | 2089
5660 | 2089 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 Develop Exit Transition Work Plan | 210 hrs | 15 days | 2026-09-30 | 2026-10-20 | 2088 | 2090
5661 | 2090 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 Determine Entry and Exit Criteria | 120 hrs | 15 days | 2026-10-21 | 2026-11-10 | 2089 | 2091
5662 | 2091 | Future Task |  |  | WP428 | Joy Schneider |  | WP428 Review and Confirm Exit Transition Plan | 20 hrs | 15 days | 2026-11-12 | 2026-12-04 | 2090 | 2092
5663 | 2092 | Future Task |  |  | WP428 | Joy Schneider | Submit | WP WP428 - Exit Transition Work Plan - Submit | 0 hrs | 0 days | 2026-12-04 | 2026-12-04 | 2091 | 2093
5664 | 2093 | Future Task |  |  | WP428 | Joy Schneider | Review | WP WP428 - Exit Transition Work Plan - Collaborative Review & Update | 12 hrs | 10 days | 2026-12-07 | 2026-12-18 | 2092 | 2094
5665 | 2094 | Future Task |  |  | WP428 | Joy Schneider | Review | WP WP428 - Exit Transition Work Plan - Final Review & Edits | 12 hrs | 5 days | 2026-12-21 | 2026-12-28 | 2093 | 2095
5666 | 2095 | Future Task |  |  | WP428 | Joy Schneider | Approve | WP WP428 - Exit Transition Work Plan - Approve | 0 hrs | 0 days | 2026-12-28 | 2026-12-28 | 2094 | 2069
4 | 2096 | Late | [5 empty] | Administrative Tasks | 2,164 hrs | 1174 days | 2023-05-01 | 2027-12-28
10 | 2097 | Future Task | [5 empty] | Administrative Activities | 1,320 hrs | 1152 days | 2023-06-01 | 2027-12-28
2063 | 2098 | Future Task |  |  |  | Tommy Werner |  | Budget | 308 hrs | 933 days | 2023-06-01 | 2027-02-15
2064 | 2099 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q1 | 14 hrs | 30 days | 2023-06-01 | 2023-07-13
2065 | 2100 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | 2023-06-01 | 2023-06-14 |  | 2101
2066 | 2101 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2023-06-15 | 2023-06-28 | 2100 | 2102
2067 | 2102 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2023-06-29 | 2023-07-13 | 2101 | 2103
2068 | 2103 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2023-07-13 | 2023-07-13 | 2102 | 2105SS-8 days
2069 | 2104 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q2 | 14 hrs | 30 days | 2023-07-03 | 2023-08-14
2070 | 2105 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | 2023-07-03 | 2023-07-17 | 2103SS-8 days | 2106
2071 | 2106 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2023-07-18 | 2023-07-31 | 2105 | 2107
2072 | 2107 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2023-08-01 | 2023-08-14 | 2106 | 2108
2073 | 2108 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2023-08-14 | 2023-08-14 | 2107 | 2110
2074 | 2109 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q3 | 14 hrs | 30 days | 2023-10-02 | 2023-11-13
2075 | 2110 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | 2023-10-02 | 2023-10-13 | 2108 | 2111
2076 | 2111 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2023-10-16 | 2023-10-27 | 2110 | 2112
2077 | 2112 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2023-10-30 | 2023-11-13 | 2111 | 2113
2078 | 2113 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2023-11-13 | 2023-11-13 | 2112 | 2115
2079 | 2114 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 23-24 Q4 | 14 hrs | 30 days | 2024-01-02 | 2024-02-13
2080 | 2115 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | 2024-01-02 | 2024-01-16 | 2113 | 2116
2081 | 2116 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2024-01-17 | 2024-01-30 | 2115 | 2117
2082 | 2117 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2024-01-31 | 2024-02-13 | 2116 | 2118
2083 | 2118 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2024-02-13 | 2024-02-13 | 2117 | 2130
2084 | 2119 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 24-25 | 14 hrs | 30 days | 2024-05-01 | 2024-06-12
2085 | 2120 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 24-25 - Create | 4 hrs | 10 days | 2024-05-01 | 2024-05-14 |  | 2121
2086 | 2121 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 24-25 - Collaborative Review and Update | 4 hrs | 10 days | 2024-05-15 | 2024-05-29 | 2120 | 2122
2087 | 2122 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 24-25 - Final Review and Edit | 6 hrs | 10 days | 2024-05-30 | 2024-06-12 | 2121 | 2123
2088 | 2123 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | 2024-06-12 | 2024-06-12 | 2122 | 2150
2089 | 2124 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 24-25 | 14 hrs | 40 days | 2023-06-01 | 2023-07-27
2090 | 2125 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 24-25 - Create | 4 hrs | 20 days | 2023-06-01 | 2023-06-28 |  | 2126
2091 | 2126 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 24-25 - Collaborative Review and Update | 4 hrs | 10 days | 2023-06-29 | 2023-07-13 | 2125 | 2127
2092 | 2127 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 24-25 - Final Review and Edit | 6 hrs | 10 days | 2023-07-14 | 2023-07-27 | 2126 | 2128
2093 | 2128 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | 2023-07-27 | 2023-07-27 | 2127 | 2155
2094 | 2129 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q1 | 14 hrs | 30 days | 2024-06-03 | 2024-07-15
2095 | 2130 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | 2024-06-03 | 2024-06-14 | 2118 | 2131
2096 | 2131 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2024-06-17 | 2024-06-28 | 2130 | 2132
2097 | 2132 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2024-07-01 | 2024-07-15 | 2131 | 2133
2098 | 2133 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2024-07-15 | 2024-07-15 | 2132 | 2135SS-10 days
2099 | 2134 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q2 | 14 hrs | 30 days | 2024-07-01 | 2024-08-12
2100 | 2135 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | 2024-07-01 | 2024-07-15 | 2133SS-10 days | 2136
2101 | 2136 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2024-07-16 | 2024-07-29 | 2135 | 2137
2102 | 2137 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2024-07-30 | 2024-08-12 | 2136 | 2138
2103 | 2138 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2024-08-12 | 2024-08-12 | 2137 | 2140
2104 | 2139 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q3 | 14 hrs | 30 days | 2024-10-01 | 2024-11-12
2105 | 2140 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | 2024-10-01 | 2024-10-14 | 2138 | 2141
2106 | 2141 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2024-10-15 | 2024-10-28 | 2140 | 2142
2107 | 2142 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2024-10-29 | 2024-11-12 | 2141 | 2143
2108 | 2143 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2024-11-12 | 2024-11-12 | 2142 | 2145
2109 | 2144 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 24-25 Q4 | 14 hrs | 30 days | 2025-01-02 | 2025-02-13
2110 | 2145 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | 2025-01-02 | 2025-01-15 | 2143 | 2146
2111 | 2146 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2025-01-16 | 2025-01-30 | 2145 | 2147
2112 | 2147 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2025-01-31 | 2025-02-13 | 2146 | 2148
2113 | 2148 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2025-02-13 | 2025-02-13 | 2147 | 2160
2114 | 2149 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 25-26 | 14 hrs | 30 days | 2025-05-01 | 2025-06-12
2115 | 2150 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 25-26 - Create | 4 hrs | 10 days | 2025-05-01 | 2025-05-14 | 2123 | 2151
2116 | 2151 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 25-26 - Collaborative Review and Update | 4 hrs | 10 days | 2025-05-15 | 2025-05-29 | 2150 | 2152
2117 | 2152 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 25-26 - Final Review and Edit | 6 hrs | 10 days | 2025-05-30 | 2025-06-12 | 2151 | 2153
2118 | 2153 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | 2025-06-12 | 2025-06-12 | 2152 | 2180
2119 | 2154 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 25-26 | 14 hrs | 40 days | 2024-06-03 | 2024-07-29
2120 | 2155 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 25-26 - Create | 4 hrs | 20 days | 2024-06-03 | 2024-06-28 | 2128 | 2156
2121 | 2156 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 25-26 - Collaborative Review and Update | 4 hrs | 10 days | 2024-07-01 | 2024-07-15 | 2155 | 2157
2122 | 2157 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 25-26 - Final Review and Edit | 6 hrs | 10 days | 2024-07-16 | 2024-07-29 | 2156 | 2158
2123 | 2158 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | 2024-07-29 | 2024-07-29 | 2157 | 2185
2124 | 2159 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q1 | 14 hrs | 30 days | 2025-06-02 | 2025-07-14
2125 | 2160 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | 2025-06-02 | 2025-06-13 | 2148 | 2161
2126 | 2161 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2025-06-16 | 2025-06-27 | 2160 | 2162
2127 | 2162 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2025-06-30 | 2025-07-14 | 2161 | 2163
2128 | 2163 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2025-07-14 | 2025-07-14 | 2162 | 2165FS-9 days
2129 | 2164 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q2 | 14 hrs | 30 days | 2025-07-01 | 2025-08-12
2130 | 2165 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | 2025-07-01 | 2025-07-15 | 2163FS-9 days | 2166
2131 | 2166 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2025-07-16 | 2025-07-29 | 2165 | 2167
2132 | 2167 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2025-07-30 | 2025-08-12 | 2166 | 2168
2133 | 2168 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2025-08-12 | 2025-08-12 | 2167 | 2170
2134 | 2169 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q3 | 14 hrs | 30 days | 2025-10-01 | 2025-11-12
2135 | 2170 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | 2025-10-01 | 2025-10-14 | 2168 | 2171
2136 | 2171 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2025-10-15 | 2025-10-28 | 2170 | 2172
2137 | 2172 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2025-10-29 | 2025-11-12 | 2171 | 2173
2138 | 2173 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2025-11-12 | 2025-11-12 | 2172 | 2175
2139 | 2174 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 25-26 Q4 | 14 hrs | 30 days | 2026-01-02 | 2026-02-13
2140 | 2175 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | 2026-01-02 | 2026-01-15 | 2173 | 2176
2141 | 2176 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2026-01-16 | 2026-01-30 | 2175 | 2177
2142 | 2177 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2026-02-02 | 2026-02-13 | 2176 | 2178
2143 | 2178 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2026-02-13 | 2026-02-13 | 2177 | 2190
2144 | 2179 | Future Task |  |  |  | Tommy Werner |  | Spend Plan FY 26-27 | 14 hrs | 30 days | 2026-05-01 | 2026-06-12
2145 | 2180 | Future Task |  |  |  | Tommy Werner | Create | Spend Plan Template FY 26-27 - Create | 4 hrs | 10 days | 2026-05-01 | 2026-05-14 | 2153 | 2181
2146 | 2181 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 26-27 - Collaborative Review and Update | 4 hrs | 10 days | 2026-05-15 | 2026-05-29 | 2180 | 2182
2147 | 2182 | Future Task |  |  |  | Tommy Werner | Review | Spend Plan Template FY 26-27 - Final Review and Edit | 6 hrs | 10 days | 2026-06-01 | 2026-06-12 | 2181 | 2183
2148 | 2183 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved Spend Plan Template to DFS Budget Office | 0 hrs | 0 days | 2026-06-12 | 2026-06-12 | 2182
2149 | 2184 | Future Task |  |  |  | Tommy Werner |  | Legislative Budget Request FY 26-27 | 14 hrs | 40 days | 2025-06-02 | 2025-07-28
2150 | 2185 | Future Task |  |  |  | Tommy Werner | Create | LBR FY 26-27 - Create | 4 hrs | 20 days | 2025-06-02 | 2025-06-27 | 2158 | 2186
2151 | 2186 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 26-27 - Collaborative Review and Update | 4 hrs | 10 days | 2025-06-30 | 2025-07-14 | 2185 | 2187
2152 | 2187 | Future Task |  |  |  | Tommy Werner | Review | LBR FY 26-27 - Final Review and Edit | 6 hrs | 10 days | 2025-07-15 | 2025-07-28 | 2186 | 2188
2153 | 2188 | Future Task |  |  |  | Tommy Werner | Submit | Submit approved LBR to DFS Budget Office | 0 hrs | 0 days | 2025-07-28 | 2025-07-28 | 2187
2154 | 2189 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q1 | 14 hrs | 30 days | 2026-06-01 | 2026-07-13
2155 | 2190 | Future Task |  |  |  | Tommy Werner | Create | Draft Q1 Budget amendment | 4 hrs | 10 days | 2026-06-01 | 2026-06-12 | 2178 | 2191
2156 | 2191 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2026-06-15 | 2026-06-26 | 2190 | 2192
2157 | 2192 | Future Task |  |  |  | Tommy Werner | Review | Q1 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2026-06-29 | 2026-07-13 | 2191 | 2193
2158 | 2193 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q1 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2026-07-13 | 2026-07-13 | 2192 | 2195FS-8 days
2159 | 2194 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q2 | 14 hrs | 30 days | 2026-07-01 | 2026-08-12
2160 | 2195 | Future Task |  |  |  | Tommy Werner | Create | Draft Q2 Budget amendment | 4 hrs | 10 days | 2026-07-01 | 2026-07-15 | 2193FS-8 days | 2196
2161 | 2196 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2026-07-16 | 2026-07-29 | 2195 | 2197
2162 | 2197 | Future Task |  |  |  | Tommy Werner | Review | Q2 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2026-07-30 | 2026-08-12 | 2196 | 2198
2163 | 2198 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q2 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2026-08-12 | 2026-08-12 | 2197 | 2200
2164 | 2199 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q3 | 14 hrs | 30 days | 2026-10-01 | 2026-11-12
2165 | 2200 | Future Task |  |  |  | Tommy Werner | Create | Draft Q3 Budget amendment | 4 hrs | 10 days | 2026-10-01 | 2026-10-14 | 2198 | 2201
2166 | 2201 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2026-10-15 | 2026-10-28 | 2200 | 2202
2167 | 2202 | Future Task |  |  |  | Tommy Werner | Review | Q3 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2026-10-29 | 2026-11-12 | 2201 | 2203
2168 | 2203 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q3 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2026-11-12 | 2026-11-12 | 2202 | 2205
2169 | 2204 | Future Task |  |  |  | Tommy Werner |  | Budget Amendment FY 26-27 Q4 | 14 hrs | 30 days | 2027-01-04 | 2027-02-15
2170 | 2205 | Future Task |  |  |  | Tommy Werner | Create | Draft Q4 Budget amendment | 4 hrs | 10 days | 2027-01-04 | 2027-01-15 | 2203 | 2206
2171 | 2206 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Collaborative Review and Update | 4 hrs | 10 days | 2027-01-19 | 2027-02-01 | 2205 | 2207
2172 | 2207 | Future Task |  |  |  | Tommy Werner | Review | Q4 Budget Amendment - Final Review and Edits | 6 hrs | 10 days | 2027-02-02 | 2027-02-15 | 2206 | 2208
2173 | 2208 | Future Task |  |  |  | Tommy Werner | Submit | Submit Q4 Budget Amendment to DFS Budget Office | 0 hrs | 0 days | 2027-02-15 | 2027-02-15 | 2207
2174 | 2209 | Future Task | [5 empty] | Project Resources | 1,012 hrs | 1131 days | 2023-06-30 | 2027-12-28
2175 | 2210 | Future Task |  |  |  | Tommy Werner |  | Project Management Plan | 462 hrs | 1045 days | 2023-11-01 | 2027-12-28
2176 | 2211 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2023 | 54 hrs | 38 days | 2023-11-01 | 2023-12-28
2177 | 2212 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2023-11-01 | 2023-12-01 |  | 2213
2178 | 2213 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2023-12-04 | 2023-12-15 | 2212 | 2214
2179 | 2214 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2023-12-18 | 2023-12-22 | 2213 | 2215
2180 | 2215 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 4 hrs | 3 days | 2023-12-26 | 2023-12-28 | 2214 | 2217
2181 | 2216 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2024 | 51 hrs | 38 days | 2024-05-03 | 2024-06-26
2182 | 2217 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2024-05-03 | 2024-05-31 | 2215 | 2218
2183 | 2218 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2024-06-03 | 2024-06-14 | 2217 | 2219
2184 | 2219 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2024-06-17 | 2024-06-21 | 2218 | 2220
2185 | 2220 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2024-06-24 | 2024-06-26 | 2219 | 2222
2186 | 2221 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2024 | 51 hrs | 38 days | 2024-11-04 | 2024-12-31
2187 | 2222 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2024-11-04 | 2024-12-04 | 2220 | 2223
2188 | 2223 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2024-12-05 | 2024-12-18 | 2222 | 2224
2189 | 2224 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2024-12-19 | 2024-12-26 | 2223 | 2225
2190 | 2225 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2024-12-27 | 2024-12-31 | 2224 | 2227
2191 | 2226 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2025 | 51 hrs | 38 days | 2025-05-02 | 2025-06-25
2192 | 2227 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2025-05-02 | 2025-05-30 | 2225 | 2228
2193 | 2228 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2025-06-02 | 2025-06-13 | 2227 | 2229
2194 | 2229 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2025-06-16 | 2025-06-20 | 2228 | 2230
2195 | 2230 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2025-06-23 | 2025-06-25 | 2229 | 2232
2196 | 2231 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2025 | 51 hrs | 38 days | 2025-11-03 | 2025-12-30
2197 | 2232 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2025-11-03 | 2025-12-03 | 2230 | 2233
2198 | 2233 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2025-12-04 | 2025-12-17 | 2232 | 2234
2199 | 2234 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2025-12-18 | 2025-12-24 | 2233 | 2235
2200 | 2235 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2025-12-26 | 2025-12-30 | 2234 | 2237
2201 | 2236 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2026 | 51 hrs | 38 days | 2026-05-01 | 2026-06-24
2202 | 2237 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2026-05-01 | 2026-05-29 | 2235 | 2238
2203 | 2238 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2026-06-01 | 2026-06-12 | 2237 | 2239
2204 | 2239 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2026-06-15 | 2026-06-19 | 2238 | 2240
2205 | 2240 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2026-06-22 | 2026-06-24 | 2239 | 2242
2206 | 2241 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2026 | 51 hrs | 38 days | 2026-11-02 | 2026-12-29
2207 | 2242 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2026-11-02 | 2026-12-02 | 2240 | 2243
2208 | 2243 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2026-12-03 | 2026-12-16 | 2242 | 2244
2209 | 2244 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2026-12-17 | 2026-12-23 | 2243 | 2245
2210 | 2245 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2026-12-24 | 2026-12-29 | 2244 | 2247
2211 | 2246 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan May 2027 | 51 hrs | 38 days | 2027-05-03 | 2027-06-24
2212 | 2247 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2027-05-03 | 2027-05-28 | 2245 | 2248
2213 | 2248 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2027-06-01 | 2027-06-14 | 2247 | 2249
2214 | 2249 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2027-06-15 | 2027-06-21 | 2248 | 2250
2215 | 2250 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2027-06-22 | 2027-06-24 | 2249 | 2252
2216 | 2251 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Management Plan November 2027 | 51 hrs | 38 days | 2027-11-01 | 2027-12-28
2217 | 2252 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Management Plan | 20 hrs | 20 days | 2027-11-01 | 2027-12-01 | 2250 | 2253
2218 | 2253 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Collaborative Review and Update | 20 hrs | 10 days | 2027-12-02 | 2027-12-15 | 2252 | 2254
2219 | 2254 | Future Task |  |  |  | Julian Gotreaux | Review | Project Management Plan Final Review and Edit | 10 hrs | 5 days | 2027-12-16 | 2027-12-22 | 2253 | 2255
2220 | 2255 | Future Task |  |  |  | Julian Gotreaux | Create | Publish Project Management Plan | 1 hr | 3 days | 2027-12-23 | 2027-12-28 | 2254
2221 | 2256 | Future Task |  |  |  | Dusti Kincl |  | Florida PALM Style Guide | 104 hrs | 910 days | 2023-11-01 | 2027-06-14
2222 | 2257 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 23-24 | 13 hrs | 30 days | 2023-11-01 | 2023-12-15
2223 | 2258 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2023-11-01 | 2023-11-22 |  | 2259
2224 | 2259 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2023-11-27 | 2023-12-08 | 2258 | 2260
2225 | 2260 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2023-12-11 | 2023-12-15 | 2259 | 2262
2226 | 2261 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 23-24 | 13 hrs | 30 days | 2024-05-01 | 2024-06-12
2227 | 2262 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2024-05-01 | 2024-05-21 | 2260 | 2263
2228 | 2263 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2024-05-22 | 2024-06-05 | 2262 | 2264
2229 | 2264 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2024-06-06 | 2024-06-12 | 2263 | 2266
2230 | 2265 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 24-25 | 13 hrs | 30 days | 2024-11-04 | 2024-12-18
2231 | 2266 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2024-11-04 | 2024-11-25 | 2264 | 2267
2232 | 2267 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2024-11-26 | 2024-12-11 | 2266 | 2268
2233 | 2268 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2024-12-12 | 2024-12-18 | 2267 | 2270
2234 | 2269 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 24-25 | 13 hrs | 30 days | 2025-05-01 | 2025-06-12
2235 | 2270 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2025-05-01 | 2025-05-21 | 2268 | 2271
2236 | 2271 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2025-05-22 | 2025-06-05 | 2270 | 2272
2237 | 2272 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2025-06-06 | 2025-06-12 | 2271 | 2274
2238 | 2273 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 25-26 | 13 hrs | 30 days | 2025-11-03 | 2025-12-17
2239 | 2274 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2025-11-03 | 2025-11-24 | 2272 | 2275
2240 | 2275 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2025-11-25 | 2025-12-10 | 2274 | 2276
2241 | 2276 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2025-12-11 | 2025-12-17 | 2275 | 2278
2242 | 2277 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 25-26 | 13 hrs | 30 days | 2026-04-06 | 2026-05-15
2243 | 2278 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2026-04-06 | 2026-04-24 | 2276 | 2279
2244 | 2279 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2026-04-27 | 2026-05-08 | 2278 | 2280
2245 | 2280 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2026-05-11 | 2026-05-15 | 2279 | 2282
2246 | 2281 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - November FY 26-27 | 13 hrs | 30 days | 2026-11-02 | 2026-12-16
2247 | 2282 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2026-11-02 | 2026-11-23 | 2280 | 2283
2248 | 2283 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2026-11-24 | 2026-12-09 | 2282 | 2284
2249 | 2284 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2026-12-10 | 2026-12-16 | 2283 | 2286
2250 | 2285 | Future Task |  |  |  | Dusti Kincl |  | Update Florida PALM Style Guide - May FY 26-27 | 13 hrs | 30 days | 2027-05-03 | 2027-06-14
2251 | 2286 | Future Task |  |  |  | Dusti Kincl | Create | Update Florida PALM Style Guide | 8 hrs | 15 days | 2027-05-03 | 2027-05-21 | 2284 | 2287
2252 | 2287 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Collaborative Review and Update | 4 hrs | 10 days | 2027-05-24 | 2027-06-07 | 2286 | 2288
2253 | 2288 | Future Task |  |  |  | Dusti Kincl | Review | Florida PALM Style Guide Final Review and Edit | 1 hr | 5 days | 2027-06-08 | 2027-06-14 | 2287
2254 | 2289 | Future Task | [5 empty] | Project Team Orientation Guide | 238 hrs | 252 days | 2023-06-30 | 2024-06-28
6683 | 2290 | Future Task |  |  | WP401 | Joy Schneider |  | WP401 - Project Orientation Guide | 88 hrs | 50 days | 2023-06-30 | 2023-09-11
6684 | 2291 | Future Task |  |  | WP401 | Joy Schneider | Create | WPED WP401 - Project Orientation Guide - Create | 8 hrs | 10 days | 2023-06-30 | 2023-07-14 | 28 | 2292
6685 | 2292 | Future Task |  |  | WP401 | Joy Schneider | Submit | WPED WP401 - Project Orientation Guide - Submit | 0 hrs | 0 days | 2023-07-14 | 2023-07-14 | 2291 | 2293
6686 | 2293 | Future Task |  |  | WP401 | Joy Schneider | Review | WPED WP401 - Project Orientation Guide - Review | 16 hrs | 10 days | 2023-07-17 | 2023-07-28 | 2292 | 2294
6687 | 2294 | Future Task |  |  | WP401 | Joy Schneider | Approve | WPED WP401 - Project Orientation Guide - Approve | 0 hrs | 0 days | 2023-07-28 | 2023-07-28 | 2293 | 2295
6688 | 2295 | Future Task |  |  | WP401 | Joy Schneider |  | Update Project Team Orientation Guide | 10 hrs | 5 days | 2023-07-31 | 2023-08-04 | 2294 | 2296
6689 | 2296 | Future Task |  |  | WP401 | Joy Schneider |  | Project Team Orientation Guide - Collaborative Review and Update | 10 hrs | 5 days | 2023-08-07 | 2023-08-11 | 2295 | 2297
6690 | 2297 | Future Task |  |  | WP401 | Joy Schneider |  | Project Team Orientation Guide - Final Review and Update | 20 hrs | 5 days | 2023-08-14 | 2023-08-18 | 2296 | 2298
6691 | 2298 | Future Task |  |  | WP401 | Joy Schneider | Submit | WP WP401 - Project Orientation Guide - Submit | 0 hrs | 0 days | 2023-08-18 | 2023-08-18 | 2297 | 2299
6692 | 2299 | Future Task |  |  | WP401 | Joy Schneider | Review | WP WP401 - Project Orientation Guide - Collaborative Review & Update | 12 hrs | 10 days | 2023-08-21 | 2023-09-01 | 2298 | 2300
6693 | 2300 | Future Task |  |  | WP401 | Joy Schneider | Review | WP WP401 - Project Orientation Guide - Final Review & Edits | 12 hrs | 5 days | 2023-09-05 | 2023-09-11 | 2299 | 2301
6694 | 2301 | Future Task |  |  | WP401 | Joy Schneider | Approve | WP WP401 - Project Orientation Guide - Approve | 0 hrs | 0 days | 2023-09-11 | 2023-09-11 | 2300 | 2303FS-6 days | 2023-10-01
2255 | 2302 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q1 | 30 hrs | 15 days | 2023-09-01 | 2023-09-22
2257 | 2303 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | 2023-09-01 | 2023-09-08 | 2301FS-6 days | 2304
2258 | 2304 | Future Task |  |  |  | Julian Gotreaux | Review | FPO - Collaborative Review and Update | 10 hrs | 5 days | 2023-09-11 | 2023-09-15 | 2303 | 2305
2259 | 2305 | Future Task |  |  |  | Julian Gotreaux | Review | FPO - Final Review and Update | 10 hrs | 5 days | 2023-09-18 | 2023-09-22 | 2304 | 23072407
2260 | 2306 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q2 | 40 hrs | 20 days | 2023-12-01 | 2023-12-29
2261 | 2307 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | 2023-12-01 | 2023-12-07 | 2305 | 2308
2262 | 2308 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | 2023-12-08 | 2023-12-14 | 2307 | 2309
2263 | 2309 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review and Update | 10 hrs | 5 days | 2023-12-15 | 2023-12-21 | 2308 | 2310
2264 | 2310 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review and Update | 10 hrs | 5 days | 2023-12-22 | 2023-12-29 | 2309 | 2312
2265 | 2311 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q3 | 40 hrs | 20 days | 2024-03-01 | 2024-03-28
2266 | 2312 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | 2024-03-01 | 2024-03-07 | 2310 | 2313
2267 | 2313 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | 2024-03-08 | 2024-03-14 | 2312 | 2314
2268 | 2314 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review and Update | 10 hrs | 5 days | 2024-03-15 | 2024-03-21 | 2313 | 2315
2269 | 2315 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review and Update | 10 hrs | 5 days | 2024-03-22 | 2024-03-28 | 2314 | 2317
2270 | 2316 | Future Task |  |  |  | Julian Gotreaux |  | Update Project Team Orientation Guide (FY23-24) Q4 | 40 hrs | 20 days | 2024-06-03 | 2024-06-28
2271 | 2317 | Future Task |  |  |  | Julian Gotreaux | Create | Update Project Team Orientation Guide | 10 hrs | 5 days | 2024-06-03 | 2024-06-07 | 2315 | 2318
2272 | 2318 | Future Task |  |  |  | Julian Gotreaux | Create | Update FPO Presentation | 10 hrs | 5 days | 2024-06-10 | 2024-06-14 | 2317 | 2319
2273 | 2319 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Collaborative Review and Update | 10 hrs | 5 days | 2024-06-17 | 2024-06-21 | 2318 | 2320
2274 | 2320 | Future Task |  |  |  | Julian Gotreaux | Review | Project Team Orientation Guide - Final Review and Update | 10 hrs | 5 days | 2024-06-24 | 2024-06-28 | 2319
2275 | 2321 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 23-24 | 28 hrs | 134 days | 2023-07-17 | 2024-01-29
2276 | 2322 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 23-24 Q1 | 4 hrs | 10 days | 2023-07-17 | 2023-07-28 |  | 23232324
2277 | 2323 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 23-24 Q3 | 4 hrs | 10 days | 2024-01-16 | 2024-01-29 | 2322 | 2330
2278 | 2324 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 23-24 | 4 hrs | 10 days | 2023-08-15 | 2023-08-28 | 2322 | 2325
2279 | 2325 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 23-24 | 4 hrs | 10 days | 2023-09-15 | 2023-09-28 | 2324 | 2326
2280 | 2326 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 23-24 | 4 hrs | 10 days | 2023-10-16 | 2023-10-27 | 2325 | 2327
2281 | 2327 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 23-24 | 4 hrs | 10 days | 2023-11-15 | 2023-11-30 | 2326 | 2328
2282 | 2328 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 23-24 | 4 hrs | 10 days | 2023-12-15 | 2023-12-29 | 2327 | 2332
2283 | 2329 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 24-25 | 28 hrs | 136 days | 2024-07-15 | 2025-01-29
2284 | 2330 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 24-25 Q1 | 4 hrs | 10 days | 2024-07-15 | 2024-07-26 | 2323 | 2331
2285 | 2331 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 24-25 Q3 | 4 hrs | 10 days | 2025-01-15 | 2025-01-29 | 2330 | 2338
2286 | 2332 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 24-25 | 4 hrs | 10 days | 2024-08-15 | 2024-08-28 | 2328 | 2333
2287 | 2333 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 24-25 | 4 hrs | 10 days | 2024-09-16 | 2024-09-27 | 2332 | 2334
2288 | 2334 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 24-25 | 4 hrs | 10 days | 2024-10-15 | 2024-10-28 | 2333 | 2335
2289 | 2335 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 24-25 | 4 hrs | 10 days | 2024-11-15 | 2024-12-02 | 2334 | 2336
2290 | 2336 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 24-25 | 4 hrs | 10 days | 2024-12-16 | 2024-12-30 | 2335 | 2340
2291 | 2337 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 25-26 | 28 hrs | 136 days | 2025-07-15 | 2026-01-29
2292 | 2338 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 25-26 Q1 | 4 hrs | 10 days | 2025-07-15 | 2025-07-28 | 2331 | 2339
2293 | 2339 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 25-26 Q3 | 4 hrs | 10 days | 2026-01-15 | 2026-01-29 | 2338 | 2346
2294 | 2340 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 25-26 | 4 hrs | 10 days | 2025-08-15 | 2025-08-28 | 2336 | 2341
2295 | 2341 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 25-26 | 4 hrs | 10 days | 2025-09-15 | 2025-09-26 | 2340 | 2342
2296 | 2342 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 25-26 | 4 hrs | 10 days | 2025-10-15 | 2025-10-28 | 2341 | 2343
2297 | 2343 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 25-26 | 4 hrs | 10 days | 2025-11-17 | 2025-12-02 | 2342 | 2344
2298 | 2344 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 25-26 | 4 hrs | 10 days | 2025-12-15 | 2025-12-29 | 2343 | 2348
2299 | 2345 | Future Task |  |  |  | Julian Gotreaux |  | Audits FY 26-27 | 28 hrs | 136 days | 2026-07-15 | 2027-01-29
2300 | 2346 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 26-27 Q1 | 4 hrs | 10 days | 2026-07-15 | 2026-07-28 | 2339 | 2347
2301 | 2347 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Asset Management Tracker - State FY 26-27 Q3 | 4 hrs | 10 days | 2027-01-15 | 2027-01-29 | 2346
2302 | 2348 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle OCI Access Tracker FY 26-27 | 4 hrs | 10 days | 2026-08-17 | 2026-08-28 | 2344 | 2349
2303 | 2349 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Software Support Tools Trackers FY 26-27 | 4 hrs | 10 days | 2026-09-15 | 2026-09-28 | 2348 | 2350
2304 | 2350 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle Software Tracker FY 26-27 | 4 hrs | 10 days | 2026-10-15 | 2026-10-28 | 2349 | 2351
2305 | 2351 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Third-Party Contract Tracker FY 26-27 | 4 hrs | 10 days | 2026-11-16 | 2026-12-01 | 2350 | 2352
2306 | 2352 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Oracle CSI Access Tracker FY 26-27 | 4 hrs | 10 days | 2026-12-15 | 2026-12-29 | 2351
2307 | 2353 | Future Task |  |  |  | Julian Gotreaux |  | Access Control | 96 hrs | 965 days | 2023-08-15 | 2027-06-14
2308 | 2354 | Future Task |  |  |  | Julian Gotreaux |  | SharePoint Access Control | 32 hrs | 965 days | 2023-08-15 | 2027-06-14
2309 | 2355 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q1 | 2 hrs | 10 days | 2023-08-15 | 2023-08-28 |  | 2356
2310 | 2356 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q2 | 2 hrs | 10 days | 2023-11-15 | 2023-11-30 | 2355 | 2357
2311 | 2357 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q3 | 2 hrs | 10 days | 2024-02-15 | 2024-02-28 | 2356 | 2358
2312 | 2358 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 23-24 Q4 | 2 hrs | 10 days | 2024-05-15 | 2024-05-29 | 2357 | 2359
2313 | 2359 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q1 | 2 hrs | 10 days | 2024-08-15 | 2024-08-28 | 2358 | 2360
2314 | 2360 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q2 | 2 hrs | 10 days | 2024-11-15 | 2024-12-02 | 2359 | 2361
2315 | 2361 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q3 | 2 hrs | 10 days | 2025-02-17 | 2025-02-28 | 2360 | 2362
2316 | 2362 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 24-25 Q4 | 2 hrs | 10 days | 2025-05-15 | 2025-05-29 | 2361 | 2363
2317 | 2363 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q1 | 2 hrs | 10 days | 2025-08-15 | 2025-08-28 | 2362 | 2364
2318 | 2364 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q2 | 2 hrs | 10 days | 2025-11-17 | 2025-12-02 | 2363 | 2365
2319 | 2365 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q3 | 2 hrs | 10 days | 2026-02-16 | 2026-02-27 | 2364 | 2366
2320 | 2366 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 25-26 Q4 | 2 hrs | 10 days | 2026-05-15 | 2026-05-29 | 2365 | 2367
2321 | 2367 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q1 | 2 hrs | 10 days | 2026-08-17 | 2026-08-28 | 2366 | 2368
2322 | 2368 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q2 | 2 hrs | 10 days | 2026-11-16 | 2026-12-01 | 2367 | 2369
2323 | 2369 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q3 | 2 hrs | 10 days | 2027-02-15 | 2027-02-26 | 2368 | 2370
2324 | 2370 | Future Task |  |  |  | Julian Gotreaux | Create | Audit Access control log FY 26-27 Q4 | 2 hrs | 20 days | 2027-05-17 | 2027-06-14 | 2369
2325 | 2371 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2023 | 8 hrs | 35 days | 2023-08-28 | 2023-10-16
2326 | 2372 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2023-08-28 | 2023-09-01 |  | 2373
2327 | 2373 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2023-09-05 | 2023-09-18 | 2372 | 2374
2328 | 2374 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2023-09-19 | 2023-10-09 | 2373 | 2375
2329 | 2375 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2023-10-10 | 2023-10-16 | 2374
2330 | 2376 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2024 | 8 hrs | 35 days | 2024-02-27 | 2024-04-15
2331 | 2377 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2024-02-27 | 2024-03-04 |  | 2378
2332 | 2378 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2024-03-05 | 2024-03-18 | 2377 | 2379
2333 | 2379 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2024-03-19 | 2024-04-08 | 2378 | 2380
2334 | 2380 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2024-04-09 | 2024-04-15 | 2379 | 2382
2335 | 2381 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2024 | 8 hrs | 35 days | 2024-08-27 | 2024-10-15
2336 | 2382 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2024-08-27 | 2024-09-03 | 2380 | 2383
2337 | 2383 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2024-09-04 | 2024-09-17 | 2382 | 2384
2338 | 2384 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2024-09-18 | 2024-10-08 | 2383 | 2385
2339 | 2385 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2024-10-09 | 2024-10-15 | 2384 | 2387
2340 | 2386 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2025 | 8 hrs | 35 days | 2025-02-25 | 2025-04-14
2341 | 2387 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2025-02-25 | 2025-03-03 | 2385 | 2388
2342 | 2388 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2025-03-04 | 2025-03-17 | 2387 | 2389
2343 | 2389 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2025-03-18 | 2025-04-07 | 2388 | 2390
2344 | 2390 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2025-04-08 | 2025-04-14 | 2389 | 2392
2345 | 2391 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2025 | 8 hrs | 35 days | 2025-08-26 | 2025-10-14
2346 | 2392 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2025-08-26 | 2025-09-02 | 2390 | 2393
2347 | 2393 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2025-09-03 | 2025-09-16 | 2392 | 2394
2348 | 2394 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2025-09-17 | 2025-10-07 | 2393 | 2395
2349 | 2395 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2025-10-08 | 2025-10-14 | 2394 | 2397
2350 | 2396 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2026 | 8 hrs | 35 days | 2026-02-24 | 2026-04-13
2351 | 2397 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2026-02-24 | 2026-03-02 | 2395 | 2398
2352 | 2398 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2026-03-03 | 2026-03-16 | 2397 | 2399
2353 | 2399 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2026-03-17 | 2026-04-06 | 2398 | 2400
2354 | 2400 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2026-04-07 | 2026-04-13 | 2399 | 2402
2355 | 2401 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review September 2026 | 8 hrs | 35 days | 2026-08-25 | 2026-10-13
2356 | 2402 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2026-08-25 | 2026-08-31 | 2400 | 2403
2357 | 2403 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2026-09-01 | 2026-09-15 | 2402 | 2404
2358 | 2404 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2026-09-16 | 2026-10-06 | 2403 | 2405
2359 | 2405 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2026-10-07 | 2026-10-13 | 2404
2360 | 2406 | Future Task |  |  |  | Julian Gotreaux |  | Smartsheet Access Review March 2027 | 8 hrs | 35 days | 2027-02-23 | 2027-04-12
2361 | 2407 | Future Task |  |  |  | Julian Gotreaux | Create | Prepare for Smartsheet Review | 2 hrs | 5 days | 2027-02-23 | 2027-03-01 | 2305 | 2408
2362 | 2408 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Compile and Verify Agency Responses | 2 hrs | 10 days | 2027-03-02 | 2027-03-15 | 2407 | 2409
2363 | 2409 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Update Smartsheet Permissions | 2 hrs | 15 days | 2027-03-16 | 2027-04-05 | 2408 | 2410
2364 | 2410 | Future Task |  |  |  | Julian Gotreaux | Create | Smartsheet Review - Confirm with Agencies | 2 hrs | 5 days | 2027-04-06 | 2027-04-12 | 2409
2365 | 2411 | Late | [5 empty] | Proviso Requirements | 844 hrs | 1089 days | 2023-05-01 | 2027-08-24
2366 | 2412 | Future Task |  |  |  | Tommy Werner |  | Monthly Status Reporting | 192 hrs | 241 days | 2023-08-01 | 2024-07-15
2367 | 2413 | Future Task |  |  |  | Tommy Werner |  | July 2023 Monthly Status Reporting | 16 hrs | 11 days | 2023-08-01 | 2023-08-15
2368 | 2414 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | 2023-08-01 | 2023-08-10 |  | 2415SS,2416SS,2417SS
2369 | 2415 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | 2023-08-01 | 2023-08-14 | 2414SS | 2418
2370 | 2416 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | 2023-08-01 | 2023-08-10 | 2414SS | 2418
2371 | 2417 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | 2023-08-01 | 2023-08-14 | 2414SS | 2418
2372 | 2418 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2023-08-15 | 2023-08-15 | 241724152416 | 2420
2373 | 2419 | Future Task |  |  |  | Tommy Werner |  | August 2023 Monthly Status Reporting | 16 hrs | 10 days | 2023-09-01 | 2023-09-15
2374 | 2420 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 5 days | 2023-09-01 | 2023-09-08 | 2418 | 2421SS,2422SS,2423SS,2424
2375 | 2421 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | 2023-09-01 | 2023-09-14 | 2420SS | 2424
2376 | 2422 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 5 days | 2023-09-01 | 2023-09-08 | 2420SS | 2424
2377 | 2423 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | 2023-09-01 | 2023-09-14 | 2420SS | 2424
2378 | 2424 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2023-09-15 | 2023-09-15 | 2420242124222420 | 2426
2379 | 2425 | Future Task |  |  |  | Tommy Werner |  | September 2023 Monthly Status Reporting | 16 hrs | 10 days | 2023-10-02 | 2023-10-13
2380 | 2426 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | 2023-10-02 | 2023-10-10 | 2424 | 2427SS,2428SS,2429SS,2430
2381 | 2427 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | 2023-10-02 | 2023-10-12 | 2426SS | 2430
2382 | 2428 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | 2023-10-02 | 2023-10-10 | 2426SS | 2430
2383 | 2429 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | 2023-10-02 | 2023-10-12 | 2426SS | 2430
2384 | 2430 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2023-10-13 | 2023-10-13 | 2426242724282420 | 2432
2385 | 2431 | Future Task |  |  |  | Tommy Werner |  | October 2023 Monthly Status Reporting | 16 hrs | 10 days | 2023-11-01 | 2023-11-15
2386 | 2432 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | 2023-11-01 | 2023-11-09 | 2430 | 2433SS,2434SS,2435SS,2436
2387 | 2433 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | 2023-11-01 | 2023-11-14 | 2432SS | 2436
2388 | 2434 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | 2023-11-01 | 2023-11-09 | 2432SS | 2436
2389 | 2435 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | 2023-11-01 | 2023-11-14 | 2432SS | 2436
2390 | 2436 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2023-11-15 | 2023-11-15 | 2432243324342430 | 2438
2391 | 2437 | Future Task |  |  |  | Tommy Werner |  | November 2023 Monthly Status Reporting | 16 hrs | 11 days | 2023-12-01 | 2023-12-15
2392 | 2438 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | 2023-12-01 | 2023-12-08 | 2436 | 2439SS,2440SS,2441SS,2442
2393 | 2439 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | 2023-12-01 | 2023-12-14 | 2438SS | 2442
2394 | 2440 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | 2023-12-01 | 2023-12-08 | 2438SS
2395 | 2441 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | 2023-12-01 | 2023-12-14 | 2438SS | 2442
2396 | 2442 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2023-12-15 | 2023-12-15 | 243824392441 | 2444
2397 | 2443 | Future Task |  |  |  | Tommy Werner |  | December 2023 Monthly Status Reporting | 16 hrs | 9 days | 2024-01-02 | 2024-01-12
2398 | 2444 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | 2024-01-02 | 2024-01-09 | 2442 | 2445SS,2448,2446SS,2447SS
2399 | 2445 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 8 days | 2024-01-02 | 2024-01-11 | 2444SS | 2448
2400 | 2446 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | 2024-01-02 | 2024-01-09 | 2444SS | 2448
2401 | 2447 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 8 days | 2024-01-02 | 2024-01-11 | 2444SS | 2448
2402 | 2448 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-01-12 | 2024-01-12 | 2444244524462440 | 2450
2403 | 2449 | Future Task |  |  |  | Tommy Werner |  | January 2023 Monthly Status Reporting | 16 hrs | 11 days | 2024-02-01 | 2024-02-15
2404 | 2450 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | 2024-02-01 | 2024-02-09 | 2448 | 2451SS,2452SS,2453SS,2454
2405 | 2451 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | 2024-02-01 | 2024-02-14 | 2450SS | 2454
2406 | 2452 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | 2024-02-01 | 2024-02-09 | 2450SS | 2454
2407 | 2453 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | 2024-02-01 | 2024-02-14 | 2450SS | 2454
2408 | 2454 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-02-15 | 2024-02-15 | 2450245124522450 | 2456
2409 | 2455 | Future Task |  |  |  | Tommy Werner |  | February 2024 Monthly Status Reporting | 16 hrs | 11 days | 2024-03-01 | 2024-03-15
2410 | 2456 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | 2024-03-01 | 2024-03-08 | 2454 | 2457SS,2458SS,2459SS,2460
2411 | 2457 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | 2024-03-01 | 2024-03-14 | 2456SS | 2460
2412 | 2458 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | 2024-03-01 | 2024-03-08 | 2456SS | 2460
2413 | 2459 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | 2024-03-01 | 2024-03-14 | 2456SS | 2460
2414 | 2460 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-03-15 | 2024-03-15 | 2456245724582450 | 2462
2415 | 2461 | Future Task |  |  |  | Tommy Werner |  | March 2024 Monthly Status Reporting | 16 hrs | 11 days | 2024-04-01 | 2024-04-15
2416 | 2462 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | 2024-04-01 | 2024-04-10 | 2460 | 2463SS,2464SS,2465SS,2466
2417 | 2463 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | 2024-04-01 | 2024-04-12 | 2462SS | 2466
2418 | 2464 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | 2024-04-01 | 2024-04-10 | 2462SS | 2466
2419 | 2465 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | 2024-04-01 | 2024-04-12 | 2462SS | 2466
2420 | 2466 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-04-15 | 2024-04-15 | 2462246324642460 | 2468
2421 | 2467 | Future Task |  |  |  | Tommy Werner |  | April 2024 Monthly Status Reporting | 16 hrs | 11 days | 2024-05-01 | 2024-05-15
2422 | 2468 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 8 days | 2024-05-01 | 2024-05-10 | 2466 | 2469SS,2470SS,2471SS,2472
2423 | 2469 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 10 days | 2024-05-01 | 2024-05-14 | 2468SS | 2472
2424 | 2470 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 8 days | 2024-05-01 | 2024-05-10 | 2468SS | 2472
2425 | 2471 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 10 days | 2024-05-01 | 2024-05-14 | 2468SS | 2472
2426 | 2472 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-05-15 | 2024-05-15 | 2468246924702470 | 2474
2427 | 2473 | Future Task |  |  |  | Tommy Werner |  | May 2024 Monthly Status Reporting | 16 hrs | 10 days | 2024-06-03 | 2024-06-14
2428 | 2474 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 6 days | 2024-06-03 | 2024-06-10 | 2472 | 2475SS,2476SS,2477SS,2478
2429 | 2475 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | 2024-06-03 | 2024-06-13 | 2474SS
2430 | 2476 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 6 days | 2024-06-03 | 2024-06-10 | 2474SS | 2478
2431 | 2477 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | 2024-06-03 | 2024-06-13 | 2474SS | 2478
2432 | 2478 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-06-14 | 2024-06-14 | 247424762477 | 2480
2433 | 2479 | Future Task |  |  |  | Tommy Werner |  | June 2024 Monthly Status Reporting | 16 hrs | 10 days | 2024-07-01 | 2024-07-15
2434 | 2480 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute EOM Project Schedule | 2 hrs | 7 days | 2024-07-01 | 2024-07-10 | 2478 | 2481SS,2482SS,2483SS
2435 | 2481 | Future Task |  |  |  | Tommy Werner | Create | Create Project Status Report | 8 hrs | 9 days | 2024-07-01 | 2024-07-12 | 2480SS | 2484
2436 | 2482 | Future Task |  |  |  | Tommy Werner | Create | Update and distribute Project Spend Plan and Spend Plan Release Notes | 2 hrs | 7 days | 2024-07-01 | 2024-07-10 | 2480SS | 2484
2437 | 2483 | Future Task |  |  |  | Tommy Werner | Create | Collect and compile Agency Status Report | 2 hrs | 9 days | 2024-07-01 | 2024-07-12 | 2480SS | 2484
2438 | 2484 | Future Task |  |  |  | Tommy Werner | Create | Distribute Monthly Status Report documents | 2 hrs | 1 day | 2024-07-15 | 2024-07-15 | 248124822483
9 | 2485 | Late | [5 empty] | Monthly Performance Reporting | 520 hrs | 1089 days | 2023-05-01 | 2027-08-24
6232 | 2486 | Late |  |  | D219 | Joy Schneider |  | D219 - Monthly Performance Report (April 2023) | 10 hrs | 17 days | 2023-05-01 | 2023-05-23
6364 | 2487 | Late |  |  | D219 | Joy Schneider | Create | Create April 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-05-01 | 2023-05-09 | 1 | 2488
6233 | 2488 | Late |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-05-10 | 2023-05-10 | 2487 | 2489
6234 | 2489 | Late |  |  | D219 | Joy Schneider | Submit | DEL D219 - Monthly Performance Report (April 2023) - Submit | 0 hrs | 0 days | 2023-05-10 | 2023-05-10 | 2488 | 2490
6235 | 2490 | Late |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Department QC | 1 hr | 7 days | 2023-05-11 | 2023-05-19 | 2489 | 2491
6236 | 2491 | Late |  |  | D219 | Joy Schneider | Review | DEL D219 - Monthly Performance Report (April 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-05-22 | 2023-05-23 | 2490 | 2492
6237 | 2492 | Late |  |  | D219 | Joy Schneider | Accept | DEL D219 - Monthly Performance Report (April 2023) - Accept | 0 hrs | 0 days | 2023-05-23 | 2023-05-23 | 2491 | 2494
6238 | 2493 | Future Task |  |  | D225 | Joy Schneider |  | D225 - Monthly Performance Report (May 2023) | 10 hrs | 17 days | 2023-06-01 | 2023-06-23
6365 | 2494 | Future Task |  |  | D225 | Joy Schneider | Create | Create May 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-06-01 | 2023-06-09 | 2492 | 2495
6239 | 2495 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-06-12 | 2023-06-12 | 2494 | 2496
6240 | 2496 | Future Task |  |  | D225 | Joy Schneider | Submit | DEL D225 - Monthly Performance Report (May 2023) - Submit | 0 hrs | 0 days | 2023-06-12 | 2023-06-12 | 2495 | 2497
6241 | 2497 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Department QC | 1 hr | 7 days | 2023-06-13 | 2023-06-21 | 2496 | 2498
6242 | 2498 | Future Task |  |  | D225 | Joy Schneider | Review | DEL D225 - Monthly Performance Report (May 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-06-22 | 2023-06-23 | 2497 | 2499
6243 | 2499 | Future Task |  |  | D225 | Joy Schneider | Accept | DEL D225 - Monthly Performance Report (May 2023) - Accept | 0 hrs | 0 days | 2023-06-23 | 2023-06-23 | 2498 | 2501
6244 | 2500 | Future Task |  |  | D232 | Joy Schneider |  | D232 - Monthly Performance Report (June 2023) | 10 hrs | 17 days | 2023-07-03 | 2023-07-26
6366 | 2501 | Future Task |  |  | D232 | Joy Schneider | Create | Create June 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-07-03 | 2023-07-12 | 2499 | 2502
6245 | 2502 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-07-13 | 2023-07-13 | 2501 | 2503
6246 | 2503 | Future Task |  |  | D232 | Joy Schneider | Submit | DEL D232 - Monthly Performance Report (June 2023) - Submit | 0 hrs | 0 days | 2023-07-13 | 2023-07-13 | 2502 | 2504
6247 | 2504 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Department QC | 1 hr | 7 days | 2023-07-14 | 2023-07-24 | 2503 | 2505
6248 | 2505 | Future Task |  |  | D232 | Joy Schneider | Review | DEL D232 - Monthly Performance Report (June 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-07-25 | 2023-07-26 | 2504 | 2506
6249 | 2506 | Future Task |  |  | D232 | Joy Schneider | Accept | DEL D232 - Monthly Performance Report (June 2023) - Accept | 0 hrs | 0 days | 2023-07-26 | 2023-07-26 | 2505 | 2508
6250 | 2507 | Future Task |  |  | D239 | Joy Schneider |  | D239 - Monthly Performance Report (July 2023) | 10 hrs | 17 days | 2023-08-01 | 2023-08-23
6367 | 2508 | Future Task |  |  | D239 | Joy Schneider | Create | Create July 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-08-01 | 2023-08-09 | 2506 | 2509
6251 | 2509 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-08-10 | 2023-08-10 | 2508 | 2510
6252 | 2510 | Future Task |  |  | D239 | Joy Schneider | Submit | DEL D239 - Monthly Performance Report (July 2023) - Submit | 0 hrs | 0 days | 2023-08-10 | 2023-08-10 | 2509 | 2511
6253 | 2511 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Department QC | 1 hr | 7 days | 2023-08-11 | 2023-08-21 | 2510 | 2512
6254 | 2512 | Future Task |  |  | D239 | Joy Schneider | Review | DEL D239 - Monthly Performance Report (July 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-08-22 | 2023-08-23 | 2511 | 2513
6255 | 2513 | Future Task |  |  | D239 | Joy Schneider | Accept | DEL D239 - Monthly Performance Report (July 2023) - Accept | 0 hrs | 0 days | 2023-08-23 | 2023-08-23 | 2512 | 2515
6256 | 2514 | Future Task |  |  | D249 | Joy Schneider |  | D249 - Monthly Performance Report (August 2023) | 10 hrs | 17 days | 2023-09-01 | 2023-09-26
6368 | 2515 | Future Task |  |  | D249 | Joy Schneider | Create | Create August 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-09-01 | 2023-09-12 | 2513 | 2516
6257 | 2516 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-09-13 | 2023-09-13 | 2515 | 2517
6258 | 2517 | Future Task |  |  | D249 | Joy Schneider | Submit | DEL D249 - Monthly Performance Report (August 2023) - Submit | 0 hrs | 0 days | 2023-09-13 | 2023-09-13 | 2516 | 2518
6259 | 2518 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Department QC | 1 hr | 7 days | 2023-09-14 | 2023-09-22 | 2517 | 2519
6260 | 2519 | Future Task |  |  | D249 | Joy Schneider | Review | DEL D249 - Monthly Performance Report (August 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-09-25 | 2023-09-26 | 2518 | 2520
6261 | 2520 | Future Task |  |  | D249 | Joy Schneider | Accept | DEL D249 - Monthly Performance Report (August 2023) - Accept | 0 hrs | 0 days | 2023-09-26 | 2023-09-26 | 2519 | 2522
6262 | 2521 | Future Task |  |  | D253 | Joy Schneider |  | D253 - Monthly Performance Report (September 2023) | 10 hrs | 17 days | 2023-10-02 | 2023-10-24
6369 | 2522 | Future Task |  |  | D253 | Joy Schneider | Create | Create September 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-10-02 | 2023-10-10 | 2520 | 2523
6263 | 2523 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-10-11 | 2023-10-11 | 2522 | 2524
6264 | 2524 | Future Task |  |  | D253 | Joy Schneider | Submit | DEL D253 - Monthly Performance Report (September 2023) - Submit | 0 hrs | 0 days | 2023-10-11 | 2023-10-11 | 2523 | 2525
6265 | 2525 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Department QC | 1 hr | 7 days | 2023-10-12 | 2023-10-20 | 2524 | 2526
6266 | 2526 | Future Task |  |  | D253 | Joy Schneider | Review | DEL D253 - Monthly Performance Report (September 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-10-23 | 2023-10-24 | 2525 | 2527
6267 | 2527 | Future Task |  |  | D253 | Joy Schneider | Accept | DEL D253 - Monthly Performance Report (September 2023) - Accept | 0 hrs | 0 days | 2023-10-24 | 2023-10-24 | 2526 | 2529
6268 | 2528 | Future Task |  |  | D257 | Joy Schneider |  | D257 - Monthly Performance Report (October 2023) | 10 hrs | 17 days | 2023-11-01 | 2023-11-28
6370 | 2529 | Future Task |  |  | D257 | Joy Schneider | Create | Create October 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-11-01 | 2023-11-09 | 2527 | 2530
6269 | 2530 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-11-13 | 2023-11-13 | 2529 | 2531
6270 | 2531 | Future Task |  |  | D257 | Joy Schneider | Submit | DEL D257 - Monthly Performance Report (October 2023) - Submit | 0 hrs | 0 days | 2023-11-13 | 2023-11-13 | 2530 | 2532
6271 | 2532 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Department QC | 1 hr | 7 days | 2023-11-14 | 2023-11-22 | 2531 | 2533
6272 | 2533 | Future Task |  |  | D257 | Joy Schneider | Review | DEL D257 - Monthly Performance Report (October 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-11-27 | 2023-11-28 | 2532 | 2534
6273 | 2534 | Future Task |  |  | D257 | Joy Schneider | Accept | DEL D257 - Monthly Performance Report (October 2023) - Accept | 0 hrs | 0 days | 2023-11-28 | 2023-11-28 | 2533 | 2536
6274 | 2535 | Future Task |  |  | D261 | Joy Schneider |  | D261 - Monthly Performance Report (November 2023) | 10 hrs | 17 days | 2023-12-01 | 2023-12-26
6385 | 2536 | Future Task |  |  | D261 | Joy Schneider | Create | Create November 2023 Monthly Performance Report | 3 hrs | 7 days | 2023-12-01 | 2023-12-11 | 2534 | 2537
6275 | 2537 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2023-12-12 | 2023-12-12 | 2536 | 2538
6276 | 2538 | Future Task |  |  | D261 | Joy Schneider | Submit | DEL D261 - Monthly Performance Report (November 2023) - Submit | 0 hrs | 0 days | 2023-12-12 | 2023-12-12 | 2537 | 2539
6277 | 2539 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Department QC | 1 hr | 7 days | 2023-12-13 | 2023-12-21 | 2538 | 2540
6278 | 2540 | Future Task |  |  | D261 | Joy Schneider | Review | DEL D261 - Monthly Performance Report (November 2023) - Contract Manager Review | 2 hrs | 2 days | 2023-12-22 | 2023-12-26 | 2539 | 2541
6279 | 2541 | Future Task |  |  | D261 | Joy Schneider | Accept | DEL D261 - Monthly Performance Report (November 2023) - Accept | 0 hrs | 0 days | 2023-12-26 | 2023-12-26 | 2540 | 2543
6280 | 2542 | Future Task |  |  | D267 | Joy Schneider |  | D267 - Monthly Performance Report (December 2023) | 10 hrs | 17 days | 2024-01-02 | 2024-01-25
6384 | 2543 | Future Task |  |  | D267 | Joy Schneider | Create | Create December 2023 Monthly Performance Report | 3 hrs | 7 days | 2024-01-02 | 2024-01-10 | 2541 | 2544
6281 | 2544 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-01-11 | 2024-01-11 | 2543 | 2545
6282 | 2545 | Future Task |  |  | D267 | Joy Schneider | Submit | DEL D267 - Monthly Performance Report (December 2023) - Submit | 0 hrs | 0 days | 2024-01-11 | 2024-01-11 | 2544 | 2546
6283 | 2546 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Department QC | 1 hr | 7 days | 2024-01-12 | 2024-01-23 | 2545 | 2547
6284 | 2547 | Future Task |  |  | D267 | Joy Schneider | Review | DEL D267 - Monthly Performance Report (December 2023) - Contract Manager Review | 2 hrs | 2 days | 2024-01-24 | 2024-01-25 | 2546 | 2548
6285 | 2548 | Future Task |  |  | D267 | Joy Schneider | Accept | DEL D267 - Monthly Performance Report (December 2023) - Accept | 0 hrs | 0 days | 2024-01-25 | 2024-01-25 | 2547 | 2550
6286 | 2549 | Future Task |  |  | D277 | Joy Schneider |  | D277 - Monthly Performance Report (January 2024) | 10 hrs | 17 days | 2024-02-01 | 2024-02-23
6383 | 2550 | Future Task |  |  | D277 | Joy Schneider | Create | Create January 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-02-01 | 2024-02-09 | 2548 | 2551
6287 | 2551 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-02-12 | 2024-02-12 | 2550 | 2552
6288 | 2552 | Future Task |  |  | D277 | Joy Schneider | Submit | DEL D277 - Monthly Performance Report (January 2024) - Submit | 0 hrs | 0 days | 2024-02-12 | 2024-02-12 | 2551 | 2553
6289 | 2553 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Department QC | 1 hr | 7 days | 2024-02-13 | 2024-02-21 | 2552 | 2554
6290 | 2554 | Future Task |  |  | D277 | Joy Schneider | Review | DEL D277 - Monthly Performance Report (January 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-02-22 | 2024-02-23 | 2553 | 2555
6291 | 2555 | Future Task |  |  | D277 | Joy Schneider | Accept | DEL D277 - Monthly Performance Report (January 2024) - Accept | 0 hrs | 0 days | 2024-02-23 | 2024-02-23 | 2554 | 2557
6292 | 2556 | Future Task |  |  | D284 | Joy Schneider |  | D284 - Monthly Performance Report (February 2024) | 10 hrs | 17 days | 2024-03-01 | 2024-03-25
6382 | 2557 | Future Task |  |  | D284 | Joy Schneider | Create | Create February 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-03-01 | 2024-03-11 | 2555 | 2558
6293 | 2558 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-03-12 | 2024-03-12 | 2557 | 2559
6294 | 2559 | Future Task |  |  | D284 | Joy Schneider | Submit | DEL D284 - Monthly Performance Report (February 2024) - Submit | 0 hrs | 0 days | 2024-03-12 | 2024-03-12 | 2558 | 2560
6295 | 2560 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Department QC | 1 hr | 7 days | 2024-03-13 | 2024-03-21 | 2559 | 2561
6296 | 2561 | Future Task |  |  | D284 | Joy Schneider | Review | DEL D284 - Monthly Performance Report (February 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-03-22 | 2024-03-25 | 2560 | 2562
6297 | 2562 | Future Task |  |  | D284 | Joy Schneider | Accept | DEL D284 - Monthly Performance Report (February 2024) - Accept | 0 hrs | 0 days | 2024-03-25 | 2024-03-25 | 2561 | 2564
6298 | 2563 | Future Task |  |  | D288 | Joy Schneider |  | D288 - Monthly Performance Report (March 2024) | 10 hrs | 17 days | 2024-04-01 | 2024-04-23
6381 | 2564 | Future Task |  |  | D288 | Joy Schneider | Create | Create March 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-04-01 | 2024-04-09 | 2562 | 2565
6299 | 2565 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-04-10 | 2024-04-10 | 2564 | 2566
6300 | 2566 | Future Task |  |  | D288 | Joy Schneider | Submit | DEL D288 - Monthly Performance Report (March 2024) - Submit | 0 hrs | 0 days | 2024-04-10 | 2024-04-10 | 2565 | 2567
6301 | 2567 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Department QC | 1 hr | 7 days | 2024-04-11 | 2024-04-19 | 2566 | 2568
6302 | 2568 | Future Task |  |  | D288 | Joy Schneider | Review | DEL D288 - Monthly Performance Report (March 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-04-22 | 2024-04-23 | 2567 | 2569
6303 | 2569 | Future Task |  |  | D288 | Joy Schneider | Accept | DEL D288 - Monthly Performance Report (March 2024) - Accept | 0 hrs | 0 days | 2024-04-23 | 2024-04-23 | 2568 | 2571
6304 | 2570 | Future Task |  |  | D296 | Joy Schneider |  | D296 - Monthly Performance Report (April 2024) | 10 hrs | 17 days | 2024-05-01 | 2024-05-23
6380 | 2571 | Future Task |  |  | D296 | Joy Schneider | Create | Create April 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-05-01 | 2024-05-09 | 2569 | 2572
6305 | 2572 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-05-10 | 2024-05-10 | 2571 | 2573
6306 | 2573 | Future Task |  |  | D296 | Joy Schneider | Submit | DEL D296 - Monthly Performance Report (April 2024) - Submit | 0 hrs | 0 days | 2024-05-10 | 2024-05-10 | 2572 | 2574
6307 | 2574 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Department QC | 1 hr | 7 days | 2024-05-13 | 2024-05-21 | 2573 | 2575
6308 | 2575 | Future Task |  |  | D296 | Joy Schneider | Review | DEL D296 - Monthly Performance Report (April 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-05-22 | 2024-05-23 | 2574 | 2576
6309 | 2576 | Future Task |  |  | D296 | Joy Schneider | Accept | DEL D296 - Monthly Performance Report (April 2024) - Accept | 0 hrs | 0 days | 2024-05-23 | 2024-05-23 | 2575 | 2578
6310 | 2577 | Future Task |  |  | D302 | Joy Schneider |  | D302 - Monthly Performance Report (May 2024) | 10 hrs | 17 days | 2024-06-03 | 2024-06-25
6379 | 2578 | Future Task |  |  | D302 | Joy Schneider | Create | Create May 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-06-03 | 2024-06-11 | 2576 | 2579
6311 | 2579 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-06-12 | 2024-06-12 | 2578 | 2580
6312 | 2580 | Future Task |  |  | D302 | Joy Schneider | Submit | DEL D302 - Monthly Performance Report (May 2024) - Submit | 0 hrs | 0 days | 2024-06-12 | 2024-06-12 | 2579 | 2581
6313 | 2581 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Department QC | 1 hr | 7 days | 2024-06-13 | 2024-06-21 | 2580 | 2582
6314 | 2582 | Future Task |  |  | D302 | Joy Schneider | Review | DEL D302 - Monthly Performance Report (May 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-06-24 | 2024-06-25 | 2581 | 2583
6315 | 2583 | Future Task |  |  | D302 | Joy Schneider | Accept | DEL D302 - Monthly Performance Report (May 2024) - Accept | 0 hrs | 0 days | 2024-06-25 | 2024-06-25 | 2582 | 2585
6316 | 2584 | Future Task |  |  | D311 | Joy Schneider |  | D311 - Monthly Performance Report (June 2024) | 10 hrs | 17 days | 2024-07-01 | 2024-07-24
6378 | 2585 | Future Task |  |  | D311 | Joy Schneider | Create | Create June 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-07-01 | 2024-07-10 | 2583 | 2586
6317 | 2586 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-07-11 | 2024-07-11 | 2585 | 2587
6318 | 2587 | Future Task |  |  | D311 | Joy Schneider | Submit | DEL D311 - Monthly Performance Report (June 2024) - Submit | 0 hrs | 0 days | 2024-07-11 | 2024-07-11 | 2586 | 2588
6319 | 2588 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Department QC | 1 hr | 7 days | 2024-07-12 | 2024-07-22 | 2587 | 2589
6320 | 2589 | Future Task |  |  | D311 | Joy Schneider | Review | DEL D311 - Monthly Performance Report (June 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-07-23 | 2024-07-24 | 2588 | 2590
6321 | 2590 | Future Task |  |  | D311 | Joy Schneider | Accept | DEL D311 - Monthly Performance Report (June 2024) - Accept | 0 hrs | 0 days | 2024-07-24 | 2024-07-24 | 2589 | 2592
6322 | 2591 | Future Task |  |  | D319 | Joy Schneider |  | D319 - Monthly Performance Report (July 2024) | 10 hrs | 17 days | 2024-08-01 | 2024-08-23
6377 | 2592 | Future Task |  |  | D319 | Joy Schneider | Create | Create July 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-08-01 | 2024-08-09 | 2590 | 2593
6323 | 2593 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-08-12 | 2024-08-12 | 2592 | 2594
6324 | 2594 | Future Task |  |  | D319 | Joy Schneider | Submit | DEL D319 - Monthly Performance Report (July 2024) - Submit | 0 hrs | 0 days | 2024-08-12 | 2024-08-12 | 2593 | 2595
6325 | 2595 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Department QC | 1 hr | 7 days | 2024-08-13 | 2024-08-21 | 2594 | 2596
6326 | 2596 | Future Task |  |  | D319 | Joy Schneider | Review | DEL D319 - Monthly Performance Report (July 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-08-22 | 2024-08-23 | 2595 | 2597
6327 | 2597 | Future Task |  |  | D319 | Joy Schneider | Accept | DEL D319 - Monthly Performance Report (July 2024) - Accept | 0 hrs | 0 days | 2024-08-23 | 2024-08-23 | 2596 | 2599
6328 | 2598 | Future Task |  |  | D328 | Joy Schneider |  | D328 - Monthly Performance Report (August 2024) | 10 hrs | 17 days | 2024-09-03 | 2024-09-25
6376 | 2599 | Future Task |  |  | D328 | Joy Schneider | Create | Create August 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-09-03 | 2024-09-11 | 2597 | 2600
6329 | 2600 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-09-12 | 2024-09-12 | 2599 | 2601
6330 | 2601 | Future Task |  |  | D328 | Joy Schneider | Submit | DEL D328 - Monthly Performance Report (August 2024) - Submit | 0 hrs | 0 days | 2024-09-12 | 2024-09-12 | 2600 | 2602
6331 | 2602 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Department QC | 1 hr | 7 days | 2024-09-13 | 2024-09-23 | 2601 | 2603
6332 | 2603 | Future Task |  |  | D328 | Joy Schneider | Review | DEL D328 - Monthly Performance Report (August 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-09-24 | 2024-09-25 | 2602 | 2604
6333 | 2604 | Future Task |  |  | D328 | Joy Schneider | Accept | DEL D328 - Monthly Performance Report (August 2024) - Accept | 0 hrs | 0 days | 2024-09-25 | 2024-09-25 | 2603 | 2606
6334 | 2605 | Future Task |  |  | D334 | Joy Schneider |  | D334 - Monthly Performance Report (September 2024) | 10 hrs | 17 days | 2024-10-01 | 2024-10-23
6375 | 2606 | Future Task |  |  | D334 | Joy Schneider | Create | Create September 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-10-01 | 2024-10-09 | 2604 | 2607
6335 | 2607 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-10-10 | 2024-10-10 | 2606 | 2608
6336 | 2608 | Future Task |  |  | D334 | Joy Schneider | Submit | DEL D334 - Monthly Performance Report (September 2024) - Submit | 0 hrs | 0 days | 2024-10-10 | 2024-10-10 | 2607 | 2609
6337 | 2609 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Department QC | 1 hr | 7 days | 2024-10-11 | 2024-10-21 | 2608 | 2610
6338 | 2610 | Future Task |  |  | D334 | Joy Schneider | Review | DEL D334 - Monthly Performance Report (September 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-10-22 | 2024-10-23 | 2609 | 2611
6339 | 2611 | Future Task |  |  | D334 | Joy Schneider | Accept | DEL D334 - Monthly Performance Report (September 2024) - Accept | 0 hrs | 0 days | 2024-10-23 | 2024-10-23 | 2610 | 2613
6340 | 2612 | Future Task |  |  | D342 | Joy Schneider |  | D342 - Monthly Performance Report (October 2024) | 10 hrs | 17 days | 2024-11-01 | 2024-11-26
6374 | 2613 | Future Task |  |  | D342 | Joy Schneider | Create | Create October 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-11-01 | 2024-11-12 | 2611 | 2614
6341 | 2614 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-11-13 | 2024-11-13 | 2613 | 2615
6342 | 2615 | Future Task |  |  | D342 | Joy Schneider | Submit | DEL D342 - Monthly Performance Report (October 2024) - Submit | 0 hrs | 0 days | 2024-11-13 | 2024-11-13 | 2614 | 2616
6343 | 2616 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Department QC | 1 hr | 7 days | 2024-11-14 | 2024-11-22 | 2615 | 2617
6344 | 2617 | Future Task |  |  | D342 | Joy Schneider | Review | DEL D342 - Monthly Performance Report (October 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-11-25 | 2024-11-26 | 2616 | 2618
6345 | 2618 | Future Task |  |  | D342 | Joy Schneider | Accept | DEL D342 - Monthly Performance Report (October 2024) - Accept | 0 hrs | 0 days | 2024-11-26 | 2024-11-26 | 2617 | 2620
6346 | 2619 | Future Task |  |  | D347 | Joy Schneider |  | D347 - Monthly Performance Report (November 2024) | 10 hrs | 17 days | 2024-12-02 | 2024-12-24
6373 | 2620 | Future Task |  |  | D347 | Joy Schneider | Create | Create November 2024 Monthly Performance Report | 3 hrs | 7 days | 2024-12-02 | 2024-12-10 | 2618 | 2621
6347 | 2621 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2024-12-11 | 2024-12-11 | 2620 | 2622
6348 | 2622 | Future Task |  |  | D347 | Joy Schneider | Submit | DEL D347 - Monthly Performance Report (November 2024) - Submit | 0 hrs | 0 days | 2024-12-11 | 2024-12-11 | 2621 | 2623
6349 | 2623 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Department QC | 1 hr | 7 days | 2024-12-12 | 2024-12-20 | 2622 | 2624
6350 | 2624 | Future Task |  |  | D347 | Joy Schneider | Review | DEL D347 - Monthly Performance Report (November 2024) - Contract Manager Review | 2 hrs | 2 days | 2024-12-23 | 2024-12-24 | 2623 | 2625
6351 | 2625 | Future Task |  |  | D347 | Joy Schneider | Accept | DEL D347 - Monthly Performance Report (November 2024) - Accept | 0 hrs | 0 days | 2024-12-24 | 2024-12-24 | 2624 | 2627
6352 | 2626 | Future Task |  |  | D353 | Joy Schneider |  | D353 - Monthly Performance Report (December 2024) | 10 hrs | 17 days | 2025-01-02 | 2025-01-27
6372 | 2627 | Future Task |  |  | D353 | Joy Schneider | Create | Create December 2024 Monthly Performance Report | 3 hrs | 7 days | 2025-01-02 | 2025-01-10 | 2625 | 2628
6353 | 2628 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-01-13 | 2025-01-13 | 2627 | 2629
6354 | 2629 | Future Task |  |  | D353 | Joy Schneider | Submit | DEL D353 - Monthly Performance Report (December 2024) - Submit | 0 hrs | 0 days | 2025-01-13 | 2025-01-13 | 2628 | 2630
6355 | 2630 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Department QC | 1 hr | 7 days | 2025-01-14 | 2025-01-23 | 2629 | 2631
6356 | 2631 | Future Task |  |  | D353 | Joy Schneider | Review | DEL D353 - Monthly Performance Report (December 2024) - Contract Manager Review | 2 hrs | 2 days | 2025-01-24 | 2025-01-27 | 2630 | 2632
6357 | 2632 | Future Task |  |  | D353 | Joy Schneider | Accept | DEL D353 - Monthly Performance Report (December 2024) - Accept | 0 hrs | 0 days | 2025-01-27 | 2025-01-27 | 2631 | 2634
6358 | 2633 | Future Task |  |  | D359 | Joy Schneider |  | D359 - Monthly Performance Report (January 2025) | 10 hrs | 17 days | 2025-02-03 | 2025-02-25
6371 | 2634 | Future Task |  |  | D359 | Joy Schneider | Create | Create January 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-02-03 | 2025-02-11 | 2632 | 2635
6359 | 2635 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-02-12 | 2025-02-12 | 2634 | 2636
6360 | 2636 | Future Task |  |  | D359 | Joy Schneider | Submit | DEL D359 - Monthly Performance Report (January 2025) - Submit | 0 hrs | 0 days | 2025-02-12 | 2025-02-12 | 2635 | 2637
6361 | 2637 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Department QC | 1 hr | 7 days | 2025-02-13 | 2025-02-21 | 2636 | 2638
6362 | 2638 | Future Task |  |  | D359 | Joy Schneider | Review | DEL D359 - Monthly Performance Report (January 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-02-24 | 2025-02-25 | 2637 | 2639
6363 | 2639 | Future Task |  |  | D359 | Joy Schneider | Accept | DEL D359 - Monthly Performance Report (January 2025) - Accept | 0 hrs | 0 days | 2025-02-25 | 2025-02-25 | 2638 | 2641
6386 | 2640 | Future Task |  |  | D362 | Joy Schneider |  | D362 - Monthly Performance Report (February 2025) | 10 hrs | 17 days | 2025-03-03 | 2025-03-25
6490 | 2641 | Future Task |  |  | D362 | Joy Schneider | Create | Create February 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-03-03 | 2025-03-11 | 2639 | 2642
6387 | 2642 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-03-12 | 2025-03-12 | 2641 | 2643
6388 | 2643 | Future Task |  |  | D362 | Joy Schneider | Submit | DEL D362 - Monthly Performance Report (February 2025) - Submit | 0 hrs | 0 days | 2025-03-12 | 2025-03-12 | 2642 | 2644
6389 | 2644 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Department QC | 1 hr | 7 days | 2025-03-13 | 2025-03-21 | 2643 | 2645
6390 | 2645 | Future Task |  |  | D362 | Joy Schneider | Review | DEL D362 - Monthly Performance Report (February 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-03-24 | 2025-03-25 | 2644 | 2646
6391 | 2646 | Future Task |  |  | D362 | Joy Schneider | Accept | DEL D362 - Monthly Performance Report (February 2025) - Accept | 0 hrs | 0 days | 2025-03-25 | 2025-03-25 | 2645 | 2648
6392 | 2647 | Future Task |  |  | D364 | Joy Schneider |  | D364 - Monthly Performance Report (March 2025) | 10 hrs | 17 days | 2025-04-01 | 2025-04-23
6489 | 2648 | Future Task |  |  | D364 | Joy Schneider | Create | Create March 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-04-01 | 2025-04-09 | 2646 | 2649
6393 | 2649 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-04-10 | 2025-04-10 | 2648 | 2650
6394 | 2650 | Future Task |  |  | D364 | Joy Schneider | Submit | DEL D364 - Monthly Performance Report (March 2025) - Submit | 0 hrs | 0 days | 2025-04-10 | 2025-04-10 | 2649 | 2651
6395 | 2651 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Department QC | 1 hr | 7 days | 2025-04-11 | 2025-04-21 | 2650 | 2652
6396 | 2652 | Future Task |  |  | D364 | Joy Schneider | Review | DEL D364 - Monthly Performance Report (March 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-04-22 | 2025-04-23 | 2651 | 2653
6397 | 2653 | Future Task |  |  | D364 | Joy Schneider | Accept | DEL D364 - Monthly Performance Report (March 2025) - Accept | 0 hrs | 0 days | 2025-04-23 | 2025-04-23 | 2652 | 2655
6398 | 2654 | Future Task |  |  | D366 | Joy Schneider |  | D366 - Monthly Performance Report (April 2025) | 10 hrs | 17 days | 2025-05-01 | 2025-05-23
6488 | 2655 | Future Task |  |  | D366 | Joy Schneider | Create | Create April 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-05-01 | 2025-05-09 | 2653 | 2656
6399 | 2656 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-05-12 | 2025-05-12 | 2655 | 2657
6400 | 2657 | Future Task |  |  | D366 | Joy Schneider | Submit | DEL D366 - Monthly Performance Report (April 2025) - Submit | 0 hrs | 0 days | 2025-05-12 | 2025-05-12 | 2656 | 2658
6401 | 2658 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Department QC | 1 hr | 7 days | 2025-05-13 | 2025-05-21 | 2657 | 2659
6402 | 2659 | Future Task |  |  | D366 | Joy Schneider | Review | DEL D366 - Monthly Performance Report (April 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-05-22 | 2025-05-23 | 2658 | 2660
6403 | 2660 | Future Task |  |  | D366 | Joy Schneider | Accept | DEL D366 - Monthly Performance Report (April 2025) - Accept | 0 hrs | 0 days | 2025-05-23 | 2025-05-23 | 2659 | 2662
6404 | 2661 | Future Task |  |  | D367 | Joy Schneider |  | D367 - Monthly Performance Report (May 2025) | 10 hrs | 17 days | 2025-06-02 | 2025-06-24
6487 | 2662 | Future Task |  |  | D367 | Joy Schneider | Create | Create May 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-06-02 | 2025-06-10 | 2660 | 2663
6405 | 2663 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-06-11 | 2025-06-11 | 2662 | 2664
6406 | 2664 | Future Task |  |  | D367 | Joy Schneider | Submit | DEL D367 - Monthly Performance Report (May 2025) - Submit | 0 hrs | 0 days | 2025-06-11 | 2025-06-11 | 2663 | 2665
6407 | 2665 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Department QC | 1 hr | 7 days | 2025-06-12 | 2025-06-20 | 2664 | 2666
6408 | 2666 | Future Task |  |  | D367 | Joy Schneider | Review | DEL D367 - Monthly Performance Report (May 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-06-23 | 2025-06-24 | 2665 | 2667
6409 | 2667 | Future Task |  |  | D367 | Joy Schneider | Accept | DEL D367 - Monthly Performance Report (May 2025) - Accept | 0 hrs | 0 days | 2025-06-24 | 2025-06-24 | 2666 | 2669
6410 | 2668 | Future Task |  |  | D368 | Joy Schneider |  | D368 - Monthly Performance Report (June 2025) | 10 hrs | 17 days | 2025-07-01 | 2025-07-24
6486 | 2669 | Future Task |  |  | D368 | Joy Schneider | Create | Create June 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-07-01 | 2025-07-10 | 2667 | 2670
6411 | 2670 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-07-11 | 2025-07-11 | 2669 | 2671
6412 | 2671 | Future Task |  |  | D368 | Joy Schneider | Submit | DEL D368 - Monthly Performance Report (June 2025) - Submit | 0 hrs | 0 days | 2025-07-11 | 2025-07-11 | 2670 | 2672
6413 | 2672 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Department QC | 1 hr | 7 days | 2025-07-14 | 2025-07-22 | 2671 | 2673
6414 | 2673 | Future Task |  |  | D368 | Joy Schneider | Review | DEL D368 - Monthly Performance Report (June 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-07-23 | 2025-07-24 | 2672 | 2674
6415 | 2674 | Future Task |  |  | D368 | Joy Schneider | Accept | DEL D368 - Monthly Performance Report (June 2025) - Accept | 0 hrs | 0 days | 2025-07-24 | 2025-07-24 | 2673 | 2676
6416 | 2675 | Future Task |  |  | D369 | Joy Schneider |  | D369 - Monthly Performance Report (July 2025) | 10 hrs | 17 days | 2025-08-01 | 2025-08-25
6485 | 2676 | Future Task |  |  | D369 | Joy Schneider | Create | Create July 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-08-01 | 2025-08-11 | 2674 | 2677
6417 | 2677 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-08-12 | 2025-08-12 | 2676 | 2678
6418 | 2678 | Future Task |  |  | D369 | Joy Schneider | Submit | DEL D369 - Monthly Performance Report (July 2025) - Submit | 0 hrs | 0 days | 2025-08-12 | 2025-08-12 | 2677 | 2679
6419 | 2679 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Department QC | 1 hr | 7 days | 2025-08-13 | 2025-08-21 | 2678 | 2680
6420 | 2680 | Future Task |  |  | D369 | Joy Schneider | Review | DEL D369 - Monthly Performance Report (July 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-08-22 | 2025-08-25 | 2679 | 2681
6421 | 2681 | Future Task |  |  | D369 | Joy Schneider | Accept | DEL D369 - Monthly Performance Report (July 2025) - Accept | 0 hrs | 0 days | 2025-08-25 | 2025-08-25 | 2680 | 2683
6422 | 2682 | Future Task |  |  | D370 | Joy Schneider |  | D370 - Monthly Performance Report (August 2025) | 10 hrs | 17 days | 2025-09-02 | 2025-09-24
6484 | 2683 | Future Task |  |  | D370 | Joy Schneider | Create | Create August 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-09-02 | 2025-09-10 | 2681 | 2684
6423 | 2684 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-09-11 | 2025-09-11 | 2683 | 2685
6424 | 2685 | Future Task |  |  | D370 | Joy Schneider | Submit | DEL D370 - Monthly Performance Report (August 2025) - Submit | 0 hrs | 0 days | 2025-09-11 | 2025-09-11 | 2684 | 2686
6425 | 2686 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Department QC | 1 hr | 7 days | 2025-09-12 | 2025-09-22 | 2685 | 2687
6426 | 2687 | Future Task |  |  | D370 | Joy Schneider | Review | DEL D370 - Monthly Performance Report (August 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-09-23 | 2025-09-24 | 2686 | 2688
6427 | 2688 | Future Task |  |  | D370 | Joy Schneider | Accept | DEL D370 - Monthly Performance Report (August 2025) - Accept | 0 hrs | 0 days | 2025-09-24 | 2025-09-24 | 2687 | 2690
6428 | 2689 | Future Task |  |  | D371 | Joy Schneider |  | D371 - Monthly Performance Report (September 2025) | 10 hrs | 17 days | 2025-10-01 | 2025-10-23
6483 | 2690 | Future Task |  |  | D371 | Joy Schneider | Create | Create September 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-10-01 | 2025-10-09 | 2688 | 2691
6429 | 2691 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-10-10 | 2025-10-10 | 2690 | 2692
6430 | 2692 | Future Task |  |  | D371 | Joy Schneider | Submit | DEL D371 - Monthly Performance Report (September 2025) - Submit | 0 hrs | 0 days | 2025-10-10 | 2025-10-10 | 2691 | 2693
6431 | 2693 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Department QC | 1 hr | 7 days | 2025-10-13 | 2025-10-21 | 2692 | 2694
6432 | 2694 | Future Task |  |  | D371 | Joy Schneider | Review | DEL D371 - Monthly Performance Report (September 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-10-22 | 2025-10-23 | 2693 | 2695
6433 | 2695 | Future Task |  |  | D371 | Joy Schneider | Accept | DEL D371 - Monthly Performance Report (September 2025) - Accept | 0 hrs | 0 days | 2025-10-23 | 2025-10-23 | 2694 | 2697
6434 | 2696 | Future Task |  |  | D373 | Joy Schneider |  | D373 - Monthly Performance Report (October 2025) | 10 hrs | 17 days | 2025-11-03 | 2025-11-26
6482 | 2697 | Future Task |  |  | D373 | Joy Schneider | Create | Create October 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-11-03 | 2025-11-12 | 2695 | 2698
6435 | 2698 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-11-13 | 2025-11-13 | 2697 | 2699
6436 | 2699 | Future Task |  |  | D373 | Joy Schneider | Submit | DEL D373 - Monthly Performance Report (October 2025) - Submit | 0 hrs | 0 days | 2025-11-13 | 2025-11-13 | 2698 | 2700
6437 | 2700 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Department QC | 1 hr | 7 days | 2025-11-14 | 2025-11-24 | 2699 | 2701
6438 | 2701 | Future Task |  |  | D373 | Joy Schneider | Review | DEL D373 - Monthly Performance Report (October 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-11-25 | 2025-11-26 | 2700 | 2702
6439 | 2702 | Future Task |  |  | D373 | Joy Schneider | Accept | DEL D373 - Monthly Performance Report (October 2025) - Accept | 0 hrs | 0 days | 2025-11-26 | 2025-11-26 | 2701 | 2704
6440 | 2703 | Future Task |  |  | D374 | Joy Schneider |  | D374 - Monthly Performance Report (November 2025) | 10 hrs | 17 days | 2025-12-01 | 2025-12-23
6481 | 2704 | Future Task |  |  | D374 | Joy Schneider | Create | Create November 2025 Monthly Performance Report | 3 hrs | 7 days | 2025-12-01 | 2025-12-09 | 2702 | 2705
6441 | 2705 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2025-12-10 | 2025-12-10 | 2704 | 2706
6442 | 2706 | Future Task |  |  | D374 | Joy Schneider | Submit | DEL D374 - Monthly Performance Report (November 2025) - Submit | 0 hrs | 0 days | 2025-12-10 | 2025-12-10 | 2705 | 2707
6443 | 2707 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Department QC | 1 hr | 7 days | 2025-12-11 | 2025-12-19 | 2706 | 2708
6444 | 2708 | Future Task |  |  | D374 | Joy Schneider | Review | DEL D374 - Monthly Performance Report (November 2025) - Contract Manager Review | 2 hrs | 2 days | 2025-12-22 | 2025-12-23 | 2707 | 2709
6445 | 2709 | Future Task |  |  | D374 | Joy Schneider | Accept | DEL D374 - Monthly Performance Report (November 2025) - Accept | 0 hrs | 0 days | 2025-12-23 | 2025-12-23 | 2708 | 2711
6446 | 2710 | Future Task |  |  | D375 | Joy Schneider |  | D375 - Monthly Performance Report (December 2025) | 10 hrs | 17 days | 2026-01-02 | 2026-01-27
6480 | 2711 | Future Task |  |  | D375 | Joy Schneider | Create | Create December 2025 Monthly Performance Report | 3 hrs | 7 days | 2026-01-02 | 2026-01-12 | 2709 | 2712
6447 | 2712 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-01-13 | 2026-01-13 | 2711 | 2713
6448 | 2713 | Future Task |  |  | D375 | Joy Schneider | Submit | DEL D375 - Monthly Performance Report (December 2025) - Submit | 0 hrs | 0 days | 2026-01-13 | 2026-01-13 | 2712 | 2714
6449 | 2714 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Department QC | 1 hr | 7 days | 2026-01-14 | 2026-01-23 | 2713 | 2715
6450 | 2715 | Future Task |  |  | D375 | Joy Schneider | Review | DEL D375 - Monthly Performance Report (December 2025) - Contract Manager Review | 2 hrs | 2 days | 2026-01-26 | 2026-01-27 | 2714 | 2716
6451 | 2716 | Future Task |  |  | D375 | Joy Schneider | Accept | DEL D375 - Monthly Performance Report (December 2025) - Accept | 0 hrs | 0 days | 2026-01-27 | 2026-01-27 | 2715 | 2718
6452 | 2717 | Future Task |  |  | D432 | Joy Schneider |  | D432 - Monthly Performance Report (January 2026) | 10 hrs | 17 days | 2026-02-02 | 2026-02-24
6479 | 2718 | Future Task |  |  | D432 | Joy Schneider | Create | Create January 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-02-02 | 2026-02-10 | 2716 | 2719
6453 | 2719 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-02-11 | 2026-02-11 | 2718 | 2720
6454 | 2720 | Future Task |  |  | D432 | Joy Schneider | Submit | DEL D432 - Monthly Performance Report (January 2026) - Submit | 0 hrs | 0 days | 2026-02-11 | 2026-02-11 | 2719 | 2721
6455 | 2721 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Department QC | 1 hr | 7 days | 2026-02-12 | 2026-02-20 | 2720 | 2722
6456 | 2722 | Future Task |  |  | D432 | Joy Schneider | Review | DEL D432 - Monthly Performance Report (January 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-02-23 | 2026-02-24 | 2721 | 2723
6457 | 2723 | Future Task |  |  | D432 | Joy Schneider | Accept | DEL D432 - Monthly Performance Report (January 2026) - Accept | 0 hrs | 0 days | 2026-02-24 | 2026-02-24 | 2722 | 2725
6458 | 2724 | Future Task |  |  | D434 | Joy Schneider |  | D434 - Monthly Performance Report (February 2026) | 10 hrs | 17 days | 2026-03-02 | 2026-03-24
6478 | 2725 | Future Task |  |  | D434 | Joy Schneider | Create | Create February 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-03-02 | 2026-03-10 | 2723 | 2726
6459 | 2726 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-03-11 | 2026-03-11 | 2725 | 2727
6460 | 2727 | Future Task |  |  | D434 | Joy Schneider | Submit | DEL D434 - Monthly Performance Report (February 2026) - Submit | 0 hrs | 0 days | 2026-03-11 | 2026-03-11 | 2726 | 2728
6461 | 2728 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Department QC | 1 hr | 7 days | 2026-03-12 | 2026-03-20 | 2727 | 2729
6462 | 2729 | Future Task |  |  | D434 | Joy Schneider | Review | DEL D434 - Monthly Performance Report (February 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-03-23 | 2026-03-24 | 2728 | 2730
6463 | 2730 | Future Task |  |  | D434 | Joy Schneider | Accept | DEL D434 - Monthly Performance Report (February 2026) - Accept | 0 hrs | 0 days | 2026-03-24 | 2026-03-24 | 2729 | 2732
6464 | 2731 | Future Task |  |  | D435 | Joy Schneider |  | D435 - Monthly Performance Report (March 2026) | 10 hrs | 17 days | 2026-04-01 | 2026-04-23
6477 | 2732 | Future Task |  |  | D435 | Joy Schneider | Create | Create March 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-04-01 | 2026-04-09 | 2730 | 2733
6465 | 2733 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-04-10 | 2026-04-10 | 2732 | 2734
6466 | 2734 | Future Task |  |  | D435 | Joy Schneider | Submit | DEL D435 - Monthly Performance Report (March 2026) - Submit | 0 hrs | 0 days | 2026-04-10 | 2026-04-10 | 2733 | 2735
6467 | 2735 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Department QC | 1 hr | 7 days | 2026-04-13 | 2026-04-21 | 2734 | 2736
6468 | 2736 | Future Task |  |  | D435 | Joy Schneider | Review | DEL D435 - Monthly Performance Report (March 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-04-22 | 2026-04-23 | 2735 | 2737
6469 | 2737 | Future Task |  |  | D435 | Joy Schneider | Accept | DEL D435 - Monthly Performance Report (March 2026) - Accept | 0 hrs | 0 days | 2026-04-23 | 2026-04-23 | 2736 | 2739
6470 | 2738 | Future Task |  |  | D437 | Joy Schneider |  | D437 - Monthly Performance Report (April 2026) | 10 hrs | 17 days | 2026-05-01 | 2026-05-26
6476 | 2739 | Future Task |  |  | D437 | Joy Schneider | Create | Create April 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-05-01 | 2026-05-11 | 2737 | 2740
6471 | 2740 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-05-12 | 2026-05-12 | 2739 | 2741
6472 | 2741 | Future Task |  |  | D437 | Joy Schneider | Submit | DEL D437 - Monthly Performance Report (April 2026) - Submit | 0 hrs | 0 days | 2026-05-12 | 2026-05-12 | 2740 | 2742
6473 | 2742 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Department QC | 1 hr | 7 days | 2026-05-13 | 2026-05-21 | 2741 | 2743
6474 | 2743 | Future Task |  |  | D437 | Joy Schneider | Review | DEL D437 - Monthly Performance Report (April 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-05-22 | 2026-05-26 | 2742 | 2744
6475 | 2744 | Future Task |  |  | D437 | Joy Schneider | Accept | DEL D437 - Monthly Performance Report (April 2026) - Accept | 0 hrs | 0 days | 2026-05-26 | 2026-05-26 | 2743 | 2746
6491 | 2745 | Future Task |  |  | D438 | Joy Schneider |  | D438 - Monthly Performance Report (May 2026) | 10 hrs | 17 days | 2026-06-01 | 2026-06-23
6595 | 2746 | Future Task |  |  | D438 | Joy Schneider | Create | Create May 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-06-01 | 2026-06-09 | 2744 | 2747
6492 | 2747 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-06-10 | 2026-06-10 | 2746 | 2748
6493 | 2748 | Future Task |  |  | D438 | Joy Schneider | Submit | DEL D438 - Monthly Performance Report (May 2026) - Submit | 0 hrs | 0 days | 2026-06-10 | 2026-06-10 | 2747 | 2749
6494 | 2749 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Department QC | 1 hr | 7 days | 2026-06-11 | 2026-06-19 | 2748 | 2750
6495 | 2750 | Future Task |  |  | D438 | Joy Schneider | Review | DEL D438 - Monthly Performance Report (May 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-06-22 | 2026-06-23 | 2749 | 2751
6496 | 2751 | Future Task |  |  | D438 | Joy Schneider | Accept | DEL D438 - Monthly Performance Report (May 2026) - Accept | 0 hrs | 0 days | 2026-06-23 | 2026-06-23 | 2750 | 2753
6497 | 2752 | Future Task |  |  | D439 | Joy Schneider |  | D439 - Monthly Performance Report (June 2026) | 10 hrs | 17 days | 2026-07-01 | 2026-07-24
6594 | 2753 | Future Task |  |  | D439 | Joy Schneider | Create | Create June 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-07-01 | 2026-07-10 | 2751 | 2754
6498 | 2754 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-07-13 | 2026-07-13 | 2753 | 2755
6499 | 2755 | Future Task |  |  | D439 | Joy Schneider | Submit | DEL D439 - Monthly Performance Report (June 2026) - Submit | 0 hrs | 0 days | 2026-07-13 | 2026-07-13 | 2754 | 2756
6500 | 2756 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Department QC | 1 hr | 7 days | 2026-07-14 | 2026-07-22 | 2755 | 2757
6501 | 2757 | Future Task |  |  | D439 | Joy Schneider | Review | DEL D439 - Monthly Performance Report (June 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-07-23 | 2026-07-24 | 2756 | 2758
6502 | 2758 | Future Task |  |  | D439 | Joy Schneider | Accept | DEL D439 - Monthly Performance Report (June 2026) - Accept | 0 hrs | 0 days | 2026-07-24 | 2026-07-24 | 2757 | 2760
6503 | 2759 | Future Task |  |  | D441 | Joy Schneider |  | D441 - Monthly Performance Report (July 2026) | 10 hrs | 17 days | 2026-08-03 | 2026-08-25
6593 | 2760 | Future Task |  |  | D441 | Joy Schneider | Create | Create July 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-08-03 | 2026-08-11 | 2758 | 2761
6504 | 2761 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-08-12 | 2026-08-12 | 2760 | 2762
6505 | 2762 | Future Task |  |  | D441 | Joy Schneider | Submit | DEL D441 - Monthly Performance Report (July 2026) - Submit | 0 hrs | 0 days | 2026-08-12 | 2026-08-12 | 2761 | 2763
6506 | 2763 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Department QC | 1 hr | 7 days | 2026-08-13 | 2026-08-21 | 2762 | 2764
6507 | 2764 | Future Task |  |  | D441 | Joy Schneider | Review | DEL D441 - Monthly Performance Report (July 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-08-24 | 2026-08-25 | 2763 | 2765
6508 | 2765 | Future Task |  |  | D441 | Joy Schneider | Accept | DEL D441 - Monthly Performance Report (July 2026) - Accept | 0 hrs | 0 days | 2026-08-25 | 2026-08-25 | 2764 | 2767
6509 | 2766 | Future Task |  |  | D442 | Joy Schneider |  | D442 - Monthly Performance Report (August 2026) | 10 hrs | 17 days | 2026-09-01 | 2026-09-24
6592 | 2767 | Future Task |  |  | D442 | Joy Schneider | Create | Create August 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-09-01 | 2026-09-10 | 2765 | 2768
6510 | 2768 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-09-11 | 2026-09-11 | 2767 | 2769
6511 | 2769 | Future Task |  |  | D442 | Joy Schneider | Submit | DEL D442 - Monthly Performance Report (August 2026) - Submit | 0 hrs | 0 days | 2026-09-11 | 2026-09-11 | 2768 | 2770
6512 | 2770 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Department QC | 1 hr | 7 days | 2026-09-14 | 2026-09-22 | 2769 | 2771
6513 | 2771 | Future Task |  |  | D442 | Joy Schneider | Review | DEL D442 - Monthly Performance Report (August 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-09-23 | 2026-09-24 | 2770 | 2772
6514 | 2772 | Future Task |  |  | D442 | Joy Schneider | Accept | DEL D442 - Monthly Performance Report (August 2026) - Accept | 0 hrs | 0 days | 2026-09-24 | 2026-09-24 | 2771 | 2774
6515 | 2773 | Future Task |  |  | D443 | Joy Schneider |  | D443 - Monthly Performance Report (September 2026) | 10 hrs | 17 days | 2026-10-01 | 2026-10-23
6591 | 2774 | Future Task |  |  | D443 | Joy Schneider | Create | Create September 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-10-01 | 2026-10-09 | 2772 | 2775
6516 | 2775 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-10-12 | 2026-10-12 | 2774 | 2776
6517 | 2776 | Future Task |  |  | D443 | Joy Schneider | Submit | DEL D443 - Monthly Performance Report (September 2026) - Submit | 0 hrs | 0 days | 2026-10-12 | 2026-10-12 | 2775 | 2777
6518 | 2777 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Department QC | 1 hr | 7 days | 2026-10-13 | 2026-10-21 | 2776 | 2778
6519 | 2778 | Future Task |  |  | D443 | Joy Schneider | Review | DEL D443 - Monthly Performance Report (September 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-10-22 | 2026-10-23 | 2777 | 2779
6520 | 2779 | Future Task |  |  | D443 | Joy Schneider | Accept | DEL D443 - Monthly Performance Report (September 2026) - Accept | 0 hrs | 0 days | 2026-10-23 | 2026-10-23 | 2778 | 2781
6521 | 2780 | Future Task |  |  | D444 | Joy Schneider |  | D444 - Monthly Performance Report (October 2026) | 10 hrs | 17 days | 2026-11-02 | 2026-11-25
6590 | 2781 | Future Task |  |  | D444 | Joy Schneider | Create | Create October 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-11-02 | 2026-11-10 | 2779 | 2782
6522 | 2782 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-11-12 | 2026-11-12 | 2781 | 2783
6523 | 2783 | Future Task |  |  | D444 | Joy Schneider | Submit | DEL D444 - Monthly Performance Report (October 2026) - Submit | 0 hrs | 0 days | 2026-11-12 | 2026-11-12 | 2782 | 2784
6524 | 2784 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Department QC | 1 hr | 7 days | 2026-11-13 | 2026-11-23 | 2783 | 2785
6525 | 2785 | Future Task |  |  | D444 | Joy Schneider | Review | DEL D444 - Monthly Performance Report (October 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-11-24 | 2026-11-25 | 2784 | 2786
6526 | 2786 | Future Task |  |  | D444 | Joy Schneider | Accept | DEL D444 - Monthly Performance Report (October 2026) - Accept | 0 hrs | 0 days | 2026-11-25 | 2026-11-25 | 2785 | 2788
6527 | 2787 | Future Task |  |  | D445 | Joy Schneider |  | D445 - Monthly Performance Report (November 2026) | 10 hrs | 17 days | 2026-12-01 | 2026-12-23
6589 | 2788 | Future Task |  |  | D445 | Joy Schneider | Create | Create November 2026 Monthly Performance Report | 3 hrs | 7 days | 2026-12-01 | 2026-12-09 | 2786 | 2789
6528 | 2789 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2026-12-10 | 2026-12-10 | 2788 | 2790
6529 | 2790 | Future Task |  |  | D445 | Joy Schneider | Submit | DEL D445 - Monthly Performance Report (November 2026) - Submit | 0 hrs | 0 days | 2026-12-10 | 2026-12-10 | 2789 | 2791
6530 | 2791 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Department QC | 1 hr | 7 days | 2026-12-11 | 2026-12-21 | 2790 | 2792
6531 | 2792 | Future Task |  |  | D445 | Joy Schneider | Review | DEL D445 - Monthly Performance Report (November 2026) - Contract Manager Review | 2 hrs | 2 days | 2026-12-22 | 2026-12-23 | 2791 | 2793
6532 | 2793 | Future Task |  |  | D445 | Joy Schneider | Accept | DEL D445 - Monthly Performance Report (November 2026) - Accept | 0 hrs | 0 days | 2026-12-23 | 2026-12-23 | 2792 | 2795
6533 | 2794 | Future Task |  |  | D446 | Joy Schneider |  | D446 - Monthly Performance Report (December 2026) | 10 hrs | 17 days | 2027-01-04 | 2027-01-27
6588 | 2795 | Future Task |  |  | D446 | Joy Schneider | Create | Create December 2026 Monthly Performance Report | 3 hrs | 7 days | 2027-01-04 | 2027-01-12 | 2793 | 2796
6534 | 2796 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-01-13 | 2027-01-13 | 2795 | 2797
6535 | 2797 | Future Task |  |  | D446 | Joy Schneider | Submit | DEL D446 - Monthly Performance Report (December 2026) - Submit | 0 hrs | 0 days | 2027-01-13 | 2027-01-13 | 2796 | 2798
6536 | 2798 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Department QC | 1 hr | 7 days | 2027-01-14 | 2027-01-25 | 2797 | 2799
6537 | 2799 | Future Task |  |  | D446 | Joy Schneider | Review | DEL D446 - Monthly Performance Report (December 2026) - Contract Manager Review | 2 hrs | 2 days | 2027-01-26 | 2027-01-27 | 2798 | 2800
6538 | 2800 | Future Task |  |  | D446 | Joy Schneider | Accept | DEL D446 - Monthly Performance Report (December 2026) - Accept | 0 hrs | 0 days | 2027-01-27 | 2027-01-27 | 2799 | 2802
6539 | 2801 | Future Task |  |  | D447 | Joy Schneider |  | D447 - Monthly Performance Report (January 2027) | 10 hrs | 17 days | 2027-02-01 | 2027-02-23
6587 | 2802 | Future Task |  |  | D447 | Joy Schneider | Create | Create January 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-02-01 | 2027-02-09 | 2800 | 2803
6540 | 2803 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-02-10 | 2027-02-10 | 2802 | 2804
6541 | 2804 | Future Task |  |  | D447 | Joy Schneider | Submit | DEL D447 - Monthly Performance Report (January 2027) - Submit | 0 hrs | 0 days | 2027-02-10 | 2027-02-10 | 2803 | 2805
6542 | 2805 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Department QC | 1 hr | 7 days | 2027-02-11 | 2027-02-19 | 2804 | 2806
6543 | 2806 | Future Task |  |  | D447 | Joy Schneider | Review | DEL D447 - Monthly Performance Report (January 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-02-22 | 2027-02-23 | 2805 | 2807
6544 | 2807 | Future Task |  |  | D447 | Joy Schneider | Accept | DEL D447 - Monthly Performance Report (January 2027) - Accept | 0 hrs | 0 days | 2027-02-23 | 2027-02-23 | 2806 | 2809
6545 | 2808 | Future Task |  |  | D448 | Joy Schneider |  | D448 - Monthly Performance Report (February 2027) | 10 hrs | 17 days | 2027-03-01 | 2027-03-23
6586 | 2809 | Future Task |  |  | D448 | Joy Schneider | Create | Create February 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-03-01 | 2027-03-09 | 2807 | 2810
6546 | 2810 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-03-10 | 2027-03-10 | 2809 | 2811
6547 | 2811 | Future Task |  |  | D448 | Joy Schneider | Submit | DEL D448 - Monthly Performance Report (February 2027) - Submit | 0 hrs | 0 days | 2027-03-10 | 2027-03-10 | 2810 | 2812
6548 | 2812 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Department QC | 1 hr | 7 days | 2027-03-11 | 2027-03-19 | 2811 | 2813
6549 | 2813 | Future Task |  |  | D448 | Joy Schneider | Review | DEL D448 - Monthly Performance Report (February 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-03-22 | 2027-03-23 | 2812 | 2814
6550 | 2814 | Future Task |  |  | D448 | Joy Schneider | Accept | DEL D448 - Monthly Performance Report (February 2027) - Accept | 0 hrs | 0 days | 2027-03-23 | 2027-03-23 | 2813 | 2816
6551 | 2815 | Future Task |  |  | D449 | Joy Schneider |  | D449 - Monthly Performance Report (March 2027) | 10 hrs | 17 days | 2027-04-01 | 2027-04-23
6585 | 2816 | Future Task |  |  | D449 | Joy Schneider | Create | Create March 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-04-01 | 2027-04-09 | 2814 | 2817
6552 | 2817 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-04-12 | 2027-04-12 | 2816 | 2818
6553 | 2818 | Future Task |  |  | D449 | Joy Schneider | Submit | DEL D449 - Monthly Performance Report (March 2027) - Submit | 0 hrs | 0 days | 2027-04-12 | 2027-04-12 | 2817 | 2819
6554 | 2819 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Department QC | 1 hr | 7 days | 2027-04-13 | 2027-04-21 | 2818 | 2820
6555 | 2820 | Future Task |  |  | D449 | Joy Schneider | Review | DEL D449 - Monthly Performance Report (March 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-04-22 | 2027-04-23 | 2819 | 2821
6556 | 2821 | Future Task |  |  | D449 | Joy Schneider | Accept | DEL D449 - Monthly Performance Report (March 2027) - Accept | 0 hrs | 0 days | 2027-04-23 | 2027-04-23 | 2820 | 2823
6557 | 2822 | Future Task |  |  | D450 | Joy Schneider |  | D450 - Monthly Performance Report (April 2027) | 10 hrs | 17 days | 2027-05-03 | 2027-05-25
6584 | 2823 | Future Task |  |  | D450 | Joy Schneider | Create | Create April 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-05-03 | 2027-05-11 | 2821 | 2824
6558 | 2824 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-05-12 | 2027-05-12 | 2823 | 2825
6559 | 2825 | Future Task |  |  | D450 | Joy Schneider | Submit | DEL D450 - Monthly Performance Report (April 2027) - Submit | 0 hrs | 0 days | 2027-05-12 | 2027-05-12 | 2824 | 2826
6560 | 2826 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Department QC | 1 hr | 7 days | 2027-05-13 | 2027-05-21 | 2825 | 2827
6561 | 2827 | Future Task |  |  | D450 | Joy Schneider | Review | DEL D450 - Monthly Performance Report (April 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-05-24 | 2027-05-25 | 2826 | 2828
6562 | 2828 | Future Task |  |  | D450 | Joy Schneider | Accept | DEL D450 - Monthly Performance Report (April 2027) - Accept | 0 hrs | 0 days | 2027-05-25 | 2027-05-25 | 2827 | 2830
6563 | 2829 | Future Task |  |  | D451 | Joy Schneider |  | D451 - Monthly Performance Report (May 2027) | 10 hrs | 17 days | 2027-06-02 | 2027-06-24
6583 | 2830 | Future Task |  |  | D451 | Joy Schneider | Create | Create May 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-06-02 | 2027-06-10 | 2828 | 2831
6564 | 2831 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-06-11 | 2027-06-11 | 2830 | 2832
6565 | 2832 | Future Task |  |  | D451 | Joy Schneider | Submit | DEL D451 - Monthly Performance Report (May 2027) - Submit | 0 hrs | 0 days | 2027-06-11 | 2027-06-11 | 2831 | 2833
6566 | 2833 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Department QC | 1 hr | 7 days | 2027-06-14 | 2027-06-22 | 2832 | 2834
6567 | 2834 | Future Task |  |  | D451 | Joy Schneider | Review | DEL D451 - Monthly Performance Report (May 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-06-23 | 2027-06-24 | 2833 | 2835
6568 | 2835 | Future Task |  |  | D451 | Joy Schneider | Accept | DEL D451 - Monthly Performance Report (May 2027) - Accept | 0 hrs | 0 days | 2027-06-24 | 2027-06-24 | 2834 | 2837
6569 | 2836 | Future Task |  |  | D694 | Joy Schneider |  | D694 - Monthly Performance Report (June 2027) | 10 hrs | 17 days | 2027-07-01 | 2027-07-26
6582 | 2837 | Future Task |  |  | D694 | Joy Schneider | Create | Create June 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-07-01 | 2027-07-12 | 2835 | 2838
6570 | 2838 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-07-13 | 2027-07-13 | 2837 | 2839
6571 | 2839 | Future Task |  |  | D694 | Joy Schneider | Submit | DEL D694 - Monthly Performance Report (June 2027) - Submit | 0 hrs | 0 days | 2027-07-13 | 2027-07-13 | 2838 | 2840
6572 | 2840 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Department QC | 1 hr | 7 days | 2027-07-14 | 2027-07-22 | 2839 | 2841
6573 | 2841 | Future Task |  |  | D694 | Joy Schneider | Review | DEL D694 - Monthly Performance Report (June 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-07-23 | 2027-07-26 | 2840 | 2842
6574 | 2842 | Future Task |  |  | D694 | Joy Schneider | Accept | DEL D694 - Monthly Performance Report (June 2027) - Accept | 0 hrs | 0 days | 2027-07-26 | 2027-07-26 | 2841 | 2844
6575 | 2843 | Future Task |  |  | D695 | Joy Schneider |  | D695 - Monthly Performance Report (July 2027) | 10 hrs | 17 days | 2027-08-02 | 2027-08-24
6581 | 2844 | Future Task |  |  | D695 | Joy Schneider | Create | Create July 2027 Monthly Performance Report | 3 hrs | 7 days | 2027-08-02 | 2027-08-10 | 2842 | 2845
6576 | 2845 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Final Collaborative Review & Update | 4 hrs | 1 day | 2027-08-11 | 2027-08-11 | 2844 | 2846
6577 | 2846 | Future Task |  |  | D695 | Joy Schneider | Submit | DEL D695 - Monthly Performance Report (July 2027) - Submit | 0 hrs | 0 days | 2027-08-11 | 2027-08-11 | 2845 | 2847
6578 | 2847 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Department QC | 1 hr | 7 days | 2027-08-12 | 2027-08-20 | 2846 | 2848
6579 | 2848 | Future Task |  |  | D695 | Joy Schneider | Review | DEL D695 - Monthly Performance Report (July 2027) - Contract Manager Review | 2 hrs | 2 days | 2027-08-23 | 2027-08-24 | 2847 | 2849
6580 | 2849 | Future Task |  |  | D695 | Joy Schneider | Accept | DEL D695 - Monthly Performance Report (July 2027) - Accept | 0 hrs | 0 days | 2027-08-24 | 2027-08-24 | 2848
4047 | 2850 | Future Task | [5 empty] | Quarterly Newsletter for DDI of Reporting Functionality | 132 hrs | 658 days | 2023-06-21 | 2026-02-02
4048 | 2851 | Future Task | [5 empty] | Quarterly Newsletter | 132 hrs | 658 days | 2023-06-21 | 2026-02-02
4049 | 2852 | Future Task | [5 empty] | Quarterly Newsletter FY 22-23 Q4 | 12 hrs | 17 days | 2023-06-21 | 2023-07-14
4050 | 2853 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2023-06-21 | 2023-06-27 |  | 2854
4051 | 2854 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2023-06-28 | 2023-07-05 | 2853 | 2855
4052 | 2855 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2023-07-06 | 2023-07-12 | 2854 | 2856
4053 | 2856 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2023-07-13 | 2023-07-14 | 2855 | 2858
4054 | 2857 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q1 | 12 hrs | 17 days | 2023-09-22 | 2023-10-16
4055 | 2858 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2023-09-22 | 2023-09-28 | 2856 | 2859
4056 | 2859 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2023-09-29 | 2023-10-05 | 2858 | 2860
4057 | 2860 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2023-10-06 | 2023-10-12 | 2859 | 2861
4058 | 2861 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2023-10-13 | 2023-10-16 | 2860 | 2863
4059 | 2862 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q2 | 12 hrs | 17 days | 2023-12-18 | 2024-01-11
4060 | 2863 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2023-12-18 | 2023-12-22 | 2861 | 2864
4061 | 2864 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2023-12-26 | 2024-01-02 | 2863 | 2865
4062 | 2865 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2024-01-03 | 2024-01-09 | 2864 | 2866
4063 | 2866 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2024-01-10 | 2024-01-11 | 2865 | 2868
4064 | 2867 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q3 | 12 hrs | 17 days | 2024-03-22 | 2024-04-15
4065 | 2868 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2024-03-22 | 2024-03-28 | 2866 | 2869
4066 | 2869 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2024-03-29 | 2024-04-04 | 2868 | 2870
4067 | 2870 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2024-04-05 | 2024-04-11 | 2869 | 2871
4068 | 2871 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2024-04-12 | 2024-04-15 | 2870 | 2873
4069 | 2872 | Future Task | [5 empty] | Quarterly Newsletter FY 23-24 Q4 | 12 hrs | 17 days | 2024-06-20 | 2024-07-15
4070 | 2873 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2024-06-20 | 2024-06-26 | 2871 | 2874
4071 | 2874 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2024-06-27 | 2024-07-03 | 2873 | 2875
4072 | 2875 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2024-07-05 | 2024-07-11 | 2874 | 2876
4073 | 2876 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2024-07-12 | 2024-07-15 | 2875 | 2878
4074 | 2877 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q1 | 12 hrs | 17 days | 2024-09-23 | 2024-10-15
4075 | 2878 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2024-09-23 | 2024-09-27 | 2876 | 2879
4076 | 2879 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2024-09-30 | 2024-10-04 | 2878 | 2880
4077 | 2880 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2024-10-07 | 2024-10-11 | 2879 | 2881
4078 | 2881 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2024-10-14 | 2024-10-15 | 2880 | 2883
4079 | 2882 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q2 | 12 hrs | 17 days | 2024-12-16 | 2025-01-09
4080 | 2883 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2024-12-16 | 2024-12-20 | 2881 | 2884
4081 | 2884 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2024-12-23 | 2024-12-30 | 2883 | 2885
4082 | 2885 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2024-12-31 | 2025-01-07 | 2884 | 2886
4083 | 2886 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2025-01-08 | 2025-01-09 | 2885 | 2888
4084 | 2887 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q3 | 12 hrs | 17 days | 2025-03-24 | 2025-04-15
4085 | 2888 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2025-03-24 | 2025-03-28 | 2886 | 2889
4086 | 2889 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2025-03-31 | 2025-04-04 | 2888 | 2890
4087 | 2890 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2025-04-07 | 2025-04-11 | 2889 | 2891
4088 | 2891 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2025-04-14 | 2025-04-15 | 2890 | 2893
4089 | 2892 | Future Task | [5 empty] | Quarterly Newsletter FY 24-25 Q4 | 12 hrs | 17 days | 2025-06-20 | 2025-07-15
4090 | 2893 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2025-06-20 | 2025-06-26 | 2891 | 2894
4091 | 2894 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2025-06-27 | 2025-07-03 | 2893 | 2895
4092 | 2895 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2025-07-07 | 2025-07-11 | 2894 | 2896
4093 | 2896 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2025-07-14 | 2025-07-15 | 2895 | 2898
4094 | 2897 | Future Task | [5 empty] | Quarterly Newsletter FY 25-26 Q1 | 12 hrs | 17 days | 2025-09-26 | 2025-10-20
4095 | 2898 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2025-09-26 | 2025-10-02 | 2896 | 2899
4096 | 2899 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2025-10-03 | 2025-10-09 | 2898 | 2900
4097 | 2900 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2025-10-10 | 2025-10-16 | 2899 | 2901
4098 | 2901 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2025-10-17 | 2025-10-20 | 2900 | 2903
4099 | 2902 | Future Task | [5 empty] | Quarterly Newsletter FY 25-26 Q2 | 12 hrs | 17 days | 2026-01-08 | 2026-02-02
4100 | 2903 | Future Task |  |  |  | Jennifer Reeves | Create | Create - Quarterly Newsletter | 2 hrs | 5 days | 2026-01-08 | 2026-01-14 | 2901 | 2904
4101 | 2904 | Future Task |  |  |  | Jennifer Reeves | Review | Collaborative Review and Update - Quarterly Newsletter | 7 hrs | 5 days | 2026-01-15 | 2026-01-22 | 2903 | 2905
4102 | 2905 | Future Task |  |  |  | Jennifer Reeves | Approve | Approve - Quarterly Newsletter | 2 hrs | 5 days | 2026-01-23 | 2026-01-29 | 2904 | 2906
4103 | 2906 | Future Task |  | RW-Communication |  | Jennifer Reeves | Create | Publish and Distribute - Quarterly Newsletter | 1 hr | 2 days | 2026-01-30 | 2026-02-02 | 2905