## Monthly Summary
Department of Financial Services
Florida PALM FY 2023 - 2024 Spend Plan Summary FYTD
As of October 31, 2023
| Annual |  |  |  |  | July 2023 |  |  |  | August 2023 |  |  |  | September 2023 |  |  |  | Q2 Baseline Adjustment | October 2023 |  |  |  | November 2023 |  |  | December 2023 |  |  | January 2024 |  |  | February 2024 |  |  | March 2024 |  |  | April 2024 |  |  | May 2024 |  |  | June 2024 |  |  | CF 2023-24 |  | Fiscal Year to Date
Category (Cost Area / Contract) | 0 | 0 | 0 | 43703549.6492 | 0 | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
| Appropriated | Released | Unreleased | Projected | Release Remaining
FLAIR System Replacement (100781) | 44440408 | 18867226 | 25573182 | 43703549.6492 | 8320162.8375 | 1318418.8608 | 1182932.44 |  | 429853.44 | 4873634.4258 | 4331673.82 |  | 851326.02 | 887276.8608 | 2405994.26 |  | 4269691.06 | 841270.3725 | 2754648.1192 | 2626462.6425 |  | 3076890.74 | 4851894.0525 | 0 | 0 | 3180346.4875 | 0 | 0 | 1456860.34 | 0 | 0 | 4466928.235 | 0 | 0 | 8004366.4875 | 0 | 0 | 4384636.4875 | 0 | 0 | 5342760.0875 | 0 | 0 | 1340508.8325 | 0 | 0 | 0 | 0 | 10675248.6392 | 10547063.1625 | 8627761.26 | 33156486.4867 | 75.87%
SSI Implementation Services (FP004) |  |  |  | 29745300 |  | 0 | 0 | 3 | 0 | 3415500 | 3415500 |  | 0 | 0 | 1500000 |  | 3415500 | 1500000 | 1448400 | 1448400 |  | 1500000 | 3415500 | 0 | 0 | 2310500 | 0 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 7024400 | 0 | 0 | 3250000 | 0 | 0 | 3965500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6363900 | 6363900 | 4915500 | 23381400 | 78.61%
Facilities and Maintenance (FP004) |  |  |  | 415692 |  | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 138564 | 138564 | 138564 | 277128 | 66.67%
Production Support (FP004) |  |  |  | 8771850 |  | 1068287 | 1034011 |  | 390692 | 664400 | 664400 |  | 643319 | 664400 | 664400 |  | 664400 | -34276 | 805457 | 785758 |  | 1450158 | 664400 | 0 | 0 | 664400 | 0 | 0 | 805457 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 811725 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 0 | 0 | 3168268 | 3148569 | 3148569 | 5623281 | 64.11%
Production Support Administration |  |  |  | 51800.04 |  | 2405.2 | 2384.34 |  | 2384.34 | 2405.2 | 0.1 | 2 | 0.1 | 2405.2 | 4768.8 | 3 | 4768.8 | -62.36 | 2405.2 | 2384.15 |  | 2384.15 | 7405.2 | 0 | 0 | 20405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 0 | 0 | 9558.44 | 9537.39 | 9537.39 | 42262.65 | 81.59%
Oracle Software and Maintenance (FP005) |  |  |  | 2145187.6092 |  | 9749.8308 | 0 | 2 | 0 | 597217.3958 | 0 | 2 | 0 | 9749.8308 | 0 | 2 | 0 | -616717.0575 | 321911.8525 | 321911.9025 |  | 0 | 597217.3958 | 0 | 0 | 9749.8308 | 0 | 0 | 331661.6833 | 0 | 0 | 77811.5783 | 0 | 0 | 9749.8308 | 0 | 0 | 9749.8308 | 0 | 0 | 399723.4308 | 0 | 0 | 387612.1758 | 0 | 0 | 0 | 0 | 321911.8525 | 321911.9025 | 0 | 1823275.7067 | 84.99%
Project Administration |  |  |  | 150000 |  | 63935.83 | 2136.1 | 2 | 2136.1 | 3910.83 | 70252.72 | 3 | 63605.92 | 40680.83 | 67224.46 | 2 | 73871.26 | 31085.79 | -38766.9333 | -115622.41 |  | -115622.41 | 4050.4567 | 0 | 0 | 5250.4567 | 0 | 0 | 14575.4567 | 0 | 0 | 4050.4567 | 0 | 0 | 9050.4567 | 0 | 0 | 4075.4567 | 0 | 0 | 4050.4567 | 0 | 0 | 4050.4567 | 0 | 0 | 0 | 0 | 100846.3467 | 23990.87 | 23990.87 | 126009.13 | 84.01%
ERP and OC Support Services |  |  |  | 1695720 |  | 139400 | 109760 | 1 | 0 | 155560 | 146880 | 1 | 109760 | 135400 | 134960 |  | 76510 | -38760 | 180600 | 148990 | 2 | 205330 | 128680 | 0 | 0 | 135400 | 0 | 0 | 142120 | 0 | 0 | 142120 | 0 | 0 | 142120 | 0 | 0 | 148840 | 0 | 0 | 148840 | 0 | 0 | 135400 | 0 | 0 | 0 | 0 | 572200 | 540590 | 391600 | 1155130 | 68.12%
QA Support Services |  |  |  | 728000 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 0 | 0 | 126000 | 0 | 0 | 117600 | 0 | 0 | 123200 | 0 | 0 | 123200 | 0 | 0 | 112000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728000 | 100%
IT Service Management Implementation and Software (100777) | 2000000 | 2000000 | 0 | 1738420 | 2000000 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998420 | 0 | 0 | 185000 | 0 | 0 | 185000 | 0 | 0 | 185000 | 0 | 0 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1738420 | 100%
ITSM Implementation |  |  |  | 925000 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 0 | 0 | 185000 | 0 | 0 | 185000 | 0 | 0 | 185000 | 0 | 0 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 925000 | 100%
ITSM Software |  |  |  | 813420 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813420 | 100%
Contingency (100819) | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DMS IV&V Transfer (100821) | 6053061 | 6053061 | 0 | 6053061 | 0 | 6053061 | 6053061 |  | 6053061 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6053061 | 6053061 | 6053061 | 0 | 0%
Salaries & Benefits (010000) | 9743087 | 9743087 | 0 | 8311423.97 | 7617071.97 | 754567.06 | 496925.61 |  | 496925.61 | 754567.06 | 530433.8 |  | 530433.8 | 754567.06 | 492961.02 |  | 492961.02 | -743380.75 | 754567.06 | 605694.6 |  | 81645.96 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 0 | 0 | 2274887.49 | 2126015.03 | 1601966.39 | 6185408.94 | 74.42%
Risk Management Insurance (103241) | 7978 | 7978 | 0 | 7978 | 0 | 6944 | 0 |  | 0 | 0 | 7978 |  | 7978 | 0 | 0 |  | 0 | 1034 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7978 | 7978 | 7978 | 0 | 0%
DMS HR Transfer (107040) | 24609 | 24609 | 0 | 23273 | 18456.75 | 5818.25 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -5818.25 | 11636.5 | 6152.25 |  | 6152.25 | 0 | 0 | 0 | 0 | 0 | 0 | 5818.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5818.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11636.5 | 6152.25 | 6152.25 | 17120.75 | 73.56%
Totals | 63769143 | 36695961 | 27073182 | 59837705.6192 | 17955691.5575 | 8138809.1708 | 7732919.05 |  | 6979840.05 | 5628201.4858 | 4870085.62 |  | 1389737.82 | 1641843.9208 | 2898955.28 |  | 4762652.08 | 93105.3725 | 3520851.6792 | 3238309.4925 |  | 3164688.95 | 5606461.1125 | 0 | 0 | 3934913.5475 | 0 | 0 | 2217245.65 | 0 | 0 | 6219915.295 | 0 | 0 | 8943933.5475 | 0 | 0 | 5330021.7975 | 0 | 0 | 6282327.1475 | 0 | 0 | 2280075.8925 | 0 | 0 | 0 | 0 | 19022811.6292 | 18740269.4425 | 16296918.9 | 41097436.1767 | 68.68%
Running Totals | [5 empty] | 8138809.1708 | 7732919.05 |  | 6979840.05 | 13767010.6567 | 12603004.67 |  | 8369577.87 | 15408854.5775 | 15501959.95 |  | 13132229.95 | 15501959.95 | 19022811.6292 | 18740269.4425 |  | 16296918.9 | 24629272.7417 | 18740269.4425 | 16296918.9 | 28564186.2892 | 18740269.4425 | 16296918.9 | 30781431.9392 | 18740269.4425 | 16296918.9 | 37001347.2342 | 18740269.4425 | 16296918.9 | 45945280.7817 | 18740269.4425 | 16296918.9 | 51275302.5792 | 18740269.4425 | 16296918.9 | 57557629.7267 | 18740269.4425 | 16296918.9 | 59837705.6192 | 18740269.4425 | 16296918.9 |  | 16296918.9 |  | Total Incurred/Total Projected FYTD | Total Incurred/Total Projected FYTD |  | 98.51%
Monthly Total Incurred/Total Projected | [5 empty] | 95.01% |  |  |  | 86.53% |  |  |  | 176.6% |  |  |  |  | 91.98% |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% | [5 empty] | Total Paid/Total Projected FYTD | Total Paid/Total Projected FYTD |  | 85.67%
Monthly Total Incurred/Total Projected (Variance) | [5 empty] | -4.987% |  |  |  | -13.47% |  |  |  | 76.57% |  |  |  |  | -8.025% |  |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [5 empty] | 95.01% |  |  |  | 91.54% |  |  |  | 100.6% |  |  |  |  | 98.51% |  |  |  | 76.09% |  |  | 65.61% |  |  | 60.88% |  |  | 50.65% |  |  | 40.79% |  |  | 36.55% |  |  | 32.56% |  |  | 31.32% | [5 empty] | Total Release/Total Appropriation | Total Release/Total Appropriation |  | 57.55%
FYTD Total Incurred/Total Projected (Variance) | [5 empty] | -4.987% |  |  |  | -8.455% |  |  |  | 0.6042% |  |  |  |  | -1.485% |  |  |  | -23.91% |  |  | -34.39% |  |  | -39.12% |  |  | -49.35% |  |  | -59.21% |  |  | -63.45% |  |  | -67.44% |  |  | -68.68%
[50 empty] | Total Paid/Total Release | Total Paid/Total Release |  | 44.41%
`
Note on BF11: Werner, Tommy: July

## SSI
|  |  | July 2023 |  |  | August 2023 |  |  | September 2023 |  |  |  | October 2023 |  |  | November 2023 |  |  | December 2023 |  |  | January 2024 |  |  | February 2024 |  |  | March 2024 |  |  | April 2024 |  |  | May 2024 |  |  | June 2024 |  |  | CF 2022-23
|  | Description | July Projection | July Accepted / Approved | July Paid | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid | Q2 Baseline Adjustment | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Q1 Projection | Total Projection
Department of Financial Services
Florida PALM FY 2023 - 2024 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
D636 | Completion of Solution Design (Requirements) Segment I | Implementation | 0 | 0 | 0 | 3415500 | 3415500 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 3415500
D637 | Completion of Solution Design (Requirements) Segment II | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500
D638 | Updated Data Conversion and Migration Strategy | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
D639 | Development of Standardized Business Process Models – Payroll | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448400 | 1448400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2896800
D640 | Development of the Master Data Configuration Workbooks | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310500
D641 | Completion of Solution Design (Requirements) Segment III | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500
D642 | Updated Technical Architecture Design | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3811500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3811500
D643 | Updated System Testing Plan | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3212900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3212900
D644 | Completion of Solution Design (Requirements) Segment IV | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500
D645 | Updated Deployment Strategy | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
D646 | Completion of Build Segment I | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000
D647 | Establish DW/BI Environments | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 103923 | 450333
Prod Supp | AM Services | Prod Supp | 537195 | 537195 | 0 | 554500 | 554500 | 537195 | 554500 | 554500 | 554500 | 0 | 554500 | 534801 | 1089301 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 0 | 0 | 1646195 | 7191195
Prod Supp | IM Services | Prod Supp | 106124 | 106124 | 0 | 109900 | 109900 | 106124 | 109900 | 109900 | 109900 | 0 | 109900 | 109900 | 219800 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 0 | 0 | 325924 | 1424924
Prod Supp | Oracle OCI Costs | Prod Supp | 141057 | 141057 | 141057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141057 | 141057 | 141057 | 0 | 0 | 0 | 0 | 0 | 0 | 141057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141057 | 711553
Prod Supp | Support Tools Maintenance | Prod Supp | 45030 | 45030 | 45030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45030 | 45030
Prod Supp | Support Tools Purchase | Prod Supp | 203556 | 169280 | 169280 | 0 | 0 | 0 | 0 | 0 | 0 | -34276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203556 | 169280
Prod Supp | Solution Software Support | Prod Supp | 35325 | 35325 | 35325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35325 | 35325
| Implementation Total: |  | 0 | 0 | 0 | 3415500 | 3415500 | 0 | 0 | 1500000 | 3415500 | 1500000 | 1448400 | 1448400 | 1500000 | 3415500 | 0 | 0 | 2310500 | 0 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 7024400 | 0 | 0 | 3250000 | 0 | 0 | 3965500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 31193700
| Production Support Facilities: |  | 34641 | 0 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 103923 | 450333
| Production Support (No Facilities) Total: |  | 1068287 | 1034011 | 0 | 664400 | 664400 | 643319 | 664400 | 664400 | 664400 | -34276 | 805457 | 785758 | 1450158 | 664400 | 0 | 0 | 664400 | 0 | 0 | 805457 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 811725 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 0 | 0 | 2397087 | 9577307
Monthly Totals |  |  | 1102928 | 1068652 | 425333 | 4114541 | 4114541 | 677960 | 699041 | 2199041 | 4114541 | 1465724 | 2288498 | 2268799 | 2984799 | 4114541 | 0 | 0 | 3009541 | 0 | 0 | 840098 | 0 | 0 | 4114541 | 0 | 0 | 7723441 | 0 | 0 | 4096366 | 0 | 0 | 4664541 | 0 | 0 | 699041 | 0 | 0 | 0 | 0 | 5916510 | 41221340
| Projected YTD |  | 1102928 |  |  | 5217469 |  |  | 5916510 |  |  | 7382234 | 9670732 |  |  | 13785273 |  |  | 16794814 |  |  | 17634912 |  |  | 21749453 |  |  | 29472894 |  |  | 33569260 |  |  | 38233801 |  |  | 38932842
| Incurred YTD |  |  | 1068652 |  |  | 5183193 |  |  | 7382234 |  |  |  | 9651033 |  |  | 9651033 |  |  | 9651033 |  |  | 9651033 |  |  | 9651033 |  |  | 9651033 |  |  | 9651033 |  |  | 9651033 |  |  | 9651033 |  | 9651033
| Paid YTD |  |  |  | 425333 |  |  | 1103293 |  |  | 5217834 |  |  |  | 8202633 |  |  | 8202633 |  |  | 8202633 |  |  | 8202633 |  |  | 8202633 |  |  | 8202633 |  |  | 8202633 |  |  | 8202633 |  |  | 8202633 |  | 8202633
0

## Oracle
Department of Financial Services
Florida PALM FY 2023 - 2024 Contractor Detail FYTD
| Annual |  |  | July 2023 |  |  |  | August 2023 |  |  |  | September 2023 |  |  |  | Q2 Baseline Adjustment | October 2023 |  |  |  | November 2023 |  |  |  | December 2023 |  |  |  | January 2024 |  |  |  | February 2024 |  |  |  | March 2024 |  |  |  | April 2024 |  |  |  | May 2024 |  |  |  | June 2024 | [5 empty] | Total
Program | Tech Support | Purchase | Total Projection | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  |  | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support | 1287647.41 | 0 | 1287647.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321911.8525 | 321911.9025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321911.8525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321911.8525 | 0 | 0 | 0 | 321911.8525 | 0 | 0 | 0 | 0 | 0 | 321911.8525 | 321911.9025 | 0
**Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 3401.27 |  | 3401.27 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 850.3175 | 850.3175 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 850.3175 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 850.3175 | 0 |  | 0 | 850.3175 | 0 |  | 0 | 0 | 0 | 850.3175 | 850.3175 | 0
Oracle Business Intelligence (Analytics) Server Administrator | 1450.58 |  | 1450.58 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 362.645 | 362.645 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 362.645 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 362.645 | 0 |  | 0 | 362.645 | 0 |  | 0 | 0 | 0 | 362.645 | 362.645 | 0
Oracle Business Intelligence Management Pack | 2876.25 |  | 2876.25 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 719.0625 | 719.0625 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 719.0625 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 719.0625 | 0 |  | 0 | 719.0625 | 0 |  | 0 | 0 | 0 | 719.0625 | 719.0625 | 0
Oracle Business Intelligence Suite Foundation Edition | 75048.11 |  | 75048.11 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 18762.0275 | 18762.0275 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 18762.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 18762.0275 | 0 |  | 0 | 18762.0275 | 0 |  | 0 | 0 | 0 | 18762.0275 | 18762.0275 | 0
Oracle Data Integrator Enterprise Edition | 37524.06 |  | 37524.06 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 9381.015 | 9381.015 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9381.015 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9381.015 | 0 |  | 0 | 9381.015 | 0 |  | 0 | 0 | 0 | 9381.015 | 9381.015 | 0
Oracle Data Visualization | 25016.72 |  | 25016.72 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 6254.18 | 6254.18 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6254.18 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6254.18 | 0 |  | 0 | 6254.18 | 0 |  | 0 | 0 | 0 | 6254.18 | 6254.18 | 0
*Oracle Financial Analytics Fusion Edition | 14509.91 |  | 14509.91 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3627.4775 | 3627.4775 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3627.4775 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3627.4775 | 0 |  | 0 | 3627.4775 | 0 |  | 0 | 0 | 0 | 3627.4775 | 3627.4775 | 0
Oracle Managed File Transfer | 20954.23 |  | 20954.23 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5238.5575 | 5238.5575 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5238.5575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5238.5575 | 0 |  | 0 | 5238.5575 | 0 |  | 0 | 0 | 0 | 5238.5575 | 5238.5575 | 0
Oracle Management Pack for Oracle Data Integrator | 6904.25 |  | 6904.25 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 1726.0625 | 1726.0625 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1726.0625 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1726.0625 | 0 |  | 0 | 1726.0625 | 0 |  | 0 | 0 | 0 | 1726.0625 | 1726.0625 | 0
Oracle SOA Management Pack Enterprise Edition | 20265.39 |  | 20265.39 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5066.3475 | 5066.3475 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5066.3475 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5066.3475 | 0 |  | 0 | 5066.3475 | 0 |  | 0 | 0 | 0 | 5066.3475 | 5066.3475 | 0
Oracle SOA Suite for Oracle Middleware | 46609.98 |  | 46609.98 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11652.495 | 11652.495 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11652.495 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11652.495 | 0 |  | 0 | 11652.495 | 0 |  | 0 | 0 | 0 | 11652.495 | 11652.495 | 0
Oracle WebLogic Server Management Pack Enterprise Edition | 18108.82 |  | 18108.82 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 4527.205 | 4527.205 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4527.205 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4527.205 | 0 |  | 0 | 4527.205 | 0 |  | 0 | 0 | 0 | 4527.205 | 4527.205 | 0
Oracle WebLogic Suite | 67908.63 |  | 67908.63 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 16977.1575 | 16977.1575 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 16977.1575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 16977.1575 | 0 |  | 0 | 16977.1575 | 0 |  | 0 | 0 | 0 | 16977.1575 | 16977.1575 | 0
*PeopleSoft Enterprise Contracts | 51822.24 |  | 51822.24 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 12955.56 | 12955.56 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12955.56 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12955.56 | 0 |  | 0 | 12955.56 | 0 |  | 0 | 0 | 0 | 12955.56 | 12955.56 | 0
*PeopleSoft Enterprise eSettlements | 34008.55 |  | 34008.55 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 8502.1375 | 8502.1375 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 8502.1375 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 8502.1375 | 0 |  | 0 | 8502.1375 | 0 |  | 0 | 0 | 0 | 8502.1375 | 8502.1375 | 0
*PeopleSoft Enterprise Expenses | 68825.48 |  | 68825.48 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 | 17206.37 | 17206.37 | 0
*PeopleSoft Enterprise Financials | 370847.94 |  | 370847.94 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 92711.985 | 92712.035 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 92711.985 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 92711.985 | 0 |  | 0 | 92711.985 | 0 |  | 0 | 0 | 0 | 92711.985 | 92712.035 | 0
*PeopleSoft Enterprise Grants | 48582.45 |  | 48582.45 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 12145.6125 | 12145.6125 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12145.6125 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12145.6125 | 0 |  | 0 | 12145.6125 | 0 |  | 0 | 0 | 0 | 12145.6125 | 12145.6125 | 0
*PeopleSoft Enterprise Human Resources | 46998.39 |  | 46998.39 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11749.5975 | 11749.5975 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11749.5975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11749.5975 | 0 |  | 0 | 11749.5975 | 0 |  | 0 | 0 | 0 | 11749.5975 | 11749.5975 | 0
*PeopleSoft Enterprise Payroll | 57159.76 |  | 57159.76 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14289.94 | 14289.94 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14289.94 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14289.94 | 0 |  | 0 | 14289.94 | 0 |  | 0 | 0 | 0 | 14289.94 | 14289.94 | 0
*PeopleSoft Enterprise Project Costing | 68825.48 |  | 68825.48 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 | 17206.37 | 17206.37 | 0
*PeopleSoft Enterprise Purchasing | 76113.47 |  | 76113.47 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 19028.3675 | 19028.3675 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19028.3675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19028.3675 | 0 |  | 0 | 19028.3675 | 0 |  | 0 | 0 | 0 | 19028.3675 | 19028.3675 | 0
*PeopleSoft Enterprise Supplier Contract Management | 68825.48 |  | 68825.48 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 | 17206.37 | 17206.37 | 0
*PeopleSoft Enterprise Treasury | 55059.97 |  | 55059.97 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13764.9925 | 13764.9925 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13764.9925 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13764.9925 | 0 |  | 0 | 13764.9925 | 0 |  | 0 | 0 | 0 | 13764.9925 | 13764.9925 | 0
Time and Labor Year 1 Support | 176803.62 | 0 | 176803.62 | 0 | 0 | 0 | 0 | 37782.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37782.975 | 0 | 0 | 0 | 0 | 37782.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37782.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37782.975 | 0 | 0 | 0 | 25671.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Time and Labor | 176803.62 |  | 176803.62 | 0 | 0 |  | 0 | 37782.975 | 0 |  | 0 | 0 | 0 |  | 0 | -37782.975 | 0 | 0 |  | 0 | 37782.975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 37782.975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 37782.975 | 0 |  | 0 | 25671.72 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
New License Purchase and Tech Support | 121115.09 | 666682.56 | 1297453.6367 | 9749.8308 | 0 | 0 | 0 | 559434.4208 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | -578934.0825 | 0 | 0 | 0 | 0 | 559434.4208 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 40028.6033 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 40028.6033 | 0 | 0 | 0 | 40028.6033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Financials | 29707.57 | 134665.46 | 291611.5975 | 0 | 0 |  | 0 | 134665.46 | 0 |  | 0 | 0 | 0 |  | 0 | -134665.46 | 0 | 0 |  | 0 | 134665.46 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 7426.8925 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 7426.8925 | 0 |  | 0 | 7426.8925 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Treasury | 4410.73 | 19994 | 43296.0475 | 0 | 0 |  | 0 | 19994 | 0 |  | 0 | 0 | 0 |  | 0 | -19994 | 0 | 0 |  | 0 | 19994 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1102.6825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1102.6825 | 0 |  | 0 | 1102.6825 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Expenses | 5513.41 | 24992.5 | 54120.0575 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | -24992.5 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise eSettlements | 2724.27 | 12349.23 | 26741.6625 | 0 | 0 |  | 0 | 12349.23 | 0 |  | 0 | 0 | 0 |  | 0 | -12349.23 | 0 | 0 |  | 0 | 12349.23 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 681.0675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 681.0675 | 0 |  | 0 | 681.0675 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Contracts | 4151.28 | 18817.88 | 40749.22 | 0 | 0 |  | 0 | 18817.88 | 0 |  | 0 | 0 | 0 |  | 0 | -18817.88 | 0 | 0 |  | 0 | 18817.88 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1037.82 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1037.82 | 0 |  | 0 | 1037.82 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Grants | 3891.82 | 17641.76 | 38202.385 | 0 | 0 |  | 0 | 17641.76 | 0 |  | 0 | 0 | 0 |  | 0 | -17641.76 | 0 | 0 |  | 0 | 17641.76 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 972.955 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 972.955 | 0 |  | 0 | 972.955 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Project Costing | 5513.41 | 24992.5 | 54120.0575 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | -24992.5 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Supplier Contract Management | 5513.41 | 24992.5 | 54120.0575 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | -24992.5 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Purchasing | 6097.19 | 27638.76 | 59850.4125 | 0 | 0 |  | 0 | 27638.76 | 0 |  | 0 | 0 | 0 |  | 0 | -27638.76 | 0 | 0 |  | 0 | 27638.76 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1524.2975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1524.2975 | 0 |  | 0 | 1524.2975 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
HR Analytics | 44660 | 203000 | 439495 | 0 | 0 |  | 0 | 203000 | 0 |  | 0 | 0 | 0 |  | 0 | -203000 | 0 | 0 |  | 0 | 203000 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11165 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11165 | 0 |  | 0 | 11165 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Project Analytics | 8932 | 40600 | 87899 | 0 | 0 |  | 0 | 40600 | 0 |  | 0 | 0 | 0 |  | 0 | -40600 | 0 | 0 |  | 0 | 40600 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2233 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2233 | 0 |  | 0 | 2233 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle Autonomous Cloud (OAC) Dev | 0 | 53218.69 | 48783.7992 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | -13304.6725 | 0 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle Autonomous Cloud (OAC) Test | 0 | 63779.28 | 58464.34 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | -15944.82 | 0 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total | 1585566.12 | 666682.56 | 2761904.6667 | 9749.8308 | 0 | 0 | 0 | 597217.3958 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | -616717.0575 | 321911.8525 | 321911.9025 | 0 | 0 | 597217.3958 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 331661.6833 | 0 | 0 | 0 | 77811.5783 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 399723.4308 | 0 | 0 | 0 | 387612.1758 | 0 | 0 | 0 | 0 | 0 | 321911.8525 | 321911.9025 | 0
Projected FYTD |  |  |  | 9749.8308 |  |  |  | 606967.2267 |  |  |  | 616717.0575 |  |  |  | 0 | 321911.8525 |  |  |  | 919129.2483 |  |  |  | 928879.0792 |  |  |  | 1260540.7625 |  |  |  | 1338352.3408 |  |  |  | 1348102.1717 |  |  |  | 1357852.0025 |  |  |  | 1757575.4333 |  |  |  | 2145187.6092
Incurred FYTD |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 321911.9025 |  |  |  | 321911.9025 |  |  |  | 321911.9025 |  |  |  | 321911.9025 |  |  |  | 321911.9025 |  |  |  | 321911.9025 |  |  |  | 321911.9025 |  |  |  | 321911.9025 |  |  |  | 321911.9025
Paid FYTD | [6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
0

## Footnotes
Department of Financial Services
FY 2023 - 2024 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5
6