## Monthly Summary
Department of Financial Services
Florida PALM FY 2023 - 2024 Spend Plan Summary FYTD
As of December 31, 2023
| Annual |  |  |  |  | July 2023 |  |  |  | August 2023 |  |  |  | September 2023 |  |  |  | Q2 Baseline Adjustment | October 2023 |  |  |  | November 2023 |  |  |  | December 2023 |  |  |  | Q2 Baseline Adjustment | January 2024 |  |  | February 2024 |  |  | March 2024 |  |  | April 2024 |  |  | May 2024 |  |  | June 2024 |  |  | CF 2023-24 |  | Fiscal Year to Date
Category (Cost Area / Contract) | 0 | 0 | 0 | 43474709.6025 | 0 | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
| Appropriated | Released | Unreleased | Projected | Release Remaining
FLAIR System Replacement (100781) | 44440408 | 18867226 | 25573182 | 43474709.6025 | 376994.3075 | 1318418.8608 | 1182932.44 |  | 429853.44 | 4873634.4258 | 4331673.82 |  | 851326.02 | 887276.8608 | 2405994.26 |  | 4269691.06 | 841270.3725 | 2754648.1225 | 2626462.6425 |  | 3076890.74 | 4851894.0525 | 4567898.11 |  | 1583128.9 | 3180346.4875 | 3375270.42 |  | 4213918.64 | -217257.49 | 1511321.795 | 0 | 0 | 4345626.64 | 0 | 0 | 8018696.8825 | 0 | 0 | 4398134.8825 | 0 | 0 | 5356258.4825 | 0 | 0 | 1354439.2275 | 0 | 0 | 0 | 0 | 18707489.1825 | 18490231.6925 | 14424808.8 | 24984477.91 | 57.47%
SSI Implementation Services (FP004) |  |  |  | 29745300 |  | 0 | 0 | 3 | 0 | 3415500 | 3415500 |  | 0 | 0 | 1500000 |  | 3415500 | 1500000 | 1448400 | 1448400 |  | 1500000 | 3415500 | 3415500 |  | 1448400 | 2310500 | 2310500 |  | 3415500 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 7024400 | 0 | 0 | 3250000 | 0 | 0 | 3965500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12089900 | 12089900 | 9779400 | 17655400 | 59.36%
Facilities and Maintenance (FP004) |  |  |  | 415692 |  | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 207846 | 207846 | 207846 | 207846 | 50%
Production Support (FP004) |  |  |  | 8752151 |  | 1068287 | 1034011 |  | 390692 | 664400 | 664400 |  | 643319 | 664400 | 664400 |  | 664400 | -34276 | 805457 | 785758 |  | 1450158 | 664400 | 664400 |  | 0 | 664400 | 664400 |  | 664400 | -19699 | 805457 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 811725 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 0 | 0 | 4497068 | 4477369 | 3812969 | 4274782 | 48.84%
Production Support Administration |  |  |  | 47969.54 |  | 2405.2 | 2384.34 |  | 2384.34 | 2405.2 | 0.1 | 2 | 0.1 | 2405.2 | 4768.8 | 3 | 4768.8 | -62.36 | 2405.2 | 2384.15 |  | 2384.15 | 7405.2 | 2383.44 | 2 | 0.18 | 20405.2 | 2284.07 | 2 | 2383.44 | -23163.94 | 21738.64 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 0 | 0 | 37368.84 | 14204.9 | 11921.01 | 33764.64 | 70.39%
Oracle Software and Maintenance (FP005) |  |  |  | 2148812.0625 |  | 9749.8308 | 0 | 2 | 0 | 597217.3958 | 0 | 2 | 0 | 9749.8308 | 0 | 2 | 0 | -616717.0575 | 321911.8525 | 321911.9025 |  | 0 | 597217.3958 | 343867.57 | 2 | 0 | 9749.8308 | 241860 | 3 | 37782.98 | -21239.6067 | 354061.7333 | 0 | 0 | 77811.5883 | 0 | 0 | 10981.8308 | 0 | 0 | 9749.8308 | 0 | 0 | 399723.4308 | 0 | 0 | 388844.1758 | 0 | 0 | 0 | 0 | 928879.0792 | 907639.4725 | 37782.98 | 1241172.59 | 57.76%
Project Administration |  |  |  | 150000 |  | 63935.83 | 2136.1 | 2 | 2136.1 | 3910.83 | 70252.72 | 3 | 63605.92 | 40680.83 | 67224.46 | 2 | 73871.26 | 31085.79 | -38766.93 | -115622.41 |  | -115622.41 | 4050.4567 | 116.1 | 2 | 97.72 | 5250.4567 | 10370.35 | 3 | 10211.22 | -75669.9433 | 66753.4217 | 0 | 0 | 8748.8517 | 0 | 0 | 13748.8517 | 0 | 0 | 8773.8517 | 0 | 0 | 8748.8517 | 0 | 0 | 8748.8517 | 0 | 0 | 0 | 0 | 110147.2633 | 34477.32 | 34299.81 | 115522.68 | 77.02%
ERP and OC Support Services |  |  |  | 1704785 |  | 139400 | 109760 | 1 | 0 | 155560 | 146880 | 1 | 109760 | 135400 | 134960 |  | 76510 | -38760 | 180600 | 148990 | 2 | 205330 | 128680 | 106990 | 1 | 99990 | 135400 | 111215 |  | 49000 | -77485 | 228670 | 0 | 0 | 142120 | 0 | 0 | 142120 | 0 | 0 | 148840 | 0 | 0 | 148840 | 0 | 0 | 135400 | 0 | 0 | 0 | 0 | 836280 | 758795 | 540590 | 945990 | 55.49%
QA Support Services |  |  |  | 510000 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 0 | 0 | 132000 | 0 | 0 | 132000 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 100%
IT Service Management Implementation and Software (100777) | 2000000 | 2000000 | 0 | 995670.41 | 2000000 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13147.67 | 0 | 0 | 813420 | 0 | 0 | 27887 | 0 | 0 | 58328.52 | 0 | 0 | 54812.26 | 0 | 0 | 28074.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 995670.41 | 100%
ITSM Implementation |  |  |  | 182250.41 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13147.67 | 0 | 0 | 0 | 0 | 0 | 27887 | 0 | 0 | 58328.52 | 0 | 0 | 54812.26 | 0 | 0 | 28074.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182250.41 | 100%
ITSM Software |  |  |  | 813420 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 813420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813420 | 100%
Contingency (100819) | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DMS IV&V Transfer (100821) | 6053061 | 6053061 | 0 | 6053061 | 0 | 6053061 | 6053061 |  | 6053061 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6053061 | 6053061 | 6053061 | 0 | 0%
Salaries & Benefits (010000) | 9743087 | 9743087 | 0 | 7709314.66 | 6561174.7 | 754567.06 | 496925.61 |  | 496925.61 | 754567.06 | 530433.8 |  | 530433.8 | 754567.06 | 492961.02 |  | 492961.02 | -743380.75 | 754567.06 | 605694.6 |  | 81645.96 | 754567.06 | 510087.05 |  | 1034135.69 | 754567.06 | 545810.22 |  | 545810.22 | -602109.31 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 0 | 0 | 3784021.61 | 3181912.3 | 3181912.3 | 4527402.36 | 58.73%
Risk Management Insurance (103241) | 7978 | 7978 | 0 | 7978 | 0 | 6944 | 0 |  | 0 | 0 | 7978 |  | 7978 | 0 | 0 |  | 0 | 1034 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7978 | 7978 | 7978 | 0 | 0%
DMS HR Transfer (107040) | 24609 | 24609 | 0 | 24609 | 18456.75 | 5818.25 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -5818.25 | 11636.5 | 6152.25 |  | 6152.25 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -5484.25 | 6152.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6152.25 | 0 | 0 | 0 | 0 | 0 | 6152.25 | 0 | 0 | 0 | 0 | 11636.5 | 6152.25 | 6152.25 | 18456.75 | 75%
Totals | 63769143 | 36695961 | 27073182 | 58265342.6725 | 8956625.7575 | 8138809.1708 | 7732919.05 |  | 6979840.05 | 5628201.4858 | 4870085.62 |  | 1389737.82 | 1641843.9208 | 2898955.28 |  | 4762652.08 | 93105.3725 | 3520851.6825 | 3238309.4925 |  | 3164688.95 | 5606461.1125 | 5077985.16 |  | 2617264.59 | 3934913.5475 | 3921080.64 |  | 4759728.86 | -824851.05 | 2285188.775 | 0 | 0 | 5913613.7 | 0 | 0 | 8801150.9425 | 0 | 0 | 5217182.7125 | 0 | 0 | 6165637.8025 | 0 | 0 | 2143233.4975 | 0 | 0 | 0 | 0 | 28564186.2925 | 27739335.2425 | 23673912.35 | 30526007.43 | 52.39%
Running Totals | [5 empty] | 8138809.1708 | 7732919.05 |  | 6979840.05 | 13767010.6567 | 12603004.67 |  | 8369577.87 | 15408854.5775 | 15501959.95 |  | 13132229.95 | 15501959.95 | 19022811.6325 | 18740269.4425 |  | 16296918.9 | 24629272.745 | 23818254.6025 |  | 18914183.49 | 28564186.2925 | 27739335.2425 |  | 23673912.35 | 27739335.2425 | 30849375.0675 | 27739335.2425 | 23673912.35 | 36762988.7675 | 27739335.2425 | 23673912.35 | 45564139.71 | 27739335.2425 | 23673912.35 | 50781322.4225 | 27739335.2425 | 23673912.35 | 56946960.225 | 27739335.2425 | 23673912.35 | 59090193.7225 | 27739335.2425 | 23673912.35 |  | 23673912.35 |  | Total Incurred/Total Projected FYTD | Total Incurred/Total Projected FYTD |  | 97.11%
Monthly Total Incurred/Total Projected | [5 empty] | 95.01% |  |  |  | 86.53% |  |  |  | 176.6% |  |  |  |  | 91.98% |  |  |  | 90.57% |  |  |  | 99.65% |  |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% | [5 empty] | Total Paid/Total Projected FYTD | Total Paid/Total Projected FYTD |  | 82.88%
Monthly Total Incurred/Total Projected (Variance) | [5 empty] | -4.987% |  |  |  | -13.47% |  |  |  | 76.57% |  |  |  |  | -8.025% |  |  |  | -9.426% |  |  |  | -0.3515% |  |  |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [5 empty] | 95.01% |  |  |  | 91.54% |  |  |  | 100.6% |  |  |  |  | 98.51% |  |  |  | 96.71% |  |  |  | 97.11% |  |  |  |  | 89.92% |  |  | 75.45% |  |  | 60.88% |  |  | 54.63% |  |  | 48.71% |  |  | 46.94% | [5 empty] | Total Release/Total Appropriation | Total Release/Total Appropriation |  | 57.55%
FYTD Total Incurred/Total Projected (Variance) | [5 empty] | -4.987% |  |  |  | -8.455% |  |  |  | 0.6042% |  |  |  |  | -1.485% |  |  |  | -3.293% |  |  |  | -2.888% |  |  |  |  | -10.08% |  |  | -24.55% |  |  | -39.12% |  |  | -45.37% |  |  | -51.29% |  |  | -53.06%
[53 empty] | Total Paid/Total Release | Total Paid/Total Release |  | 64.51%
`
Note on BG11: Werner, Tommy: July

## SSI
|  |  | July 2023 |  |  | August 2023 |  |  | September 2023 |  |  |  | October 2023 |  |  | November 2023 |  |  | December 2023 |  |  |  | January 2024 |  |  | February 2024 |  |  | March 2024 |  |  | April 2024 |  |  | May 2024 |  |  | June 2024 |  |  | CF 2022-23
|  | Description | July Projection | July Accepted / Approved | July Paid | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid | Q2 Baseline Adjustment | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid | Q2 Baseline Adjustment | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Q1 Projection | Total Projection
Department of Financial Services
Florida PALM FY 2023 - 2024 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
D636 | Completion of Solution Design (Requirements) Segment I | Implementation | 0 | 0 | 0 | 3415500 | 3415500 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 3415500
D637 | Completion of Solution Design (Requirements) Segment II | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 3415500 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500
D638 | Updated Data Conversion and Migration Strategy | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
D639 | Development of Standardized Business Process Models – Payroll | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448400 | 1448400 | 0 | 0 | 0 | 1448400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448400
D640 | Development of the Master Data Configuration Workbooks | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310500 | 2310500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310500
D641 | Completion of Solution Design (Requirements) Segment III | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500
D642 | Updated Technical Architecture Design | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3811500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3811500
D643 | Updated System Testing Plan | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3212900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3212900
D644 | Completion of Solution Design (Requirements) Segment IV | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500
D645 | Updated Deployment Strategy | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
D646 | Completion of Build Segment I | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000
D647 | Establish DW/BI Environments | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 103923 | 415692
Prod Supp | AM Services | Prod Supp | 537195 | 537195 | 0 | 554500 | 554500 | 537195 | 554500 | 554500 | 554500 | 0 | 554500 | 534801 | 1089301 | 554500 | 554500 | 0 | 554500 | 554500 | 554500 | -19699 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 0 | 0 | 1646195 | 6616996
Prod Supp | IM Services | Prod Supp | 106124 | 106124 | 0 | 109900 | 109900 | 106124 | 109900 | 109900 | 109900 | 0 | 109900 | 109900 | 219800 | 109900 | 109900 | 0 | 109900 | 109900 | 109900 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 0 | 0 | 325924 | 1315024
Prod Supp | Oracle OCI Costs | Prod Supp | 141057 | 141057 | 141057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141057 | 141057 | 141057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141057 | 570496
Prod Supp | Support Tools Maintenance | Prod Supp | 45030 | 45030 | 45030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45030 | 45030
Prod Supp | Support Tools Purchase | Prod Supp | 203556 | 169280 | 169280 | 0 | 0 | 0 | 0 | 0 | 0 | -34276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203556 | 169280
Prod Supp | Solution Software Support | Prod Supp | 35325 | 35325 | 35325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35325 | 35325
| Implementation Total: |  | 0 | 0 | 0 | 3415500 | 3415500 | 0 | 0 | 1500000 | 3415500 | 1500000 | 1448400 | 1448400 | 1500000 | 3415500 | 3415500 | 1448400 | 2310500 | 2310500 | 3415500 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 7024400 | 0 | 0 | 3250000 | 0 | 0 | 3965500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 29745300
| Production Support Facilities: |  | 34641 | 0 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 103923 | 415692
| Production Support (No Facilities) Total: |  | 1068287 | 1034011 | 0 | 664400 | 664400 | 643319 | 664400 | 664400 | 664400 | -34276 | 805457 | 785758 | 1450158 | 664400 | 664400 | 0 | 664400 | 664400 | 664400 | -19699 | 805457 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 811725 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 0 | 0 | 2397087 | 8752151
Monthly Totals |  |  | 1102928 | 1068652 | 425333 | 4114541 | 4114541 | 677960 | 699041 | 2199041 | 4114541 | 1465724 | 2288498 | 2268799 | 2984799 | 4114541 | 4114541 | 1483041 | 3009541 | 3009541 | 4114541 | -19699 | 840098 | 0 | 0 | 4114541 | 0 | 0 | 7723441 | 0 | 0 | 4096366 | 0 | 0 | 4664541 | 0 | 0 | 699041 | 0 | 0 | 0 | 0 | 5916510 | 38913143
| Projected YTD |  | 1102928 |  |  | 5217469 |  |  | 5916510 |  |  | 7382234 | 9670732 |  |  | 13785273 |  |  | 16794814 |  |  | 16775115 | 17615213 |  |  | 21729754 |  |  | 29453195 |  |  | 33549561 |  |  | 38214102 |  |  | 38913143
| Incurred YTD |  |  | 1068652 |  |  | 5183193 |  |  | 7382234 |  |  |  | 9651033 |  |  | 13765574 |  |  | 16775115 |  |  |  | 16775115 |  |  | 16775115 |  |  | 16775115 |  |  | 16775115 |  |  | 16775115 |  |  | 16775115 |  | 16775115
| Paid YTD |  |  |  | 425333 |  |  | 1103293 |  |  | 5217834 |  |  |  | 8202633 |  |  | 9685674 |  |  | 13800215 |  |  |  | 13800215 |  |  | 13800215 |  |  | 13800215 |  |  | 13800215 |  |  | 13800215 |  |  | 13800215 |  | 13800215
0

## Oracle
Department of Financial Services
Florida PALM FY 2023 - 2024 Contractor Detail FYTD
| Annual |  |  | July 2023 |  |  |  | August 2023 |  |  |  | September 2023 |  |  |  | Q2 Baseline Adjustment | October 2023 |  |  |  | November 2023 |  |  |  | December 2023 |  |  |  | Q2 Baseline Adjustment | January 2024 |  |  |  | February 2024 |  |  |  | March 2024 |  |  |  | April 2024 |  |  |  | May 2024 |  |  |  | June 2024 | [5 empty] | Total
Program | Tech Support | Purchase | Total Projection | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  |  | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support | 1287647.41 | 0 | 1287647.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321911.8525 | 321911.9025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 321911.9025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321911.8525 | 0 | 0 | 0 | 321911.8525 | 0 | 0 | 0 | 0 | 0 | 321911.8525 | 321911.9025 | 0
**Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 3401.27 |  | 3401.27 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 850.3175 | 850.3175 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 850.3175 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 850.3175 | 0 |  | 0 | 850.3175 | 0 |  | 0 | 0 | 0 | 850.3175 | 850.3175 | 0
Oracle Business Intelligence (Analytics) Server Administrator | 1450.58 |  | 1450.58 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 362.645 | 362.645 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 362.645 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 362.645 | 0 |  | 0 | 362.645 | 0 |  | 0 | 0 | 0 | 362.645 | 362.645 | 0
Oracle Business Intelligence Management Pack | 2876.25 |  | 2876.25 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 719.0625 | 719.0625 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 719.0625 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 719.0625 | 0 |  | 0 | 719.0625 | 0 |  | 0 | 0 | 0 | 719.0625 | 719.0625 | 0
Oracle Business Intelligence Suite Foundation Edition | 75048.11 |  | 75048.11 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 18762.0275 | 18762.0275 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 18762.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 18762.0275 | 0 |  | 0 | 18762.0275 | 0 |  | 0 | 0 | 0 | 18762.0275 | 18762.0275 | 0
Oracle Data Integrator Enterprise Edition | 37524.06 |  | 37524.06 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 9381.015 | 9381.015 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 9381.015 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9381.015 | 0 |  | 0 | 9381.015 | 0 |  | 0 | 0 | 0 | 9381.015 | 9381.015 | 0
Oracle Data Visualization | 25016.72 |  | 25016.72 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 6254.18 | 6254.18 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 6254.18 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6254.18 | 0 |  | 0 | 6254.18 | 0 |  | 0 | 0 | 0 | 6254.18 | 6254.18 | 0
*Oracle Financial Analytics Fusion Edition | 14509.91 |  | 14509.91 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3627.4775 | 3627.4775 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3627.4775 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3627.4775 | 0 |  | 0 | 3627.4775 | 0 |  | 0 | 0 | 0 | 3627.4775 | 3627.4775 | 0
Oracle Managed File Transfer | 20954.23 |  | 20954.23 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5238.5575 | 5238.5575 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5238.5575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5238.5575 | 0 |  | 0 | 5238.5575 | 0 |  | 0 | 0 | 0 | 5238.5575 | 5238.5575 | 0
Oracle Management Pack for Oracle Data Integrator | 6904.25 |  | 6904.25 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 1726.0625 | 1726.0625 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 1726.0625 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1726.0625 | 0 |  | 0 | 1726.0625 | 0 |  | 0 | 0 | 0 | 1726.0625 | 1726.0625 | 0
Oracle SOA Management Pack Enterprise Edition | 20265.39 |  | 20265.39 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5066.3475 | 5066.3475 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5066.3475 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5066.3475 | 0 |  | 0 | 5066.3475 | 0 |  | 0 | 0 | 0 | 5066.3475 | 5066.3475 | 0
Oracle SOA Suite for Oracle Middleware | 46609.98 |  | 46609.98 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11652.495 | 11652.495 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11652.495 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11652.495 | 0 |  | 0 | 11652.495 | 0 |  | 0 | 0 | 0 | 11652.495 | 11652.495 | 0
Oracle WebLogic Server Management Pack Enterprise Edition | 18108.82 |  | 18108.82 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 4527.205 | 4527.205 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 4527.205 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4527.205 | 0 |  | 0 | 4527.205 | 0 |  | 0 | 0 | 0 | 4527.205 | 4527.205 | 0
Oracle WebLogic Suite | 67908.63 |  | 67908.63 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 16977.1575 | 16977.1575 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 16977.1575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 16977.1575 | 0 |  | 0 | 16977.1575 | 0 |  | 0 | 0 | 0 | 16977.1575 | 16977.1575 | 0
*PeopleSoft Enterprise Contracts | 51822.24 |  | 51822.24 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 12955.56 | 12955.56 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 12955.56 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12955.56 | 0 |  | 0 | 12955.56 | 0 |  | 0 | 0 | 0 | 12955.56 | 12955.56 | 0
*PeopleSoft Enterprise eSettlements | 34008.55 |  | 34008.55 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 8502.1375 | 8502.1375 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 8502.1375 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 8502.1375 | 0 |  | 0 | 8502.1375 | 0 |  | 0 | 0 | 0 | 8502.1375 | 8502.1375 | 0
*PeopleSoft Enterprise Expenses | 68825.48 |  | 68825.48 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 | 17206.37 | 17206.37 | 0
*PeopleSoft Enterprise Financials | 370847.94 |  | 370847.99 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 92711.985 | 92712.035 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.05 | 92712.035 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 92711.985 | 0 |  | 0 | 92711.985 | 0 |  | 0 | 0 | 0 | 92711.985 | 92712.035 | 0
*PeopleSoft Enterprise Grants | 48582.45 |  | 48582.45 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 12145.6125 | 12145.6125 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 12145.6125 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12145.6125 | 0 |  | 0 | 12145.6125 | 0 |  | 0 | 0 | 0 | 12145.6125 | 12145.6125 | 0
*PeopleSoft Enterprise Human Resources | 46998.39 |  | 46998.39 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11749.5975 | 11749.5975 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11749.5975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11749.5975 | 0 |  | 0 | 11749.5975 | 0 |  | 0 | 0 | 0 | 11749.5975 | 11749.5975 | 0
*PeopleSoft Enterprise Payroll | 57159.76 |  | 57159.76 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14289.94 | 14289.94 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14289.94 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14289.94 | 0 |  | 0 | 14289.94 | 0 |  | 0 | 0 | 0 | 14289.94 | 14289.94 | 0
*PeopleSoft Enterprise Project Costing | 68825.48 |  | 68825.48 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 | 17206.37 | 17206.37 | 0
*PeopleSoft Enterprise Purchasing | 76113.47 |  | 76113.47 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 19028.3675 | 19028.3675 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 19028.3675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19028.3675 | 0 |  | 0 | 19028.3675 | 0 |  | 0 | 0 | 0 | 19028.3675 | 19028.3675 | 0
*PeopleSoft Enterprise Supplier Contract Management | 68825.48 |  | 68825.48 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 | 17206.37 | 17206.37 | 0
*PeopleSoft Enterprise Treasury | 55059.97 |  | 55059.97 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13764.9925 | 13764.9925 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13764.9925 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13764.9925 | 0 |  | 0 | 13764.9925 | 0 |  | 0 | 0 | 0 | 13764.9925 | 13764.9925 | 0
Time and Labor Year 1 Support | 176803.62 | 0 | 176803.63 | 0 | 0 | 0 | 0 | 37782.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37782.975 | 0 | 0 | 0 | 0 | 37782.975 | 37782.98 | 0 | 0 | 0 | 0 | 0 | 37782.98 | 0.01 | 0 | 0 | 0 | 0 | 37782.985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37782.975 | 0 | 0 | 0 | 25671.72 | 0 | 0 | 0 | 0 | 0 | 37782.975 | 37782.98 | 0
*PeopleSoft Enterprise Time and Labor | 176803.62 |  | 176803.63 | 0 | 0 |  | 0 | 37782.975 | 0 |  | 0 | 0 | 0 |  | 0 | -37782.975 | 0 | 0 |  | 0 | 37782.975 | 37782.98 |  | 0 | 0 | 0 |  | 37782.98 | 0.01 | 0 | 0 |  | 0 | 37782.985 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 37782.975 | 0 |  | 0 | 25671.72 | 0 |  | 0 | 0 | 0 | 37782.975 | 37782.98 | 0
New License Purchase and Tech Support | 123579.09 | 689082.56 | 1322317.6367 | 9749.8308 | 0 | 0 | 0 | 559434.4208 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | -578934.0825 | 0 | 0 | 0 | 0 | 559434.4208 | 306084.59 | 0 | 0 | 9749.8308 | 241860 | 0 | 0 | -21239.6617 | 32149.8308 | 0 | 0 | 0 | 40028.6033 | 0 | 0 | 0 | 10981.8308 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 40028.6033 | 0 | 0 | 0 | 41260.6033 | 0 | 0 | 0 | 0 | 0 | 569184.2517 | 547944.59 | 0
*PeopleSoft Enterprise Financials | 29707.57 | 134665.46 | 291611.5975 | 0 | 0 |  | 0 | 134665.46 | 0 |  | 0 | 0 | 0 |  | 0 | -134665.46 | 0 | 0 |  | 0 | 134665.46 | 134665.46 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 7426.8925 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 7426.8925 | 0 |  | 0 | 7426.8925 | 0 |  | 0 | 0 | 0 | 134665.46 | 134665.46 | 0
*PeopleSoft Enterprise Treasury | 4410.73 | 19994 | 43296.0475 | 0 | 0 |  | 0 | 19994 | 0 |  | 0 | 0 | 0 |  | 0 | -19994 | 0 | 0 |  | 0 | 19994 | 19994 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1102.6825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1102.6825 | 0 |  | 0 | 1102.6825 | 0 |  | 0 | 0 | 0 | 19994 | 19994 | 0
*PeopleSoft Enterprise Expenses | 5513.41 | 24992.5 | 54120.0575 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | -24992.5 | 0 | 0 |  | 0 | 24992.5 | 24992.5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 | 24992.5 | 24992.5 | 0
*PeopleSoft Enterprise eSettlements | 2724.27 | 12349.23 | 26741.6625 | 0 | 0 |  | 0 | 12349.23 | 0 |  | 0 | 0 | 0 |  | 0 | -12349.23 | 0 | 0 |  | 0 | 12349.23 | 12349.23 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 681.0675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 681.0675 | 0 |  | 0 | 681.0675 | 0 |  | 0 | 0 | 0 | 12349.23 | 12349.23 | 0
*PeopleSoft Enterprise Contracts | 4151.28 | 18817.88 | 40749.22 | 0 | 0 |  | 0 | 18817.88 | 0 |  | 0 | 0 | 0 |  | 0 | -18817.88 | 0 | 0 |  | 0 | 18817.88 | 18817.88 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1037.82 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1037.82 | 0 |  | 0 | 1037.82 | 0 |  | 0 | 0 | 0 | 18817.88 | 18817.88 | 0
*PeopleSoft Enterprise Grants | 3891.82 | 17641.76 | 38202.385 | 0 | 0 |  | 0 | 17641.76 | 0 |  | 0 | 0 | 0 |  | 0 | -17641.76 | 0 | 0 |  | 0 | 17641.76 | 17641.76 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 972.955 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 972.955 | 0 |  | 0 | 972.955 | 0 |  | 0 | 0 | 0 | 17641.76 | 17641.76 | 0
*PeopleSoft Enterprise Project Costing | 5513.41 | 24992.5 | 54120.0575 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | -24992.5 | 0 | 0 |  | 0 | 24992.5 | 24992.5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 | 24992.5 | 24992.5 | 0
*PeopleSoft Enterprise Supplier Contract Management | 5513.41 | 24992.5 | 54120.0575 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | -24992.5 | 0 | 0 |  | 0 | 24992.5 | 24992.5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 | 24992.5 | 24992.5 | 0
*PeopleSoft Enterprise Purchasing | 6097.19 | 27638.76 | 59850.4125 | 0 | 0 |  | 0 | 27638.76 | 0 |  | 0 | 0 | 0 |  | 0 | -27638.76 | 0 | 0 |  | 0 | 27638.76 | 27638.76 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1524.2975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1524.2975 | 0 |  | 0 | 1524.2975 | 0 |  | 0 | 0 | 0 | 27638.76 | 27638.76 | 0
HR Analytics | 44660 | 203000 | 439495 | 0 | 0 |  | 0 | 203000 | 0 |  | 0 | 0 | 0 |  | 0 | -203000 | 0 | 0 |  | 0 | 203000 | 0 |  | 0 | 0 | 201550 |  | 0 | -1450 | 0 | 0 |  | 0 | 11165 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11165 | 0 |  | 0 | 11165 | 0 |  | 0 | 0 | 0 | 203000 | 201550 | 0
Project Analytics | 8932 | 40600 | 87899 | 0 | 0 |  | 0 | 40600 | 0 |  | 0 | 0 | 0 |  | 0 | -40600 | 0 | 0 |  | 0 | 40600 | 0 |  | 0 | 0 | 40310 |  | 0 | -290 | 0 | 0 |  | 0 | 2233 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2233 | 0 |  | 0 | 2233 | 0 |  | 0 | 0 | 0 | 40600 | 40310 | 0
COBOL | 2464 | 22400 | 24864 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 22400 | 0 |  | 0 | 0 | 0 |  | 0 | 1232 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1232 | 0 |  | 0 | 0 | 0 | 0
Oracle Autonomous Cloud (OAC) Dev | 0 | 53218.69 | 48783.7992 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | -13304.6725 | 0 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | -8869.7817 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 0 | 0 | 8869.7817 | 0 | 0
Oracle Autonomous Cloud (OAC) Test | 0 | 63779.28 | 58464.34 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | -15944.82 | 0 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | -10629.88 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 0 | 0 | 10629.88 | 0 | 0
Total | 1588030.12 | 689082.56 | 2786768.7267 | 9749.8308 | 0 | 0 | 0 | 597217.3958 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | -616717.0575 | 321911.8525 | 321911.9025 | 0 | 0 | 597217.3958 | 343867.57 | 0 | 0 | 9749.8308 | 241860 | 0 | 37782.98 | -21239.6017 | 354061.7333 | 0 | 0 | 0 | 77811.5883 | 0 | 0 | 0 | 10981.8308 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 399723.4308 | 0 | 0 | 0 | 388844.1758 | 0 | 0 | 0 | 0 | 0 | 928879.0792 | 907639.4725 | 0
Projected FYTD |  |  |  | 9749.8308 |  |  |  | 606967.2267 |  |  |  | 616717.0575 |  |  |  | 0 | 321911.8525 |  |  |  | 919129.2483 |  |  |  | 928879.0792 |  |  |  | 907639.4775 | 1261701.2108 |  |  |  | 1339512.7992 |  |  |  | 1350494.63 |  |  |  | 1360244.4608 |  |  |  | 1759967.8917 |  |  |  | 2148812.0675
Incurred FYTD |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 321911.9025 |  |  |  | 665779.4725 |  |  |  | 907639.4725 |  |  |  |  | 907639.4725 |  |  |  | 907639.4725 |  |  |  | 907639.4725 |  |  |  | 907639.4725 |  |  |  | 907639.4725 |  |  |  | 907639.4725
Paid FYTD | [6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 37782.98 |  |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98
[16 empty] | 0 | [12 empty] | 0

## Footnotes
Department of Financial Services
FY 2023 - 2024 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5
6