## Monthly Summary
Department of Financial Services
Florida PALM FY 2023 - 2024 Spend Plan Summary FYTD
As of August 31, 2023
| Annual |  |  |  |  | July 2023 |  |  |  | August 2023 |  |  |  | September 2023 |  |  | October 2023 |  |  | November 2023 |  |  | December 2023 |  |  | January 2024 |  |  | February 2024 |  |  | March 2024 |  |  | April 2024 |  |  | May 2024 |  |  | June 2024 |  |  | CF 2023-24 |  | Fiscal Year to Date
Category (Cost Area / Contract) | 0 | 0 | 0 | 43851949.08 | 0 | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
| Appropriated | Released | Unreleased | Projected | Release Remaining
FLAIR System Replacement (100781) | 44440408 | 3420777 | 41019631 | 43851949.08 | -2069206.85 | 1318418.8642 | 1183502.44 |  | 429853.44 | 4873634.4292 | 4306481.41 |  | 851326.02 | 887276.8642 | 0 | 0 | 4275340.7167 | 0 | 0 | 4332348.6117 | 0 | 0 | 3180206.8642 | 0 | 0 | 1446220.7167 | 0 | 0 | 4466788.6117 | 0 | 0 | 8004226.8642 | 0 | 0 | 4384496.8642 | 0 | 0 | 5342620.4642 | 0 | 0 | 1340369.2092 | 0 | 0 | 0 | 0 | 6192053.2933 | 5489983.85 | 1281179.46 | 38361965.23 | 87.48%
SSI Implementation Services (FP004) |  |  |  | 29745300 |  | 0 | 0 |  | 0 | 3415500 | 3415500 |  | 0 | 0 | 0 | 0 | 2948400 | 0 | 0 | 3415500 | 0 | 0 | 2310500 | 0 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 7024400 | 0 | 0 | 3250000 | 0 | 0 | 3965500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 3415500 | 0 | 26329800 | 88.52%
Facilities and Maintenance (FP004) |  |  |  | 415692 |  | 34641 | 34641 |  | 34641 | 34641 | 34651 |  | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 69282 | 69292 | 69282 | 346400 | 83.33%
Production Support (FP004) |  |  |  | 8806126 |  | 1068287 | 1034011 |  | 390692 | 664400 | 664400 |  | 643319 | 664400 | 0 | 0 | 805457 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 805457 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 811725 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 0 | 0 | 1732687 | 1698411 | 1034011 | 7107715 | 80.71%
Production Support Administration |  |  |  | 51862.4 |  | 2405.2 | 2384.34 |  | 2384.34 | 2405.2 | 0.1 | 2 | 0.1 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 7405.2 | 0 | 0 | 20405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 2405.2 | 0 | 0 | 0 | 0 | 4810.4 | 2384.44 | 2384.44 | 49477.96 | 95.4%
Oracle Software and Maintenance (FP005) |  |  |  | 2252248.68 |  | 9749.8308 | 0 | 2 | 0 | 597217.3958 | 37782.98 | 2 | 0 | 9749.8308 | 0 | 0 | 331661.6833 | 0 | 0 | 77811.5783 | 0 | 0 | 9749.8308 | 0 | 0 | 331661.6833 | 0 | 0 | 77811.5783 | 0 | 0 | 9749.8308 | 0 | 0 | 9749.8308 | 0 | 0 | 399723.4308 | 0 | 0 | 387612.1758 | 0 | 0 | 0 | 0 | 606967.2267 | 37782.98 | 0 | 2214465.7 | 98.32%
Project Administration |  |  |  | 150000 |  | 63935.8333 | 2136.1 | 2 | 2136.1 | 3910.8333 | 6972.33 | 3 | 63605.92 | 40680.8333 | 0 | 0 | 3935.8333 | 0 | 0 | 3910.8333 | 0 | 0 | 5110.8333 | 0 | 0 | 3935.8333 | 0 | 0 | 3910.8333 | 0 | 0 | 8910.8333 | 0 | 0 | 3935.8333 | 0 | 0 | 3910.8333 | 0 | 0 | 3910.8333 | 0 | 0 | 0 | 0 | 67846.6667 | 9108.43 | 65742.02 | 140891.57 | 93.93%
ERP and OC Support Services |  |  |  | 1702720 |  | 139400 | 110330 | 1 | 0 | 155560 | 147175 | 1 | 109760 | 135400 | 0 | 0 | 148840 | 0 | 0 | 128680 | 0 | 0 | 135400 | 0 | 0 | 142120 | 0 | 0 | 142120 | 0 | 0 | 142120 | 0 | 0 | 148840 | 0 | 0 | 148840 | 0 | 0 | 135400 | 0 | 0 | 0 | 0 | 294960 | 257505 | 109760 | 1445215 | 84.88%
QA Support Services |  |  |  | 728000 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 0 | 0 | 126000 | 0 | 0 | 117600 | 0 | 0 | 123200 | 0 | 0 | 123200 | 0 | 0 | 112000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728000 | 100%
IT Service Management Implementation and Software (100777) | 2000000 | 2000000 | 0 | 1920427.52 | 2000000 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 940125.68 | 0 | 0 | 133374.4 | 0 | 0 | 140043.12 | 0 | 0 | 140043.12 | 0 | 0 | 140043.12 | 0 | 0 | 146711.84 | 0 | 0 | 146711.84 | 0 | 0 | 133374.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920427.52 | 100%
ITSM Implementation and Administration |  |  |  | 1107007.52 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126705.68 | 0 | 0 | 133374.4 | 0 | 0 | 140043.12 | 0 | 0 | 140043.12 | 0 | 0 | 140043.12 | 0 | 0 | 146711.84 | 0 | 0 | 146711.84 | 0 | 0 | 133374.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1107007.52 | 100%
ITSM Software |  |  |  | 813420 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813420 | 100%
Contingency (100819) | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DMS IV&V Transfer (100821) | 6053061 | 6053061 | 0 | 6053061 | 0 | 6053061 | 6053061 |  | 6053061 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6053061 | 6053061 | 6053061 | 0 | 0%
Salaries & Benefits (010000) | 9230956 | 9230956 | 0 | 9054804.72 | 8203596.59 | 754567.06 | 496925.61 |  | 496925.61 | 754567.06 | 530433.8 |  | 530433.8 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 754567.06 | 0 | 0 | 0 | 0 | 1509134.12 | 1027359.41 | 1027359.41 | 8027445.31 | 88.65%
Risk Management Insurance (103241) | 7978 | 7978 | 0 | 6944 | 0 | 6944 | 0 |  | 0 | 0 | 7978 |  | 7978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6944 | 7978 | 7978 | -1034 | -14.89%
DMS HR Transfer (107040) | 23273 | 23273 | 0 | 23273 | 23273 | 5818.25 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 5818.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5818.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5818.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5818.25 | 0 | 0 | 23273 | 100%
Totals | 63255676 | 20736045 | 42519631 | 60910459.32 | 8157662.74 | 8138809.1742 | 7733489.05 |  | 6979840.05 | 5628201.4892 | 4844893.21 |  | 1389737.82 | 1641843.9242 | 0 | 0 | 5035726.0267 | 0 | 0 | 6027041.3517 | 0 | 0 | 4068148.3242 | 0 | 0 | 2346649.1467 | 0 | 0 | 5361398.7917 | 0 | 0 | 8898837.0442 | 0 | 0 | 5291594.0142 | 0 | 0 | 6243899.3642 | 0 | 0 | 2228310.6692 | 0 | 0 | 0 | 0 | 13767010.6633 | 12578382.26 | 8369577.87 | 48332077.06 | 79.35%
Running Totals | [5 empty] | 8138809.1742 | 7733489.05 |  | 6979840.05 | 13767010.6633 | 12578382.26 |  | 8369577.87 | 15408854.5875 | 12578382.26 | 8369577.87 | 20444580.6142 | 12578382.26 | 8369577.87 | 26471621.9658 | 12578382.26 | 8369577.87 | 30539770.29 | 12578382.26 | 8369577.87 | 32886419.4367 | 12578382.26 | 8369577.87 | 38247818.2283 | 12578382.26 | 8369577.87 | 47146655.2725 | 12578382.26 | 8369577.87 | 52438249.2867 | 12578382.26 | 8369577.87 | 58682148.6508 | 12578382.26 | 8369577.87 | 60910459.32 | 12578382.26 | 8369577.87 |  | 8369577.87 |  | Total Incurred/Total Projected FYTD | Total Incurred/Total Projected FYTD |  | 91.37%
Monthly Total Incurred/Total Projected | [5 empty] | 95.02% |  |  |  | 86.08% |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% | [5 empty] | Total Paid/Total Projected FYTD | Total Paid/Total Projected FYTD |  | 60.79%
Monthly Total Incurred/Total Projected (Variance) | [5 empty] | -4.98% |  |  |  | -13.92% |  |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [5 empty] | 95.02% |  |  |  | 91.37% |  |  |  | 81.63% |  |  | 61.52% |  |  | 47.52% |  |  | 41.19% |  |  | 38.25% |  |  | 32.89% |  |  | 26.68% |  |  | 23.99% |  |  | 21.43% |  |  | 20.65% | [5 empty] | Total Release/Total Appropriation | Total Release/Total Appropriation |  | 32.78%
FYTD Total Incurred/Total Projected (Variance) | [5 empty] | -4.98% |  |  |  | -8.634% |  |  |  | -18.37% |  |  | -38.48% |  |  | -52.48% |  |  | -58.81% |  |  | -61.75% |  |  | -67.11% |  |  | -73.32% |  |  | -76.01% |  |  | -78.57% |  |  | -79.35%
[47 empty] | Total Paid/Total Release | Total Paid/Total Release |  | 40.36%
`
Note on BE11: Werner, Tommy: July

## SSI
|  |  | July 2023 |  |  | August 2023 |  |  | September 2023 |  |  | October 2023 |  |  | November 2023 |  |  | December 2023 |  |  | January 2024 |  |  | February 2024 |  |  | March 2024 |  |  | April 2024 |  |  | May 2024 |  |  | June 2024 |  |  | CF 2022-23
|  | Description | July Projection | July Accepted / Approved | July Paid | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Q1 Projection | Total Projection
Department of Financial Services
Florida PALM FY 2023 - 2024 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
D636 | Completion of Solution Design (Requirements) Segment I | Implementation | 0 | 0 | 0 | 3415500 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 3415500
D637 | Completion of Solution Design (Requirements) Segment II | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500
D638 | Updated Data Conversion and Migration Strategy | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
D639 | Development of Standardized Business Process Models – Payroll | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448400
D640 | Development of the Master Data Configuration Workbooks | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310500
D641 | Completion of Solution Design (Requirements) Segment III | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500
D642 | Updated Technical Architecture Design | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3811500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3811500
D643 | Updated System Testing Plan | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3212900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3212900
D644 | Completion of Solution Design (Requirements) Segment IV | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500
D645 | Updated Deployment Strategy | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
D646 | Completion of Build Segment I | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000
D647 | Establish DW/BI Environments | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 34641 | 34641 | 34641 | 34641 | 34651 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 103923 | 415692
Prod Supp | AM Services | Prod Supp | 537195 | 537195 | 0 | 554500 | 554500 | 537195 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 554500 | 0 | 0 | 0 | 0 | 1646195 | 6636695
Prod Supp | IM Services | Prod Supp | 106124 | 106124 | 0 | 109900 | 109900 | 106124 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 109900 | 0 | 0 | 0 | 0 | 325924 | 1315024
Prod Supp | Oracle OCI Costs | Prod Supp | 141057 | 141057 | 141057 | 0 | 0 | 0 | 0 | 0 | 0 | 141057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141057 | 570496
Prod Supp | Support Tools Maintenance | Prod Supp | 45030 | 45030 | 45030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45030 | 45030
Prod Supp | Support Tools Purchase | Prod Supp | 203556 | 169280 | 169280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203556 | 203556
Prod Supp | Solution Software Support | Prod Supp | 35325 | 35325 | 35325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35325 | 35325
| Implementation Total: |  | 0 | 0 | 0 | 3415500 | 3415500 | 0 | 0 | 0 | 0 | 2948400 | 0 | 0 | 3415500 | 0 | 0 | 2310500 | 0 | 0 | 0 | 0 | 0 | 3415500 | 0 | 0 | 7024400 | 0 | 0 | 3250000 | 0 | 0 | 3965500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 29745300
| Production Support Facilities: |  | 34641 | 0 | 0 | 34641 | 34651 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 103923 | 415692
| Production Support (No Facilities) Total: |  | 1068287 | 1034011 | 0 | 664400 | 664400 | 643319 | 664400 | 0 | 0 | 805457 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 805457 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 811725 | 0 | 0 | 664400 | 0 | 0 | 664400 | 0 | 0 | 0 | 0 | 2397087 | 8806126
Monthly Totals |  |  | 1102928 | 1068652 | 425333 | 4114541 | 4114551 | 677960 | 699041 | 0 | 0 | 3788498 | 0 | 0 | 4114541 | 0 | 0 | 3009541 | 0 | 0 | 840098 | 0 | 0 | 4114541 | 0 | 0 | 7723441 | 0 | 0 | 4096366 | 0 | 0 | 4664541 | 0 | 0 | 699041 | 0 | 0 | 0 | 0 | 5916510 | 38967118
| Projected YTD |  | 1102928 |  |  | 5217469 |  |  | 5916510 |  |  | 9705008 |  |  | 13819549 |  |  | 16829090 |  |  | 17669188 |  |  | 21783729 |  |  | 29507170 |  |  | 33603536 |  |  | 38268077 |  |  | 38967118
| Incurred YTD |  |  | 1068652 |  |  | 5183203 |  |  | 5183203 |  |  | 5183203 |  |  | 5183203 |  |  | 5183203 |  |  | 5183203 |  |  | 5183203 |  |  | 5183203 |  |  | 5183203 |  |  | 5183203 |  |  | 5183203 |  | 5183203
| Paid YTD |  |  |  | 425333 |  |  | 1103293 |  |  | 1103293 |  |  | 1103293 |  |  | 1103293 |  |  | 1103293 |  |  | 1103293 |  |  | 1103293 |  |  | 1103293 |  |  | 1103293 |  |  | 1103293 |  |  | 1103293 |  | 1103293
0

## Oracle
Department of Financial Services
Florida PALM FY 2023 - 2024 Contractor Detail FYTD
| Annual |  |  | July 2023 |  |  |  | August 2023 |  |  |  | September 2023 |  |  |  | October 2023 |  |  |  | November 2023 |  |  |  | December 2023 |  |  |  | January 2024 |  |  |  | February 2024 |  |  |  | March 2024 |  |  |  | April 2024 |  |  |  | May 2024 |  |  |  | June 2024 | [5 empty] | Total
Program | Tech Support | Purchase | Total Projection | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  |  | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support | 1287647.41 | 0 | 1287647.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321911.8525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321911.8525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321911.8525 | 0 | 0 | 0 | 321911.8525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
**Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 3401.27 |  | 3401.27 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 850.3175 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 850.3175 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 850.3175 | 0 |  | 0 | 850.3175 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle Business Intelligence (Analytics) Server Administrator | 1450.58 |  | 1450.58 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 362.645 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 362.645 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 362.645 | 0 |  | 0 | 362.645 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle Business Intelligence Management Pack | 2876.25 |  | 2876.25 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 719.0625 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 719.0625 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 719.0625 | 0 |  | 0 | 719.0625 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle Business Intelligence Suite Foundation Edition | 75048.11 |  | 75048.11 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 18762.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 18762.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 18762.0275 | 0 |  | 0 | 18762.0275 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle Data Integrator Enterprise Edition | 37524.06 |  | 37524.06 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9381.015 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9381.015 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9381.015 | 0 |  | 0 | 9381.015 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle Data Visualization | 25016.72 |  | 25016.72 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6254.18 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6254.18 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6254.18 | 0 |  | 0 | 6254.18 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*Oracle Financial Analytics Fusion Edition | 14509.91 |  | 14509.91 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3627.4775 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3627.4775 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3627.4775 | 0 |  | 0 | 3627.4775 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle Managed File Transfer | 20954.23 |  | 20954.23 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5238.5575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5238.5575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5238.5575 | 0 |  | 0 | 5238.5575 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle Management Pack for Oracle Data Integrator | 6904.25 |  | 6904.25 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1726.0625 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1726.0625 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1726.0625 | 0 |  | 0 | 1726.0625 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle SOA Management Pack Enterprise Edition | 20265.39 |  | 20265.39 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5066.3475 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5066.3475 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5066.3475 | 0 |  | 0 | 5066.3475 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle SOA Suite for Oracle Middleware | 46609.98 |  | 46609.98 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11652.495 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11652.495 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11652.495 | 0 |  | 0 | 11652.495 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle WebLogic Server Management Pack Enterprise Edition | 18108.82 |  | 18108.82 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4527.205 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4527.205 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4527.205 | 0 |  | 0 | 4527.205 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Oracle WebLogic Suite | 67908.63 |  | 67908.63 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 16977.1575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 16977.1575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 16977.1575 | 0 |  | 0 | 16977.1575 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Contracts | 51822.24 |  | 51822.24 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12955.56 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12955.56 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12955.56 | 0 |  | 0 | 12955.56 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise eSettlements | 34008.55 |  | 34008.55 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 8502.1375 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 8502.1375 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 8502.1375 | 0 |  | 0 | 8502.1375 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Expenses | 68825.48 |  | 68825.48 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Financials | 370847.94 |  | 370847.94 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 92711.985 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 92711.985 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 92711.985 | 0 |  | 0 | 92711.985 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Grants | 48582.45 |  | 48582.45 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12145.6125 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12145.6125 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12145.6125 | 0 |  | 0 | 12145.6125 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Human Resources | 46998.39 |  | 46998.39 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11749.5975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11749.5975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11749.5975 | 0 |  | 0 | 11749.5975 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Payroll | 57159.76 |  | 57159.76 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14289.94 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14289.94 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14289.94 | 0 |  | 0 | 14289.94 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Project Costing | 68825.48 |  | 68825.48 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Purchasing | 76113.47 |  | 76113.47 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19028.3675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19028.3675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19028.3675 | 0 |  | 0 | 19028.3675 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Supplier Contract Management | 68825.48 |  | 68825.48 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 17206.37 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
*PeopleSoft Enterprise Treasury | 55059.97 |  | 55059.97 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13764.9925 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13764.9925 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13764.9925 | 0 |  | 0 | 13764.9925 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Time and Labor Year 1 Support | 176803.62 | 0 | 176803.62 | 0 | 0 | 0 | 0 | 37782.975 | 37782.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37782.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37782.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37782.975 | 0 | 0 | 0 | 25671.72 | 0 | 0 | 0 | 0 | 0 | 37782.975 | 37782.98 | 0
*PeopleSoft Enterprise Time and Labor | 176803.62 |  | 176803.62 | 0 | 0 |  | 0 | 37782.975 | 37782.98 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 37782.975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 37782.975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 37782.975 | 0 |  | 0 | 25671.72 | 0 |  | 0 | 0 | 0 | 37782.975 | 37782.98 | 0
New License Purchase and Tech Support | 121115.09 | 666682.56 | 787797.65 | 9749.8308 | 0 | 0 | 0 | 559434.4208 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 40028.6033 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 40028.6033 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 40028.6033 | 0 | 0 | 0 | 40028.6033 | 0 | 0 | 0 | 0 | 0 | 569184.2517 | 0 | 0
*PeopleSoft Enterprise Financials | 29707.57 | 134665.46 | 164373.03 | 0 | 0 |  | 0 | 134665.46 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 7426.8925 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 7426.8925 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 7426.8925 | 0 |  | 0 | 7426.8925 | 0 |  | 0 | 0 | 0 | 134665.46 | 0 | 0
*PeopleSoft Enterprise Treasury | 4410.73 | 19994 | 24404.73 | 0 | 0 |  | 0 | 19994 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1102.6825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1102.6825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1102.6825 | 0 |  | 0 | 1102.6825 | 0 |  | 0 | 0 | 0 | 19994 | 0 | 0
*PeopleSoft Enterprise Expenses | 5513.41 | 24992.5 | 30505.91 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 | 24992.5 | 0 | 0
*PeopleSoft Enterprise eSettlements | 2724.27 | 12349.23 | 15073.5 | 0 | 0 |  | 0 | 12349.23 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 681.0675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 681.0675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 681.0675 | 0 |  | 0 | 681.0675 | 0 |  | 0 | 0 | 0 | 12349.23 | 0 | 0
*PeopleSoft Enterprise Contracts | 4151.28 | 18817.88 | 22969.16 | 0 | 0 |  | 0 | 18817.88 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1037.82 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1037.82 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1037.82 | 0 |  | 0 | 1037.82 | 0 |  | 0 | 0 | 0 | 18817.88 | 0 | 0
*PeopleSoft Enterprise Grants | 3891.82 | 17641.76 | 21533.58 | 0 | 0 |  | 0 | 17641.76 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 972.955 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 972.955 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 972.955 | 0 |  | 0 | 972.955 | 0 |  | 0 | 0 | 0 | 17641.76 | 0 | 0
*PeopleSoft Enterprise Project Costing | 5513.41 | 24992.5 | 30505.91 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 | 24992.5 | 0 | 0
*PeopleSoft Enterprise Supplier Contract Management | 5513.41 | 24992.5 | 30505.91 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 1378.3525 | 0 |  | 0 | 0 | 0 | 24992.5 | 0 | 0
*PeopleSoft Enterprise Purchasing | 6097.19 | 27638.76 | 33735.95 | 0 | 0 |  | 0 | 27638.76 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1524.2975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1524.2975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1524.2975 | 0 |  | 0 | 1524.2975 | 0 |  | 0 | 0 | 0 | 27638.76 | 0 | 0
HR Analytics | 44660 | 203000 | 247660 | 0 | 0 |  | 0 | 203000 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11165 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11165 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11165 | 0 |  | 0 | 11165 | 0 |  | 0 | 0 | 0 | 203000 | 0 | 0
Project Analytics | 8932 | 40600 | 49532 | 0 | 0 |  | 0 | 40600 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2233 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2233 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2233 | 0 |  | 0 | 2233 | 0 |  | 0 | 0 | 0 | 40600 | 0 | 0
OAC Dev | 0 | 53218.69 | 53218.69 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 0 | 0 | 8869.7817 | 0 | 0
OAC Test | 0 | 63779.28 | 63779.28 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 0 | 0 | 10629.88 | 0 | 0
Total | 1585566.12 | 666682.56 | 2252248.68 | 9749.8308 | 0 | 0 | 0 | 597217.3958 | 37782.98 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 331661.6833 | 0 | 0 | 0 | 77811.5783 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 331661.6833 | 0 | 0 | 0 | 77811.5783 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | 399723.4308 | 0 | 0 | 0 | 387612.1758 | 0 | 0 | 0 | 0 | 0 | 606967.2267 | 37782.98 | 0
Projected FYTD |  |  |  | 9749.8308 |  |  |  | 606967.2267 |  |  |  | 616717.0575 |  |  |  | 948378.7408 |  |  |  | 1026190.3192 |  |  |  | 1035940.15 |  |  |  | 1367601.8333 |  |  |  | 1445413.4117 |  |  |  | 1455163.2425 |  |  |  | 1464913.0733 |  |  |  | 1864636.5042 |  |  |  | 2252248.68
Incurred FYTD |  |  |  |  | 0 |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98 |  |  |  | 37782.98
Paid FYTD | [6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0

## Footnotes
Department of Financial Services
FY 2023 - 2024 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5
6