## Monthly Summary
Department of Financial Services
Florida PALM FY 2024 - 2025 Spend Plan Summary FYTD
As of August 31, 2024
Annual
| TRUE | TRUE | TRUE |  | TRUE | July 2024 |  |  |  | August 2024 |  |  |  | September 2024 |  |  | October 2024 |  |  | November 2024 |  |  | December 2024 |  |  | January 2025 |  |  | February 2025 |  |  | March 2025 |  |  | April 2025 |  |  | May 2025 |  |  | June 2025 |  |  | CF 2024-25 |  | Fiscal Year to Date
Category (Cost Area / Contract) | 46381361 | 11595340 | 34786021 | 45243510.012 | 6860695.89 | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
| Appropriated | Released | Unreleased | Projected | Release Remaining
FLAIR System Replacement (100781) | 46381361 | 11595340 | 34786021 | 45243510.012 | 6860695.89 | 3724003.705 | 3754458.96 |  | 3526393.96 | 1038867.705 | 980185.15 |  | 912032.65 | 1104165.705 | 0 | 0 | 5214718.462 | 0 | 0 | 2366939.6135 | 0 | 0 | 3748731.705 | 0 | 0 | 6369690.462 | 0 | 0 | 5247471.6135 | 0 | 0 | 3171523.705 | 0 | 0 | 3361420.092 | 0 | 0 | 3386756.2435 | 0 | 0 | 6509221.0005 | 0 | 0 | 0 | 0 | 4762871.41 | 4734644.11 | 4438426.61 | 40508865.902 | 89.54%
SSI Implementation Services (FP004) |  |  |  | 28946400 |  | 2250000 | 2250000 |  | 2250000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 3450000 | 0 | 0 | 1200000 | 0 | 0 | 2574100 | 0 | 0 | 4600000 | 0 | 0 | 4074100 | 0 | 0 | 2000000 | 0 | 0 | 1630000 | 0 | 0 | 2200000 | 0 | 0 | 4968200 | 0 | 0 | 0 | 0 | 2250000 | 2250000 | 2250000 | 26696400 | 92.23%
Facilities and Maintenance (FP004) |  |  |  | 415692 |  | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 69282 | 69282 | 69282 | 346410 | 83.33%
Production Support (FP004) |  |  |  | 9243877 |  | 1134539 | 1225344 | 3 | 1225344 | 686100 | 686100 |  | 686100 | 686100 | 0 | 0 | 873512 | 0 | 0 | 686100 | 0 | 0 | 686100 | 0 | 0 | 873512 | 0 | 0 | 686100 | 0 | 0 | 686100 | 0 | 0 | 873514 | 0 | 0 | 686100 | 0 | 0 | 686100 | 0 | 0 | 0 | 0 | 1820639 | 1911444 | 1911444 | 7332433 | 79.32%
Additional Facilities |  |  |  | 129724.05 |  | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 0 | 0 | 10756.18 | 0 | 0 | 10756.18 | 0 | 0 | 10756.18 | 0 | 0 | 10756.18 | 0 | 0 | 10756.18 | 0 | 0 | 10756.18 | 0 | 0 | 10972.81 | 0 | 0 | 10972.81 | 0 | 0 | 10972.81 | 0 | 0 | 0 | 0 | 21512.36 | 21512.36 | 21512.36 | 108211.69 | 83.42%
Production Support Administration |  |  |  | 53839.12 |  | 2403.26 | 2383.44 |  | 2383.44 | 2403.26 | 2383.26 |  | 2383.26 | 2403.26 | 0 | 0 | 2403.26 | 0 | 0 | 2403.26 | 0 | 0 | 2403.26 | 0 | 0 | 27403.26 | 0 | 0 | 2403.26 | 0 | 0 | 2403.26 | 0 | 0 | 2403.26 | 0 | 0 | 2403.26 | 0 | 0 | 2403.26 | 0 | 0 | 0 | 0 | 4806.52 | 4766.7 | 4766.7 | 49072.42 | 91.15%
Oracle Software and Maintenance (FP005) |  |  |  | 1906753.842 |  | 27839.9317 | 0 | 2 | 0 | 27839.9317 | 0 | 2 | 0 | 27839.9317 | 0 | 0 | 395992.6887 | 0 | 0 | 52855.8402 | 0 | 0 | 27839.9317 | 0 | 0 | 395992.6887 | 0 | 0 | 52855.8402 | 0 | 0 | 27839.9317 | 0 | 0 | 395992.6887 | 0 | 0 | 52855.8402 | 0 | 0 | 421008.5972 | 0 | 0 | 0 | 0 | 55679.8633 | 0 | 0 | 1906753.842 | 100%
Project Administration |  |  |  | 210000 |  | 22096.3333 | 3269.34 | 2 | 3269.34 | 14735.3333 | 15871.21 | 3 | 15871.21 | 87505.3333 | 0 | 0 | 20285.3333 | 0 | 0 | 6735.3333 | 0 | 0 | 7235.3333 | 0 | 0 | 6785.3333 | 0 | 0 | 7455.3333 | 0 | 0 | 16735.3333 | 0 | 0 | 6960.3333 | 0 | 0 | 6735.3333 | 0 | 0 | 6735.3333 | 0 | 0 | 0 | 0 | 36831.6667 | 19140.55 | 19140.55 | 190859.45 | 90.89%
Support Services |  |  |  | 3306088 |  | 159536 | 149537 | 1 | 0 | 180200 | 150249.5 | 1 | 100297 | 180200 | 0 | 0 | 341200 | 0 | 0 | 306200 | 0 | 0 | 327200 | 0 | 0 | 327200 | 0 | 0 | 285760 | 0 | 0 | 299648 | 0 | 0 | 313536 | 0 | 0 | 299648 | 0 | 0 | 285760 | 0 | 0 | 0 | 0 | 339736 | 299786.5 | 100297 | 3006301.5 | 90.93%
QA Support Services |  |  |  | 1031136 |  | 82192 | 78528 |  | 0 | 82192 | 80184 |  | 61984 | 74720 | 0 | 0 | 85928 | 0 | 0 | 67248 | 0 | 0 | 78456 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 0 | 0 | 164384 | 158712 | 61984 | 872424 | 84.61%
IT Service Management Implementation and Software (100777) | 1304572 | 1304572 | 0 | 882912.94 | 1266959.04 | 38576.48 | 0 |  | 0 | 963.52 | 37612.96 |  | 37612.96 | 20124.28 | 0 | 0 | 130138.15 | 0 | 0 | 3333.09 | 0 | 0 | 16139.54 | 0 | 0 | 963.52 | 0 | 0 | 668820.28 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 0 | 0 | 39540 | 37612.96 | 37612.96 | 845299.98 | 95.74%
ITSM Implementation and Administrative Support |  |  |  | 203493.94 |  | 37612.96 | 0 | 2 | 0 | 0 | 37612.96 | 3 | 37612.96 | 19160.76 | 0 | 0 | 129174.63 | 0 | 0 | 2369.57 | 0 | 0 | 15176.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37612.96 | 37612.96 | 37612.96 | 165880.98 | 81.52%
ITSM Software |  |  |  | 679419 |  | 963.52 | 0 | 2 | 0 | 963.52 | 0 | 2 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 668820.28 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 0 | 0 | 1927.04 | 0 | 0 | 679419 | 100%
Contingency (100819) | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Salaries & Benefits (010000) | 9886462 | 9886462 | 0 | 9886462 | 8411795.08 | 823871.84 | 697273.25 |  | 697273.25 | 823871.83 | 777393.67 |  | 777393.67 | 823871.83 | 0 | 0 | 823871.84 | 0 | 0 | 823871.83 | 0 | 0 | 823871.83 | 0 | 0 | 823871.84 | 0 | 0 | 823871.83 | 0 | 0 | 823871.83 | 0 | 0 | 823871.84 | 0 | 0 | 823871.83 | 0 | 0 | 823871.83 | 0 | 0 | 0 | 0 | 1647743.67 | 1474666.92 | 1474666.92 | 8411795.08 | 85.08%
Risk Management Insurance (103241) | 13957 | 13957 | 0 | 7978 | 0 | 7978 | 0 |  | 0 | 0 | 13957 | 5 | 13957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7978 | 13957 | 13957 | -5979 | -74.94%
DMS HR Transfer (107040) | 24609 | 24609 | 0 | 24609 | 24609 | 6152.25 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 6152.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6152.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6152.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6152.25 | 0 | 0 | 24609 | 100%
Totals | 60610961 | 22824940 | 37786021 | 56045471.952 | 16564059.01 | 4600582.275 | 4451732.21 |  | 4223667.21 | 1863703.055 | 1809148.78 |  | 1740996.28 | 1948161.815 | 0 | 0 | 6174880.702 | 0 | 0 | 3194144.5335 | 0 | 0 | 4588743.075 | 0 | 0 | 7200678.072 | 0 | 0 | 6740163.7235 | 0 | 0 | 3996359.055 | 0 | 0 | 4192407.702 | 0 | 0 | 4211591.5935 | 0 | 0 | 7334056.3505 | 0 | 0 | 0 | 0 | 6464285.33 | 6260880.99 | 5964663.49 | 49784590.962 | 88.83%
Running Totals | [5 empty] | 4600582.275 | 4451732.21 |  | 4223667.21 | 6464285.33 | 6260880.99 |  | 5964663.49 | 8412447.145 | 6260880.99 | 5964663.49 | 14587327.847 | 6260880.99 | 5964663.49 | 17781472.3805 | 6260880.99 | 5964663.49 | 22370215.4555 | 6260880.99 | 5964663.49 | 29570893.5275 | 6260880.99 | 5964663.49 | 36311057.251 | 6260880.99 | 5964663.49 | 40307416.306 | 6260880.99 | 5964663.49 | 44499824.008 | 6260880.99 | 5964663.49 | 48711415.6015 | 6260880.99 | 5964663.49 | 56045471.952 | 6260880.99 | 5964663.49 |  | 5964663.49
Monthly Total Incurred/Total Projected | [5 empty] | 96.76% |  |  |  | 97.07% |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Monthly Total Incurred/Total Projected (Variance) | [5 empty] | -3.235% |  |  |  | -2.927% |  |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [5 empty] | 96.76% |  |  |  | 96.85% |  |  |  | 74.42% |  |  | 42.92% |  |  | 35.21% |  |  | 27.99% |  |  | 21.17% |  |  | 17.24% |  |  | 15.53% |  |  | 14.07% |  |  | 12.85% |  |  | 11.17%
FYTD Total Incurred/Total Projected (Variance) | [5 empty] | -3.235% |  |  |  | -3.147% |  |  |  | -25.58% |  |  | -57.08% |  |  | -64.79% |  |  | -72.01% |  |  | -78.83% |  |  | -82.76% |  |  | -84.47% |  |  | -85.93% |  |  | -87.15% |  |  | -88.83%

## Footnotes
Department of Financial Services
FY 2024 - 2025 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5 | Incurred amounts were greater than anticipated due to an additional appropriation to the category.
6

## SSI Detail
|  |  |  | July 2024 |  |  | August 2024 |  |  | September 2024 |  |  | October 2024 |  |  | November 2024 |  |  | December 2024 |  |  | January 2025 |  |  | February 2025 |  |  | March 2025 |  |  | April 2025 |  |  | May 2025 |  |  | June 2025 |  |  | CF 2024-25
|  | Description | Total Deliverable Cost FY 24-25 | July Projection | July Accepted / Approved | July Paid | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Projection | Projection Remaining | Projected FYTD | Total Accepted / Approved | Projected FYTD Pending | Total Paid | Payment Pending
Department of Financial Services
Florida PALM FY 2024 - 2025 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
D648 | Completion of Build Segment II | Implementation | 2250000 | 2250000 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 2250000 | -2250000 | 2250000 | 0
D649 | Completion of Build Segment III | Implementation | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0
D650 | Completion of Solution Design (Requirements) DW/BI | Implementation | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0
D651 | Completion of Mock Conversion I | Implementation | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0
D652 | Completion of System Test Segment I | Implementation | 2574100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574100 | 2574100 | 0 | 0 | 0 | 0 | 0
D653 | Completion of Build Segment I DW/BI | Implementation | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0
D654 | Completion of Build Segment IV | Implementation | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0
D655 | Completion of Mock Conversion II (System Test Environment) | Implementation | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0
D656 | Completion of System Test Segment II | Implementation | 2574100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574100 | 2574100 | 0 | 0 | 0 | 0 | 0
D657 | Completion of Mock Conversion III (UAT) | Implementation | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0
D658 | Develop the Deployment and Contingency Plan | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0
D659 | Completion of Build Segment II DW/BI | Implementation | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0
D660 | Payroll Parallel Testing Plan | Implementation | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 280000 | 0 | 0 | 0 | 0 | 0
D661 | Completion of System Test DW/BI | Implementation | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0
D662 | Completion of Dress Rehearsal (Mock Conversion IV) | Implementation | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0
D663 | Completion of Interface Testing Segment I | Implementation | 2081700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2081700 | 0 | 0 | 0 | 0 | 2081700 | 2081700 | 0 | 0 | 0 | 0 | 0
D664 | Development of the Hypercare Support Plan | Implementation | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000 | 0 | 0 | 0 | 0 | 455000 | 455000 | 0 | 0 | 0 | 0 | 0
D665 | Updated Post-Implementation Support Plan | Implementation | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000 | 0 | 0 | 0 | 0 | 455000 | 455000 | 0 | 0 | 0 | 0 | 0
D666 | Support of UAT Segment I | Implementation | 1976500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1976500 | 0 | 0 | 0 | 0 | 1976500 | 1976500 | 0 | 0 | 0 | 0 | 0
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 415692 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692 | 346410 | 0 | 69282 | -69282 | 69282 | 0
Prod Supp | AM Services | Prod Supp | 6849800 | 554500 | 554500 | 554500 | 572300 | 572300 | 572300 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 0 | 0 | 6849800 | 5723000 | 0 | 1126800 | -1126800 | 1126800 | 0
Prod Supp | IM Services | Prod Supp | 1361700 | 109900 | 109900 | 109900 | 113800 | 113800 | 113800 | 113800 | 0 | 0 | 113800 | 0 | 0 | 113800 | 0 | 0 | 113800 | 0 | 0 | 113800 | 0 | 0 | 113800 | 0 | 0 | 113800 | 0 | 0 | 113800 | 0 | 0 | 113800 | 0 | 0 | 113800 | 0 | 0 | 0 | 0 | 1361700 | 1138000 | 0 | 223700 | -223700 | 223700 | 0
Prod Supp | Oracle OCI Costs | Prod Supp | 749650 | 187412 | 187412 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749650 | 562238 | 0 | 187412 | -187412 | 187412 | 0
Prod Supp | Support Tools Maintenance | Prod Supp | 46381 | 46381 | 46381 | 46381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46381 | 0 | 0 | 46381 | -46381 | 46381 | 0
Prod Supp | Support Tools Purchase | Prod Supp | 203556 | 203556 | 311780 | 311780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203556 | -108224 | 0 | 311780 | -311780 | 311780 | 0
Prod Supp | Solution Software Support | Prod Supp | 32790 | 32790 | 15371 | 15371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32790 | 17419 | 0 | 15371 | -15371 | 15371 | 0
| Implementation Total: |  |  | 2250000 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 3450000 | 0 | 0 | 1200000 | 0 | 0 | 2574100 | 0 | 0 | 4600000 | 0 | 0 | 4074100 | 0 | 0 | 2000000 | 0 | 0 | 1630000 | 0 | 0 | 2200000 | 0 | 0 | 4968200 | 0 | 0 | 0 | 0 | 28946400 | 26696400 | 0 | 2250000 | -2250000 | 2250000 | 0
| Production Support Facilities Total: |  |  | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692 | 346410 | 0 | 69282 | -69282 | 69282 | 0
| Production Support (No Facilities) Total: |  |  | 1134539 | 1225344 | 1225344 | 686100 | 686100 | 686100 | 686100 | 0 | 0 | 873512 | 0 | 0 | 686100 | 0 | 0 | 686100 | 0 | 0 | 873512 | 0 | 0 | 686100 | 0 | 0 | 686100 | 0 | 0 | 873514 | 0 | 0 | 686100 | 0 | 0 | 686100 | 0 | 0 | 0 | 0 | 9243877 | 7332433 | 0 | 1911444 | -1911444 | 1911444 | 0
Monthly Totals |  |  | 38605969 | 3419180 | 3509985 | 3509985 | 720741 | 720741 | 720741 | 720741 | 0 | 0 | 4358153 | 0 | 0 | 1920741 | 0 | 0 | 3294841 | 0 | 0 | 5508153 | 0 | 0 | 4794841 | 0 | 0 | 2720741 | 0 | 0 | 2538155 | 0 | 0 | 2920741 | 0 | 0 | 5688941 | 0 | 0 | 0 | 0 | 38605969 | 34375243 | 0 | 4230726 | -4230726 | 4230726 | 0
| Projected YTD |  |  | 3419180 |  |  | 4139921 |  |  | 4860662 |  |  | 9218815 |  |  | 11139556 |  |  | 14434397 |  |  | 19942550 |  |  | 24737391 |  |  | 27458132 |  |  | 29996287 |  |  | 32917028 |  |  | 38605969
| Incurred YTD |  |  |  | 3509985 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  | 4230726
| Paid YTD |  |  |  |  | 3509985 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  |  | 4230726 |  | 4230726

## Oracle Summary
Department of Financial Services
Florida PALM FY 2024 - 2025 Oracle Summary FYTD
| Quantity/Months | Quote |  |  | July 2024 |  |  |  | August 2024 |  |  |  | September 2024 |  |  |  | October 2024 |  |  |  | November 2024 |  |  |  | December 2024 |  |  |  | January 2025 |  |  |  | February 2025 |  |  |  | March 2025 |  |  |  | April 2025 |  |  |  | May 2025 |  |  |  | June 2025 |  |  |  | FY 2024-25 CF |  | Total
Program |  | Tech Support | Total Purchase/ Subscription | Total Projection | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | CF Incurred | CF Paid | Total Projected | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support |  | 1518401.278 |  | 1518401.278 | 0 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 368152.757 | 0 | #REF! | 0 | 11447.5625 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 368152.757 | 0 | #REF! | 0 | 11447.5625 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 368152.757 | 0 | #REF! | 0 | 11447.5625 | 0 | #REF! | 0 | 379600.3195 | 0 | #REF! | 0 | 0 | 0 | 1518401.278 | 1906753.842 | 1308375.7974 | 0
Assignment |  | 1518401.278 | 0 | 1518401.278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368152.757 | 0 | 0 | 0 | 11447.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368152.757 | 0 | 0 | 0 | 11447.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368152.757 | 0 | 0 | 0 | 11447.5625 | 0 | 0 | 0 | 379600.3195 | 0 | 0 | 0 | 0 | 0 | 1518401.278 | 1518401.278 | 1308375.7974 | 0
Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 2 | 8525.418 | 0 | 8525.418 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2131.3545 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2131.3545 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2131.3545 | 0 |  | 0 | 0 | 0 |  | 0 | 2131.3545 | 0 |  | 0 | 0 | 0 | 8525.418 | 8525.418 | 157679.5968 | 0
Oracle Business Intelligence (Analytics) Server Administrator | 4 | 1479.59 | 0 | 1479.59 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 | 1479.59 | 1479.59 | 1327.5504 | 0
Oracle Business Intelligence Management Pack | 4 | 2933.77 | 0 | 2933.77 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 | 2933.77 | 2933.77 | 2632.212 | 0
Oracle Business Intelligence Suite Foundation Edition | 4 | 76549.07 | 0 | 76549.07 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 | 76549.07 | 76549.07 | 68666.4 | 0
Oracle Data Integrator Enterprise Edition | 20 | 38274.54 | 0 | 38274.54 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 | 38274.54 | 38274.54 | 34333.2 | 0
Oracle Data Visualization | 4 | 25517.06 | 0 | 25517.06 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 | 25517.06 | 25517.06 | 22888.8 | 0
Oracle Financial Analytics Fusion Edition (DW/BI) | 100 | 14800.11 | 0 | 14800.11 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 | 14800.11 | 14800.11 | 13275.3 | 0
Oracle Managed File Transfer | 12 | 21373.31 | 0 | 21373.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 | 21373.31 | 21373.31 | 20599.92 | 0
Oracle Management Pack for Oracle Data Integrator | 16 | 7042.33 | 0 | 7042.33 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 | 7042.33 | 7042.33 | 6317.3088 | 0
Oracle SOA Management Pack Enterprise Edition | 14 | 20670.71 | 0 | 20670.71 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 | 20670.71 | 20670.71 | 20027.7 | 0
Oracle SOA Suite for Oracle Middleware | 14 | 47542.18 | 0 | 47542.18 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 | 47542.18 | 47542.18 | 46063.71 | 0
Oracle WebLogic Server Management Pack Enterprise Edition | 26 | 18471 | 0 | 18471 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 | 18471 | 18471 | 17853.264 | 0
Oracle WebLogic Suite | 26 | 69266.8 | 0 | 69266.8 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 | 69266.8 | 69266.8 | 66949.74 | 0
PeopleSoft Enterprise Contracts | 92083 | 55673.81 | 0 | 55673.81 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13214.6675 | 0 |  | 0 | 703.785 | 0 |  | 0 | 0 | 0 |  | 0 | 13214.6675 | 0 |  | 0 | 703.785 | 0 |  | 0 | 0 | 0 |  | 0 | 13214.6675 | 0 |  | 0 | 703.785 | 0 |  | 0 | 13918.4525 | 0 |  | 0 | 0 | 0 | 55673.81 | 55673.81 | 56354.796 | 0
PeopleSoft Enterprise eSettlements | 92083 | 36536.19 | 0 | 36536.19 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 8672.185 | 0 |  | 0 | 461.8625 | 0 |  | 0 | 0 | 0 |  | 0 | 8672.185 | 0 |  | 0 | 461.8625 | 0 |  | 0 | 0 | 0 |  | 0 | 8672.185 | 0 |  | 0 | 461.8625 | 0 |  | 0 | 9134.0475 | 0 |  | 0 | 0 | 0 | 36536.19 | 36536.19 | 37569.864 | 0
PeopleSoft Enterprise Expenses | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 73940.87 | 73940.87 | 76078.9746 | 0
PeopleSoft Enterprise Financials | 92083 | 398410.84 | 0 | 398410.84 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 94566.2225 | 0 |  | 0 | 5036.4875 | 0 |  | 0 | 0 | 0 |  | 0 | 94566.2225 | 0 |  | 0 | 5036.4875 | 0 |  | 0 | 0 | 0 |  | 0 | 94566.2225 | 0 |  | 0 | 5036.4875 | 0 |  | 0 | 99602.71 | 0 |  | 0 | 0 | 0 | 398410.84 | 398410.84 | 405754.5312 | 0
PeopleSoft Enterprise Grants | 92083 | 52193.31 | 0 | 52193.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12388.525 | 0 |  | 0 | 659.8025 | 0 |  | 0 | 0 | 0 |  | 0 | 12388.525 | 0 |  | 0 | 659.8025 | 0 |  | 0 | 0 | 0 |  | 0 | 12388.525 | 0 |  | 0 | 659.8025 | 0 |  | 0 | 13048.3275 | 0 |  | 0 | 0 | 0 | 52193.31 | 52193.31 | 52597.8096 | 0
PeopleSoft Enterprise Human Resources | 114800 | 47938.36 | 0 | 47938.36 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 | 47938.36 | 47938.36 | 46838.4 | 0
PeopleSoft Enterprise Payroll | 114800 | 58302.96 | 0 | 58302.96 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 | 58302.96 | 58302.96 | 0 | 0
PeopleSoft Enterprise Project Costing | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 73940.87 | 73940.87 | 0 | 0
PeopleSoft Enterprise Purchasing | 92083 | 81770.5 | 0 | 81770.5 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19408.935 | 0 |  | 0 | 1033.69 | 0 |  | 0 | 0 | 0 |  | 0 | 19408.935 | 0 |  | 0 | 1033.69 | 0 |  | 0 | 0 | 0 |  | 0 | 19408.935 | 0 |  | 0 | 1033.69 | 0 |  | 0 | 20442.625 | 0 |  | 0 | 0 | 0 | 81770.5 | 81770.5 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 73940.87 | 73940.87 | 0 | 0
PeopleSoft Enterprise Treasury | 92083 | 59152.27 | 0 | 59152.27 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14040.2925 | 0 |  | 0 | 747.775 | 0 |  | 0 | 0 | 0 |  | 0 | 14040.2925 | 0 |  | 0 | 747.775 | 0 |  | 0 | 0 | 0 |  | 0 | 14040.2925 | 0 |  | 0 | 747.775 | 0 |  | 0 | 14788.0675 | 0 |  | 0 | 0 | 0 | 59152.27 | 59152.27 | 0 | 0
PeopleSoft Enterprise Time and Labor | 114800 | 154154.54 | 0 | 154154.54 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 38538.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 38538.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 38538.635 | 0 |  | 0 | 0 | 0 |  | 0 | 38538.635 | 0 |  | 0 | 0 | 0 | 154154.54 | 154154.54 | 154566.72 | 0
Analytics |  | 54273.384 |  | 54273.384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13568.346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13568.346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13568.346 | 0 | 0 | 0 | 13568.346 | 0 | 0 | 0 | 0 | 0 | 54273.384 | 54273.384 | 0 | 0
HR Analytics (DW/BI) | 100 | 45227.82 | 0 | 45227.82 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11306.955 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11306.955 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11306.955 | 0 |  | 0 | 11306.955 | 0 |  | 0 | 0 | 0 | 45227.82 | 45227.82 | 0 | 0
Project Analytics (DW/BI) | 20 | 9045.564 | 0 | 9045.564 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2261.391 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2261.391 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2261.391 | 0 |  | 0 | 2261.391 | 0 |  | 0 | 0 | 0 | 9045.564 | 9045.564 | 0 | 0
OCI |  | 0 |  | 334079.18 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 0 | 0 | 334079.18 | 334079.18 | 0 | 0
OAC (DW/BI) - DEV: $53,218.69 - Test : $63,779.29 - DR : $93,780.73 - Production : $123,300.47 | 4 | 0 | 334079.18 | 334079.18 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 0 | 0 | 334079.18 | 334079.18 | 0 | 0
New License Purchase and Tech Support |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Financials | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Treasury | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Expenses | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise eSettlements | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Contracts | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Grants | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Project Costing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Purchasing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Human Resources | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Payroll | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Time and Labor | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 1572674.662 |  | 1906753.842 | 27839.9317 | 0 | #REF! | 0 | 27839.9317 | 0 | #REF! | 0 | 27839.9317 | 0 | #REF! | 0 | 395992.6887 | 0 | #REF! | 0 | 52855.8402 | 0 | #REF! | 0 | 27839.9317 | 0 | #REF! | 0 | 395992.6887 | 0 | #REF! | 0 | 52855.8402 | 0 | #REF! | 0 | 27839.9317 | 0 | #REF! | 0 | 395992.6887 | 0 | #REF! | 0 | 52855.8402 | 0 | #REF! | 0 | 421008.5972 | 0 | #REF! | 0 | 0 | 0 | 1906753.842 | 1906753.842 | 1308375.7974 | 0
Projected FYTD |  |  |  |  | 27839.9317 |  |  |  | 55679.8633 |  |  |  | 83519.795 |  |  |  | 479512.4837 |  |  |  | 532368.3238 |  |  |  | 560208.2555 |  |  |  | 956200.9442 |  |  |  | 1009056.7843 |  |  |  | 1036896.716 |  |  |  | 1432889.4047 |  |  |  | 1485745.2448 |  |  |  | 1906753.842
Incurred FYTD | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Paid FYTD | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[10 empty] | 55679.8633 |  | 55679.8633 |  | 83519.795 |  | 0 |  | 479512.4837 |  | 479512.4837 |  | 532368.3238 |  | 532368.3238 |  | 560208.2555 |  | 560208.2555 |  | 956200.9442 |  | 956200.9442 |  | 1009056.7843 |  | 1009056.7843 |  | 1036896.716 |  | 1036896.716 |  | 1432889.4047 |  | 1432889.4047 |  | 1485745.2448 |  | 1485745.2448 |  | 1906753.842 |  | 1906753.842