## Monthly Summary
Department of Financial Services
Florida PALM FY 2024 - 2025 Spend Plan Summary FYTD
As of October 31, 2024
Annual
| TRUE | TRUE | TRUE |  | TRUE | July 2024 |  |  |  | August 2024 |  |  |  | September 2024 |  |  |  | Q2 Basline Adjustment | October 2024 |  |  |  | November 2024 |  |  | December 2024 |  |  | January 2025 |  |  | February 2025 |  |  | March 2025 |  |  | April 2025 |  |  | May 2025 |  |  | June 2025 |  |  | CF 2024-25 |  | Fiscal Year to Date
Category (Cost Area / Contract) | 46381361 | 17337427 | 29043934 | 45926103.947 | 10479948.221 | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
| Appropriated | Released | Unreleased | Projected | Release Remaining | [12 empty] | Q1 Baseline Adjustment
FLAIR System Replacement (100781) | 46381361 | 17337427 | 29043934 | 45926103.947 | 10479948.221 | 3724003.7017 | 3754458.96 |  | 3526393.96 | 1038867.7017 | 980185.15 |  | 912032.65 | 1104165.7017 | 956326.57 |  | 931197.19 | -176066.425 | 5078311.7014 | 1166508.099 |  | 1146445.87 | 2289008.2879 | 0 | 0 | 3077546.3794 | 0 | 0 | 6860912.8714 | 0 | 0 | 4709934.2879 | 0 | 0 | 3209438.3794 | 0 | 0 | 3400686.7664 | 0 | 0 | 4803510.9179 | 0 | 0 | 6805783.6749 | 0 | 0 | 0 | 0 | 10769282.3814 | 6857478.779 | 6516069.67 | 39068625.168 | 85.07%
SSI Implementation Services (FP004) |  |  |  | 29837040 |  | 2250000 | 2250000 |  | 2250000 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3450000 | 0 | 2 | 0 | 1200000 | 0 | 0 | 2000000 | 0 | 0 | 5000000 | 0 | 0 | 3500000 | 0 | 0 | 2000000 | 0 | 0 | 1630000 | 0 | 0 | 3578840 | 0 | 0 | 5228200 | 0 | 0 | 0 | 0 | 5700000 | 2250000 | 2250000 | 27587040 | 92.46%
Facilities and Maintenance (FP004) |  |  |  | 415692 |  | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 138564 | 138564 | 138564 | 277128 | 66.67%
Production Support (FP004) |  |  |  | 9379682 |  | 1134539 | 1225344 | 3 | 1225344 | 686100 | 686100 |  | 686100 | 686100 | 686100 |  | 686100 | 90805 | 873512 | 873512 |  | 873512 | 686100 | 0 | 0 | 686100 | 0 | 0 | 873512 | 0 | 0 | 695100 | 0 | 0 | 695100 | 0 | 0 | 882514 | 0 | 0 | 695100 | 0 | 0 | 695100 | 0 | 0 | 0 | 0 | 3471056 | 3471056 | 3471056 | 5908626 | 62.99%
Additional Facilities |  |  |  | 129724.05 |  | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 10756.18 |  | 10756.18 | 0 | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 0 | 0 | 10756.18 | 0 | 0 | 10756.18 | 0 | 0 | 10756.18 | 0 | 0 | 10756.18 | 0 | 0 | 10972.81 | 0 | 0 | 10972.81 | 0 | 0 | 10972.81 | 0 | 0 | 0 | 0 | 43024.72 | 43024.72 | 43024.72 | 86699.33 | 66.83%
Production Support Administration |  |  |  | 53599.3 |  | 2403.26 | 2383.44 |  | 2383.44 | 2403.26 | 2383.26 |  | 2383.26 | 2403.26 | 2383.26 |  | 0 | -59.82 | 2383.26 | 2383.26 |  | 2383.26 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 27383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 0 | 0 | 9533.22 | 9533.22 | 7149.96 | 44066.08 | 82.21%
Oracle Software and Maintenance (FP005) |  |  |  | 1835036.097 |  | 27839.9317 | 0 | 2 | 0 | 27839.9317 | 0 | 2 | 0 | 27839.9317 | 11802.05 | 2 | 0 | -71717.745 | 395992.6887 | 0 | 2 | 11802.05 | 52855.8402 | 0 | 0 | 27839.9317 | 0 | 0 | 395992.6887 | 0 | 0 | 52855.8402 | 0 | 0 | 27839.9317 | 0 | 0 | 395992.6887 | 0 | 0 | 52855.8402 | 0 | 0 | 421008.5972 | 0 | 0 | 0 | 0 | 407794.7387 | 11802.05 | 11802.05 | 1823234.047 | 99.36%
Project Administration |  |  |  | 210000 |  | 22096.33 | 3269.34 | 2 | 3269.34 | 14735.33 | 15871.21 | 3 | 15871.21 | 87505.33 | 8724.08 | 2 | 202.51 | -96472.36 | 44898.5728 | 15975.159 | 2 | 27771.38 | 12488.0078 | 0 | 0 | 7778.0078 | 0 | 0 | 69635.7428 | 0 | 0 | 7998.0078 | 0 | 0 | 17278.0078 | 0 | 0 | 7503.0078 | 0 | 0 | 7278.0078 | 0 | 0 | 7278.0078 | 0 | 0 | 0 | 0 | 72763.2028 | 43839.789 | 47114.44 | 166160.211 | 79.12%
Support Services |  |  |  | 3048844 |  | 159536 | 149537 | 1 | 0 | 180200 | 150249.5 | 1 | 100297 | 180200 | 136177.5 | 1 | 149049.5 | -83972 | 180200 | 144268.5 | 1 | 90197.5 | 222536 | 0 | 0 | 229592 | 0 | 0 | 355592 | 0 | 0 | 312800 | 0 | 0 | 328040 | 0 | 0 | 343280 | 0 | 0 | 328040 | 0 | 0 | 312800 | 0 | 0 | 0 | 0 | 616164 | 580232.5 | 339544 | 2468611.5 | 80.97%
QA Support Services |  |  |  | 1016486.5 |  | 82192 | 78528 |  | 0 | 82192 | 80184 |  | 61984 | 74720 | 65742.5 | 1 | 50448 | -14649.5 | 85928 | 84972 |  | 95382.5 | 67248 | 0 | 0 | 78456 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 0 | 0 | 310382.5 | 309426.5 | 207814.5 | 707060 | 69.56%
IT Service Management Implementation and Software (100777) | 1304572 | 1304572 | 0 | 880022.38 | 1117873.65 | 38576.48 | 0 |  | 0 | 963.52 | 37612.96 |  | 37612.96 | 20124.28 | 0 |  | 0 | -22051.32 | 149298.91 | 149085.39 |  | 750 | 3333.09 | 0 | 0 | 16139.54 | 0 | 0 | 963.52 | 0 | 0 | 668820.28 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 0 | 0 | 186911.87 | 186698.35 | 38362.96 | 693324.03 | 78.78%
ITSM Implementation and Administrative Support |  |  |  | 203493.94 |  | 37612.96 | 0 | 2 | 0 | 0 | 37612.96 | 3 | 37612.96 | 19160.76 | 0 | 2 | 0 | -19160.76 | 148335.39 | 148335.39 |  | 0 | 2369.57 | 0 | 0 | 15176.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185948.35 | 185948.35 | 37612.96 | 17545.59 | 8.622%
ITSM Software |  |  |  | 676528.44 |  | 963.52 | 0 | 2 | 0 | 963.52 | 0 | 2 | 0 | 963.52 | 0 | 2 | 0 | -2890.56 | 963.52 | 750 |  | 750 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 668820.28 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 0 | 0 | 963.52 | 750 | 750 | 675778.44 | 99.89%
Contingency (100819) | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Salaries & Benefits (010000) | 10146991 | 10146991 | 0 | 9657955.11 | 7112767.39 | 823871.84 | 697273.25 |  | 697273.25 | 823871.83 | 777393.67 |  | 777393.67 | 823871.83 | 768441.69 |  | 768441.69 | -228506.89 | 823871.84 | 791115 |  | 791115 | 823871.83 | 0 | 0 | 823871.83 | 0 | 0 | 823871.84 | 0 | 0 | 823871.83 | 0 | 0 | 823871.83 | 0 | 0 | 823871.84 | 0 | 0 | 823871.83 | 0 | 0 | 823871.83 | 0 | 0 | 0 | 0 | 3066980.45 | 3034223.61 | 3034223.61 | 6623731.5 | 68.58%
Risk Management Insurance (103241) | 13957 | 13957 | 0 | 13957 | 0 | 7978 | 0 |  | 0 | 0 | 13957 | 5 | 13957 | 0 | 0 |  | 0 | 5979 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13957 | 13957 | 13957 | 0 | 0%
DMS HR Transfer (107040) | 24000 | 24000 | 0 | 24000 | 24000 | 6152.25 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -6152.25 | 12000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 24000 | 100%
Totals | 60870881 | 28826947 | 32043934 | 56502038.437 | 18734589.261 | 4600582.2717 | 4451732.21 |  | 4223667.21 | 1863703.0517 | 1809148.78 |  | 1740996.28 | 1948161.8117 | 1724768.26 |  | 1699638.88 | -426797.885 | 6063482.4514 | 2106708.489 |  | 1938310.87 | 3116213.2079 | 0 | 0 | 3917557.7494 | 0 | 0 | 7691748.2314 | 0 | 0 | 6202626.3979 | 0 | 0 | 4034273.7294 | 0 | 0 | 4231522.1264 | 0 | 0 | 5628346.2679 | 0 | 0 | 7630619.0249 | 0 | 0 | 0 | 0 | 14049131.7014 | 10092357.739 | 9602613.24 | 46409680.698 | 82.14%
Running Totals | [5 empty] | 4600582.2717 | 4451732.21 |  | 4223667.21 | 6464285.3233 | 6260880.99 |  | 5964663.49 | 8412447.135 | 7985649.25 |  | 7664302.37 | 7985649.25 | 14049131.7014 | 10092357.739 |  | 9602613.24 | 17165344.9094 | 10092357.739 | 9602613.24 | 21082902.6588 | 10092357.739 | 9602613.24 | 28774650.8903 | 10092357.739 | 9602613.24 | 34977277.2882 | 10092357.739 | 9602613.24 | 39011551.0177 | 10092357.739 | 9602613.24 | 43243073.1441 | 10092357.739 | 9602613.24 | 48871419.4121 | 10092357.739 | 9602613.24 | 56502038.437 | 10092357.739 | 9602613.24 |  | 9602613.24
Monthly Total Incurred/Total Projected | [5 empty] | 96.76% |  |  |  | 97.07% |  |  |  | 88.53% |  |  |  |  | 34.74% |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Monthly Total Incurred/Total Projected (Variance) | [5 empty] | -3.235% |  |  |  | -2.927% |  |  |  | -11.47% |  |  |  |  | -65.26% |  |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [5 empty] | 96.76% |  |  |  | 96.85% |  |  |  | 94.93% |  |  |  |  | 71.84% |  |  |  | 58.79% |  |  | 47.87% |  |  | 35.07% |  |  | 28.85% |  |  | 25.87% |  |  | 23.34% |  |  | 20.65% |  |  | 17.86%
FYTD Total Incurred/Total Projected (Variance) | [5 empty] | -3.235% |  |  |  | -3.147% |  |  |  | -5.073% |  |  |  |  | -28.16% |  |  |  | -41.21% |  |  | -52.13% |  |  | -64.93% |  |  | -71.15% |  |  | -74.13% |  |  | -76.66% |  |  | -79.35% |  |  | -82.14%

## Footnotes
Department of Financial Services
FY 2024 - 2025 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5 | Incurred amounts were greater than anticipated due to an additional appropriation to the category.
6

## SSI Detail
|  |  |  | July 2024 |  |  | August 2024 |  |  | September 2024 |  |  | Q2 Baseline Adjustment | October 2024 |  |  | November 2024 |  |  | December 2024 |  |  | January 2025 |  |  | February 2025 |  |  | March 2025 |  |  | April 2025 |  |  | May 2025 |  |  | June 2025 |  |  | CF 2024-25
|  | Description | Total Deliverable Cost FY 24-25 | July Projection | July Accepted / Approved | July Paid | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid |  | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Projection
Department of Financial Services
Florida PALM FY 2024 - 2025 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
D648 | Completion of Build Segment II | Implementation | 2250000 | 2250000 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000
D649 | Completion of Build Segment III | Implementation | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000
D650 | Completion of Solution Design (Requirements) DW/BI | Implementation | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
D651 | Completion of Mock Conversion I | Implementation | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D652 | Completion of System Test Segment I | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D653 | Completion of Build Segment I DW/BI | Implementation | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D654 | Completion of Build Segment IV | Implementation | 2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D655 | Completion of Mock Conversion II (System Test Environment) | Implementation | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D656 | Completion of System Test Segment II | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D657 | Completion of Mock Conversion III (UAT) | Implementation | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D658 | Develop the Deployment and Contingency Plan | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D659 | Completion of Build Segment II DW/BI | Implementation | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D660 | Payroll Parallel Testing Plan | Implementation | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D661 | Completion of System Test DW/BI | Implementation | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D662 | Completion of Dress Rehearsal (Mock Conversion IV) | Implementation | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D663 | Completion of Interface Testing Segment I | Implementation | 2081700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2081700 | 0 | 0 | 0 | 0 | 0
D664 | Development of the Hypercare Support Plan | Implementation | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000 | 0 | 0 | 0 | 0 | 0
D665 | Updated Post-Implementation Support Plan | Implementation | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000 | 0 | 0 | 0 | 0 | 0
D666 | Support of UAT Segment I | Implementation | 2236500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2236500 | 0 | 0 | 0 | 0 | 0
D696 | Completion of System Test Segment III | Implementation | 1378840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1378840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 415692 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 138564
Prod Supp | AM Services | Prod Supp | 6849800 | 554500 | 554500 | 554500 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 0 | 572300 | 572300 | 572300 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 0 | 0 | 2271400
Prod Supp | IM Services | Prod Supp | 1406700 | 109900 | 109900 | 109900 | 113800 | 113800 | 113800 | 113800 | 113800 | 113800 | 0 | 113800 | 113800 | 113800 | 113800 | 0 | 0 | 113800 | 0 | 0 | 113800 | 0 | 0 | 122800 | 0 | 0 | 122800 | 0 | 0 | 122800 | 0 | 0 | 122800 | 0 | 0 | 122800 | 0 | 0 | 0 | 0 | 451300
Prod Supp | Oracle OCI Costs | Prod Supp | 749650 | 187412 | 187412 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187412 | 187412 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374824
Prod Supp | Support Tools Maintenance | Prod Supp | 46381 | 46381 | 46381 | 46381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46381
Prod Supp | Support Tools Purchase | Prod Supp | 311780 | 203556 | 311780 | 311780 | 0 | 0 | 0 | 0 | 0 | 0 | 108224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311780
Prod Supp | Solution Software Support | Prod Supp | 32790 | 32790 | 15371 | 15371 | 0 | 0 | 0 | 0 | 0 | 0 | -17419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15371
| Implementation Total: |  |  | 2250000 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450000 | 0 | 0 | 1200000 | 0 | 0 | 2000000 | 0 | 0 | 5000000 | 0 | 0 | 3500000 | 0 | 0 | 2000000 | 0 | 0 | 1630000 | 0 | 0 | 3578840 | 0 | 0 | 5228200 | 0 | 0 | 0 | 0 | 5700000
| Production Support Facilities Total: |  |  | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 138564
| Production Support (No Facilities) Total: |  |  | 1134539 | 1225344 | 1225344 | 686100 | 686100 | 686100 | 686100 | 686100 | 686100 |  | 873512 | 873512 | 873512 | 686100 | 0 | 0 | 686100 | 0 | 0 | 873512 | 0 | 0 | 695100 | 0 | 0 | 695100 | 0 | 0 | 882514 | 0 | 0 | 695100 | 0 | 0 | 695100 | 0 | 0 | 0 | 0 | 3471056
Monthly Totals |  |  | 39649833 | 3419180 | 3509985 | 3509985 | 720741 | 720741 | 720741 | 720741 | 720741 | 720741 | 90805 | 4358153 | 908153 | 908153 | 1920741 | 0 | 0 | 2720741 | 0 | 0 | 5908153 | 0 | 0 | 4229741 | 0 | 0 | 2729741 | 0 | 0 | 2547155 | 0 | 0 | 4308581 | 0 | 0 | 5957941 | 0 | 0 | 0 | 0 | 9309620
| Projected YTD |  |  | 3419180 |  |  | 4139921 |  |  | 4860662 |  |  |  | 9309620 |  |  | 11230361 |  |  | 13951102 |  |  | 19859255 |  |  | 24088996 |  |  | 26818737 |  |  | 29365892 |  |  | 33674473 |  |  | 39632414
| Incurred YTD |  |  |  | 3509985 |  |  | 4230726 |  |  | 4951467 |  |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  | 5859620
| Paid YTD |  |  |  |  | 3509985 |  |  | 4230726 |  |  | 4951467 | 4951467 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  |  | 5859620 |  | 5859620

## Oracle Summary
Department of Financial Services
Florida PALM FY 2024 - 2025 Oracle Summary FYTD
| Quantity/Months | Quote |  |  | July 2024 |  |  |  | August 2024 |  |  |  | September 2024 |  |  |  | Q2 Baseline Adjustment | October 2024 |  |  |  | November 2024 |  |  |  | December 2024 |  |  |  | January 2025 |  |  |  | February 2025 |  |  |  | March 2025 |  |  |  | April 2025 |  |  |  | May 2025 |  |  |  | June 2025 |  |  |  | FY 2024-25 CF |  | Total
Program |  | Tech Support | Total Purchase/ Subscription | Total Projection | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | CF Incurred | CF Paid | Total Projected | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support |  | 1518401.278 |  | 1518401.278 | 0 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 |  | 368152.757 | 0 | #REF! | 0 | 11447.5625 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 368152.757 | 0 | #REF! | 0 | 11447.5625 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 368152.757 | 0 | #REF! | 0 | 11447.5625 | 0 | #REF! | 0 | 379600.3195 | 0 | #REF! | 0 | 0 | 0 | 1518401.278 | 407794.7387 | 11802.05 | 11802.05
Assignment |  | 1518401.278 | 0 | 1518401.278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 368152.757 | 0 | 0 | 0 | 11447.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368152.757 | 0 | 0 | 0 | 11447.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368152.757 | 0 | 0 | 0 | 11447.5625 | 0 | 0 | 0 | 379600.3195 | 0 | 0 | 0 | 0 | 0 | 1518401.278 | 368152.757 | 0 | 0
Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 2 | 8525.418 | 0 | 8525.418 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 2131.3545 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2131.3545 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2131.3545 | 0 |  | 0 | 0 | 0 |  | 0 | 2131.3545 | 0 |  | 0 | 0 | 0 | 8525.418 | 2131.3545 | 0 | 0
Oracle Business Intelligence (Analytics) Server Administrator | 4 | 1479.59 | 0 | 1479.59 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 | 1479.59 | 369.8975 | 0 | 0
Oracle Business Intelligence Management Pack | 4 | 2933.77 | 0 | 2933.77 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 | 2933.77 | 733.4425 | 0 | 0
Oracle Business Intelligence Suite Foundation Edition | 4 | 76549.07 | 0 | 76549.07 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 | 76549.07 | 19137.2675 | 0 | 0
Oracle Data Integrator Enterprise Edition | 20 | 38274.54 | 0 | 38274.54 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 | 38274.54 | 9568.635 | 0 | 0
Oracle Data Visualization | 4 | 25517.06 | 0 | 25517.06 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 | 25517.06 | 6379.265 | 0 | 0
Oracle Financial Analytics Fusion Edition (DW/BI) | 100 | 14800.11 | 0 | 14800.11 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 | 14800.11 | 3700.0275 | 0 | 0
Oracle Managed File Transfer | 12 | 21373.31 | 0 | 21373.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 | 21373.31 | 5343.3275 | 0 | 0
Oracle Management Pack for Oracle Data Integrator | 16 | 7042.33 | 0 | 7042.33 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 | 7042.33 | 1760.5825 | 0 | 0
Oracle SOA Management Pack Enterprise Edition | 14 | 20670.71 | 0 | 20670.71 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 | 20670.71 | 5167.6775 | 0 | 0
Oracle SOA Suite for Oracle Middleware | 14 | 47542.18 | 0 | 47542.18 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 | 47542.18 | 11885.545 | 0 | 0
Oracle WebLogic Server Management Pack Enterprise Edition | 26 | 18471 | 0 | 18471 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 | 18471 | 4617.75 | 0 | 0
Oracle WebLogic Suite | 26 | 69266.8 | 0 | 69266.8 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 | 69266.8 | 17316.7 | 0 | 0
PeopleSoft Enterprise Contracts | 92083 | 55673.81 | 0 | 55673.81 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13214.6675 | 0 |  | 0 | 703.785 | 0 |  | 0 | 0 | 0 |  | 0 | 13214.6675 | 0 |  | 0 | 703.785 | 0 |  | 0 | 0 | 0 |  | 0 | 13214.6675 | 0 |  | 0 | 703.785 | 0 |  | 0 | 13918.4525 | 0 |  | 0 | 0 | 0 | 55673.81 | 13214.6675 | 0 | 0
PeopleSoft Enterprise eSettlements | 92083 | 36536.19 | 0 | 36536.19 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 8672.185 | 0 |  | 0 | 461.8625 | 0 |  | 0 | 0 | 0 |  | 0 | 8672.185 | 0 |  | 0 | 461.8625 | 0 |  | 0 | 0 | 0 |  | 0 | 8672.185 | 0 |  | 0 | 461.8625 | 0 |  | 0 | 9134.0475 | 0 |  | 0 | 0 | 0 | 36536.19 | 8672.185 | 0 | 0
PeopleSoft Enterprise Expenses | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 73940.87 | 17550.4975 | 0 | 0
PeopleSoft Enterprise Financials | 92083 | 398410.84 | 0 | 398410.84 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 94566.2225 | 0 |  | 0 | 5036.4875 | 0 |  | 0 | 0 | 0 |  | 0 | 94566.2225 | 0 |  | 0 | 5036.4875 | 0 |  | 0 | 0 | 0 |  | 0 | 94566.2225 | 0 |  | 0 | 5036.4875 | 0 |  | 0 | 99602.71 | 0 |  | 0 | 0 | 0 | 398410.84 | 94566.2225 | 0 | 0
PeopleSoft Enterprise Grants | 92083 | 52193.31 | 0 | 52193.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 12388.525 | 0 |  | 0 | 659.8025 | 0 |  | 0 | 0 | 0 |  | 0 | 12388.525 | 0 |  | 0 | 659.8025 | 0 |  | 0 | 0 | 0 |  | 0 | 12388.525 | 0 |  | 0 | 659.8025 | 0 |  | 0 | 13048.3275 | 0 |  | 0 | 0 | 0 | 52193.31 | 12388.525 | 0 | 0
PeopleSoft Enterprise Human Resources | 114800 | 47938.36 | 0 | 47938.36 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 | 47938.36 | 11984.59 | 0 | 0
PeopleSoft Enterprise Payroll | 114800 | 58302.96 | 0 | 58302.96 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 | 58302.96 | 14575.74 | 0 | 0
PeopleSoft Enterprise Project Costing | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 73940.87 | 17550.4975 | 0 | 0
PeopleSoft Enterprise Purchasing | 92083 | 81770.5 | 0 | 81770.5 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 19408.935 | 0 |  | 0 | 1033.69 | 0 |  | 0 | 0 | 0 |  | 0 | 19408.935 | 0 |  | 0 | 1033.69 | 0 |  | 0 | 0 | 0 |  | 0 | 19408.935 | 0 |  | 0 | 1033.69 | 0 |  | 0 | 20442.625 | 0 |  | 0 | 0 | 0 | 81770.5 | 19408.935 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 73940.87 | 17550.4975 | 0 | 0
PeopleSoft Enterprise Treasury | 92083 | 59152.27 | 0 | 59152.27 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14040.2925 | 0 |  | 0 | 747.775 | 0 |  | 0 | 0 | 0 |  | 0 | 14040.2925 | 0 |  | 0 | 747.775 | 0 |  | 0 | 0 | 0 |  | 0 | 14040.2925 | 0 |  | 0 | 747.775 | 0 |  | 0 | 14788.0675 | 0 |  | 0 | 0 | 0 | 59152.27 | 14040.2925 | 0 | 0
PeopleSoft Enterprise Time and Labor | 114800 | 154154.54 | 0 | 154154.54 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 38538.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 38538.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 38538.635 | 0 |  | 0 | 0 | 0 |  | 0 | 38538.635 | 0 |  | 0 | 0 | 0 | 154154.54 | 38538.635 | 0 | 0
Analytics |  | 54273.384 |  | 54273.384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13568.346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13568.346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13568.346 | 0 | 0 | 0 | 13568.346 | 0 | 0 | 0 | 0 | 0 | 54273.384 | 0 | 0 | 0
HR Analytics (DW/BI) | 100 | 45227.82 | 0 | 45227.82 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 11306.955 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11306.955 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11306.955 | 0 |  | 0 | 11306.955 | 0 |  | 0 | 0 | 0 | 45227.82 | 0 | 0 | 0
Project Analytics (DW/BI) | 20 | 9045.564 | 0 | 9045.564 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 2261.391 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2261.391 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2261.391 | 0 |  | 0 | 2261.391 | 0 |  | 0 | 0 | 0 | 9045.564 | 0 | 0 | 0
OCI |  | 0 |  | 334079.18 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 11802.05 | 0 | 0 | -71717.745 | 27839.9317 | 0 | 0 | 11802.05 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 0 | 0 | 334079.18 | 39641.9817 | 11802.05 | 11802.05
OAC (DW/BI) - DEV: $53,218.69 - Test : $63,779.29 - DR : $93,780.73 - Production : $123,300.47 | 4 | 0 | 334079.18 | 334079.18 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 11802.05 |  | 0 | -71717.745 | 27839.9317 | 0 |  | 11802.05 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 0 | 0 | 334079.18 | 39641.9817 | 11802.05 | 11802.05
New License Purchase and Tech Support |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Financials | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Treasury | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Expenses | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise eSettlements | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Contracts | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Grants | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Project Costing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Purchasing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Human Resources | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Payroll | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Time and Labor | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 1572674.662 |  | 1906753.842 | 27839.9317 | 0 | #REF! | 0 | 27839.9317 | 0 | #REF! | 0 | 27839.9317 | 11802.05 | #REF! | 0 | -71717.745 | 395992.6887 | 0 | #REF! | 11802.05 | 52855.8402 | 0 | #REF! | 0 | 27839.9317 | 0 | #REF! | 0 | 395992.6887 | 0 | #REF! | 0 | 52855.8402 | 0 | #REF! | 0 | 27839.9317 | 0 | #REF! | 0 | 395992.6887 | 0 | #REF! | 0 | 52855.8402 | 0 | #REF! | 0 | 421008.5972 | 0 | #REF! | 0 | 0 | 0 | 1906753.842 | 407794.7387 | 11802.05 | 23604.1
Projected FYTD |  |  |  |  | 27839.9317 |  |  |  | 55679.8633 |  |  |  | 83519.795 |  |  |  |  | 407794.7387 |  |  |  | 460650.5788 |  |  |  | 488490.5105 |  |  |  | 884483.1992 |  |  |  | 937339.0393 |  |  |  | 965178.971 |  |  |  | 1361171.6597 |  |  |  | 1414027.4998 |  |  |  | 1835036.097
Incurred FYTD | [5 empty] | 0 |  |  |  | 0 |  |  |  | 11802.05 |  |  | 11802.05 |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05
Paid FYTD | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05 |  |  |  | 11802.05