## Monthly Summary
Department of Financial Services
Florida PALM FY 2025 - 2026 Spend Plan Summary FYTD
As of March 31, 2026
Annual
| TRUE | TRUE | TRUE | TRUE | TRUE |  | ERROR | July 2025 |  |  |  | August 2025 |  |  |  | September 2025 |  |  |  | Q2 Baseline Adjustment | October 2025 |  |  |  | November 2025 |  |  |  | A13 Baseline Adjustment | December 2025 |  |  |  | January 2026 |  |  |  | Q3 Baseline Adjustment | February 2026 |  |  |  | March 2026 |  |  |  | April 2026 |  |  | May 2026 |  |  | June 2026 |  |  | CF 2025-26 |  | Fiscal Year to Date
Category (Cost Area / Contract) | 10130387 | 45930662 | 56061049 | 42379233 | 13681816 | 42347672.9137 | 15218761.19 | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
| FY 24-25 Revert & Appropriated | FY 25-26 GAA Appropriated | FY 25-26 Total Appropriation | Released | Unreleased | Projected | Release Remaining | [12 empty] | Q1 Baseline Adjustment | [8 empty] | Q1 Baseline Adjustment | [8 empty] | Q1 Baseline Adjustment
FLAIR System Replacement (100781) | 10130387 | 45930662 | 56061049 | 42379233 | 13681816 | 42347672.9137 | 15218761.19 | 4631851.0633 | 2445591.29 |  | 1335444.96 | 6967995.1871 | 3224806.19 |  | 1127783.64 | 2639834.5033 | 2227550.22 |  | 4239157.48 | -6341733.0537 | 6296159.5453 | 6059775.695 |  | 4184106.54 | 4692752.3639 | 1093743.965 |  | 2473576.6 | -3835392.2492 | 2652110.5243 | 2418941.65 |  | 1755552.02 | 3404552.7586 | 4937063.99 |  | 6553724.33 | 1297550.6921 | 4033261.5707 | 3971178.86 |  | 851954.37 | 1767062.8307 | 1224498.47 |  | 4639171.87 | 2582712.2684 | 0 | 0 | 5866180.6407 | 0 | 0 | 5692774.2684 | 0 | 0 | #REF! | #REF! | 28206005.7363 | 27600522.025 | 27160471.81 | 14747150.8887 | 34.82%
SSI Implementation Services (FP004) | [5 empty] | 20780583 |  | 2000000 | 0 |  | 0 | 5338840 | 2000000 | 2 | 0 | 994983 | 994983 |  | 2994983 | -5338840 | 4000000 | 3819462 |  | 1909731 | 3420540 | 0 |  | 1909731 | -3601078 | 1338840 | 1248571 |  | 0 | 1500000 | 3191000 | 3 | 4439571 | 1600731 | 2081700 | 2081700 |  | 0 | 0 | 0 |  | 2081700 | 0 | 0 | 0 | 3863167 | 0 | 0 | 3581700 | 0 | 0 | 0 | 0 | 13335716 | 13335716 | 13335716 | 7444867 | 35.83%
Facilities and Maintenance (FP004) | [5 empty] | 415692 |  | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 311769 | 311769 | 311769 | 103923 | 25%
Production Support (FP004) | [5 empty] | 9935896 |  | 1534630 | 1521776 |  | 830806 | 713885 | 713885 |  | 690970 | 713885 | 713885 |  | 713885 | -12854 | 907013 | 910013 |  | 1623898 | 710885 | 707885 |  | 0 | 0 | 710885 | 710885 |  | 707885 | 907013 | 907013 |  | 1617898 | 0 | 710885 | 710885 |  | 0 | 710885 | 710885 |  | 1421770 | 907014 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 0 | 0 | 7607112 | 7607112 | 7607112 | 2328784 | 23.44%
Additional Facilities | [5 empty] | 241100.58 |  | 19961.81 | 19961.81 |  | 0 | 19961.81 | 19961.81 |  | 39923.62 | 19961.81 | 19961.81 |  | 19961.81 | 0 | 19961.81 | 19961.81 |  | 8989 | 19961.81 | 19961.81 |  | 8989 | 0 | 19961.81 | 19961.81 |  | 41907.43 | 19961.81 | 19961.81 |  | 19961.81 | 0 | 20143.61 | 20143.61 |  | 20143.61 | 20143.61 | 20143.61 |  | 20143.61 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 0 | 0 | 180019.89 | 180019.89 | 180019.89 | 61080.69 | 25.33%
Production Support Administration | [5 empty] | 785579.68 |  | 41971.78 | 1177 | 2 | 1177 | 7971.78 | 5355.02 |  | 5355.02 | 7971.78 | 2971.76 | 2 | 2971.76 | -48411.56 | 41971.78 | 36872.39 |  | 36872.39 | 7971.78 | 2971.76 |  | 0 | -10099.41 | 7971.78 | 3349.54 | 2 | 6321.3 | 34971.78 | 7998.21 | 2 | 7998.21 | -31595.81 | 692996.88 | 687597.25 |  | 188.89 | 7971.78 | 3938.04 | 2 | 691346.4 | 7971.78 | 0 | 0 | 7971.78 | 0 | 0 | 7971.78 | 0 | 0 | 0 | 0 | 761664.34 | 752230.97 | 752230.97 | 33348.71 | 4.245%
Oracle Software and Maintenance (FP005) | [5 empty] | 2062068.0687 |  | 44165.81 | 17097.05 | 2 | 17097.05 | 394048.7637 | 24821.06 | 2 | 1217.22 | 33788.58 | 20602.24 | 2 | 23603.84 | -409482.8037 | 714227.1064 | 724762.52 |  | 20602.24 | 72151.865 | 35794.56 | 6 | 408364.33 | -25821.8914 | 33788.58 | 8502.33 | 2 | 360695.08 | 380106.3844 | 331407.46 | 6 | 18571.22 | -73985.1744 | 69530.3467 | 56705.27 |  | 369541.51 | 27835.9167 | 39523.25 | 3 | 25450.83 | 380106.3844 | 0 | 0 | 41501.8167 | 0 | 0 | 380106.3844 | 0 | 0 | 0 | 0 | 1260353.4833 | 1259215.74 | 1245143.32 | 802852.3287 | 38.93%
Project Administration | [5 empty] | 293888.04 |  | 30988.5233 | 19025.51 | 2 | 19025.51 | 30724.2733 | 18534.26 | 2 | 18534.26 | 80067.4133 | 8503.03 | 2 | 8503.03 | -95717.41 | 113869.5689 | 88298.53 | 2 | 88298.53 | 36175.7089 | 7979.94 | 2 | 7097.27 | -53766.8078 | 54606.4343 | 10779.9 | 2 | 11662.57 | 16922.8643 | 18640.87 | 3 | 18640.87 | -42108.5286 | 28239.534 | 5399.13 | 2 | 4776.47 | 26241.604 | 1595.78 | 2 | 2218.44 | 25813.754 | 0 | 0 | 21690.554 | 0 | 0 | 20140.554 | 0 | 0 | 0 | 0 | 226243.178 | 178756.95 | 178756.95 | 115131.09 | 39.18%
Florida PALM-UAT | [5 empty] | 2534817.3 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 275000 | 0 | 2 | 0 | -275000 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 59520 | 59520 |  | 0 | 0 | 0 | 0 |  | 59520 | 506292 | 0 | 2 | 0 | 758173.2 | 0 | 0 | 729854.7 | 0 | 0 | 480977.4 | 0 | 0 | #REF! | #REF! | 565812 | 59520 | 59520 | 2475297.3 | 97.65%
Support Services | [5 empty] | 3654440.245 |  | 585621.14 | 503522.92 | 5,1 | 252332.4 | 288650.56 | 272608.04 |  | 223318.52 | 333631.92 | 304834.38 |  | 300480.04 | -126938.28 | 345795.28 | 310004.445 | 1 | 304834.38 | 287225.2 | 202661.895 | 1 | 104754 | -120354.14 | 306391.92 | 266265.07 | 1 | 407375.64 | 306391.92 | 256585.64 | 1 | 267912.22 | -91724.795 | 277525.2 | 262605.6 |  | 252846.89 | 303691.92 | 293483.79 |  | 264799.59 | 319271.92 | 0 | 0 | 312628.56 | 0 | 0 | 326631.92 | 0 | 0 | 0 | 0 | 2695907.845 | 2669943.475 | 2378653.68 | 984496.77 | 26.94%
QA Support Services | [5 empty] | 1643608 |  | 339871 | 328390 |  | 180366 | 139272 | 135000 |  | 113824 | 145904 | 127168 | 1 | 140128 | -34489 | 118680 | 115760 |  | 156240 | 103200 | 81848 | 1 | 0 | -24272 | 145024 | 115986 | 1 | 185064 | 145024 | 110296 | 1 | 128530 | -63766 | 117600 | 111502 |  | 110296 | 129360 | 120288 |  | 97102 | 129360 | 0 | 0 | 123480 | 0 | 0 | 129360 | 0 | 0 | #REF! | #REF! | 1261408 | 1246238 | 1111550 | 397370 | 24.18%
Florida PALM Unprojected Project Reserves | [5 empty] | 0
Contingency (100819) | 3000000 |  | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Salaries & Benefits (010000) IRTF |  | 11281661 | 11281661 | 11281661 | 0 | 10316043.0933 | 3835254.45 | 916309.9167 | 849765.77 |  | 849765.77 | 916309.9167 | 810184.44 |  | 810184.44 | 916309.9167 | 826946.02 |  | 826946.02 | -262033.52 | 916309.9167 | 784148.4 |  | 784148.4 | 916309.9167 | 793281.18 |  | 793281.18 | -255190.2533 | 916309.9167 | 810094.26 |  | 810094.26 | 916309.9167 | 860073.44 |  | 860073.44 | -162452.1333 | 916309.9167 | 857064.79 |  | 857064.79 | 916309.9167 | 854848.25 |  | 854848.25 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 0 | 0 | 7567113.3433 | 7446406.55 | 7446406.55 | 2869636.5433 | 27.82%
Salaries & Benefits (010000) GRF |  | 1938303 | 1938303 | 1938303 | 0 | 1052234.18 | 1594581.78 | 157482 | 33013 |  | 33013 | 157482 | 33013.01 |  | 33013.01 | 157482 | 33013.01 |  | 33013.01 | -373406.98 | 157482 | 68345.15 |  | 68345.15 | 157482 | 33013.01 |  | 33013.01 | -213605.84 | 157482 | 34284.01 |  | 34284.01 | 157482 | 30142.99 |  | 30142.99 | -250537 | 157482 | 27384.51 |  | 27384.51 | 157482 | 51512.53 |  | 51512.53 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 |  |  | 579788.18 | 343721.22 | 343721.22 | 708512.96 | 67.33%
Data Processing Services (210000) |  | 0 | 0 | 0 | 0 | 0 | 0 | 112138 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -112138 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Risk Management Insurance (103241) |  | 14572 | 14572 | 14572 | 0 | 14572 | 0 | 13957 | 0 |  | 0 | 0 | 0 |  | 0 | 615 | 14572 | 3 | 14572 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14572 | 14572 | 14572 | 0 | 0%
DMS HR Transfer (107040) IRTF |  | 24081 | 24081 | 24081 | 0 | 24081 | 6020.25 | 6000 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -6000 | 12040.5 | 12040.5 |  | 12040.5 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 6020.25 | 6020.25 |  | 6020.25 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6020.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18060.75 | 18060.75 | 18060.75 | 6020.25 | 25%
DMS HR Transfer (107040) GRF |  | 3528 | 3528 | 3528 |  | 3528 | 882 | 880 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -880 | 1764 | 1764 |  | 1764 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 882 | 882 |  | 882 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2646 | 2646 | 2646 | 882 | 25%
Totals | 13130387 | 59192807 | 72323194 | 55641378 | 16681816 | 53758131.187 | 20655499.67 | 5838617.98 | 3328370.06 |  | 2218223.73 | 8041787.1037 | 4068003.64 |  | 1970981.09 | 3714241.42 | 3102081.25 |  | 5113688.51 | -7096191.5538 | 7383755.962 | 6926073.745 |  | 5050404.59 | 5766544.2806 | 1920038.155 |  | 3299870.79 | -4304188.3426 | 3725902.441 | 3263319.92 |  | 2599930.29 | 4485246.9253 | 5834182.67 |  | 7450843.01 | 884561.5587 | 5107053.4873 | 4855628.16 |  | 1736403.67 | 2840854.7473 | 2130859.25 |  | 5545532.65 | 3663406.435 | 0 | 0 | 6939972.5573 | 0 | 0 | 6766566.185 | 0 | 0 | #REF! | #REF! | 36388186.0097 | 35425928.545 | 34985878.33 | 18332202.642 | 100%
Running Totals | [7 empty] | 5838617.98 | 3328370.06 |  | 2218223.73 | 13880405.0838 | 7396373.7 |  | 4189204.82 | 17594646.5038 | 10498454.95 |  | 9302893.33 | 10498454.95 | 17882210.912 | 17424528.695 |  | 14353297.92 | 23648755.1926 | 19344566.85 |  | 17653168.71 | 19344566.85 | 23070469.291 | 22607886.77 |  | 20253099 | 27555716.2163 | 28442069.44 |  | 27703942.01 | 28440277.775 | 33547331.2623 | 33297697.6 |  | 29440345.68 | 36388186.0097 | 35428556.85 |  | 34985878.33 | 40051592.4447 | 35428556.85 | 34985878.33 | 46991565.002 | 35428556.85 | 34985878.33 | 53758131.187 | 35428556.85 | 34985878.33 |  | #REF! |  |  | Total Incurred/Total Projected FYTD |  | 97.36%
Monthly Total Incurred/Total Projected | [7 empty] | 57.01% |  |  |  | 50.59% |  |  |  | 83.52% |  |  |  |  | 93.8% |  |  |  | 33.3% |  |  |  |  | 87.58% |  |  |  | 130.1% |  |  |  |  | 95.08% |  |  |  | 75.01% |  |  |  | 0% |  |  | 0% |  |  | 0% | [6 empty] | Total Paid/Total Projected FYTD |  | 96.15%
Monthly Total Incurred/Total Projected (Variance) | [7 empty] | -42.99% |  |  |  | -49.41% |  |  |  | -16.48% |  |  |  |  | -6.199% |  |  |  | -66.7% |  |  |  |  | -12.42% |  |  |  | 30.07% |  |  |  |  | -4.923% |  |  |  | -24.99% |  |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [7 empty] | 57.01% |  |  |  | 53.29% |  |  |  | 59.67% |  |  |  |  | 97.44% |  |  |  | 81.8% |  |  |  |  | 97.99% |  |  |  | 103.2% |  |  |  |  | 99.26% |  |  |  | 97.36% |  |  |  | 88.46% |  |  | 75.39% |  |  | 65.9% | [6 empty] | Total Release/Total Appropriation |  | 76.93%
FYTD Total Incurred/Total Projected (Variance) | [7 empty] | -42.99% |  |  |  | -46.71% |  |  |  | -40.33% |  |  |  |  | -2.559% |  |  |  | -18.2% |  |  |  |  | -2.005% |  |  |  | 3.217% |  |  |  |  | -0.7441% |  |  |  | -2.637% |  |  |  | -11.54% |  |  | -24.61% |  |  | -34.1%
[60 empty] | Total Paid/Total Release |  | 62.88%
Reconciles to ALRR | No |  | Yes | Yes | Yes | [5 empty] | No |  |  |  | No |  |  |  | No |  |  |  |  | No |  |  |  | No |  |  |  |  | No |  |  |  | No |  |  |  |  | No |  |  |  | No |  |  | No |  |  | No |  |  | No |  | #REF!

## Footnotes
Department of Financial Services
FY 2025 - 2026 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5 | Contractor hours projected and incurred amounts were greater than anticipated due to June 2025 hours not being projected to be incurred in July 2025.
6 | Incurred amounts were less than anticipated due to the timing of planned purchases and a credit applied to invoice.

## SSI Detail
|  |  |  | July 2025 |  |  | August 2025 |  |  | September 2025 |  |  | Q2 Baseline Adjustment | October 2025 |  |  | November 2025 |  |  | A13 Baseline Adjustment | December 2025 |  |  | January 2026 |  |  | Q3 Baseline Adjustment | February 2026 |  |  | March 2026 |  |  | April 2026 |  |  | May 2026 |  |  | June 2026 |  |  | CF 2025-26
|  | Description | Total Deliverable Cost FY 25-26 | July Projection | July Accepted / Approved | July Paid | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid |  | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid |  | December Projection | December Accepted / Approved | December Paid | January Projection | January Accepted / Approved | January Paid |  | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Projection | Projection Remaining | Projected FYTD | Total Accepted / Approved | Projected FYTD Pending | Total Paid | Payment Pending
Department of Financial Services
Florida PALM FY 2025 - 2026 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
657 | Completion of Mock Conversion III (UAT) | Implementation | 2000000 |  |  |  | 2000000 | 2000000 |  |  |  | 2000000 | 0 | [6 empty] | 0 | [6 empty] | 0 | [15 empty] | 0 | 0 | 2000000 | 0 | 2000000 | 2000000 | 0 | 2000000 | 0
658 | Develop the Deployment and Contingency Plan | Implementation | 2000000 |  |  |  | 2000000 | [5 empty] | -2000000 | 2000000 | 1909731 | 1909731 |  |  |  | -90269 | [6 empty] | 0 | [15 empty] | 0 | 0 | 1909731 | 0 | 1909731 | 1909731 | 0 | 1909731 | 0
661 | Completion of System Test DW/BI | Implementation | 1338840 |  |  |  | 1338840 | [5 empty] | -1338840 |  |  |  | 1338840 |  |  | -1338840 | 1338840 | 1248571 |  |  |  | 1248571 | -90269 | [15 empty] | 0 | 0 | 1248571 | 0 | 0 | 1248571 | -1248571 | 1248571 | 0
662 | Completion of Mock Conversion IV | Implementation | 1500000 | [9 empty] | 0 | [6 empty] | 0 |  |  |  | 1500000 | 1500000 | 1500000 | 0 | [15 empty] | 0 | 0 | 1500000 | 0 | 0 | 1500000 | -1500000 | 1500000 | 0
663 | Completion of Interface Testing Segment I | Implementation | 2081700 | [9 empty] | 0 |  |  |  | 2081700 |  |  | -2081700 | [6 empty] | 0 | 2081700 | 2081700 |  |  |  | 2081700 | [9 empty] | 0 | 0 | 2081700 | 0 | 0 | 2081700 | -2081700 | 2081700 | 0
666 | Support of UAT Segment I | Implementation | 1691000 | [9 empty] | 0 | [6 empty] | 0 |  |  |  |  | 1691000 | 1691000 | 1691000 | [15 empty] | 0 | 0 | 1691000 | 0 | 0 | 1691000 | -1691000 | 1691000 | 0
667 | Completion of Mock Go-Lives (Dry Run #1) | Implementation | 1500000 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [12 empty] | 1500000 |  |  | 0 | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0
669 | Support of UAT Segment II | Implementation | 2063167 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [9 empty] | 2063167 | [5 empty] | 0 | 0 | 2063167 | 2063167 | 0 | 0 | 0 | 0 | 0
670 | Completion of Payroll Parallel Testing | Implementation | [10 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
671 | Completion of Interface Testing Segment II | Implementation | 2081700 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [12 empty] | 2081700 |  |  | 0 | 0 | 2081700 | 2081700 | 0 | 0 | 0 | 0 | 0
672 | Support of UAT Segment III | Implementation | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
673 | Completion of Mock Go-Lives (Dry Run #2) | Implementation | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
674 | Completion of Penetration Testing | Implementation | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
675 | Completion of Performance Testing | Implementation | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
676 | Completion of Disaster Recovery Testing | Implementation | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
677 | Completion of Mock Go-Lives (Dry Run #3) | Implementation | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
696 | Completion of System Test Segment III | Implementation | 2000000 | 2000000 | [8 empty] | -2000000 | 2000000 | 1909731 |  |  |  | 1909731 | -90269 | [6 empty] | 0 | [15 empty] | 0 | 0 | 1909731 | 0 | 1909731 | 1909731 | 0 | 1909731 | 0
697 | Completion of Employee Self-Service Build | Implementation | 994983 | [6 empty] | 994983 | 994983 | 994983 | 0 | [6 empty] | 0 | [6 empty] | 0 | [15 empty] | 0 | 0 | 994983 | 0 | 994983 | 994983 | 0 | 994983 | 0
709 | In-Person Support of UAT (NEW) | Implementation | 1800000 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [9 empty] | 1800000 | [5 empty] | 0 | 0 | 1800000 | 1800000 | 0 | 0 | 0 | 0 | 0
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 415692 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 |  |  | 34641 |  |  | 34641 |  |  | 0 | 0 | 415692 | 103923 | 173205 | 311769 | -138564 | 311769 | 0
Prod Supp | AM Services | Prod Supp | 7071100 | 572300 | 572300 |  | 590800 | 590800 | 572300 | 590800 | 590800 | 590800 | 0 | 590800 | 590800 | 1181600 | 590800 | 590800 |  | 0 | 590800 | 590800 | 590800 | 590800 | 590800 | 1181600 | 0 | 590800 | 590800 |  | 590800 | 590800 | 1181600 | 590800 |  |  | 590800 |  |  | 590800 |  |  | 0 | 0 | 7071100 | 1772400 | 2935500 | 5298700 | -2363200 | 5298700 | 0
Prod Supp | IM Services (Reduced Monthly by $3,715 SNow Credit) | Prod Supp | 1446020 | 119085 | 118670 |  | 123085 | 123085 | 118670 | 123085 | 123085 | 123085 | -415 | 120085 | 123085 | 246170 | 120085 | 117085 |  | 0 | 120085 | 120085 | 117085 | 120085 | 120085 | 240170 | 0 | 120085 | 120085 |  | 120085 | 120085 | 240170 | 120085 |  |  | 120085 |  |  | 120085 |  |  | 0 | 0 | 1445605 | 360255 | 605010 | 1085350 | -480340 | 1085350 | 0
Prod Supp | Oracle OCI Costs | Prod Supp | 784513 | 196128 | 196128 | 196128 | 0 |  |  | 0 |  |  | 0 | 196128 | 196128 | 196128 | 0 |  |  | 0 | 0 |  |  | 196128 | 196128 | 196128 | 0 | 0 |  |  | 0 |  |  | 196129 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 784513 | 196129 | 392256 | 588384 | -196128 | 588384 | 0
Prod Supp | Support Tools Maintenance | Prod Supp | 47772 | 47772 | 47772 | 47772 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 47772 | 0 | 47772 | 47772 | 0 | 47772 | 0
Prod Supp | Support Tools Purchase | Prod Supp | 571800 | 571800 | 571800 | 571800 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 571800 | 0 | 571800 | 571800 | 0 | 571800 | 0
Prod Supp | Solution Software Support (Reduced by $4,980 for A7 credit) | Prod Supp | 27545 | 27545 | 15106 | 15106 | 0 |  |  | 0 |  |  | -12439 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 15106 | 0 | 15106 | 15106 | 0 | 15106 | 0
| Implementation Total: |  | 21051390 | 2000000 | 0 | 0 | 5338840 | 2000000 | 0 | 994983 | 994983 | 2994983 | -5338840 | 4000000 | 3819462 | 1909731 | 3420540 | 0 | 1909731 | -3601078 | 1338840 | 1248571 | 0 | 1500000 | 3191000 | 4439571 | 1600731 | 2081700 | 2081700 | 0 | 0 | 0 | 2081700 | 0 | 0 | 0 | 3863167 | 0 | 0 | 3581700 | 0 | 0 | 0 | 0 | 20780583 | 7444867 | 6814445 | 13335716 | -6521271 | 13335716 | 0
| Production Support Facilities Total: |  | 415692 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692 | 103923 | 173205 | 311769 | -138564 | 311769 | 0
| Production Support (No Facilities) Total: |  | 9948750 | 1534630 | 1521776 | 830806 | 713885 | 713885 | 690970 | 713885 | 713885 | 713885 | -12854 | 907013 | 910013 | 1623898 | 710885 | 707885 | 0 | 0 | 710885 | 710885 | 707885 | 907013 | 907013 | 1617898 | 0 | 710885 | 710885 | 0 | 710885 | 710885 | 1421770 | 907014 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 0 | 0 | 9935896 | 2328784 | 4567444 | 7607112 | -3039668 | 7607112 | 0
Monthly Totals |  |  | 31415832 | 3569271 | 1556417 | 865447 | 6087366 | 2748526 | 725611 | 1743509 | 1743509 | 3743509 | -5351694 | 4941654 | 4764116 | 3568270 | 4166066 | 742526 | 1944372 | -3601078 | 2084366 | 1994097 | 742526 | 2441654 | 4132654 | 6092110 | 1600731 | 2827226 | 2827226 | 34641 | 745526 | 745526 | 3538111 | 941655 | 0 | 0 | 4608693 | 0 | 0 | 4327226 | 0 | 0 | 0 | 0 | 31132171 | 9877574 | 11555094 | 21254597 | -9699503 | 21254597 | 0
| Projected YTD |  |  | 3569271 |  |  | 9656637 |  |  | 11400146 |  |  | 6048452 | 10990106 |  |  | 15156172 |  |  | 11555094 | 13639460 |  |  | 16081114 |  |  | 17681845 | 20509071 |  |  | 21254597 |  |  | 22196252 |  |  | 26804945 |  |  | 31132171
| Incurred YTD |  |  |  | 1556417 |  |  | 4304943 |  |  | 6048452 |  |  |  | 10812568 |  |  | 11555094 |  |  |  | 13549191 |  |  | 17681845 |  |  |  | 20509071 |  |  | 21254597 |  |  | 21254597 |  |  | 21254597 |  |  | 21254597 |  | 21254597
| Paid YTD |  |  |  |  | 865447 |  |  | 1591058 |  |  | 5334567 |  |  |  | 8902837 |  |  | 10847209 |  |  |  | 11589735 |  |  | 17681845 |  |  |  | 17716486 |  |  | 21254597 |  |  | 21254597 |  |  | 21254597 |  |  | 21254597 |  | 21254597

## Oracle Summary
Department of Financial Services
Florida PALM FY 2025 - 2026 Oracle Summary FYTD
| Quantity/Months | Quote |  |  | July 2025 |  |  |  | August 2025 |  |  |  | September 2025 |  |  |  | Q2 Baseline Adjustment | October 2025 |  |  |  | November 2025 |  |  |  | A13 Baseline Adjustment | December 2025 |  |  |  | January 2026 |  |  |  | Q3 Baseline Adjustment | February 2026 |  |  |  | March 2026 |  |  |  | April 2026 |  |  |  | May 2026 |  |  |  | June 2026 |  |  |  | FY 2025-26 CF |  | Total
Program |  | Tech Support | Total Purchase/ Subscription | Total Projection | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | CF Incurred | CF Paid | Total Projected | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support |  | 1413950.7308 | 0 | 1413950.7308 | 0 | 0 | #REF! | 0 | 346738.6537 | 1217.22 | #REF! | 1217.22 | 0 | 0 | #REF! | 0 | -345521.4338 | 680438.5264 | 697654.51 | #REF! | 0 | 18570.595 | 1217.22 | #REF! | 353487.77 | -137.3914 | 0 | 0 | #REF! | 345383.96 | 352270.4677 | 352270.55 | #REF! | 0 | 0.08231 | 1217.22 | 1217.22 | #REF! | 353487.77 | 0 | 0 | #REF! | 0 | 352270.4677 | 0 | #REF! | 0 | 1217.22 | 0 | #REF! | 0 | 352270.4677 | 0 | #REF! | 0 | 0 | 0 | 2108261.9187 | 1260353.4833 | 1259215.74 | 1245143.32
Assignment |  | 1413950.7308 | 0 | 1413950.7308 | 0 | 0 | 0 | 0 | 346738.6537 | 1217.22 | 0 | 1217.22 | 0 | 0 | 0 | 0 | -345521.4338 | 680438.5264 | 697654.51 | 0 | 0 | 18570.595 | 1217.22 | 0 | 353487.77 | -137.3914 | 0 | 0 | 0 | 345383.96 | 352270.4677 | 352270.55 | 0 | 0 | 0.08231 | 1217.22 | 1217.22 | 0 | 353487.77 | 0 | 0 | 0 | 0 | 352270.4677 | 0 | 0 | 0 | 1217.22 | 0 | 0 | 0 | 352270.4677 | 0 | 0 | 0 | 0 | 0 | 1759334.8754 | 1053576.72 | 1053576.72 | 1053576.72
Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 2 | 8407.53 | 0 | 8407.53 | 0 | 0 |  | 0 | 2084.5425 | 1217.22 |  | 1217.22 | 0 | 0 |  | 0 | -867.3225 | 1751.99 | 1752 |  | 0 | 1217.22 | 1217.22 |  | 2101.89 | 0.01 | 0 | 0 |  | 867.33 | 884.6675 | 884.67 |  | 0 | 0.0025 | 1217.22 | 1217.22 |  | 2101.89 | 0 | 0 |  | 0 | 884.6675 | 0 |  | 0 | 1217.22 | 0 |  | 0 | 884.6675 | 0 |  | 0 |  |  | 9274.885 | 6288.33 | 6288.33 | 6288.33
Oracle Business Intelligence (Analytics) Server Administrator | 4 | 1509.1834 | 0 | 1509.1834 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | -369.8975 | 747.1934 | 747.19 |  | 0 | 0 | 0 |  | 377.3 | -0.003358 | 0 | 0 |  | 369.89 | 377.2959 | 377.3 |  | 0 | 0.004142 | 0 | 0 |  | 377.3 | 0 | 0 |  | 0 | 377.2959 | 0 |  | 0 | 0 | 0 |  | 0 | 377.2959 | 0 |  | 0 |  |  | 1879.0817 | 1124.49 | 1124.49 | 1124.49
Oracle Business Intelligence Management Pack | 4 | 2992.44 | 0 | 2992.44 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | -733.4425 | 1481.5525 | 1481.56 |  | 0 | 0 | 0 |  | 748.11 | 0.0075 | 0 | 0 |  | 733.45 | 748.11 | 748.11 |  | 0 | 0 | 0 | 0 |  | 748.11 | 0 | 0 |  | 0 | 748.11 | 0 |  | 0 | 0 | 0 |  | 0 | 748.11 | 0 |  | 0 |  |  | 3725.89 | 2229.67 | 2229.67 | 2229.67
Oracle Business Intelligence Suite Foundation Edition | 4 | 78080.06 | 0 | 78080.06 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | -19137.2675 | 38657.2825 | 38657.28 |  | 0 | 0 | 0 |  | 19520.02 | -0.0025 | 0 | 0 |  | 19137.26 | 19520.015 | 19520.02 |  | 0 | 0.005 | 0 | 0 |  | 19520.02 | 0 | 0 |  | 0 | 19520.015 | 0 |  | 0 | 0 | 0 |  | 0 | 19520.015 | 0 |  | 0 |  |  | 97217.33 | 58177.3 | 58177.3 | 58177.3
Oracle Data Integrator Enterprise Edition | 20 | 39040.032 | 0 | 39040.032 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | -9568.635 | 19328.643 | 19328.63 |  | 0 | 0 | 0 |  | 9760.01 | -0.013006 | 0 | 0 |  | 9568.62 | 9760.008 | 9760.01 |  | 0 | 0.001994 | 0 | 0 |  | 9760.01 | 0 | 0 |  | 0 | 9760.008 | 0 |  | 0 | 0 | 0 |  | 0 | 9760.008 | 0 |  | 0 |  |  | 48608.656 | 29088.64 | 29088.64 | 29088.64
Oracle Data Visualization | 4 | 26027.3955 | 0 | 26027.3955 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | -6379.265 | 12886.1139 | 12886.1 |  | 0 | 0 | 0 |  | 6506.85 | -0.013872 | 0 | 0 |  | 6379.25 | 6506.8489 | 6506.85 |  | 0 | 0.001128 | 0 | 0 |  | 6506.85 | 0 | 0 |  | 0 | 6506.8489 | 0 |  | 0 | 0 | 0 |  | 0 | 6506.8489 | 0 |  | 0 |  |  | 32406.6477 | 19392.95 | 19392.95 | 19392.95
Oracle Financial Analytics Fusion Edition (DW/BI) | 100 | 15096.1104 | 0 | 15096.1104 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | -3700.0275 | 7474.0551 | 7474.05 |  | 0 | 0 | 0 |  | 3774.03 | -0.005091 | 0 | 0 |  | 3700.02 | 3774.0276 | 3774.03 |  | 0 | 0.002409 | 0 | 0 |  | 3774.03 | 0 | 0 |  | 0 | 3774.0276 | 0 |  | 0 | 0 | 0 |  | 0 | 3774.0276 | 0 |  | 0 |  |  | 18796.1352 | 11248.08 | 11248.08 | 11248.08
Oracle Managed File Transfer | 12 | 21800.7813 | 0 | 21800.7813 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | -5343.3275 | 10793.5228 | 10793.52 |  | 0 | 0 | 0 |  | 5450.2 | -0.002827 | 0 | 0 |  | 5343.32 | 5450.1953 | 5450.2 |  | 0 | 0.004673 | 0 | 0 |  | 5450.2 | 0 | 0 |  | 0 | 5450.1953 | 0 |  | 0 | 0 | 0 |  | 0 | 5450.1953 | 0 |  | 0 |  |  | 27144.1107 | 16243.72 | 16243.72 | 16243.72
Oracle Management Pack for Oracle Data Integrator | 16 | 7183.1817 | 0 | 7183.1817 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | -1760.5825 | 3556.3779 | 3556.39 |  | 0 | 0 | 0 |  | 1795.8 | 0.012075 | 0 | 0 |  | 1760.59 | 1795.7954 | 1795.8 |  | 0 | 0.004575 | 0 | 0 |  | 1795.8 | 0 | 0 |  | 0 | 1795.7954 | 0 |  | 0 | 0 | 0 |  | 0 | 1795.7954 | 0 |  | 0 |  |  | 8943.7808 | 5352.19 | 5352.19 | 5352.19
Oracle SOA Management Pack Enterprise Edition | 14 | 21084.1199 | 0 | 21084.1199 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | -5167.6775 | 10438.7075 | 10438.7 |  | 0 | 0 | 0 |  | 5271.03 | -0.00747 | 0 | 0 |  | 5167.67 | 5271.03 | 5271.03 |  | 0 | 3e-05 | 0 | 0 |  | 5271.03 | 0 | 0 |  | 0 | 5271.03 | 0 |  | 0 | 0 | 0 |  | 0 | 5271.03 | 0 |  | 0 |  |  | 26251.7899 | 15709.73 | 15709.73 | 15709.73
Oracle SOA Suite for Oracle Middleware | 14 | 48493.0302 | 0 | 48493.0302 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | -11885.545 | 24008.8025 | 24008.79 |  | 0 | 0 | 0 |  | 12123.26 | -0.01254 | 0 | 0 |  | 11885.53 | 12123.2575 | 12123.26 |  | 0 | 0.00246 | 0 | 0 |  | 12123.26 | 0 | 0 |  | 0 | 12123.2575 | 0 |  | 0 | 0 | 0 |  | 0 | 12123.2575 | 0 |  | 0 |  |  | 60378.5651 | 36132.05 | 36132.05 | 36132.05
Oracle WebLogic Server Management Pack Enterprise Edition | 26 | 18840.42 | 0 | 18840.42 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | -4617.75 | 9327.855 | 9327.82 |  | 0 | 0 | 0 |  | 4710.1 | -0.035 | 0 | 0 |  | 4617.72 | 4710.105 | 4710.1 |  | 0 | -0.005 | 0 | 0 |  | 4710.1 | 0 | 0 |  | 0 | 4710.105 | 0 |  | 0 | 0 | 0 |  | 0 | 4710.105 | 0 |  | 0 |  |  | 23458.13 | 14037.92 | 14037.92 | 14037.92
Oracle WebLogic Suite | 26 | 70652.1264 | 0 | 70652.1264 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | -17316.7 | 34979.7316 | 34979.73 |  | 0 | 0 | 0 |  | 17663.03 | -0.0016014 | 0 | 0 |  | 17316.7 | 17663.0316 | 17663.03 |  | 0 | -0.0016014 | 0 | 0 |  | 17663.03 | 0 | 0 |  | 0 | 17663.0316 | 0 |  | 0 | 0 | 0 |  | 0 | 17663.0316 | 0 |  | 0 |  |  | 87968.8232 | 52642.76 | 52642.76 | 52642.76
PeopleSoft Enterprise Contracts | 92083 | 58183.35 | 0 | 58183.35 | 0 | 0 |  | 0 | 14270.345 | 0 |  | 0 | 0 | 0 |  | 0 | -14270.345 | 27749.3125 | 28807.73 |  | 0 | 1066.87 | 0 |  | 14545.84 | -8.4525 | 0 | 0 |  | 14261.89 | 14545.8375 | 14545.84 |  | 0 | 0.0025 | 0 | 0 |  | 14545.84 | 0 | 0 |  | 0 | 14545.8375 | 0 |  | 0 | 0 | 0 |  | 0 | 14545.8375 | 0 |  | 0 |  |  | 72445.245 | 43353.57 | 43353.57 | 43353.57
PeopleSoft Enterprise eSettlements | 92083 | 38183.04 | 0 | 38183.04 | 0 | 0 |  | 0 | 9364.9788 | 0 |  | 0 | 0 | 0 |  | 0 | -9364.9788 | 18210.6013 | 18905.19 |  | 0 | 700.1375 | 0 |  | 9545.77 | -5.5488 | 0 | 0 |  | 9359.42 | 9545.76 | 9545.77 |  | 0 | 0.01 | 0 | 0 |  | 9545.77 | 0 | 0 |  | 0 | 9545.76 | 0 |  | 0 | 0 | 0 |  | 0 | 9545.76 | 0 |  | 0 |  |  | 47542.48 | 28450.96 | 28450.96 | 28450.96
PeopleSoft Enterprise Expenses | 92083 | 77273.8 | 0 | 77273.8 | 0 | 0 |  | 0 | 18952.5775 | 0 |  | 0 | 0 | 0 |  | 0 | -18952.5775 | 36854.085 | 38259.85 |  | 0 | 1416.9425 | 0 |  | 19318.46 | -11.1775 | 0 | 0 |  | 18941.39 | 19318.45 | 19318.46 |  | 0 | 0.01 | 0 | 0 |  | 19318.46 | 0 | 0 |  | 0 | 19318.45 | 0 |  | 0 | 0 | 0 |  | 0 | 19318.45 | 0 |  | 0 |  |  | 96215.21 | 57578.31 | 57578.31 | 57578.31
PeopleSoft Enterprise Financials | 92083 | 416369.45 | 0 | 416369.45 | 0 | 0 |  | 0 | 102120.9538 | 0 |  | 0 | 0 | 0 |  | 0 | -102120.9538 | 198578.4987 | 206152.87 |  | 0 | 7634.8175 | 0 |  | 104092.37 | -60.4463 | 0 | 0 |  | 102060.5 | 104092.3625 | 104092.37 |  | 0 | 0.0075 | 0 | 0 |  | 104092.37 | 0 | 0 |  | 0 | 104092.3625 | 0 |  | 0 | 0 | 0 |  | 0 | 104092.3625 | 0 |  | 0 |  |  | 518429.965 | 310245.24 | 310245.24 | 310245.24
PeopleSoft Enterprise Grants | 92083 | 54545.96 | 0 | 54545.96 | 0 | 0 |  | 0 | 13378.2288 | 0 |  | 0 | 0 | 0 |  | 0 | -13378.2288 | 26014.5212 | 27006.78 |  | 0 | 1000.1975 | 0 |  | 13636.49 | -7.9387 | 0 | 0 |  | 13370.29 | 13636.49 | 13636.49 |  | 0 | 0 | 0 | 0 |  | 13636.49 | 0 | 0 |  | 0 | 13636.49 | 0 |  | 0 | 0 | 0 |  | 0 | 13636.49 | 0 |  | 0 |  |  | 67916.25 | 40643.27 | 40643.27 | 40643.27
PeopleSoft Enterprise Human Resources | 114800 | 48897.13 | 0 | 48897.13 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | -11984.59 | 24208.8725 | 24208.87 |  | 0 | 0 | 0 |  | 12224.28 | -0.0025 | 0 | 0 |  | 11984.59 | 12224.2825 | 12224.28 |  | 0 | -0.0025 | 0 | 0 |  | 12224.28 | 0 | 0 |  | 0 | 12224.2825 | 0 |  | 0 | 0 | 0 |  | 0 | 12224.2825 | 0 |  | 0 |  |  | 60881.715 | 36433.15 | 36433.15 | 36433.15
PeopleSoft Enterprise Payroll | 114800 | 59469.02 | 0 | 59469.02 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | -14575.74 | 29442.995 | 29443 |  | 0 | 0 | 0 |  | 14867.26 | 0.005 | 0 | 0 |  | 14575.74 | 14867.255 | 14867.26 |  | 0 | 0.005 | 0 | 0 |  | 14867.26 | 0 | 0 |  | 0 | 14867.255 | 0 |  | 0 | 0 | 0 |  | 0 | 14867.255 | 0 |  | 0 |  |  | 74044.77 | 44310.26 | 44310.26 | 44310.26
PeopleSoft Enterprise Project Costing | 92083 | 77273.8 | 0 | 77273.8 | 0 | 0 |  | 0 | 18952.5775 | 0 |  | 0 | 0 | 0 |  | 0 | -18952.5775 | 36854.085 | 38259.85 |  | 0 | 1416.9425 | 0 |  | 19318.46 | -11.1775 | 0 | 0 |  | 18941.39 | 19318.45 | 19318.46 |  | 0 | 0.01 | 0 | 0 |  | 19318.46 | 0 | 0 |  | 0 | 19318.45 | 0 |  | 0 | 0 | 0 |  | 0 | 19318.45 | 0 |  | 0 |  |  | 96215.21 | 57578.31 | 57578.31 | 57578.31
PeopleSoft Enterprise Purchasing | 92083 | 85456.36 | 0 | 85456.36 | 0 | 0 |  | 0 | 20959.47 | 0 |  | 0 | 0 | 0 |  | 0 | -20959.47 | 40756.5875 | 42311.15 |  | 0 | 1566.9725 | 0 |  | 21364.1 | -12.41 | 0 | 0 |  | 20947.05 | 21364.09 | 21364.1 |  | 0 | 0.01 | 0 | 0 |  | 21364.1 | 0 | 0 |  | 0 | 21364.09 | 0 |  | 0 | 0 | 0 |  | 0 | 21364.09 | 0 |  | 0 |  |  | 106403.43 | 63675.25 | 63675.25 | 63675.25
PeopleSoft Enterprise Supplier Contract Management | 92083 | 77273.8 | 0 | 77273.8 | 0 | 0 |  | 0 | 18952.5775 | 0 |  | 0 | 0 | 0 |  | 0 | -18952.5775 | 36854.085 | 38259.85 |  | 0 | 1416.9425 | 0 |  | 19318.46 | -11.1775 | 0 | 0 |  | 18941.39 | 19318.45 | 19318.46 |  | 0 | 0.01 | 0 | 0 |  | 19318.46 | 0 | 0 |  | 0 | 19318.45 | 0 |  | 0 | 0 | 0 |  | 0 | 19318.45 | 0 |  | 0 |  |  | 96215.21 | 57578.31 | 57578.31 | 57578.31
PeopleSoft Enterprise Treasury | 92083 | 61818.61 | 0 | 61818.61 | 0 | 0 |  | 0 | 15161.955 | 0 |  | 0 | 0 | 0 |  | 0 | -15161.955 | 29483.055 | 30607.61 |  | 0 | 1133.5525 | 0 |  | 15454.65 | -8.9975 | 0 | 0 |  | 15152.96 | 15454.6525 | 15454.65 |  | 0 | -0.0025 | 0 | 0 |  | 15454.65 | 0 | 0 |  | 0 | 15454.6525 | 0 |  | 0 | 0 | 0 |  | 0 | 15454.6525 | 0 |  | 0 |  |  | 76971.565 | 46062.26 | 46062.26 | 46062.26
PeopleSoft Enterprise Time and Labor | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Oracle Credits |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | -6759.54 |  | 0 | -6759.54 | 0 | 0 |  | -6759.54 | 0 | -39434.31 |  | 0 | -39434.31 | 0 | 0 |  | -39434.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | -46193.85 | -46193.85 | -46193.85 | -46193.85
Oracle Credits |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | -6759.54 |  | 0 | -6759.54 | 0 | 0 |  | -6759.54 | 0 | -39434.31 |  | 0 | -39434.31 | 0 | 0 |  | -39434.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | -46193.85 | -46193.85 | -46193.85 | -46193.85
Analytics |  | 55358.8517 | 0 | 55358.8517 | 0 | 0 | 0 | 0 | 13568.35 | 13568.35 | 0 | 0 | 0 | 0 | 0 | 13568.35 | 0 | 0 | 0 | 0 | 0 | 19792.69 | 13568.33 | 0 | 0 | -6224.36 | 0 | 0 | 0 | 13568.33 | 0 | 0 | 0 | 0 | 0 | 12448.68 | 0 | 0 | 0 | 0 | 14072.42 | 0 | 0 | 0 | 0 | 0 | 0 | 12448.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52034.04 | 39585.36 | 41209.1 | 27136.68
HR Analytics (DW/BI) | 200 | 46132.3764 | 0 | 46132.3764 | 0 | 0 |  | 0 | 11307 | 11307 |  | 0 | 0 | 0 |  | 11307 | 0 | 0 | 0 |  | 0 | 16493.97 | 11307 |  | 0 | -5186.97 | 0 | 0 |  | 11307 | 0 | 0 |  | 0 | 0 | 10373.94 | 0 |  | 0 | 0 | 11727.07 |  | 0 | 0 | 0 |  | 0 | 10373.94 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 43361.88 | 32987.94 | 34341.07 | 22614
Project Analytics (DW/BI) | 100 | 9226.4753 | 0 | 9226.4753 | 0 | 0 |  | 0 | 2261.35 | 2261.35 |  | 0 | 0 | 0 |  | 2261.35 | 0 | 0 | 0 |  | 0 | 3298.72 | 2261.33 |  | 0 | -1037.39 | 0 | 0 |  | 2261.33 | 0 | 0 |  | 0 | 0 | 2074.74 | 0 |  | 0 | 0 | 2345.35 |  | 0 | 0 | 0 |  | 0 | 2074.74 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 8672.16 | 6597.42 | 6868.03 | 4522.68
Financials Analytics (DW/BI) | 3000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
OAC |  | 0 | 405463 | 405463 | 44165.81 | 17097.05 | 0 | 17097.05 | 33741.76 | 10035.49 | 0 | 0 | 33788.58 | 20602.24 | 0 | 10035.49 | -63961.37 | 33788.58 | 27108.01 | 0 | 20602.24 | 33788.58 | 27768.55 | 0 | 54876.56 | -12700.6 | 33788.58 | 8502.33 | 0 | 8502.33 | 27835.9167 | 18571.22 | 0 | 18571.22 | -34550.9467 | 55864.4467 | 55488.05 | 0 | 55488.05 | 27835.9167 | 25450.83 | 0 | 25450.83 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 0 | 0 | 296893.0033 | 213385.2533 | 210623.77 | 210623.77
OAC (DW/BI) - DEV: $53,219.00 - Test: $63,779.00 - DR: $94,238.00 - Production: $194,227.00 | 4 | 0 | 405463 | 405463 | 44165.81 | 17097.05 |  | 17097.05 | 33741.76 | 10035.49 |  | 0 | 33788.58 | 20602.24 |  | 10035.49 | -63961.37 | 33788.58 | 27108.01 |  | 20602.24 | 33788.58 | 27768.55 |  | 54876.56 | -12700.6 | 33788.58 | 8502.33 |  | 8502.33 | 27835.9167 | 18571.22 |  | 18571.22 | -34550.9467 | 55864.4467 | 55488.05 |  | 55488.05 | 27835.9167 | 25450.83 |  | 25450.83 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 0 | 0 | 296893.0033 | 213385.2533 | 210623.77 | 210623.77
New License Purchase and Tech Support |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Financials | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Treasury | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Expenses | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise eSettlements | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Contracts | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Grants | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Project Costing | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Purchasing | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Human Resources | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Payroll | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Time and Labor | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 1469309.5824 | 405463 | 1874772.5824 | 44165.81 | 17097.05 | #REF! | 17097.05 | 394048.7637 | 24821.06 | #REF! | 1217.22 | 33788.58 | 20602.24 | #REF! | 23603.84 | -409482.8038 | 714227.1064 | 724762.52 | #REF! | 20602.24 | 72151.865 | 35794.56 | #REF! | 408364.33 | -25821.8914 | 33788.58 | 8502.33 | #REF! | 360695.08 | 380106.3844 | 331407.46 | #REF! | 18571.22 | -73985.1744 | 69530.3467 | 56705.27 | #REF! | 369541.51 | 27835.9167 | 39523.25 | #REF! | 25450.83 | 380106.3844 | 0 | #REF! | 0 | 41501.8167 | 0 | #REF! | 0 | 380106.3844 | 0 | #REF! | 0 | 0 | 0 | 2062068.0687 | 1260353.4833 | 1259215.74 | 1245143.32
Projected FYTD |  |  |  |  | 44165.81 |  |  |  | 438214.5737 |  |  |  | 472003.1537 |  |  |  | 62520.35 | 776747.4564 |  |  |  | 848899.3214 |  |  |  | 823077.43 | 856866.01 |  |  |  | 1236972.3944 |  |  |  | 1162987.22 | 1232517.5667 |  |  |  | 1260353.4833 |  |  |  | 1640459.8677 |  |  |  | 1681961.6844 |  |  |  | 2062068.0687
Incurred FYTD | [5 empty] | 17097.05 |  |  |  | 41918.11 |  |  |  | 62520.35 |  |  |  |  | 787282.87 |  |  |  | 823077.43 |  |  |  |  | 831579.76 |  |  |  | 1162987.22 |  |  |  |  | 1219692.49 |  |  |  | 1259215.74 |  |  |  | 1259215.74 |  |  |  | 1259215.74 |  |  |  | 1259215.74
Paid FYTD | [7 empty] | 17097.05 |  |  |  | 18314.27 |  |  |  | 41918.11 |  |  |  |  | 62520.35 |  |  |  | 470884.68 |  |  |  |  | 831579.76 |  |  |  | 850150.98 |  |  |  |  | 1219692.49 |  |  |  | 1245143.32 |  |  |  | 1245143.32 |  |  |  | 1245143.32 |  |  |  | 1245143.32

## Florida PALM-UAT
Department of Financial Services
Florida PALM FY 2025 - 2026 PALM Readiness Detail FYTD
|  |  |  | July 2025 |  |  | August 2025 |  |  | September 2025 |  |  | Q2 Baseline Adjustment | October 2025 |  |  | November 2025 |  |  | A13 Baseline Adjustment | December 2025 |  |  | January 2026 |  |  | Q3 Baseline Adjustment | February 2026 |  |  | March 2026 |  |  | April 2026 |  |  | May 2026 |  |  | June 2026 |  |  | CF 2025-26 |  | Total
Item Description | Rate | Quantity | Total Projected | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid |  | Projected | Incurred | Paid | Projected | Incurred | Paid |  | Projected | Incurred | Paid | Projected | Incurred | Paid |  | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Incurred | Paid | Projected FYTD | Incurred FYTD | Paid FYTD
PALM Readiness Deliverables |  |  | 2534817.3 | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | -275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59520 | 59520 | 0 | 0 | 0 | 0 | 59520 | 506292 | 0 | 0 | 758173.2 | 0 | 0 | 729854.7 | 0 | 0 | 480977.4 | 0 | 0 | 0 | 0 | 565812 | 59520 | 59520
UAT-QA D1 Project Schedule |  |  | 59520 | [6 empty] | 275000 |  |  | -275000 | [6 empty] | 0 |  |  |  | 59520 | 59520 |  | 0 |  |  | 59520 | [14 empty] | 59520 | 59520 | 59520
UAT-QA D2 Standardized UAT and Automation Testing Plan |  |  | 506292 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 |  |  |  | 506292 | [13 empty] | 506292 | 0 | 0
UAT-QA D3 Report Identifying Common Agency Test Scripts |  |  | 758173.2 | [16 empty] | 0 | [6 empty] | 0 | [6 empty] | 758173.2 | [10 empty] | 0 | 0 | 0
UAT-QA D4 Report Providing Confirmation of Functional / Non-Functional Requirements and Agencies Ability to Comply with Financial Regulations |  |  | 729854.7 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [9 empty] | 729854.7 | [7 empty] | 0 | 0 | 0
UAT-QA D5 Deployment of Streamline Testing Efforts and Regression Testing Automation |  |  | 332177.4 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [12 empty] | 332177.4 |  |  |  |  | 0 | 0 | 0
UAT-QA D6 Final Assessment Report |  |  | 148800 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [12 empty] | 148800 |  |  |  |  | 0 | 0 | 0
Total |  |  | 2534817.3 | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | -275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59520 | 59520 | 0 | 0 | 0 | 0 | 59520 | 506292 | 0 | 0 | 758173.2 | 0 | 0 | 729854.7 | 0 | 0 | 480977.4 | 0 | 0 | 0 | 0 | 565812 | 59520 | 59520
Projected FYTD |  |  |  | 0 |  |  | 0 |  |  | 275000 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 59520 |  |  | 59520 | 59520 |  |  | 565812 |  |  | 1323985.2 |  |  | 2053839.9 |  |  | 2534817.3
Incurred FYTD |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 59520 |  |  |  | 59520 |  |  | 59520 |  |  | 59520 |  |  | 59520 |  |  | 59520 |  | 59520
Paid FYTD | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 59520 |  |  | 59520 |  |  | 59520 |  |  | 59520 |  |  | 59520 |  | 59520