## Monthly Summary
Department of Financial Services
Florida PALM FY 2026 - 2027 Spend Plan Summary FYTD
As of August 31, 2026
Annual
[12 empty] | July 2026 |  |  |  | Release Request Baseline Adjustment | August 2026 |  |  |  | September 2026 |  |  | October 2026 |  |  | November 2026 |  |  | December 2026 |  |  | January 2027 |  |  | February 2027 |  |  | March 2027 |  |  | April 2027 |  |  | May 2027 |  |  | June 2027 |  |  | CF 2026-27 |  | Fiscal Year to Date
Category (Cost Area / Contract) |  |  |  | FY 25-26 Revert & Appropriated | FY 26-27 GAA Appropriated | FY 26-27 Total Appropriation | Released | Unreleased | Unobligated | 53686394.8764 | 1579797.72 | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
[10 empty] | Projected | Release Remaining
FLAIR System Replacement (100781) | Payment Terms | Contract Type | Disbursement Type | 15533430 | 39040586 | 54574016 | 11611760 | 42962256 | 887621.1236 | 53686394.8764 | 1579797.72 | 5084877.0525 | 3301970.79 |  | 2387390.14 | -1782906.2625 | 6870324.3616 | 6729991.49 |  | 4144074.61 | 1371919.4639 | 0 | 0 | 2477978.2063 | 0 | 0 | 9487354.8606 | 0 | 0 | 1355031.3306 | 0 | 0 | 4967081.6196 | 0 | 0 | 7596932.8967 | 0 | 0 | 4258330.5439 | 0 | 0 | 4802125.5696 | 0 | 0 | 4261568.9439 | 0 | 0 | 2935776.2896 | 0 | 0 | 0 | 0 | 10172295.1516 | 10031962.28 | 6531464.75 | 43654432.5964 | 81.31%
SSI Implementation Services (FP004) | Paid in Arrears | Fixed Fee | Encumbered | [6 empty] | 29472433 |  | 1480900 | 0 | 2 | 0 | -1480900 | 4957400 | 4846332.5 |  | 1976500 | 0 | 0 | 0 | 600000 | 0 | 0 | 8102500 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 4953733 | 0 | 0 | 2374000 | 0 | 0 | 2374000 | 0 | 0 | 2374000 | 0 | 0 | 736800 | 0 | 0 | 0 | 0 | 4957400 | 4846332.5 | 1976500 | 24626100.5 | 83.56%
Facilities and Maintenance (FP004) | Advance Pay | Fixed Fee | Encumbered | [6 empty] | 415692 |  | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 69282 | 69282 | 69282 | 346410 | 83.33%
Production Support (FP004) | Both | Fixed Fee | Encumbered | [6 empty] | 12427182.5 |  | 1398177 | 1316027.5 | 2 | 1119896.5 | -82149.5 | 735896 | 735896 |  | 932027 | 735896 | 0 | 0 | 932027 | 0 | 0 | 735896 | 0 | 0 | 735896 | 0 | 0 | 932027 | 0 | 0 | 1221085 | 0 | 0 | 1221085 | 0 | 0 | 1419177 | 0 | 0 | 1221085 | 0 | 0 | 1221085 | 0 | 0 | 0 | 0 | 2051923.5 | 2051923.5 | 2051923.5 | 10375259 | 83.49%
Additional Facilities | Advance Pay | Fixed Fee | Encumbered | [6 empty] | 245681.66 |  | 20360.23 | 20360.23 |  | 20360.23 | 0 | 20360.23 | 20360.23 |  | 20360.23 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 20542.03 | 0 | 0 | 20542.03 | 0 | 0 | 20542.03 | 0 | 0 | 20766.98 | 0 | 0 | 20766.98 | 0 | 0 | 0 | 0 | 40720.46 | 40720.46 | 40720.46 | 204961.2 | 83.43%
Oracle Software and Maintenance (FP005) | Paid in Arrears | Fixed Fee | Encumbered | [6 empty] | 2433842.3836 |  | 27835.9167 | 28885.77 | 3 | 28885.77 | 1049.8533 | 457413.2744 | 435241 | 6 | 435241 | 27835.9167 | 0 | 0 | 387151.7923 | 0 | 0 | 105142.8067 | 0 | 0 | 27835.9167 | 0 | 0 | 387151.7923 | 0 | 0 | 105142.8067 | 0 | 0 | 27835.9167 | 0 | 0 | 387151.7923 | 0 | 0 | 105142.8067 | 0 | 0 | 387151.7923 | 0 | 0 | 0 | 0 | 486299.0444 | 464126.77 | 464126.77 | 1969715.6136 | 80.93%
Project Administration | Paid in Arrears | Fixed Fee | Both | [6 empty] | 342391.35 |  | 17454.8458 | 28119.49 | 3 | 28119.49 | 10664.6442 | 53776.5373 | 44825.28 | 2 | 38393.18 | 66765.6373 | 0 | 0 | 16665.8373 | 0 | 0 | 17365.8373 | 0 | 0 | 49165.8373 | 0 | 0 | 16665.8373 | 0 | 0 | 17295.8373 | 0 | 0 | 16665.8373 | 0 | 0 | 21572.9873 | 0 | 0 | 16665.8373 | 0 | 0 | 21665.8373 | 0 | 0 | 0 | 0 | 81896.0273 | 72944.77 | 66512.67 | 269446.58 | 78.7%
Support Services | Paid in Arrears | Time & Materials | Encumbered | [6 empty] | 5381600.52 |  | 676464.2 | 594227.16 | 5,1 | 310354.91 | -82237.04 | 356465.56 | 353512.93 |  | 283872.25 | 380848.92 | 0 | 0 | 424440.5867 | 0 | 0 | 408757.2267 | 0 | 0 | 424440.5867 | 0 | 0 | 478410.6667 | 0 | 0 | 485775.6667 | 0 | 0 | 492735.6667 | 0 | 0 | 474215.6667 | 0 | 0 | 418442.2267 | 0 | 0 | 442840.5867 | 0 | 0 | 0 | 0 | 950692.72 | 947740.09 | 594227.16 | 4433860.43 | 82.39%
QA Support Services | Paid in Arrears | Time & Materials | Encumbered | [6 empty] | 954808 |  | 215040 | 214328 |  | 111928 | -712 | 102400 | 107520 | 4 | 88000 | 102400 | 0 | 0 | 59520 | 0 | 0 | 59520 | 0 | 0 | 59520 | 0 | 0 | 59520 | 0 | 0 | 59520 | 0 | 0 | 59520 | 0 | 0 | 59520 | 0 | 0 | 59520 | 0 | 0 | 59520 | 0 | 0 | 0 | 0 | 316728 | 321848 | 199928 | 632960 | 66.29%
Production Support Administration | Paid in Arrears | Fixed Fee | Both | [6 empty] | 801931.3628 |  | 3171.76 | 3349.54 | 3 | 3349.54 | 177.78 | 3171.76 | 2862.55 |  | 2862.55 | 3171.76 | 0 | 0 | 3171.76 | 0 | 0 | 3171.76 | 0 | 0 | 3171.76 | 0 | 0 | 38305.0933 | 0 | 0 | 699197.5561 | 0 | 0 | 11305.0933 | 0 | 0 | 11305.0933 | 0 | 0 | 11305.0933 | 0 | 0 | 11305.0933 | 0 | 0 | 0 | 0 | 6521.3 | 6212.09 | 6212.09 | 795719.2728 | 99.23%
Florida PALM-UAT | Paid in Arrears | Fixed Fee | Encumbered | [6 empty] | 1210832.1 |  | 1210832.1 | 1062032.1 | 2 | 729854.7 | -148800 | 148800 | 148800 |  | 332177.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1210832.1 | 1210832.1 | 1062032.1 | 0 | 0%
Contingency (100819) |  |  |  | 3000000 | 0 | 3000000 | 0 | 3000000 | 3000000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Salaries & Benefits (010000) |  |  |  | 0 | 11338685 | 11338685 | 11338685 | 0 | 116718.8267 | 11221966.1733 | 9703263.26 | 944890.4167 | 828171.59 |  | 828171.59 | -116718.8267 | 944890.4167 | 807250.15 |  | 807250.15 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 0 | 0 | 1773062.0067 | 1635421.74 | 1635421.74 | 9586544.4333 | 85.43%
Salaries & Benefits (010000) |  |  |  | 0 | 1948107 | 1948107 | 487027 | 1461080 | 96900.08 | 1851206.92 | 331870.52 | 162342.25 | 65442.17 |  | 65442.17 | -96900.08 | 162342.25 | 89714.31 |  | 89714.31 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 0 | 0 | 227784.42 | 155156.48 | 155156.48 | 1696050.44 | 91.62%
Risk Management Insurance (103241) |  |  |  | 0 | 14572 | 14572 | 14572 | 0 | 0 | 14572 | 14572 | 14572 | 0 | 2 | 0 | -14572 | 14572 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14572 | 0 | 0 | 14572 | 100%
DMS HR Transfer (107040) |  |  |  | 0 | 24081 | 24081 | 24081 | 0 | 0 | 24081 | 18060.75 | 6020.25 | 0 | 2 | 0 | -6020.25 | 6020.25 | 6020.25 |  | 6020.25 | 0 | 0 | 0 | 6020.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6020.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6020.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6020.25 | 6020.25 | 6020.25 | 18060.75 | 75%
DMS HR Transfer (107040) |  |  |  | 0 | 3528 | 3528 | 3528 | 0 | 0 | 3528 | 2646 | 882 | 0 |  | 0 | -882 | 882 | 882 |  | 882 | 0 | 0 | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882 | 882 | 882 | 2646 | 75%
Totals |  |  |  | 18533430 | 52369559 | 70902989 | 23479653 | 47423336 | 4101240.0302 | 66801748.9698 | 11650210.25 | 6213583.9692 | 4195584.55 |  | 3281003.9 | -2017999.4192 | 7999031.2783 | 7633858.2 |  | 5047059.32 | 2479152.1306 | 0 | 0 | 3592113.1229 | 0 | 0 | 10594587.5273 | 0 | 0 | 2462263.9973 | 0 | 0 | 6081216.5363 | 0 | 0 | 8704165.5634 | 0 | 0 | 5365563.2106 | 0 | 0 | 5916260.4863 | 0 | 0 | 5368801.6106 | 0 | 0 | 4043008.9563 | 0 | 0 | 0 | 0 | 12194615.8283 | 11829442.75 | 8328945.22 | 54972306.2198 | 100%
Running Totals | [11 empty] | 6213583.9692 | 4195584.55 |  | 3281003.9 | 4195584.55 | 12194615.8283 | 11829442.75 |  | 8328063.22 | 14673767.9589 | 11829442.75 | 8328063.22 | 18265881.0818 | 11829442.75 | 8328063.22 | 28860468.6091 | 11829442.75 | 8328063.22 | 31322732.6064 | 11829442.75 | 8328063.22 | 37403949.1426 | 11829442.75 | 8328063.22 | 46108114.706 | 11829442.75 | 8328063.22 | 51473677.9166 | 11829442.75 | 8328063.22 | 57389938.4029 | 11829442.75 | 8328063.22 | 62758740.0135 | 11829442.75 | 8328063.22 | 66801748.9698 | 11829442.75 | 8328063.22 |  | 8328063.22 |  |  | Total Incurred/Total Projected FYTD |  | 97.01%
Monthly Total Incurred/Total Projected | [11 empty] | 67.52% |  |  |  |  | 95.43% |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% | [6 empty] | Total Paid/Total Projected FYTD |  | 68.3%
Monthly Total Incurred/Total Projected (Variance) | [11 empty] | -32.48% |  |  |  |  | -4.565% |  |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [11 empty] | 67.52% |  |  |  |  | 97.01% |  |  |  | 80.62% |  |  | 64.76% |  |  | 40.99% |  |  | 37.77% |  |  | 31.63% |  |  | 25.66% |  |  | 22.98% |  |  | 20.61% |  |  | 18.85% |  |  | 17.71% | [6 empty] | Total Release/Total Appropriation |  | 33.12%
FYTD Total Incurred/Total Projected (Variance) | [11 empty] | -32.48% |  |  |  |  | -2.995% |  |  |  | -19.38% |  |  | -35.24% |  |  | -59.01% |  |  | -62.23% |  |  | -68.37% |  |  | -74.34% |  |  | -77.02% |  |  | -79.39% |  |  | -81.15% |  |  | -82.29%
[55 empty] | Total Paid/Total Release |  | 35.47%
Reconciles to ALRR |  |  |  | Yes |  |  | Yes | Yes | Yes | [5 empty] | Yes |  |  |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  | Yes |  |  | No

## Footnotes
Department of Financial Services
FY 2026 - 2027 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5 | Contractor hours projected and incurred amounts were greater than anticipated due to June 2026 hours being projected to be incurred in July 2026.
6 | Incurred amounts were less than anticipated due to a credit applied to invoice.

## SSI Detail
[7 empty] | July 2026 |  |  | Request Release Baseline Adjustment | August 2026 |  |  | September 2026 |  |  | October 2026 |  |  | November 2026 |  |  | December 2026 |  |  | January 2027 |  |  | February 2027 |  |  | March 2027 |  |  | April 2027 |  |  | May 2027 |  |  | June 2027 |  |  | CF 2026-27
|  | Description | Total Deliverable Cost FY 26-27 | Payment Terms | Contract Type | Disbursement Type | July Projection | July Accepted / Approved | July Paid |  | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Projection
Department of Financial Services
Florida PALM FY 2026 - 2027 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
670 | Completion of Payroll Parallel Testing | Implementation | 600000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [6 empty] | 600000 | [28 empty] | 600000
672 | Support of UAT Segment III | Implementation | 1976500 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | 1976500 | 1976500 | 1976500 | [30 empty] | 0 | 0 | 1976500
673 | Completion of Dry Run #2 | Implementation | 1500000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | 1500000 | 1500000 | [31 empty] | 0 | 0 | 1500000
674 | Completion of Penetration Testing | Implementation | 513400 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [9 empty] | 513400 | [23 empty] | 0 | 0 | 513400
675 | Completion of Performance Testing | Implementation | 1480900 | Paid in Arrears | Fixed Fee | Encumbered | 1480900 |  |  | -1480900 | 1480900 | 1369832.5 | [31 empty] | 0 | 0 | 1480900
676 | Completion of Disaster Recovery Testing | Implementation | 550000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [9 empty] | 550000 | [23 empty] | 0 | 0 | 550000
677 | Completion of Dry Run #3 | Implementation | 1500000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [9 empty] | 1500000 | [23 empty] | 0 | 0 | 1500000
679 | Go-Live of Financials and Payroll Waves | Implementation | 2579733 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [18 empty] | 2579733 | [14 empty] | 0 | 0 | 2579733
680 | Hypercare Monthly Deliverable (Month 1) | Implementation | 2374000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [18 empty] | 2374000 | [14 empty] | 0 | 0 | 2374000
681 | Hypercare Monthly Deliverable (Month 2) | Implementation | 2374000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [21 empty] | 2374000 | [11 empty] | 0 | 0 | 2374000
682 | Hypercare Monthly Deliverable (Month 3) | Implementation | 2374000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [24 empty] | 2374000 | [8 empty] | 0 | 0 | 2374000
683 | Hypercare Monthly Deliverable (Month 4) | Implementation | 2374000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [27 empty] | 2374000 | [5 empty] | 0 | 0 | 2374000
684 | Post-Implementation Support Monthly Deliverable (Month 1) | Implementation | 736800 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [30 empty] | 736800 |  |  | 0 | 0 | 736800
707 | Support of UAT Segment IV | Implementation | 1976500 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [9 empty] | 1976500 | [23 empty] | 0 | 0 | 1976500
708 | Completion of Dry Run #4 | Implementation | 1500000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [15 empty] | 1500000 | [17 empty] | 0 | 0 | 1500000
710 | Completion of Interface Testing Segment III | Implementation | 2081700 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [9 empty] | 2081700 | [23 empty] | 0 | 0 | 2081700
711 | Completion of Performance Testing Segment II | Implementation | 1480900 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [9 empty] | 1480900 | [23 empty] | 0 | 0 | 1480900
712 | Go-Live of Financials and Payroll Waves (pre Cutover Activities) | Implementation | 1500000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [15 empty] | 1500000 | [17 empty] | 0 | 0 | 1500000
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 415692 | Advance Pay | Fixed Fee | Encumbered | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 0 | 0 | 415692
Prod Supp | AM Services | Prod Supp | 9311168 | Paid in Arrears | Fixed Fee | Encumbered | 590800 | 590800 | 590800 | 0 | 611478 | 611478 | 611478 | 611478 |  |  | 611478 |  |  | 611478 |  |  | 611478 |  |  | 611478 |  |  | 1010300 |  |  | 1010300 |  |  | 1010300 |  |  | 1010300 |  |  | 1010300 |  |  | 0 | 0 | 9311168
Prod Supp | IM Services (includes $3,715 SNow Credit) | Prod Supp | 1920518 | Paid in Arrears | Fixed Fee | Encumbered | 120085 | 120085 | 120085 | 0 | 124418 | 124418 | 124418 | 124418 |  |  | 124418 |  |  | 124418 |  |  | 124418 |  |  | 124418 |  |  | 210785 |  |  | 210785 |  |  | 210785 |  |  | 210785 |  |  | 210785 |  |  | 0 | 0 | 1920518
Prod Supp | Oracle OCI Costs | Prod Supp | 786485 | Paid in Arrears | Fixed Fee | Encumbered | 196131 | 196131 |  | 0 | 0 |  | 196131 | 0 |  |  | 196131 |  |  | 0 |  |  | 0 |  |  | 196131 |  |  | 0 |  |  | 0 |  |  | 198092 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 786485
Prod Supp | Support Tools Maintenance | Prod Supp | 49205 | Advance Pay | Fixed Fee | Encumbered | 49205 | 49205 | 49205 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 49205
Prod Supp | Support Tools Purchase | Prod Supp | 336230 | Advance Pay | Fixed Fee | Encumbered | 409670 | 336230 | 336230 | -73440 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 336230
Prod Supp | Solution Software Support | Prod Supp | 23576.5 | Advance Pay | Fixed Fee | Encumbered | 32286 | 23576.5 | 23576.5 | -8709.5 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 23576.5
| Implementation Total: | [5 empty] | 1480900 | 0 | 0 |  | 4957400 | 4846332.5 | 1976500 | 0 | 0 | 0 | 600000 | 0 | 0 | 8102500 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 4953733 | 0 | 0 | 2374000 | 0 | 0 | 2374000 | 0 | 0 | 2374000 | 0 | 0 | 736800 | 0 | 0 | 0 | 0 | 29472433
| Production Support Facilities Total: | [5 empty] | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692
| Production Support (No Facilities) Total: | [5 empty] | 1398177 | 1316027.5 | 1119896.5 |  | 735896 | 735896 | 932027 | 735896 | 0 | 0 | 932027 | 0 | 0 | 735896 | 0 | 0 | 735896 | 0 | 0 | 932027 | 0 | 0 | 1221085 | 0 | 0 | 1221085 | 0 | 0 | 1419177 | 0 | 0 | 1221085 | 0 | 0 | 1221085 | 0 | 0 | 0 | 0 | 12427182.5
Monthly Totals |  |  | 42315307.5 |  |  |  | 2913718 | 1350668.5 | 1154537.5 | -1563049.5 | 5727937 | 5616869.5 | 2943168 | 770537 | 0 | 0 | 1566668 | 0 | 0 | 8873037 | 0 | 0 | 770537 | 0 | 0 | 3966668 | 0 | 0 | 6209459 | 0 | 0 | 3629726 | 0 | 0 | 3827818 | 0 | 0 | 3629726 | 0 | 0 | 1992526 | 0 | 0 | 0 | 0 | 42315307.5
| Projected YTD | [5 empty] | 2913718 |  |  | 1350668.5 | 7078605.5 |  |  | 7849142.5 |  |  | 9415810.5 |  |  | 18288847.5 |  |  | 19059384.5 |  |  | 23026052.5 |  |  | 29235511.5 |  |  | 32865237.5 |  |  | 36693055.5 |  |  | 40322781.5 |  |  | 42315307.5
| Incurred YTD | [6 empty] | 1350668.5 |  |  |  | 6967538 |  |  | 6967538 |  |  | 6967538 |  |  | 6967538 |  |  | 6967538 |  |  | 6967538 |  |  | 6967538 |  |  | 6967538 |  |  | 6967538 |  |  | 6967538 |  |  | 6967538 |  | 6967538
| Paid YTD | [7 empty] | 1154537.5 |  |  |  | 4097705.5 |  |  | 4097705.5 |  |  | 4097705.5 |  |  | 4097705.5 |  |  | 4097705.5 |  |  | 4097705.5 |  |  | 4097705.5 |  |  | 4097705.5 |  |  | 4097705.5 |  |  | 4097705.5 |  |  | 4097705.5 |  | 4097705.5

## Oracle Summary
Department of Financial Services
Florida PALM FY 2026 - 2027 Oracle Summary FYTD
| Quantity/Months | Quote |  |  | Payment Terms | Contract Type | Disbursement Type | July 2026 |  |  |  | Request Release Baseline Adjustment | August 2026 |  |  |  | September 2026 |  |  |  | October 2026 |  |  |  | November 2026 |  |  |  | December 2026 |  |  |  | January 2027 |  |  |  | February 2027 |  |  |  | March 2027 |  |  |  | April 2027 |  |  |  | May 2027 |  |  |  | June 2027 |  |  |  | FY 2026-27 CF |  | Total
Program |  | Tech Support | Total Purchase/ Subscription | Total Projection |  |  |  | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | CF Incurred | CF Paid | Total Projected | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support |  | 1442327.1126 | 0 | 1442327.1126 |  |  |  | 0 | 0 | #REF! | 0 | 0 | 353536.3702 | 353536.12 | #REF! | 353536.12 | 0 | 0 | #REF! | 0 | 359315.8757 | 0 | #REF! | 0 | 1265.9025 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 359315.8757 | 0 | #REF! | 0 | 1265.9025 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 359315.8757 | 0 | #REF! | 0 | 1265.9025 | 0 | #REF! | 0 | 359315.8757 | 0 | #REF! | 0 | 0 | 0 | 1794597.5803 | 486299.0444 | 464126.77 | 464126.77
Assignment |  | 1442327.1126 | 0 | 1442327.1126 |  |  |  | 0 | 0 | 0 | 0 | 0 | 353536.3702 | 353536.12 | 0 | 353536.12 | 0 | 0 | 0 | 0 | 359315.8757 | 0 | 0 | 0 | 1265.9025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359315.8757 | 0 | 0 | 0 | 1265.9025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359315.8757 | 0 | 0 | 0 | 1265.9025 | 0 | 0 | 0 | 359315.8757 | 0 | 0 | 0 | 0 | 0 | 1794597.5803 | 353536.3702 | 353536.12 | 353536.12
Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 2 | 8673.05 |  | 8673.05 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 2150.57 | 2150.56 |  | 2150.56 | 0 | 0 |  | 0 | 902.36 | 0 |  | 0 | 1265.9025 | 0 |  | 0 | 0 | 0 |  | 0 | 902.36 | 0 |  | 0 | 1265.9025 | 0 |  | 0 | 0 | 0 |  | 0 | 902.36 | 0 |  | 0 | 1265.9025 | 0 |  | 0 | 902.36 | 0 |  | 0 |  |  | 9557.7175 | 2150.57 | 2150.56 | 2150.56
Oracle Business Intelligence (Analytics) Server Administrator | 4 | 1539.36 |  | 1539.36 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 377.2959 | 377.28 |  | 377.28 | 0 | 0 |  | 0 | 384.84 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 384.84 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 384.84 | 0 |  | 0 | 0 | 0 |  | 0 | 384.84 | 0 |  | 0 |  |  | 1916.6559 | 377.2959 | 377.28 | 377.28
Oracle Business Intelligence Management Pack | 4 | 3052.29 |  | 3052.29 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 748.11 | 748.11 |  | 748.11 | 0 | 0 |  | 0 | 763.0725 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 763.0725 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 763.0725 | 0 |  | 0 | 0 | 0 |  | 0 | 763.0725 | 0 |  | 0 |  |  | 3800.4 | 748.11 | 748.11 | 748.11
Oracle Business Intelligence Suite Foundation Edition | 4 | 79641.66 |  | 79641.66 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 19520.015 | 19520 |  | 19520 | 0 | 0 |  | 0 | 19910.415 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19910.415 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19910.415 | 0 |  | 0 | 0 | 0 |  | 0 | 19910.415 | 0 |  | 0 |  |  | 99161.675 | 19520.015 | 19520 | 19520
Oracle Data Integrator Enterprise Edition | 20 | 39820.83 |  | 39820.83 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 9760.008 | 9760 |  | 9760 | 0 | 0 |  | 0 | 9955.2075 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9955.2075 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9955.2075 | 0 |  | 0 | 0 | 0 |  | 0 | 9955.2075 | 0 |  | 0 |  |  | 49580.838 | 9760.008 | 9760 | 9760
Oracle Data Visualization | 4 | 26547.95 |  | 26547.95 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 6506.8489 | 6506.85 |  | 6506.85 | 0 | 0 |  | 0 | 6636.9875 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6636.9875 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6636.9875 | 0 |  | 0 | 0 | 0 |  | 0 | 6636.9875 | 0 |  | 0 |  |  | 33054.7989 | 6506.8489 | 6506.85 | 6506.85
Oracle Financial Analytics Fusion Edition (DW/BI) | 100 | 15398.03 |  | 15398.03 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 3774.0276 | 3774.02 |  | 3774.02 | 0 | 0 |  | 0 | 3849.5075 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3849.5075 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3849.5075 | 0 |  | 0 | 0 | 0 |  | 0 | 3849.5075 | 0 |  | 0 |  |  | 19172.0576 | 3774.0276 | 3774.02 | 3774.02
Oracle Managed File Transfer | 12 | 22236.79 |  | 22236.79 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 5450.1953 | 5450.18 |  | 5450.18 | 0 | 0 |  | 0 | 5559.1975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5559.1975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5559.1975 | 0 |  | 0 | 0 | 0 |  | 0 | 5559.1975 | 0 |  | 0 |  |  | 27686.9853 | 5450.1953 | 5450.18 | 5450.18
Oracle Management Pack for Oracle Data Integrator | 16 | 7326.84 |  | 7326.84 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 1795.7954 | 1795.78 |  | 1795.78 | 0 | 0 |  | 0 | 1831.71 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1831.71 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1831.71 | 0 |  | 0 | 0 | 0 |  | 0 | 1831.71 | 0 |  | 0 |  |  | 9122.6354 | 1795.7954 | 1795.78 | 1795.78
Oracle SOA Management Pack Enterprise Edition | 14 | 21505.81 |  | 21505.81 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 5271.03 | 5271.03 |  | 5271.03 | 0 | 0 |  | 0 | 5376.4525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5376.4525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5376.4525 | 0 |  | 0 | 0 | 0 |  | 0 | 5376.4525 | 0 |  | 0 |  |  | 26776.84 | 5271.03 | 5271.03 | 5271.03
Oracle SOA Suite for Oracle Middleware | 14 | 49462.9 |  | 49462.9 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 12123.2575 | 12123.25 |  | 12123.25 | 0 | 0 |  | 0 | 12365.725 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12365.725 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12365.725 | 0 |  | 0 | 0 | 0 |  | 0 | 12365.725 | 0 |  | 0 |  |  | 61586.1575 | 12123.2575 | 12123.25 | 12123.25
Oracle WebLogic Server Management Pack Enterprise Edition | 26 | 19217.22 |  | 19217.22 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 4710.105 | 4710.12 |  | 4710.12 | 0 | 0 |  | 0 | 4804.305 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4804.305 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4804.305 | 0 |  | 0 | 0 | 0 |  | 0 | 4804.305 | 0 |  | 0 |  |  | 23927.325 | 4710.105 | 4710.12 | 4710.12
Oracle WebLogic Suite | 26 | 72065.18 |  | 72065.18 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 17663.0316 | 17663.04 |  | 17663.04 | 0 | 0 |  | 0 | 18016.295 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 18016.295 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 18016.295 | 0 |  | 0 | 0 | 0 |  | 0 | 18016.295 | 0 |  | 0 |  |  | 89728.2116 | 17663.0316 | 17663.04 | 17663.04
PeopleSoft Enterprise Contracts | 92083 | 59347 |  | 59347 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 14545.8375 | 14545.83 |  | 14545.83 | 0 | 0 |  | 0 | 14836.7474 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14836.7474 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14836.7474 | 0 |  | 0 | 0 | 0 |  | 0 | 14836.7474 | 0 |  | 0 |  |  | 73892.8271 | 14545.8375 | 14545.83 | 14545.83
PeopleSoft Enterprise eSettlements | 92083 | 38946.69 |  | 38946.69 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 9545.76 | 9545.73 |  | 9545.73 | 0 | 0 |  | 0 | 9736.6728 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9736.6728 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9736.6728 | 0 |  | 0 | 0 | 0 |  | 0 | 9736.6728 | 0 |  | 0 |  |  | 48492.451 | 9545.76 | 9545.73 | 9545.73
PeopleSoft Enterprise Expenses | 92083 | 78819.28 |  | 78819.28 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 19318.45 | 19318.42 |  | 19318.42 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 |  |  | 98137.7354 | 19318.45 | 19318.42 | 19318.42
PeopleSoft Enterprise Financials | 92083 | 424696.86 |  | 424696.86 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 104092.3625 | 104092.34 |  | 104092.34 | 0 | 0 |  | 0 | 106174.2139 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 106174.2139 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 106174.2139 | 0 |  | 0 | 0 | 0 |  | 0 | 106174.2139 | 0 |  | 0 |  |  | 528789.2179 | 104092.3625 | 104092.34 | 104092.34
PeopleSoft Enterprise Grants | 92083 | 55636.88 |  | 55636.88 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 13636.49 | 13636.49 |  | 13636.49 | 0 | 0 |  | 0 | 13909.2215 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13909.2215 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13909.2215 | 0 |  | 0 | 0 | 0 |  | 0 | 13909.2215 | 0 |  | 0 |  |  | 69273.3758 | 13636.49 | 13636.49 | 13636.49
PeopleSoft Enterprise Human Resources | 114800 | 49875.07 |  | 49875.07 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 12224.2825 | 12224.29 |  | 12224.29 | 0 | 0 |  | 0 | 12468.7675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12468.7675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12468.7675 | 0 |  | 0 | 0 | 0 |  | 0 | 12468.7675 | 0 |  | 0 |  |  | 62099.3525 | 12224.2825 | 12224.29 | 12224.29
PeopleSoft Enterprise Payroll | 114800 | 60658.4 |  | 60658.4 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 14867.255 | 14867.24 |  | 14867.24 | 0 | 0 |  | 0 | 15164.6 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 15164.6 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 15164.6 | 0 |  | 0 | 0 | 0 |  | 0 | 15164.6 | 0 |  | 0 |  |  | 75525.655 | 14867.255 | 14867.24 | 14867.24
PeopleSoft Enterprise Project Costing | 92083 | 78819.28 |  | 78819.28 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 19318.45 | 19318.42 |  | 19318.42 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 |  |  | 98137.7354 | 19318.45 | 19318.42 | 19318.42
PeopleSoft Enterprise Purchasing | 92083 | 87165.48 |  | 87165.48 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 21364.09 | 21364.06 |  | 21364.06 | 0 | 0 |  | 0 | 21791.3694 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 21791.3694 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 21791.3694 | 0 |  | 0 | 0 | 0 |  | 0 | 21791.3694 | 0 |  | 0 |  |  | 108529.5678 | 21364.09 | 21364.06 | 21364.06
PeopleSoft Enterprise Supplier Contract Management | 92083 | 78819.28 |  | 78819.28 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 19318.45 | 19318.42 |  | 19318.42 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 |  |  | 98137.7354 | 19318.45 | 19318.42 | 19318.42
PeopleSoft Enterprise Treasury | 92083 | 63054.9826 |  | 63054.9826 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 15454.6525 | 15454.66 |  | 15454.66 | 0 | 0 |  | 0 | 15763.7442 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 15763.7442 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 15763.7442 | 0 |  | 0 | 0 | 0 |  | 0 | 15763.7442 | 0 |  | 0 |  |  | 78509.6293 | 15454.6525 | 15454.66 | 15454.66
PeopleSoft Enterprise Time and Labor | 0 | 0 |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Oracle Credits |  |  |  |  | Payment Terms | Contract Type | Disbursement Type | 0 | 0 | 0 | 0 | 0 | 0 | -21426.7 | 0 | -21426.7 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | -21426.7 | -21426.7
Oracle Credits |  |  |  |  | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 0 | -21426.7 |  | -21426.7 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | -21426.7 | -21426.7
Analytics |  | 304163.95 | 0 | 304163.95 | Payment Terms | Contract Type | Disbursement Type | 0 | 0 | 0 | 0 | 0 | 76040.9875 | 76041 | 0 | 76041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76040.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76040.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76040.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304163.95 | 76040.9875 | 76041 | 76041
HR Analytics (DW/BI) | 400 | 56637.43 | 0 | 56637.43 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 14159.3575 | 14159.36 |  | 14159.36 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14159.3575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14159.3575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14159.3575 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 56637.43 | 14159.3575 | 14159.36 | 14159.36
Financial Analytics (DW/BI) | 3000 | 231567.78 | 0 | 231567.78 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 57891.945 | 57891.95 |  | 57891.95 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 57891.945 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 57891.945 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 57891.945 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 231567.78 | 57891.945 | 57891.95 | 57891.95
Project Analytics (DW/BI) | 200 | 15958.74 | 0 | 15958.74 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 3989.685 | 3989.69 |  | 3989.69 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3989.685 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3989.685 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3989.685 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 15958.74 | 3989.685 | 3989.69 | 3989.69
OCI |  | 0 | 334031 | 334031 | Payment Terms | Contract Type | Disbursement Type | 27835.9167 | 28885.77 | 0 | 28885.77 | 1049.8533 | 27835.9167 | 27090.58 | 0 | 27090.58 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 0 | 0 | 335080.8533 | 56721.6867 | 55976.35 | 55976.35
OAC (DW/BI) - DEV: $53,219.00 - Test: $63,779.00 - DR: $94,238.00 - Production: $194,227.00 | 4 | 0 | 334031 | 334031 | Paid in Arrears | Fixed Fee | Encumbered | 27835.9167 | 28885.77 |  | 28885.77 | 1049.8533 | 27835.9167 | 27090.58 |  | 27090.58 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 |  |  | 335080.8533 | 56721.6867 | 55976.35 | 55976.35
New License Purchase and Tech Support |  | 0 |  | 0 | Payment Terms | Contract Type | Disbursement Type | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Financials | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Treasury | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Expenses | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise eSettlements | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Contracts | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Grants | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Project Costing | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Purchasing | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Human Resources | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Payroll | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Time and Labor | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 1746491.0626 | 334031 | 2080522.0626 |  |  |  | 27835.9167 | 28885.77 | #REF! | 28885.77 | 1049.8533 | 457413.2744 | 435241 | #REF! | 435241 | 27835.9167 | 0 | #REF! | 0 | 387151.7923 | 0 | #REF! | 0 | 105142.8067 | 0 | #REF! | 0 | 27835.9167 | 0 | #REF! | 0 | 387151.7923 | 0 | #REF! | 0 | 105142.8067 | 0 | #REF! | 0 | 27835.9167 | 0 | #REF! | 0 | 387151.7923 | 0 | #REF! | 0 | 105142.8067 | 0 | #REF! | 0 | 387151.7923 | 0 | #REF! | 0 | 0 | 0 | 2433842.3836 | 486299.0444 | 464126.77 | 464126.77
Projected FYTD | [7 empty] | 27835.9167 |  |  |  | 28885.77 | 486299.0444 |  |  |  | 514134.961 |  |  |  | 901286.7533 |  |  |  | 1006429.56 |  |  |  | 1034265.4767 |  |  |  | 1421417.269 |  |  |  | 1526560.0757 |  |  |  | 1554395.9923 |  |  |  | 1941547.7846 |  |  |  | 2046690.5913 |  |  |  | 2433842.3836
Incurred FYTD | [8 empty] | 28885.77 |  |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77
Paid FYTD | [10 empty] | 28885.77 |  |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77 |  |  |  | 464126.77
[14 empty] | 22172.2744 |  | 22172.2744 |  | 50008.191 |  | 0 |  | 437159.9833 |  | 437159.9833 |  | 542302.79 |  | 542302.79 |  | 570138.7067 |  | 570138.7067 |  | 957290.499 |  | 957290.499 |  | 1062433.3057 |  | 1062433.3057 |  | 1090269.2223 |  | 1090269.2223 |  | 1477421.0146 |  | 1477421.0146 |  | 1582563.8213 |  | 1582563.8213 |  | 1969715.6136 |  | 1969715.6136

## Florida PALM-UAT
Department of Financial Services
Florida PALM FY 2026 - 2027 PALM Readiness Detail FYTD
[7 empty] | July 2026 |  |  | Request Release Baseline Adjustment | August 2026 |  |  | September 2026 |  |  | October 2026 |  |  | November 2026 |  |  | December 2026 |  |  | January 2027 |  |  | February 2027 |  |  | March 2027 |  |  | April 2027 |  |  | May 2027 |  |  | June 2027 |  |  | CF 2026-27 |  | Total
Item Description | Rate | Quantity | Total Projected | Payment Terms | Contract Type | Disbursement Type | Projected | Incurred | Paid |  | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Incurred | Paid | Projected FYTD | Incurred FYTD | Paid FYTD
PALM Readiness Deliverables |  |  | 1210832.1 |  |  |  | 1210832.1 | 1062032.1 | 729854.7 | -148800 | 148800 | 148800 | 332177.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210832.1 | 1210832.1 | 1062032.1
UAT-QA D4 Report Providing Confirmation of Functional / Non-Functional Requirements and Agencies Ability to Comply with Financial Regulations |  |  | 729854.7 | Paid in Arrears | Fixed Fee | Encumbered | 729854.7 | 729854.7 | 729854.7 | 0 | [35 empty] | 729854.7 | 729854.7 | 729854.7
UAT-QA D5 Deployment of Streamline Testing Efforts and Regression Testing Automation |  |  | 332177.4 | Paid in Arrears | Fixed Fee | Encumbered | 332177.4 | 332177.4 |  | 0 |  |  | 332177.4 | [32 empty] | 332177.4 | 332177.4 | 332177.4
UAT-QA D6 Final Assessment Report |  |  | 148800 | Paid in Arrears | Fixed Fee | Encumbered | 148800 |  |  | -148800 | 148800 | 148800 | [33 empty] | 148800 | 148800 | 0
Total |  |  | 1210832.1 |  |  |  | 1210832.1 | 1062032.1 | 729854.7 | -148800 | 148800 | 148800 | 332177.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210832.1 | 1210832.1 | 1062032.1
Projected FYTD | [6 empty] | 1210832.1 |  |  | 1062032.1 | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1
Incurred FYTD | [7 empty] | 1062032.1 |  |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  | 1210832.1
Paid FYTD | [8 empty] | 729854.7 |  |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  | 1062032.1