## as of 10-15-24
ID | Title | Requester Name | Owner Name | Created | Due Date | Wave | Risk Score | Status | Risk Category | Probability | Trend | Impact Rating | Status Comment | Background | Mitigate or Monitor Plan and Resolution | Impact if Unmanaged
1 | The Project may have negative impacts if insufficient staffing occurs. | Jimmy Cox | Angie Robertson | 2023-04-26 14:05 | 2025-06-30 | Financials; Payroll | 3 | Monitoring | 2. Schedule; 3. Cost | 1 | Stable | 3 | 08/16/2024 - Updated Due Date | The Project may have negative impacts if insufficient staffing occurs. This would impact: 1. The ability to make time-critical and informed decisions 2. The ability to perform mission critical duties 3. Execute knowledge transfer to new resources | The Project will track the status of all positions to identify where possible, which positions will be coming vacant and when. The Project will use, at a minimum, the following resources and strategies to decrease the time needed to fill the vacancy and to bring the team member up to speed quickly: 1. Florida PALM Orientation and Onboarding materials and process 2. Standard Operating Procedures 3. Florida PALM Project Management Plan 4. Project Team member mentoring 5. Accenture Staffing Plan The Project will also: 1. Identify backups for decision making resources to be kept informed and be able to assist if a position is vacated unexpectedly or a replacement is not on-boarded timely 2. Hold regular staff meetings with the Team Managers, Project Architects and Project Directors to provide updates on Project progress, planning, and needs 3. Where possible, hire replacements to overlap current resources and allow for knowledge transfer 4. Keep the ESC and Executive sponsors informed of staffing issues as appropriate 5. Review the SSI contractor staffing plan regularly to ensure alignment with the planned activities or Schedule tasks | Schedule: Tasks may not be completed on or before the scheduled due date resulting in downstream delays in dependent tasks. This could ultimately delay the implementation of Florida PALM's next Major Implementation. Cost: A delay in completing work could delay critical path activities resulting in additional costs.
2 | External stakeholders (e.g., Legislature, EOG) and agencies expectations may not be aligned with the Florida PALM cost, schedule, or scope | Jimmy Cox | Jimmy Cox | 2023-04-26 14:08 | 2025-06-30 | Financials; Payroll | 6 | Monitoring | 1. Scope; 2. Schedule; 3. Cost | 2 | Increasing | 3 | 09/16/2024 - Probability Increased from 1 to 2, resulting in a change in the overall Risk Score from 3 to 6; Changed Trend to Increasing. | External stakeholders (e.g., Legislature, EOG) expectations may not be aligned with the Florida PALM cost, schedule, or scope which could result in impacts to funding and support of the Project, as well as agency’s ability to be ready for implementation. An example of potential misalignment relates to the scope of Data Warehouse/Business Intelligence (DW/BI) Solution. DW/BI was added to the project’s scope as part of Amendment 8 to provide self-service reporting for agencies and to replace the legacy FLAIR Information Warehouse (IW). Numerous agencies currently use large data extracts from the IW to seed their agency-specific data warehouses using an ODBC or similar connection to connect to the FLAIR IW and extract large sets of data into their Agency-Specific Data Warehouse. By design, the design and build phases for the DW/BI solution lag behind the implementation work for the Financials (FIN) and Human Capital Management (HCM) modules. This has caused a delay in being able to fully define the end point design for the DW/BI solution. Consequently, agencies have numerous questions and concerns regarding what specific data will be available and how they will be able to extract the data. This has led to agencies having to: 1.) select interface files they may not use; and 2.) making assumptions about what will/will not be available in the DW/BI solution. If agency assumptions turn out to be incorrect, there will likely be a direct impact on the agency’s ability to timely participate in interface testing, which could impact their ability to be ready for deployment in January 2026. | Project Directors will provide Project cost, schedule, and scope updates to external stakeholders regularly using the monthly Project status report, other required reports per Proviso, legislative meetings (e.g., committee meetings) and other ad hoc opportunities. The Project will: 1. Share information about business process models, interface designs and report design through the Knowledge Center as they are approved. 2. Share comprehensive details about the Solution (FIN/Payroll/DW) as it becomes available and is ready for distribution. 3. Hold Design Workshops (respectively) to support agencies understanding of the to be Solution (FIN/Payroll/DW). 4. Work with agencies as needed to educate agencies on available reports, queries, and interface files, and to support the agencies determinations on whether their agency critical business needs are met by these Solutions, or if additional agency specific Solutions are required. 5. Address agency questions during Readiness Touchpoints and as follow-ups to agency submitted questions. 6. Support agency evaluation of business system needs as they relate to data and reporting. | Scope: Legislative action could increase or decrease scope based on incorrect assumptions. Schedule: The tasks on the Project's critical path, including the go live date, could be impacted by additions of scope. Cost: Project funding may not be commensurate with the needs to meet the scope or timeline for implementation. Agencies may select incorrect interfaces due to timing of when information about the DW/BI Solution will be ready for sharing. This may result in unnecessary work preparing for interfaces that could be met through self-service in the Data Warehouse, etc. Conversely, agencies might incorrectly assume information is available through self-service in the DW/BI and fail to prepare adequately (e.g., select the appropriate interfaces).
3 | Budget related events may impact Project cost | Jimmy Cox | Jimmy Cox | 2023-04-26 14:12 | 2025-06-30 | Financials; Payroll | 3 | Monitoring | 2. Schedule; 3. Cost | 1 | Stable | 3 | 08/16/2024 - Updated Due Date | The Project budget may be affected by the following budget related events: 1. Deliverables not being accepted with sufficient time to be paid within the current fiscal year 2. Project LBR not being fully approved 3. Budget amendments not being fully or timely approved 4. The identification of unplanned expenditures | The Project will utilize one or more of the following strategies to manage the risk: 1. Use the weekly RADAR process to record schedule task progress and to identify potential delays 2. Work with task owners and coordinators for deliverables at risk of delay to keep deliverables on schedule 3. Notify Project Leadership as soon as potential delays are identified 4. Actively communicate budget needs 5. Submit clear budget related documentation, including the monthly spend plan, in a timely manner 6. Consider all available solutions to unplanned needs | Cost: The Project may not have sufficient funds available to pay for accepted deliverables or other incurred expenditures in a timely manner or at all. This could cost the State money due to the Project incurring interest on invoices or requiring a settlement agreement on unpaid expenditures. Schedule: Lack of funding or delays in paying for services could delay completion of implementation activities.
4 | Agencies’ ability to adequately engage and participate may impact agency readiness. | Jimmy Cox | Angie Robertson | 2023-04-26 14:17 | 2025-11-26 | Financials; Payroll | 6 | Mitigating | 2. Schedule; 3. Cost | 2 | Increasing | 3 | 08/16/2024 - Updated Due Date | Inadequate agency engagement and participation in readiness activities, not completing tasks in a timely manner, and not including knowledgeable staff in work efforts may impact an agency’s readiness to implement Florida PALM and contribute to a misunderstanding of the Florida PALM scope and implementation timeline. An agency’s ability to engage may be impacted by several factors, including inadequate funding or staffing (resources), lack of planning, or other unplanned events. | The Project will utilize one or more of the following mitigations to manage the risk: 1. Conduct monthly meetings between Readiness Coordinators and agency Change Champion Network members to discuss their internal readiness and preparation to transition to Florida PALM 2. Conduct meetings between Project leadership and agency sponsors to discuss the agency’s progress and any concerns, needs, or roadblocks that the agency is facing in their transition activities 3. Lead meetings and workshops designed to share timely and relevant information with agencies throughout the project lifecycle 4. Provide tools and information (e.g., graphics and content) to support messaging and communication within the agency regarding key implementation activities and change impacts 5. Review bimonthly agency status reports for indicators and trends relating to engagement difficulties | Schedule: Agencies may not be prepared to transition to Florida PALM resulting in a delay to launch. Cost: A delay in launch could extend the Project's lifecycle and require additional funding.
5 | The timing and efficiency of information sharing between enterprise partners and agencies, and the Project could impact the success of the Project | Jimmy Cox | Jimmy Cox | 2023-04-26 14:21 | 2025-06-30 | Financials; Payroll | 6 | Mitigating | 1. Scope; 2. Schedule | 2 | Increasing | 3 | 08/16/2024 - Updated Due Date | Untimely or ineffective information sharing between enterprise partners (e.g., MFMP, People First) and agencies, and the Project could negatively impact the success of the next major implementation. | The Project will leverage existing meetings and schedule additional as needed to discuss: 1. The Project's timeline and status identifying timing for key work to be completed 2. Projected changes to: a. enterprise systems and their potential impact on the Project b. the Project and its potential impact on enterprise systems 3. Progress of integration 4. The Project will look for potential connections between the applications and Florida PALM identified during design and development and their impacts to enterprise partners | Scope: Enterprise partners and agencies may identify needs outside of what was expected during implementation resulting in changes to requirements or unplanned customizations Schedule; Lack of necessary information may result in enterprise partners and agencies needing more time to address critical changes to their systems, and overall readiness to transition to Florida Palm, which may impact the implementation date for Florida PALM
6 | The execution of contracts and procurement activities outside of the Project may impact Florida PALM implementation and agency readiness | Angie Robertson | Angie Robertson | 2023-04-26 14:34 | 2025-06-30 | Financials; Payroll | 6 | Mitigating | 2. Schedule; 3. Cost | 2 | Increasing | 3 | 08/16/2024 - Updated Due Date; Changed Trend to Increasing | Agencies and enterprise partners are or may need to execute amendments to existing contracts or procure services from outside parties to support their readiness activities, including system remediation or internal business process redesigns / updates. Delays in executing those agreements or failure to secure the services could impact the system or agency readiness and the Project's ability to complete design, build, or testing activities. Delays could be due to lack of action, poor vendor response, or lack of budgetary authority. Preparation or readiness of enterprise systems, such as the vendor portal, PCard Works, or People First could have an even larger scale impact. | The Project will utilize one or more of the following strategies to manage the risk: 1. Provide the Project's timeline and key Project dates essential for agency and enterprise partner readiness (e.g., milestones) 2. Engage regularly with agency and enterprise partners to share information and to report progress towards key milestone dates 3. Request updates and status reporting on key readiness activities 4. Provide support or information to support agency, enterprise partner, or oversight body planning or decision making or needs 5. Continue regular meetings and develop mitigation actions should specific contracts not be executed and applications ready at Florida PALM Launch | Schedule: Agencies and enterprise partners may not be prepared to timely or thoroughly test their systems or processes with the Project, resulting in delays in confirming readiness. Cost: Unidentified or misidentified interface needs could result in Project Change Requests to add or change development items after approved design.
8 | Scope and timing of Build Segments may impact the Project’s ability to meet Stage Gate 3 and several Critical Path Items. | Jimmy Cox | Jimmy Cox | 2024-03-28 | 2025-03-28 | Financials; Payroll | 6 | Mitigating | 2. Schedule | 2 | Increasing | 3 | 08/16/2024 Removed Stage Gate 2 from Title; Updated Due Date; Changed Trend to Increasing; Updated Background and Impact if Unmanaged to include DW/BI. | The implementation of Florida PALM depends heavily on timely and accurate design, build, and test activities. The Project uses an overlapping approach for implementation to meet its aggressive implementation date. This approach allows build to begin on some activities while design is still occurring on other activities and system testing to begin while build is still ongoing. This approach facilitates work to be completed concurrently, shortening the time to implement. In addition to the Project Schedule, implementation progress is measured and reported around seven Stage Gates, each with specific criteria which must be met before the project completes or begins the next phase (e.g., Ready to Begin System Testing, Ready to Begin UAT). The Stage Gates are milestones throughout the Financials and Payroll Waves implementation that require contractual criteria be met and approval given by the Project Director or the Executive Steering Committee to move into the next leg of the implementation journey. For Financials and Payroll, Build Segment I (D646 – Completion of Build Segment I) included 52 build items and Build Segment II (D648 – Completion of Build Segment II) included 75 build items for a total of 127, or an average of 63.5 build items between these two segments. This leaves more than 230 build items to be completed during Build Segments III (D649 – Completion of Build Segment III) and IV (D654 – Completion of Build Segment IV). The addition of the Data Warehouse/Business Intelligence Solution as part of Amendment 8 to the Software and System Integrator (SSI) contract has increased the already high number of design and build elements. These DW/BI design and build activities run concurrently with Financials and Payroll Build Segments III and IV, and system testing. The timely completion of the Build segments is critical for the completion of System Testing. Financial and Payroll Build Segments III and IV are scheduled to be completed in October 2024 and January 2025, respectively, occurring during System Testing, and prior to the Stage Gate 3 – Ready to Begin UAT decision occurring in March 2025. DW/BI Build Segment I, II, and III are scheduled to be completed in October 2024, December 2024, and February 2025, respectively. These build activities overlap System Testing. Finally, adding to the risk of the extensive scope for Financials and Payroll Build Segments III and IV, and DW/BI Build Segments I, II, and II, is the timing of the numerous holidays (i.e., Veterans’ Day, Thanksgiving, Christmas and New Years) that fall during Financials and Payroll Build Segment IV and DW/BI Build Segments II and III which could also cause delays if a large percentage of the build documentation is provided for Project team review at the end of Financials and Payroll Build Segment IV, and DW/BI Build Segment II and III. | 1. Onboard additional application development staff to supplement the existing staff. 2. Hold daily build update meetings (i.e., 15-minute stand-ups) to discuss the current progress of build activities, including any delays. 3. Increase the involvement of ERP Support Services team members to speed up reviews of application development documentation. 4. Reduce the number of reviewers for each application development document. 5. Hold internal working meetings to identify additional dependencies and schedule tasks to assist with work planning and execution. | If there is a delay in completing build activities, this could result in a failure of the Project to meet one or more of the following critical path items or milestones. 1. System Test – D652 – Completion of Segment I in December 2024 2. System Test – D656 – Completion of Segment II in February 2025 3. System Test DW/BI – D661 – Completion in March 2025 4. Stage Gate 3 – Ready to begin UAT in March 2025 Failure to meet Stage Gate 3 or to timely start the related Deliverable activities will result in delays which may negatively impact the Projects ability to implement Florida PALM on schedule.
9 | Overlap of System Testing with the Start of User Acceptance Testing (UAT) may result in a delay of UAT and higher defects and issues | Jimmy Cox | Jimmy Cox | 2024-04-05 | 2025-11-26 | Financials; Payroll | 6 | Mitigating | 2. Schedule | 2 | Increasing | 6 | 08/16/2024 Updated Title; Updated Due Date; Changed Trend to Increasing; Updated Background and Mitigation. | The implementation of Florida PALM depends heavily on timely and accurate design, build, and test activities. The Project uses an overlapping approach for implementation to meet its aggressive implementation date. This approach allows build to begin on those items for which design have been completed; design to continue the incomplete items; system testing to begin on those items for which build is complete; while build continues on those items that are not yet complete. This approach facilitates work to be completed concurrently, shortening the time to implement. However, while these overlapping activities were envisioned from the start, the Project did not plan for an overlap of System Testing and UAT. In addition to the Project Schedule, implementation progress is measured and reported around seven Stage Gates, each with specific criteria which must be met before the Project completes or begins the next phase (e.g., Ready to Begin System Testing, Ready to Begin UAT). Stage Gates are milestones throughout the Financials and Payroll Waves implementation that require contractual criteria be met and approval be given by the Project Director or the Executive Steering Committee to move into the next leg of the implementation journey. With Deliverable 643 - Updated System Testing Plan, the SSI vendor has proposed to update the Project Schedule to include an overlap of the final system testing segment, System Testing Segment II, with UAT. In addition to this overlap, this also expands system testing to continue past the scheduled ESC vote for Stage Gate 3 – Ready to Begin UAT. While System Testing does not have to be completed prior to presenting the Stage Gate 3 – Ready to Begin UAT decision to the ESC for vote, system testing does have to be 90% complete. Additionally, work associated with the Data Warehouse and Business Intelligence (DW/BI) components of the Project was added as part of amendment 8 to the Software and System Integrator (SSI) contract, expanding Project scope increasing the effort and demands placed on System Testing. Overall, this overlap adds a high percentage of risk that: 1. System testing may need to be extended to meet the 90% completion requirement for Stage Gate 3 - Ready to Begin UAT either increasing the overlap with UAT or delaying the start of UAT. 2. UAT will not begin on time, reducing the time agencies must familiarize themselves with the new system, to remediate their business processes and prepare their end-users for Florida PALM implementation. 3. A higher volume of issues discovered during system testing will not be resolved by the start of UAT (compared to the original System Testing planned execution), which could impact the integrity of the UAT phase. 4. More defects (compared to the original System Testing planned execution) being identified during UAT, requiring additional remediation and retesting during UAT. 5. Knowledgeable SSI Vendor Staff will not be available to participate in UAT until System Testing is completed, or at a minimum will have a reduced participation in UAT support. 6. Testing with enterprise and integration partners may be delayed, which would directly impact their ability to be ready to implement on the current Florida PALM schedule. | 1. Hold daily update meetings (i.e., 15–30-minute stand-ups) to discuss the current progress of Project activities, including any delays. 2. Increase the number of SSI Vendor system testers (e.g., supplement with current production support staff) in order to complete system testing activities quicker. 3. Combine the State and SSI Vendor system testing resources to speed up the system testing timeline, instead of each group testing independently. 4. Monitor progress to determine if other mitigation approaches are needed. 5. Onboard additional state resources to support DW/BI activities. 6. Hold internal working meetings to identify additional dependencies and schedule tasks to assist with work planning and execution. | 1. Inability to meet Stage Gate 3 - Ready to Begin UAT in March 2025, resulting in a delay in starting UAT. If this occurs, then the UAT period will have to be reduced in order to meet the planned implementation date. Reducing the duration of UAT will likely impact state agencies’ business users, agency business systems, enterprise systems and third-party systems ability to be ready for implementation in January 2026. 2. Reduced quality of the UAT testing experience due to incomplete or inaccurate code, system configuration, etc., resulting in ineffective processes or results during UAT. If this occurs, UAT participants may obtain poor (inaccurate or lacking) results from their testing efforts, reducing their ability to be ready for transition to Florida PALM.