## as of 20250523
ID | Title | Requester Name | Owner Name | Created | Due Date | Wave | Risk Score | Status | Risk Category | Probability | Trend | Impact Rating | Status Comment | Background | Mitigate or Monitor Plan and Resolution | Impact if Unmanaged
1 | The Project may have negative impacts due to insufficient staffing or delays in onboarding. | Jimmy Cox | Angie Robertson | 2023-04-26 14:05 | 2025-06-30 | Financials; Payroll | 9 | Monitoring | 2. Schedule; 3. Cost | 3 | Increasing | 3 | 05/23/2025 - Updated Probability from 2 to 3; updated Risk Scores from 6 to 9; updated Background, Mitigation or Monitoring Plan and Resolution, and Impact if Unmanaged to provide additional information. | The Project may have negative impacts due to insufficient staffing or delays in onboarding. This would impact: 1. The ability to make time-critical and informed decisions 2. The ability to perform mission critical duties 3. Execute knowledge transfer to new resources The Project has several vacancies in key roles, which have been difficult to fill with qualified candidates. As go live approaches, and testing activities ramp up, turnover and vacancies create additional risk of missed deadlines. | The Project will track the status of all positions to identify where possible, which positions will be coming vacant and when. The Project will use, at a minimum, the following resources and strategies to decrease the time needed to fill the vacancy, onboard the new team member, and to bring the team member up to speed quickly: 1. Florida PALM Orientation and Onboarding materials and process 2. Standard Operating Procedures 3. Florida PALM Project Management Plan 4. Project Team member mentoring 5. Accenture Staffing Plan 6. Onboarding Checklist The Project will also: 1. Identify backups for decision making resources to be kept informed and be able to assist if a position is vacated unexpectedly or a replacement is not on-boarded timely 2. Hold regular staff meetings with the Team Managers, Project Architects and Project Directors to provide updates on Project progress, planning, and needs 3. Where possible, hire replacements to overlap current resources and allow for knowledge transfer 4. Keep the ESC and Executive sponsors informed of staffing issues as appropriate 5. Review the SSI contractor staffing plan regularly to ensure alignment with the planned activities or Schedule tasks 6. Partner with other DFS Divisions and Bureaus to enhance awareness and understanding of the needs of the Project with regard to personnel and technology resources 7. Leverage staff augmentation resources, where possible, to perform planned activities 8. Transition resources from other Project activities when those activities have been completed and the resources become available | Schedule: Gaps in staffing could result in delayed completion of work related to building, testing, training or cutting over/deploying, which could result in a greater compression for Project activities. Compounded or significant delays could impact the Florida PALM’s go-live date. Cost: The Project could incur additional costs due to rework or the cost of securing additional resources.
2 | External stakeholders (e.g., Legislature, EOG) and agencies expectations may not be aligned with the Florida PALM cost, schedule, or scope | Jimmy Cox | Jimmy Cox | 2023-04-26 14:08 | 2025-06-30 | Financials; Payroll | 6 | Monitoring | 1. Scope; 2. Schedule; 3. Cost | 2 | Increasing | 3 | 05/23/2025 - Changed Status from Mitigating to Monitoring. | External stakeholders (e.g., Legislature, EOG) expectations may not be aligned with the Florida PALM cost, schedule, or scope which could result in impacts to funding and support of the Project, as well as agency’s ability to be ready for implementation. An example of potential misalignment relates to the scope of Data Warehouse/Business Intelligence (DW/BI) Solution. DW/BI was added to the project’s scope as part of Amendment 8 to provide self-service reporting for agencies and to replace the legacy FLAIR Information Warehouse (IW). Numerous agencies currently use large data extracts from the IW to seed their agency-specific data warehouses using an ODBC or similar connection to connect to the FLAIR IW and extract large sets of data into their Agency-Specific Data Warehouse. By design, the design and build phases for the DW/BI solution lag behind the implementation work for the Financials (FIN) and Human Capital Management (HCM) modules. This has caused a delay in being able to fully define the end point design for the DW/BI solution. Consequently, agencies have numerous questions and concerns regarding what specific data will be available and how they will be able to extract the data. This has led to agencies having to: 1.) select interface files they may not use; and 2.) making assumptions about what will/will not be available in the DW/BI solution. If agency assumptions turn out to be incorrect, there will likely be a direct impact on the agency’s ability to timely participate in interface testing, which could impact their ability to be ready for deployment in July 2026. | Project Directors will provide Project cost, schedule, and scope updates to external stakeholders regularly using the monthly Project status report, other required reports per Proviso, legislative meetings (e.g., committee meetings) and other ad hoc opportunities. The Project will: 1. Share information about business process models, interface designs and report designs through the Knowledge Center as they are approved. 2. Share comprehensive details about the Solution (FIN/Payroll/DW) as it becomes available and is ready for distribution. 3.Share information through activities, such as Advisory Council meetings and Sponsor Summits, and through written materials, such as Newsletter, Sponsor Scoops, and articles in the Knowledge Center. 4. Work with agencies as needed to educate agencies on available reports, queries, and interface files, and to support the agencies determinations on whether their agency critical business needs are met by these Solutions, or if additional agency specific Solutions are required. 5. Address agency questions during Readiness Touchpoints and as follow-ups to agency submitted questions, including publishing questions to the public view of the Question Log on Florida PALM website. 6. Support agency evaluation of business system needs as they relate to data and reporting. | Scope: Legislative action could increase or decrease scope based on incorrect assumptions. Schedule: The tasks on the Project's critical path, including the go live date, could be impacted by additions of scope. Cost: Project funding may not be commensurate with the needs to meet the scope or timeline for implementation. Agencies may select incorrect interfaces due to timing of when information about the DW/BI Solution will be ready for sharing. This may result in unnecessary work preparing for interfaces that could be met through self-service in the Data Warehouse, etc. Conversely, agencies might incorrectly assume information is available through self-service in the DW/BI and fail to prepare adequately (e.g., select the appropriate interfaces).
3 | Budget related events may impact Project cost | Jimmy Cox | Jimmy Cox | 2023-04-26 14:12 | 2025-06-30 | Financials; Payroll | 6 | Mitigating | 2. Schedule; 3. Cost | 2 | Increasing | 3 | 05/23/2025 - Updated Probability from 1 to 2; updated Risk Score from 3 to 6; updated Trend from Stable to Increasing; updated Background and Mitigation or Monitoring Plan and Resolution for additional information. | The Project budget may be affected by the following budget related events: 1. Deliverables not being accepted with sufficient time to be paid within the current fiscal year 2. Project LBR not being fully or timely approved 3. Budget amendments not being fully or timely approved 4. The identification of unplanned expenditures | The Project will utilize one or more of the following strategies to manage the risk: 1. Use the weekly RADAR process to record schedule task progress and to identify potential delays 2. Work with task owners and coordinators for deliverables at risk of delay to keep deliverables on schedule 3. Notify Project Leadership as soon as potential delays are identified 4. Actively communicate budget needs internally and externally 5. Submit clear budget related documentation, including the monthly spend plan, as early as practicable 6. Utilize Carry Forward funding for invoices which could otherwise be delayed due to a delay in approval of the next fiscal year’s budget | Cost: The Project may not have sufficient funds available to pay for accepted deliverables or other incurred expenditures in a timely manner or at all. This could cost the State money due to the Project incurring interest on invoices or requiring a settlement agreement on unpaid expenditures. Schedule: Lack of funding or delays in paying for services could delay completion of implementation activities.
4 | Agencies’ ability to adequately engage and participate may impact agency readiness. | Jimmy Cox | Angie Robertson | 2023-04-26 14:17 | 2026-01-30 | Financials; Payroll | 9 | Mitigating | 2. Schedule; 3. Cost | 3 | Increasing | 3 | 03/27/2025 - Updated Due Date to align with SG4; updated Background to include references to Amendment 12 and the new Stage Gate decision date; updated Impact if Unmanaged for Schedule impacts. | Inadequate agency engagement and participation in readiness activities, not completing tasks in a timely manner, not including knowledgeable staff in work efforts, and insufficient planning for transition may impact an agency’s readiness to implement Florida PALM and contribute to a misunderstanding of the Florida PALM scope and implementation timeline. An agency’s ability to engage may be impacted by several factors, including inadequate funding or staffing (resources), lack of planning, or other unplanned events. As more Readiness Workplan Tasks are released with a Direct Impact on the Project, the criticality of timely completion increases and compounds the probability agencies may fall behind, without adequate planning and resource engagement. In Amendment 12, a new Stage Gate (SG4) Continue Deployment was added for the Executive Steering Committee to decide whether to continue deployment activities for a July 2026 go live or to defer the go live date to January 2027. That decision will be based on a State readiness evaluation on the status of interface testing, agency UAT and enterprise system readiness and must be made no later than January 30, 2026. | The Project will utilize one or more of the following mitigations to manage the risk: 1. Conduct monthly meetings between Readiness Coordinators and agency Change Champion Network members to discuss their internal readiness and preparation to transition to Florida PALM 2. Conduct meetings between Project leadership and agency sponsors to discuss the agency’s progress and any concerns, needs, or roadblocks that the agency is facing in their transition activities 3. Lead meetings and workshops designed to share timely and relevant information with agencies throughout the project lifecycle 4. Provide tools and information (e.g., graphics and content) to support messaging and communication within the agency regarding key implementation activities and change impacts 5. Review bimonthly agency status reports for indicators and trends relating to engagement difficulties | Schedule: Agencies may not be prepared to transition to Florida PALM resulting in a delay to launch or in a decision in Stage Gate 4 to change the go live date to January 2027. Cost: A delay in launch could extend the Project's lifecycle and require additional funding.
5 | The timing and efficiency of information sharing between enterprise partners and agencies, and the Project could impact the success of the Project | Jimmy Cox | Jimmy Cox | 2023-04-26 14:21 | 2025-06-30 | Financials; Payroll | 9 | Mitigating | 1. Scope; 2. Schedule | 3 | Increasing | 3 | 02/12/2025 - Updated Probability from 2 to 3; updated Risk Score from 6 to 9. | Untimely or ineffective information sharing between enterprise partners (e.g., MFMP, People First) and agencies, and the Project could negatively impact the success of the next major implementation. | The Project will leverage existing meetings and schedule additional as needed to discuss: 1. The Project's timeline and status identifying timing for key work to be completed 2. Projected changes to: a. enterprise systems and their potential impact on the Project b. the Project and its potential impact on enterprise systems. 3. Progress of integration 4. The Project will look for potential connections between the applications and Florida PALM identified during design and development and their impacts to enterprise partners. | Scope: Enterprise partners and agencies may identify needs outside of what was expected during implementation resulting in changes to requirements or unplanned customizations Schedule: Lack of necessary information may result in enterprise partners and agencies needing more time to address critical changes to their systems, and overall readiness to transition to Florida Palm, which may impact the implementation date for Florida PALM
6 | The execution of contracts and procurement activities outside of the Project may impact Florida PALM implementation and agency readiness | Angie Robertson | Angie Robertson | 2023-04-26 14:34 | 2025-06-30 | Financials; Payroll | 6 | Monitoring | 2. Schedule; 3. Cost | 2 | Increasing | 3 | 05/23/2025 - Updated Probability from 3 to 2; updated Risk Score from 9 to 6. | Agencies and enterprise partners are or may need to execute amendments to existing contracts or procure services from outside parties to support their readiness activities, including system remediation or internal business process redesigns / updates. Delays in executing those agreements or failure to secure the services could impact the system or agency readiness and the Project's ability to complete design, build, or testing activities. Delays could be due to lack of action, poor vendor response, or lack of budgetary authority. Preparation or readiness of enterprise systems, such as the vendor portal, PCard Works, or People First could have an even larger scale impact. As the Project approaches Interface Testing - Cycle 2, pertinent contracts have been executed, therefore, the approach to this risk has been updated to Monitoring. While the approach has changed, the overall Risk Score remains unchanged, due to the criticality of the external partners in testing efforts. | The Project will utilize one or more of the following strategies to manage the risk: 1. Provide the Project's timeline and key Project dates essential for agency and enterprise partner readiness (e.g., milestones). 2. Engage regularly with agency and enterprise partners to share information and to report progress towards key milestone dates. 3. Request updates and status reporting on key readiness activities. 4. Provide support or information to support agency, enterprise partner, or oversight body planning or decision making or needs. 5. Continue regular meetings and develop mitigation actions should specific contracts not be executed and applications ready at Florida PALM Launch. | Schedule: Agencies and enterprise partners may not be prepared to timely or thoroughly test their systems or processes with the Project, resulting in delays in confirming readiness. Cost: Unidentified or misidentified interface needs could result in Project Change Requests to add or change development items after approved design.