## Sheet1
Estimation Tool for Activity and Small Project
Assumptions
Item Identifier | Deliverable Short Description | Estimated days to do work if fully dedicated | Average Allocation % (100, 50, 33, 25) | With Allocation & Noise | Deliverable Requires Review and Approval? (Y,N) | Net Effect | Risk | Estimated days to do work is work effort only, excluding allocation, productivity, risk, noise, research, planning, consultation, sick leave, personal leave and holidays and fully dedicated
|  |  | 100 | 0 | N | 0 | 0 | For allocation, enter the allocation of the key resource for deliverable
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0 | Risk is 50%
|  |  | 100 | 0 | N | 0 | 0 | Noise is 5%
|  |  | 100 | 0 | N | 0 | 0 | Review and Approval requires 3 days plus 10% rework
|  |  | 100 | 0 | N | 0 | 0 | One iteration for review, modify and approve process
|  |  | 100 | 0 | N | 0 | 0 | Each month has loss of 3 days due to sick, personal leave, holidays
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0 | Workweek is 5 days
|  |  | 100 | 0 | N | 0 | 0 | Day is 8 hours
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0 | Legend
|  |  | 100 | 0 | N | 0 | 0 |  | Calculated fields
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0 | Additional loss in days enter any forceable days of loss beyond what is included in the assumptions above.
|  |  | 100 | 0 | N | 0 | 0 | Enter explanation for additional loss in days
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0
|  |  | 100 | 0 | N | 0 | 0
[5 empty] | Duration Days | 0 | 0
[5 empty] | Additional Loss in Days | 0 | 0
[5 empty] | Elapsed Time in months | 0 | 0